| Meeting Purpose: | Palika Level Coordination Meeting |
| --- | --- |
| Meeting Date: | 180307 |
| Meeting Time: | 12:15 PM |
| Meeting Location: | Kalika RM ,Rasuwa |
| Meeting Facilitator: | Rijan Gajurel |
| Minutes Taken By: | Rijan Gajurel |

Discussion: (Items/Knowledge Shared)

Agenda’s Welcome and Introduction - HRRP Palika level coordination meeting was chaired by Kalika Rural Municipality chairperson Mrs. Sita Kumari Poudel Adhikari,program facilitator was Mr.Rijan Gajurel. Vice-Chairperson Mr. Bhawani Prasad Neupane, Chief Administrative Officer Mr. Mohan Shrestha and Ward Chaipersons of all wards at Palika Level and Mr Prabhu Pokharal were present in meeting .HRRP welcomed all the participants in the meeting and thanked for their support in coordination and also requested to raise any types of issues related to reconstruction through this platform in the coming days and all participants introduced themselves from their respective places. Reconstruction Update –HRRP District focal person of HRRP Mr.Rijan Gajurel Update the reconstruction status of district to all participant .As of 06,March ,2018 the enrollment /Tranche distribution matrix as per new structure : Data Source :EHRP Rasuwa(as of 6-Mar ,2018) SN; Rural Municipality; Eligible HH; First tranche Received HHs; second Tranche Received HHs; Third Tranche Received HHs. 1; Gosaikunda RM; 1772; 1599; 1004; 292. 2; Naukunda RM; 3228; 2924; 1077; 493. 3; Aamo Chhodingmo RM; 1779; 1619; 1000; 281. 4; Kalika RM; 2342; 2222; 1566; 676. 5; Uttargaya RM; 2508; 2145; 1269; 641. Total; 11,629; 10,509; 5916; 2383. HRRP brief about the social and technical assistance based on the NRA’s six minimum technical assistance package and highlighted on the gaps and duplication as per new structure. Graphs on technical assistance were shown and gaps were discussed in the terms of NRA’s minimum technical assistance package. HRRP also update the status of mason training (7days and 50 days) in district as well as in Kalika RM. - Reconstruction status impressive -90% targeted to receive 2nd tranches within deadline. 80% targeted to receive 3rd tranches within deadline. - Chairperson has suggested ward chief and members as well as NRA technical person for individual HHs visits and orientations for those who have not started construction yet. - Further suggestions regarding orientations and technical aspects for correction /retrofitting of non-compliance houses led for joint team visit of reconstruction Er/SE/ASE and ward chiefs. - IEC materials/awareness activities by POs mainly Lumanti was properly conducted. Technical Person : Some of the key issues raised during meeting and interactions are : - Collection of information about number of houses constructed, 2nd and 3rd tranches status and HHs who have not started construction yet going on. Study about old, single women headed, physically disabled HHs going on who have not constructed houses is also in progress. - Frequent interaction with beneficiaries done during programs of other POs like NAF. Local Body Representatives - Meeting with ward chief of wards 2,3,5 Bikram Neupane, Pushpa Raj Neupane and Ram Hari Devkota respectively. - Ward has system of house registration before layout of foundation then NRA technical person were deployed in the field from that information for technical assistance. - Ward Chiefs are fully satisfied with the role of technical person . Partners Presence : - Lumanti /Coardaid provide cash grant support and technical support for 381 HHs at Dhabung and Laharapauwa..They already completed project. - Lumanti ,NRA , DLPIU ,NRCS conducted 7 days mason training on this rural municipality. - Helvetas and TCN Nepal conducted 50 days OJT training also constructed Demo house during 50 days training . Challenges : - One of the biggest challenges is that people are adding floors on one storey load bearing houses after receiving 3rd tranche. Some of them are adding verandahs, extending rooms vulnerably. Few photos of such HHs are figured below. As significant number of houses has received 3rd tranches here the trend of floor addition and extension after receiving 3rd tranches has reminded us of another challenge that reconstruction is going to face. - Skilled as well as unskilled manpower are insufficient.

Miscellaneous Items / AOB:

Decisions Made: (What, Why, Impacts)

Extension of buildings violating MRs after receiving 3rd tranches. Need Orientation for HHs from Palika and NRA technical person.Also, System of punishing those who have violated MR and extended buildings after receiving 3rd tranche .

| Next Steps: (Task, Assigned to, Checkpoint Date) | Person(s) Responsible | Due Date |
| --- | --- | --- |
| Provide construction tools and Tablet for technical person | Prabhu Pokharal | ASAP |

| Attendees | Organisation | Phone No. | Email |
| --- | --- | --- | --- |
| Sita Poudel Adhikari | Kalika RM | 9841705405 |  |
| Mr. Bhawani Prasad Neupane | Kalika RM |  |  |
| Mr. Mohan Shrestha | Kalika RM |  |  |
| Bikram Neupane | Kalika ward 2 |  |  |
| Rijan Gajurel | HRRP | 9851114937 | im.rasuwa@hrrpnepal.org |
| Prabhu Pokheral | CLPIU | 9851224243 |  |
| Prakash Poudel | DLPIU | 9851203410 |  |
| Sandesh Pun Magar | DLPIU | 9848275959 |  |
| Bikash Shah | DLPIU | 9848175479 |  |
| Gauri Shankar Mandal | DLPIU | 9869128952 |  |
| Ajay Awasthi | DLPIU |  |  |
| Binay Krishna KC | DLPIU |  |  |
| Keshab Raj Pandey | DLPIU | 9848156683 |  |
| Navaraj BK | DLPIU | 9848310287 |  |
| Krishna Kumar Samal | DLPIU |  |  |
| Ram Hari Lamichhane | DLPIU |  |  |
| Nabin Bhandary | DLPIU |  |  |