| Program/Area: | HRRP District Coordination meeting |
| --- | --- |
| Meeting Purpose: | To increase coordination in the housing reconstruction and recovery sector of Makwanpur |
| Meeting Date: | 31/003/2017 |
| Meeting Time: | 8.00-11.00 AM |
| Meeting Location: | Plan International Nepal, Hetauda Field Office Meeting hall |
| Meeting Facilitator: | Mr Puspa Raj Adhikari, Chief of NRA, Makwanpur |
| Minutes Taken By: | Ram Hari Adhikari |

| Attendees | Organization/Affiliation | Contact Detail |
| --- | --- | --- |
| Bibek Gautam | MOFALD Makwanpur, M&E Specialist | vibek.gautam@gmail.com, 9801033456 |
| Puspa Raj Adhikari | NRA Makwanpur, Chief | 9841868897 |
| Netra Prasad Upadhyaya | Plan International Nepal, Program Unit Manager, | 9801067231 |
| Bitu Babu Shribastav | DCA, Consortium Manager, | bbsh@dca.org, 9852023033 |
| Suk Bahadur Chaudhari | Helvetas, Cluster Coordinator | suk.chaudhari@helvetas.org, 9847830069 |
| Dr Soniya Bhagat | WHO-ERM, WEDS Officer | drsoniyabhagat@gmail.com, 9801123150 |
| Ganesh Khatiwada | H4 Life, PC | gkhatiwada@rti.org, 9851210281 |
| Sagar Shrestha | MDI Nepal, PC | Shrestha.sagar6@gmail.com, 9845149231 |
| Deuta Rijal | SABAL, DM &CCAO | dewta.rijal@care.org , 9845427899 |
| Bishnu Dhital | RADO, IMO | dhitalbishnu2072@gmail.com, 845029712 |
| Rabin Bhandari | RRN, DC | rabinb@rrn.org.np, 9841319434 |
| Mukti Ghimire | NRCS, Field Coordinator | mukti.ghimire8@gmail.com, 9841289577 |
| Tri Ratna Manandhar | Lumanti, DC | triratna@lumanti.org.np, 9841453892 |
| Ram Hari Adhikari | HRRP, DC | dc.makwanpur@hrrpnepal.org |
| Poshak Bhandari | RWDC/Care Nepal | 'poshak.bhandari@gmail.com', 9845057283 |
| Bijaya Dhakal | NRCS-ERO< shelter officer | bijay8wrc@gmail.com, 9843314810 |
| Bijaya Koirala | Helvetas, Civil Engineer | Bijaya.koirala@helvetas.org, 9841914213 |

Discussion: (Items/Knowledge Shared)

Agendas and discussion of the meeting - Updates from NRA - Puspa Adhikari, NRA Head of Makwanpur - Weekly update and detail of HRRP 3-Ram Hari Adhikari - New federal structure in Makwanpur and its role in terms of reconstruction and recovery - Bibek Gautam, MOFALD - Election code of ethics and our role during election period :- Puspa Adhikari ( Briefing of the instruction by Election Commission and MOHA) and Bitu Shribastav ( on behalf of AIN) - Information management and 4 W updates:- Ram Hari - The present issues and progress of the partners:- Participants PARKING LOT: The reconstruction and recovery works in the new federal structure and how the existing bodies functionalize in the changed structure

Miscellaneous Items / AOB:

- DRR in Health sector in the district agenda by Ganesh Khatiwada, H4Life - DPRP update:- Deuta Rijal, SABAL - Project approval of Lumanti - The structure and role of LDMC, VWASHCC, WWASHCC and WCF in the changed federal structure - Monthly actin plan - Technical support in the field - Presentation by HELVETAS/ Employment Fund on vocation trainning

Decisions Made: (What, Why, Impacts)

- All the partner organizations present in the meeting made their commitment to provide support to NRA for reconstruction and recovery. NRA district secretariat will coordinate and support the 1. 1. POs to work together in the district. It will enable the POs to work in the reconstruction and recovery more effectively and efficiently. - All POs will be updated on what is going on in the reconstruction and recovery, in the district and what is being instructed from the NRA on the basis of the weekly updated from the HRRP central to the HRRP district teams. The updates will be discriminated and updates will be sent to the POs frequently by HRRP district teams. - NRA district secretariat and MOFALD district team will keep updating about the new federal structure and the role of new municipalities as clear instructions on this has not come to them from the. Government yet. All the POs will have to follow the instructions from the government in terms of new structure. - All the partners decided to follow the security instructions from the MOHA and AIN. They will be stopping the community programs and be involved in in office activities just before the election if they are instructed to do the same. - Discussion on Information management and 4 W update concluded in deciding to send 4 W updates again to HRRP and HRRP will be sending the required report to NRA district chapter and MOFALD regularly. MOFALD and NRA team can contact the POs directly if required as well. 5 W will be sent after it is launched after a few months. - NRA district chapter head Puspa Adhikari requested all POs to convey their problems and issues they are facing to him any time and promised to solve or transfer it to senior officials if he cannot solve them. It was decided that all decisions made in the meetings will be shared with the CDO immediately after each meeting and he will be invited in some of the next HRRP meetings as well as per requirement. - Miscellaneous:- 7.1 The three issues regarding DRR in Health sector in the district, DPRP update and project approval of Lumanti will be put as an agenda of the DDRC meeting on the 2nd of March and all the members of DDRC will be requested to respond on this. 7.2 NRA district chief Mr Puspa Adhikari will describe about the'' 7.3 New structure and role of LDMC, VWASHCC, WWASHCC and WCF in the changed federal structure'' in the next meeting after having consultation with the line ministries. 7.3 It was decided that the NRA district head, MOFALD team and HRRP will sit together and make a joint monthly action plan and coordination among them will be made much stronger. 7.4. The technical coordinator that is going to be recruited by HRRP in Makwanpur inputs and work closely with POs will be providing technical. Technical workshops and meetings will be organized in the various parts of the district as per need. 7.5 In the last of the meeting, Mr. Suk Bahadur Chaudhary of Helvetas district team of Makwanpur demonstrated how their vocational training can be monitored by using its online application by logging on www.Employmentfind.org.np/epmsdfid . The team further told that the training and demonstration house construction activities can be monitored very easily by logging and every can use by logging as a guest.

| Next Steps: (Task, Assigned to, Checkpoint Date) | Owner | Due Date |
| --- | --- | --- |
| Submit 4 W regularly. |  | 7th and 22nd of each month |
| Make joint action plan with MOFALD and NRA in the district jointly. | . | By the end of first week of each month |