## Slide 1: Responsive and Adoptive Shelter for Earthquake Affected Communities – RASEAC e'sDk lkl8t ;d'bfosf] nflu pTt/bfoL tyf cg's'n cfjf; sfo{qmd Working VDCs- Yarsa & Ramche
Supporting Organizations
Disaster Emergency Committee
Islamic Relief Worldwide
The Lutheran World Federation Nepal
Implementing Organization
BATAS Foundation

## Slide 2: Program Activities:
WASH/DRR
Livelihood
Shelter

## Slide 3: Program Activities
3. Shelter
Training to Masons on Earthquake Resilient House Construction (2 events; 60 Beneficiaries; Ramche & Yarsa)- Completed
Training on ICS for Smoke Free Houses (1 event; 40 Beneficiaries- Ramche) Completed
Community Orientation and Awareness- On Progress

## Slide 4: Shelter…………….. Contd.
Support for Construction of Earthquake
Resilient Permanent Houses (Target 151 HHs)
Awareness Raising to community
Support to construct in any design of Buildings approved by DUDBC/GOs.)
Technical & quality Construction Material support (equivalent to government support fund + Transportation)
Tri-Parties Agreement for 151 Permanent Shelters Construction- Completed

## Slide 5: Shelter…………….. Contd.
Construction activities started in 139 HHs
  Site Clearance: 18
  E/W Excavation: 6
  Vertical Rod Erection: 6
  DPC Completed: 20
  Sill Band Completed: 21
  Stitch Band Completed: 16
  Lintel Completed: 52
  Toilet under construction: 20 HHs

## Slide 6: Documentation
Tri-Parties (Beneficiary, LWF Nepal &
BATAS Foundation) Agreement.
Beneficiary Card (Yellow Card) includes Beneficiary details & materials received by communities from Project Support.
Monitoring Template for House & Toilet Construction- Stepwise Verification from BATAS Foundation Technical Team/ Cross-check/verification by LWF PM/Technical Team
Daily Progress report/Measurement Book- BATAS Technical Official

## Slide 7: Documentation……………. Contd.
Daily Attendance Card for Labor involved
in Shelter Construction
Material Quality Report- MQR- Prepared by Technical Team after material inspection.
Goods Receiving Note- GRN: According to MQR.
Stock Book Entry- Daily Updated
Stock Release/Chalan

## Slide 8: Materials Support/Supply
Bricks
Sand
Aggregate
Reinforcement Bar
Cement
Truss
CGI Sheet & Plain Sheet
Shovel, Axe Peak, Layout Thread, Measuring Tape, Tagari, etc.
Toilet Construction materials- equivalent to 10,000
And other Masonry equipments

## Slide 9: Shelter Construction Support Modality
Agreement: any DUDBC/GOs approved Models
Clusters identification: 4 major working clusters identified.
Working Committee: 1 (or more) formed in each Cluster.
Material delivery: upto beneficiaries nearest road access
Technical Support: Minimum one BATAS Technical official in each cluster at every crucial stage of shelter construction- facilitated by one SM.

## Slide 10: Shelter Construction Support Modality…………………contd.
Skilled Mason: minimum 2 Trained/skilled mason present in each HHs during shelter construction
Earthquake Resilient Verification: Stage-wise verification of Shelter Construction (Foundation, Plinth Band, Sill Band, Stitching Band, Lintel Band, etc.) by TO
Field Level Monitoring: frequently by BATAS FC and LWF PM/Engineer- jointly/individually.
Joint/official monitoring from district/center.
Provision of Complain Box at Office premises.

## Slide 11: Community participation in site clearance
During Site Clearance (Dismantling existing Old House)

## Slide 12
70 Years old Couples actively involved in site clearance (Earthquake damaged building)

## Slide 13
Vertical Rod Erection in Foundation

## Slide 14
Bar Bending Work at Plinth Level

## Slide 15
Casting of Plinth Band (DPC)

## Slide 16
Compacting & Stone Soling in Floor

## Slide 17
Plain Cement Concrete Work at Floor Level

## Slide 18
Skilled Mason Ensuring Constructed Wall by Plumbob

## Slide 19: Sill Band

## Slide 20
Laying of Window

## Slide 21: The House Reached At Stitch Band Stage
At Stitch Band Stage Monitored By NRA Chief of Rasuwa District

## Slide 22: Formwork For lintel Band
Formwork And shuttering Work for lintel Band

## Slide 23: Houses ready for Roofing

## Slide 24: Ready For Roofing After paster
Houses With internal Plaster Competed

## Slide 25
Construction Materials

## Slide 26: Joint monitoring visit from Government Stakeholders (CDO, LDO, DSP, Program Officer, Monitoring Officer, VDC Secreteriat, etc.)

## Slide 27
Inspection of construction material quality and quantity by BATAS Foundation Technical Officials

## Slide 28: Shelter…………….. Contd.
Challenges :
Access of Road (Earthen, Heavy Boulders throughout alignment)
Geology and Topography of Land (Difficulty on site clearance & Earthwork excavation)
Scarcity of Skilled/Unskilled Labor

## Slide 29
Thanks