| Meeting Purpose: | Palika Level Coordination Meeting |
| --- | --- |
| Meeting Date: | 180306 |
| Meeting Time: | 12:15 PM |
| Meeting Location: | Naukunda RM,Parchang Rasuwa |
| Meeting Facilitator: | Rijan Gajurel |
| Minutes Taken By: | Rijan Gajurel |

Discussion: (Items/Knowledge Shared)

Agenda’s Welcome and Introduction HRRP Palika level coordination meeting was chaired by Naukunda Rural Municipality Technical persion Mr. Arun kumar sharma and the program facilitator was Mr.Rijan Gajurel.HRRP welcomed all the participants in the meeting and thanked for their support in coordination and also requested to raise any types of issues related to reconstruction through this platform in the coming days and all participants introduced themselves from their respective places. Reconstruction Update –HRRP District focal person of HRRP Mr.Rijan Gajurel Update the reconstruction status of district to all participant .As of 06,March ,2018 the enrollment /Tranche distribution matrix as per new structure : Data Source :EHRP Rasuwa(as of 06-March,2018) SN; Rural Municipality; Eligible HH; First tranche Received HHs; second Tranche Received HHs; Third Tranche Received HHs. 1; Gosaikunda RM; 1772; 1599; 1004; 292. 2; Naukunda RM; 3228; 2924; 1077; 493. 3; Parbatikunda RM; 1779; 1619; 1000; 281. 4; Kalika RM; 2342; 2222; 1566; 676. 5; Uttargaya RM; 2508; 2145; 1269; 641. Total; 11,629; 10,509; 5916; 2383. HRRP brief about the social and technical assistance based on the NRA’s six minimum technical assistance package and highlighted on the gaps and duplication as per new structure. Graphs on technical assistance were shown and gaps were discussed in the terms of NRA’s minimum technical assistance package. HRRP also update the status of mason training (7days and 50 days) in district as well as in Parbatikunda RM. Technical Person : Some of the key issues raised during meeting and interactions are : - They are mobilized well and present in field but the language problem has become great barrier. They are not being able to convince HHs well. - Other challenges like tablets, trainings ToT. - No public transportation so they have to spend two days to reach DLPIU office in Dhunche. One day stay at kalikasthan and another day to Dhunche. So almost 3-4 days is spend for up/down from DLPIU. . - RM and ward offices are not setup well so, it has made work difficult. Local Body Representatives - Local representatives are not satisfied with District and center role. They have asked for POs to be made available in their area. - Mason trainings are immediate requirement. - Fully Satisfied with role of NRA technical person. Beneficiaries - Few of the beneficiaries in ward 3 were complaining about delay in 2nd tranches. - Asked about help from POs and/or GoN for materials supply chain, as construction materials transportation individually has resulted in higher prices. - When asked about local representative and RM Chairperson role, local representative and RM. Chairperson themselves were found spending most time outside the RM. Partners Presence : - Batash foundation support 152 HHs in Lambhu Yarsa .The project was already competed. - NRCS, Batash foundation conducted 7 days mason training on yarsa , saramthali , Bhorle of this rural municipality. - Helvetas conducted 50 days OJT training on Bhorle , Saramthali . - NRA is planning to conduct 7 days mason training on parchang Yarsa . Challenges : - Overall reconstruction status is lowest in Naukunda RM with respect to other rural municipality . - The status of technical person mobilization/presence is good. But most of the technical person are new and without any trainings and orientations. - RM itself has no internet access. Photocopy and print facility is not available. - No public transportation access in few road connectivity available. - No IEC materials and/or awareness activities. - Phone network and other communication access is not reliable so, R.M. is not able to make contact and follow up technical persion . - Trained masons are not available. - Immediate need of mason training- 50 days and awareness activities with the help from POs needed.

Miscellaneous Items / AOB:

Decisions Made: (What, Why, Impacts)

| Next Steps: (Task, Assigned to, Checkpoint Date) | Person(s) Responsible | Due Date |
| --- | --- | --- |

| Attendees | Organisation | Phone No. | Email |
| --- | --- | --- | --- |
| Rijan Gajurel | HRRP | 9851114937 | im.rasuwa@hrrpnepal.org |
| Prabhu Pokheral | CLPIU | 9851224243 | Prabhupidge@gmail.com |
| Arun Kumar Sharma | DLPIU |  |  |
| Nirmal Chaulagai | DLPIU |  |  |
| Dipesh Panta | DLPIU |  |  |
| Dev Kumar Isar | DLPIU |  |  |
| Jukti Chaudhari | DLPIU |  |  |
| Mina Shrestha | DLPIU |  |  |
| Ramesh Ale | DLPIU |  |  |