| Meeting Purpose: | District Coordination Meeting |
| --- | --- |
| Meeting Date: | 180116 |
| Meeting Time: | 12:00PM |
| Meeting Location: | DAO office hall ,Dhunche Rasuwa |
| Meeting Facilitator: | Krishna Kant Upadhaya |
| Minutes Taken By: | Rijan Gajurel |

Discussion: (Items/Knowledge Shared)

Agenda’s Welcome and Introduction HRRP general coordination meeting was chaired by NRA district chief officer Mr. Chobendra Neupane and the program was facilitator was Mr.Krishna kant Upadhayay,DUDBC/DLPIU chief Mr.Dhira Phadera was gust of that meeting. HRRP welcomed all the participants in the meeting and thanked for their support in coordination and also requested to raise any types of issues related to reconstruction through this platform in the coming days and all participants introduced themselves from their respective places. Reconstruction Update –HRRP District focal person of HRRP Mr.Rijan Gajurel Update the reconstruction status of district to all participant .As of 16-Jan,2018 the enrollment /Tranche distribution matrix as per new structure : Data Source :EHRP Rasuwa(as of 16-Jan,2018) SN; Rural Municipality; Eligible HH; First tranche Received HHs; second Tranche Received HHs; Third Tranche Received HHs. 1; Gosaikunda RM; 1772; 1568; 596; 210. 2; Naukunda RM; 3228; 2732; 535; 322. 3; Parbatikunda RM; 1779; 1606; 351; 231. 4; Kalika RM; 2342; 2182; 768; 451. 5; Uttargaya RM; 2508; 2081; 882; 466. Total; 11,629; 10,250; 3132; 1680. HRRP brief about the social and technical assistance based on the NRA’s six minimum technical assistance package and highlighted on the gaps and duplication as per new structure. Graphs on technical assistance were shown and gaps were discussed in the terms of NRA’s minimum technical assistance package. HRRP also update the status of mason trainings (7days and 50 days) in district. NRA Rasuwa: NRA chief Mr.Krishna kant Upadhayay thanks all GoN and partners organization for their support in reconstruction .He request all partners and GoN agency to submit monthly progress report to NRA in time. NRA is focused on resettlement and relocation process for displaced households he said. Out 729 displaced households only 93 HHs were resettled. Limited land in district is main challenge for NRA to resettled these displaced HHs .He request all GoN and partners organization to support NRA on this regards. DUDBC/DLPIU : DUDBC chief Mr.Dhira Phadera shared the deadline provide by NRA plays great role in reconstruction process .Because of the deadline reconstruction process is rapidly increase in district .We achieved 52% progress for second tranche because of deadline .He said on this last months (ie Push ) we increased 20% more progress for second tranche. CLPIU is doing assessment of land for resettlement and relocation for displaced HHs .Once the report will finalized then report helps to finalized land for relocation . DUDBC also start six government structure constructions in district. Education: DLPIU education chief shared 7 school were already constructed, 7 school building is ongoing in district, contract sign process is ongoing for 6 schools and because of lack of land 10 school construction is stopped. 3 schools were planned by china embassy but the construction is not start yet. ADB is constructing 1 school . Lack of sufficient land for school building construction is major challenges. Chief district officer Mr.Chobendra Neupane said to coordinate with respective rural municipality to manage land for school construction. Health : 10 health center of was supported by karuna foundation Nepal and all of them were completed. Haku health post was supported by Trishuli 3A hydropower .Save the children construct Goljung VDC health post construction. Nepal red cross society construct district hospital and the permanent building for district hospital was planned by KFW . DCC/DLPIU : As per EHRP 10250 HHs received 1st tranche ,3132 HHs received 2nd tranche and 1680 HHs received 3rd tranche in district till date. Because of deadline there were more files for 2nd tranche in office. They are focusing to realize second tranche for collected files send by dlpiu engineers. Nepal Red Cross society (NRCS): NRCS shelter officer Mr.Pawan Bhatta shared out of 443 HHs they plan to support 435 HHs received 1st tranche , 314 HHs received 2nd tranche and 142 HHs received 3rd tranche .349 People were trained during short mason training in different vdc's of district . Challenges : - Some of HHs already build at Nuwakot - 16 HHs need to relocate on different place from their working areas. - Few people construct their house only to received GoN tranche. Samaratan Purse : Samaratan Purse project coordinator Mr.Pramod Titung shared they planed to construct 19 HHs in langtang .Out of 19 10 HHs were already completed and remaining 9 HHs were planned .They selected most vulnerable 19 HHs from community. LWF/Batash : LWF senior DRR officer share they already construct 152 HHs at lambu yarsa Vdc .Also constructed 100 toilets in Ramche and Yarsa Vdc. They are supporting on 1500 meter foot trail , 10 public bath station , 8 school toilet construction short mason training for 60 participant , irrigation panel for 104 HHs , first aid training , awareness program for toilet wash program in district . CSRC: CSRC district coordinator Mr.Bishwash Nepali share about the update of durable solution .They are supporting NRA for resettlement and relocation program in district. 93HHs already received land grant to buy new land. Oxfam, PIN , CSRC is supporting NRA for resettlement and relocation program through durable solution project in district. Chief district Officer : CDO Mr.Chobendra Neupane thanks all GoN and Partners organization for their support in reconstruction .He request to update their work progress and challenge in CDO office frequently. So, he will support partners on their challenges as well. He also request DDRC to put an agenda regarding extension of second tranche deadline in DDRC meeting .So, DDRC will request NRA for deadline extension .

Miscellaneous Items / AOB:

Decisions Made: (What, Why, Impacts)

- Put agenda in DDRC meeting regarding deadline extension of 2nd tranche and request central NRA for extension through DDRC . - Coordinate with Lumanti regarding their shelter support progress and challenges they are facing during this period.

| Next Steps: (Task, Assigned to, Checkpoint Date) | Person(s) Responsible | Due Date |
| --- | --- | --- |
| Contact Lumanti district coordinator for meeting with CDO | HRRP | ASAP |

| Attendees | Organisation | Phone No. | Email |
| --- | --- | --- | --- |
| Chobendra Neupane | DAO | 9851277777 |  |
| Krishna Kant Upadhaye | NRA | 9843588686 | Kku2070@gmail.com |
| Dhira Phadera | DUDBC | 9851209996 | Phaderadhera@gmail.com |
| Babu Ram Fyuba | DFID | 9840364193 | BaburamF@unops.org |
| Bishwash Nepali | CSRC | 9851241866 | biswash@csrcnepal.org |
| Rijan Gajurel | HRRP | 9851114937 | im.rasuwa@hrrpnepal.org |
| Pramod Titung | SP | 9849118316 | PTitung@samaritan.org |
| Pawan Bhatta | NRCS | 9806467356 | dewalpawan@gmail.com |
| Sukdev Sapkota | DEO | 9851153677 |  |
| Jhalak sharma Gautam | DHO | 9841335957 |  |
| Babu Lal Tamang | NRCS |  |  |
| Krishna Parsad Nirula | GIZ | 9852683038 | krishna.nirula@giz.de |
| Rajendra Paukurel | NRA | 9860667888 | NRAdccorasuwa100@gmail.com |