| Meeting Purpose: | General Palika -level Coordination Meeting |  |  |
| --- | --- | --- | --- |
| Meeting Date: | 7 July 2019 |  |  |
| Meeting Time: | 12:00 PM |  |  |
| Meeting Location: | Kathekhola Gaunpalika Office, Baglung district |  |  |
| Meeting Facilitator: | Rijan Gajurel, HRRP District Coordinator, Lamjung Cluster |  |  |
| Minutes Taken By: | Ambika Amatya, HRRP District Coordinator, Lalitpur Cluster |  |  |
| Summary of participants: | Total: 9 | Female: 2 | Male: 7 |

Discussion: (Items/Knowledge Shared)

Agendas: - Welcome and sharing of objective - Reconstruction updates and related challenges at the Palika level - Discussion on reconstruction efforts - AOB Agenda 1 - Welcome and sharing of objective The general palika level coordination meeting was conducted at Palika office of Kathekhola Rural Municipality. The coordination meeting was chaired by Mr. Amar Bahadur Thapa, Palika Chief in presence of Deputy Chief and Chief Administrative Officer of Kathekhola Gaupalika, DLPIU deployed engineers and HRRP Nepal. The main agenda of the meeting was to discuss on the reconstruction updates, progresses and issues at Palika level. Agenda 2 - Reconstruction updates and related challenges at the Palika level # Total Beneficiaries; # 283. # PA enrolled; # 259. # 1st tranche; # 259. # 2nd tranche; # 161. # 3rd tranche; # 131. Ward level reconstruction update: - Majority of housing typology in practice includes wall system BMC, SMC and SMM. - Majority of beneficiaries have rebuild the shelter soon after earthquake and their houses havenot received 2nd tranche yet with due conditions of failing to meet minimum requirements that makes houses safer and resilient. - Till date, construction completion certificate have not been provided to none of the houses that have received upto 3rd tranche. - Many beneficiaries have rebuild 1-roomed houses for the sake of taking government grant. Such houses were utilized as cow shed and to store agricultural stuffs by beneficiaries. - The cost of construction materials is high due to poor road condition as well as of near proximity of Baglung Bazaar. - Due to lack of clarity, current decision of NRA to issue reconstruction grant of Rs 300000 to beneficiaries that have rebuild houses soon after earthquake have caused confusions and disputes among people in communities about minimum requirements and grant disbursement mechanisms. - Three technical personnel (engineer and sub engineer) are deployed from DLPIU Building to work in Kathekhola Gaupalika.

Miscellaneous Items / AOB:

- Team member of HRRP Nepal reminded Palika Chief and Deputy Palika Chief about the MOU agreement conducted between municipalities and GON/NRA during district-level reconstruction review meeting.

Decisions Made: (What, Why, Impacts)

- Palika office will soon prepare list of beneficiaries who have reconstructed house before the endorsement of NRA’s guidelines and before placement of engineers.

| Next Steps/action points: | Person(s) Responsible | Due Date |
| --- | --- | --- |
| To inform and encourage beneficiaries to carry out rebuilding of houses. | Palika Office | On-going |
| To facilitate grant application file process of beneficiaries | Palika Office | On-going |
| To prepare list of beneficiaries who have reconstructed houses soon after earthquake and before endorsement of NRA’s guidelines | Palika Office | As soon as possible |

| S.N. | Attendees | Gender | Organization | Designation | Phone No. | Email |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Amar Bahadur Thapa | Male | Kathekhola Gaupalika | Palika Chief | 9857638796 |  |
| 2 | Arjun Bahadur Khatri | Male | Kathekhola Gaupalika | Deputy Palika Chief |  |  |
| 3 | Tika Sangam Bishwakarma | Male | Kathekhola Gaupalika | Member of Palika |  |  |
| 4 | Khem Bahadur Bishwakarma | Male | Kathekhola Gaupalika | Chief Administrative Officer | 9857621884 |  |
| 5 | Ambika Amatya | Female | HRRP Lalitpur Cluster | Cluster Coordinator | 9841356409 |  |
| 6 | Rijan Gajurel | Male | HRRP Lamjung Cluster | Cluster Coordinator | 9843217112 | Rizan.gajurel@hrrpnepal.org |
| 7 | Biren Shah | Male | HRRP Lamjung Cluster | District Technical Coordinator | 9817396852 | Biren.shah@hrrpnepal.org |
| 8 | Rakshya Shrestha | Female | DLPIU Building Baglung | Engineer |  |  |
| 9 | Ganga Lal Yadav | Male | Kathekhola Gaupalika | Engineer |  |  |