16459 | Rasuwa | Thulogoun | 9 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 3
16460 | Rasuwa | Thuman | 1 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 1
16461 | Rasuwa | Thuman | 2 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 1
16462 | Rasuwa | Thuman | 3 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 1
16463 | Rasuwa | Thuman | 4 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 1
16464 | Rasuwa | Thuman | 5 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 1
16465 | Rasuwa | Thuman | 6 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 1
16466 | Rasuwa | Thuman | 7 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 1
16467 | Rasuwa | Thuman | 8 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 1
16468 | Rasuwa | Thuman | 9 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 1
16469 | Rasuwa | Timure | 1 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 2
16470 | Rasuwa | Timure | 2 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 2
16471 | Rasuwa | Timure | 3 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 2
16472 | Rasuwa | Timure | 4 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 2
16473 | Rasuwa | Timure | 5 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 2
16474 | Rasuwa | Timure | 6 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 2
16475 | Rasuwa | Timure | 7 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 2
16476 | Rasuwa | Timure | 8 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 2
16477 | Rasuwa | Timure | 9 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 2
16478 | Rasuwa | Ramche | 1 | KF | KF | KF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-08-05 | 2016-08-11 |  | Kalika | 1
16479 | Rasuwa | Ramche | 2 | KF | KF | KF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-08-05 | 2016-08-11 |  | Kalika | 1
16480 | Rasuwa | Ramche | 5 | KF | KF | KF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-08-05 | 2016-08-11 |  | Kalika | 1
16481 | Rasuwa | Ramche | 6 | KF | KF | KF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-08-05 | 2016-08-11 |  | Kalika | 1
16482 | Rasuwa | Ramche | 7 | KF | KF | KF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-05 | 2016-08-11 |  | Kalika | 1
16483 | Rasuwa | Ramche | 8 | KF | KF | KF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-08-05 | 2016-08-11 |  | Kalika | 1
16484 | Rasuwa | Ramche | 9 | KF | KF | KF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-08-05 | 2016-08-11 |  | Kalika | 1
16485 | Rasuwa | Thulogoun | 1 | Norlang SAHAS | Norlang SAHAS | Norlang SAHAS | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 Days DUDBC rural | # of trainees | Yes | Completed | 9 | 9 | 2016-11-23 | 2016-11-28 |  | Uttargaya | 3
16486 | Rasuwa | Thulogoun | 2 | Norlang SAHAS | Norlang SAHAS | Norlang SAHAS | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 Days DUDBC rural | # of trainees | Yes | Completed | 10 | 10 | 2016-11-23 | 2016-11-28 |  | Uttargaya | 3
16487 | Rasuwa | Thulogoun | 3 | Norlang SAHAS | Norlang SAHAS | Norlang SAHAS | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 Days DUDBC rural | # of trainees | Yes | Completed | 7 | 7 | 2016-11-23 | 2016-11-28 |  | Uttargaya | 3
16488 | Rasuwa | Thulogoun | 4 | Norlang SAHAS | Norlang SAHAS | Norlang SAHAS | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 Days DUDBC rural | # of trainees | Yes | Completed | 4 | 4 | 2016-11-23 | 2016-11-28 |  | Uttargaya | 3
16489 | Rasuwa | Thulogoun | 5 | Norlang SAHAS | Norlang SAHAS | Norlang SAHAS | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 Days DUDBC rural | # of trainees | Yes | Completed | 4 | 4 | 2016-11-23 | 2016-11-28 |  | Uttargaya | 3
16490 | Rasuwa | Thulogoun | 6 | Norlang SAHAS | Norlang SAHAS | Norlang SAHAS | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 Days DUDBC rural | # of trainees | Yes | Completed | 6 | 6 | 2016-11-23 | 2016-11-28 |  | Uttargaya | 3
16491 | Rasuwa | Thulogoun | 7 | Norlang SAHAS | Norlang SAHAS | Norlang SAHAS | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 Days DUDBC rural | # of trainees | Yes | Completed | 5 | 5 | 2016-11-23 | 2016-11-28 |  | Uttargaya | 3
16492 | Rasuwa | Thulogoun | 9 | Norlang SAHAS | Norlang SAHAS | Norlang SAHAS | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 Days DUDBC rural | # of trainees | Yes | Completed | 5 | 5 | 2016-11-23 | 2016-11-28 |  | Uttargaya | 3
16493 | Rasuwa | Dhunche | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Gosaikunda | 6
16494 | Rasuwa | Dhunche | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Gosaikunda | 6
16495 | Rasuwa | Dhunche | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Gosaikunda | 6
16496 | Rasuwa | Dhunche | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Gosaikunda | 6
16497 | Rasuwa | Dhunche | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Gosaikunda | 6
16498 | Rasuwa | Dhunche | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Gosaikunda | 6
16499 | Rasuwa | Dhunche | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Gosaikunda | 6
16500 | Rasuwa | Dhunche | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Gosaikunda | 6
16501 | Rasuwa | Dhunche | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Gosaikunda | 6
16502 | Rasuwa | Dhunche | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gosaikunda | 6
16503 | Rasuwa | Dhunche | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gosaikunda | 6
16504 | Rasuwa | Dhunche | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gosaikunda | 6
16505 | Rasuwa | Dhunche | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gosaikunda | 6
16506 | Rasuwa | Dhunche | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gosaikunda | 6
16507 | Rasuwa | Dhunche | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gosaikunda | 6
16508 | Rasuwa | Dhunche | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gosaikunda | 6
16509 | Rasuwa | Dhunche | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gosaikunda | 6
16510 | Rasuwa | Dhunche | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gosaikunda | 6
16511 | Rasuwa | Syafru | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Gosaikunda | 5
16512 | Rasuwa | Syafru | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Gosaikunda | 5
16513 | Rasuwa | Syafru | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Gosaikunda | 5
16514 | Rasuwa | Syafru | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Gosaikunda | 5
16515 | Rasuwa | Syafru | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Gosaikunda | 5
16516 | Rasuwa | Syafru | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Gosaikunda | 5
16517 | Rasuwa | Syafru | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Gosaikunda | 5
16518 | Rasuwa | Syafru | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Gosaikunda | 5
16519 | Rasuwa | Syafru | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Gosaikunda | 5
16520 | Rasuwa | Syafru | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gosaikunda | 5
16521 | Rasuwa | Syafru | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gosaikunda | 5
16522 | Rasuwa | Syafru | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gosaikunda | 5
16523 | Rasuwa | Syafru | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gosaikunda | 5
16524 | Rasuwa | Syafru | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gosaikunda | 5
16525 | Rasuwa | Syafru | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gosaikunda | 5
16526 | Rasuwa | Syafru | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gosaikunda | 5
16527 | Rasuwa | Syafru | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gosaikunda | 5
16528 | Rasuwa | Syafru | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gosaikunda | 5
16529 | Rasuwa | Jibjibe(Nilkantha) | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Kalika | 3
16530 | Rasuwa | Jibjibe(Nilkantha) | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Kalika | 3
16531 | Rasuwa | Jibjibe(Nilkantha) | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Kalika | 3
16532 | Rasuwa | Jibjibe(Nilkantha) | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Kalika | 3
16533 | Rasuwa | Jibjibe(Nilkantha) | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Kalika | 3
16534 | Rasuwa | Jibjibe(Nilkantha) | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Kalika | 3
16535 | Rasuwa | Jibjibe(Nilkantha) | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Kalika | 3
16536 | Rasuwa | Jibjibe(Nilkantha) | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Kalika | 3
16537 | Rasuwa | Jibjibe(Nilkantha) | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-01 |  |  | Kalika | 3
16538 | Rasuwa | Jibjibe(Nilkantha) | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kalika | 3
16539 | Rasuwa | Jibjibe(Nilkantha) | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kalika | 3
16540 | Rasuwa | Jibjibe(Nilkantha) | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kalika | 3
16541 | Rasuwa | Jibjibe(Nilkantha) | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kalika | 3
16542 | Rasuwa | Jibjibe(Nilkantha) | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kalika | 3
16543 | Rasuwa | Jibjibe(Nilkantha) | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kalika | 3
16544 | Rasuwa | Jibjibe(Nilkantha) | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kalika | 3
16545 | Rasuwa | Jibjibe(Nilkantha) | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kalika | 3
16546 | Rasuwa | Jibjibe(Nilkantha) | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kalika | 3
16547 | Rasuwa | Ramche | All | GON | TCN | GON | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Kalika | 1
16548 | Rasuwa | Ramche | All | GON | TCN | GON | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Kalika | 1
16549 | Rasuwa | Ramche | All | GON | TCN | GON | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Kalika | 1
16550 | Rasuwa | Ramche | All | GON | TCN | GON | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Kalika | 1
16551 | Rasuwa | Ramche | All | GON | TCN | GON | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Kalika | 1
16552 | Rasuwa | Ramche | All | GON | TCN | GON | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Kalika | 1
16553 | Rasuwa | Ramche | All | GON | TCN | GON | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Kalika | 1
16554 | Rasuwa | Ramche | All | GON | TCN | GON | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Kalika | 1
16555 | Rasuwa | Ramche | All | GON | TCN | GON | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Kalika | 1
16556 | Rasuwa | Ramche | All | GON | TCN | GON | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kalika | 1
16557 | Rasuwa | Ramche | All | GON | TCN | GON | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kalika | 1
16558 | Rasuwa | Ramche | All | GON | TCN | GON | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kalika | 1
16559 | Rasuwa | Ramche | All | GON | TCN | GON | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kalika | 1
16560 | Rasuwa | Ramche | All | GON | TCN | GON | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kalika | 1
16561 | Rasuwa | Ramche | All | GON | TCN | GON | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kalika | 1
16562 | Rasuwa | Ramche | All | GON | TCN | GON | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kalika | 1
16563 | Rasuwa | Ramche | All | GON | TCN | GON | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kalika | 1
16564 | Rasuwa | Ramche | All | GON | TCN | GON | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kalika | 1
16565 | Rasuwa | Thulogoun | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-02 |  |  | Uttargaya | 3
16566 | Rasuwa | Thulogoun | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-03 |  |  | Uttargaya | 3
16567 | Rasuwa | Thulogoun | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-04 |  |  | Uttargaya | 3
16568 | Rasuwa | Thulogoun | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-05 |  |  | Uttargaya | 3
16569 | Rasuwa | Thulogoun | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-06 |  |  | Uttargaya | 3
16570 | Rasuwa | Thulogoun | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-07 |  |  | Uttargaya | 3
16571 | Rasuwa | Thulogoun | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-08 |  |  | Uttargaya | 3
16572 | Rasuwa | Thulogoun | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-09 |  |  | Uttargaya | 3
16573 | Rasuwa | Thulogoun | All | GON | TCN | GoN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-10 |  |  | Uttargaya | 3
16574 | Rasuwa | Thulogoun | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Uttargaya | 3
16575 | Rasuwa | Thulogoun | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Uttargaya | 3
16576 | Rasuwa | Thulogoun | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Uttargaya | 3
16577 | Rasuwa | Thulogoun | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Uttargaya | 3
16578 | Rasuwa | Thulogoun | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Uttargaya | 3
16579 | Rasuwa | Thulogoun | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Uttargaya | 3
16580 | Rasuwa | Thulogoun | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Uttargaya | 3
16581 | Rasuwa | Thulogoun | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Uttargaya | 3
16582 | Rasuwa | Thulogoun | All | GON | TCN | GoN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Uttargaya | 3
16583 | Rasuwa | Jibjibe(Nilkantha) | 4 | GON | DUDBC | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2017-12-11 | 2017-12-16 |  | Kalika | 3
16584 | Rasuwa | Jibjibe(Nilkantha) | 5 | GON | DUDBC | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2017-12-11 | 2017-12-16 |  | Kalika | 2
16585 | Rasuwa | Jibjibe(Nilkantha) | 9 | GON | DUDBC | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-12-11 | 2017-12-16 |  | Kalika | 5
16586 | Rasuwa | Yarsa | 2 | NAF | NAF | ASIA ONLUS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-11-08 | 2017-11-14 |  | Naukunda | 2
16587 | Rasuwa | Saramthali | 5 | NAF | NAF | ASIA ONLUS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2017-11-08 | 2017-11-14 |  | Naukunda | 4
16588 | Rasuwa | Saramthali | 6 | NAF | NAF | ASIA ONLUS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2017-11-08 | 2017-11-14 |  | Naukunda | 3
16589 | Rasuwa | Bhorle | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Kalika | 5
16590 | Rasuwa | Bhorle | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Naukunda | 6
16591 | Rasuwa | Bhorle | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Naukunda | 6
16592 | Rasuwa | Bhorle | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Naukunda | 5
16593 | Rasuwa | Bhorle | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Naukunda | 5
16594 | Rasuwa | Bhorle | 6 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kalika | 4
16595 | Rasuwa | Bhorle | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Naukunda | 5
16596 | Rasuwa | Bhorle | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kalika | 4
16597 | Rasuwa | Bhorle | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kalika | 4
16598 | Rasuwa | Dandagoun | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 2
16599 | Rasuwa | Dandagoun | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 2
16600 | Rasuwa | Dandagoun | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 2
16601 | Rasuwa | Dandagoun | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 2
16602 | Rasuwa | Dandagoun | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 2
16603 | Rasuwa | Dandagoun | 6 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 2
16604 | Rasuwa | Dandagoun | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 1
16605 | Rasuwa | Dandagoun | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 1
16606 | Rasuwa | Dandagoun | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 1
16607 | Rasuwa | Jibjibe(Nilkantha) | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Kalika | 3
16608 | Rasuwa | Jibjibe(Nilkantha) | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kalika | 3
16609 | Rasuwa | Jibjibe(Nilkantha) | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kalika | 3
16610 | Rasuwa | Jibjibe(Nilkantha) | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kalika | 3
16611 | Rasuwa | Jibjibe(Nilkantha) | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kalika | 2
16612 | Rasuwa | Jibjibe(Nilkantha) | 6 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kalika | 2
16613 | Rasuwa | Jibjibe(Nilkantha) | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kalika | 2
16614 | Rasuwa | Jibjibe(Nilkantha) | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kalika | 5
16615 | Rasuwa | Jibjibe(Nilkantha) | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kalika | 5
16616 | Rasuwa | Laharepouwa | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 5
16617 | Rasuwa | Laharepouwa | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 5
16618 | Rasuwa | Laharepouwa | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 5
16619 | Rasuwa | Laharepouwa | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 4
16620 | Rasuwa | Laharepouwa | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 4
16621 | Rasuwa | Laharepouwa | 6 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 4
16622 | Rasuwa | Laharepouwa | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 4
16623 | Rasuwa | Laharepouwa | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kalika | 2
16624 | Rasuwa | Laharepouwa | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 5
16625 | Rasuwa | Saramthali | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Naukunda | 4
16626 | Rasuwa | Saramthali | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Naukunda | 4
16627 | Rasuwa | Saramthali | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Naukunda | 4
16628 | Rasuwa | Saramthali | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Naukunda | 4
16629 | Rasuwa | Saramthali | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Naukunda | 4
16630 | Rasuwa | Saramthali | 6 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Naukunda | 3
16631 | Rasuwa | Saramthali | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 8 | 8 | 2016-01-01 | 2018-12-31 |  | Naukunda | 3
16632 | Rasuwa | Saramthali | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 8 | 8 | 2016-01-01 | 2018-12-31 |  | Naukunda | 3
16633 | Rasuwa | Saramthali | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 8 | 8 | 2016-01-01 | 2018-12-31 |  | Naukunda | 3
16634 | Rasuwa | Thulogoun | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 14 | 14 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 3
16635 | Rasuwa | Thulogoun | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 3
16636 | Rasuwa | Thulogoun | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 3
16637 | Rasuwa | Thulogoun | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 3
16638 | Rasuwa | Thulogoun | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 14 | 14 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 3
16639 | Rasuwa | Thulogoun | 6 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 14 | 14 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 3
16640 | Rasuwa | Thulogoun | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 3
16641 | Rasuwa | Thulogoun | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 12 | 12 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 2
16642 | Rasuwa | Thulogoun | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Uttargaya | 3
16643 | Rasuwa | Yarsa | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Naukunda | 2
16644 | Rasuwa | Yarsa | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 8 | 8 | 2016-01-01 | 2018-12-31 |  | Naukunda | 2
16645 | Rasuwa | Yarsa | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Naukunda | 2
16646 | Rasuwa | Yarsa | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 8 | 8 | 2016-01-01 | 2018-12-31 |  | Naukunda | 2
16647 | Rasuwa | Yarsa | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Naukunda | 1
16648 | Rasuwa | Yarsa | 6 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Naukunda | 1
16649 | Rasuwa | Yarsa | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Naukunda | 1
16650 | Rasuwa | Yarsa | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Naukunda | 1
16651 | Rasuwa | Yarsa | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Naukunda | 6
16652 | Rasuwa | Thulogoun | 1 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 49 | 48 | 2016-02-15 | 2016-08-29 |  | Uttargaya | 3
16653 | Rasuwa | Thulogoun | 2 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 32 | 33 | 2016-02-15 | 2016-08-29 |  | Uttargaya | 3
16654 | Rasuwa | Thulogoun | 3 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 32 | 31 | 2016-02-15 | 2016-08-29 |  | Uttargaya | 3
16655 | Rasuwa | Thulogoun | 4 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 43 | 43 | 2016-02-15 | 2016-08-29 |  | Uttargaya | 3
16656 | Rasuwa | Thulogoun | 5 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 50 | 47 | 2016-02-15 | 2016-08-29 |  | Uttargaya | 3
16657 | Rasuwa | Thulogoun | 6 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 60 | 57 | 2016-02-15 | 2016-08-29 |  | Uttargaya | 3
16658 | Rasuwa | Thulogoun | 7 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 33 | 31 | 2016-02-15 | 2016-08-29 |  | Uttargaya | 3
16659 | Rasuwa | Thulogoun | 8 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 69 | 69 | 2016-02-15 | 2016-08-29 |  | Uttargaya | 2
16660 | Rasuwa | Thulogoun | 9 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 75 | 74 | 2016-01-25 | 2016-12-15 |  | Uttargaya | 3
16661 | Rasuwa | Thulogoun | 1 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 49 | 45 | 2016-09-01 | 2018-12-31 |  | Uttargaya | 3
16662 | Rasuwa | Thulogoun | 2 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 32 | 24 | 2016-09-01 | 2018-12-31 |  | Uttargaya | 3
16663 | Rasuwa | Thulogoun | 3 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 32 | 39 | 2016-09-01 | 2018-12-31 |  | Uttargaya | 3
16664 | Rasuwa | Thulogoun | 4 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 43 | 46 | 2016-09-01 | 2018-12-31 |  | Uttargaya | 3
16665 | Rasuwa | Thulogoun | 5 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 50 | 37 | 2016-09-01 | 2018-12-31 |  | Uttargaya | 3
16666 | Rasuwa | Thulogoun | 6 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 60 | 10 | 2016-09-01 | 2018-12-31 |  | Uttargaya | 3
16667 | Rasuwa | Thulogoun | 7 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 33 | 19 | 2016-09-01 | 2018-12-31 |  | Uttargaya | 3
16668 | Rasuwa | Thulogoun | 8 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 69 | 36 | 2016-09-01 | 2018-12-31 |  | Uttargaya | 2
16669 | Rasuwa | Thulogoun | 9 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 75 | 20 | 2016-09-01 | 2018-12-31 |  | Uttargaya | 3
16670 | Rasuwa | Thulogoun | 1 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 49 | 39 | 2016-09-01 | 2018-12-31 |  | Uttargaya | 3
16671 | Rasuwa | Thulogoun | 2 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 32 | 16 | 2016-09-01 | 2018-12-31 |  | Uttargaya | 3
16672 | Rasuwa | Thulogoun | 3 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 32 | 27 | 2016-09-01 | 2018-12-31 |  | Uttargaya | 3
16673 | Rasuwa | Thulogoun | 4 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 43 | 34 | 2016-09-01 | 2018-12-31 |  | Uttargaya | 3
16674 | Rasuwa | Thulogoun | 5 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 50 | 21 | 2016-09-01 | 2018-12-31 |  | Uttargaya | 3
16675 | Rasuwa | Thulogoun | 6 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 60 | 7 | 2016-09-01 | 2018-12-31 |  | Uttargaya | 3
16676 | Rasuwa | Thulogoun | 7 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 33 | 13 | 2016-09-01 | 2018-12-31 |  | Uttargaya | 3
16677 | Rasuwa | Thulogoun | 8 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 69 | 26 | 2016-09-01 | 2018-12-31 |  | Uttargaya | 2
16678 | Rasuwa | Thulogoun | 9 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 75 | 11 | 2016-09-01 | 2018-12-31 |  | Uttargaya | 3
16679 | Rasuwa | Thulogoun | 1 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 49 | 48 | 2017-01-15 | 2018-12-31 |  | Uttargaya | 3
16680 | Rasuwa | Thulogoun | 2 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 32 | 33 | 2017-01-15 | 2018-12-31 |  | Uttargaya | 3
16681 | Rasuwa | Thulogoun | 3 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 32 | 31 | 2017-01-15 | 2018-12-31 |  | Uttargaya | 3
16682 | Rasuwa | Thulogoun | 4 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 43 | 43 | 2017-01-15 | 2018-12-31 |  | Uttargaya | 3
16683 | Rasuwa | Thulogoun | 5 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 50 | 47 | 2017-01-15 | 2018-12-31 |  | Uttargaya | 3
16684 | Rasuwa | Thulogoun | 6 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 60 | 57 | 2017-01-15 | 2018-12-31 |  | Uttargaya | 3
16685 | Rasuwa | Thulogoun | 7 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 33 | 31 | 2017-01-15 | 2018-12-31 |  | Uttargaya | 3
16686 | Rasuwa | Thulogoun | 8 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 69 | 69 | 2017-01-15 | 2018-12-31 |  | Uttargaya | 2
16687 | Rasuwa | Thulogoun | 9 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 75 | 73 | 2017-01-15 | 2018-12-31 |  | Uttargaya | 3
16688 | Sindhupalchok | Gunsakot | 1 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 9 | 9 | 2016-07-21 | 2016-09-20 | 4 lots in same VDCs but different wards ( 21-27-Jul-2016, 25-31-Jul-2016, 3-9-Aug-16, 14-20-Sep-16) verified with Karna sir on 18th April 2017 | Panchpokhari Thangpal | 5
16689 | Sindhupalchok | Gunsakot | 2 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 15 | 15 | 2016-07-21 | 2016-09-20 | 4 lots in same VDCs but different wards ( 21-27-Jul-2016, 25-31-Jul-2016, 3-9-Aug-16, 14-20-Sep-16) verified with Karna sir on 18th April 2017 | Panchpokhari Thangpal | 5
16690 | Sindhupalchok | Gunsakot | 3 | ARSOW-TGH | ARSOW-N | FDF | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Planned | 1 | 0 | 2016-08-01 |  |  | Panchpokhari Thangpal | 5
16691 | Sindhupalchok | Gunsakot | 3 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 14 | 14 | 2016-07-21 | 2016-09-20 | 4 lots in same VDCs but different wards ( 21-27-Jul-2016, 25-31-Jul-2016, 3-9-Aug-16, 14-20-Sep-16) verified with Karna sir on 18th April 2017 | Panchpokhari Thangpal | 5
16692 | Sindhupalchok | Gunsakot | 4 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 14 | 14 | 2016-07-21 | 2016-09-20 | 4 lots in same VDCs but different wards ( 21-27-Jul-2016, 25-31-Jul-2016, 3-9-Aug-16, 14-20-Sep-16) verified with Karna sir on 18th April 2017 | Panchpokhari Thangpal | 5
16693 | Sindhupalchok | Gunsakot | 5 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 11 | 11 | 2016-07-21 | 2016-09-20 | 4 lots in same VDCs but different wards ( 21-27-Jul-2016, 25-31-Jul-2016, 3-9-Aug-16, 14-20-Sep-16) verified with Karna sir on 18th April 2017 | Panchpokhari Thangpal | 5
16694 | Sindhupalchok | Gunsakot | 5 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Carpenter | Carpenter training | # of trainees | Yes | Planned | 26 | 0 | 2017-06-15 |  |  | Panchpokhari Thangpal | 5
16695 | Sindhupalchok | Gunsakot | 5 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Bar bender | Welder Training | # of trainees | Yes | Planned | 13 | 0 | 2017-10-15 |  |  | Panchpokhari Thangpal | 5
16696 | Sindhupalchok | Gunsakot | 5 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Plumber | Plumber training | # of trainees | Yes | Planned | 13 | 0 | 2017-11-15 |  |  | Panchpokhari Thangpal | 5
16697 | Sindhupalchok | Gunsakot | 5 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Plumber | Electrician Training | # of trainees | Yes | Planned | 13 | 0 | 2017-11-15 |  |  | Panchpokhari Thangpal | 5
16698 | Sindhupalchok | Gunsakot | 6 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 8 | 8 | 2016-07-21 | 2016-09-20 | 4 lots in same VDCs but different wards ( 21-27-Jul-2016, 25-31-Jul-2016, 3-9-Aug-16, 14-20-Sep-16) verified with Karna sir on 18th April 2017 | Panchpokhari Thangpal | 5
16699 | Sindhupalchok | Gunsakot | 7 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 12 | 12 | 2016-07-21 | 2016-09-20 | 4 lots in same VDCs but different wards ( 21-27-Jul-2016, 25-31-Jul-2016, 3-9-Aug-16, 14-20-Sep-16) verified with Karna sir on 18th April 2017 | Panchpokhari Thangpal | 5
16700 | Sindhupalchok | Gunsakot | 8 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 12 | 12 | 2016-07-21 | 2016-09-20 | 4 lots in same VDCs but different wards ( 21-27-Jul-2016, 25-31-Jul-2016, 3-9-Aug-16, 14-20-Sep-16) verified with Karna sir on 18th April 2017 | Panchpokhari Thangpal | 5
16701 | Sindhupalchok | Gunsakot | 9 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 2 | 2 | 2016-07-21 | 2016-09-20 |  | Panchpokhari Thangpal | 5
16702 | Sindhupalchok | Gunsakot |  | ARSOW-TGH | ARSOW-N | FDF | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Ongoing | 491 | 180 | 2017-03-21 |  | equal to 35000 NPR material support (4 bundles of CGI sheet for stone mud murtar house and 30 sacks of Cement to RCC/Pilar system house) | Panchpokhari Thangpal | 5
16703 | Sindhupalchok | Gunsakot |  | ARSOW-TGH | ARSOW-N | FDF | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 2 | 0 | 2018-01-25 |  | Support based on the NRA policy | Panchpokhari Thangpal | 5
16704 | Sindhupalchok | Gunsakot |  | ARSOW-TGH | ARSOW-N | FDF | Training | ToT | Skilled masons |  | # of trainees | Yes | Ongoing | 60 | 30 | 2016-04-01 | 2016-12-30 |  | Panchpokhari Thangpal | 5
16705 | Sindhupalchok | Gunsakot | All | ARSOW-TGH | ARSOW-N | FDF | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 660 | 250 | 2017-08-01 |  |  | #N/A | #N/A
16706 | Sindhupalchok | Gunsakot |  | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Carpenter |  | # of trainees | Yes | Planned | 14 | 0 | 2018-01-15 |  |  | Panchpokhari Thangpal | 5
16707 | Sindhupalchok | Gunsakot |  | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Plumber |  | # of trainees | Yes | Planned | 7 | 0 | 2018-01-15 |  |  | Panchpokhari Thangpal | 5
16708 | Sindhupalchok | Gunsakot |  | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Electrician |  | # of trainees | Yes | Planned | 7 | 0 | 2018-01-15 |  |  | Panchpokhari Thangpal | 5
16709 | Sindhupalchok | Gunsakot |  | ARSOW-TGH | ARSOW-N | FDF | Training | Other trainings | Other trainings (specify in Activity Detail) | Welder Training | # of trainees | Yes | Planned | 7 | 0 | 2018-01-15 |  |  | Panchpokhari Thangpal | 5
16710 | Sindhupalchok | Gunsakot |  | ARSOW-TGH | ARSOW-N | FDF | Technical Assistance | Demonstration Construction | House | Community Building | # of constructions | Yes | Completed | 1 | 1 | 2017-03-01 | 2017-12-01 |  | Panchpokhari Thangpal | 5
16711 | Sindhupalchok | Gunsakot | All | ARSOW-TGH | ARSOW-N | FDF | Technical Assistance | Household toilet construction | Household toilet construction | Materials support | # of households | Yes | Planned | 400 | 0 | 2018-01-15 |  |  | #N/A | #N/A
16712 | Sindhupalchok | Gunsakot | All | ARSOW-TGH | ARSOW-N | FDF | Training | Other trainings | Other trainings (specify in Activity Detail) | Training to beneficiaries on toilet construction | # of trainees | Yes | Planned | 50 | 0 | 2018-01-10 |  |  | #N/A | #N/A
16713 | Sindhupalchok | ThampalChhap | 1 | ARSOW-TGH | ARSOW-N | FDF | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Planned | 1 | 0 | 2016-08-01 |  | karunakhadka50@gmail.com | Panchpokhari Thangpal | 6
16714 | Sindhupalchok | ThampalChhap | 1 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 17 | 17 | 2016-03-09 | 2016-09-02 | 4 lots 9-15 Mar-2016, 3-9-Sep-2016, 20-26-Aug-2016 & 27-Aug-2 Sep-2016(Verified with Karna Nepali, PC from ARSOW on 18th April 2017 | Panchpokhari Thangpal | 6
16715 | Sindhupalchok | ThampalChhap | 2 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 10 | 10 | 2016-03-09 | 2016-09-02 | 4 lots 9-15 Mar-2016, 3-9-Sep-2016, 20-26-Aug-2016 & 27-Aug-2 Sep-2016(Verified with Karna Nepali, PC from ARSOW on 18th April 2017 | Panchpokhari Thangpal | 6
16716 | Sindhupalchok | ThampalChhap | 3 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 7 | 7 | 2016-03-09 | 2016-09-02 | 4 lots 9-15 Mar-2016, 3-9-Sep-2016, 20-26-Aug-2016 & 27-Aug-2 Sep-2016(Verified with Karna Nepali, PC from ARSOW on 18th April 2017 | Panchpokhari Thangpal | 6
16717 | Sindhupalchok | ThampalChhap | 4 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 12 | 12 | 2016-03-09 | 2016-09-02 | 4 lots 9-15 Mar-2016, 3-9-Sep-2016, 20-26-Aug-2016 & 27-Aug-2 Sep-2016(Verified with Karna Nepali, PC from ARSOW on 18th April 2017 | Panchpokhari Thangpal | 6
16718 | Sindhupalchok | ThampalChhap | 5 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 22 | 22 | 2016-03-09 | 2016-09-02 | 4 lots 9-15 Mar-2016, 3-9-Sep-2016, 20-26-Aug-2016 & 27-Aug-2 Sep-2016(Verified with Karna Nepali, PC from ARSOW on 18th April 2017 | Panchpokhari Thangpal | 6
16719 | Sindhupalchok | ThampalChhap | 6 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 2 | 2 | 2016-03-09 | 2016-09-02 | 4 lots 9-15 Mar-2016, 3-9-Sep-2016, 20-26-Aug-2016 & 27-Aug-2 Sep-2016(Verified with Karna Nepali, PC from ARSOW on 18th April 2017 | Panchpokhari Thangpal | 6
16720 | Sindhupalchok | ThampalChhap | 6 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | Carpenter training | # of trainees | Yes | Planned | 26 | 0 | 2017-06-15 |  |  | Panchpokhari Thangpal | 6
16721 | Sindhupalchok | ThampalChhap | 6 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Bar bender | Welder Training | # of trainees | Yes | Planned | 13 | 0 | 2017-10-15 |  |  | Panchpokhari Thangpal | 6
16722 | Sindhupalchok | ThampalChhap | 6 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Plumber | Plumber training | # of trainees | Yes | Planned | 13 | 0 | 2017-11-15 |  |  | Panchpokhari Thangpal | 6
16723 | Sindhupalchok | ThampalChhap | 6 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Electrician | Electrician Training | # of trainees | Yes | Planned | 13 | 0 | 2017-11-15 |  |  | Panchpokhari Thangpal | 6
16724 | Sindhupalchok | ThampalChhap | 7 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 24 | 24 | 2016-03-09 | 2016-09-02 | 4 lots 9-15 Mar-2016, 3-9-Sep-2016, 20-26-Aug-2016 & 27-Aug-2 Sep-2016(Verified with Karna Nepali, PC from ARSOW on 18th April 2017 | Panchpokhari Thangpal | 6
16725 | Sindhupalchok | ThampalChhap | 8 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 29 | 29 | 2016-03-09 | 2016-09-02 | 4 lots 9-15 Mar-2016, 3-9-Sep-2016, 20-26-Aug-2016 & 27-Aug-2 Sep-2016(Verified with Karna Nepali, PC from ARSOW on 18th April 2017 | Panchpokhari Thangpal | 6
16726 | Sindhupalchok | ThampalChhap | 9 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 32 | 32 | 2016-03-09 | 2016-09-02 | 4 lots 9-15 Mar-2016, 3-9-Sep-2016, 20-26-Aug-2016 & 27-Aug-2 Sep-2016(Verified with Karna Nepali, PC from ARSOW on 18th April 2017 | Panchpokhari Thangpal | 6
16727 | Sindhupalchok | ThampalChhap |  | ARSOW-TGH | ARSOW-N | FDF | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Ongoing | 1006 | 180 | 2017-03-21 |  | Support based on the NRA policy | Panchpokhari Thangpal | 6
16728 | Sindhupalchok | ThampalChhap |  | ARSOW-TGH | ARSOW-N | FDF | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-06-04 |  | Support based on the NRA policy | Panchpokhari Thangpal | 6
16729 | Sindhupalchok | ThampalChhap |  | ARSOW-TGH | ARSOW-N | FDF | Training | ToT | Skilled masons |  | # of trainees | Yes | Planned | 60 | 0 | 2016-04-01 | 2016-12-30 |  | Panchpokhari Thangpal | 6
16730 | Sindhupalchok | ThampalChhap |  | ARSOW-TGH | ARSOW-N | FDF | Technical Assistance | Demonstration Construction | House | Community Building | # of constructions | Yes | Completed | 1 | 1 | 2017-03-02 | 2017-11-01 |  | Panchpokhari Thangpal | 6
16731 | Sindhupalchok | ThampalChhap | 2 | ARSOW-TGH | ARSOW-N | FDF | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 150 | 25 | 2017-08-01 |  |  | Panchpokhari Thangpal | 6
16732 | Sindhupalchok | ThampalChhap | 3 | ARSOW-TGH | ARSOW-N | FDF | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 100 | 20 | 2017-08-01 |  |  | Panchpokhari Thangpal | 6
16733 | Sindhupalchok | ThampalChhap |  | ARSOW-TGH | ARSOW-N | FDF | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 | 2018-01-25 |  |  | Panchpokhari Thangpal | 6
16734 | Sindhupalchok | Thanpalkot | 1 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 19 | 19 | 2016-06-23 | 2016-09-21 | 4 lots in VDC in different wards from 23-29-Jun-2016, 11-17-Aug-2016, 26-31-Aug-16, 15-21-Sep-2016 (verified with Karna sir on 18th April 2017 | Panchpokhari Thangpal | 4
16735 | Sindhupalchok | Thanpalkot | 2 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 22 | 22 | 2016-06-23 | 2016-09-21 | 4 lots in VDC in different wards from 23-29-Jun-2016, 11-17-Aug-2016, 26-31-Aug-16, 15-21-Sep-2016 (verified with Karna sir on 18th April 2017 | Panchpokhari Thangpal | 4
16736 | Sindhupalchok | Thanpalkot | 3 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 6 | 6 | 2016-06-23 | 2016-09-21 | 4 lots in VDC in different wards from 23-29-Jun-2016, 11-17-Aug-2016, 26-31-Aug-16, 15-21-Sep-2016 (verified with Karna sir on 18th April 2017 | Panchpokhari Thangpal | 4
16737 | Sindhupalchok | Thanpalkot | 4 | ARSOW-TGH | ARSOW-N | FDF | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Planned | 1 | 0 | 2016-08-01 |  |  | Panchpokhari Thangpal | 4
16738 | Sindhupalchok | Thanpalkot | 4 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 16 | 16 | 2016-06-23 | 2016-09-21 | 4 lots in VDC in different wards from 23-29-Jun-2016, 11-17-Aug-2016, 26-31-Aug-16, 15-21-Sep-2016 (verified with Karna sir on 18th April 2017 | Panchpokhari Thangpal | 4
16739 | Sindhupalchok | Thanpalkot | 4 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Carpenter | Carpenter training | # of trainees | Yes | Planned | 26 | 0 | 2017-06-15 |  |  | Panchpokhari Thangpal | 4
16740 | Sindhupalchok | Thanpalkot | 4 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Bar bender | Welder Training | # of trainees | Yes | Planned | 13 | 0 | 2017-10-15 |  |  | Panchpokhari Thangpal | 4
16741 | Sindhupalchok | Thanpalkot | 4 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Plumber | Plumber training | # of trainees | Yes | Planned | 13 | 0 | 2017-11-15 |  |  | Panchpokhari Thangpal | 4
16742 | Sindhupalchok | Thanpalkot | 4 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Electrician | Electrician Training | # of trainees | Yes | Planned | 13 | 0 | 2017-11-15 |  |  | Panchpokhari Thangpal | 4
16743 | Sindhupalchok | Thanpalkot | 5 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 9 | 9 | 2016-06-23 | 2016-09-21 | 4 lots in VDC in different wards from 23-29-Jun-2016, 11-17-Aug-2016, 26-31-Aug-16, 15-21-Sep-2016 (verified with Karna sir on 18th April 2017 | Panchpokhari Thangpal | 4
16744 | Sindhupalchok | Thanpalkot | 6 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 13 | 13 | 2016-06-23 | 2016-09-21 | 4 lots in VDC in different wards from 23-29-Jun-2016, 11-17-Aug-2016, 26-31-Aug-16, 15-21-Sep-2016 (verified with Karna sir on 18th April 2017 | Panchpokhari Thangpal | 4
16745 | Sindhupalchok | Thanpalkot | 7 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 11 | 11 | 2016-06-23 | 2016-09-21 | 4 lots in VDC in different wards from 23-29-Jun-2016, 11-17-Aug-2016, 26-31-Aug-16, 15-21-Sep-2016 (verified with Karna sir on 18th April 2017 | Panchpokhari Thangpal | 4
16746 | Sindhupalchok | Thanpalkot | 8 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 12 | 12 | 2016-06-23 | 2016-09-21 | 4 lots in VDC in different wards from 23-29-Jun-2016, 11-17-Aug-2016, 26-31-Aug-16, 15-21-Sep-2016 (verified with Karna sir on 18th April 2017 | Panchpokhari Thangpal | 4
16747 | Sindhupalchok | Thanpalkot | 9 | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days masons training in 4 lots | # of trainees | Yes | Completed | 6 | 6 | 2016-06-23 | 2016-09-21 | 4 lots in VDC in different wards from 23-29-Jun-2016, 11-17-Aug-2016, 26-31-Aug-16, 15-21-Sep-2016 (verified with Karna sir on 18th April 2017 | Panchpokhari Thangpal | 4
16748 | Sindhupalchok | Thanpalkot |  | ARSOW-TGH | ARSOW-N | FDF | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Ongoing | 862 | 245 | 2017-03-21 |  | Support based on the NRA policy | Panchpokhari Thangpal | 4
16749 | Sindhupalchok | Thanpalkot |  | ARSOW-TGH | ARSOW-N | FDF | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-02-01 | 2017-06-01 | Support based on the NRA policy | Panchpokhari Thangpal | 4
16750 | Sindhupalchok | Thanpalkot |  | ARSOW-TGH | ARSOW-N | FDF | Training | ToT | Skilled masons |  | # of trainees | Yes | Ongoing | 60 | 30 | 2016-04-01 | 2016-12-30 |  | Panchpokhari Thangpal | 4
16751 | Sindhupalchok | Thanpalkot | 6 | ARSOW-TGH | ARSOW-N | FDF | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 150 | 130 | 2017-08-01 |  |  | Panchpokhari Thangpal | 4
16752 | Sindhupalchok | Thanpalkot | 7 | ARSOW-TGH | ARSOW-N | FDF | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 150 | 125 | 2017-08-01 |  |  | Panchpokhari Thangpal | 4
16753 | Sindhupalchok | Thanpalkot |  | ARSOW-TGH | ARSOW-N | FDF | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 | 2018-01-25 |  |  | Panchpokhari Thangpal | 4
16754 | Sindhupalchok | Motang |  | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Carpenter |  | # of trainees | Yes | Planned | 10 | 0 | 2018-01-15 |  |  | #N/A | #N/A
16755 | Sindhupalchok | Motang |  | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Plumber |  | # of trainees | Yes | Planned | 5 | 0 | 2018-01-15 |  |  | #N/A | #N/A
16756 | Sindhupalchok | Motang |  | ARSOW-TGH | ARSOW-N | FDF | Training | Short training | Electrician |  | # of trainees | Yes | Planned | 5 | 0 | 2018-01-15 |  |  | #N/A | #N/A
16757 | Sindhupalchok | Motang |  | ARSOW-TGH | ARSOW-N | FDF | Training | Other trainings | Other trainings (specify in Activity Detail) | Welder Training | # of trainees |  | Planned | 5 | 0 | 2018-01-15 |  |  | #N/A | #N/A
16758 | Sindhupalchok | Bahrabise |  | BC | ARSOW-N | WVIN | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2017-11-01 |  |  | Barhabise | 4
16759 | Sindhupalchok | Chautara N.P. |  | BC | ARSOW-N | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 1456 | 1456 | 2016-05-30 | 2016-06-03 | 10 Key Messages | Chautara Sangachokgadhi | 7
16760 | Sindhupalchok | Chautara N.P. |  | BC | ARSOW-N | WVIN | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2017-11-01 |  |  | Chautara Sangachokgadhi | 7
16761 | Sindhupalchok | Haibung |  | BC | ARSOW-N | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 1058 | 1058 | 2016-05-16 | 2016-05-20 | 10 Key Messages | Melamchi | 3
16762 | Sindhupalchok | Jalbire |  | BC | ARSOW-N | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 1049 | 1049 | 2016-05-21 | 2016-05-25 | 11 Key Messages | Balefi | 2
16763 | Sindhupalchok | Melamchi N.P. |  | BC | ARSOW-N | WVIN | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2017-11-01 |  |  | Melamchi | 13
16764 | Sindhupalchok | Sangachok | 1 | BC | ARSOW-N | WVIN | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 404 | 118 | 2016-08-01 |  | 3 Technical Support Centers are in ward no. 4,5&8 | Chautara Sangachokgadhi | 10
16765 | Sindhupalchok | Sangachok | 1 | BC | ARSOW-N | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-01 | 2016-06-07 |  | Chautara Sangachokgadhi | 10
16766 | Sindhupalchok | Sangachok | 1 | BC | ARSOW-N | WVIN | Others | Others | (Please specify in Activity Detail) | Design and drawing support through resource center | # of trainees | Yes | Ongoing | 100 | 90 |  |  |  | Chautara Sangachokgadhi | 10
16767 | Sindhupalchok | Sangachok | 2 | BC | ARSOW-N | WVIN | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 217 | 131 | 2016-08-01 |  | 3 Technical Support Centers are in ward no. 4,5&8 | Chautara Sangachokgadhi | 10
16768 | Sindhupalchok | Sangachok | 2 | BC | ARSOW-N | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 |  |  |  | Chautara Sangachokgadhi | 10
16769 | Sindhupalchok | Sangachok | 2 | BC | ARSOW-N | WVIN | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Ongoing | 150 | 121 |  |  |  | Chautara Sangachokgadhi | 10
16770 | Sindhupalchok | Sangachok | 3 | BC | ARSOW-N | WVIN | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Assisted for drawing approval and Technical assistance | # of households supported | Yes | Ongoing | 225 | 152 |  |  | 3 Technical Support Centers are in ward no. 4,5&8 | Chautara Sangachokgadhi | 12
16771 | Sindhupalchok | Sangachok | 3 | BC | ARSOW-N | WVIN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0 | 2017-03-25 |  |  | Chautara Sangachokgadhi | 12
16772 | Sindhupalchok | Sangachok | 3 | BC | ARSOW-N | WVIN | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Ongoing | 150 | 125 |  |  |  | Chautara Sangachokgadhi | 12
16773 | Sindhupalchok | Sangachok | 4 | BC | ARSOW-N | WVIN | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Assisted for drawing approval and Technical assistance | # of households supported | Yes | Ongoing | 242 | 139 |  |  | 3 Technical Support Centers are in ward no. 4,5&8 | Chautara Sangachokgadhi | 12
16774 | Sindhupalchok | Sangachok | 4 | BC | ARSOW-N | WVIN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0 | 2017-03-25 |  |  | Chautara Sangachokgadhi | 12
16775 | Sindhupalchok | Sangachok | 4 | BC | ARSOW-N | WVIN | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Ongoing | 150 | 112 |  |  |  | Chautara Sangachokgadhi | 12
16776 | Sindhupalchok | Sangachok | 5 | BC | ARSOW-N | WVIN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 | 2017-03-10 |  |  | Chautara Sangachokgadhi | 11
16777 | Sindhupalchok | Sangachok | 5 | BC | ARSOW-N | WVIN | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Assisted for drawing approval and Technical assistance | # of households supported | Yes | Ongoing | 233 | 169 |  |  | 3 Technical Support Centers are in ward no. 4,5&8 | Chautara Sangachokgadhi | 11
16778 | Sindhupalchok | Sangachok | 5 | BC | ARSOW-N | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 17 |  |  |  | Chautara Sangachokgadhi | 11
16779 | Sindhupalchok | Sangachok | 5 | BC | ARSOW-N | WVIN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 136 | 0 | 2017-03-25 |  |  | Chautara Sangachokgadhi | 11
16780 | Sindhupalchok | Sangachok | 5 | BC | ARSOW-N | WVIN | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 100 | 55 |  |  |  | Chautara Sangachokgadhi | 11
16781 | Sindhupalchok | Sangachok | 5 | BC | ARSOW-N | WVIN | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Ongoing | 100 | 74 |  |  |  | Chautara Sangachokgadhi | 11
16782 | Sindhupalchok | Sangachok | 6 | BC | ARSOW-N | WVIN | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Assisted for drawing approval and Technical assistance | # of households supported | Yes | Ongoing | 196 | 133 |  |  | 3 Technical Support Centers are in ward no. 4,5&8 | Chautara Sangachokgadhi | 12
16783 | Sindhupalchok | Sangachok | 6 | BC | ARSOW-N | WVIN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0 | 2017-03-25 |  |  | Chautara Sangachokgadhi | 12
16784 | Sindhupalchok | Sangachok | 6 | BC | ARSOW-N | WVIN | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Ongoing | 100 | 84 |  |  |  | Chautara Sangachokgadhi | 12
16785 | Sindhupalchok | Sangachok | 7 | BC | ARSOW-N | WVIN | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Assisted for drawing approval and Technical assistance | # of households supported | Yes | Ongoing | 180 | 124 |  |  | 3 Technical Support Centers are in ward no. 4,5&8 | Chautara Sangachokgadhi | 10
16786 | Sindhupalchok | Sangachok | 7 | BC | ARSOW-N | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 |  |  |  | Chautara Sangachokgadhi | 10
16787 | Sindhupalchok | Sangachok | 7 | BC | ARSOW-N | WVIN | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Ongoing | 150 | 103 |  |  |  | Chautara Sangachokgadhi | 10
16788 | Sindhupalchok | Sangachok | 8 | BC | ARSOW-N | WVIN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 2 | 1 | 2016-03-29 | 2017-02-28 |  | Chautara Sangachokgadhi | 11
16789 | Sindhupalchok | Sangachok | 8 | BC | ARSOW-N | WVIN | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Assisted for drawing approval and Technical assistance | # of households supported | Yes | Ongoing | 281 | 136 |  |  | 3 Technical Support Centers are in ward no. 4,5&8 | Chautara Sangachokgadhi | 11
16790 | Sindhupalchok | Sangachok | 8 | BC | ARSOW-N | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Chautara Sangachokgadhi | 11
16791 | Sindhupalchok | Sangachok | 8 | BC | ARSOW-N | WVIN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0 | 2017-03-25 |  |  | Chautara Sangachokgadhi | 11
16792 | Sindhupalchok | Sangachok | 8 | BC | ARSOW-N | WVIN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 143 | 0 | 2017-03-25 |  |  | Chautara Sangachokgadhi | 11
16793 | Sindhupalchok | Sangachok | 8 | BC | ARSOW-N | WVIN | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 50 | 10 |  |  |  | Chautara Sangachokgadhi | 11
16794 | Sindhupalchok | Sangachok | 8 | BC | ARSOW-N | WVIN | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Ongoing | 100 | 77 |  |  |  | Chautara Sangachokgadhi | 11
16795 | Sindhupalchok | Sangachok | 9 | BC | ARSOW-N | WVIN | Technical Assistance | Demonstration Construction | House | Assisted for drawing approval and Technical assistance | # of constructions | Yes | Completed | 1 | 1 | 2017-01-01 | 2017-04-19 |  | Chautara Sangachokgadhi | 11
16796 | Sindhupalchok | Sangachok | 9 | BC | ARSOW-N | WVIN | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Assisted for drawing approval and Technical assistance | # of households supported | Yes | Ongoing | 386 | 336 | 2016-08-01 |  | 3 Technical Support Centers are in ward no. 4,5&8 | Chautara Sangachokgadhi | 11
16797 | Sindhupalchok | Sangachok | 9 | BC | ARSOW-N | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Chautara Sangachokgadhi | 11
16798 | Sindhupalchok | Sangachok | 9 | BC | ARSOW-N | WVIN | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 150 | 62 |  |  |  | Chautara Sangachokgadhi | 11
16799 | Sindhupalchok | Sangachok | 9 | BC | ARSOW-N | WVIN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 28 | 0 | 2017-03-25 |  |  | Chautara Sangachokgadhi | 11
16800 | Sindhupalchok | Sangachok | 9 | BC | ARSOW-N | WVIN | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Ongoing | 200 | 148 |  |  |  | Chautara Sangachokgadhi | 11
16801 | Sindhupalchok | Sangachok | 5,8,9 | BC | ARSOW-N | WVIN | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Ongoing | 307 | 198 | 2016-08-01 |  |  | Chautara Sangachokgadhi | 12
16802 | Sindhupalchok | Sangachok |  | BC | ARSOW-N | BC | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 440 | 1866 | 2016-08-08 | 2016-09-07 | 10 Key Messages | Chautara Sangachokgadhi | 12
16803 | Sindhupalchok | Sangachok |  | BC | ARSOW-N | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 1530 | 1530 | 2016-03-29 | 2016-07-04 | 10 Key Messages | Chautara Sangachokgadhi | 12
16804 | Sindhupalchok | Sangachok |  | BC | ARSOW-N | BC | Training | Other trainings | Other trainings (specify in Activity Detail) | social mobilizer training | # of trainees | Yes | Completed | 20 | 20 | 2016-08-08 | 2016-09-07 | Community Ambassador skill development on BBS | Chautara Sangachokgadhi | 12
16805 | Sindhupalchok | Sangachok |  | BC | ARSOW-N | WVIN | Training | Other trainings | Other trainings (specify in Activity Detail) | Training on how to build house using block | # of trainees | Yes | Ongoing | 5 | 5 | 2017-02-20 |  |  | Chautara Sangachokgadhi | 12
16806 | Sindhupalchok | Sangachok |  | ARSOW-TGH | ARSOW-N | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Repair and retrofit | Retrofitting technical support by BC | # of households | Yes | Ongoing | 35 | 20 | 2017-10-01 |  |  | Chautara Sangachokgadhi | 12
16807 | Sindhupalchok | Atarpur | 1 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 31 | 31 | 2017-07-10 | 2017-07-10 |  | Lisangkhu Pakhar | 4
16808 | Sindhupalchok | Atarpur | 2 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 17 | 17 | 2017-07-10 | 2017-07-10 |  | Lisangkhu Pakhar | 4
16809 | Sindhupalchok | Atarpur | 3 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 20 | 20 | 2017-07-10 | 2017-07-10 |  | Lisangkhu Pakhar | 4
16810 | Sindhupalchok | Atarpur | 4 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 21 | 21 | 2017-07-10 | 2017-07-10 |  | Lisangkhu Pakhar | 4
16811 | Sindhupalchok | Atarpur | 5 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 17 | 17 | 2017-07-10 | 2017-07-10 |  | Lisangkhu Pakhar | 4
16812 | Sindhupalchok | Atarpur | 6 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 7 | 7 | 2017-07-10 | 2017-07-10 |  | Lisangkhu Pakhar | 4
16813 | Sindhupalchok | Atarpur | 7 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 22 | 22 | 2017-07-10 | 2017-07-10 |  | Lisangkhu Pakhar | 4
16814 | Sindhupalchok | Atarpur | 8 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 40 | 40 | 2017-07-10 | 2017-07-10 |  | Lisangkhu Pakhar | 4
16815 | Sindhupalchok | Atarpur | 9 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 50 | 50 | 2017-07-10 | 2017-07-10 |  | Lisangkhu Pakhar | 5
16816 | Sindhupalchok | Atarpur | All | CA | CA | CA | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Completed | 113 | 113 | 2016-01-10 | 2016-04-30 |  | Lisangkhu Pakhar | 4
16817 | Sindhupalchok | Atarpur | All | CA | CA | CA | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2016-01-10 | 2016-08-30 |  | Lisangkhu Pakhar | 4
16818 | Sindhupalchok | Atarpur | All | CA | CA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 113 | 113 | 2016-01-10 | 2016-06-15 |  | Lisangkhu Pakhar | 4
16819 | Sindhupalchok | Atarpur | All | CA | CA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 50 | 68 | 2016-01-10 | 2016-06-15 |  | Lisangkhu Pakhar | 4
16820 | Sindhupalchok | Pagretar | 1 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 32 | 32 | 2017-07-10 | 2017-07-10 |  | Sunkoshi | 7
16821 | Sindhupalchok | Pagretar | 2 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 53 | 53 | 2017-07-10 | 2017-07-10 |  | Sunkoshi | 7
16822 | Sindhupalchok | Pagretar | 2 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 12 | 12 | 2017-07-10 | 2017-07-10 |  | Sunkoshi | 7
16823 | Sindhupalchok | Pagretar | 3 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 70 | 70 | 2017-07-10 | 2017-07-10 |  | Sunkoshi | 7
16824 | Sindhupalchok | Pagretar | 3 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 27 | 27 | 2017-07-10 | 2017-07-10 |  | Sunkoshi | 7
16825 | Sindhupalchok | Pagretar | 4 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 50 | 50 | 2017-07-10 | 2017-07-10 |  | Sunkoshi | 7
16826 | Sindhupalchok | Pagretar | 4 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 21 | 21 | 2017-07-10 | 2017-07-10 |  | Sunkoshi | 7
16827 | Sindhupalchok | Pagretar | 5 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 60 | 60 | 2017-07-10 | 2017-07-10 |  | Sunkoshi | 7
16828 | Sindhupalchok | Pagretar | 5 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 20 | 20 | 2017-07-10 | 2017-07-10 |  | Sunkoshi | 7
16829 | Sindhupalchok | Pagretar | 6 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 41 | 41 | 2017-07-10 | 2017-07-10 |  | Sunkoshi | 7
16830 | Sindhupalchok | Pagretar | 6 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 28 | 28 | 2017-07-10 | 2017-07-10 |  | Sunkoshi | 7
16831 | Sindhupalchok | Pagretar | 7 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 55 | 55 | 2017-07-10 | 2017-07-10 |  | Sunkoshi | 7
16832 | Sindhupalchok | Pagretar | 7 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 12 | 12 | 2017-07-10 | 2017-07-10 |  | Sunkoshi | 7
16833 | Sindhupalchok | Pagretar | 8 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 85 | 85 | 2017-07-10 | 2017-07-10 |  | Sunkoshi | 7
16834 | Sindhupalchok | Pagretar | 8 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 37 | 37 | 2017-07-10 | 2017-07-10 |  | Sunkoshi | 7
16835 | Sindhupalchok | Pagretar | 9 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 41 | 41 | 2017-07-10 | 2017-07-10 |  | Sunkoshi | 7
16836 | Sindhupalchok | Pagretar | 9 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 34 | 34 | 2017-07-10 | 2017-07-10 |  | Sunkoshi | 7
16837 | Sindhupalchok | Pagretar | All | CA | CA | CA | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Completed | 650 | 650 | 2016-01-10 | 2016-04-30 |  | Sunkoshi | 7
16838 | Sindhupalchok | Pagretar | All | CA | CA | CA | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 4 | 4 | 2016-01-10 | 2016-08-30 |  | Sunkoshi | 7
16839 | Sindhupalchok | Pagretar | All | CA | CA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 650 | 650 | 2016-01-10 | 2016-06-15 |  | Sunkoshi | 7
16840 | Sindhupalchok | Pagretar | All | CA | CA | CA | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 117 | 117 | 2016-01-10 | 2016-06-15 |  | Sunkoshi | 7
16841 | Sindhupalchok | Tekanpur | 1 | CA | Janahit | CA | Technical Assistance | Community reconstruction orientation | 1 session | Oriented 10 Key Messages | # of participants | Yes | Completed | 20 | 20 | 2017-07-10 | 2017-07-10 |  | Tripura Sundari | 6
16842 | Sindhupalchok | Tekanpur | All | CA | CA | CA | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 7 | 7 | 2016-01-10 | 2016-06-15 |  | Tripura Sundari | 6
16843 | Sindhupalchok | Banskharka | 1 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-06-10 |  |  | Panchpokhari Thangpal | 1
16844 | Sindhupalchok | Banskharka | 1 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 19 | 2016-07-06 | 2016-07-06 |  | Panchpokhari Thangpal | 1
16845 | Sindhupalchok | Banskharka | 1 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 21 | 21 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 1
16846 | Sindhupalchok | Banskharka | 1 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 40 | 40 | 2016-08-10 | 2016-11-15 |  | Panchpokhari Thangpal | 1
16847 | Sindhupalchok | Banskharka | 1 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-10 | 2016-06-24 | 2 events | Panchpokhari Thangpal | 1
16848 | Sindhupalchok | Banskharka | 2 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 6 | 6 | 2016-06-10 |  |  | Panchpokhari Thangpal | 1
16849 | Sindhupalchok | Banskharka | 2 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 25 | 2016-07-08 | 2016-07-08 |  | Panchpokhari Thangpal | 1
16850 | Sindhupalchok | Banskharka | 2 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 24 | 30 |  |  | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 1
16851 | Sindhupalchok | Banskharka | 2 | CARE-N | CSRC | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 1 | 1 | 2016-12-02 |  |  | Panchpokhari Thangpal | 1
16852 | Sindhupalchok | Banskharka | 2 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 40 | 40 |  | 2017-11-15 |  | Panchpokhari Thangpal | 1
16853 | Sindhupalchok | Banskharka | 2 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-10 | 2016-06-24 |  | Panchpokhari Thangpal | 1
16854 | Sindhupalchok | Banskharka | 3 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 7 | 7 | 2016-06-10 | 2016-06-24 |  | Panchpokhari Thangpal | 1
16855 | Sindhupalchok | Banskharka | 3 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 28 | 2016-08-02 | 2016-08-02 |  | Panchpokhari Thangpal | 1
16856 | Sindhupalchok | Banskharka | 3 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 30 | 25 |  |  | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 1
16857 | Sindhupalchok | Banskharka | 3 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 40 | 31 |  |  |  | Panchpokhari Thangpal | 1
16858 | Sindhupalchok | Banskharka | 3 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-10 | 2016-06-24 |  | Panchpokhari Thangpal | 1
16859 | Sindhupalchok | Banskharka | 4 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 6 | 6 | 2016-06-10 |  |  | Panchpokhari Thangpal | 1
16860 | Sindhupalchok | Banskharka | 4 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 43 | 2016-07-20 | 2016-07-20 |  | Panchpokhari Thangpal | 1
16861 | Sindhupalchok | Banskharka | 4 | CARE-N | CSRC | ADH | Technical Assistance | Demonstration Construction | House | One model house for one VDC | # of constructions | Yes | Completed | 1 | 1 | 2017-01-05 | 2017-04-15 |  | Panchpokhari Thangpal | 1
16862 | Sindhupalchok | Banskharka | 4 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 42 | 36 |  |  | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 1
16863 | Sindhupalchok | Banskharka | 4 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 40 | 45 |  |  |  | Panchpokhari Thangpal | 1
16864 | Sindhupalchok | Banskharka | 4 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-10 | 2016-06-24 |  | Panchpokhari Thangpal | 1
16865 | Sindhupalchok | Banskharka | 5 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 | 2016-06-10 | 2016-06-24 |  | Panchpokhari Thangpal | 1
16866 | Sindhupalchok | Banskharka | 5 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 83 | 2016-06-05 | 2016-06-05 |  | Panchpokhari Thangpal | 1
16867 | Sindhupalchok | Banskharka | 5 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 138 | 105 |  |  | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 1
16868 | Sindhupalchok | Banskharka | 5 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 40 | 50 |  |  |  | Panchpokhari Thangpal | 1
16869 | Sindhupalchok | Banskharka | 5 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-10 | 2016-06-24 |  | Panchpokhari Thangpal | 1
16870 | Sindhupalchok | Banskharka | 6 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 11 | 11 | 2016-06-10 |  |  | Panchpokhari Thangpal | 1
16871 | Sindhupalchok | Banskharka | 6 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 72 | 2016-06-05 | 2016-06-05 |  | Panchpokhari Thangpal | 1
16872 | Sindhupalchok | Banskharka | 6 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 150 | 160 |  |  | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 1
16873 | Sindhupalchok | Banskharka | 6 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 40 | 22 |  |  |  | Panchpokhari Thangpal | 1
16874 | Sindhupalchok | Banskharka | 6 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-06-10 | 2016-06-24 |  | Panchpokhari Thangpal | 1
16875 | Sindhupalchok | Banskharka | 7 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-06-10 |  |  | Panchpokhari Thangpal | 1
16876 | Sindhupalchok | Banskharka | 7 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 23 | 2016-06-04 | 2016-06-04 |  | Panchpokhari Thangpal | 1
16877 | Sindhupalchok | Banskharka | 7 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 31 | 33 |  |  | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 1
16878 | Sindhupalchok | Banskharka | 7 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 40 | 32 |  |  |  | Panchpokhari Thangpal | 1
16879 | Sindhupalchok | Banskharka | 7 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-10 | 2016-06-24 |  | Panchpokhari Thangpal | 1
16880 | Sindhupalchok | Banskharka | 8 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 | 2016-06-10 |  |  | Panchpokhari Thangpal | 1
16881 | Sindhupalchok | Banskharka | 8 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 79 | 2016-06-04 | 2016-06-04 |  | Panchpokhari Thangpal | 1
16882 | Sindhupalchok | Banskharka | 8 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 90 | 88 |  |  | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 1
16883 | Sindhupalchok | Banskharka | 8 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 40 | 63 |  |  |  | Panchpokhari Thangpal | 1
16884 | Sindhupalchok | Banskharka | 8 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-10 | 2016-06-24 |  | Panchpokhari Thangpal | 1
16885 | Sindhupalchok | Banskharka | 9 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-06-10 |  |  | Panchpokhari Thangpal | 1
16886 | Sindhupalchok | Banskharka | 9 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 95 | 2016-06-04 | 2016-06-04 |  | Panchpokhari Thangpal | 1
16887 | Sindhupalchok | Banskharka | 9 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 123 | 88 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 1
16888 | Sindhupalchok | Banskharka | 9 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 40 | 15 |  | 2017-11-15 |  | Panchpokhari Thangpal | 1
16889 | Sindhupalchok | Banskharka | 9 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-10 | 2016-06-24 |  | Panchpokhari Thangpal | 1
16890 | Sindhupalchok | Baruwa | 1 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 10 | 2016-05-28 | 2016-06-25 |  | Panchpokhari Thangpal | 2
16891 | Sindhupalchok | Baruwa | 1 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 76 | 2016-06-10 | 2016-06-10 |  | Panchpokhari Thangpal | 2
16892 | Sindhupalchok | Baruwa | 1 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 101 | 85 |  | 2017-11-15 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 2
16893 | Sindhupalchok | Baruwa | 1 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 71 | 2016-08-01 | 2017-12-15 |  | Panchpokhari Thangpal | 2
16894 | Sindhupalchok | Baruwa | 1 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-05-28 | 2016-06-25 |  | Panchpokhari Thangpal | 2
16895 | Sindhupalchok | Baruwa | 2 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | 2 lots trainings in same VDCs | # of kits | Yes | Completed | 3 | 3 | 2016-05-28 | 2016-06-25 |  | Panchpokhari Thangpal | 2
16896 | Sindhupalchok | Baruwa | 2 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 50 | 2016-07-06 | 2016-07-06 |  | Panchpokhari Thangpal | 2
16897 | Sindhupalchok | Baruwa | 2 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 35 | 20 |  | 2016-06-25 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 2
16898 | Sindhupalchok | Baruwa | 2 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 45 | 14 | 2017-11-15 |  |  | Panchpokhari Thangpal | 2
16899 | Sindhupalchok | Baruwa | 2 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-28 | 2016-06-25 |  | Panchpokhari Thangpal | 2
16900 | Sindhupalchok | Baruwa | 3 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | 2 lots trainings in same VDCs | # of kits | Yes | Completed | 13 | 13 | 2016-05-28 |  |  | Panchpokhari Thangpal | 2
16901 | Sindhupalchok | Baruwa | 3 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 74 | 2016-06-04 | 2016-06-04 |  | Panchpokhari Thangpal | 2
16902 | Sindhupalchok | Baruwa | 3 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 81 | 81 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 2
16903 | Sindhupalchok | Baruwa | 3 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 45 | 65 |  | 2017-11-15 |  | Panchpokhari Thangpal | 2
16904 | Sindhupalchok | Baruwa | 3 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-05-28 | 2016-06-25 |  | Panchpokhari Thangpal | 2
16905 | Sindhupalchok | Baruwa | 4 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | 2 lots trainings in same VDCs | # of kits | Yes | Completed | 5 | 5 | 2016-05-28 |  |  | Panchpokhari Thangpal | 2
16906 | Sindhupalchok | Baruwa | 4 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 36 | 2016-06-04 | 2016-06-04 |  | Panchpokhari Thangpal | 2
16907 | Sindhupalchok | Baruwa | 4 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 39 | 42 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 2
16908 | Sindhupalchok | Baruwa | 4 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 45 | 32 |  | 2017-11-15 |  | Panchpokhari Thangpal | 2
16909 | Sindhupalchok | Baruwa | 4 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-28 | 2016-06-25 |  | Panchpokhari Thangpal | 2
16910 | Sindhupalchok | Baruwa | 5 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | 2 lots trainings in same VDCs | # of kits | Yes | Completed | 13 | 13 | 2016-05-28 | 2017-03-23 |  | Panchpokhari Thangpal | 2
16911 | Sindhupalchok | Baruwa | 5 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 36 | 2016-07-05 | 2016-07-05 |  | Panchpokhari Thangpal | 2
16912 | Sindhupalchok | Baruwa | 5 | CARE-N | CSRC | ADH | Technical Assistance | Demonstration Construction | House | 2 lots trainings in same VDCs | # of constructions | Yes | Completed | 2 | 2 | 2017-01-13 | 2017-04-30 |  | Panchpokhari Thangpal | 2
16913 | Sindhupalchok | Baruwa | 5 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 51 | 46 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 2
16914 | Sindhupalchok | Baruwa | 5 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 45 | 27 |  | 2017-11-15 |  | Panchpokhari Thangpal | 2
16915 | Sindhupalchok | Baruwa | 5 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots trainings in same VDCs | # of trainees | Yes | Completed | 13 | 13 | 2016-05-28 | 2017-03-23 | 1st lot (28-May-3 Jun-16) 2nd (17-23-Mar-17) | Panchpokhari Thangpal | 2
16916 | Sindhupalchok | Baruwa | 6 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | 2 lots trainings in same VDCs | # of kits | Yes | Completed | 4 | 4 | 2016-05-28 |  |  | Panchpokhari Thangpal | 2
16917 | Sindhupalchok | Baruwa | 6 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 26 | 2016-07-04 | 2016-07-04 |  | Panchpokhari Thangpal | 2
16918 | Sindhupalchok | Baruwa | 6 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 57 | 17 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 2
16919 | Sindhupalchok | Baruwa | 6 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 45 | 18 |  |  |  | Panchpokhari Thangpal | 2
16920 | Sindhupalchok | Baruwa | 6 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots trainings in same VDCs | # of trainees | Yes | Completed | 4 | 4 | 2016-05-28 | 2017-03-23 | 1st lot (28-May-3 Jun-16) 2nd (17-23-Mar-17) | Panchpokhari Thangpal | 2
16921 | Sindhupalchok | Baruwa | 7 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | 2 lots trainings in same VDCs | # of kits | Yes | Completed | 11 | 11 | 2016-05-28 | 2017-03-23 | 1st lot (28-May-3 Jun-16) 2nd (17-23-Mar-17) | Panchpokhari Thangpal | 2
16922 | Sindhupalchok | Baruwa | 7 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 70 | 2016-07-11 | 2016-07-11 |  | Panchpokhari Thangpal | 2
16923 | Sindhupalchok | Baruwa | 7 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 78 | 73 |  | 2018-04-15 |  | Panchpokhari Thangpal | 2
16924 | Sindhupalchok | Baruwa | 7 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 45 | 77 |  | 2017-11-15 |  | Panchpokhari Thangpal | 2
16925 | Sindhupalchok | Baruwa | 7 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots trainings in same VDCs | # of trainees | Yes | Completed | 11 | 11 | 2016-05-28 | 2017-03-23 | 1st lot (28-May-3 Jun-16) 2nd (17-23-Mar-17) | Panchpokhari Thangpal | 2
16926 | Sindhupalchok | Baruwa | 8 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | 2 lots trainings in same VDCs | # of kits | Yes | Completed | 12 | 12 | 2016-05-28 | 2017-03-23 | 1st lot (28-May-3 Jun-16) 2nd (17-23-Mar-17) | Panchpokhari Thangpal | 2
16927 | Sindhupalchok | Baruwa | 8 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 53 | 2016-07-09 | 2016-07-09 |  | Panchpokhari Thangpal | 2
16928 | Sindhupalchok | Baruwa | 8 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 81 | 50 |  | 2018-03-20 |  | Panchpokhari Thangpal | 2
16929 | Sindhupalchok | Baruwa | 8 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 67 |  | 2017-11-15 |  | Panchpokhari Thangpal | 2
16930 | Sindhupalchok | Baruwa | 8 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots trainings in same VDCs | # of trainees | Yes | Completed | 12 | 12 | 2016-05-28 | 2017-03-23 | 1st lot (28-May-3 Jun-16) 2nd (17-23-Mar-17) | Panchpokhari Thangpal | 2
16931 | Sindhupalchok | Baruwa | 9 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 48 | 2016-07-13 | 2016-07-13 |  | Panchpokhari Thangpal | 2
16932 | Sindhupalchok | Baruwa | 9 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 47 | 37 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 2
16933 | Sindhupalchok | Baruwa | 9 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 45 | 52 |  | 2017-11-15 |  | Panchpokhari Thangpal | 2
16934 | Sindhupalchok | Baruwa | 9 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2017-03-17 | 2017-03-23 |  | Panchpokhari Thangpal | 2
16935 | Sindhupalchok | Baruwa |  | CARE-N | CSRC | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 1 | 1 | 2017-11-01 |  |  | Panchpokhari Thangpal | 2
16936 | Sindhupalchok | Dubachour | 1 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-06-12 | 2016-06-26 |  | Melamchi | 7
16937 | Sindhupalchok | Dubachour | 1 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 97 | 2016-06-05 | 2016-06-05 |  | Melamchi | 7
16938 | Sindhupalchok | Dubachour | 1 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 127 | 34 | 2018-02-10 |  | Marked as 1 to indicate the activity is going on | Melamchi | 7
16939 | Sindhupalchok | Dubachour | 1 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 50 | 126 | 2016-08-08 | 2016-12-15 |  | Melamchi | 7
16940 | Sindhupalchok | Dubachour | 1 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-12 | 2016-06-26 |  | Melamchi | 7
16941 | Sindhupalchok | Dubachour | 2 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-06-12 | 2016-06-26 |  | Melamchi | 7
16942 | Sindhupalchok | Dubachour | 2 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 77 | 2016-06-05 | 2016-06-05 |  | Melamchi | 7
16943 | Sindhupalchok | Dubachour | 2 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 112 | 93 |  | 2018-01-25 | Marked as 1 to indicate the activity is going on | Melamchi | 7
16944 | Sindhupalchok | Dubachour | 2 | CARE-N | CSRC | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 1 | 1 | 2016-11-16 |  |  | Melamchi | 7
16945 | Sindhupalchok | Dubachour | 2 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 50 | 58 |  | 2018-11-15 |  | Melamchi | 7
16946 | Sindhupalchok | Dubachour | 2 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots trainings in same VDCs | # of trainees | Yes | Completed | 4 | 4 | 2016-06-12 | 2017-03-23 | 1st lot (12-26-Jun-16) 2nd (17-23-Mar-17) | Melamchi | 7
16947 | Sindhupalchok | Dubachour | 3 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 11 | 11 | 2016-06-12 | 2017-03-23 | 1st lot (12-26-Jun-16) 2nd (17-23-Mar-17) | Melamchi | 7
16948 | Sindhupalchok | Dubachour | 3 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 70 | 2016-07-06 | 2016-07-06 |  | Melamchi | 7
16949 | Sindhupalchok | Dubachour | 3 | CARE-N | CSRC | ADH | Technical Assistance | Demonstration Construction | House | One model house for one VDC | # of constructions | Yes | Completed | 1 | 1 | 2017-01-03 | 2017-04-30 | 1st lot (12-26-Jun-16) 2nd (17-23-Mar-17) | Melamchi | 7
16950 | Sindhupalchok | Dubachour | 3 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 211 | 195 |  | 2018-01-25 | 1st lot (12-26-Jun-16) 2nd (17-23-Mar-17) | Melamchi | 7
16951 | Sindhupalchok | Dubachour | 3 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 50 | 127 |  | 2017-11-15 |  | Melamchi | 7
16952 | Sindhupalchok | Dubachour | 3 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots trainings in same VDCs | # of trainees | Yes | Completed | 11 | 11 | 2016-06-12 | 2017-03-23 | 1st lot (12-26-Jun-16) 2nd (17-23-Mar-17) | Melamchi | 7
16953 | Sindhupalchok | Dubachour | 4 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | 2 lots trainings in same VDCs | # of kits | Yes | Completed | 8 | 8 | 2016-06-12 | 2017-03-23 | 1st lot (12-26-Jun-16) 2nd (17-23-Mar-17) | Melamchi | 7
16954 | Sindhupalchok | Dubachour | 4 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 141 | 2016-07-31 | 2017-03-23 |  | Melamchi | 7
16955 | Sindhupalchok | Dubachour | 4 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 171 | 63 |  | 2018-02-15 | 1st lot (12-26-Jun-16) 2nd (17-23-Mar-17) | Melamchi | 7
16956 | Sindhupalchok | Dubachour | 4 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 50 | 107 |  | 2017-11-15 |  | Melamchi | 7
16957 | Sindhupalchok | Dubachour | 4 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots trainings in same VDCs | # of trainees | Yes | Completed | 8 | 8 | 2016-06-12 | 2017-03-23 | 1st lot (12-26-Jun-16) 2nd (17-23-Mar-17) | Melamchi | 7
16958 | Sindhupalchok | Dubachour | 5 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | 2 lots trainings in same VDCs | # of kits | Yes | Completed | 21 | 21 | 2016-06-12 | 2017-03-23 | 1st lot (12-26-Jun-16) 2nd (17-23-Mar-17) | Melamchi | 7
16959 | Sindhupalchok | Dubachour | 5 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 138 | 2016-07-07 | 2017-03-23 |  | Melamchi | 7
16960 | Sindhupalchok | Dubachour | 5 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 203 | 215 |  | 2018-02-15 | 1st lot (12-26-Jun-16) 2nd (17-23-Mar-17) | Melamchi | 7
16961 | Sindhupalchok | Dubachour | 5 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 50 | 106 |  | 2017-11-15 |  | Melamchi | 7
16962 | Sindhupalchok | Dubachour | 5 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots trainings in same VDCs | # of trainees | Yes | Completed | 21 | 21 | 2016-06-12 | 2017-03-23 | 1st lot (12-26-Jun-16) 2nd (17-23-Mar-17) | Melamchi | 7
16963 | Sindhupalchok | Dubachour | 6 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | 2 lots trainings in same VDCs | # of kits | Yes | Completed | 15 | 15 | 2016-06-12 | 2017-03-23 | 1st lot (12-26-Jun-16) 2nd (17-23-Mar-17) | Melamchi | 7
16964 | Sindhupalchok | Dubachour | 6 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 156 | 2016-08-01 | 2017-03-23 |  | Melamchi | 7
16965 | Sindhupalchok | Dubachour | 6 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 247 | 9 |  | 2018-02-15 | 1st lot (12-26-Jun-16) 2nd (17-23-Mar-17) | Melamchi | 7
16966 | Sindhupalchok | Dubachour | 6 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 50 | 113 |  | 2017-11-15 |  | Melamchi | 7
16967 | Sindhupalchok | Dubachour | 6 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots trainings in same VDCs | # of trainees | Yes | Completed | 15 | 15 | 2016-06-12 | 2017-03-23 | 1st lot (12-26-Jun-16) 2nd (17-23-Mar-17) | Melamchi | 7
16968 | Sindhupalchok | Dubachour | 7 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 9 | 9 | 2016-06-12 |  |  | Melamchi | 8
16969 | Sindhupalchok | Dubachour | 7 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 123 | 2016-06-08 | 2016-06-08 |  | Melamchi | 8
16970 | Sindhupalchok | Dubachour | 7 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 165 | 85 |  | 2018-03-15 | Marked as 1 to indicate the activity is going on | Melamchi | 8
16971 | Sindhupalchok | Dubachour | 7 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 50 | 88 |  | 2017-11-15 |  | Melamchi | 8
16972 | Sindhupalchok | Dubachour | 7 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-12 | 2016-06-26 |  | Melamchi | 8
16973 | Sindhupalchok | Dubachour | 8 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 10 | 2016-06-12 | 2016-06-26 |  | Melamchi | 8
16974 | Sindhupalchok | Dubachour | 8 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 105 | 2016-06-19 | 2016-06-19 |  | Melamchi | 8
16975 | Sindhupalchok | Dubachour | 8 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 204 | 213 |  | 2018-03-15 | Marked as 1 to indicate the activity is going on | Melamchi | 8
16976 | Sindhupalchok | Dubachour | 8 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 50 | 122 |  |  |  | Melamchi | 8
16977 | Sindhupalchok | Dubachour | 8 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-06-12 | 2016-06-26 |  | Melamchi | 8
16978 | Sindhupalchok | Dubachour | 9 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 1 | 1 | 2016-06-12 |  |  | Melamchi | 8
16979 | Sindhupalchok | Dubachour | 9 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 233 | 2016-06-10 | 2016-06-10 |  | Melamchi | 8
16980 | Sindhupalchok | Dubachour | 9 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 1 | 175 |  | 2018-03-10 | Marked as 1 to indicate the activity is going on | Melamchi | 8
16981 | Sindhupalchok | Dubachour | 9 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 50 | 39 |  | 2017-11-15 |  | Melamchi | 8
16982 | Sindhupalchok | Dubachour | 9 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-12 | 2016-06-26 |  | Melamchi | 8
16983 | Sindhupalchok | Lagarche | 1 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 21 | 21 | 2016-05-25 | 2016-06-16 |  | Panchpokhari Thangpal | 8
16984 | Sindhupalchok | Lagarche | 1 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 73 | 2016-06-01 | 2016-06-01 |  | Panchpokhari Thangpal | 8
16985 | Sindhupalchok | Lagarche | 1 | CARE-N | CSRC | ADH | Technical Assistance | Demonstration Construction | House | One model house for one VDC | # of constructions | Yes | Completed | 1 | 1 | 2017-01-17 | 2017-04-30 |  | Panchpokhari Thangpal | 8
16986 | Sindhupalchok | Lagarche | 1 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 155 | 83 |  | 2018-11-15 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 8
16987 | Sindhupalchok | Lagarche | 1 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 45 | 117 | 2016-08-01 | 2017-11-15 |  | Panchpokhari Thangpal | 8
16988 | Sindhupalchok | Lagarche | 1 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 21 | 21 | 2016-05-25 | 2016-06-16 |  | Panchpokhari Thangpal | 8
16989 | Sindhupalchok | Lagarche | 2 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 34 | 2016-06-02 | 2016-06-02 |  | Panchpokhari Thangpal | 8
16990 | Sindhupalchok | Lagarche | 2 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 129 | 125 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 8
16991 | Sindhupalchok | Lagarche | 2 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 45 | 97 |  | 2017-11-15 |  | Panchpokhari Thangpal | 8
16992 | Sindhupalchok | Lagarche | 3 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 6 | 6 | 2016-05-25 | 2016-06-16 |  | Panchpokhari Thangpal | 8
16993 | Sindhupalchok | Lagarche | 3 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 22 | 2016-06-01 | 2016-06-01 |  | Panchpokhari Thangpal | 8
16994 | Sindhupalchok | Lagarche | 3 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 75 | 71 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 8
16995 | Sindhupalchok | Lagarche | 3 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 45 | 32 |  | 2017-11-15 |  | Panchpokhari Thangpal | 8
16996 | Sindhupalchok | Lagarche | 3 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-25 | 2016-06-16 |  | Panchpokhari Thangpal | 8
16997 | Sindhupalchok | Lagarche | 4 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 | 2016-05-25 | 2016-06-16 |  | Panchpokhari Thangpal | 8
16998 | Sindhupalchok | Lagarche | 4 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 29 | 2016-06-01 | 2016-06-01 |  | Panchpokhari Thangpal | 8
16999 | Sindhupalchok | Lagarche | 4 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 43 | 43 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 8
17000 | Sindhupalchok | Lagarche | 4 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 45 | 30 |  | 2017-11-15 |  | Panchpokhari Thangpal | 8
17001 | Sindhupalchok | Lagarche | 4 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-05-25 | 2016-06-16 |  | Panchpokhari Thangpal | 8
17002 | Sindhupalchok | Lagarche | 5 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-05-25 |  |  | Panchpokhari Thangpal | 8
17003 | Sindhupalchok | Lagarche | 5 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 37 | 2016-07-06 | 2016-07-06 |  | Panchpokhari Thangpal | 8
17004 | Sindhupalchok | Lagarche | 5 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 64 | 54 |  | 2018-02-20 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 8
17005 | Sindhupalchok | Lagarche | 5 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 45 | 30 |  | 2017-11-15 |  | Panchpokhari Thangpal | 8
17006 | Sindhupalchok | Lagarche | 5 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-25 | 2016-06-16 |  | Panchpokhari Thangpal | 8
17007 | Sindhupalchok | Lagarche | 6 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-05-25 | 2016-06-16 |  | Panchpokhari Thangpal | 8
17008 | Sindhupalchok | Lagarche | 6 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 40 | 2016-07-06 | 2016-07-06 |  | Panchpokhari Thangpal | 8
17009 | Sindhupalchok | Lagarche | 6 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 102 | 83 |  | 2018-04-10 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 8
17010 | Sindhupalchok | Lagarche | 6 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 45 | 65 |  | 2017-11-15 |  | Panchpokhari Thangpal | 8
17011 | Sindhupalchok | Lagarche | 6 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-25 | 2016-06-16 |  | Panchpokhari Thangpal | 8
17012 | Sindhupalchok | Lagarche | 7 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-05-25 | 2016-06-16 |  | Panchpokhari Thangpal | 8
17013 | Sindhupalchok | Lagarche | 7 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 55 | 2016-07-05 | 2016-07-05 |  | Panchpokhari Thangpal | 8
17014 | Sindhupalchok | Lagarche | 7 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 68 | 50 |  | 2018-01-25 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 8
17015 | Sindhupalchok | Lagarche | 7 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 45 | 55 |  | 2017-11-15 |  | Panchpokhari Thangpal | 8
17016 | Sindhupalchok | Lagarche | 7 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-25 | 2016-06-16 |  | Panchpokhari Thangpal | 8
17017 | Sindhupalchok | Lagarche | 8 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-05-25 | 2016-06-16 |  | Panchpokhari Thangpal | 8
17018 | Sindhupalchok | Lagarche | 8 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 37 | 2016-07-05 | 2016-07-05 |  | Panchpokhari Thangpal | 8
17019 | Sindhupalchok | Lagarche | 8 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 83 | 75 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 8
17020 | Sindhupalchok | Lagarche | 8 | CARE-N | CSRC | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 1 | 1 | 2016-11-17 |  |  | Panchpokhari Thangpal | 8
17021 | Sindhupalchok | Lagarche | 8 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 45 | 64 |  | 2017-11-15 |  | Panchpokhari Thangpal | 8
17022 | Sindhupalchok | Lagarche | 8 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-25 | 2016-06-16 |  | Panchpokhari Thangpal | 8
17023 | Sindhupalchok | Lagarche | 9 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 6 | 6 | 2016-05-25 | 2016-06-16 |  | Panchpokhari Thangpal | 8
17024 | Sindhupalchok | Lagarche | 9 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 58 | 2016-07-04 | 2016-07-04 |  | Panchpokhari Thangpal | 8
17025 | Sindhupalchok | Lagarche | 9 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 116 | 85 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 8
17026 | Sindhupalchok | Lagarche | 9 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 45 | 75 |  | 2017-11-15 |  | Panchpokhari Thangpal | 8
17027 | Sindhupalchok | Lagarche | 9 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-25 | 2016-06-16 |  | Panchpokhari Thangpal | 8
17028 | Sindhupalchok | Lagarche |  | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 33 | 33 | 2017-06-18 | 2017-06-24 |  | Panchpokhari Thangpal | 8
17029 | Sindhupalchok | Motang | 1 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 18 | 18 | 2016-05-25 | 2017-03-04 |  | Panchpokhari Thangpal | 3
17030 | Sindhupalchok | Motang | 1 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 92 | 2016-06-04 | 2016-06-04 |  | Panchpokhari Thangpal | 3
17031 | Sindhupalchok | Motang | 1 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 161 | 114 |  | 2018-12-25 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 3
17032 | Sindhupalchok | Motang | 1 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 40 | 63 | 2016-08-01 | 2016-12-15 |  | Panchpokhari Thangpal | 3
17033 | Sindhupalchok | Motang | 1 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots trainings in same VDCs | # of trainees | Yes | Completed | 18 | 18 | 2016-05-25 | 2017-03-04 | 1st lot (25-31-May-16) 2nd lot (Feb 26-4 Mar-17) | Panchpokhari Thangpal | 3
17034 | Sindhupalchok | Motang | 2 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-05-25 | 2017-03-04 |  | Panchpokhari Thangpal | 3
17035 | Sindhupalchok | Motang | 2 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 33 | 2016-06-03 | 2016-06-03 |  | Panchpokhari Thangpal | 3
17036 | Sindhupalchok | Motang | 2 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 94 | 68 |  | 2018-01-15 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 3
17037 | Sindhupalchok | Motang | 2 | CARE-N | CSRC | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 1 | 1 | 2016-11-21 |  |  | Panchpokhari Thangpal | 3
17038 | Sindhupalchok | Motang | 2 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 40 | 60 |  | 2017-11-15 |  | Panchpokhari Thangpal | 3
17039 | Sindhupalchok | Motang | 2 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots trainings in same VDCs | # of trainees | Yes | Completed | 4 | 4 | 2016-05-25 | 2017-03-04 | 1st lot (25-31-May-16) 2nd lot (Feb 26-4 Mar-17) | Panchpokhari Thangpal | 3
17040 | Sindhupalchok | Motang | 3 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | 2 lots trainings in same VDCs | # of kits | Yes | Completed | 2 | 2 | 2016-05-25 | 2017-03-04 | 1st lot (25-31-May-16) 2nd lot (Feb 26-4 Mar-17) | Panchpokhari Thangpal | 3
17041 | Sindhupalchok | Motang | 3 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 39 | 2016-07-05 | 2016-07-05 |  | Panchpokhari Thangpal | 3
17042 | Sindhupalchok | Motang | 3 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 43 | 33 |  | 2018-01-15 |  | Panchpokhari Thangpal | 3
17043 | Sindhupalchok | Motang | 3 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 40 | 31 |  | 2017-11-15 |  | Panchpokhari Thangpal | 3
17044 | Sindhupalchok | Motang | 3 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots trainings in same VDCs | # of trainees | Yes | Completed | 2 | 2 | 2016-05-25 | 2017-03-04 | 1st lot (25-31-May-16) 2nd lot (Feb 26-4 Mar-17) | Panchpokhari Thangpal | 3
17045 | Sindhupalchok | Motang | 4 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | 2 lots trainings in same VDCs | # of kits | Yes | Completed | 8 | 8 | 2016-05-25 | 2017-03-04 | 1st lot (25-31-May-16) 2nd lot (Feb 26-4 Mar-17) | Panchpokhari Thangpal | 3
17046 | Sindhupalchok | Motang | 4 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 38 | 2016-11-18 | 2016-11-18 |  | Panchpokhari Thangpal | 3
17047 | Sindhupalchok | Motang | 4 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 64 | 53 |  | 2018-01-15 |  | Panchpokhari Thangpal | 3
17048 | Sindhupalchok | Motang | 4 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 40 | 34 |  | 2017-11-15 |  | Panchpokhari Thangpal | 3
17049 | Sindhupalchok | Motang | 4 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots trainings in same VDCs | # of trainees | Yes | Completed | 8 | 8 | 2016-05-25 | 2017-03-04 | 1st lot (25-31-May-16) 2nd lot (Feb 26-4 Mar-17) | Panchpokhari Thangpal | 3
17050 | Sindhupalchok | Motang | 5 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | 2 lots trainings in same VDCs | # of kits | Yes | Completed | 22 | 22 | 2016-05-25 | 2017-03-04 | 1st lot (25-31-May-16) 2nd lot (Feb 26-4 Mar-17) | Panchpokhari Thangpal | 3
17051 | Sindhupalchok | Motang | 5 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 59 | 2016-06-01 | 2016-06-01 |  | Panchpokhari Thangpal | 3
17052 | Sindhupalchok | Motang | 5 | CARE-N | CSRC | ADH | Technical Assistance | Demonstration Construction | House | 2 lots trainings in same VDCs | # of constructions | Yes | Completed | 1 | 1 | 2017-02-05 | 2017-05-15 | 1st lot (25-31-May-16) 2nd lot (Feb 26-4 Mar-17) | Panchpokhari Thangpal | 3
17053 | Sindhupalchok | Motang | 5 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 115 | 104 |  | 2018-01-15 |  | Panchpokhari Thangpal | 3
17054 | Sindhupalchok | Motang | 5 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 40 | 39 |  | 2017-11-15 |  | Panchpokhari Thangpal | 3
17055 | Sindhupalchok | Motang | 5 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots trainings in same VDCs | # of trainees | Yes | Completed | 22 | 22 | 2016-05-25 | 2017-03-04 | 1st lot (25-31-May-16) 2nd lot (Feb 26-4 Mar-17) | Panchpokhari Thangpal | 3
17056 | Sindhupalchok | Motang | 6 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 6 | 6 | 2016-05-25 | 2016-06-16 |  | Panchpokhari Thangpal | 3
17057 | Sindhupalchok | Motang | 6 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 35 | 2016-07-15 | 2016-07-15 |  | Panchpokhari Thangpal | 3
17058 | Sindhupalchok | Motang | 6 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 54 | 53 |  | 2018-02-10 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 3
17059 | Sindhupalchok | Motang | 6 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 40 | 24 |  | 2017-11-15 |  | Panchpokhari Thangpal | 3
17060 | Sindhupalchok | Motang | 6 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-25 | 2016-06-16 |  | Panchpokhari Thangpal | 3
17061 | Sindhupalchok | Motang | 7 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-05-25 | 2017-03-04 |  | Panchpokhari Thangpal | 3
17062 | Sindhupalchok | Motang | 7 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 49 | 2016-06-02 | 2016-06-02 |  | Panchpokhari Thangpal | 3
17063 | Sindhupalchok | Motang | 7 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 77 | 51 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Panchpokhari Thangpal | 3
17064 | Sindhupalchok | Motang | 7 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 40 | 34 |  | 2017-11-15 |  | Panchpokhari Thangpal | 3
17065 | Sindhupalchok | Motang | 7 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots trainings in same VDCs | # of trainees | Yes | Completed | 4 | 4 | 2016-05-25 | 2017-03-04 | 1st lot (25-31-May-16) 2nd lot (Feb 26-4 Mar-17) | Panchpokhari Thangpal | 3
17066 | Sindhupalchok | Motang | 8 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | 2 lots trainings in same VDCs | # of kits | Yes | Completed | 13 | 13 | 2016-05-25 | 2017-03-04 | 1st lot (25-31-May-16) 2nd lot (Feb 26-4 Mar-17) | Panchpokhari Thangpal | 3
17067 | Sindhupalchok | Motang | 8 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 100 | 2016-07-06 | 2016-07-06 |  | Panchpokhari Thangpal | 3
17068 | Sindhupalchok | Motang | 8 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 112 | 132 |  | 2018-04-15 |  | Panchpokhari Thangpal | 3
17069 | Sindhupalchok | Motang | 8 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 40 | 49 |  | 2017-11-15 |  | Panchpokhari Thangpal | 3
17070 | Sindhupalchok | Motang | 8 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots trainings in same VDCs | # of trainees | Yes | Completed | 13 | 13 | 2016-05-25 | 2017-03-04 | 1st lot (25-31-May-16) 2nd lot (Feb 26-4 Mar-17) | Panchpokhari Thangpal | 3
17071 | Sindhupalchok | Motang | 9 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | 2 lots trainings in same VDCs | # of kits | Yes | Completed | 12 | 12 | 2016-05-25 | 2017-03-04 | 1st lot (25-31-May-16) 2nd lot (Feb 26-4 Mar-17) | Panchpokhari Thangpal | 3
17072 | Sindhupalchok | Motang | 9 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 55 | 22 | 2016-06-02 | 2016-06-02 |  | Panchpokhari Thangpal | 3
17073 | Sindhupalchok | Motang | 9 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 64 | 67 |  | 2018-04-15 |  | Panchpokhari Thangpal | 3
17074 | Sindhupalchok | Motang | 9 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 40 | 51 |  | 2017-11-15 |  | Panchpokhari Thangpal | 3
17075 | Sindhupalchok | Motang | 9 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots trainings in same VDCs | # of trainees | Yes | Completed | 12 | 12 | 2016-05-25 | 2017-03-04 | 1st lot (25-31-May-16) 2nd lot (Feb 26-4 Mar-17) | Panchpokhari Thangpal | 3
17076 | Sindhupalchok | Thakani | 1 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 | 2016-05-01 | 2016-06-25 |  | Melamchi | 4
17077 | Sindhupalchok | Thakani | 1 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 63 | 2016-06-02 | 2016-06-02 |  | Melamchi | 4
17078 | Sindhupalchok | Thakani | 1 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 81 | 62 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Melamchi | 4
17079 | Sindhupalchok | Thakani | 1 | CARE-N | CSRC | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 1 | 1 | 2016-08-24 |  |  | Melamchi | 4
17080 | Sindhupalchok | Thakani | 1 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 50 | 44 | 2016-08-01 | 2017-11-15 |  | Melamchi | 4
17081 | Sindhupalchok | Thakani | 1 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-05-01 | 2016-06-25 | 3 events | Melamchi | 4
17082 | Sindhupalchok | Thakani | 2 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 7 | 7 | 2016-05-01 | 2016-06-25 |  | Melamchi | 4
17083 | Sindhupalchok | Thakani | 2 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 60 | 2016-06-05 | 2016-06-05 |  | Melamchi | 4
17084 | Sindhupalchok | Thakani | 2 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 107 | 60 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Melamchi | 4
17085 | Sindhupalchok | Thakani | 2 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 50 | 66 |  | 2017-11-15 |  | Melamchi | 4
17086 | Sindhupalchok | Thakani | 2 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-01 | 2016-06-25 |  | Melamchi | 4
17087 | Sindhupalchok | Thakani | 3 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-05-01 | 2016-06-25 |  | Melamchi | 4
17088 | Sindhupalchok | Thakani | 3 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 35 | 2016-06-03 | 2016-06-03 |  | Melamchi | 4
17089 | Sindhupalchok | Thakani | 3 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 92 | 40 |  | 2017-12-20 | Marked as 1 to indicate the activity is going on | Melamchi | 4
17090 | Sindhupalchok | Thakani | 3 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 50 | 28 |  | 2017-11-15 |  | Melamchi | 4
17091 | Sindhupalchok | Thakani | 3 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-01 | 2016-06-25 |  | Melamchi | 4
17092 | Sindhupalchok | Thakani | 4 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 | 2016-05-01 | 2016-06-25 |  | Melamchi | 4
17093 | Sindhupalchok | Thakani | 4 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 88 | 2016-06-01 | 2016-06-01 |  | Melamchi | 4
17094 | Sindhupalchok | Thakani | 4 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 130 | 86 |  |  | Marked as 1 to indicate the activity is going on | Melamchi | 4
17095 | Sindhupalchok | Thakani | 4 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 50 | 86 |  | 2017-11-15 |  | Melamchi | 4
17096 | Sindhupalchok | Thakani | 4 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-05-01 | 2016-06-25 |  | Melamchi | 4
17097 | Sindhupalchok | Thakani | 5 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 21 | 21 | 2016-05-01 | 2016-06-25 |  | Melamchi | 4
17098 | Sindhupalchok | Thakani | 5 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 76 | 2016-06-05 | 2016-06-05 |  | Melamchi | 4
17099 | Sindhupalchok | Thakani | 5 | CARE-N | CSRC | ADH | Technical Assistance | Demonstration Construction | House | One model house for one VDC | # of constructions | Yes | Completed | 1 | 1 | 2017-01-15 | 2017-04-30 |  | Melamchi | 4
17100 | Sindhupalchok | Thakani | 5 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 118 | 82 |  | 2018-02-20 | Marked as 1 to indicate the activity is going on | Melamchi | 4
17101 | Sindhupalchok | Thakani | 5 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 50 | 57 |  | 2017-11-15 |  | Melamchi | 4
17102 | Sindhupalchok | Thakani | 5 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 21 | 21 | 2016-05-01 | 2016-06-25 |  | Melamchi | 4
17103 | Sindhupalchok | Thakani | 6 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 | 2016-05-01 | 2016-06-25 |  | Melamchi | 4
17104 | Sindhupalchok | Thakani | 6 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 114 | 2016-07-10 | 2016-07-10 |  | Melamchi | 4
17105 | Sindhupalchok | Thakani | 6 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 127 | 74 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Melamchi | 4
17106 | Sindhupalchok | Thakani | 6 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 50 | 75 |  | 2017-11-15 |  | Melamchi | 4
17107 | Sindhupalchok | Thakani | 6 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-05-01 | 2016-06-25 |  | Melamchi | 4
17108 | Sindhupalchok | Thakani | 7 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 6 | 6 | 2016-05-01 | 2016-06-25 |  | Melamchi | 4
17109 | Sindhupalchok | Thakani | 7 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 30 | 2016-06-05 | 2016-06-05 |  | Melamchi | 4
17110 | Sindhupalchok | Thakani | 7 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 35 | 34 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Melamchi | 4
17111 | Sindhupalchok | Thakani | 7 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 50 | 24 |  | 2017-11-15 |  | Melamchi | 4
17112 | Sindhupalchok | Thakani | 7 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-01 | 2016-06-25 |  | Melamchi | 4
17113 | Sindhupalchok | Thakani | 8 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 19 | 19 | 2016-05-01 |  |  | Melamchi | 4
17114 | Sindhupalchok | Thakani | 8 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 135 | 2016-04-30 | 2016-04-30 |  | Melamchi | 4
17115 | Sindhupalchok | Thakani | 8 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 202 | 115 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Melamchi | 4
17116 | Sindhupalchok | Thakani | 8 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 50 | 131 |  | 2017-11-15 |  | Melamchi | 4
17117 | Sindhupalchok | Thakani | 8 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 19 | 19 | 2016-05-01 | 2016-06-25 |  | Melamchi | 4
17118 | Sindhupalchok | Thakani | 9 | CARE-N | CSRC | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-05-01 | 2016-06-25 |  | Melamchi | 4
17119 | Sindhupalchok | Thakani | 9 | CARE-N | CSRC | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 67 | 91 | 2016-06-26 | 2016-06-26 |  | Melamchi | 4
17120 | Sindhupalchok | Thakani | 9 | CARE-N | CSRC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 129 | 89 |  | 2018-04-15 | Marked as 1 to indicate the activity is going on | Melamchi | 4
17121 | Sindhupalchok | Thakani | 9 | CARE-N | CSRC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 50 | 80 |  | 2017-11-15 |  | Melamchi | 4
17122 | Sindhupalchok | Thakani | 9 | CARE-N | CSRC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-01 | 2016-06-25 |  | Melamchi | 4
17123 | Sindhupalchok | Lagarche | All | CARE-N | CSRC | ADH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 1 day refreshment and 6 days OJT | # of trainees | Yes | Completed | 33 | 33 | 2018-02-21 | 2018-02-27 |  | #N/A | #N/A
17124 | Sindhupalchok | Lagarche | All | CARE-N | CSRC | ADH | Training | Other trainings | Masons (other curriculums, specify in Activity Detail) | 1 day refresher with 5 days OJT |  | Yes | Completed | 60 | 88 | 2018-02-21 | 2018-05-08 |  | #N/A | #N/A
17125 | Sindhupalchok | Dubachour |  | CARE-N | CSRC | ADH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 1 day refreshment and 6 days OJT | # of trainees | Yes | Completed | 12 | 12 | 2018-02-23 | 2018-03-01 |  | Melamchi | 8
17126 | Sindhupalchok | Dubachour |  | CARE-N | CSRC | ADH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 1 day refreshment and 6 days OJT | # of trainees | Yes | Completed | 10 | 10 | 2018-02-23 | 2018-03-01 |  | Melamchi | 8
17127 | Sindhupalchok | Dubachour |  | CARE-N | CSRC | ADH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 1 day refreshment and 6 days OJT | # of trainees | Yes | Completed | 10 | 10 | 2018-02-23 | 2018-03-01 |  | Melamchi | 8
17128 | Sindhupalchok | Dubachour |  | CARE-N | CSRC | ADH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 1 day refreshment and 6 days OJT | # of trainees | Yes | Ongoing | 20 | 20 | 2018-03-07 | 2018-03-12 |  | Melamchi | 8
17129 | Sindhupalchok | Dubachour | 2,3,4,5,6,7,8,9 | CARE-N | CSRC | ADH | Training | Other trainings | Masons (other curriculums, specify in Activity Detail) | 1 day refreshment and 6 days OJT |  | Yes | Completed | 60 | 83 | 2018-02-23 | 2018-05-08 |  | #N/A | #N/A
17130 | Sindhupalchok | Motang | All | CARE-N | CSRC | ADH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 1 day refreshment and 6 days OJT | # of trainees | Yes | Ongoing | 30 | 30 | 2018-03-06 | 2018-03-11 |  | Panchpokhari Thangpal | 3
17131 | Sindhupalchok | Motang | 1,2,3,5,8 | CARE-N | CSRC | ADH | Training | Other trainings | Masons (other curriculums, specify in Activity Detail) | 1 day refreshment and 5 days OJT |  | Yes | Completed | 60 | 58 | 2018-03-07 | 2018-05-22 |  | #N/A | #N/A
17132 | Sindhupalchok | Banskharka | All | CARE-N | CSRC | ADH | Training | Other trainings | Masons (other curriculums, specify in Activity Detail) | 1 day refresher and 5 days OJT | # of trainees | Yes | Completed | 40 | 50 | 2018-04-07 | 2018-05-12 |  | #N/A | #N/A
17133 | Sindhupalchok | Thakani | 1,2,4,5,6,8,9 | CARE-N | CSRC | ADH | Training | Other trainings | Masons (other curriculums, specify in Activity Detail) | 1 day refresher and 5 days OJT | # of trainees | Yes | Completed | 40 | 27 | 2018-05-03 | 2018-05-07 |  | #N/A | #N/A
17134 | Sindhupalchok | Baruwa | 1,5,6,7,8,9 | CARE-N | CSRC | ADH | Training | Other trainings | Masons (other curriculums, specify in Activity Detail) | 1 day refresher and 5 days OJT | # of trainees | Yes | Completed | 40 | 18 | 2018-05-14 | 2018-05-17 |  | #N/A | #N/A
17135 | Sindhupalchok | Lagarche | All | CARE-N | CSRC | ADH | Training | Vocational training | New masons (50 days OJT CTEVT) | 45 days OJT | # of trainees | Yes | Ongoing | 5 | 5 | 2018-03-20 | 2018-05-05 |  | #N/A | #N/A
17136 | Sindhupalchok | Dubachour | 1,2,3,4,5,6 | CARE-N | CSRC | ADH | Training | Vocational training | New masons (50 days OJT CTEVT) | 45 days OJT | # of trainees | Yes | Ongoing | 5 | 5 | 2018-03-20 | 2018-05-05 |  | #N/A | #N/A
17137 | Sindhupalchok | Dubachour | 7,8,9 | CARE-N | CSRC | ADH | Training | Vocational training | New masons (50 days OJT CTEVT) | 45 days OJT | # of trainees | Yes | Ongoing | 5 | 5 | 2018-03-20 | 2018-05-05 |  | #N/A | #N/A
17138 | Sindhupalchok | Kalika | 1 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 82 | 82 | 2016-10-15 |  | VDC coverage | Sunkoshi | 3
17139 | Sindhupalchok | Kalika | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage | Sunkoshi | 3
17140 | Sindhupalchok | Kalika | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 4 | 4 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee | Sunkoshi | 3
17141 | Sindhupalchok | Kalika | 1 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 18 | 18 | 2016-09-07 | 2016-09-14 |  | Sunkoshi | 3
17142 | Sindhupalchok | Kalika | 2 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 63 | 63 | 2016-10-15 |  | VDC coverage | Sunkoshi | 3
17143 | Sindhupalchok | Kalika | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage | Sunkoshi | 3
17144 | Sindhupalchok | Kalika | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 3 | 3 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee | Sunkoshi | 3
17145 | Sindhupalchok | Kalika | 2 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-07 | 2016-09-14 |  | Sunkoshi | 3
17146 | Sindhupalchok | Kalika | 3 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 107 | 107 | 2016-10-15 |  | VDC coverage | Sunkoshi | 3
17147 | Sindhupalchok | Kalika | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage | Sunkoshi | 3
17148 | Sindhupalchok | Kalika | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 5 | 5 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee | Sunkoshi | 3
17149 | Sindhupalchok | Kalika | 3 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-09-07 | 2016-09-14 |  | Sunkoshi | 3
17150 | Sindhupalchok | Kalika | 4 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 61 | 61 | 2016-10-15 |  | VDC coverage | Sunkoshi | 3
17151 | Sindhupalchok | Kalika | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage | Sunkoshi | 3
17152 | Sindhupalchok | Kalika | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 3 | 3 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee | Sunkoshi | 3
17153 | Sindhupalchok | Kalika | 4 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-07 | 2016-09-14 |  | Sunkoshi | 3
17154 | Sindhupalchok | Kalika | 5 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 69 | 69 | 2016-10-15 |  | VDC coverage | Sunkoshi | 3
17155 | Sindhupalchok | Kalika | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage | Sunkoshi | 3
17156 | Sindhupalchok | Kalika | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 3 | 3 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee | Sunkoshi | 3
17157 | Sindhupalchok | Kalika | 5 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-06 | 2016-09-13 |  | Sunkoshi | 3
17158 | Sindhupalchok | Kalika | 6 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 92 | 92 | 2016-10-15 |  | VDC coverage | Sunkoshi | 3
17159 | Sindhupalchok | Kalika | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage | Sunkoshi | 3
17160 | Sindhupalchok | Kalika | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 4 | 4 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee | Sunkoshi | 3
17161 | Sindhupalchok | Kalika | 6 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-09-06 | 2016-09-13 |  | Sunkoshi | 3
17162 | Sindhupalchok | Kalika | 7 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 53 | 53 | 2016-10-15 |  | VDC coverage | Sunkoshi | 3
17163 | Sindhupalchok | Kalika | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage | Sunkoshi | 3
17164 | Sindhupalchok | Kalika | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 3 | 3 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee | Sunkoshi | 3
17165 | Sindhupalchok | Kalika | 7 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-06 | 2016-09-13 |  | Sunkoshi | 3
17166 | Sindhupalchok | Kalika | 8 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 38 | 38 | 2016-10-15 |  | VDC coverage | Sunkoshi | 3
17167 | Sindhupalchok | Kalika | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage | Sunkoshi | 3
17168 | Sindhupalchok | Kalika | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 3 | 3 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee | Sunkoshi | 3
17169 | Sindhupalchok | Kalika | 8 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-06 | 2016-09-13 |  | Sunkoshi | 3
17170 | Sindhupalchok | Kalika | 9 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 87 | 87 | 2016-10-15 |  | VDC coverage | Sunkoshi | 3
17171 | Sindhupalchok | Kalika | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage | Sunkoshi | 3
17172 | Sindhupalchok | Kalika | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 5 | 5 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee | Sunkoshi | 3
17173 | Sindhupalchok | Kalika | 9 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-06 | 2016-09-13 |  | Sunkoshi | 3
17174 | Sindhupalchok | Kalika | All | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Suport to house construction | # of households | Yes | Ongoing | 652 | 636 | 2017-03-23 |  |  | Sunkoshi | 3
17175 | Sindhupalchok | Kalika | all | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Suport to house construction | # of households | Yes | Ongoing | 652 | 414 | 2017-08-08 |  |  | Sunkoshi | 3
17176 | Sindhupalchok | Kalika | All | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Team mobilized of 4 technical persons including sub engineer and assit. Sub enginner | # of households | Yes | Ongoing | 653 | 640 | 2016-10-15 |  | Team mobilized of 4 technical persons including sub engineer and assit. Sub enginner | Sunkoshi | 3
17177 | Sindhupalchok | Kalika |  | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Support to enrollment centre (Volunteer Suppot) | # of trainees | Yes | Completed | 653 | 645 | 2016-07-01 | 2016-08-08 |  | Sunkoshi | 3
17178 | Sindhupalchok | Kalika |  | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Support to enrollment centre (Volunteer Suppot) | # of trainees | Yes | Ongoing | 653 | 645 | 2016-07-15 | 2016-08-15 |  | Sunkoshi | 3
17179 | Sindhupalchok | Kalika |  | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Demonstration Construction | House | Model house | # of constructions | Yes | Ongoing | 2 | 2 | 2016-12-05 | 2016-03-10 |  | Sunkoshi | 3
17180 | Sindhupalchok | Kalika |  | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | VDC coverage | # of households supported | Yes | Planned | 0 | 0 | 2017-03-15 |  | VDC coverage | Sunkoshi | 3
17181 | Sindhupalchok | Kalika |  | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-06-14 | 2017-06-20 |  | Sunkoshi | 3
17182 | Sindhupalchok | Thokarpa | 1 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 111 | 111 | 2016-10-15 |  | VDC coverage | Sunkoshi | 1
17183 | Sindhupalchok | Thokarpa | 2 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 166 | 166 | 2016-10-15 |  | VDC coverage | Sunkoshi | 1
17184 | Sindhupalchok | Thokarpa | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage | Sunkoshi | 1
17185 | Sindhupalchok | Thokarpa | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 5 | 5 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee | Sunkoshi | 1
17186 | Sindhupalchok | Thokarpa | 1 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-09-20 | 2016-09-27 |  | Sunkoshi | 1
17187 | Sindhupalchok | Thokarpa | 3 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 186 | 186 | 2016-10-15 |  | VDC coverage | Sunkoshi | 1
17188 | Sindhupalchok | Thokarpa | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage | Sunkoshi | 1
17189 | Sindhupalchok | Thokarpa | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 5 | 5 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee | Sunkoshi | 1
17190 | Sindhupalchok | Thokarpa | 2 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-09-20 | 2016-09-27 |  | Sunkoshi | 1
17191 | Sindhupalchok | Thokarpa | 4 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 134 | 134 | 2016-10-15 |  | VDC coverage | Sunkoshi | 1
17192 | Sindhupalchok | Thokarpa | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage | Sunkoshi | 1
17193 | Sindhupalchok | Thokarpa | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 6 | 6 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee | Sunkoshi | 1
17194 | Sindhupalchok | Thokarpa | 3 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-09-20 | 2016-09-27 |  | Sunkoshi | 1
17195 | Sindhupalchok | Thokarpa | 5 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 179 | 179 | 2016-10-15 |  | VDC coverage | Sunkoshi | 2
17196 | Sindhupalchok | Thokarpa | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage | Sunkoshi | 1
17197 | Sindhupalchok | Thokarpa | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 5 | 5 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee | Sunkoshi | 1
17198 | Sindhupalchok | Thokarpa | 4 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-09-20 | 2016-09-27 |  | Sunkoshi | 1
17199 | Sindhupalchok | Thokarpa | 6 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 81 | 81 | 2016-10-15 |  | VDC coverage | Sunkoshi | 2
17200 | Sindhupalchok | Thokarpa | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage | Sunkoshi | 2
17201 | Sindhupalchok | Thokarpa | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 6 | 6 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee | Sunkoshi | 2
17202 | Sindhupalchok | Thokarpa | 5 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-09-20 | 2016-09-27 |  | Sunkoshi | 2
17203 | Sindhupalchok | Thokarpa | 7 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 86 | 86 | 2016-10-15 |  | VDC coverage | Sunkoshi | 2
17204 | Sindhupalchok | Thokarpa | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage | Sunkoshi | 2
17205 | Sindhupalchok | Thokarpa | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 5 | 5 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee | Sunkoshi | 2
17206 | Sindhupalchok | Thokarpa | 6 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-09-20 | 2016-09-27 |  | Sunkoshi | 2
17207 | Sindhupalchok | Thokarpa | 8 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 87 | 87 | 2016-10-15 |  | VDC coverage | Sunkoshi | 2
17208 | Sindhupalchok | Thokarpa | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage | Sunkoshi | 2
17209 | Sindhupalchok | Thokarpa | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 5 | 5 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee | Sunkoshi | 2
17210 | Sindhupalchok | Thokarpa | 7 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-09-20 | 2016-09-27 |  | Sunkoshi | 2
17211 | Sindhupalchok | Thokarpa | 9 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Suport to house construction | # of households | Yes | Ongoing | 107 | 107 | 2016-10-15 | 2018-02-02 | Ward level construction committee formation | Sunkoshi | 2
17212 | Sindhupalchok | Thokarpa | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage | Sunkoshi | 2
17213 | Sindhupalchok | Thokarpa | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 5 | 5 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee | Sunkoshi | 2
17214 | Sindhupalchok | Thokarpa | 8 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-09-20 | 2016-09-27 |  | Sunkoshi | 2
17215 | Sindhupalchok | Thokarpa | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Ward coverage | # of participants | Yes | Ongoing | 0 | 0 | 2016-11-25 |  | Ward coverage | Sunkoshi | 2
17216 | Sindhupalchok | Thokarpa | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Ongoing | 5 | 5 | 2016-09-12 | 2016-10-03 | one in each ward and some tole committee | Sunkoshi | 2
17217 | Sindhupalchok | Thokarpa | 9 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-09-20 | 2016-09-27 |  | Sunkoshi | 2
17218 | Sindhupalchok | Thokarpa | All | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Team mobilized of 4 technical persons including sub engineer and assit. Sub enginner | # of households | Yes | Ongoing | 1137 | 1100 | 2016-10-15 |  | Team mobilized of 4 technical persons including sub engineer and assit. Sub enginner | Sunkoshi | 2
17219 | Sindhupalchok | Thokarpa | All | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Beneficiaries from Grievances | # of households | Yes | Completed | 41 | 41 | 2017-12-15 | 2018-01-01 |  | Sunkoshi | 2
17220 | Sindhupalchok | Thokarpa | All | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | support to house construction | # of households | Yes | Ongoing | 1137 | 1137 | 2017-03-23 |  |  | Sunkoshi | 2
17221 | Sindhupalchok | Thokarpa | All | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | support to house construction | # of households | Yes | Ongoing | 1137 | 646 | 2017-08-08 |  |  | Sunkoshi | 2
17222 | Sindhupalchok | Thokarpa |  | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Support to enrollment centre (Volunteer Suppot) | # of trainees | Yes | Completed | 1137 | 1107 | 2016-07-26 | 2016-08-16 |  | Sunkoshi | 2
17223 | Sindhupalchok | Thokarpa |  | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Support to enrollment centre (Volunteer Suppot) | # of trainees | Yes | Completed | 1137 | 1103 | 2016-07-15 | 2016-08-20 |  | Sunkoshi | 2
17224 | Sindhupalchok | Thokarpa |  | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Demonstration Construction | House | Model house | # of constructions | Yes | Ongoing | 2 | 2 | 2016-12-13 |  |  | Sunkoshi | 2
17225 | Sindhupalchok | Thokarpa |  | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | VDC coverage | # of households supported | Yes | Planned | 0 | 0 | 2017-03-15 |  | VDC coverage | Sunkoshi | 2
17226 | Sindhupalchok | Thokarpa |  | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 38 | 38 | 2016-10-04 | 2016-10-23 | Tole level construction group formation | Sunkoshi | 2
17227 | Sindhupalchok | Thokarpa |  | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 9 | 9 | 2016-10-04 | 2016-10-23 | Ward level construction committee formation | Sunkoshi | 2
17228 | Sindhupalchok | Thokarpa |  | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-06-14 | 2017-06-20 |  | Sunkoshi | 2
17229 | Sindhupalchok | Thokarpa | All | CARITAS-N | CARITAS-N | CARITAS | Training | Other trainings | Other trainings (specify in Activity Detail) | 1 day refreshment training | # of trainees | Yes | Completed | 69 | 69 | 2018-03-09 | 2018-03-09 |  | Sunkoshi | 2
17230 | Sindhupalchok | Yamunadanda | All | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 68 | 68 | 2018-02-01 | 2018-02-01 |  | #N/A | #N/A
17231 | Sindhupalchok | Sunkhani | All | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 72 | 72 | 2018-02-01 | 2018-02-01 |  | #N/A | #N/A
17232 | Sindhupalchok | Sipalkavre | All | CARITAS-N | JGSS | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 18 | 2017-12-09 | 2017-12-15 |  | #N/A | #N/A
17233 | Sindhupalchok | Sunkhani | All | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Short mason training | # of trainees | Yes | Ongoing | 140 | 43 | 2018-03-17 | 2018-03-23 |  | #N/A | #N/A
17234 | Sindhupalchok | Yamunadanda | All | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Short mason training | # of trainees | Yes | Ongoing | 100 | 28 | 2018-03-17 | 2018-03-23 |  | #N/A | #N/A
17235 | Sindhupalchok | Sunkhani | All | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 850 | 450 | 2018-02-01 |  |  | #N/A | #N/A
17236 | Sindhupalchok | Yamunadanda | All | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 500 | 220 | 2018-02-01 |  |  | #N/A | #N/A
17237 | Sindhupalchok | Jalbire |  | GoN | GON - DLPIU | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 29 | 2017-06-19 | 2017-06-25 |  | Balefi | 2
17238 | Sindhupalchok | Petaku |  | GoN | GON - DLPIU | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 35 | 2017-06-21 | 2017-06-27 |  | Lisangkhu Pakhar | 6
17239 | Sindhupalchok | Thumpakhar |  | GoN | GON - DLPIU | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 35 | 2017-06-20 | 2017-06-26 |  | Sunkoshi | 6
17240 | Sindhupalchok | Melamchi N.P. | All | GoN | GON - DLPIU | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2018-02-11 | 2018-02-17 |  | Melamchi | 13
17241 | Sindhupalchok | Dubachour | All | GoN | GON - DLPIU | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2018-02-15 | 2018-02-21 |  | Melamchi | 8
17242 | Sindhupalchok | Thakani | All | GoN | GON - DLPIU | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2018-02-21 | 2018-02-27 |  | Melamchi | 4
17243 | Sindhupalchok | Thakani | All | GoN | GON - DLPIU | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 30 | 30 | 2018-03-07 |  |  | Melamchi | 4
17244 | Sindhupalchok | Selang | All | GoN | GON - DLPIU | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 30 | 30 | 2018-03-06 |  |  | #N/A | #N/A
17245 | Sindhupalchok | Bahrabise |  | GON - PAF | GMSP | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-28 | 2017-07-03 |  | Barhabise | 4
17246 | Sindhupalchok | Bahrabise |  | GON - PAF | TUKI | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-28 | 2017-07-03 |  | Barhabise | 4
17247 | Sindhupalchok | Banskharka |  | GON - PAF | SSS | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-19 | 2017-06-25 |  | Panchpokhari Thangpal | 1
17248 | Sindhupalchok | Baramchi |  | GON - PAF | JGSS | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 events in Baramchi (first in 13-19 Jun, second in 20-26 Jun, 2017) | # of trainees | Yes | Completed | 50 | 50 | 2017-06-13 | 2017-06-19 |  | Jugal | 5
17249 | Sindhupalchok | Baruwa |  | GON - PAF | CEED | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-11 | 2017-06-17 |  | Panchpokhari Thangpal | 2
17250 | Sindhupalchok | BhoteNamlang |  | GON - PAF | SIDEC | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 34 | 34 | 2017-06-11 | 2017-06-17 |  | Panchpokhari Thangpal | 7
17251 | Sindhupalchok | Chautara N.P. |  | GON - PAF | Comfortc | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-22 | 2017-06-28 |  | Chautara Sangachokgadhi | 7
17252 | Sindhupalchok | Dhuyang |  | GON - PAF | ARSOW-N | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 22 | 22 | 2017-05-28 | 2017-06-03 |  | Barhabise | 7
17253 | Sindhupalchok | Ghorthali |  | GON - PAF | TUKI | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-10 | 2017-06-16 |  | Tripura Sundari | 1
17254 | Sindhupalchok | Hagam |  | GON - PAF | LDF | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 groups | # of trainees | Yes | Completed | 50 | 50 | 2017-06-12 | 2017-06-18 |  | Jugal | 7
17255 | Sindhupalchok | Lagarche |  | GON - PAF | CIDEC | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 16 | 16 | 2017-06-18 | 2017-06-24 |  | Panchpokhari Thangpal | 8
17256 | Sindhupalchok | Marming |  | GON - PAF | GMSP | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-11 | 2017-06-17 |  | Bhotekoshi | 5
17257 | Sindhupalchok | Nawalpur |  | GON - PAF | FECOFUN | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 events in Badegau (first in 10-16 Jun, second in 17-23 Jun, 2017) | # of trainees | Yes | Completed | 50 | 50 | 2017-06-10 | 2017-06-23 |  | Indrawati | 4
17258 | Sindhupalchok | Sangachok |  | GON - PAF | Comfortc | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-22 | 2017-06-28 |  | Chautara Sangachokgadhi | 12
17259 | Sindhupalchok | Tatopani |  | GON - PAF | SSS | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-05-27 | 2017-06-02 |  | Bhotekoshi | 3
17260 | Sindhupalchok | ThampalChhap |  | GON - PAF | ARSOW-N | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 28 | 28 | 2017-06-11 | 2017-06-17 |  | Panchpokhari Thangpal | 6
17261 | Sindhupalchok | Thanpalkot |  | GON - PAF | CEED | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-07-01 | 2017-07-07 |  | Panchpokhari Thangpal | 4
17262 | Sindhupalchok | Thulosirubari | 1 | HELP | TCM | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Distribution of 10 key message booklets | # of participants | Yes | Ongoing | 170 | 138 | 2017-08-01 | 2017-08-31 |  | Chautara Sangachokgadhi | 13
17263 | Sindhupalchok | Thulosirubari | 2 | HELP | TCM | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Distribution of 10 key message booklets | # of participants | Yes | Ongoing | 130 | 42 | 2017-05-19 |  |  | Chautara Sangachokgadhi | 13
17264 | Sindhupalchok | Thulosirubari | 3 | HELP | TCM | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Distribution of 10 key message booklets | # of participants | Yes | Ongoing | 195 | 105 | 2017-03-28 | 2017-06-16 |  | Chautara Sangachokgadhi | 13
17265 | Sindhupalchok | Thulosirubari | 3 | Help | TUKI | ADH | Technical Assistance | Demonstration Construction | House | Demo house construction | # of constructions | Yes | Completed | 1 | 1 | 2016-12-01 | 2017-02-25 |  | Chautara Sangachokgadhi | 13
17266 | Sindhupalchok | Thulosirubari | 4 | HELP | TCM | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Distribution of 10 key message booklets | # of participants | Yes | Ongoing | 217 | 191 | 2017-05-23 | 2017-08-03 |  | Chautara Sangachokgadhi | 13
17267 | Sindhupalchok | Thulosirubari | 5 | HELP | TCM | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Distribution of 10 key message booklets | # of participants | Yes | Ongoing | 166 | 104 | 2017-05-30 | 2017-08-30 |  | Chautara Sangachokgadhi | 13
17268 | Sindhupalchok | Thulosirubari | 6 | HELP | TCM | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Distribution of 10 key message booklets | # of participants | Yes | Ongoing | 249 | 137 | 2017-04-07 | 2017-08-18 |  | Chautara Sangachokgadhi | 13
17269 | Sindhupalchok | Thulosirubari | 6 | HELP | TUKI | ADH | Technical Assistance | Demonstration Construction | House | Demo house construction | # of constructions | Yes | Completed | 1 | 1 | 2016-12-01 | 2017-02-25 | 2 house on progress 22.11.16 to25.12.16 / to be used as community building | Chautara Sangachokgadhi | 13
17270 | Sindhupalchok | Thulosirubari | 7 | HELP | TCM | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Distribution of 10 key message booklets | # of participants | Yes | Completed | 167 | 109 | 2017-06-14 | 2017-07-20 |  | Chautara Sangachokgadhi | 14
17271 | Sindhupalchok | Thulosirubari | 8 | HELP | TCM | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Distribution of 10 key message booklets | # of participants | Yes | Ongoing | 302 | 244 | 2017-04-19 | 2017-08-17 |  | Chautara Sangachokgadhi | 14
17272 | Sindhupalchok | Thulosirubari | 9 | HELP | TCM | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Distribution of 10 key message booklets | # of participants | Yes | Ongoing | 196 | 64 | 2017-04-20 | 2017-07-21 |  | Chautara Sangachokgadhi | 14
17273 | Sindhupalchok | Thulosirubari | ALL | HELP | TUKI | ADH | Technical Assistance | Demonstration Construction | House | Planned for 7 model house construction | # of constructions | Yes | Planned | 7 | 0 | 2017-04-01 | 2017-12-01 |  | Chautara Sangachokgadhi | 13
17274 | Sindhupalchok | Thulosirubari |  | HELP | TUKI | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Suport to house construction | # of kits | Yes | Completed | 114 | 54 | 2016-03-14 | 2016-09-30 | Training provided by Traininc Center Nepal - TCN | Chautara Sangachokgadhi | 13
17275 | Sindhupalchok | Thulosirubari |  | HELP | TUKI | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Suport to house construction | # of households | Yes | Completed | 1789 | 1789 | 2015-05-01 | 2015-11-01 | tools purchased localy | Chautara Sangachokgadhi | 13
17276 | Sindhupalchok | Thulosirubari |  | HELP | TUKI | ADH | Others | Others | (Please specify in Activity Detail) | 4 schools construction under 1st phase | # of trainees | Yes | Completed | 12 | 4 | 2016-05-01 | 2018-08-30 |  | Chautara Sangachokgadhi | 13
17277 | Sindhupalchok | Thulosirubari |  | HELP | TUKI | ADH | Others | Others | (Please specify in Activity Detail) | 6 schools construction under 2 nd phase | # of trainees | Yes | Ongoing | 6 | 2 | 2017-09-01 |  |  | Chautara Sangachokgadhi | 13
17278 | Sindhupalchok | Thulosirubari |  | HELP | TUKI | ADH | Others | Others | (Please specify in Activity Detail) | Building Sensitization Training and 1800 10 key message booklet distributed | # of trainees | Yes | Completed | 1335 | 1335 | 2017-03-28 | 2017-10-26 |  | Chautara Sangachokgadhi | 13
17279 | Sindhupalchok | Thulosirubari |  | HELP | TUKI | ADH | Technical Assistance | Community reconstruction orientation | 1 session | PASSA training provided by IFRC, shelter Cluster | # of participants | Yes | Completed | 2 | 2 | 2015-12-01 | 2015-12-01 | PASSA training provided by IFRC, shelter Cluster | Chautara Sangachokgadhi | 13
17280 | Sindhupalchok | Thulosirubari |  | HELP | TUKI | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 45 | 10 | 2016-11-22 | 2017-06-30 | short training hands-on on the model house | Chautara Sangachokgadhi | 13
17281 | Sindhupalchok | Thulosirubari |  | HELP | TUKI | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 18 | 2 | 2016-11-22 | 2017-06-30 | short training hands-on on the model house | Chautara Sangachokgadhi | 13
17282 | Sindhupalchok | Thulosirubari |  | HELP | TUKI | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 54 | 54 | 2016-03-14 | 2016-03-31 | Training provided by Traininc Center Nepal - TCN. | Chautara Sangachokgadhi | 13
17283 | Sindhupalchok | Thulosirubari |  | HELP | TCM | ADH | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-11-23 | 2015-11-29 | 2 Help engineers, provided by NSET | Chautara Sangachokgadhi | 13
17284 | Sindhupalchok | Thulosirubari | ALL | HELP | TCM | ADH | Others | others | (Please specify in Activity Detail) | One day Orientation on Community Natural Disaster Awareness program | # of trainees | Yes | Completed | 1782 | 1782 | 2017-06-17 | 2017-08-29 |  | Chautara Sangachokgadhi | 13
17285 | Sindhupalchok | Dubachour | 1 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 10 | 10 | 2016-05-19 | 2016-11-25 | 50 days vocational training | Melamchi | 7
17286 | Sindhupalchok | Dubachour | 1 | HELVETAS | SBPK | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 29 | 29 | 2016-05-19 | 2016-11-25 | 50 days vocational training | Melamchi | 7
17287 | Sindhupalchok | Dubachour | 4 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 2 | 2 | 2016-05-19 | 2016-11-25 | 50 days vocational training | Melamchi | 7
17288 | Sindhupalchok | Dubachour | 4 | HELVETAS | SBPK | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 9 | 9 | 2016-05-19 | 2016-11-25 | 50 days vocational training | Melamchi | 7
17289 | Sindhupalchok | Dubachour | 5 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 2 | 2 | 2016-05-19 | 2016-11-25 | 50 days vocational training | Melamchi | 7
17290 | Sindhupalchok | Dubachour | 5 | HELVETAS | SBPK | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 11 | 11 | 2016-05-19 | 2016-11-25 | 50 days vocational training | Melamchi | 7
17291 | Sindhupalchok | Dubachour | 6 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 4 | 4 | 2016-05-19 | 2016-11-25 | 50 days vocational training | Melamchi | 7
17292 | Sindhupalchok | Dubachour | 1,2,4,5,6 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Tranche I released signing tripartite agreement with DDC and Banks. | # of households | Yes | Completed | 104 | 104 | 2016-09-09 | 2017-07-15 | Continuing Target Individuals and Vulnerable individuals will be confirmed once the selection based on score card and VDC consultation is finalised. We will work in three vulnerable wards selected by the VDC | Melamchi | 8
17293 | Sindhupalchok | Dubachour | 1,2,4,5,6 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | The construction completed following building codes during 50 day training. | # of constructions | Yes | Ongoing | 177 | 35 | 2016-05-19 | 2016-11-25 |  | Melamchi | 8
17294 | Sindhupalchok | Dubachour | 1,2,4,5,6,7 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Approved by DUDBC for 2nd installment | # of households | Yes | Ongoing | 104 | 101 | 2017-07-12 |  |  | Melamchi | 8
17295 | Sindhupalchok | Dubachour | 1,2,4,5,6,7 | HELVETAS | CDECF | SWS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 104 | 104 | 2017-01-01 |  |  | Melamchi | 8
17296 | Sindhupalchok | Dubachour | 1,2,4,5,6,7 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 104 | 89 | 2017-10-16 |  |  | Melamchi | 8
17297 | Sindhupalchok | Helumbu | 1 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 9 | 9 | 2016-05-24 | 2016-11-25 | 50 days vocational training | Helambu | 1
17298 | Sindhupalchok | Helumbu | 7 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 18 | 18 | 2016-05-24 | 2016-11-25 | 50 days vocational training | Helambu | 1
17299 | Sindhupalchok | Helumbu | 7 | HELVETAS | TCCEE | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 8 | 2016-06-05 |  | 51 days vocational training | Helambu | 1
17300 | Sindhupalchok | Helumbu | 1,7,10 | HELVETAS | CDECF | SDC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Approved by DUDBC for 3rd installment | # of households | Yes | Ongoing | 38 | 29 | 2017-07-10 |  |  | Helambu | 1
17301 | Sindhupalchok | Helumbu | 1,7,8 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Tranche I released signing tripartite agreement with DDC and Banks. | # of households | Yes | Completed | 38 | 38 | 2016-09-09 | 2017-07-15 | Continuing Target Individuals and Vulnerable individuals will be confirmed once the selection based on score card and VDC consultation is finalised. We will work in three vulnerable wards selected by the VDC | Helambu | 1
17302 | Sindhupalchok | Helumbu | 1,7,8 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | The construction completed following building codes during 50 day training. | # of constructions | Yes | Ongoing | 99 | 15 | 2016-05-24 | 2016-11-25 |  | Helambu | 1
17303 | Sindhupalchok | Helumbu | 1,7,9 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 38 | 36 | 2017-06-09 |  |  | Helambu | 1
17304 | Sindhupalchok | Helumbu | 1,7,9 | HELVETAS | CDECF | SWS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 38 | 38 | 2017-01-01 |  |  | Helambu | 1
17305 | Sindhupalchok | Ichok | 6 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 6 | 6 | 2016-05-27 | 2016-09-20 | 50 days vocational training | Helambu | 7
17306 | Sindhupalchok | Ichok | 6 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 9 | 2016-08-29 |  | 55 days vocational training | Helambu | 7
17307 | Sindhupalchok | Ichok | 6 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 19 | 19 | 2016-05-27 | 2016-11-25 | 50 days vocational training | Helambu | 7
17308 | Sindhupalchok | Ichok | 8 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 9 | 9 | 2016-05-27 | 2017-09-20 | 50 days vocational training | Helambu | 7
17309 | Sindhupalchok | Ichok | 8 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 9 | 2016-08-29 |  | 56 days vocational training | Helambu | 7
17310 | Sindhupalchok | Ichok | 8 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 16 | 16 | 2016-05-27 | 2016-11-25 | 50 days vocational training | Helambu | 7
17311 | Sindhupalchok | Ichok | 9 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 9 | 9 | 2016-05-27 | 2016-11-25 | 50 days vocational training | Helambu | 7
17312 | Sindhupalchok | Ichok | 9 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 10 | 2016-08-22 | 2016-10-21 | 57 days vocational training | Helambu | 7
17313 | Sindhupalchok | Ichok | 9 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 10 | 10 | 2016-05-27 | 2016-11-25 | 50 days vocational training | Helambu | 7
17314 | Sindhupalchok | Ichok | 9 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 9 | 2016-08-29 |  | 58 days vocational training | Helambu | 7
17315 | Sindhupalchok | Ichok | 1,2,8,6 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Tranche I released signing tripartite agreement with DDC and Banks. | # of households | Yes | Completed | 184 | 184 | 2016-09-09 | 2017-06-15 | Continuing Target Individuals and Vulnerable individuals will be confirmed once the selection based on score card and VDC consultation is finalised. We will work in three vulnerable wards selected by the VDC | Helambu | 7
17316 | Sindhupalchok | Ichok | 1,2,8,6 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | The construction completed following building codes during 50 day training. | # of constructions | Yes | Ongoing | 156 | 40 | 2016-05-27 | 2016-11-25 |  | Helambu | 7
17317 | Sindhupalchok | Ichok | 1,2,8,7 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Approved by DUDBC for 2nd installment | # of households | Yes | Ongoing | 184 | 169 | 2017-03-23 |  |  | Helambu | 7
17318 | Sindhupalchok | Ichok | 1,2,8,7 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Approved by DUDBC for 2nd installment | # of households | Yes | Ongoing | 156 | 135 | 2017-07-15 |  |  | Helambu | 7
17319 | Sindhupalchok | Ichok |  | HELVETAS | CDECF | SDC | Technical Assistance | Community orientation on toilet construction | 2-3 sessions |  | # of participants | Yes | Ongoing | 112 | 1 | 2017-07-15 |  |  | Helambu | 7
17320 | Sindhupalchok | Ichok |  | HELVETAS | CDECF | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-07-15 |  |  | Helambu | 7
17321 | Sindhupalchok | Ichok |  | HELVETAS | CDECF | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 1000 | 529 | 2017-07-01 |  |  | Helambu | 7
17322 | Sindhupalchok | Ichok |  | HELVETAS | CDECF | SDC | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 112 | 50 | 2017-08-01 |  |  | Helambu | 7
17323 | Sindhupalchok | Ichok |  | HELVETAS | ANS | SDC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 100 | 0 | 2017-08-01 |  |  | Helambu | 7
17324 | Sindhupalchok | Ichok |  | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 40 | 0 | 2017-08-01 |  |  | Helambu | 7
17325 | Sindhupalchok | Kiwool | 1 | HELVETAS | GMTI | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 10 | 10 | 2016-05-27 | 2016-11-25 | 50 days vocational training | Helambu | 2
17326 | Sindhupalchok | Kiwool | 1 | HELVETAS | GMTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 15 | 15 | 2016-05-27 | 2016-11-25 | 50 days vocational training | Helambu | 2
17327 | Sindhupalchok | Kiwool | 1 | HELVETAS | GMTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 10 | 2016-08-22 |  | 52 days vocational training | Helambu | 2
17328 | Sindhupalchok | Kiwool | 1 | HELVETAS | TCCEE | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 9 | 2016-08-22 |  | 53 days vocational training | Helambu | 2
17329 | Sindhupalchok | Kiwool | 4 | HELVETAS | GMTI | SDC | Training | Vocational training | Carpenter (CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 6 | 2016-05-27 | 2016-09-13 | 54 days vocational training | Helambu | 2
17330 | Sindhupalchok | Kiwool | 4 | HELVETAS | GMTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 20 | 20 | 2016-05-27 | 2016-11-25 | 50 days vocational training | Helambu | 2
17331 | Sindhupalchok | Kiwool | 1,2,4 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Tranche I released signing tripartite agreement with DDC and Banks. | # of households | Yes | Completed | 119 | 119 | 2016-09-09 | 2018-01-31 | Continuing Target Individuals and Vulnerable individuals will be confirmed once the selection based on score card and VDC consultation is finalised. We will work in three vulnerable wards selected by the VDC | Helambu | 2
17332 | Sindhupalchok | Kiwool | 1,2,4 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | The construction completed following building codes during 50 day training. | # of constructions | Yes | Ongoing | 112 | 28 | 2016-05-27 | 2016-11-25 |  | Helambu | 2
17333 | Sindhupalchok | Kiwool | 1,2,5 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 119 | 93 | 2017-04-03 |  |  | Helambu | 2
17334 | Sindhupalchok | Kiwool | 1,2,6 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 119 | 86 | 2017-07-20 |  |  | Helambu | 2
17335 | Sindhupalchok | Kiwool | 1,2,6 | HELVETAS | CDECF | SWS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 119 | 119 | 2017-01-01 |  |  | Helambu | 2
17336 | Sindhupalchok | Mahankal | 3 | HELVETAS | GMTI | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-07 | 2016-09-22 | 50 days vocational training | Helambu | 5
17337 | Sindhupalchok | Mahankal | 3 | HELVETAS | GMTI | SDC | Training | Vocational training | Carpenter (CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 10 | 2016-11-28 |  | 59 days vocational training | Helambu | 5
17338 | Sindhupalchok | Mahankal | 3 | HELVETAS | GMTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 30 | 30 | 2016-06-01 | 2016-11-25 | 50 days vocational training | Helambu | 5
17339 | Sindhupalchok | Mahankal | 6 | HELVETAS | GMTI | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 5 | 5 | 2016-06-01 | 2016-11-25 | 50 days vocational training | Helambu | 5
17340 | Sindhupalchok | Mahankal | 6 | HELVETAS | GMTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 5 | 5 | 2016-06-01 | 2016-11-25 | 50 days vocational training | Helambu | 5
17341 | Sindhupalchok | Mahankal | 6 | HELVETAS | GMTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Ongoing Training. | # of trainees | Yes | Ongoing | 10 | 10 | 2016-11-28 |  | 60 days vocational training | Helambu | 5
17342 | Sindhupalchok | Mahankal | 3,6,7 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Tranche I released signing tripartite agreement with DDC and Banks. | # of households | Yes | Ongoing | 93 | 93 | 2016-09-09 | 2018-01-31 | Continuing Target Individuals and Vulnerable individuals will be confirmed once the selection based on score card and VDC consultation is finalised. We will work in three vulnerable wards selected by the VDC | Helambu | 5
17343 | Sindhupalchok | Mahankal | 3,6,7 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | The construction completed following building codes during 50 day training. | # of constructions | Yes | Ongoing | 134 | 29 | 2016-06-01 | 2016-11-25 |  | Helambu | 5
17344 | Sindhupalchok | Mahankal | 3,6,8 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 93 | 91 | 2017-06-09 |  |  | Helambu | 5
17345 | Sindhupalchok | Mahankal | 3,6,9 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 93 | 79 | 2017-07-20 |  |  | Helambu | 5
17346 | Sindhupalchok | Mahankal |  | HELVETAS | CDECF | SDC | Technical Assistance | Community orientation on toilet construction | 2-3 sessions |  | # of participants | Yes | Ongoing | 134 | 1 | 2017-07-15 |  |  | Helambu | 5
17347 | Sindhupalchok | Mahankal |  | HELVETAS | CDECF | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 | 2017-08-01 |  |  | Helambu | 5
17348 | Sindhupalchok | Mahankal |  | HELVETAS | CDECF | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 1000 | 500 | 2017-07-01 |  |  | Helambu | 5
17349 | Sindhupalchok | Mahankal |  | HELVETAS | CDECF | SDC | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 134 | 50 | 2017-08-01 |  |  | Helambu | 5
17350 | Sindhupalchok | Mahankal |  | HELVETAS | GMTI | SDC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 100 | 0 |  |  |  | Helambu | 5
17351 | Sindhupalchok | Mahankal |  | HELVETAS | GMTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 40 | 0 | 2017-08-01 |  |  | Helambu | 5
17352 | Sindhupalchok | Melamchi N.P. | 2 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 7 | 7 | 2016-09-01 |  | 50 days vocational training | Melamchi | 6
17353 | Sindhupalchok | Melamchi N.P. | 2 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 15 | 15 | 2016-09-01 |  | 50 days vocational training | Melamchi | 6
17354 | Sindhupalchok | Melamchi N.P. | 3 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 3 | 3 | 2016-09-01 |  | 50 days vocational training | Melamchi | 5
17355 | Sindhupalchok | Melamchi N.P. | 3 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 5 | 5 | 2016-09-08 |  | 50 days vocational training | Melamchi | 5
17356 | Sindhupalchok | Melamchi N.P. | 4 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 5 | 5 | 2016-09-01 |  | 50 days vocational training | Melamchi | 5
17357 | Sindhupalchok | Melamchi N.P. | 4 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 19 | 19 | 2016-08-31 |  | 50 days vocational training | Melamchi | 5
17358 | Sindhupalchok | Melamchi N.P. | 7 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 4 | 4 | 2016-09-01 |  | 50 days vocational training | Melamchi | 11
17359 | Sindhupalchok | Melamchi N.P. | 7 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 5 | 5 | 2016-09-17 |  | 50 days vocational training | Melamchi | 11
17360 | Sindhupalchok | Melamchi N.P. | 8 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 2 | 2 | 2016-09-01 |  | 50 days vocational training | Melamchi | 12
17361 | Sindhupalchok | Melamchi N.P. | 8 | HELVETAS | TCCEE | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 8 | 8 | 2016-09-17 |  | 50 days vocational training | Melamchi | 12
17362 | Sindhupalchok | Melamchi N.P. | 9 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 2 | 2 | 2016-09-01 |  | 50 days vocational training | Melamchi | 12
17363 | Sindhupalchok | Melamchi N.P. | 9 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 5 | 5 | 2016-09-01 |  | 50 days vocational training | Melamchi | 12
17364 | Sindhupalchok | Melamchi N.P. | 3,4,9 &… | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Tranche I released signing tripartite agreement with DDC and Banks. | # of households | Yes | Completed | 218 | 218 | 2016-09-09 | 2018-01-31 | Continuing Target Individuals and Vulnerable individuals will be confirmed once the selection based on score card and VDC consultation is finalised. We will work in three vulnerable wards selected by the VDC | Melamchi | 13
17365 | Sindhupalchok | Melamchi N.P. | 3,4,9 &… | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | The construction completed following building codes during 50 day training. | # of constructions | Yes | Ongoing | 250 | 16 | 2016-08-01 | 2016-11-25 |  | Melamchi | 13
17366 | Sindhupalchok | Melamchi N.P. |  | HELVETAS | TCCEE | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 6 | 6 | 2016-09-01 |  | 50 days vocational training | Melamchi | 13
17367 | Sindhupalchok | Melamchi N.P. |  | HELVETAS | TCCEE | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 10 | 10 | 2016-09-17 |  | 50 days vocational training | Melamchi | 13
17368 | Sindhupalchok | Melamchi N.P. | 3,4,9 &… | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 218 | 141 | 2016-08-01 | 2016-11-25 |  | Melamchi | 13
17369 | Sindhupalchok | Melamchi N.P. | 3,4,9 &… | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 218 | 105 | 2017-08-15 |  |  | Melamchi | 13
17370 | Sindhupalchok | Melamchi N.P. | 3,4,9 &… | HELVETAS | CDECF | SWS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 218 | 218 | 2017-01-01 |  | Baikuntha.Chalise@helvetas.org | Melamchi | 13
17371 | Sindhupalchok | Palchok | 1 | HELVETAS | SBPK | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 9 | 9 | 2016-02-05 |  | 50 days vocational training | Helambu | 3
17372 | Sindhupalchok | Palchok | 3 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 3 | 3 | 2016-02-05 | 2016-11-25 | 50 days vocational training | Helambu | 3
17373 | Sindhupalchok | Palchok | 3 | HELVETAS | SBPK | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 10 | 10 | 2016-02-05 |  | 50 days vocational training | Helambu | 3
17374 | Sindhupalchok | Palchok | 4 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 6 | 6 | 2016-02-05 | 2016-11-25 | 50 days vocational training | Helambu | 3
17375 | Sindhupalchok | Palchok | 5 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) | Complition of two Model Houses during training. | # of trainees | Yes | Completed | 1 | 1 | 2016-02-05 | 2016-11-25 | 50 days vocational training | Helambu | 3
17376 | Sindhupalchok | Palchok | 1,3,4,5 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Tranche I released signing tripartite agreement with DDC and Banks. | # of households | Yes | Completed | 27 | 27 | 2016-09-09 | 2018-01-31 | Continuing Target Individuals and Vulnerable individuals will be confirmed once the selection based on score card and VDC consultation is finalised. We will work in three vulnerable wards selected by the VDC | Helambu | 3
17377 | Sindhupalchok | Palchok | 1,3,4,5 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 27 | 23 | 2017-09-06 |  |  | Helambu | 3
17378 | Sindhupalchok | Palchok | 1,3,4,5 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | The construction completed following building codes during 50 day training. | # of constructions | Yes | Ongoing | 72 | 8 | 2016-02-05 | 2016-11-25 |  | Helambu | 3
17379 | Sindhupalchok | Palchok | 1,3,4,5 | HELVETAS | CDECF | SWS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 27 | 27 | 2017-01-01 |  |  | Helambu | 3
17380 | Sindhupalchok | Palchok | 1,3,4,5 | HELVETAS | CDECF | SWS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 27 | 18 | 2017-12-28 |  |  | Helambu | 3
17381 | Sindhupalchok | Kadambas |  | INCLUSIVE |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 51 |  |  |  | Chautara Sangachokgadhi | 9
17382 | Sindhupalchok | Gati | 1 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 108 | 108 | 2016-04-01 | 2016-04-01 | Verified by Badri Ji Senior Shelter Engineer | Barhabise | 5
17383 | Sindhupalchok | Gati | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 108 | 108 | 2016-03-09 | 2016-03-09 |  | Barhabise | 5
17384 | Sindhupalchok | Gati | 2 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 118 | 118 | 2016-04-01 | 2016-04-01 | Verified by Badri Ji Senior Shelter Engineer | Barhabise | 5
17385 | Sindhupalchok | Gati | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 118 | 118 | 2016-03-10 | 2016-03-10 |  | Barhabise | 5
17386 | Sindhupalchok | Gati | 3 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 68 | 68 | 2016-04-01 | 2016-04-01 | Verified by Badri Ji Senior Shelter Engineer | Barhabise | 5
17387 | Sindhupalchok | Gati | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-03-11 | 2016-03-11 |  | Barhabise | 5
17388 | Sindhupalchok | Gati | 4 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 133 | 133 | 2016-03-31 | 2016-03-31 | Verified by Badri Ji Senior Shelter Engineer | Barhabise | 5
17389 | Sindhupalchok | Gati | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 133 | 133 | 2016-03-12 | 2016-03-12 |  | Barhabise | 5
17390 | Sindhupalchok | Gati | 5 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 80 | 80 | 2016-03-30 | 2016-03-30 | Verified by Badri Ji Senior Shelter Engineer | Barhabise | 5
17391 | Sindhupalchok | Gati | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 80 | 80 | 2016-03-13 | 2016-03-13 |  | Barhabise | 5
17392 | Sindhupalchok | Gati | 6 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 79 | 79 | 2016-03-30 | 2016-03-30 | Verified by Badri Ji Senior Shelter Engineer | Barhabise | 6
17393 | Sindhupalchok | Gati | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 79 | 79 | 2016-03-14 | 2016-03-14 |  | Barhabise | 6
17394 | Sindhupalchok | Gati | 7 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 164 | 164 | 2016-03-30 | 2016-03-30 | Verified by Badri Ji Senior Shelter Engineer | Barhabise | 6
17395 | Sindhupalchok | Gati | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 164 | 164 | 2016-03-15 | 2016-03-15 |  | Barhabise | 6
17396 | Sindhupalchok | Gati | 8 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 58 | 58 | 2016-04-01 | 2016-04-01 | Verified by Badri Ji Senior Shelter Engineer | Barhabise | 6
17397 | Sindhupalchok | Gati | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 58 | 58 | 2016-03-17 | 2016-03-17 |  | Barhabise | 6
17398 | Sindhupalchok | Gati | 9 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 114 | 114 | 2016-04-01 | 2016-04-01 | Verified by Badri Ji Senior Shelter Engineer | Barhabise | 6
17399 | Sindhupalchok | Gati | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 114 | 114 | 2016-03-19 | 2016-03-19 |  | Barhabise | 6
17400 | Sindhupalchok | Jalbire | 1 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 32 | 32 | 2016-03-28 | 2016-03-28 | Verified by Badri Ji Senior Shelter Engineer | Balefi | 1
17401 | Sindhupalchok | Jalbire | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 32 | 32 | 2016-02-15 | 2016-02-15 |  | Balefi | 1
17402 | Sindhupalchok | Jalbire | 2 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 43 | 43 | 2016-03-28 | 2016-03-28 |  | Balefi | 1
17403 | Sindhupalchok | Jalbire | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 44 | 44 | 2016-02-19 | 2016-02-20 |  | Balefi | 1
17404 | Sindhupalchok | Jalbire | 3 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 42 | 42 | 2016-03-28 | 2016-03-28 | Verified by Badri Ji Senior Shelter Engineer | Balefi | 1
17405 | Sindhupalchok | Jalbire | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 42 | 42 | 2016-02-19 | 2016-02-20 |  | Balefi | 1
17406 | Sindhupalchok | Jalbire | 7 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 32 | 32 | 2016-03-28 | 2016-03-28 |  | Balefi | 1
17407 | Sindhupalchok | Jalbire | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 33 | 33 | 2016-02-18 | 2016-02-19 |  | Balefi | 1
17408 | Sindhupalchok | Jalbire | 8 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 25 | 25 | 2016-03-28 | 2016-03-28 |  | Balefi | 1
17409 | Sindhupalchok | Jalbire | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 27 | 27 | 2016-02-18 | 2016-02-19 |  | Balefi | 1
17410 | Sindhupalchok | Jalbire | 9 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 40 | 40 | 2016-04-16 | 2016-04-16 | Verified by Badri Ji Senior Shelter Engineer | Balefi | 1
17411 | Sindhupalchok | Jalbire | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 40 | 40 | 2016-02-17 | 2016-02-18 |  | Balefi | 1
17412 | Sindhupalchok | Marming | 1 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 108 | 108 | 2016-04-28 | 2016-04-28 | Verified by Badri Ji Senior Shelter Engineer | Bhotekoshi | 5
17413 | Sindhupalchok | Marming | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 108 | 108 | 2016-04-20 | 2016-04-20 |  | Bhotekoshi | 5
17414 | Sindhupalchok | Marming | 2 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 120 | 120 | 2016-04-28 | 2016-04-28 | Verified by Badri Ji Senior Shelter Engineer | Bhotekoshi | 5
17415 | Sindhupalchok | Marming | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 120 | 120 | 2016-04-21 | 2016-04-21 |  | Bhotekoshi | 5
17416 | Sindhupalchok | Marming | 3 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 53 | 53 | 2016-04-28 | 2016-04-28 | Verified by Badri Ji Senior Shelter Engineer | Bhotekoshi | 5
17417 | Sindhupalchok | Marming | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 53 | 53 | 2016-04-22 | 2016-04-22 |  | Bhotekoshi | 5
17418 | Sindhupalchok | Marming | 4 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 88 | 88 | 2016-04-28 | 2016-04-28 | Verified by Badri Ji Senior Shelter Engineer | Bhotekoshi | 5
17419 | Sindhupalchok | Marming | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 88 | 88 | 2016-04-23 | 2016-04-23 |  | Bhotekoshi | 5
17420 | Sindhupalchok | Marming | 5 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 108 | 108 | 2016-04-28 | 2016-04-28 | Verified by Badri Ji Senior Shelter Engineer | Bhotekoshi | 5
17421 | Sindhupalchok | Marming | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 108 | 108 | 2016-04-24 | 2016-04-24 |  | Bhotekoshi | 5
17422 | Sindhupalchok | Marming | 6 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 35 | 35 | 2016-04-28 | 2016-04-28 | Verified by Badri Ji Senior Shelter Engineer | Bhotekoshi | 5
17423 | Sindhupalchok | Marming | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 35 | 35 | 2016-04-25 | 2016-04-25 |  | Bhotekoshi | 5
17424 | Sindhupalchok | Marming | 7 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 83 | 83 | 2016-04-28 | 2016-04-28 | Verified by Badri Ji Senior Shelter Engineer | Bhotekoshi | 5
17425 | Sindhupalchok | Marming | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 83 | 83 | 2016-04-26 | 2016-04-26 |  | Bhotekoshi | 5
17426 | Sindhupalchok | Marming | 8 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 89 | 89 | 2016-04-28 | 2016-04-28 | Verified by Badri Ji Senior Shelter Engineer | Bhotekoshi | 5
17427 | Sindhupalchok | Marming | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 89 | 89 | 2016-04-27 | 2016-04-27 |  | Bhotekoshi | 5
17428 | Sindhupalchok | Marming | 9 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 35 | 35 | 2016-04-28 | 2016-04-28 | Verified by Badri Ji Senior Shelter Engineer | Bhotekoshi | 5
17429 | Sindhupalchok | Marming | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 35 | 35 | 2016-04-28 | 2016-04-28 |  | Bhotekoshi | 5
17430 | Sindhupalchok | Petaku | 1 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 35 | 35 | 2016-04-19 | 2016-04-19 |  | Lisangkhu Pakhar | 6
17431 | Sindhupalchok | Petaku | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 40 | 40 | 2016-04-07 | 2016-04-07 |  | Lisangkhu Pakhar | 6
17432 | Sindhupalchok | Petaku | 2 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 60 | 60 | 2016-04-19 | 2016-04-19 | Verified by Badri Ji Senior Shelter Engineer | Lisangkhu Pakhar | 6
17433 | Sindhupalchok | Petaku | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 60 | 60 | 2016-04-05 | 2016-04-05 |  | Lisangkhu Pakhar | 6
17434 | Sindhupalchok | Petaku | 3 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 32 | 32 | 2016-04-19 | 2016-04-19 | Verified by Badri Ji Senior Shelter Engineer | Lisangkhu Pakhar | 6
17435 | Sindhupalchok | Petaku | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 32 | 32 | 2016-04-05 | 2016-04-05 |  | Lisangkhu Pakhar | 6
17436 | Sindhupalchok | Petaku | 4 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 40 | 40 | 2016-04-19 | 2016-04-19 |  | Lisangkhu Pakhar | 6
17437 | Sindhupalchok | Petaku | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 47 | 47 | 2016-04-05 | 2016-04-05 |  | Lisangkhu Pakhar | 6
17438 | Sindhupalchok | Petaku | 5 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 68 | 68 | 2016-04-19 | 2016-04-19 | Verified by Badri Ji Senior Shelter Engineer | Lisangkhu Pakhar | 6
17439 | Sindhupalchok | Petaku | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-04-07 | 2016-04-07 |  | Lisangkhu Pakhar | 6
17440 | Sindhupalchok | Petaku | 6 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 35 | 35 | 2016-04-19 | 2016-04-19 | Verified by Badri Ji Senior Shelter Engineer | Lisangkhu Pakhar | 6
17441 | Sindhupalchok | Petaku | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 35 | 35 | 2016-04-06 | 2016-04-06 |  | Lisangkhu Pakhar | 6
17442 | Sindhupalchok | Petaku | 7 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 38 | 38 | 2016-04-19 | 2016-04-19 | Verified by Badri Ji Senior Shelter Engineer | Lisangkhu Pakhar | 6
17443 | Sindhupalchok | Petaku | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 38 | 38 | 2016-04-06 | 2016-04-06 |  | Lisangkhu Pakhar | 6
17444 | Sindhupalchok | Petaku | 8 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 44 | 44 | 2016-04-19 | 2016-04-19 | Verified by Badri Ji Senior Shelter Engineer | Lisangkhu Pakhar | 6
17445 | Sindhupalchok | Petaku | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 44 | 44 | 2016-04-08 | 2016-04-08 |  | Lisangkhu Pakhar | 6
17446 | Sindhupalchok | Petaku | 9 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 56 | 56 | 2016-04-19 | 2016-04-19 | Verified by Badri Ji Senior Shelter Engineer | Lisangkhu Pakhar | 6
17447 | Sindhupalchok | Petaku | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 56 | 56 | 2016-04-08 | 2016-04-08 |  | Lisangkhu Pakhar | 6
17448 | Sindhupalchok | Sunkhani | 1 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 41 | 41 | 2016-05-20 | 2016-05-20 | Verified by Badri Ji Senior Shelter Engineer | Sunkoshi | 5
17449 | Sindhupalchok | Sunkhani | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 41 | 41 | 2016-05-17 | 2016-05-17 |  | Sunkoshi | 5
17450 | Sindhupalchok | Sunkhani | 2 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 165 | 165 | 2016-05-20 | 2016-05-20 |  | Sunkoshi | 5
17451 | Sindhupalchok | Sunkhani | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 172 | 172 | 2016-05-11 | 2016-05-11 |  | Sunkoshi | 5
17452 | Sindhupalchok | Sunkhani | 3 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 67 | 67 | 2016-05-20 | 2016-05-20 |  | Sunkoshi | 5
17453 | Sindhupalchok | Sunkhani | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 71 | 71 | 2016-05-12 | 2016-05-12 |  | Sunkoshi | 5
17454 | Sindhupalchok | Sunkhani | 4 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 45 | 45 | 2016-05-20 | 2016-05-20 |  | Sunkoshi | 5
17455 | Sindhupalchok | Sunkhani | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 48 | 48 | 2016-05-12 | 2016-05-12 |  | Sunkoshi | 5
17456 | Sindhupalchok | Sunkhani | 5 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 45 | 45 | 2016-05-20 | 2016-05-20 | Verified by Badri Ji Senior Shelter Engineer | Sunkoshi | 5
17457 | Sindhupalchok | Sunkhani | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 45 | 45 | 2016-05-13 | 2016-05-13 |  | Sunkoshi | 5
17458 | Sindhupalchok | Sunkhani | 6 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 44 | 44 | 2016-05-20 | 2016-05-20 |  | Sunkoshi | 5
17459 | Sindhupalchok | Sunkhani | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 45 | 45 | 2016-05-13 | 2016-05-13 |  | Sunkoshi | 5
17460 | Sindhupalchok | Sunkhani | 7 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 118 | 118 | 2016-05-19 | 2016-05-19 |  | Sunkoshi | 5
17461 | Sindhupalchok | Sunkhani | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 123 | 123 | 2016-05-09 | 2016-05-09 |  | Sunkoshi | 5
17462 | Sindhupalchok | Sunkhani | 8 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 55 | 55 | 2016-05-19 | 2016-05-19 |  | Sunkoshi | 5
17463 | Sindhupalchok | Sunkhani | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 57 | 57 | 2016-05-10 | 2016-05-10 |  | Sunkoshi | 5
17464 | Sindhupalchok | Sunkhani | 9 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 117 | 117 | 2016-05-19 | 2016-05-19 |  | Sunkoshi | 5
17465 | Sindhupalchok | Sunkhani | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 123 | 123 | 2016-05-13 | 2016-05-13 |  | Sunkoshi | 5
17466 | Sindhupalchok | ThuloDhading | 2,4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 70 | 70 | 2016-05-19 | 2016-05-19 |  | Lisangkhu Pakhar | 1
17467 | Sindhupalchok | ThuloDhading | 3,5,8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 43 | 43 | 2016-05-18 | 2016-05-18 |  | Lisangkhu Pakhar | 1
17468 | Sindhupalchok | ThuloDhading | 6,4,1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 64 | 64 | 2016-05-19 | 2016-05-19 |  | Lisangkhu Pakhar | 1
17469 | Sindhupalchok | ThuloDhading | 7,9,6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 106 | 106 | 2016-05-20 | 2016-05-20 |  | Lisangkhu Pakhar | 1
17470 | Sindhupalchok | Yamunadanda | 1 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 28 | 28 | 2016-03-25 | 2016-03-25 | Verified by Badri Ji Senior Shelter Engineer | Sunkoshi | 4
17471 | Sindhupalchok | Yamunadanda | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 28 | 28 | 2016-01-22 | 2016-01-23 |  | Sunkoshi | 4
17472 | Sindhupalchok | Yamunadanda | 4 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 40 | 40 | 2016-03-28 | 2016-03-28 | Verified by Badri Ji Senior Shelter Engineer | Sunkoshi | 4
17473 | Sindhupalchok | Yamunadanda | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 40 | 40 | 2016-02-10 | 2016-02-10 |  | Sunkoshi | 4
17474 | Sindhupalchok | Yamunadanda | 5 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 40 | 40 | 2016-04-16 | 2016-04-16 | Verified by Badri Ji Senior Shelter Engineer | Sunkoshi | 4
17475 | Sindhupalchok | Yamunadanda | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 40 | 40 | 2016-02-10 | 2016-02-10 |  | Sunkoshi | 4
17476 | Sindhupalchok | Yamunadanda | 8 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 116 | 116 | 2016-04-01 | 2016-04-01 | Verified by Badri Ji Senior Shelter Engineer | Sunkoshi | 4
17477 | Sindhupalchok | Yamunadanda | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 113 | 113 | 2016-02-13 | 2016-02-13 |  | Sunkoshi | 4
17478 | Sindhupalchok | Yamunadanda | 9 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 34 | 34 | 2016-03-30 | 2016-03-30 | Verified by Badri Ji Senior Shelter Engineer | Sunkoshi | 4
17479 | Sindhupalchok | Yamunadanda | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 34 | 34 | 2016-02-11 | 2016-02-11 |  | Sunkoshi | 4
17480 | Sindhupalchok | Yamunadanda | 2,3 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 40 | 40 | 2016-03-26 | 2016-03-26 | Verified by Badri Ji Senior Shelter Engineer | Sunkoshi | 4
17481 | Sindhupalchok | Yamunadanda | 2,3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 40 | 40 | 2016-02-09 | 2016-02-09 |  | Sunkoshi | 4
17482 | Sindhupalchok | Yamunadanda | 6,7 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 32 | 32 | 2016-03-29 | 2016-03-29 | Verified by Badri Ji Senior Shelter Engineer | Sunkoshi | 4
17483 | Sindhupalchok | Yamunadanda | 6,7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 32 | 32 | 2016-02-11 | 2016-02-11 |  | Sunkoshi | 4
17484 | Sindhupalchok | Atarpur | 6 | Islamic Relief | BATAS | Islamic Relief | Others | Others | (Please specify in Activity Detail) | As per Sagun 51 was planned but only 49 distribute due to lack of Government EQ Card but she advised covert 51 into 49 | # of trainees | Yes | Completed | 49 | 49 | 2016-01-07 | 2015-01-30 |  | Lisangkhu Pakhar | 4
17485 | Sindhupalchok | Atarpur | 7 | Islamic Relief | BATAS | Islamic Relief | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Completed | 47 | 47 | 2016-01-05 | 2015-01-30 |  | Lisangkhu Pakhar | 4
17486 | Sindhupalchok | Jethal | 1 | Islamic Relief | BATAS | Islamic Relief | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Completed | 86 | 86 | 2016-01-04 | 2015-01-30 |  | Lisangkhu Pakhar | 5
17487 | Sindhupalchok | Jethal | 2 | Islamic Relief | BATAS | Islamic Relief | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Completed | 80 | 80 | 2016-01-02 | 2015-01-30 |  | Lisangkhu Pakhar | 5
17488 | Sindhupalchok | Jethal | 3 | Islamic Relief | BATAS | Islamic Relief | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Completed | 45 | 45 | 2016-01-02 | 2015-01-30 |  | Lisangkhu Pakhar | 5
17489 | Sindhupalchok | Jethal | 4 | Islamic Relief | BATAS | Islamic Relief | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Completed | 50 | 50 | 2015-12-28 | 2015-01-30 |  | Lisangkhu Pakhar | 5
17490 | Sindhupalchok | Bahrabise | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 79 | 79 | 2016-09-22 | 2016-09-30 |  | Barhabise | 3
17491 | Sindhupalchok | Bahrabise | All | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 1000 | 864 | 2017-07-02 |  |  | Barhabise | 4
17492 | Sindhupalchok | Bahrabise | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Barhadevi CBRC | Barhabise | 3
17493 | Sindhupalchok | Bahrabise | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-21 | Khursanibari CBRC | Barhabise | 3
17494 | Sindhupalchok | Bahrabise | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2017-02-25 | 2017-02-26 |  | Barhabise | 3
17495 | Sindhupalchok | Bahrabise | 1 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 14 | 14 | 2016-06-11 | 2016-09-28 | 1st lot (11-17-Jun-16) 2nd lot (22-28-Sep-16), 3rd lot (3-9-Jan-17) | Barhabise | 3
17496 | Sindhupalchok | Bahrabise | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 | 2016-09-22 | 2016-09-30 |  | Barhabise | 3
17497 | Sindhupalchok | Bahrabise | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Ward no 2 CBRC | Barhabise | 3
17498 | Sindhupalchok | Bahrabise | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-02-25 | 2017-02-26 |  | Barhabise | 3
17499 | Sindhupalchok | Bahrabise | 2 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 8 | 8 | 2016-06-11 | 2016-09-28 | 1st lot (11-17-Jun-16) 2nd lot (22-28-Sep-16), 3rd lot (3-9-Jan-17) | Barhabise | 3
17500 | Sindhupalchok | Bahrabise | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 70 | 2016-09-22 | 2016-09-30 |  | Barhabise | 3
17501 | Sindhupalchok | Bahrabise | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Bageshwori CBRC | Barhabise | 3
17502 | Sindhupalchok | Bahrabise | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Harabari CBRC | Barhabise | 3
17503 | Sindhupalchok | Bahrabise | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-25 | 2017-02-26 |  | Barhabise | 3
17504 | Sindhupalchok | Bahrabise | 3 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-11 | 2016-09-28 | 1st lot (11-17-Jun-16) 2nd lot (22-28-Sep-16) | Barhabise | 3
17505 | Sindhupalchok | Bahrabise | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 48 | 48 | 2016-09-22 | 2016-09-30 |  | Barhabise | 3
17506 | Sindhupalchok | Bahrabise | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 14 | 14 | 2017-02-25 | 2017-02-26 |  | Barhabise | 3
17507 | Sindhupalchok | Bahrabise | 4 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 25 | 25 | 2016-06-11 | 2016-09-28 | 1st lot (11-17-Jun-16) 2nd lot (22-28-Sep-16), 3rd lot (3-9-Jan-17) | Barhabise | 3
17508 | Sindhupalchok | Bahrabise | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 61 | 61 | 2016-09-22 | 2016-09-30 |  | Barhabise | 4
17509 | Sindhupalchok | Bahrabise | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-22 | Okhreni CBRC | Barhabise | 4
17510 | Sindhupalchok | Bahrabise | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 8 | 8 | 2017-02-25 | 2017-02-26 |  | Barhabise | 4
17511 | Sindhupalchok | Bahrabise | 5 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 11 | 11 | 2016-06-11 | 2016-09-28 | 1st lot (11-17-Jun-16) 2nd lot (22-28-Sep-16), 3rd lot (3-9-Jan-17) | Barhabise | 4
17512 | Sindhupalchok | Bahrabise | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 66 | 66 | 2016-09-22 | 2016-09-30 |  | Barhabise | 4
17513 | Sindhupalchok | Bahrabise | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-25 | 2017-02-26 |  | Barhabise | 4
17514 | Sindhupalchok | Bahrabise | 6 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 7 | 7 | 2016-06-11 | 2016-09-28 | 1st lot (11-17-Jun-16) 2nd lot (22-28-Sep-16), 3rd lot (3-9-Jan-17) | Barhabise | 4
17515 | Sindhupalchok | Bahrabise | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 71 | 71 | 2016-09-22 | 2016-09-30 |  | Barhabise | 4
17516 | Sindhupalchok | Bahrabise | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2017-02-25 | 2017-02-26 |  | Barhabise | 4
17517 | Sindhupalchok | Bahrabise | 7 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 14 | 14 | 2016-06-11 | 2016-09-28 | 1st lot (11-17-Jun-16) 2nd lot (22-28-Sep-16), 3rd lot (3-9-Jan-17) | Barhabise | 4
17518 | Sindhupalchok | Bahrabise | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 52 | 52 | 2016-09-22 | 2016-09-30 |  | Barhabise | 4
17519 | Sindhupalchok | Bahrabise | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-25 | 2017-02-26 |  | Barhabise | 4
17520 | Sindhupalchok | Bahrabise | 8 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-11 | 2016-09-28 |  | Barhabise | 4
17521 | Sindhupalchok | Bahrabise | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-09-22 | 2016-09-30 |  | Barhabise | 4
17522 | Sindhupalchok | Bahrabise | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-25 | 2017-02-26 |  | Barhabise | 4
17523 | Sindhupalchok | Bahrabise | 9 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 5 | 5 | 2016-06-11 | 2016-09-28 | 1st lot (11-17-Jun-16) 2nd lot (22-28-Sep-16), 3rd lot (3-9-Jan-17) | Barhabise | 4
17524 | Sindhupalchok | Bahrabise |  | JICA |  | JICA | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 | 2015-12-01 | 2016-12-31 |  | Barhabise | 4
17525 | Sindhupalchok | Bahrabise | All | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 15 | 15 | 2018-01-01 | 2018-02-15 |  | Barhabise | 4
17526 | Sindhupalchok | Batase | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 26 | 26 | 2016-09-26 | 2016-10-03 |  | Chautara Sangachokgadhi | 2
17527 | Sindhupalchok | Batase | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | PanchaKanya Devi | Chautara Sangachokgadhi | 2
17528 | Sindhupalchok | Batase | 1 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-01-06 | 2017-01-06 |  | Chautara Sangachokgadhi | 2
17529 | Sindhupalchok | Batase | 1 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 8 | 8 | 2016-01-22 | 2017-01-19 | 1st lot (22-28 Jan -16) 2nd (13-19 Jan-17) | Chautara Sangachokgadhi | 2
17530 | Sindhupalchok | Batase | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 75 | 75 | 2016-09-26 | 2016-10-03 |  | Chautara Sangachokgadhi | 2
17531 | Sindhupalchok | Batase | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-04 | Sera Guru Ganesh | Chautara Sangachokgadhi | 2
17532 | Sindhupalchok | Batase | All | JICA | TCN | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 500 | 376 | 2017-07-13 |  |  | Chautara Sangachokgadhi | 3
17533 | Sindhupalchok | Batase | 2 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-01-06 | 2017-01-06 |  | Chautara Sangachokgadhi | 2
17534 | Sindhupalchok | Batase | 2 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 5 | 5 | 2016-01-22 | 2017-01-19 | 1st lot (22-28 Jan -16) 2nd (13-19 Jan-17) | Chautara Sangachokgadhi | 2
17535 | Sindhupalchok | Batase | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 59 | 59 | 2016-09-26 | 2016-10-03 |  | Chautara Sangachokgadhi | 2
17536 | Sindhupalchok | Batase | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | BK tole CBRC | Chautara Sangachokgadhi | 2
17537 | Sindhupalchok | Batase | 3 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 9 | 9 | 2017-01-06 | 2017-01-06 |  | Chautara Sangachokgadhi | 2
17538 | Sindhupalchok | Batase | 3 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 13 | 13 | 2016-01-22 | 2017-01-19 | 1st lot (22-28 Jan -16) 2nd (13-19 Jan-17) | Chautara Sangachokgadhi | 2
17539 | Sindhupalchok | Batase | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 65 | 65 | 2016-09-26 | 2016-10-03 |  | Chautara Sangachokgadhi | 2
17540 | Sindhupalchok | Batase | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-21 | Chitaeswori CBRC | Chautara Sangachokgadhi | 2
17541 | Sindhupalchok | Batase | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-22 | Shree Ganesh Kharitar CBRC | Chautara Sangachokgadhi | 2
17542 | Sindhupalchok | Batase | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-19 | Kalika Devi CBRC | Chautara Sangachokgadhi | 2
17543 | Sindhupalchok | Batase | 4 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 8 | 8 | 2016-01-22 | 2017-01-19 | 1st lot (22-28 Jan -16) 2nd (13-19 Jan-17) | Chautara Sangachokgadhi | 2
17544 | Sindhupalchok | Batase | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 34 | 34 | 2016-09-26 | 2016-10-03 |  | Chautara Sangachokgadhi | 2
17545 | Sindhupalchok | Batase | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-04 | Baluwa Setidevi | Chautara Sangachokgadhi | 2
17546 | Sindhupalchok | Batase | 5 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-01-06 | 2017-01-06 |  | Chautara Sangachokgadhi | 2
17547 | Sindhupalchok | Batase | 5 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 6 | 6 | 2016-01-22 | 2017-01-19 | 1st lot (22-28 Jan -16) 2nd (13-19 Jan-17) | Chautara Sangachokgadhi | 2
17548 | Sindhupalchok | Batase | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 59 | 59 | 2016-09-26 | 2016-10-03 |  | Chautara Sangachokgadhi | 3
17549 | Sindhupalchok | Batase | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | GairiGaun CBRC | Chautara Sangachokgadhi | 3
17550 | Sindhupalchok | Batase | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Bhalayakharka CBRC | Chautara Sangachokgadhi | 3
17551 | Sindhupalchok | Batase | 6 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-01-06 | 2017-01-06 |  | Chautara Sangachokgadhi | 3
17552 | Sindhupalchok | Batase | 6 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 7 | 7 | 2016-01-22 | 2017-01-19 | 1st lot (22-28 Jan -16) 2nd (13-19 Jan-17) | Chautara Sangachokgadhi | 3
17553 | Sindhupalchok | Batase | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 56 | 56 | 2016-09-26 | 2016-10-03 |  | Chautara Sangachokgadhi | 3
17554 | Sindhupalchok | Batase | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-16 | Kitini CBRC | Chautara Sangachokgadhi | 3
17555 | Sindhupalchok | Batase | 7 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 2 | 2 | 2016-01-22 | 2017-01-19 | 1st lot (22-28 Jan -16) 2nd (13-19 Jan-17) | Chautara Sangachokgadhi | 3
17556 | Sindhupalchok | Batase | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 61 | 61 | 2016-09-26 | 2016-10-03 |  | Chautara Sangachokgadhi | 3
17557 | Sindhupalchok | Batase | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-15 | Bhagau CBRC | Chautara Sangachokgadhi | 3
17558 | Sindhupalchok | Batase | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-20 | Gaurati CBRC | Chautara Sangachokgadhi | 3
17559 | Sindhupalchok | Batase | 8 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-01-06 | 2017-01-06 |  | Chautara Sangachokgadhi | 3
17560 | Sindhupalchok | Batase | 8 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 7 | 7 | 2016-01-22 | 2017-01-19 | 1st lot (22-28 Jan -16) 2nd (13-19 Jan-17) | Chautara Sangachokgadhi | 3
17561 | Sindhupalchok | Batase | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 72 | 72 | 2016-09-26 | 2016-10-03 |  | Chautara Sangachokgadhi | 3
17562 | Sindhupalchok | Batase | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-17 | Jangali Kali Devi CBRC | Chautara Sangachokgadhi | 3
17563 | Sindhupalchok | Batase | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-18 | Dhaukhani VBRC | Chautara Sangachokgadhi | 3
17564 | Sindhupalchok | Batase | 9 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-01-06 | 2017-01-06 |  | Chautara Sangachokgadhi | 3
17565 | Sindhupalchok | Batase | 9 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 6 | 6 | 2016-01-22 | 2017-01-19 | 1st lot (22-28 Jan -16) 2nd (13-19 Jan-17) | Chautara Sangachokgadhi | 3
17566 | Sindhupalchok | Batase |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 82 | 2015-12-01 | 2016-12-31 |  | Chautara Sangachokgadhi | 3
17567 | Sindhupalchok | Batase |  | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 20 | 9 | 2017-10-05 | 2018-02-15 |  | Chautara Sangachokgadhi | 3
17568 | Sindhupalchok | Bhotasipa | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 70 | 2016-11-10 | 2016-11-16 |  | Indrawati | 9
17569 | Sindhupalchok | Bhotasipa | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 70 | 2016-11-10 | 2016-11-16 |  | Indrawati | 9
17570 | Sindhupalchok | Bhotasipa | All | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 500 | 511 | 2017-01-18 |  |  | Indrawati | 10
17571 | Sindhupalchok | Bhotasipa | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Sipa Bikas CBRC | Indrawati | 9
17572 | Sindhupalchok | Bhotasipa | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 14 | 14 | 2017-02-04 | 2017-02-04 |  | Indrawati | 9
17573 | Sindhupalchok | Bhotasipa | 1 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 11 | 12 | 2016-02-27 | 2017-02-20 | 1st lot (20-27Feb -16) 2nd (14-20 Feb-17) | Indrawati | 9
17574 | Sindhupalchok | Bhotasipa | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 37 | 37 | 2016-11-10 | 2016-11-16 |  | Indrawati | 9
17575 | Sindhupalchok | Bhotasipa | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 37 | 37 | 2016-11-10 | 2016-11-16 |  | Indrawati | 9
17576 | Sindhupalchok | Bhotasipa | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Garigau Lama tole CBRC | Indrawati | 9
17577 | Sindhupalchok | Bhotasipa | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-04 | 2017-02-04 |  | Indrawati | 9
17578 | Sindhupalchok | Bhotasipa | 2 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 10 | 10 | 2016-02-27 | 2017-02-20 | 1st lot (20-27Feb -16) 2nd (14-20 Feb-17) | Indrawati | 9
17579 | Sindhupalchok | Bhotasipa | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 | 2016-11-10 | 2016-11-16 |  | Indrawati | 9
17580 | Sindhupalchok | Bhotasipa | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 | 2016-11-10 | 2016-11-16 |  | Indrawati | 9
17581 | Sindhupalchok | Bhotasipa | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Batsala Devi Tindhara CBRC | Indrawati | 9
17582 | Sindhupalchok | Bhotasipa | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-04 | 2017-02-04 |  | Indrawati | 9
17583 | Sindhupalchok | Bhotasipa | 3 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 8 | 8 | 2016-02-27 | 2017-02-20 | 1st lot (20-27Feb -16) 2nd (14-20 Feb-17) | Indrawati | 9
17584 | Sindhupalchok | Bhotasipa | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-10 | 2016-11-16 |  | Indrawati | 9
17585 | Sindhupalchok | Bhotasipa | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-10 | 2016-11-16 |  | Indrawati | 9
17586 | Sindhupalchok | Bhotasipa | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Kalika Devi CBRC | Indrawati | 9
17587 | Sindhupalchok | Bhotasipa | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 90 | 90 | 2016-11-10 | 2016-11-16 |  | Indrawati | 10
17588 | Sindhupalchok | Bhotasipa | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 90 | 90 | 2016-11-10 | 2016-11-16 |  | Indrawati | 10
17589 | Sindhupalchok | Bhotasipa | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Batteshwori CBRC | Indrawati | 10
17590 | Sindhupalchok | Bhotasipa | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-04 | 2017-02-04 |  | Indrawati | 10
17591 | Sindhupalchok | Bhotasipa | 5 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 1 | 1 | 2016-02-27 | 2017-02-20 | 1st lot (20-27Feb -16) 2nd (14-20 Feb-17) | Indrawati | 10
17592 | Sindhupalchok | Bhotasipa | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-10 | 2016-11-16 |  | Indrawati | 10
17593 | Sindhupalchok | Bhotasipa | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-10 | 2016-11-16 |  | Indrawati | 10
17594 | Sindhupalchok | Bhotasipa | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Jwalamukhi CBRC | Indrawati | 10
17595 | Sindhupalchok | Bhotasipa | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-04 | 2017-02-04 |  | Indrawati | 10
17596 | Sindhupalchok | Bhotasipa | 6 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 8 | 10 | 2016-02-27 | 2017-02-20 | 1st lot (20-27Feb -16) 2nd (14-20 Feb-17) | Indrawati | 10
17597 | Sindhupalchok | Bhotasipa | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-11-10 | 2016-11-16 |  | Indrawati | 10
17598 | Sindhupalchok | Bhotasipa | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-11-10 | 2016-11-16 |  | Indrawati | 10
17599 | Sindhupalchok | Bhotasipa | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Chandeswori CBRC | Indrawati | 10
17600 | Sindhupalchok | Bhotasipa | 7 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 4 | 5 | 2016-02-27 | 2017-02-20 | 1st lot (20-27Feb -16) 2nd (14-20 Feb-17) | Indrawati | 10
17601 | Sindhupalchok | Bhotasipa | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-10 | 2016-11-16 |  | Indrawati | 10
17602 | Sindhupalchok | Bhotasipa | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-10 | 2016-11-16 |  | Indrawati | 10
17603 | Sindhupalchok | Bhotasipa | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Dandagau CBRC | Indrawati | 10
17604 | Sindhupalchok | Bhotasipa | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-04 | 2017-02-04 |  | Indrawati | 10
17605 | Sindhupalchok | Bhotasipa | 8 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 6 | 6 | 2016-02-27 | 2017-02-20 | 1st lot (20-27Feb -16) 2nd (14-20 Feb-17) | Indrawati | 10
17606 | Sindhupalchok | Bhotasipa | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 | 2016-11-10 | 2016-11-16 |  | Indrawati | 10
17607 | Sindhupalchok | Bhotasipa | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 | 2016-11-10 | 2016-11-16 |  | Indrawati | 10
17608 | Sindhupalchok | Bhotasipa | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Kali devi CBRC | Indrawati | 10
17609 | Sindhupalchok | Bhotasipa | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-02-04 | 2017-02-04 |  | Indrawati | 10
17610 | Sindhupalchok | Bhotasipa | 9 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 6 | 6 | 2016-02-27 | 2017-02-20 | 1st lot (20-27Feb -16) 2nd (14-20 Feb-17) | Indrawati | 10
17611 | Sindhupalchok | Bhotasipa | 8 and 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Aksehshor CBRC | Indrawati | 10
17612 | Sindhupalchok | Bhotasipa |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 60 | 2015-12-01 | 2016-12-31 |  | Indrawati | 10
17613 | Sindhupalchok | Bhotasipa |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 60 | 2015-12-01 | 2016-12-31 |  | Indrawati | 10
17614 | Sindhupalchok | Bhotasipa |  | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 18 | 13 | 2017-10-20 | 2018-02-15 |  | Indrawati | 10
17615 | Sindhupalchok | Bhotechaur | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 65 | 65 | 2016-09-25 | 2016-10-04 |  | Melamchi | 1
17616 | Sindhupalchok | Bhotechaur | All | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 1000 | 807 | 2017-07-11 |  |  | Melamchi | 2
17617 | Sindhupalchok | Bhotechaur | 1 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 9 | 9 | 2016-04-07 | 2016-12-27 | 1st lot (7-13 Apr-16_ 2nd (21-27-Dec-16) | Melamchi | 1
17618 | Sindhupalchok | Bhotechaur | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 39 | 39 | 2016-09-25 | 2016-10-04 |  | Melamchi | 1
17619 | Sindhupalchok | Bhotechaur | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Thulapaata CBRC | Melamchi | 1
17620 | Sindhupalchok | Bhotechaur | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Mausamtole Toridada CBRC | Melamchi | 1
17621 | Sindhupalchok | Bhotechaur | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Chapabot-thapatole CBRC | Melamchi | 1
17622 | Sindhupalchok | Bhotechaur | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Bhumistan jhakritol CBRC | Melamchi | 1
17623 | Sindhupalchok | Bhotechaur | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Phusretole-Poudelthok CBRC | Melamchi | 1
17624 | Sindhupalchok | Bhotechaur | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Chisapani Dandathok CBRC | Melamchi | 1
17625 | Sindhupalchok | Bhotechaur | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 11 | 11 | 2017-02-13 | 2017-02-13 |  | Melamchi | 1
17626 | Sindhupalchok | Bhotechaur | 2 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 19 | 19 | 2016-04-07 | 2016-12-27 | 1st lot (7-13 Apr-16_ 2nd (21-27-Dec-16) | Melamchi | 1
17627 | Sindhupalchok | Bhotechaur | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 28 | 28 | 2016-09-25 | 2016-10-04 |  | Melamchi | 1
17628 | Sindhupalchok | Bhotechaur | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-18 | Dandagaun Pipalbot CBRC | Melamchi | 1
17629 | Sindhupalchok | Bhotechaur | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-13 | 2017-02-13 |  | Melamchi | 1
17630 | Sindhupalchok | Bhotechaur | 3 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 1 | 1 | 2016-04-07 | 2016-12-27 | 1st lot (7-13 Apr-16_ 2nd (21-27-Dec-16) | Melamchi | 1
17631 | Sindhupalchok | Bhotechaur | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 63 | 63 | 2016-09-25 | 2016-10-04 |  | Melamchi | 1
17632 | Sindhupalchok | Bhotechaur | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-18 | Dihi-Pipalbot | Melamchi | 1
17633 | Sindhupalchok | Bhotechaur | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 48 | 48 | 2016-09-25 | 2016-10-04 |  | Melamchi | 2
17634 | Sindhupalchok | Bhotechaur | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Nibugaun | Melamchi | 2
17635 | Sindhupalchok | Bhotechaur | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-02-13 | 2017-02-13 |  | Melamchi | 2
17636 | Sindhupalchok | Bhotechaur | 5 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 15 | 15 | 2016-04-07 | 2016-12-27 | 1st lot (7-13 Apr-16_ 2nd (21-27-Dec-16) | Melamchi | 2
17637 | Sindhupalchok | Bhotechaur | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 43 | 43 | 2016-09-25 | 2016-10-04 |  | Melamchi | 2
17638 | Sindhupalchok | Bhotechaur | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Suyachap CBRC | Melamchi | 2
17639 | Sindhupalchok | Bhotechaur | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-13 | 2017-02-13 |  | Melamchi | 2
17640 | Sindhupalchok | Bhotechaur | 6 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 3 | 3 | 2016-04-07 | 2016-12-27 | 1st lot (7-13 Apr-16_ 2nd (21-27-Dec-16) | Melamchi | 2
17641 | Sindhupalchok | Bhotechaur | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 36 | 36 | 2016-09-25 | 2016-10-04 |  | Melamchi | 2
17642 | Sindhupalchok | Bhotechaur | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Kabra Bot CBRC | Melamchi | 2
17643 | Sindhupalchok | Bhotechaur | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Manakamana CBRC | Melamchi | 2
17644 | Sindhupalchok | Bhotechaur | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-13 | 2017-02-13 |  | Melamchi | 2
17645 | Sindhupalchok | Bhotechaur | 7 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 10 | 10 | 2016-04-07 | 2016-12-27 | 1st lot (7-13 Apr-16_ 2nd (21-27-Dec-16) | Melamchi | 2
17646 | Sindhupalchok | Bhotechaur | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 58 | 58 | 2016-09-25 | 2016-10-04 |  | Melamchi | 2
17647 | Sindhupalchok | Bhotechaur | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Jalpadevi CBRC | Melamchi | 2
17648 | Sindhupalchok | Bhotechaur | 8 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 1 | 1 | 2016-12-21 | 2016-12-27 |  | Melamchi | 2
17649 | Sindhupalchok | Bhotechaur | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 52 | 52 | 2016-09-25 | 2016-10-04 |  | Melamchi | 2
17650 | Sindhupalchok | Bhotechaur | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Tapachuli CBRC | Melamchi | 2
17651 | Sindhupalchok | Bhotechaur | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-13 | 2017-02-13 |  | Melamchi | 2
17652 | Sindhupalchok | Bhotechaur | 9 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 2 | 2 | 2016-12-21 | 2016-12-27 |  | Melamchi | 2
17653 | Sindhupalchok | Bhotechaur |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 84 | 2015-12-01 | 2016-12-31 |  | Melamchi | 2
17654 | Sindhupalchok | Bhotechaur |  | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 16 | 16 | 2017-10-05 | 2018-02-02 |  | Melamchi | 2
17655 | Sindhupalchok | Chautara N.P. | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 178 | 178 | 2016-10-19 | 2016-12-14 |  | Chautara Sangachokgadhi | 6
17656 | Sindhupalchok | Chautara N.P. | All | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 2000 | 2317 | 2017-07-02 |  |  | Chautara Sangachokgadhi | 7
17657 | Sindhupalchok | Chautara N.P. | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Dakshinkali Tole CBRC | Chautara Sangachokgadhi | 6
17658 | Sindhupalchok | Chautara N.P. | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-18 | Pragatishil tole CBRC | Chautara Sangachokgadhi | 6
17659 | Sindhupalchok | Chautara N.P. | 1 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 9 | 9 | 2016-12-23 | 2016-12-23 |  | Chautara Sangachokgadhi | 6
17660 | Sindhupalchok | Chautara N.P. | 1 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 20 | 20 | 2016-03-13 | 2016-12-20 | TCN/ERTech, Batch dates combined 1st lot (18-23-Dec-15) 2nd (22-28-Sep-16) 3rd lot (23-29-Dec-16) | Chautara Sangachokgadhi | 6
17661 | Sindhupalchok | Chautara N.P. | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 177 | 177 | 2016-10-19 | 2016-12-14 |  | Chautara Sangachokgadhi | 6
17662 | Sindhupalchok | Chautara N.P. | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-18 | Bhirkuna-Makhlo Gau CBRC | Chautara Sangachokgadhi | 6
17663 | Sindhupalchok | Chautara N.P. | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Setidevi CBRC | Chautara Sangachokgadhi | 6
17664 | Sindhupalchok | Chautara N.P. | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Shree Mahadev CBRC | Chautara Sangachokgadhi | 6
17665 | Sindhupalchok | Chautara N.P. | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Shree Bageswori CBRC | Chautara Sangachokgadhi | 6
17666 | Sindhupalchok | Chautara N.P. | 2 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 10 | 10 | 2016-12-24 | 2016-12-24 |  | Chautara Sangachokgadhi | 6
17667 | Sindhupalchok | Chautara N.P. | 2 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 24 | 24 | 2016-03-13 | 2016-12-20 | TCN/ERTech, Batch dates combined 1st lot (18-23-Dec-15) 2nd (22-28-Sep-16) 3rd lot (23-29-Dec-16) | Chautara Sangachokgadhi | 6
17668 | Sindhupalchok | Chautara N.P. | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 154 | 154 | 2016-10-19 | 2016-12-14 |  | Chautara Sangachokgadhi | 5
17669 | Sindhupalchok | Chautara N.P. | 3 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 9 | 9 | 2016-03-13 | 2016-12-20 | TCN/ERTech, Batch dates combined 1st lot (18-23-Dec-15) 2nd (22-28-Sep-16) 3rd lot (23-29-Dec-16) | Chautara Sangachokgadhi | 5
17670 | Sindhupalchok | Chautara N.P. | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 168 | 168 | 2016-10-19 | 2016-12-14 |  | Chautara Sangachokgadhi | 5
17671 | Sindhupalchok | Chautara N.P. | 4 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 8 | 8 | 2016-12-23 | 2016-12-23 |  | Chautara Sangachokgadhi | 5
17672 | Sindhupalchok | Chautara N.P. | 4 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 15 | 15 | 2016-03-13 | 2016-12-20 | TCN/ERTech, Batch dates combined 1st lot (18-23-Dec-15) 2nd (22-28-Sep-16) 3rd lot (23-29-Dec-16) | Chautara Sangachokgadhi | 5
17673 | Sindhupalchok | Chautara N.P. | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 138 | 138 | 2016-10-19 | 2016-12-14 |  | Chautara Sangachokgadhi | 4
17674 | Sindhupalchok | Chautara N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-28 | Chature CBRC | Chautara Sangachokgadhi | 4
17675 | Sindhupalchok | Chautara N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-28 | Ganeshthan CBRC | Chautara Sangachokgadhi | 4
17676 | Sindhupalchok | Chautara N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Bashpati CBRC | Chautara Sangachokgadhi | 4
17677 | Sindhupalchok | Chautara N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-16 | Chaugule CBRC | Chautara Sangachokgadhi | 4
17678 | Sindhupalchok | Chautara N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-17 | Deurali CBRC | Chautara Sangachokgadhi | 4
17679 | Sindhupalchok | Chautara N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Simle CBRC | Chautara Sangachokgadhi | 4
17680 | Sindhupalchok | Chautara N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-21 | Lama tole Chaap CBRC | Chautara Sangachokgadhi | 4
17681 | Sindhupalchok | Chautara N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-21 | SauneGhaire CBRC | Chautara Sangachokgadhi | 4
17682 | Sindhupalchok | Chautara N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-22 | Charchare CBRC | Chautara Sangachokgadhi | 4
17683 | Sindhupalchok | Chautara N.P. | 5 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 8 | 8 | 2016-12-24 | 2016-12-24 |  | Chautara Sangachokgadhi | 4
17684 | Sindhupalchok | Chautara N.P. | 5 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 23 | 23 | 2016-03-13 | 2016-12-20 | TCN/ERTech, Batch dates combined 1st lot (18-23-Dec-15) 2nd (22-28-Sep-16) 3rd lot (23-29-Dec-16) | Chautara Sangachokgadhi | 4
17685 | Sindhupalchok | Chautara N.P. | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 190 | 190 | 2016-10-19 | 2016-12-14 |  | Chautara Sangachokgadhi | 4
17686 | Sindhupalchok | Chautara N.P. | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Taalchaur CBRC | Chautara Sangachokgadhi | 4
17687 | Sindhupalchok | Chautara N.P. | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Saahu Tole CBRC | Chautara Sangachokgadhi | 4
17688 | Sindhupalchok | Chautara N.P. | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | MajhTole CBRC | Chautara Sangachokgadhi | 4
17689 | Sindhupalchok | Chautara N.P. | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Nepaltole CBRC | Chautara Sangachokgadhi | 4
17690 | Sindhupalchok | Chautara N.P. | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Simpani Pallo Tole CBRC | Chautara Sangachokgadhi | 4
17691 | Sindhupalchok | Chautara N.P. | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Simpani Tallo Tole CBRC | Chautara Sangachokgadhi | 4
17692 | Sindhupalchok | Chautara N.P. | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Markendanda CBRC | Chautara Sangachokgadhi | 4
17693 | Sindhupalchok | Chautara N.P. | 6 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2016-12-24 | 2016-12-24 |  | Chautara Sangachokgadhi | 4
17694 | Sindhupalchok | Chautara N.P. | 6 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 11 | 11 | 2016-03-13 | 2016-12-20 | TCN/ERTech, Batch dates combined 1st lot (18-23-Dec-15) 2nd (22-28-Sep-16) 3rd lot (23-29-Dec-16) | Chautara Sangachokgadhi | 4
17695 | Sindhupalchok | Chautara N.P. | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 154 | 154 | 2016-10-19 | 2016-12-14 |  | Chautara Sangachokgadhi | 5
17696 | Sindhupalchok | Chautara N.P. | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-16 | GhaleGau CBRC | Chautara Sangachokgadhi | 5
17697 | Sindhupalchok | Chautara N.P. | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-18 | Gairigau CBRC | Chautara Sangachokgadhi | 5
17698 | Sindhupalchok | Chautara N.P. | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-11 | Hungdrung kalidevi CBRC | Chautara Sangachokgadhi | 5
17699 | Sindhupalchok | Chautara N.P. | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Bagbazzar CBRC | Chautara Sangachokgadhi | 5
17700 | Sindhupalchok | Chautara N.P. | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Jugal CBRC | Chautara Sangachokgadhi | 5
17701 | Sindhupalchok | Chautara N.P. | 7 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 28 | 28 | 2016-12-25 | 2016-12-25 |  | Chautara Sangachokgadhi | 5
17702 | Sindhupalchok | Chautara N.P. | 7 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 25 | 25 | 2016-03-13 | 2016-12-20 | TCN/ERTech, Batch dates combined 1st lot (18-23-Dec-15) 2nd (22-28-Sep-16) 3rd lot (23-29-Dec-16) | Chautara Sangachokgadhi | 5
17703 | Sindhupalchok | Chautara N.P. | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 283 | 283 | 2016-10-19 | 2016-12-14 |  | Chautara Sangachokgadhi | 7
17704 | Sindhupalchok | Chautara N.P. | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-15 | Kalleri CBRC | Chautara Sangachokgadhi | 7
17705 | Sindhupalchok | Chautara N.P. | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-15 | Arubote CBRC | Chautara Sangachokgadhi | 7
17706 | Sindhupalchok | Chautara N.P. | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Arrubote CBRC | Chautara Sangachokgadhi | 7
17707 | Sindhupalchok | Chautara N.P. | 8 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2016-12-24 | 2016-12-24 |  | Chautara Sangachokgadhi | 7
17708 | Sindhupalchok | Chautara N.P. | 8 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 13 | 13 | 2016-03-13 | 2016-12-20 | TCN/ERTech, Batch dates combined 1st lot (18-23-Dec-15) 2nd (22-28-Sep-16) 3rd lot (23-29-Dec-16) | Chautara Sangachokgadhi | 7
17709 | Sindhupalchok | Chautara N.P. | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 125 | 125 | 2016-10-19 | 2016-12-14 |  | Chautara Sangachokgadhi | 7
17710 | Sindhupalchok | Chautara N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Bhulbhule Danda CBRC | Chautara Sangachokgadhi | 7
17711 | Sindhupalchok | Chautara N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Arrubote CBRC | Chautara Sangachokgadhi | 7
17712 | Sindhupalchok | Chautara N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | MaleDanda CBRC | Chautara Sangachokgadhi | 7
17713 | Sindhupalchok | Chautara N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-16 | Maguwa CBRC | Chautara Sangachokgadhi | 7
17714 | Sindhupalchok | Chautara N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Jyadi CBRC | Chautara Sangachokgadhi | 7
17715 | Sindhupalchok | Chautara N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Neupane Tole CBRC | Chautara Sangachokgadhi | 7
17716 | Sindhupalchok | Chautara N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-18 | Pauwa CBRC | Chautara Sangachokgadhi | 7
17717 | Sindhupalchok | Chautara N.P. | 9 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 47 | 47 | 2016-12-21 | 2016-12-21 | Added sanosiruwari in ward no 9 | Chautara Sangachokgadhi | 7
17718 | Sindhupalchok | Chautara N.P. | 9 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 42 | 42 | 2015-12-18 | 2016-12-20 | TCN/ERTech, Batch dates combined 1st lot (18-23-Dec-15) 2nd (22-28-Sep-16) 3rd lot (23-29-Dec-16) | Chautara Sangachokgadhi | 7
17719 | Sindhupalchok | Chautara N.P. | ALL | JICA |  | JICA | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 31 | 31 | 2016-02-28 | 2016-03-07 |  | Chautara Sangachokgadhi | 7
17720 | Sindhupalchok | Chautara N.P. |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 240 | 120 | 2015-12-01 | 2016-12-31 |  | Chautara Sangachokgadhi | 7
17721 | Sindhupalchok | Chautara N.P. |  | JICA |  | JICA | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 28 | 28 | 2016-02-28 | 2016-03-07 |  | Chautara Sangachokgadhi | 7
17722 | Sindhupalchok | Chautara N.P. |  | JICA |  | JICA | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 32 | 32 | 2016-02-28 | 2016-03-07 |  | Chautara Sangachokgadhi | 7
17723 | Sindhupalchok | Chautara N.P. |  | JICA |  | JICA | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 33 | 33 | 2016-02-28 | 2016-03-07 |  | Chautara Sangachokgadhi | 7
17724 | Sindhupalchok | Chautara N.P. |  | JICA |  | JICA | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 35 | 35 | 2016-02-28 | 2016-03-07 |  | Chautara Sangachokgadhi | 7
17725 | Sindhupalchok | Chautara N.P. | ALL | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 39 | 39 | 2018-01-01 | 2018-02-15 |  | Chautara Sangachokgadhi | 7
17726 | Sindhupalchok | Dubachour | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 25 | 25 | 2016-11-21 | 2016-12-04 |  | Melamchi | 7
17727 | Sindhupalchok | Dubachour | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-08-26 | Dubachaur Ward 1 CBRC | Melamchi | 7
17728 | Sindhupalchok | Dubachour | All | jica |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 1000 | 1426 | 2017-07-02 |  |  | Melamchi | 8
17729 | Sindhupalchok | Dubachour | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-21 | 2016-12-04 |  | Melamchi | 7
17730 | Sindhupalchok | Dubachour | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-09-18 | Dubachaur Ward 2 CBRC | Melamchi | 7
17731 | Sindhupalchok | Dubachour | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-11 | 2017-02-11 |  | Melamchi | 7
17732 | Sindhupalchok | Dubachour | 2 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-16 | 2016-04-22 |  | Melamchi | 7
17733 | Sindhupalchok | Dubachour | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 26 | 26 | 2016-11-21 | 2016-12-04 |  | Melamchi | 7
17734 | Sindhupalchok | Dubachour | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-09-08 | Dubachaur Ward 3 CBRC | Melamchi | 7
17735 | Sindhupalchok | Dubachour | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-11 | 2017-02-11 |  | Melamchi | 7
17736 | Sindhupalchok | Dubachour | 3 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-04-16 | 2016-04-22 |  | Melamchi | 7
17737 | Sindhupalchok | Dubachour | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 25 | 25 | 2016-11-21 | 2016-12-04 |  | Melamchi | 7
17738 | Sindhupalchok | Dubachour | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-17 | Dubachaur Ward 4 CBRC | Melamchi | 7
17739 | Sindhupalchok | Dubachour | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 9 | 9 | 2017-02-11 | 2017-02-11 |  | Melamchi | 7
17740 | Sindhupalchok | Dubachour | 4 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-04-16 | 2016-04-22 |  | Melamchi | 7
17741 | Sindhupalchok | Dubachour | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 32 | 32 | 2016-11-21 | 2016-12-04 |  | Melamchi | 7
17742 | Sindhupalchok | Dubachour | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-20 | Dubachaur Ward 5 CBRC | Melamchi | 7
17743 | Sindhupalchok | Dubachour | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-11 | 2017-02-11 |  | Melamchi | 7
17744 | Sindhupalchok | Dubachour | 5 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-16 | 2016-04-22 |  | Melamchi | 7
17745 | Sindhupalchok | Dubachour | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 34 | 34 | 2016-11-21 | 2016-12-04 |  | Melamchi | 7
17746 | Sindhupalchok | Dubachour | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-21 | Dubachaur Ward 6 CBRC | Melamchi | 7
17747 | Sindhupalchok | Dubachour | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-11 | 2017-02-11 |  | Melamchi | 7
17748 | Sindhupalchok | Dubachour | 6 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-04-16 | 2016-04-22 |  | Melamchi | 7
17749 | Sindhupalchok | Dubachour | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 26 | 26 | 2016-11-21 | 2016-12-04 |  | Melamchi | 8
17750 | Sindhupalchok | Dubachour | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-04 | Dubachaur Ward 7 CBRC | Melamchi | 8
17751 | Sindhupalchok | Dubachour | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-11 | 2017-02-11 |  | Melamchi | 8
17752 | Sindhupalchok | Dubachour | 7 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-16 | 2016-04-22 |  | Melamchi | 8
17753 | Sindhupalchok | Dubachour | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 100 | 2016-11-21 | 2016-12-04 |  | Melamchi | 8
17754 | Sindhupalchok | Dubachour | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-24 | Dubachaur Ward 8 CBRC | Melamchi | 8
17755 | Sindhupalchok | Dubachour | 8 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-16 | 2016-04-22 |  | Melamchi | 8
17756 | Sindhupalchok | Dubachour | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 80 | 80 | 2016-11-21 | 2016-12-04 |  | Melamchi | 8
17757 | Sindhupalchok | Dubachour | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-24 | Dubachaur Ward 9 CBRC | Melamchi | 8
17758 | Sindhupalchok | Dubachour | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-11 | 2017-02-11 |  | Melamchi | 8
17759 | Sindhupalchok | Dubachour | 9 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-16 | 2016-04-22 |  | Melamchi | 8
17760 | Sindhupalchok | Dubachour |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 83 | 2016-04-01 | 2020-12-31 |  | Melamchi | 8
17761 | Sindhupalchok | Dubachour |  | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 14 | 14 | 2018-01-01 | 2018-02-15 |  | Melamchi | 8
17762 | Sindhupalchok | Fulpingdandagau | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 39 | 39 | 2016-09-25 | 2016-10-03 |  | Balefi | 4
17763 | Sindhupalchok | Fulpingdandagau | ALL | JICA | TCN | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 1000 | 621 | 2017-07-19 |  |  | Balefi | 5
17764 | Sindhupalchok | Fulpingdandagau | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-22 | 2017-02-23 |  | Balefi | 4
17765 | Sindhupalchok | Fulpingdandagau | 1 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-07-23 | 2016-07-29 |  | Balefi | 4
17766 | Sindhupalchok | Fulpingdandagau | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 47 | 47 | 2016-09-25 | 2016-10-03 |  | Balefi | 4
17767 | Sindhupalchok | Fulpingdandagau | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 10 | 10 | 2017-02-22 | 2017-02-23 |  | Balefi | 4
17768 | Sindhupalchok | Fulpingdandagau | 2 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-23 | 2016-07-29 |  | Balefi | 4
17769 | Sindhupalchok | Fulpingdandagau | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 53 | 53 | 2016-09-25 | 2016-10-03 |  | Balefi | 4
17770 | Sindhupalchok | Fulpingdandagau | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 10 | 10 | 2017-02-22 | 2017-02-23 |  | Balefi | 4
17771 | Sindhupalchok | Fulpingdandagau | 3 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-07-23 | 2016-07-29 |  | Balefi | 4
17772 | Sindhupalchok | Fulpingdandagau | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 56 | 56 | 2016-09-25 | 2016-10-03 |  | Balefi | 4
17773 | Sindhupalchok | Fulpingdandagau | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-23 | Panchakanya CBRC | Balefi | 4
17774 | Sindhupalchok | Fulpingdandagau | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-22 | 2017-02-23 |  | Balefi | 4
17775 | Sindhupalchok | Fulpingdandagau | 4 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-07-23 | 2016-07-29 |  | Balefi | 4
17776 | Sindhupalchok | Fulpingdandagau | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 63 | 63 | 2016-09-25 | 2016-10-03 |  | Balefi | 5
17777 | Sindhupalchok | Fulpingdandagau | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 19 | 19 | 2017-02-22 | 2017-02-23 |  | Balefi | 5
17778 | Sindhupalchok | Fulpingdandagau | 5 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-23 | 2016-07-29 |  | Balefi | 5
17779 | Sindhupalchok | Fulpingdandagau | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 32 | 32 | 2016-09-25 | 2016-10-03 |  | Balefi | 5
17780 | Sindhupalchok | Fulpingdandagau | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-07 | Setidevi CBRC | Balefi | 5
17781 | Sindhupalchok | Fulpingdandagau | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-22 | 2017-02-23 |  | Balefi | 5
17782 | Sindhupalchok | Fulpingdandagau | 6 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-07-23 | 2016-07-29 |  | Balefi | 5
17783 | Sindhupalchok | Fulpingdandagau | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 54 | 54 | 2016-09-25 | 2016-10-03 |  | Balefi | 5
17784 | Sindhupalchok | Fulpingdandagau | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-22 | Jyamire CBRC | Balefi | 5
17785 | Sindhupalchok | Fulpingdandagau | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 10 | 10 | 2017-02-22 | 2017-02-23 |  | Balefi | 5
17786 | Sindhupalchok | Fulpingdandagau | 7 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-07-23 | 2016-07-29 |  | Balefi | 5
17787 | Sindhupalchok | Fulpingdandagau | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 26 | 26 | 2016-09-25 | 2016-10-03 |  | Balefi | 4
17788 | Sindhupalchok | Fulpingdandagau | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-01 | Barpipal CBRC | Balefi | 4
17789 | Sindhupalchok | Fulpingdandagau | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 9 | 9 | 2017-02-22 | 2017-02-23 |  | Balefi | 4
17790 | Sindhupalchok | Fulpingdandagau | 8 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-23 | 2016-07-29 |  | Balefi | 4
17791 | Sindhupalchok | Fulpingdandagau | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-09-25 | 2016-10-03 |  | Balefi | 5
17792 | Sindhupalchok | Fulpingdandagau | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-02 | Kapileshwor CBRC | Balefi | 5
17793 | Sindhupalchok | Fulpingdandagau | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-22 | 2017-02-23 |  | Balefi | 5
17794 | Sindhupalchok | Fulpingdandagau | 9 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-23 | 2016-07-29 |  | Balefi | 5
17795 | Sindhupalchok | Fulpingdandagau |  | JICA | ERTech | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31 |  | Balefi | 5
17796 | Sindhupalchok | Fulpingdandagau |  | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 16 | 11 | 2017-10-05 | 2018-02-15 |  | Balefi | 5
17797 | Sindhupalchok | Fulpingkot | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-12-07 | 2016-12-12 |  | Balefi | 2
17798 | Sindhupalchok | Fulpingkot | ALL | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 1000 | 961 | 2017-07-04 |  |  | Balefi | 3
17799 | Sindhupalchok | Fulpingkot | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-21 | 2017-02-21 |  | Balefi | 2
17800 | Sindhupalchok | Fulpingkot | 1 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-09-15 | 2016-09-21 |  | Balefi | 2
17801 | Sindhupalchok | Fulpingkot | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 28 | 28 | 2016-12-07 | 2016-12-12 |  | Balefi | 2
17802 | Sindhupalchok | Fulpingkot | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-21 | 2017-02-21 |  | Balefi | 2
17803 | Sindhupalchok | Fulpingkot | 2 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-15 | 2016-09-21 |  | Balefi | 2
17804 | Sindhupalchok | Fulpingkot | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-12-07 | 2016-12-12 |  | Balefi | 2
17805 | Sindhupalchok | Fulpingkot | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 8 | 8 | 2017-02-21 | 2017-02-21 |  | Balefi | 2
17806 | Sindhupalchok | Fulpingkot | 3 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-09-15 | 2016-09-21 |  | Balefi | 2
17807 | Sindhupalchok | Fulpingkot | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 73 | 2016-12-07 |  |  | Balefi | 2
17808 | Sindhupalchok | Fulpingkot | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-21 | 2017-02-21 |  | Balefi | 2
17809 | Sindhupalchok | Fulpingkot | 4 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-09-15 | 2016-09-21 |  | Balefi | 2
17810 | Sindhupalchok | Fulpingkot | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 42 | 42 | 2016-12-07 | 2016-12-12 |  | Balefi | 3
17811 | Sindhupalchok | Fulpingkot | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-21 | 2017-02-21 |  | Balefi | 3
17812 | Sindhupalchok | Fulpingkot | 5 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-15 | 2016-09-21 |  | Balefi | 3
17813 | Sindhupalchok | Fulpingkot | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-12-07 | 2016-12-12 |  | Balefi | 3
17814 | Sindhupalchok | Fulpingkot | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-21 | 2017-02-21 |  | Balefi | 3
17815 | Sindhupalchok | Fulpingkot | 6 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-15 | 2016-09-21 |  | Balefi | 3
17816 | Sindhupalchok | Fulpingkot | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 | 2016-12-07 | 2016-12-12 |  | Balefi | 3
17817 | Sindhupalchok | Fulpingkot | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-21 | 2017-02-21 |  | Balefi | 3
17818 | Sindhupalchok | Fulpingkot | 7 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-15 | 2016-09-21 |  | Balefi | 3
17819 | Sindhupalchok | Fulpingkot | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 36 | 36 | 2016-12-07 | 2016-12-12 |  | Balefi | 3
17820 | Sindhupalchok | Fulpingkot | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-21 | 2017-02-21 |  | Balefi | 3
17821 | Sindhupalchok | Fulpingkot | 8 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-09-15 | 2016-09-21 |  | Balefi | 3
17822 | Sindhupalchok | Fulpingkot | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 37 | 37 | 2016-12-07 | 2016-12-12 |  | Balefi | 3
17823 | Sindhupalchok | Fulpingkot | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-21 | 2017-02-21 |  | Balefi | 3
17824 | Sindhupalchok | Fulpingkot | 9 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-09-15 | 2016-09-21 |  | Balefi | 3
17825 | Sindhupalchok | Fulpingkot |  | JICA | ERTech | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31 |  | Balefi | 3
17826 | Sindhupalchok | Fulpingkot | ALL | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 11 | 11 | 2018-01-01 | 2018-02-15 |  | Balefi | 3
17827 | Sindhupalchok | Gati | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-11-21 | 2016-12-05 |  | Barhabise | 5
17828 | Sindhupalchok | Gati | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Kukhure CBRC | Barhabise | 5
17829 | Sindhupalchok | Gati | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Khagadal CBRC | Barhabise | 5
17830 | Sindhupalchok | Gati | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-27 | 2017-02-27 |  | Barhabise | 5
17831 | Sindhupalchok | Gati | 1 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 4 | 4 | 2016-06-30 | 2016-07-06 | 1st lot (30 Jun-6-Jul-16) 2nd (16-22 Jan-17) | Barhabise | 5
17832 | Sindhupalchok | Gati | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-11-21 | 2016-12-05 |  | Barhabise | 5
17833 | Sindhupalchok | Gati | ALL | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 500 | 545 | 2017-02-03 |  |  | Barhabise | 6
17834 | Sindhupalchok | Gati | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Panchkanya CBRC | Barhabise | 5
17835 | Sindhupalchok | Gati | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-27 | 2017-02-27 |  | Barhabise | 5
17836 | Sindhupalchok | Gati | 2 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 10 | 10 | 2016-06-30 | 2016-07-06 | 1st lot (30 Jun-6-Jul-16) 2nd (16-22 Jan-17) | Barhabise | 5
17837 | Sindhupalchok | Gati | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 | 2016-11-21 | 2016-12-05 |  | Barhabise | 5
17838 | Sindhupalchok | Gati | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Setidevi CBRC | Barhabise | 5
17839 | Sindhupalchok | Gati | 3 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 2 | 2 | 2016-06-30 | 2016-07-06 | 1st lot (30 Jun-6-Jul-16) 2nd (16-22 Jan-17) | Barhabise | 5
17840 | Sindhupalchok | Gati | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-21 | 2016-12-05 |  | Barhabise | 5
17841 | Sindhupalchok | Gati | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Sundakali Setidevi CBRC | Barhabise | 5
17842 | Sindhupalchok | Gati | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-27 | 2017-02-27 |  | Barhabise | 5
17843 | Sindhupalchok | Gati | 4 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 4 | 4 | 2016-06-30 | 2016-07-06 | 1st lot (30 Jun-6-Jul-16) 2nd (16-22 Jan-17) | Barhabise | 5
17844 | Sindhupalchok | Gati | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-21 | 2016-12-05 |  | Barhabise | 5
17845 | Sindhupalchok | Gati | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Namuna CBRC | Barhabise | 5
17846 | Sindhupalchok | Gati | 5 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 2 | 2 | 2017-01-16 | 2017-01-22 |  | Barhabise | 5
17847 | Sindhupalchok | Gati | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-11-21 | 2016-12-05 |  | Barhabise | 6
17848 | Sindhupalchok | Gati | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Balhit CBRC | Barhabise | 6
17849 | Sindhupalchok | Gati | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-27 | 2017-02-27 |  | Barhabise | 6
17850 | Sindhupalchok | Gati | 6 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 9 | 9 | 2016-06-30 | 2016-07-06 | 1st lot (30 Jun-6-Jul-16) 2nd (16-22 Jan-17) | Barhabise | 6
17851 | Sindhupalchok | Gati | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 42 | 42 | 2016-11-21 | 2016-12-05 |  | Barhabise | 6
17852 | Sindhupalchok | Gati | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-08 | Shree Gorakhnath Setidevi CBRC | Barhabise | 6
17853 | Sindhupalchok | Gati | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-27 | 2017-02-27 |  | Barhabise | 6
17854 | Sindhupalchok | Gati | 7 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 6 | 6 | 2016-06-30 | 2016-07-06 | 1st lot (30 Jun-6-Jul-16) 2nd (16-22 Jan-17) | Barhabise | 6
17855 | Sindhupalchok | Gati | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-11-21 | 2016-12-05 |  | Barhabise | 6
17856 | Sindhupalchok | Gati | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-07 | Dandakateri CBRC | Barhabise | 6
17857 | Sindhupalchok | Gati | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-27 | 2017-02-27 |  | Barhabise | 6
17858 | Sindhupalchok | Gati | 8 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 9 | 9 | 2016-06-30 | 2016-07-06 | 1st lot (30 Jun-6-Jul-16) 2nd (16-22 Jan-17) | Barhabise | 6
17859 | Sindhupalchok | Gati | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 33 | 33 | 2016-11-21 | 2016-12-05 |  | Barhabise | 6
17860 | Sindhupalchok | Gati | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-01 | Bhansar CBRC | Barhabise | 6
17861 | Sindhupalchok | Gati | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-01 | Dhaneshwor CBRC | Barhabise | 6
17862 | Sindhupalchok | Gati | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-02-27 | 2017-02-27 |  | Barhabise | 6
17863 | Sindhupalchok | Gati | 9 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 13 | 13 | 2016-06-30 | 2016-07-06 | 1st lot (30 Jun-6-Jul-16) 2nd (16-22 Jan-17) | Barhabise | 6
17864 | Sindhupalchok | Gati |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31 |  | Barhabise | 6
17865 | Sindhupalchok | Gati | All | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 11 | 11 | 2018-01-01 | 2018-02-15 |  | Barhabise | 6
17866 | Sindhupalchok | Ghuskun | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-15 | 2016-12-04 |  | Tripura Sundari | 3
17867 | Sindhupalchok | Ghuskun | All | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 1000 | 566 | 2017-01-30 |  |  | Tripura Sundari | 3
17868 | Sindhupalchok | Ghuskun | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | Chhemadevi CBRC | Tripura Sundari | 3
17869 | Sindhupalchok | Ghuskun | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-02-19 |  | Tripura Sundari | 3
17870 | Sindhupalchok | Ghuskun | 1 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots masons trainings in same VDCs | # of trainees | Yes | Completed | 10 | 10 | 2016-09-13 | 2017-02-12 | 1st lot (13-19-Sep-16) 2nd lot (6-12-Feb-17) | Tripura Sundari | 3
17871 | Sindhupalchok | Ghuskun | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 | 2016-11-15 | 2016-12-04 |  | Tripura Sundari | 3
17872 | Sindhupalchok | Ghuskun | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-02-19 |  | Tripura Sundari | 3
17873 | Sindhupalchok | Ghuskun | 2 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots masons trainings in same VDCs | # of trainees | Yes | Completed | 8 | 8 | 2016-09-13 | 2017-02-12 | 1st lot (13-19-Sep-16) 2nd lot (6-12-Feb-17) | Tripura Sundari | 3
17874 | Sindhupalchok | Ghuskun | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 | 2016-11-15 | 2016-12-04 |  | Tripura Sundari | 3
17875 | Sindhupalchok | Ghuskun | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Saat Kanya CBRC | Tripura Sundari | 3
17876 | Sindhupalchok | Ghuskun | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Kabhre CBRC | Tripura Sundari | 3
17877 | Sindhupalchok | Ghuskun | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-19 | 2017-02-19 |  | Tripura Sundari | 3
17878 | Sindhupalchok | Ghuskun | 3 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots masons trainings in same VDCs | # of trainees | Yes | Completed | 7 | 7 | 2016-09-13 | 2017-02-12 | 1st lot (13-19-Sep-16) 2nd lot (6-12-Feb-17) | Tripura Sundari | 3
17879 | Sindhupalchok | Ghuskun | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 25 | 25 | 2016-11-15 | 2016-12-04 |  | Tripura Sundari | 3
17880 | Sindhupalchok | Ghuskun | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-05 | Tallogaun CBRC | Tripura Sundari | 3
17881 | Sindhupalchok | Ghuskun | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-06 | Mathillogaun CBRC | Tripura Sundari | 3
17882 | Sindhupalchok | Ghuskun | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-06 | Faparchaur CBRC | Tripura Sundari | 3
17883 | Sindhupalchok | Ghuskun | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-19 | 2017-02-19 |  | Tripura Sundari | 3
17884 | Sindhupalchok | Ghuskun | 4 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots masons trainings in same VDCs | # of trainees | Yes | Completed | 9 | 9 | 2016-09-13 | 2017-02-12 | 1st lot (13-19-Sep-16) 2nd lot (6-12-Feb-17) | Tripura Sundari | 3
17885 | Sindhupalchok | Ghuskun | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-15 | 2016-12-04 |  | Tripura Sundari | 3
17886 | Sindhupalchok | Ghuskun | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-15 | Urjaa CBRC | Tripura Sundari | 3
17887 | Sindhupalchok | Ghuskun | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-02-19 |  | Tripura Sundari | 3
17888 | Sindhupalchok | Ghuskun | 5 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots masons trainings in same VDCs | # of trainees | Yes | Completed | 3 | 3 | 2016-09-13 | 2017-02-12 | 1st lot (13-19-Sep-16) 2nd lot (6-12-Feb-17) | Tripura Sundari | 3
17889 | Sindhupalchok | Ghuskun | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 | 2016-11-15 | 2016-12-04 |  | Tripura Sundari | 3
17890 | Sindhupalchok | Ghuskun | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-19 | 2017-02-19 |  | Tripura Sundari | 3
17891 | Sindhupalchok | Ghuskun | 6 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots masons trainings in same VDCs | # of trainees | Yes | Completed | 9 | 9 | 2016-09-13 | 2017-02-12 | 1st lot (13-19-Sep-16) 2nd lot (6-12-Feb-17) | Tripura Sundari | 3
17892 | Sindhupalchok | Ghuskun | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 | 2016-11-15 | 2016-12-04 |  | Tripura Sundari | 3
17893 | Sindhupalchok | Ghuskun | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-02-19 |  | Tripura Sundari | 3
17894 | Sindhupalchok | Ghuskun | 7 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots masons trainings in same VDCs | # of trainees | Yes | Completed | 4 | 4 | 2016-09-13 | 2017-02-12 | 1st lot (13-19-Sep-16) 2nd lot (6-12-Feb-17) | Tripura Sundari | 3
17895 | Sindhupalchok | Ghuskun | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-15 | 2016-12-04 |  | Tripura Sundari | 3
17896 | Sindhupalchok | Ghuskun | 8 | JICA | TCN | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 50 | 7 | 2017-07-17 |  |  | Tripura Sundari | 3
17897 | Sindhupalchok | Ghuskun | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-19 | 2017-02-19 |  | Tripura Sundari | 3
17898 | Sindhupalchok | Ghuskun | 8 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots masons trainings in same VDCs | # of trainees | Yes | Completed | 6 | 6 | 2016-09-13 | 2017-02-12 | 1st lot (13-19-Sep-16) 2nd lot (6-12-Feb-17) | Tripura Sundari | 3
17899 | Sindhupalchok | Ghuskun | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 55 | 55 | 2016-11-15 | 2016-12-04 |  | Tripura Sundari | 3
17900 | Sindhupalchok | Ghuskun | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Siddhikali CBRC | Tripura Sundari | 3
17901 | Sindhupalchok | Ghuskun | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Siddhikali CBRC | Tripura Sundari | 3
17902 | Sindhupalchok | Ghuskun |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31 |  | Tripura Sundari | 3
17903 | Sindhupalchok | Ghuskun |  | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 15 | 11 | 2017-10-05 | 2018-02-15 |  | Tripura Sundari | 3
17904 | Sindhupalchok | Haibung | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-10-21 | 2016-10-26 |  | Melamchi | 3
17905 | Sindhupalchok | Haibung | All | JICA | TCN | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 500 | 498 | 2017-07-02 |  |  | Melamchi | 3
17906 | Sindhupalchok | Haibung | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-15 | 2017-02-16 |  | Melamchi | 3
17907 | Sindhupalchok | Haibung | 1 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-08-24 | 2016-09-11 | Training Dates are merges due to multiple batches | Melamchi | 3
17908 | Sindhupalchok | Haibung | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-10-21 | 2016-10-26 |  | Melamchi | 3
17909 | Sindhupalchok | Haibung | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | Gurung Gau CBRC | Melamchi | 3
17910 | Sindhupalchok | Haibung | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-15 | 2017-02-16 |  | Melamchi | 3
17911 | Sindhupalchok | Haibung | 2 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-08-24 | 2016-09-11 | Training Dates are merges due to multiple batches | Melamchi | 3
17912 | Sindhupalchok | Haibung | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-10-21 | 2016-10-26 |  | Melamchi | 3
17913 | Sindhupalchok | Haibung | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 24 | 24 | 2017-02-15 | 2017-02-16 |  | Melamchi | 3
17914 | Sindhupalchok | Haibung | 3 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 24 | 24 | 2016-08-24 | 2016-09-11 | Training Dates are merges due to multiple batches | Melamchi | 3
17915 | Sindhupalchok | Haibung | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 25 | 25 | 2016-10-21 | 2016-10-26 |  | Melamchi | 3
17916 | Sindhupalchok | Haibung | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | Majuwa CBRC | Melamchi | 3
17917 | Sindhupalchok | Haibung | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-15 | 2017-02-16 |  | Melamchi | 3
17918 | Sindhupalchok | Haibung | 4 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-08-24 | 2016-09-11 | Training Dates are merges due to multiple batches | Melamchi | 3
17919 | Sindhupalchok | Haibung | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-10-21 | 2016-10-26 |  | Melamchi | 3
17920 | Sindhupalchok | Haibung | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Lokeshwori CBRC | Melamchi | 3
17921 | Sindhupalchok | Haibung | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | DeviDatta CBRc | Melamchi | 3
17922 | Sindhupalchok | Haibung | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 10 | 10 | 2017-02-15 | 2017-02-16 |  | Melamchi | 3
17923 | Sindhupalchok | Haibung | 5 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-08-24 | 2016-09-11 | Training Dates are merges due to multiple batches | Melamchi | 3
17924 | Sindhupalchok | Haibung | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-10-21 | 2016-10-26 |  | Melamchi | 3
17925 | Sindhupalchok | Haibung | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-15 | 2017-02-16 |  | Melamchi | 3
17926 | Sindhupalchok | Haibung | 6 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-08-24 | 2016-09-11 | Training Dates are merges due to multiple batches | Melamchi | 3
17927 | Sindhupalchok | Haibung | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-10-21 | 2016-10-26 |  | Melamchi | 3
17928 | Sindhupalchok | Haibung | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Haibung Bhumisthan CBRC | Melamchi | 3
17929 | Sindhupalchok | Haibung | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2017-02-15 | 2017-02-16 |  | Melamchi | 3
17930 | Sindhupalchok | Haibung | 7 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-08-24 | 2016-09-11 | Training Dates are merges due to multiple batches | Melamchi | 3
17931 | Sindhupalchok | Haibung | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-10-21 | 2016-10-26 |  | Melamchi | 3
17932 | Sindhupalchok | Haibung | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Haibung Sindhupalchok CBRC | Melamchi | 3
17933 | Sindhupalchok | Haibung | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-15 | 2017-02-16 |  | Melamchi | 3
17934 | Sindhupalchok | Haibung | 8 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-08-24 | 2016-09-11 | Training Dates are merges due to multiple batches | Melamchi | 3
17935 | Sindhupalchok | Haibung | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 75 | 75 | 2016-10-21 | 2016-10-26 |  | Melamchi | 3
17936 | Sindhupalchok | Haibung | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Mathillo Dahapokhari CBRC | Melamchi | 3
17937 | Sindhupalchok | Haibung | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Tallo Dahapokhari CBRC | Melamchi | 3
17938 | Sindhupalchok | Haibung | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-15 | 2017-02-16 |  | Melamchi | 3
17939 | Sindhupalchok | Haibung | 9 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-08-24 | 2016-09-11 | Training Dates are merges due to multiple batches | Melamchi | 3
17940 | Sindhupalchok | Haibung |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31 |  | Melamchi | 3
17941 | Sindhupalchok | Haibung | All | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 12 | 12 | 2018-01-01 | 2018-02-15 |  | Melamchi | 3
17942 | Sindhupalchok | Irkhu | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 | 2016-11-20 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
17943 | Sindhupalchok | Irkhu | All | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 500 | 590 | 2017-02-09 |  |  | Chautara Sangachokgadhi | 8
17944 | Sindhupalchok | Irkhu | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Irkhu Bazzar CBRC | Chautara Sangachokgadhi | 8
17945 | Sindhupalchok | Irkhu | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | NunDanda CBRC | Chautara Sangachokgadhi | 8
17946 | Sindhupalchok | Irkhu | 1 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2016-12-26 | 2016-12-26 |  | Chautara Sangachokgadhi | 8
17947 | Sindhupalchok | Irkhu | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 2 | 2 | 2017-06-04 | 2017-06-09 |  | Chautara Sangachokgadhi | 8
17948 | Sindhupalchok | Irkhu | 1 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-08 | 2016-01-14 |  | Chautara Sangachokgadhi | 8
17949 | Sindhupalchok | Irkhu | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-20 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
17950 | Sindhupalchok | Irkhu | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | Thapa Gaun CBRC | Chautara Sangachokgadhi | 8
17951 | Sindhupalchok | Irkhu | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | chhipchet CBRC | Chautara Sangachokgadhi | 8
17952 | Sindhupalchok | Irkhu | 2 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2016-12-26 | 2016-12-26 |  | Chautara Sangachokgadhi | 8
17953 | Sindhupalchok | Irkhu | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 2 | 2 | 2017-06-04 | 2017-06-09 |  | Chautara Sangachokgadhi | 8
17954 | Sindhupalchok | Irkhu | 2 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-01-08 | 2016-01-14 |  | Chautara Sangachokgadhi | 8
17955 | Sindhupalchok | Irkhu | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 70 | 2016-11-20 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
17956 | Sindhupalchok | Irkhu | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Shyangtang CBRC | Chautara Sangachokgadhi | 8
17957 | Sindhupalchok | Irkhu | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Mulabari CBRC | Chautara Sangachokgadhi | 8
17958 | Sindhupalchok | Irkhu | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 1 | 1 | 2017-06-04 | 2017-06-09 |  | Chautara Sangachokgadhi | 8
17959 | Sindhupalchok | Irkhu | 3 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-08 | 2016-01-14 |  | Chautara Sangachokgadhi | 8
17960 | Sindhupalchok | Irkhu | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 33 | 33 | 2016-11-20 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
17961 | Sindhupalchok | Irkhu | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Tallodip CBRC | Chautara Sangachokgadhi | 8
17962 | Sindhupalchok | Irkhu | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Batase CBRC | Chautara Sangachokgadhi | 8
17963 | Sindhupalchok | Irkhu | 4 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2016-12-26 | 2016-12-26 |  | Chautara Sangachokgadhi | 8
17964 | Sindhupalchok | Irkhu | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 2 | 2 | 2017-06-04 | 2017-06-09 |  | Chautara Sangachokgadhi | 8
17965 | Sindhupalchok | Irkhu | 4 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-08 | 2016-01-14 |  | Chautara Sangachokgadhi | 8
17966 | Sindhupalchok | Irkhu | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-20 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
17967 | Sindhupalchok | Irkhu | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-11 | Tamang Tole CBRC | Chautara Sangachokgadhi | 8
17968 | Sindhupalchok | Irkhu | 5 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2016-12-26 | 2016-12-26 |  | Chautara Sangachokgadhi | 8
17969 | Sindhupalchok | Irkhu | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 1 | 1 | 2017-06-04 | 2017-06-09 |  | Chautara Sangachokgadhi | 8
17970 | Sindhupalchok | Irkhu | 5 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-08 | 2016-01-14 |  | Chautara Sangachokgadhi | 8
17971 | Sindhupalchok | Irkhu | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-20 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
17972 | Sindhupalchok | Irkhu | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Diyale CBRC | Chautara Sangachokgadhi | 8
17973 | Sindhupalchok | Irkhu | 6 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2016-12-26 | 2016-12-26 |  | Chautara Sangachokgadhi | 8
17974 | Sindhupalchok | Irkhu | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 1 | 1 | 2017-06-04 | 2017-06-09 |  | Chautara Sangachokgadhi | 8
17975 | Sindhupalchok | Irkhu | 6 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-08 | 2016-01-14 |  | Chautara Sangachokgadhi | 8
17976 | Sindhupalchok | Irkhu | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 60 | 60 | 2016-11-20 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
17977 | Sindhupalchok | Irkhu | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Gahatetole CBRC | Chautara Sangachokgadhi | 8
17978 | Sindhupalchok | Irkhu | 7 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2016-12-26 | 2016-12-26 |  | Chautara Sangachokgadhi | 8
17979 | Sindhupalchok | Irkhu | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 1 | 1 | 2017-06-04 | 2017-06-09 |  | Chautara Sangachokgadhi | 8
17980 | Sindhupalchok | Irkhu | 7 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-01-08 | 2016-03-01 | 3 more trained with chautara group later | Chautara Sangachokgadhi | 8
17981 | Sindhupalchok | Irkhu | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-20 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
17982 | Sindhupalchok | Irkhu | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Pokhare CBRC | Chautara Sangachokgadhi | 8
17983 | Sindhupalchok | Irkhu | 8 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2016-12-26 | 2016-12-26 |  | Chautara Sangachokgadhi | 8
17984 | Sindhupalchok | Irkhu | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 1 | 1 | 2017-06-04 | 2017-06-09 |  | Chautara Sangachokgadhi | 8
17985 | Sindhupalchok | Irkhu | 8 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-01-08 | 2016-03-01 | 4 more trained with chautara group later | Chautara Sangachokgadhi | 8
17986 | Sindhupalchok | Irkhu | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-20 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
17987 | Sindhupalchok | Irkhu | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Mandanda CBRC | Chautara Sangachokgadhi | 8
17988 | Sindhupalchok | Irkhu | 9 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2016-12-26 | 2016-12-26 |  | Chautara Sangachokgadhi | 8
17989 | Sindhupalchok | Irkhu | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 1 | 1 | 2017-06-04 | 2017-06-09 |  | Chautara Sangachokgadhi | 8
17990 | Sindhupalchok | Irkhu | 9 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-01-08 | 2016-03-01 | 2 more trained with Chautara group later | Chautara Sangachokgadhi | 8
17991 | Sindhupalchok | Irkhu |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 90 | 2016-04-01 | 2020-12-31 |  | Chautara Sangachokgadhi | 8
17992 | Sindhupalchok | Kadambas | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 42 | 42 | 2016-11-20 | 2016-11-30 |  | Chautara Sangachokgadhi | 9
17993 | Sindhupalchok | Kadambas | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Simle CBRC | Chautara Sangachokgadhi | 9
17994 | Sindhupalchok | Kadambas | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Lapse CBRC | Chautara Sangachokgadhi | 9
17995 | Sindhupalchok | Kadambas | 1 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-01-03 | 2017-01-03 |  | Chautara Sangachokgadhi | 9
17996 | Sindhupalchok | Kadambas | 1 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 11 | 11 | 2016-02-09 | 2017-02-02 | 1st lot in Feb 9-15, 2016 and 2nd in 5-11 Sep-16 and 3rd in Jan 27- 2 Feb -2017 | Chautara Sangachokgadhi | 9
17997 | Sindhupalchok | Kadambas | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 65 | 65 | 2016-11-20 | 2016-11-30 |  | Chautara Sangachokgadhi | 9
17998 | Sindhupalchok | Kadambas | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Kadambas ward-2 & 3 | Chautara Sangachokgadhi | 9
17999 | Sindhupalchok | Kadambas | All | JICA | TCN | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 500 | 706 | 2017-07-13 |  |  | Chautara Sangachokgadhi | 9
18000 | Sindhupalchok | Kadambas | 2 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-01-03 | 2017-01-03 |  | Chautara Sangachokgadhi | 9
18001 | Sindhupalchok | Kadambas | 2 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 11 | 11 | 2016-02-09 | 2017-02-02 | 1st lot in Feb 9-15, 2016 and 2nd in 5-11 Sep-16 and 3rd in Jan 27- 2 Feb -2017 | Chautara Sangachokgadhi | 9
18002 | Sindhupalchok | Kadambas | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 60 | 60 | 2016-11-20 | 2016-11-30 |  | Chautara Sangachokgadhi | 9
18003 | Sindhupalchok | Kadambas | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Kadambas ward-2 & 3 | Chautara Sangachokgadhi | 9
18004 | Sindhupalchok | Kadambas | 3 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-01-03 | 2017-01-03 |  | Chautara Sangachokgadhi | 9
18005 | Sindhupalchok | Kadambas | 3 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 4 | 4 | 2016-02-09 | 2017-02-02 | 1st lot in Feb 9-15, 2016 and 2nd in 5-11 Sep-16 and 3rd in Jan 27- 2 Feb -2017 | Chautara Sangachokgadhi | 9
18006 | Sindhupalchok | Kadambas | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 65 | 65 | 2016-11-20 | 2016-11-30 |  | Chautara Sangachokgadhi | 9
18007 | Sindhupalchok | Kadambas | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-17 | Kadambas ward-4 CBRC | Chautara Sangachokgadhi | 9
18008 | Sindhupalchok | Kadambas | 4 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-01-03 | 2017-01-03 |  | Chautara Sangachokgadhi | 9
18009 | Sindhupalchok | Kadambas | 4 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 15 | 15 | 2016-02-09 | 2017-02-02 | 1st lot in Feb 9-15, 2016 and 2nd in 5-11 Sep-16 and 3rd in Jan 27- 2 Feb -2017 | Chautara Sangachokgadhi | 9
18010 | Sindhupalchok | Kadambas | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 51 | 51 | 2016-11-20 | 2016-11-30 |  | Chautara Sangachokgadhi | 9
18011 | Sindhupalchok | Kadambas | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-17 | Kadambas ward-5 CBRC | Chautara Sangachokgadhi | 9
18012 | Sindhupalchok | Kadambas | 5 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-01-03 | 2017-01-03 |  | Chautara Sangachokgadhi | 9
18013 | Sindhupalchok | Kadambas | 5 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 11 | 11 | 2016-02-09 | 2017-02-02 | 1st lot in Feb 9-15, 2016 and 2nd in 5-11 Sep-16 and 3rd in Jan 27- 2 Feb -2017 | Chautara Sangachokgadhi | 9
18014 | Sindhupalchok | Kadambas | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 75 | 75 | 2016-11-20 | 2016-11-30 |  | Chautara Sangachokgadhi | 9
18015 | Sindhupalchok | Kadambas | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Siranchaur Mathilo Tole CBRC | Chautara Sangachokgadhi | 9
18016 | Sindhupalchok | Kadambas | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Siranchaur Tallo Tole CBRC | Chautara Sangachokgadhi | 9
18017 | Sindhupalchok | Kadambas | 6 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 10 | 10 | 2016-02-09 | 2017-02-02 | 1st lot in Feb 9-15, 2016 and 2nd in 5-11 Sep-16 and 3rd in Jan 27- 2 Feb -2017 | Chautara Sangachokgadhi | 9
18018 | Sindhupalchok | Kadambas | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 73 | 73 | 2016-11-20 | 2016-11-30 |  | Chautara Sangachokgadhi | 9
18019 | Sindhupalchok | Kadambas | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-17 | Kadambas ward-7 CBRC | Chautara Sangachokgadhi | 9
18020 | Sindhupalchok | Kadambas | 7 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-01-03 | 2017-01-03 |  | Chautara Sangachokgadhi | 9
18021 | Sindhupalchok | Kadambas | 7 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 12 | 12 | 2016-02-09 | 2017-02-02 | 1st lot in Feb 9-15, 2016 and 2nd in 5-11 Sep-16 and 3rd in Jan 27- 2 Feb -2017 | Chautara Sangachokgadhi | 9
18022 | Sindhupalchok | Kadambas | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 20 | 20 | 2016-11-20 | 2016-11-30 |  | Chautara Sangachokgadhi | 9
18023 | Sindhupalchok | Kadambas | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Andheri CBRC | Chautara Sangachokgadhi | 9
18024 | Sindhupalchok | Kadambas | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 100 | 2016-11-20 | 2016-11-30 |  | Chautara Sangachokgadhi | 9
18025 | Sindhupalchok | Kadambas | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-21 | Mulkharka CBRC | Chautara Sangachokgadhi | 9
18026 | Sindhupalchok | Kadambas | 9 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-01-03 | 2017-01-03 |  | Chautara Sangachokgadhi | 9
18027 | Sindhupalchok | Kadambas | 9 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 8 | 8 | 2016-02-09 | 2017-02-02 | 1st lot in Feb 9-15, 2016 and 2nd in 5-11 Sep-16 and 3rd in Jan 27- 2 Feb -2017 | Chautara Sangachokgadhi | 9
18028 | Sindhupalchok | Kadambas | 9 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 11 | 11 | 2016-02-09 | 2017-02-02 | 1st lot in Feb 9-15, 2016 and 2nd in 5-11 Sep-16 and 3rd in Jan 27- 2 Feb -2017 | Chautara Sangachokgadhi | 9
18029 | Sindhupalchok | Kadambas |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 95 | 2016-04-01 | 2020-12-31 |  | Chautara Sangachokgadhi | 9
18030 | Sindhupalchok | Kadambas |  | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 11 | 10 | 2017-06-17 | 2018-02-15 |  | Chautara Sangachokgadhi | 9
18031 | Sindhupalchok | Karthali | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 | 2016-10-01 | 2016-10-04 |  | Barhabise | 2
18032 | Sindhupalchok | Karthali | All | JICA | ERTech | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 500 | 436 | 2016-10-03 | 2016-10-06 |  | Barhabise | 2
18033 | Sindhupalchok | Karthali | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Ripar Setidevi CBRC | Barhabise | 2
18034 | Sindhupalchok | Karthali | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Kalinchwok CBRC | Barhabise | 2
18035 | Sindhupalchok | Karthali | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | Khiping CBRC | Barhabise | 2
18036 | Sindhupalchok | Karthali | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-18 | 2017-02-18 |  | Barhabise | 2
18037 | Sindhupalchok | Karthali | 1 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 11 | 11 | 2016-06-30 | 2017-01-31 | 1st lot (30 jun-6 Jul-16) 2nd lot (25-31 Jan-17) | Barhabise | 2
18038 | Sindhupalchok | Karthali | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 |  |  |  | Barhabise | 2
18039 | Sindhupalchok | Karthali | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Kabhre Gurung CBRC | Barhabise | 2
18040 | Sindhupalchok | Karthali | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-18 | 2017-02-18 |  | Barhabise | 2
18041 | Sindhupalchok | Karthali | 2 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 5 | 5 | 2016-06-30 | 2017-01-31 | 1st lot (30 jun-6 Jul-16) 2nd lot (25-31 Jan-17) | Barhabise | 2
18042 | Sindhupalchok | Karthali | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 34 | 34 |  |  |  | Barhabise | 2
18043 | Sindhupalchok | Karthali | 3 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 3 | 2017-02-01 |  |  | Barhabise | 2
18044 | Sindhupalchok | Karthali | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Sunkoshi CBRC | Barhabise | 2
18045 | Sindhupalchok | Karthali | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Bagar Baseri CBRC | Barhabise | 2
18046 | Sindhupalchok | Karthali | 3 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 5 | 5 | 2016-06-30 | 2017-01-31 | 1st lot (30 jun-6 Jul-16) 2nd lot (25-31 Jan-17) | Barhabise | 2
18047 | Sindhupalchok | Karthali | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 53 | 53 |  |  |  | Barhabise | 2
18048 | Sindhupalchok | Karthali | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Mahankali CBRC | Barhabise | 2
18049 | Sindhupalchok | Karthali | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-18 | 2017-02-18 |  | Barhabise | 2
18050 | Sindhupalchok | Karthali | 4 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-30 | 2016-07-06 |  | Barhabise | 2
18051 | Sindhupalchok | Karthali | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 61 | 61 |  |  |  | Barhabise | 2
18052 | Sindhupalchok | Karthali | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Seti devi CBRC | Barhabise | 2
18053 | Sindhupalchok | Karthali | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Latteswori mahadev CBRC | Barhabise | 2
18054 | Sindhupalchok | Karthali | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-02-18 | 2017-02-18 |  | Barhabise | 2
18055 | Sindhupalchok | Karthali | 5 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-30 | 2016-07-06 |  | Barhabise | 2
18056 | Sindhupalchok | Karthali | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 63 | 63 |  |  |  | Barhabise | 2
18057 | Sindhupalchok | Karthali | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Lali Gurans CBRC | Barhabise | 2
18058 | Sindhupalchok | Karthali | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-18 | 2017-02-18 |  | Barhabise | 2
18059 | Sindhupalchok | Karthali | 6 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 5 | 5 | 2016-06-30 | 2017-01-31 | 1st lot (30 jun-6 Jul-16) 2nd lot (25-31 Jan-17) | Barhabise | 2
18060 | Sindhupalchok | Karthali | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 54 | 54 |  |  |  | Barhabise | 2
18061 | Sindhupalchok | Karthali | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Sundaridevi CBRC | Barhabise | 2
18062 | Sindhupalchok | Karthali | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-18 | 2017-02-18 |  | Barhabise | 2
18063 | Sindhupalchok | Karthali | 7 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-30 | 2016-07-06 |  | Barhabise | 2
18064 | Sindhupalchok | Karthali | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 36 | 36 |  |  |  | Barhabise | 2
18065 | Sindhupalchok | Karthali | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Aakashwani Devi CBRC | Barhabise | 2
18066 | Sindhupalchok | Karthali | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-02-18 | 2017-02-18 |  | Barhabise | 2
18067 | Sindhupalchok | Karthali | 8 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 12 | 12 | 2016-06-30 | 2017-01-31 | 1st lot (30 jun-6 Jul-16) 2nd lot (25-31 Jan-17) | Barhabise | 2
18068 | Sindhupalchok | Karthali | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 41 | 41 |  |  |  | Barhabise | 2
18069 | Sindhupalchok | Karthali | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Shree Kamala Devi CBRC | Barhabise | 2
18070 | Sindhupalchok | Karthali | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-18 | 2017-02-18 |  | Barhabise | 2
18071 | Sindhupalchok | Karthali | 9 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 8 | 8 | 2016-06-30 | 2017-01-31 | 1st lot (30 jun-6 Jul-16) 2nd lot (25-31 Jan-17) | Barhabise | 2
18072 | Sindhupalchok | Karthali |  | JICA | ERTech | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31 |  | Barhabise | 2
18073 | Sindhupalchok | Karthali |  | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 15 | 11 | 2017-10-21 | 2018-02-15 |  | Barhabise | 2
18074 | Sindhupalchok | Maneswor | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 66 | 66 | 2016-10-19 | 2016-11-10 |  | Barhabise | 8
18075 | Sindhupalchok | Maneswor | All | JICA | ERTech | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 500 | 570 | 2017-02-13 |  |  | Barhabise | 8
18076 | Sindhupalchok | Maneswor | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-28 | 2017-02-28 |  | Barhabise | 8
18077 | Sindhupalchok | Maneswor | 1 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 8 | 8 | 2016-07-19 | 2017-02-22 | 1St lot (19-25-Jul-16) 2nd lot (16-22-Feb-17) | Barhabise | 8
18078 | Sindhupalchok | Maneswor | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 76 | 76 | 2016-10-19 | 2016-11-10 |  | Barhabise | 8
18079 | Sindhupalchok | Maneswor | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Sangbari CBRC | Barhabise | 8
18080 | Sindhupalchok | Maneswor | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-28 | 2017-02-28 |  | Barhabise | 8
18081 | Sindhupalchok | Maneswor | 2 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 6 | 6 | 2016-07-19 | 2017-02-22 | 1St lot (19-25-Jul-16) 2nd lot (16-22-Feb-17) | Barhabise | 8
18082 | Sindhupalchok | Maneswor | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 63 | 63 | 2016-10-19 | 2016-11-10 |  | Barhabise | 8
18083 | Sindhupalchok | Maneswor | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-21 | Ghude CBRC | Barhabise | 8
18084 | Sindhupalchok | Maneswor | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-22 | Maneswnara CBRC | Barhabise | 8
18085 | Sindhupalchok | Maneswor | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-28 | 2017-02-28 |  | Barhabise | 8
18086 | Sindhupalchok | Maneswor | 3 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 5 | 5 | 2016-07-19 | 2017-02-22 | 1St lot (19-25-Jul-16) 2nd lot (16-22-Feb-17) | Barhabise | 8
18087 | Sindhupalchok | Maneswor | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 32 | 32 | 2016-10-19 | 2016-11-10 |  | Barhabise | 8
18088 | Sindhupalchok | Maneswor | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-28 | 2017-02-28 |  | Barhabise | 8
18089 | Sindhupalchok | Maneswor | 4 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 3 | 3 | 2016-07-19 | 2017-02-22 | 1St lot (19-25-Jul-16) 2nd lot (16-22-Feb-17) | Barhabise | 8
18090 | Sindhupalchok | Maneswor | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 41 | 41 | 2016-10-19 | 2016-11-10 |  | Barhabise | 8
18091 | Sindhupalchok | Maneswor | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2017-02-28 | 2017-02-28 |  | Barhabise | 8
18092 | Sindhupalchok | Maneswor | 5 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 8 | 8 | 2016-07-19 | 2017-02-22 | 1St lot (19-25-Jul-16) 2nd lot (16-22-Feb-17) | Barhabise | 8
18093 | Sindhupalchok | Maneswor | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-10-19 | 2016-11-10 |  | Barhabise | 8
18094 | Sindhupalchok | Maneswor | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2017-02-28 | 2017-02-28 |  | Barhabise | 8
18095 | Sindhupalchok | Maneswor | 6 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 7 | 7 | 2016-07-19 | 2017-02-22 | 1St lot (19-25-Jul-16) 2nd lot (16-22-Feb-17) | Barhabise | 8
18096 | Sindhupalchok | Maneswor | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 31 | 31 | 2016-10-19 | 2016-11-10 |  | Barhabise | 8
18097 | Sindhupalchok | Maneswor | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Borabari CBRC | Barhabise | 8
18098 | Sindhupalchok | Maneswor | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-28 | 2017-02-28 |  | Barhabise | 8
18099 | Sindhupalchok | Maneswor | 7 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 10 | 10 | 2016-07-19 | 2017-02-22 | 1St lot (19-25-Jul-16) 2nd lot (16-22-Feb-17) | Barhabise | 8
18100 | Sindhupalchok | Maneswor | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-10-19 | 2016-11-10 |  | Barhabise | 8
18101 | Sindhupalchok | Maneswor | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Subeditol CBRC | Barhabise | 8
18102 | Sindhupalchok | Maneswor | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-28 | 2017-02-28 |  | Barhabise | 8
18103 | Sindhupalchok | Maneswor | 8 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 7 | 7 | 2016-07-19 | 2017-02-22 | 1St lot (19-25-Jul-16) 2nd lot (16-22-Feb-17) | Barhabise | 8
18104 | Sindhupalchok | Maneswor | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 | 2016-10-19 | 2016-11-10 |  | Barhabise | 8
18105 | Sindhupalchok | Maneswor | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Kharibote CBRC | Barhabise | 8
18106 | Sindhupalchok | Maneswor | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-28 | 2017-02-28 |  | Barhabise | 8
18107 | Sindhupalchok | Maneswor | 9 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 4 | 4 | 2016-07-19 | 2017-02-22 | 1St lot (19-25-Jul-16) 2nd lot (16-22-Feb-17) | Barhabise | 8
18108 | Sindhupalchok | Maneswor |  | JICA | ERTech | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31 |  | Barhabise | 8
18109 | Sindhupalchok | Maneswor |  | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 10 | 10 | 2017-10-22 | 2017-11-01 |  | Barhabise | 8
18110 | Sindhupalchok | Mankha | 1 | JICA | ERTech | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 87 | 87 | 2016-09-27 | 2016-10-04 |  | Balefi | 8
18111 | Sindhupalchok | Mankha | All | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 1000 | 633 | 2017-02-02 |  |  | Balefi | 7
18112 | Sindhupalchok | Mankha | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Lamosanghu CBRC | Balefi | 8
18113 | Sindhupalchok | Mankha | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Phantbasti CBRC | Balefi | 8
18114 | Sindhupalchok | Mankha | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Baseri CBRC | Balefi | 8
18115 | Sindhupalchok | Mankha | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Topka CBRC | Balefi | 8
18116 | Sindhupalchok | Mankha | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2017-02-24 | 2017-02-24 |  | Balefi | 8
18117 | Sindhupalchok | Mankha | 1 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 10 | 10 | 2016-07-15 | 2016-09-11 | 15-21-Jul-16) 2nd lot (5-11-Sep-16) | Balefi | 8
18118 | Sindhupalchok | Mankha | 2 | JICA | ERTech | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 69 | 69 | 2016-09-27 | 2016-10-04 |  | Balefi | 8
18119 | Sindhupalchok | Mankha | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Paharigaun CBRC | Balefi | 8
18120 | Sindhupalchok | Mankha | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-24 | 2017-02-24 |  | Balefi | 8
18121 | Sindhupalchok | Mankha | 2 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 5 | 5 | 2016-07-15 | 2016-09-11 | 15-21-Jul-16) 2nd lot (5-11-Sep-16) | Balefi | 8
18122 | Sindhupalchok | Mankha | 3 | JICA | ERTech | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 36 | 36 | 2016-09-27 | 2016-10-04 |  | Balefi | 7
18123 | Sindhupalchok | Mankha | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Mathillogaun Bamjantol CBRC | Balefi | 7
18124 | Sindhupalchok | Mankha | 3 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 3 | 3 | 2016-07-15 | 2016-09-11 | 15-21-Jul-16) 2nd lot (5-11-Sep-16) | Balefi | 7
18125 | Sindhupalchok | Mankha | 4 | JICA | ERTech | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 58 | 58 | 2016-09-27 | 2016-10-04 |  | Balefi | 7
18126 | Sindhupalchok | Mankha | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Mankha-4 CBRC | Balefi | 7
18127 | Sindhupalchok | Mankha | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-24 | 2017-02-24 |  | Balefi | 7
18128 | Sindhupalchok | Mankha | 4 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 11 | 11 | 2016-07-15 | 2016-09-11 | 15-21-Jul-16) 2nd lot (5-11-Sep-16) | Balefi | 7
18129 | Sindhupalchok | Mankha | 5 | JICA | ERTech | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 63 | 63 | 2016-09-27 | 2016-10-04 |  | Balefi | 7
18130 | Sindhupalchok | Mankha | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Kafalbot CBRC | Balefi | 7
18131 | Sindhupalchok | Mankha | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-24 | 2017-02-24 |  | Balefi | 7
18132 | Sindhupalchok | Mankha | 5 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 2 | 2 | 2016-07-15 | 2016-09-11 | 15-21-Jul-16) 2nd lot (5-11-Sep-16) | Balefi | 7
18133 | Sindhupalchok | Mankha | 6 | JICA | ERTech | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 33 | 33 | 2016-09-27 | 2016-10-04 |  | Balefi | 7
18134 | Sindhupalchok | Mankha | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Sunkoshi CBRC | Balefi | 7
18135 | Sindhupalchok | Mankha | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-24 | 2017-02-24 |  | Balefi | 7
18136 | Sindhupalchok | Mankha | 6 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 3 | 3 | 2016-07-15 | 2016-09-11 | 15-21-Jul-16) 2nd lot (5-11-Sep-16) | Balefi | 7
18137 | Sindhupalchok | Mankha | 7 | JICA | ERTech | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 | 2016-09-27 | 2016-10-04 |  | Balefi | 6
18138 | Sindhupalchok | Mankha | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Mankha CBRC | Balefi | 6
18139 | Sindhupalchok | Mankha | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 9 | 9 | 2017-02-24 | 2017-02-24 |  | Balefi | 6
18140 | Sindhupalchok | Mankha | 7 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 12 | 12 | 2016-07-15 | 2016-09-11 | 15-21-Jul-16) 2nd lot (5-11-Sep-16) | Balefi | 6
18141 | Sindhupalchok | Mankha | 8 | JICA | ERTech | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 63 | 63 | 2016-09-27 | 2016-10-04 |  | Balefi | 6
18142 | Sindhupalchok | Mankha | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Bandarpa CBRC | Balefi | 6
18143 | Sindhupalchok | Mankha | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-24 | 2017-02-24 |  | Balefi | 6
18144 | Sindhupalchok | Mankha | 8 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 5 | 5 | 2016-07-15 | 2016-09-11 | 15-21-Jul-16) 2nd lot (5-11-Sep-16) | Balefi | 6
18145 | Sindhupalchok | Mankha | 9 | JICA | ERTech | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 57 | 57 | 2016-09-27 | 2016-10-04 |  | Balefi | 6
18146 | Sindhupalchok | Mankha | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Jaalbari CBRC | Balefi | 6
18147 | Sindhupalchok | Mankha | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-24 | 2017-02-24 |  | Balefi | 6
18148 | Sindhupalchok | Mankha | 9 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 6 | 6 | 2016-07-15 | 2016-09-11 | 15-21-Jul-16) 2nd lot (5-11-Sep-16) | Balefi | 6
18149 | Sindhupalchok | Mankha |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31 |  | Balefi | 7
18150 | Sindhupalchok | Mankha | All | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 17 | 17 | 2018-01-01 | 2018-02-15 |  | Balefi | 7
18151 | Sindhupalchok | Melamchi N.P. | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-08 | Dunganabesi CBRC | Melamchi | 6
18152 | Sindhupalchok | Melamchi N.P. | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-02 | Batase CBRC | Melamchi | 6
18153 | Sindhupalchok | Melamchi N.P. | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-12 | Tar CBRC | Melamchi | 6
18154 | Sindhupalchok | Melamchi N.P. | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-13 | Kole chaur CBRC | Melamchi | 6
18155 | Sindhupalchok | Melamchi N.P. | 1 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Completed | 20 | 20 | 2016-03-30 | 2016-12-16 | mason training completed in different 6 lots (29-Jul-4 Aug-16, 2-8-Aug-16, 23-29-Sep-16, 6-12-Aug-16,10-16-Dec-16, 30 Mar-5 Apr-16) | Melamchi | 6
18156 | Sindhupalchok | Melamchi N.P. | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-01 | Derali CBRC | Melamchi | 6
18157 | Sindhupalchok | Melamchi N.P. | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-02 | Chapabot CBRC | Melamchi | 6
18158 | Sindhupalchok | Melamchi N.P. | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-06 | panchakanya CBRC | Melamchi | 6
18159 | Sindhupalchok | Melamchi N.P. | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-12 | ludetol Dhara CBRC | Melamchi | 6
18160 | Sindhupalchok | Melamchi N.P. | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-10 | Deuja tole CBRC | Melamchi | 6
18161 | Sindhupalchok | Melamchi N.P. | 2 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Completed | 19 | 19 | 2016-03-30 | 2016-12-16 | mason training completed in different 6 lots (29-Jul-4 Aug-16, 2-8-Aug-16, 23-29-Sep-16, 6-12-Aug-16,10-16-Dec-16, 30 Mar-5 Apr-16) | Melamchi | 6
18162 | Sindhupalchok | Melamchi N.P. | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-08 | Sindhukot ward 1 CBRC | Melamchi | 5
18163 | Sindhupalchok | Melamchi N.P. | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-07 | Sindhukot ward 4 CBRC | Melamchi | 5
18164 | Sindhupalchok | Melamchi N.P. | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-07 | Sindhukot ward 5 CBRC | Melamchi | 5
18165 | Sindhupalchok | Melamchi N.P. | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-06 | Sindhukot ward 9 CBRC | Melamchi | 5
18166 | Sindhupalchok | Melamchi N.P. | 3 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 19 | 19 | 2016-03-30 | 2016-12-16 | mason training completed in different 6 lots (29-Jul-4 Aug-16, 2-8-Aug-16, 23-29-Sep-16, 6-12-Aug-16,10-16-Dec-16, 30 Mar-5 Apr-16) | Melamchi | 5
18167 | Sindhupalchok | Melamchi N.P. | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-06 | Sindhukot ward 2 CBRC | Melamchi | 5
18168 | Sindhupalchok | Melamchi N.P. | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-09 | Sindhukot ward 3 CBRC | Melamchi | 5
18169 | Sindhupalchok | Melamchi N.P. | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-10 | Sindhukot ward 6 CBRC | Melamchi | 5
18170 | Sindhupalchok | Melamchi N.P. | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-10 | Sindhukot ward 7 CBRC | Melamchi | 5
18171 | Sindhupalchok | Melamchi N.P. | 4 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 22 | 22 | 2016-03-30 | 2016-12-16 | mason training completed in different 6 lots (29-Jul-4 Aug-16, 2-8-Aug-16, 23-29-Sep-16, 6-12-Aug-16,10-16-Dec-16, 30 Mar-5 Apr-16) | Melamchi | 5
18172 | Sindhupalchok | Melamchi N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Majha tol CBRC | Melamchi | 11
18173 | Sindhupalchok | Melamchi N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Daduwa CBRC | Melamchi | 11
18174 | Sindhupalchok | Melamchi N.P. | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Sindhukot ward 8 CBRC | Melamchi | 11
18175 | Sindhupalchok | Melamchi N.P. | 5 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 8 | 8 | 2016-03-30 | 2016-12-16 | mason training completed in different 6 lots (29-Jul-4 Aug-16, 2-8-Aug-16, 23-29-Sep-16, 6-12-Aug-16,10-16-Dec-16, 30 Mar-5 Apr-16) | Melamchi | 11
18176 | Sindhupalchok | Melamchi N.P. | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Katunje dulal tole CBRC | Melamchi | 11
18177 | Sindhupalchok | Melamchi N.P. | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Kartike simpani CBRC | Melamchi | 11
18178 | Sindhupalchok | Melamchi N.P. | 6 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 6 | 6 | 2016-03-30 | 2016-12-16 | mason training completed in different 6 lots (29-Jul-4 Aug-16, 2-8-Aug-16, 23-29-Sep-16, 6-12-Aug-16,10-16-Dec-16, 30 Mar-5 Apr-16) | Melamchi | 11
18179 | Sindhupalchok | Melamchi N.P. | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Arukharka CBRC | Melamchi | 11
18180 | Sindhupalchok | Melamchi N.P. | 8 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 0 | 2016-03-30 | 2016-12-16 | mason training completed in different 6 lots (29-Jul-4 Aug-16, 2-8-Aug-16, 23-29-Sep-16, 6-12-Aug-16,10-16-Dec-16, 30 Mar-5 Apr-16) | Melamchi | 12
18181 | Sindhupalchok | Melamchi N.P. | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Aapchaur CBRC | Melamchi | 12
18182 | Sindhupalchok | Melamchi N.P. | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-10 | Bansbari ward 5 CBRC | Melamchi | 12
18183 | Sindhupalchok | Melamchi N.P. | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Bansbari ward 6 CBRC | Melamchi | 12
18184 | Sindhupalchok | Melamchi N.P. | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-01 | Bansbari ward 7 CBRC | Melamchi | 12
18185 | Sindhupalchok | Melamchi N.P. | 8 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 16 | 16 | 2016-03-30 | 2016-12-16 | mason training completed in different 6 lots (29-Jul-4 Aug-16, 2-8-Aug-16, 23-29-Sep-16, 6-12-Aug-16,10-16-Dec-16, 30 Mar-5 Apr-16) | Melamchi | 12
18186 | Sindhupalchok | Melamchi N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-05 | Bansbari ward 3 CBRC | Melamchi | 12
18187 | Sindhupalchok | Melamchi N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-05 | Bansbari ward 4 CBRC | Melamchi | 12
18188 | Sindhupalchok | Melamchi N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-04 | Bansbari ward 8 CBRC | Melamchi | 12
18189 | Sindhupalchok | Melamchi N.P. | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-03 | Bansbari ward 9 CBRC | Melamchi | 12
18190 | Sindhupalchok | Melamchi N.P. | 9 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 7 | 7 | 2016-03-30 | 2016-12-16 | mason training completed in different 6 lots (29-Jul-4 Aug-16, 2-8-Aug-16, 23-29-Sep-16, 6-12-Aug-16,10-16-Dec-16, 30 Mar-5 Apr-16) | Melamchi | 12
18191 | Sindhupalchok | Melamchi N.P. | 10 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-31 | Fatakshila ward 1 CBRC | Melamchi | 13
18192 | Sindhupalchok | Melamchi N.P. | 10 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-23 | Fatakshila ward 2 CBRC | Melamchi | 13
18193 | Sindhupalchok | Melamchi N.P. | 10 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-25 | Fatakshila ward 3 CBRC | Melamchi | 13
18194 | Sindhupalchok | Melamchi N.P. | 10 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-25 | Fatakshila ward 4 CBRC | Melamchi | 13
18195 | Sindhupalchok | Melamchi N.P. | 10 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 1 | 1 | 2016-03-30 | 2016-12-16 | mason training completed in different 6 lots (29-Jul-4 Aug-16, 2-8-Aug-16, 23-29-Sep-16, 6-12-Aug-16,10-16-Dec-16, 30 Mar-5 Apr-16) | Melamchi | 13
18196 | Sindhupalchok | Melamchi N.P. | 11 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-23 | Fatakshila ward 5 CBRC | Melamchi | 13
18197 | Sindhupalchok | Melamchi N.P. | 11 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-26 | Fatakshila ward 8 CBRC | Melamchi | 13
18198 | Sindhupalchok | Melamchi N.P. | 11 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 5 | 5 | 2016-03-30 | 2016-12-16 | mason training completed in different 6 lots (29-Jul-4 Aug-16, 2-8-Aug-16, 23-29-Sep-16, 6-12-Aug-16,10-16-Dec-16, 30 Mar-5 Apr-16) | Melamchi | 13
18199 | Sindhupalchok | Melamchi N.P. | 12 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-27 | Sikharpur ward 4 CBRC | Melamchi | 10
18200 | Sindhupalchok | Melamchi N.P. | 12 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-29 | Sikharpur ward 6 CBRC | Melamchi | 10
18201 | Sindhupalchok | Melamchi N.P. | 12 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-31 | Sikharpur ward 7 CBRC | Melamchi | 10
18202 | Sindhupalchok | Melamchi N.P. | 12 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-31 | Acharya tole CBRC | Melamchi | 10
18203 | Sindhupalchok | Melamchi N.P. | 12 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-01 | Sikharpur ward 8 CBRC | Melamchi | 10
18204 | Sindhupalchok | Melamchi N.P. | 12 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-02 | Sikharpur ward 9 CBRC | Melamchi | 10
18205 | Sindhupalchok | Melamchi N.P. | 12 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 22 | 22 | 2016-03-30 | 2016-12-16 | mason training completed in different 6 lots (29-Jul-4 Aug-16, 2-8-Aug-16, 23-29-Sep-16, 6-12-Aug-16,10-16-Dec-16, 30 Mar-5 Apr-16) | Melamchi | 10
18206 | Sindhupalchok | Melamchi N.P. | 13 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-04 | Hileykholapari CBRC | Melamchi | 10
18207 | Sindhupalchok | Melamchi N.P. | 13 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-07 | Rampur CBRC | Melamchi | 10
18208 | Sindhupalchok | Melamchi N.P. | 13 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-03 | Sikharpur ward 1 CBRC | Melamchi | 10
18209 | Sindhupalchok | Melamchi N.P. | 13 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-07 | Sikharpur ward 2 CBRC | Melamchi | 10
18210 | Sindhupalchok | Melamchi N.P. | 13 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-05 | Sikharpur ward 3 CBRC | Melamchi | 10
18211 | Sindhupalchok | Melamchi N.P. | 14 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-23 | sunkhani CBRC | Melamchi | 9
18212 | Sindhupalchok | Melamchi N.P. | 14 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-23 | Ratmata CBRC | Melamchi | 9
18213 | Sindhupalchok | Melamchi N.P. | 14 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-24 | Tinkanya CBRC | Melamchi | 9
18214 | Sindhupalchok | Melamchi N.P. | 14 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-24 | Golmeshwori Manedada CBRC | Melamchi | 9
18215 | Sindhupalchok | Melamchi N.P. | 14 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-23 | Gupha CBRC | Melamchi | 9
18216 | Sindhupalchok | Melamchi N.P. | 14 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-25 | paiyatol CBRC | Melamchi | 9
18217 | Sindhupalchok | Melamchi N.P. | 14 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 25 | 25 | 2016-03-30 | 2016-12-16 | mason training completed in different 6 lots (29-Jul-4 Aug-16, 2-8-Aug-16, 23-29-Sep-16, 6-12-Aug-16,10-16-Dec-16, 30 Mar-5 Apr-16) | Melamchi | 9
18218 | Sindhupalchok | Melamchi N.P. | 15 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-31 | Milanchowk CBRC | Melamchi | 9
18219 | Sindhupalchok | Melamchi N.P. | 15 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-27 | Golmasthan CBRC | Melamchi | 9
18220 | Sindhupalchok | Melamchi N.P. | 15 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-27 | khadkathok CBRC | Melamchi | 9
18221 | Sindhupalchok | Melamchi N.P. | 15 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-28 | chyankhu CBRC | Melamchi | 9
18222 | Sindhupalchok | Melamchi N.P. | 15 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training conducted in different lots | # of trainees | Yes | Ongoing | 3 | 3 | 2016-03-30 | 2016-12-16 | mason training completed in different 6 lots (29-Jul-4 Aug-16, 2-8-Aug-16, 23-29-Sep-16, 6-12-Aug-16,10-16-Dec-16, 30 Mar-5 Apr-16) | Melamchi | 9
18223 | Sindhupalchok | Melamchi N.P. | 10, 11 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-23 | Fatakshila ward 2 and 7 CBRC | Melamchi | 13
18224 | Sindhupalchok | Melamchi N.P. | 10,11 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-12-26 | Fatakshila ward 7 and 9 CBRC | Melamchi | 13
18225 | Sindhupalchok | Melamchi N.P. | All | JICA | TCN | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 3000 | 3592 | 2017-07-02 |  |  | Melamchi | 13
18226 | Sindhupalchok | Melamchi N.P. | TBC | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 28 | 28 | 2017-02-06 | 2017-02-06 | Data of Talamrang VDC | Melamchi | 13
18227 | Sindhupalchok | Melamchi N.P. | TBC | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 34 | 34 | 2017-02-07 | 2017-02-07 | Data of Jyamire VDC | Melamchi | 13
18228 | Sindhupalchok | Melamchi N.P. | TBC | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 25 | 25 | 2017-02-08 | 2017-02-08 | Data of Shikharpur VDC | Melamchi | 13
18229 | Sindhupalchok | Melamchi N.P. | TBC | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 28 | 28 | 2017-02-09 | 2017-02-09 | Data of Bansbari VDC | Melamchi | 13
18230 | Sindhupalchok | Melamchi N.P. | TBC | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 26 | 26 | 2017-02-10 | 2017-02-10 | Data of Fataksila VDC | Melamchi | 13
18231 | Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 277 | 277 | 2016-09-22 | 2016-12-21 |  | Melamchi | 13
18232 | Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 273 | 273 | 2016-09-22 | 2016-12-21 |  | Melamchi | 13
18233 | Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 199 | 199 | 2016-09-22 | 2016-12-21 |  | Melamchi | 13
18234 | Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 244 | 244 | 2016-09-22 | 2016-12-21 |  | Melamchi | 13
18235 | Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 294 | 294 | 2016-09-22 | 2016-12-21 |  | Melamchi | 13
18236 | Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 247 | 247 | 2016-09-22 | 2016-12-21 |  | Melamchi | 13
18237 | Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 274 | 274 | 2016-09-22 | 2016-12-21 |  | Melamchi | 13
18238 | Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 258 | 258 | 2016-09-22 | 2016-12-21 |  | Melamchi | 13
18239 | Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 207 | 207 | 2016-09-22 | 2016-12-21 |  | Melamchi | 13
18240 | Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 560 | 80 | 2016-04-01 | 2020-12-31 |  | Melamchi | 13
18241 | Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 28 | 28 | 2016-07-10 | 2016-07-16 |  | Melamchi | 13
18242 | Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 24 | 24 | 2016-08-23 | 2016-08-29 |  | Melamchi | 13
18243 | Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 22 | 22 | 2016-07-31 | 2016-08-06 |  | Melamchi | 13
18244 | Sindhupalchok | Melamchi N.P. |  | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 82 | 82 | 2017-10-05 | 2018-02-15 |  | Melamchi | 13
18245 | Sindhupalchok | Ramche | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-08 | 2016-11-17 |  | Barhabise | 9
18246 | Sindhupalchok | Ramche | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-20 | Damar CBRC | Barhabise | 9
18247 | Sindhupalchok | Ramche | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-21 | Chulthe CBRC | Barhabise | 9
18248 | Sindhupalchok | Ramche | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-22 | Thotnari CBRC | Barhabise | 9
18249 | Sindhupalchok | Ramche | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-23 | Ratamata CBRC | Barhabise | 9
18250 | Sindhupalchok | Ramche | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-27 | Aarukharka CBRC | Barhabise | 9
18251 | Sindhupalchok | Ramche | All | JICA | TCN | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 500 | 614 | 2017-07-12 |  |  | Barhabise | 9
18252 | Sindhupalchok | Ramche | 1 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-03-01 | 2017-03-01 |  | Barhabise | 9
18253 | Sindhupalchok | Ramche | 1 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 4 | 4 | 2016-08-24 | 2017-02-05 | 1st lot (Aug-24-30-16) 2nd lot (27-Jan-5-Feb-17) | Barhabise | 9
18254 | Sindhupalchok | Ramche | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 60 | 60 |  |  |  | Barhabise | 9
18255 | Sindhupalchok | Ramche | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-03-01 | 2017-03-01 |  | Barhabise | 9
18256 | Sindhupalchok | Ramche | 2 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 11 | 11 | 2016-08-24 | 2017-02-05 | 1st lot (Aug-24-30-16) 2nd lot (27-Jan-5-Feb-17) | Barhabise | 9
18257 | Sindhupalchok | Ramche | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 |  |  |  | Barhabise | 9
18258 | Sindhupalchok | Ramche | 3 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-03-01 | 2017-03-01 |  | Barhabise | 9
18259 | Sindhupalchok | Ramche | 3 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 5 | 5 | 2016-08-24 | 2017-02-05 | 1st lot (Aug-24-30-16) 2nd lot (27-Jan-5-Feb-17) | Barhabise | 9
18260 | Sindhupalchok | Ramche | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 |  |  |  | Barhabise | 9
18261 | Sindhupalchok | Ramche | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Okharbote CBRC | Barhabise | 9
18262 | Sindhupalchok | Ramche | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-03-01 | 2017-03-01 |  | Barhabise | 9
18263 | Sindhupalchok | Ramche | 4 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 4 | 4 | 2016-08-24 | 2017-02-05 | 1st lot (Aug-24-30-16) 2nd lot (27-Jan-5-Feb-17) | Barhabise | 9
18264 | Sindhupalchok | Ramche | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 60 | 60 |  |  |  | Barhabise | 9
18265 | Sindhupalchok | Ramche | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-14 | Gairigaun CBRC | Barhabise | 9
18266 | Sindhupalchok | Ramche | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-17 | Setidevi CBRC | Barhabise | 9
18267 | Sindhupalchok | Ramche | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-03-01 | 2017-03-01 |  | Barhabise | 9
18268 | Sindhupalchok | Ramche | 5 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 8 | 8 | 2016-08-24 | 2017-02-05 | 1st lot (Aug-24-30-16) 2nd lot (27-Jan-5-Feb-17) | Barhabise | 9
18269 | Sindhupalchok | Ramche | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 |  |  |  | Barhabise | 9
18270 | Sindhupalchok | Ramche | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Badahare CBRC | Barhabise | 9
18271 | Sindhupalchok | Ramche | 6 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-03-01 | 2017-03-01 |  | Barhabise | 9
18272 | Sindhupalchok | Ramche | 6 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 5 | 5 | 2016-08-24 | 2017-02-05 | 1st lot (Aug-24-30-16) 2nd lot (27-Jan-5-Feb-17) | Barhabise | 9
18273 | Sindhupalchok | Ramche | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 |  |  |  | Barhabise | 9
18274 | Sindhupalchok | Ramche | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-08 | Saalbisauna CBRC | Barhabise | 9
18275 | Sindhupalchok | Ramche | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-03-01 | 2017-03-01 |  | Barhabise | 9
18276 | Sindhupalchok | Ramche | 7 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 8 | 8 | 2016-08-24 | 2017-02-05 | 1st lot (Aug-24-30-16) 2nd lot (27-Jan-5-Feb-17) | Barhabise | 9
18277 | Sindhupalchok | Ramche | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 |  |  |  | Barhabise | 9
18278 | Sindhupalchok | Ramche | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Tand Bisauna CBRC | Barhabise | 9
18279 | Sindhupalchok | Ramche | 8 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-03-01 | 2017-03-01 |  | Barhabise | 9
18280 | Sindhupalchok | Ramche | 8 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 4 | 4 | 2016-08-24 | 2017-02-05 | 1st lot (Aug-24-30-16) 2nd lot (27-Jan-5-Feb-17) | Barhabise | 9
18281 | Sindhupalchok | Ramche | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 |  |  |  | Barhabise | 9
18282 | Sindhupalchok | Ramche | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-02 | Bhatte CBRC | Barhabise | 9
18283 | Sindhupalchok | Ramche | 9 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-03-01 | 2017-03-01 |  | Barhabise | 9
18284 | Sindhupalchok | Ramche | 9 | JICA | ERTech | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason training in same wards for different people | # of trainees | Yes | Completed | 5 | 5 | 2016-08-24 | 2017-02-05 | 1st lot (Aug-24-30-16) 2nd lot (27-Jan-5-Feb-17) | Barhabise | 9
18285 | Sindhupalchok | Ramche |  | JICA | ERTech | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31 |  | Barhabise | 9
18286 | Sindhupalchok | Sangachok | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 73 | 73 | 2016-09-28 | 2016-10-04 |  | Chautara Sangachokgadhi | 10
18287 | Sindhupalchok | Sangachok | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Sukute tole CBRC | Chautara Sangachokgadhi | 10
18288 | Sindhupalchok | Sangachok | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Khatrithok CBRC | Chautara Sangachokgadhi | 10
18289 | Sindhupalchok | Sangachok | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | SatthiMure CBRC | Chautara Sangachokgadhi | 10
18290 | Sindhupalchok | Sangachok | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Karkitar CBRC | Chautara Sangachokgadhi | 10
18291 | Sindhupalchok | Sangachok | All | JICA | TCN | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 1000 | 894 | 2017-07-11 |  |  | Chautara Sangachokgadhi | 12
18292 | Sindhupalchok | Sangachok | 1 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-06 | 2016-03-12 |  | Chautara Sangachokgadhi | 10
18293 | Sindhupalchok | Sangachok | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 58 | 58 | 2016-09-28 | 2016-10-04 |  | Chautara Sangachokgadhi | 10
18294 | Sindhupalchok | Sangachok | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Dhara Pani | Chautara Sangachokgadhi | 10
18295 | Sindhupalchok | Sangachok | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Deurali CBRC | Chautara Sangachokgadhi | 10
18296 | Sindhupalchok | Sangachok | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Rakhaltole CBRC | Chautara Sangachokgadhi | 10
18297 | Sindhupalchok | Sangachok | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Gairitole CBRC | Chautara Sangachokgadhi | 10
18298 | Sindhupalchok | Sangachok | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-01-27 | MajhGaun CBRC | Chautara Sangachokgadhi | 10
18299 | Sindhupalchok | Sangachok | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-01-27 | Harre CBRC | Chautara Sangachokgadhi | 10
18300 | Sindhupalchok | Sangachok | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-01-27 | Holka CBRC | Chautara Sangachokgadhi | 10
18301 | Sindhupalchok | Sangachok | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-05 | Kande CBRC | Chautara Sangachokgadhi | 10
18302 | Sindhupalchok | Sangachok | 2 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-06 | 2016-03-12 |  | Chautara Sangachokgadhi | 10
18303 | Sindhupalchok | Sangachok | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 64 | 64 | 2016-09-28 | 2016-10-04 |  | Chautara Sangachokgadhi | 12
18304 | Sindhupalchok | Sangachok | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Pallatole CBRC | Chautara Sangachokgadhi | 12
18305 | Sindhupalchok | Sangachok | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Swarathok CBRC | Chautara Sangachokgadhi | 12
18306 | Sindhupalchok | Sangachok | 3 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-01-04 | 2017-01-04 |  | Chautara Sangachokgadhi | 12
18307 | Sindhupalchok | Sangachok | 3 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-06 | 2016-03-12 |  | Chautara Sangachokgadhi | 12
18308 | Sindhupalchok | Sangachok | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 58 | 58 | 2016-09-28 | 2016-10-04 |  | Chautara Sangachokgadhi | 12
18309 | Sindhupalchok | Sangachok | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Kotthok CBRC | Chautara Sangachokgadhi | 12
18310 | Sindhupalchok | Sangachok | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Chhap CBRC | Chautara Sangachokgadhi | 12
18311 | Sindhupalchok | Sangachok | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Sangachowk Bhanjhyang CBRC | Chautara Sangachokgadhi | 12
18312 | Sindhupalchok | Sangachok | 4 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-01-04 | 2017-01-04 |  | Chautara Sangachokgadhi | 12
18313 | Sindhupalchok | Sangachok | 4 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-06 | 2016-03-12 |  | Chautara Sangachokgadhi | 12
18314 | Sindhupalchok | Sangachok | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 71 | 71 | 2016-09-28 | 2016-10-04 |  | Chautara Sangachokgadhi | 11
18315 | Sindhupalchok | Sangachok | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-05 | Jyoti Danda CBRC | Chautara Sangachokgadhi | 11
18316 | Sindhupalchok | Sangachok | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-15 | Simlay CBRC | Chautara Sangachokgadhi | 11
18317 | Sindhupalchok | Sangachok | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 78 | 78 | 2016-09-28 | 2016-10-04 |  | Chautara Sangachokgadhi | 12
18318 | Sindhupalchok | Sangachok | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | RanaThok- Kharka CBRC | Chautara Sangachokgadhi | 12
18319 | Sindhupalchok | Sangachok | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Chootedanda- NayaGuan CBRC | Chautara Sangachokgadhi | 12
18320 | Sindhupalchok | Sangachok | 6 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-01-04 | 2017-01-04 |  | Chautara Sangachokgadhi | 12
18321 | Sindhupalchok | Sangachok | 6 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-06 | 2016-03-12 |  | Chautara Sangachokgadhi | 12
18322 | Sindhupalchok | Sangachok | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 105 | 105 | 2016-09-28 | 2016-10-04 |  | Chautara Sangachokgadhi | 10
18323 | Sindhupalchok | Sangachok | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | BhaunGau CBRC | Chautara Sangachokgadhi | 10
18324 | Sindhupalchok | Sangachok | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | PariGau CBRC | Chautara Sangachokgadhi | 10
18325 | Sindhupalchok | Sangachok | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Chapabota CBRC | Chautara Sangachokgadhi | 10
18326 | Sindhupalchok | Sangachok | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Gaurigau-Jalkeni CBRC | Chautara Sangachokgadhi | 10
18327 | Sindhupalchok | Sangachok | 7 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-01-04 | 2017-01-04 |  | Chautara Sangachokgadhi | 10
18328 | Sindhupalchok | Sangachok | 7 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-06 | 2016-03-12 |  | Chautara Sangachokgadhi | 10
18329 | Sindhupalchok | Sangachok | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 74 | 74 | 2016-09-28 | 2016-10-04 |  | Chautara Sangachokgadhi | 11
18330 | Sindhupalchok | Sangachok | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Falate CBRC | Chautara Sangachokgadhi | 11
18331 | Sindhupalchok | Sangachok | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Kavre CBRC | Chautara Sangachokgadhi | 11
18332 | Sindhupalchok | Sangachok | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-04 | Saithok CBRC | Chautara Sangachokgadhi | 11
18333 | Sindhupalchok | Sangachok | 8 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-01-04 | 2017-01-04 |  | Chautara Sangachokgadhi | 11
18334 | Sindhupalchok | Sangachok | 8 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-06 | 2016-03-12 |  | Chautara Sangachokgadhi | 11
18335 | Sindhupalchok | Sangachok | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 39 | 39 | 2016-09-28 | 2016-10-04 |  | Chautara Sangachokgadhi | 11
18336 | Sindhupalchok | Sangachok | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Jamaune CBRC | Chautara Sangachokgadhi | 11
18337 | Sindhupalchok | Sangachok | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Katunje Pani CBRC | Chautara Sangachokgadhi | 11
18338 | Sindhupalchok | Sangachok | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Mahadevtar | Chautara Sangachokgadhi | 11
18339 | Sindhupalchok | Sangachok | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-14 | Pokhare CBRC | Chautara Sangachokgadhi | 11
18340 | Sindhupalchok | Sangachok | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Ekle CBRC | Chautara Sangachokgadhi | 11
18341 | Sindhupalchok | Sangachok | 9 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 11 | 11 | 2017-01-04 | 2017-01-04 |  | Chautara Sangachokgadhi | 11
18342 | Sindhupalchok | Sangachok | 9 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-03-06 | 2016-03-12 |  | Chautara Sangachokgadhi | 11
18343 | Sindhupalchok | Sangachok | 8 & 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Bhimtar CBRC | Chautara Sangachokgadhi | 12
18344 | Sindhupalchok | Sangachok |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 78 | 2016-04-01 | 2020-12-31 |  | Chautara Sangachokgadhi | 12
18345 | Sindhupalchok | Sangachok | All | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 21 | 21 | 2018-01-01 | 2018-02-15 |  | Chautara Sangachokgadhi | 12
18346 | Sindhupalchok | SyauleBazar | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 42 | 42 | 2016-09-24 | 2016-10-04 |  | Chautara Sangachokgadhi | 1
18347 | Sindhupalchok | SyauleBazar | 1 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | One-off |  | # of households | Yes | Ongoing | 5 | 10 | 2017-01-27 |  |  | Chautara Sangachokgadhi | 1
18348 | Sindhupalchok | SyauleBazar | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Seti Bhumi CBRC | Chautara Sangachokgadhi | 1
18349 | Sindhupalchok | SyauleBazar | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | JayangderGongbo CBRC | Chautara Sangachokgadhi | 1
18350 | Sindhupalchok | SyauleBazar | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Chhangba Ningba Gunba CBRC | Chautara Sangachokgadhi | 1
18351 | Sindhupalchok | SyauleBazar | 1 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 2 | 2 | 2016-02-01 | 2017-01-07 | 1st lot in Feb 1-7, 2016 and 2nd in jan 1-7-2017 | Chautara Sangachokgadhi | 1
18352 | Sindhupalchok | SyauleBazar | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 52 | 52 | 2016-09-24 | 2016-10-04 |  | Chautara Sangachokgadhi | 1
18353 | Sindhupalchok | SyauleBazar | 2 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | One-off |  | # of households | Yes | Ongoing | 5 | 4 | 2017-02-03 |  |  | Chautara Sangachokgadhi | 1
18354 | Sindhupalchok | SyauleBazar | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Mangala Bhairavi Devi CBRC | Chautara Sangachokgadhi | 1
18355 | Sindhupalchok | SyauleBazar | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Shree Ganesh CBRC | Chautara Sangachokgadhi | 1
18356 | Sindhupalchok | SyauleBazar | 2 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-02 | 2017-02-02 |  | Chautara Sangachokgadhi | 1
18357 | Sindhupalchok | SyauleBazar | 2 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 8 | 8 | 2016-02-01 | 2017-01-07 | 1st lot in Feb 1-7, 2016 and 2nd in jan 1-7-2017 | Chautara Sangachokgadhi | 1
18358 | Sindhupalchok | SyauleBazar | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 49 | 49 | 2016-09-24 | 2016-10-04 |  | Chautara Sangachokgadhi | 1
18359 | Sindhupalchok | SyauleBazar | 3 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 0 | 0 | 2017-02-01 |  |  | Chautara Sangachokgadhi | 1
18360 | Sindhupalchok | SyauleBazar | 3 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | One-off |  | # of households | Yes | Ongoing | 5 | 4 | 2017-02-01 |  |  | Chautara Sangachokgadhi | 1
18361 | Sindhupalchok | SyauleBazar | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Satkanya Mangala devi CBRC | Chautara Sangachokgadhi | 1
18362 | Sindhupalchok | SyauleBazar | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Pach Mangala Devi CBRC | Chautara Sangachokgadhi | 1
18363 | Sindhupalchok | SyauleBazar | 3 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-02 | 2017-02-02 |  | Chautara Sangachokgadhi | 1
18364 | Sindhupalchok | SyauleBazar | 3 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 8 | 8 | 2016-02-01 | 2017-01-07 | 1st lot in Feb 1-7, 2016 and 2nd in jan 1-7-2017 | Chautara Sangachokgadhi | 1
18365 | Sindhupalchok | SyauleBazar | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 62 | 62 | 2016-09-24 | 2016-10-04 |  | Chautara Sangachokgadhi | 1
18366 | Sindhupalchok | SyauleBazar | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Khorang Yarsa CBRC | Chautara Sangachokgadhi | 1
18367 | Sindhupalchok | SyauleBazar | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | Pachpokhari CBRC | Chautara Sangachokgadhi | 1
18368 | Sindhupalchok | SyauleBazar | 4 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-02 | 2017-02-02 |  | Chautara Sangachokgadhi | 1
18369 | Sindhupalchok | SyauleBazar | 4 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 8 | 8 | 2016-02-01 | 2017-01-07 | 1st lot in Feb 1-7, 2016 and 2nd in jan 1-7-2017 | Chautara Sangachokgadhi | 1
18370 | Sindhupalchok | SyauleBazar | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 47 | 47 | 2016-09-24 | 2016-10-04 |  | Chautara Sangachokgadhi | 1
18371 | Sindhupalchok | SyauleBazar | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Shree Kalika Devi CBRC | Chautara Sangachokgadhi | 1
18372 | Sindhupalchok | SyauleBazar | 5 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-02-02 | 2017-02-02 |  | Chautara Sangachokgadhi | 1
18373 | Sindhupalchok | SyauleBazar | 5 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 3 | 3 | 2016-02-01 | 2017-01-07 | 1st lot in Feb 1-7, 2016 and 2nd in jan 1-7-2017 | Chautara Sangachokgadhi | 1
18374 | Sindhupalchok | SyauleBazar | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 45 | 45 | 2016-09-24 | 2016-10-04 |  | Chautara Sangachokgadhi | 1
18375 | Sindhupalchok | SyauleBazar | 6 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 6 | 2017-01-25 |  |  | Chautara Sangachokgadhi | 1
18376 | Sindhupalchok | SyauleBazar | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Shree Bhairavi CBRC | Chautara Sangachokgadhi | 1
18377 | Sindhupalchok | SyauleBazar | 6 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 12 | 12 | 2016-02-01 | 2017-01-07 | 1st lot in Feb 1-7, 2016 and 2nd in jan 1-7-2017 | Chautara Sangachokgadhi | 1
18378 | Sindhupalchok | SyauleBazar | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 66 | 66 | 2016-09-24 | 2016-10-04 |  | Chautara Sangachokgadhi | 1
18379 | Sindhupalchok | SyauleBazar | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Shree Bangbaa CBRC | Chautara Sangachokgadhi | 1
18380 | Sindhupalchok | SyauleBazar | 7 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 11 | 11 | 2017-02-02 | 2017-02-02 |  | Chautara Sangachokgadhi | 1
18381 | Sindhupalchok | SyauleBazar | 7 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 9 | 9 | 2016-02-01 | 2017-01-07 | 1st lot in Feb 1-7, 2016 and 2nd in jan 1-7-2017 | Chautara Sangachokgadhi | 1
18382 | Sindhupalchok | SyauleBazar | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 54 | 54 | 2016-09-24 | 2016-10-04 |  | Chautara Sangachokgadhi | 1
18383 | Sindhupalchok | SyauleBazar | 8 | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | One-off |  | # of households | Yes | Ongoing | 5 | 2 | 2017-02-06 |  |  | Chautara Sangachokgadhi | 1
18384 | Sindhupalchok | SyauleBazar | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Harlang Barlang CBRC | Chautara Sangachokgadhi | 1
18385 | Sindhupalchok | SyauleBazar | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Jayashwori Bhanjhyang CBRC | Chautara Sangachokgadhi | 1
18386 | Sindhupalchok | SyauleBazar | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Basuki Devi CBRC | Chautara Sangachokgadhi | 1
18387 | Sindhupalchok | SyauleBazar | 8 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-02 | 2017-02-02 |  | Chautara Sangachokgadhi | 1
18388 | Sindhupalchok | SyauleBazar | 8 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 10 | 10 | 2016-02-01 | 2017-01-07 | 1st lot in Feb 1-7, 2016 and 2nd in jan 1-7-2017 | Chautara Sangachokgadhi | 1
18389 | Sindhupalchok | SyauleBazar | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 63 | 63 | 2016-09-24 | 2016-10-04 |  | Chautara Sangachokgadhi | 1
18390 | Sindhupalchok | SyauleBazar | All | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 500 | 402 | 2017-07-04 |  |  | Chautara Sangachokgadhi | 1
18391 | Sindhupalchok | SyauleBazar | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-15 | Rakta kailka CBRC | Chautara Sangachokgadhi | 1
18392 | Sindhupalchok | SyauleBazar | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-16 | Kaushi-Ghar Mulabari CBRC | Chautara Sangachokgadhi | 1
18393 | Sindhupalchok | SyauleBazar | 9 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-02 | 2017-02-02 |  | Chautara Sangachokgadhi | 1
18394 | Sindhupalchok | SyauleBazar | 9 | JICA | TCN | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 7 | 7 | 2016-02-01 | 2017-01-07 | 1st lot in Feb 1-7, 2016 and 2nd in jan 1-7-2017 | Chautara Sangachokgadhi | 1
18395 | Sindhupalchok | SyauleBazar |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 82 | 2016-04-01 | 2020-12-31 |  | Chautara Sangachokgadhi | 1
18396 | Sindhupalchok | SyauleBazar |  | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 16 | 11 | 2017-10-11 | 2017-10-16 |  | Chautara Sangachokgadhi | 1
18397 | Sindhupalchok | Thakani | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-11-25 | 2016-12-05 |  | Melamchi | 4
18398 | Sindhupalchok | Thakani | All | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 800 | 620 | 2017-02-07 |  |  | Melamchi | 4
18399 | Sindhupalchok | Thakani | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-08-28 | Chhapeli CBRC | Melamchi | 4
18400 | Sindhupalchok | Thakani | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 | 2016-11-25 | 2016-12-05 |  | Melamchi | 4
18401 | Sindhupalchok | Thakani | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-04 | Barse Dhunga CBRC | Melamchi | 4
18402 | Sindhupalchok | Thakani | 2 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-12 | 2017-02-12 |  | Melamchi | 4
18403 | Sindhupalchok | Thakani | 2 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-08-24 | 2016-08-30 |  | Melamchi | 4
18404 | Sindhupalchok | Thakani | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 15 | 15 | 2016-11-25 | 2016-12-05 |  | Melamchi | 4
18405 | Sindhupalchok | Thakani | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-03 | Thakani Ward 3 CBRC | Melamchi | 4
18406 | Sindhupalchok | Thakani | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 50 | 50 | 2016-11-25 | 2016-12-05 |  | Melamchi | 4
18407 | Sindhupalchok | Thakani | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-23 | Chandeshwori Mahadev CBRC | Melamchi | 4
18408 | Sindhupalchok | Thakani | 4 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 1 | 1 | 2017-02-12 | 2017-02-12 |  | Melamchi | 4
18409 | Sindhupalchok | Thakani | 4 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-08-24 | 2016-08-30 |  | Melamchi | 4
18410 | Sindhupalchok | Thakani | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-25 | 2016-12-05 |  | Melamchi | 4
18411 | Sindhupalchok | Thakani | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-09-02 | Okhereni Chaur CBRC | Melamchi | 4
18412 | Sindhupalchok | Thakani | 5 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 3 | 3 | 2017-02-12 | 2017-02-12 |  | Melamchi | 4
18413 | Sindhupalchok | Thakani | 5 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-08-24 | 2016-08-30 |  | Melamchi | 4
18414 | Sindhupalchok | Thakani | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-11-25 | 2016-12-05 |  | Melamchi | 4
18415 | Sindhupalchok | Thakani | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-21 | Thakani Ward 6 CBRC | Melamchi | 4
18416 | Sindhupalchok | Thakani | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 35 | 35 | 2016-11-25 | 2016-12-05 |  | Melamchi | 4
18417 | Sindhupalchok | Thakani | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-08-31 | Dhauleshwori CBRC | Melamchi | 4
18418 | Sindhupalchok | Thakani | 7 | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 5 | 5 | 2017-02-12 | 2017-02-12 |  | Melamchi | 4
18419 | Sindhupalchok | Thakani | 7 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-08-24 | 2016-08-30 |  | Melamchi | 4
18420 | Sindhupalchok | Thakani | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 25 | 25 | 2016-11-25 | 2016-12-05 |  | Melamchi | 4
18421 | Sindhupalchok | Thakani | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-25 | Thakani Ward 8 CBRC | Melamchi | 4
18422 | Sindhupalchok | Thakani | 8 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-08-24 | 2016-08-30 |  | Melamchi | 4
18423 | Sindhupalchok | Thakani | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 20 | 20 | 2016-11-25 | 2016-12-05 |  | Melamchi | 4
18424 | Sindhupalchok | Thakani | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-10-19 | Thakani Ward 9 CBRC | Melamchi | 4
18425 | Sindhupalchok | Thakani | 9 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-08-24 | 2016-08-30 |  | Melamchi | 4
18426 | Sindhupalchok | Thakani |  | JICA |  | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 | 2016-04-01 | 2020-12-31 |  | Melamchi | 4
18427 | Sindhupalchok | Thakani |  | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 11 | 11 | 2017-02-12 | 2017-02-12 |  | Melamchi | 4
18428 | Sindhupalchok | Thakani |  | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-02-12 | 2017-02-12 |  | Melamchi | 4
18429 | Sindhupalchok | Thakani | All | JICA | TCN | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 11 | 11 | 2018-01-01 | 2018-02-15 |  | Melamchi | 4
18430 | Sindhupalchok | ThuloSirubari | 1 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 175 | 175 | 2016-09-25 | 2016-10-04 |  | Chautara Sangachokgadhi | 13
18431 | Sindhupalchok | ThuloSirubari | All | JICA |  | JICA | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 1000 | 974 | 2017-07-19 |  |  | Chautara Sangachokgadhi | 13
18432 | Sindhupalchok | ThuloSirubari | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Kotdanda CBRC | Chautara Sangachokgadhi | 13
18433 | Sindhupalchok | ThuloSirubari | 1 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-01-05 | 2017-01-05 |  | Chautara Sangachokgadhi | 13
18434 | Sindhupalchok | ThuloSirubari | 1 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 3 | 3 | 2016-02-19 | 2017-02-10 | 1st lot in Feb 19-25, 2016 and 2nd in Feb 4-10-2017 | Chautara Sangachokgadhi | 13
18435 | Sindhupalchok | ThuloSirubari | 2 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 84 | 84 | 2016-09-25 | 2016-10-04 |  | Chautara Sangachokgadhi | 13
18436 | Sindhupalchok | ThuloSirubari | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | Saune Chaur CBRC | Chautara Sangachokgadhi | 13
18437 | Sindhupalchok | ThuloSirubari | 2 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 4 | 4 | 2017-01-05 | 2017-01-05 |  | Chautara Sangachokgadhi | 13
18438 | Sindhupalchok | ThuloSirubari | 2 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 11 | 11 | 2016-02-19 | 2017-02-10 | 1st lot in Feb 19-25, 2016 and 2nd in Feb 4-10-2017 | Chautara Sangachokgadhi | 13
18439 | Sindhupalchok | ThuloSirubari | 3 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 64 | 64 | 2016-09-25 | 2016-10-04 |  | Chautara Sangachokgadhi | 13
18440 | Sindhupalchok | ThuloSirubari | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-15 | Narayan Devi CBRC | Chautara Sangachokgadhi | 13
18441 | Sindhupalchok | ThuloSirubari | 3 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-01-05 | 2017-01-05 |  | Chautara Sangachokgadhi | 13
18442 | Sindhupalchok | ThuloSirubari | 3 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 5 | 5 | 2016-02-19 | 2017-02-10 | 1st lot in Feb 19-25, 2016 and 2nd in Feb 4-10-2017 | Chautara Sangachokgadhi | 13
18443 | Sindhupalchok | ThuloSirubari | 4 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 92 | 92 | 2016-09-25 | 2016-10-04 |  | Chautara Sangachokgadhi | 13
18444 | Sindhupalchok | ThuloSirubari | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Kundali Devi CBRC | Chautara Sangachokgadhi | 13
18445 | Sindhupalchok | ThuloSirubari | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Markandi Devi CBRC | Chautara Sangachokgadhi | 13
18446 | Sindhupalchok | ThuloSirubari | 4 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 6 | 6 | 2017-01-05 | 2017-01-05 |  | Chautara Sangachokgadhi | 13
18447 | Sindhupalchok | ThuloSirubari | 4 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 9 | 9 | 2016-02-19 | 2017-02-10 | 1st lot in Feb 19-25, 2016 and 2nd in Feb 4-10-2017 | Chautara Sangachokgadhi | 13
18448 | Sindhupalchok | ThuloSirubari | 5 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 56 | 56 | 2016-09-25 | 2016-10-04 |  | Chautara Sangachokgadhi | 13
18449 | Sindhupalchok | ThuloSirubari | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Suganda CBRC | Chautara Sangachokgadhi | 13
18450 | Sindhupalchok | ThuloSirubari | 5 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2017-01-05 | 2017-01-05 |  | Chautara Sangachokgadhi | 13
18451 | Sindhupalchok | ThuloSirubari | 5 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 11 | 11 | 2016-02-19 | 2017-02-10 | 1st lot in Feb 19-25, 2016 and 2nd in Feb 4-10-2017 | Chautara Sangachokgadhi | 13
18452 | Sindhupalchok | ThuloSirubari | 6 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 69 | 69 | 2016-09-25 | 2016-10-04 |  | Chautara Sangachokgadhi | 13
18453 | Sindhupalchok | ThuloSirubari | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Satdobato CBRC | Chautara Sangachokgadhi | 13
18454 | Sindhupalchok | ThuloSirubari | 6 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 9 | 9 | 2016-02-19 | 2017-02-10 | 1st lot in Feb 19-25, 2016 and 2nd in Feb 4-10-2017 | Chautara Sangachokgadhi | 13
18455 | Sindhupalchok | ThuloSirubari | 7 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 49 | 49 | 2016-09-25 | 2016-10-04 |  | Chautara Sangachokgadhi | 14
18456 | Sindhupalchok | ThuloSirubari | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | ShreeRam CBRC | Chautara Sangachokgadhi | 14
18457 | Sindhupalchok | ThuloSirubari | 7 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 6 | 6 | 2016-02-19 | 2017-02-10 | 1st lot in Feb 19-25, 2016 and 2nd in Feb 4-10-2017 | Chautara Sangachokgadhi | 14
18458 | Sindhupalchok | ThuloSirubari | 8 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 71 | 71 | 2016-09-25 | 2016-10-04 |  | Chautara Sangachokgadhi | 14
18459 | Sindhupalchok | ThuloSirubari | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-17 | Ranitar CBRC | Chautara Sangachokgadhi | 14
18460 | Sindhupalchok | ThuloSirubari | 8 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 7 | 7 | 2017-01-05 | 2017-01-05 |  | Chautara Sangachokgadhi | 14
18461 | Sindhupalchok | ThuloSirubari | 8 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 12 | 12 | 2016-02-19 | 2017-02-10 | 1st lot in Feb 19-25, 2016 and 2nd in Feb 4-10-2017 | Chautara Sangachokgadhi | 14
18462 | Sindhupalchok | ThuloSirubari | 9 | JICA |  | JICA | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 37 | 37 | 2016-09-25 | 2016-10-04 |  | Chautara Sangachokgadhi | 14
18463 | Sindhupalchok | ThuloSirubari | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-16 | Kali Devi CBRC | Chautara Sangachokgadhi | 14
18464 | Sindhupalchok | ThuloSirubari | 9 | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | Refreshing one day mason training for trained mason | # of trainees | Yes | Completed | 2 | 2 | 2017-01-05 | 2017-01-05 |  | Chautara Sangachokgadhi | 14
18465 | Sindhupalchok | ThuloSirubari | 9 | JICA |  | JICA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lot mason traiing in same wards for dfferent people | # of trainees | Yes | Completed | 2 | 2 | 2016-02-19 | 2017-02-10 | 1st lot in Feb 19-25, 2016 and 2nd in Feb 4-10-2017 | Chautara Sangachokgadhi | 14
18466 | Sindhupalchok | ThuloSirubari |  | JICA | TCN | JICA | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 78 | 2016-04-01 | 2020-12-31 |  | Chautara Sangachokgadhi | 13
18467 | Sindhupalchok | ThuloSirubari |  | JICA |  | JICA | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Ongoing | 23 | 23 | 2017-10-05 |  |  | Chautara Sangachokgadhi | 13
18468 | Sindhupalchok | ThuloSirubari |  | JICA |  | JICA | Training | Other trainings | Other trainings (specify in Activity Detail) | 6 days Mobile mason training | # of trainees | Yes | Completed | 20 | 18 | 2017-10-01 | 2018-02-15 |  | Chautara Sangachokgadhi | 13
18469 | Sindhupalchok | Baramchi | 1 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27 |  | Jugal | 5
18470 | Sindhupalchok | Baramchi | 2 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27 |  | Jugal | 5
18471 | Sindhupalchok | Baramchi | 3 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-09-27 | 2015-10-27 |  | Jugal | 5
18472 | Sindhupalchok | Baramchi | 4 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-09-27 | 2015-10-27 |  | Jugal | 5
18473 | Sindhupalchok | Baramchi | 5 | LWF | GMSP | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 75 | 75 | 2016-07-01 | 2017-10-30 |  | Jugal | 5
18474 | Sindhupalchok | Baramchi | 5 | LWF | GMSP | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Completed | 75 | 75 | 2016-07-01 | 2017-10-30 |  | Jugal | 5
18475 | Sindhupalchok | Baramchi | 5 | LWF | GMSP | ACT Alliance | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 15 | 15 | 2016-11-21 | 2016-11-27 |  | Jugal | 5
18476 | Sindhupalchok | Baramchi | 5 | LWF | GMSP | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 75 | 75 | 2017-06-21 | 2017-12-20 |  | Jugal | 5
18477 | Sindhupalchok | Baramchi | 5 | LWF | GMSP | ACT Alliance | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 385 | 300 | 2016-10-10 | 2017-10-01 |  | Jugal | 5
18478 | Sindhupalchok | Baramchi | 5 | LWF | GMSP | ACT Alliance | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 75 | 75 | 2016-10-10 | 2017-12-20 |  | Jugal | 5
18479 | Sindhupalchok | Baramchi | 5 | LWF | GMSP | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-11-21 | 2016-11-27 |  | Jugal | 5
18480 | Sindhupalchok | Baramchi | 6 | LWF | GMSP | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 67 | 67 | 2016-07-01 | 2017-10-30 |  | Jugal | 5
18481 | Sindhupalchok | Baramchi | 6 | LWF | GMSP | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Completed | 67 | 67 | 2016-07-01 | 2017-10-30 |  | Jugal | 5
18482 | Sindhupalchok | Baramchi | 6 | LWF | GMSP | ACT Alliance | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 15 | 15 | 2016-11-21 | 2016-11-27 |  | Jugal | 5
18483 | Sindhupalchok | Baramchi | 6 | LWF | GMSP | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 67 | 67 | 2017-06-21 | 2017-12-20 |  | Jugal | 5
18484 | Sindhupalchok | Baramchi | 6 | LWF | GMSP | ACT Alliance | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 335 | 285 | 2016-10-10 | 2017-10-01 |  | Jugal | 5
18485 | Sindhupalchok | Baramchi | 6 | LWF | GMSP | ACT Alliance | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 67 | 67 | 2016-10-10 |  |  | Jugal | 5
18486 | Sindhupalchok | Baramchi | 6 | LWF | GMSP | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-11-21 | 2016-11-27 |  | Jugal | 5
18487 | Sindhupalchok | Baramchi | 6 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27 |  | Jugal | 5
18488 | Sindhupalchok | Baramchi | 7 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27 |  | Jugal | 5
18489 | Sindhupalchok | Baramchi | 8 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27 |  | Jugal | 5
18490 | Sindhupalchok | Baramchi | 9 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27 |  | Jugal | 5
18491 | Sindhupalchok | Melamchi N.P. | 12 | LWF | CF | LWF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-09-14 | 2017-09-20 |  | Melamchi | 10
18492 | Sindhupalchok | Melamchi N.P. | 12 | LWF | CF | LWF | Reconstruction through contractors | Construction | Private house | Integrated settlement | # of constructions | Yes | Planned | 70 | 0 | 2017-12-15 |  |  | Melamchi | 10
18493 | Sindhupalchok | Selang | 1 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-09-27 | 2015-10-27 |  | Jugal | 1
18494 | Sindhupalchok | Selang | 2 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27 |  | Jugal | 1
18495 | Sindhupalchok | Selang | 3 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27 |  | Jugal | 1
18496 | Sindhupalchok | Selang | 4 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27 |  | Jugal | 1
18497 | Sindhupalchok | Selang | 5 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27 |  | Jugal | 1
18498 | Sindhupalchok | Selang | 6 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-09-27 | 2015-10-27 |  | Jugal | 1
18499 | Sindhupalchok | Selang | 7 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-09-27 | 2015-10-27 |  | Jugal | 1
18500 | Sindhupalchok | Selang | 8 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-27 | 2015-10-27 |  | Jugal | 1
18501 | Sindhupalchok | Selang | 9 | LWF | GMSP | ACT Alliance | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-09-27 | 2015-10-27 |  | Jugal | 1
18502 | Sindhupalchok | Pangtang |  | LWF | GMSP | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 25 | 2017-11-09 | 2017-11-15 |  | Jugal | 4
18503 | Sindhupalchok | Baramchi |  | LWF | GMSP | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 31 | 2017-11-11 | 2017-11-17 |  | Jugal | 5
18504 | Sindhupalchok | Dhuyang | All | MC | CDECF | MC | Technical Assistance | Household reconstruction orientation | 1 session | mobilize team of technical and non technical person to household level for orientation on safer reconstruction and (IEC) poster distribution. | # of households | Yes | Planned | 1141 | 0 | 2017-04-15 |  |  | Barhabise | 7
18505 | Sindhupalchok | Dhuyang | All | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 |  |  |  | Barhabise | 7
18506 | Sindhupalchok | Dhuyang | All | MC | CDECF | MC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-10-15 | 2017-12-21 |  | Barhabise | 7
18507 | Sindhupalchok | Dhuyang |  | MC | CDECF | MC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-12-01 |  |  | Barhabise | 7
18508 | Sindhupalchok | Dhuyang |  | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0 | 2017-08-01 |  |  | Barhabise | 7
18509 | Sindhupalchok | Dhuyang | 1 | MC | CDECF | MC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 3 | 2017-08-15 |  |  | Barhabise | 7
18510 | Sindhupalchok | Dhuyang | 3 | MC | CDECF | MC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 16 | 2017-08-15 |  |  | Barhabise | 7
18511 | Sindhupalchok | Dhuyang | 4 | MC | CDECF | MC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 16 | 2017-08-15 |  |  | Barhabise | 7
18512 | Sindhupalchok | Dhuyang | 5 | MC | CDECF | MC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 9 | 2017-08-15 |  |  | Barhabise | 7
18513 | Sindhupalchok | Dhuyang | 6 | MC | CDECF | MC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 0 | 2017-08-15 |  |  | Barhabise | 7
18514 | Sindhupalchok | Dhuyang | 7 | MC | CDECF | MC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 10 | 2017-08-15 |  |  | Barhabise | 7
18515 | Sindhupalchok | Dhuyang | 8 | MC | CDECF | MC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 2 | 2017-08-15 |  |  | Barhabise | 7
18516 | Sindhupalchok | Ghorthali | 1 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01 |  | Barhabise | 1
18517 | Sindhupalchok | Ghorthali | 2 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01 |  | Barhabise | 1
18518 | Sindhupalchok | Ghorthali | 3 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01 |  | Barhabise | 1
18519 | Sindhupalchok | Ghorthali | 4 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-25 | 2016-10-01 |  | Barhabise | 1
18520 | Sindhupalchok | Ghorthali | 5 | MC | CDECF | MC | Others | Others | (Please specify in Activity Detail) | Reconstruction Support for School constructing 2 rooms for library | # of trainees | Yes | Ongoing | 1 | 1 |  |  |  | Tripura Sundari | 1
18521 | Sindhupalchok | Ghorthali | 5 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-25 | 2016-10-01 |  | Tripura Sundari | 1
18522 | Sindhupalchok | Ghorthali | 6 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-25 | 2016-10-01 |  | Tripura Sundari | 1
18523 | Sindhupalchok | Ghorthali | 7 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01 |  | Tripura Sundari | 1
18524 | Sindhupalchok | Ghorthali | 8 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-25 | 2016-10-01 |  | Tripura Sundari | 1
18525 | Sindhupalchok | Ghorthali | 9 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-09-25 | 2016-10-01 |  | Tripura Sundari | 1
18526 | Sindhupalchok | Ghorthali | All | MC | CDECF | MC | Technical Assistance | Household reconstruction orientation | 1 session | mobilize team of technical and non technical person to household level for orientation on safer reconstruction and (IEC) poster distribution. | # of households | Yes | Planned | 592 | 0 | 2017-04-15 |  |  | Tripura Sundari | 1
18527 | Sindhupalchok | Ghorthali |  | MC | CDECF | MC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-12-01 |  |  | Tripura Sundari | 1
18528 | Sindhupalchok | Hagam | 1 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-11-14 | 2016-11-20 |  | Jugal | 6
18529 | Sindhupalchok | Hagam | 2 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-11-14 | 2016-11-20 |  | Jugal | 6
18530 | Sindhupalchok | Hagam | 3 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-11-14 | 2016-11-20 |  | Jugal | 6
18531 | Sindhupalchok | Hagam | 4 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-11-14 | 2016-11-20 |  | Jugal | 6
18532 | Sindhupalchok | Hagam | 5 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-11-14 | 2016-11-20 |  | Jugal | 6
18533 | Sindhupalchok | Hagam | 6 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-11-14 | 2016-11-20 |  | Jugal | 7
18534 | Sindhupalchok | Hagam | 7 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-11-14 | 2016-11-20 |  | Jugal | 7
18535 | Sindhupalchok | Hagam | 8 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-11-14 | 2016-11-20 |  | Jugal | 7
18536 | Sindhupalchok | Hagam | 9 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-11-14 | 2016-11-20 |  | Jugal | 7
18537 | Sindhupalchok | Hagam | All | MC | CDECF | MC | Technical Assistance | Household reconstruction orientation | 1 session | mobilize team of technical and non technical person to household level for orientation on safer reconstruction and (IEC) poster distribution. | # of households | Yes | Planned | 1079 | 0 | 2017-04-15 |  |  | Jugal | 7
18538 | Sindhupalchok | Hagam |  | MC | CDECF | MC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-08-07 |  |  | Jugal | 7
18539 | Sindhupalchok | Karthali | 1 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-25 | 2016-10-01 |  | Barhabise | 2
18540 | Sindhupalchok | Karthali | 2 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01 |  | Barhabise | 2
18541 | Sindhupalchok | Karthali | 3 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01 |  | Barhabise | 2
18542 | Sindhupalchok | Karthali | 4 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01 |  | Barhabise | 2
18543 | Sindhupalchok | Karthali | 5 | MC | CDECF | MC | Others | Others | (Please specify in Activity Detail) | Constructing truss structure 3 rooms for Shree Nepal Rastriya Secendary School | # of trainees | Yes | Ongoing | 1 | 1 |  |  |  | Barhabise | 2
18544 | Sindhupalchok | Karthali | 5 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-25 | 2016-10-01 |  | Barhabise | 2
18545 | Sindhupalchok | Karthali | 6 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01 |  | Barhabise | 2
18546 | Sindhupalchok | Karthali | 7 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01 |  | Barhabise | 2
18547 | Sindhupalchok | Karthali | 8 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-25 | 2016-10-01 |  | Barhabise | 2
18548 | Sindhupalchok | Karthali | 9 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01 |  | Barhabise | 2
18549 | Sindhupalchok | Karthali | All | MC | CDECF | MC | Technical Assistance | Household reconstruction orientation | 1 session | mobilize team of technical and non technical person to household level for orientation on safer reconstruction and (IEC) poster distribution. | # of households | Yes | Planned | 1032 | 0 | 2017-04-15 |  |  | Barhabise | 2
18550 | Sindhupalchok | Karthali |  | MC | CDECF | MC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-08-01 |  |  | Barhabise | 2
18551 | Sindhupalchok | Maneswor | 1 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-14 | 2016-09-20 |  | Barhabise | 8
18552 | Sindhupalchok | Maneswor | 2 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20 |  | Barhabise | 8
18553 | Sindhupalchok | Maneswor | 3 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20 |  | Barhabise | 8
18554 | Sindhupalchok | Maneswor | 4 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20 |  | Barhabise | 8
18555 | Sindhupalchok | Maneswor | 5 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-14 | 2016-09-20 |  | Barhabise | 8
18556 | Sindhupalchok | Maneswor | 6 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-14 | 2016-09-20 |  | Barhabise | 8
18557 | Sindhupalchok | Maneswor | 7 | MC | CDECF | MC | Others | Others | (Please specify in Activity Detail) | Reconstruction Support for School for retrofiting and 1 floor wall coverage with 2 rooms prefack construction in Bhadrakali Secondary School | # of trainees | Yes | Ongoing | 1 | 1 |  |  |  | Barhabise | 8
18558 | Sindhupalchok | Maneswor | 7 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20 |  | Barhabise | 8
18559 | Sindhupalchok | Maneswor | 8 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20 |  | Barhabise | 8
18560 | Sindhupalchok | Maneswor | 9 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20 |  | Barhabise | 8
18561 | Sindhupalchok | Maneswor | All | MC | CDECF | MC | Technical Assistance | Household reconstruction orientation | 1 session | mobilize team of technical and non technical person to household level for orientation on safer reconstruction and (IEC) poster distribution. | # of households | Yes | Planned | 912 | 0 | 2017-04-15 |  |  | Barhabise | 8
18562 | Sindhupalchok | Maneswor |  | MC | CDECF | MC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2018-01-01 |  |  | Barhabise | 8
18563 | Sindhupalchok | Maneswor |  | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0 | 2017-08-01 |  |  | Barhabise | 8
18564 | Sindhupalchok | Maneswor |  | MC | CDECF | MC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-11-15 | 2018-02-15 |  | Barhabise | 8
18565 | Sindhupalchok | Maneswor | 4 | MC | CDECF | MC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 1 | 2017-08-15 |  |  | Barhabise | 8
18566 | Sindhupalchok | Maneswor | 5 | MC | CDECF | MC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 6 | 2017-08-15 |  |  | Barhabise | 8
18567 | Sindhupalchok | Maneswor | 7 | MC | CDECF | MC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 7 | 2017-08-15 |  |  | Barhabise | 8
18568 | Sindhupalchok | Maneswor | 8 | MC | CDECF | MC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 8 | 2017-08-15 |  |  | Barhabise | 8
18569 | Sindhupalchok | Maneswor | 9 | MC | CDECF | MC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 2 |  |  |  | Barhabise | 8
18570 | Sindhupalchok | Ramche | 1 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-14 | 2016-09-20 |  | Barhabise | 9
18571 | Sindhupalchok | Ramche | 2 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-14 | 2016-09-20 |  | Barhabise | 9
18572 | Sindhupalchok | Ramche | 3 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20 |  | Barhabise | 9
18573 | Sindhupalchok | Ramche | 4 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-14 | 2016-09-20 |  | Barhabise | 9
18574 | Sindhupalchok | Ramche | 5 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-09-14 | 2016-09-20 |  | Barhabise | 9
18575 | Sindhupalchok | Ramche | 6 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20 |  | Barhabise | 9
18576 | Sindhupalchok | Ramche | 7 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20 |  | Barhabise | 9
18577 | Sindhupalchok | Ramche | 8 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20 |  | Barhabise | 9
18578 | Sindhupalchok | Ramche | 9 | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20 |  | Barhabise | 9
18579 | Sindhupalchok | Ramche | All | MC | CDECF | MC | Technical Assistance | Household reconstruction orientation | 1 session | mobilize team of technical and non technical person to household level for orientation on safer reconstruction and (IEC) poster distribution. | # of households | Yes | Planned | 885 | 0 | 2017-04-15 |  |  | Barhabise | 9
18580 | Sindhupalchok | Ramche |  | MC | CDECF | MC | Others | Others | (Please specify in Activity Detail) | Construction Support for School constructing 2 rooms for library in Shree Sarashwati Secondary school | # of trainees | Yes | Ongoing | 1 | 1 |  |  |  | Barhabise | 9
18581 | Sindhupalchok | Ramche |  | MC | CDECF | MC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-07-20 |  |  | Barhabise | 9
18582 | Sindhupalchok | Ramche |  | MC | CDECF | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 30 | 30 | 2017-08-01 |  |  | Barhabise | 9
18583 | Sindhupalchok | Ramche | All | MC | CDECF | MC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-12-01 | 2018-02-15 |  | Barhabise | 9
18584 | Sindhupalchok | Ramche | 1 | MC | CDECF | MC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 2 | 2017-08-15 |  |  | Barhabise | 9
18585 | Sindhupalchok | Ramche | 2 | MC | CDECF | MC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 4 | 2017-08-15 |  |  | Barhabise | 9
18586 | Sindhupalchok | Ramche | 6 | MC | CDECF | MC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 1 | 2017-08-15 |  |  | Barhabise | 9
18587 | Sindhupalchok | Ramche | 7 | MC | CDECF | MC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 1 | 2017-08-15 |  |  | Barhabise | 9
18588 | Sindhupalchok | Ramche | 8 | MC | CDECF | MC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 21 | 2017-08-15 |  |  | Barhabise | 9
18589 | Sindhupalchok | Fulpingkatti |  | MEDAIR | CDECF | ECHO | Others | Others | (Please specify in Activity Detail) | Cash for Work Demolition | # of trainees | Yes | Completed | 24 | 24 | 2015-09-01 | 2015-09-30 |  | Bhotekoshi | 4
18590 | Sindhupalchok | Fulpingkatti |  | MEDAIR | CDECF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Planned | 9 | 0 |  |  |  | Bhotekoshi | 4
18591 | Sindhupalchok | Gati |  | MEDAIR | CDECF | ECHO | Others | Others | (Please specify in Activity Detail) | Cash for Work Demolition | # of trainees | Yes | Completed | 54 | 54 | 2015-09-01 | 2015-09-30 |  | Barhabise | 6
18592 | Sindhupalchok | Gati |  | MEDAIR | CDECF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Planned | 9 | 0 |  |  |  | Barhabise | 6
18593 | Sindhupalchok | Listikot |  | MEDAIR | CDECF | ECHO | Others | Others | (Please specify in Activity Detail) | Cash for Work Demolition | # of trainees | Yes | Completed | 36 | 36 | 2015-09-01 | 2015-09-30 |  | Bhotekoshi | 1
18594 | Sindhupalchok | Listikot |  | MEDAIR | CDECF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 9 | 9 | 2016-05-01 | 2016-05-05 |  | Bhotekoshi | 1
18595 | Sindhupalchok | Piskar |  | MEDAIR | CDECF | ECHO | Others | Others | (Please specify in Activity Detail) | Cash for Work Demolition | # of trainees | Yes | Completed | 84 | 84 | 2015-09-01 | 2015-09-30 |  | Tripura Sundari | 4
18596 | Sindhupalchok | Piskar |  | MEDAIR | CDECF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Planned | 9 | 0 |  |  |  | Tripura Sundari | 4
18597 | Sindhupalchok | Bahrabise |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2016-08-01 |  | In clusterwise planning phase | Barhabise | 4
18598 | Sindhupalchok | Bahrabise |  | OXFAM-GB | GMSP | OXFAM-GB | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | Block Making | # of trainees | Yes | Completed | 40 | 10 | 2016-11-01 | 2016-12-15 |  | Barhabise | 4
18599 | Sindhupalchok | Baramchi | All | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | Ward wise orientation on BBS | # of participants | Yes | Completed | 600 | 604 | 2016-11-20 | 2016-11-28 |  | Jugal | 5
18600 | Sindhupalchok | Baramchi |  | OXFAM-GB | JGSS | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | OJT | # of trainees | Yes | Completed | 19 | 19 | 2016-12-06 | 2017-01-26 |  | Jugal | 5
18601 | Sindhupalchok | Baramchi | All | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 600 | 603 | 2016-04-01 | 2017-03-30 |  | Jugal | 5
18602 | Sindhupalchok | Baramchi |  | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-12-01 | 2017-01-15 |  | Jugal | 5
18603 | Sindhupalchok | Baramchi |  | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2017-08-25 |  | In clusterwise planning phase | Jugal | 5
18604 | Sindhupalchok | Baramchi |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2016-02-23 | 2017-03-01 |  | Jugal | 5
18605 | Sindhupalchok | Baramchi | All | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 348 | 348 | 2017-07-01 | 2018-03-01 |  | Jugal | 5
18606 | Sindhupalchok | Chautara N.P. | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Retrofitting training | Skilled construction workers | One week training | # of trainees | Yes | Planned | 20 | 0 | 2017-11-23 | 2017-12-01 |  | Chautara Sangachokgadhi | 6
18607 | Sindhupalchok | Choukati | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-06-24 | 2016-06-30 |  | Tripura Sundari | 2
18608 | Sindhupalchok | Choukati | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-24 | 2016-06-30 |  | Tripura Sundari | 2
18609 | Sindhupalchok | Choukati | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-06-24 | 2016-06-30 |  | Tripura Sundari | 2
18610 | Sindhupalchok | Choukati | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-24 | 2016-06-30 |  | Tripura Sundari | 2
18611 | Sindhupalchok | Choukati | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-06-24 | 2016-06-30 |  | Tripura Sundari | 2
18612 | Sindhupalchok | Choukati | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-24 | 2016-06-30 |  | Tripura Sundari | 2
18613 | Sindhupalchok | Choukati | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-06-24 | 2016-06-30 |  | Tripura Sundari | 2
18614 | Sindhupalchok | Choukati | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-24 | 2016-06-30 |  | Tripura Sundari | 2
18615 | Sindhupalchok | Choukati | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-06-24 | 2016-06-30 |  | Tripura Sundari | 2
18616 | Sindhupalchok | Choukati | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-24 | 2016-06-30 |  | Tripura Sundari | 2
18617 | Sindhupalchok | Choukati | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-06-24 | 2016-06-30 |  | Tripura Sundari | 2
18618 | Sindhupalchok | Choukati | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-24 | 2016-06-30 |  | Tripura Sundari | 2
18619 | Sindhupalchok | Choukati | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-06-24 | 2016-06-30 |  | Tripura Sundari | 2
18620 | Sindhupalchok | Choukati | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-24 | 2016-06-30 |  | Tripura Sundari | 2
18621 | Sindhupalchok | Choukati | 8 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-06-24 | 2016-06-30 |  | Tripura Sundari | 2
18622 | Sindhupalchok | Choukati | 8 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-24 | 2016-06-30 |  | Tripura Sundari | 2
18623 | Sindhupalchok | Choukati | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-06-24 | 2016-06-30 |  | Tripura Sundari | 2
18624 | Sindhupalchok | Choukati | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-24 | 2016-06-30 |  | Tripura Sundari | 2
18625 | Sindhupalchok | Choukati |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 104 | 104 | 2016-10-01 |  | In clusterwise planning phase | Tripura Sundari | 2
18626 | Sindhupalchok | Choukati |  | OXFAM-GB | GMSP | OXFAM-GB | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-12-01 | 2016-01-15 |  | Tripura Sundari | 2
18627 | Sindhupalchok | Choukati | 6 | OXFAM-GB | GMSP | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0 | 2017-09-01 | 2017-09-07 |  | Tripura Sundari | 2
18628 | Sindhupalchok | Fulpingkatti |  | OXFAM-GB |  | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2017-08-25 |  |  | Bhotekoshi | 4
18629 | Sindhupalchok | Gloche |  | OXFAM-GB |  | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2017-08-25 |  |  | Jugal | 2
18630 | Sindhupalchok | Gloche | All | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 378 | 378 | 2017-07-01 | 2018-03-30 |  | Jugal | 2
18631 | Sindhupalchok | Gumba |  | OXFAM-GB |  | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2017-08-25 |  |  | Jugal | 3
18632 | Sindhupalchok | Gumba | All | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 421 | 421 | 2017-07-01 | 2018-03-30 |  | Jugal | 3
18633 | Sindhupalchok | Hagam | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-06-07 | 2016-06-13 |  | Jugal | 6
18634 | Sindhupalchok | Hagam | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-07 | 2016-06-13 |  | Jugal | 6
18635 | Sindhupalchok | Hagam | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-06-07 | 2016-06-13 |  | Jugal | 6
18636 | Sindhupalchok | Hagam | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-07 | 2016-06-13 |  | Jugal | 6
18637 | Sindhupalchok | Hagam | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-06-07 | 2016-06-13 |  | Jugal | 6
18638 | Sindhupalchok | Hagam | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-07 | 2016-06-13 |  | Jugal | 6
18639 | Sindhupalchok | Hagam | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-06-07 | 2016-06-13 |  | Jugal | 6
18640 | Sindhupalchok | Hagam | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-07 | 2016-06-13 |  | Jugal | 6
18641 | Sindhupalchok | Hagam | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-06-07 | 2016-06-13 |  | Jugal | 6
18642 | Sindhupalchok | Hagam | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-07 | 2016-06-13 |  | Jugal | 6
18643 | Sindhupalchok | Hagam | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-06-07 | 2016-06-13 |  | Jugal | 7
18644 | Sindhupalchok | Hagam | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-07 | 2016-06-13 |  | Jugal | 7
18645 | Sindhupalchok | Hagam | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-06-07 | 2016-06-13 |  | Jugal | 7
18646 | Sindhupalchok | Hagam | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-07 | 2016-06-13 |  | Jugal | 7
18647 | Sindhupalchok | Hagam | 8 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-06-07 | 2016-06-13 |  | Jugal | 7
18648 | Sindhupalchok | Hagam | 8 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-07 | 2016-06-13 |  | Jugal | 7
18649 | Sindhupalchok | Hagam | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-06-07 | 2016-06-13 |  | Jugal | 7
18650 | Sindhupalchok | Hagam | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-07 | 2016-06-13 |  | Jugal | 7
18651 | Sindhupalchok | Hagam |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 600 | 680 | 2016-11-29 | 2016-12-07 |  | Jugal | 7
18652 | Sindhupalchok | Hagam |  | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-12-01 | 2017-01-15 |  | Jugal | 7
18653 | Sindhupalchok | Hagam |  | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 400 | 411 | 2016-04-01 | 2017-03-30 |  | Jugal | 7
18654 | Sindhupalchok | Hagam |  | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2017-08-25 |  |  | Jugal | 7
18655 | Sindhupalchok | Hagam |  | OXFAM-GB | JGSS | OXFAM-GB | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 20 | 19 | 2017-01-26 | 2017-02-01 |  | Jugal | 7
18656 | Sindhupalchok | Hagam |  | OXFAM-GB | JGSS | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 41 days OJT mason training and construction model house | # of trainees | Yes | Completed | 20 | 20 | 2016-12-13 | 2017-01-30 |  | Jugal | 7
18657 | Sindhupalchok | Hagam |  | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 378 | 378 | 2017-07-01 | 2018-03-30 |  | Jugal | 7
18658 | Sindhupalchok | Helumbu |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Planned | 216 | 0 | 2016-06-01 |  |  | Helambu | 1
18659 | Sindhupalchok | Helumbu |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2017-08-25 |  | In clusterwise planning phase | Helambu | 1
18660 | Sindhupalchok | Helumbu |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 36 | 24 | 2016-08-15 |  | In clusterwise planning phase | Helambu | 1
18661 | Sindhupalchok | Helumbu | 5 | OXFAM-GB | MANK | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0 | 2017-09-01 | 2017-09-07 |  | Helambu | 1
18662 | Sindhupalchok | Helumbu | All | OXFAM-GB | MANK | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 243 | 243 | 2017-10-01 | 2018-03-30 |  | #N/A | #N/A
18663 | Sindhupalchok | Helumbu |  | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Construction | Private house | Integrated settlement | # of constructions | Yes | Ongoing | 40 | 40 | 2018-01-01 |  |  | Helambu | 1
18664 | Sindhupalchok | Bahrabise | All | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Construction | Private house | Integrated settlement | # of constructions | Yes | Ongoing | 6 | 6 | 2018-02-01 |  |  | Barhabise | 4
18665 | Sindhupalchok | Ichok |  | OXFAM-GB |  | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2017-08-25 |  |  | Helambu | 7
18666 | Sindhupalchok | Ichok | All | OXFAM-GB | MANK | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 233 | 233 | Ashish Purush Dhakal | 9851128965 |  | #N/A | #N/A
18667 | Sindhupalchok | Jalbire | All | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 600 | 644 | 2016-12-20 | 2016-12-28 |  | Balefi | 2
18668 | Sindhupalchok | Jalbire |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2016-08-01 |  | In clusterwise planning phase | Balefi | 2
18669 | Sindhupalchok | Kadambas | All | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 600 | 465 | 2016-11-26 | 2016-12-04 |  | Chautara Sangachokgadhi | 9
18670 | Sindhupalchok | Kadambas |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2016-08-01 |  | In clusterwise planning phase | Chautara Sangachokgadhi | 9
18671 | Sindhupalchok | Kadambas |  | OXFAM-GB | JGSS | OXFAM-GB | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-02-12 | 2017-02-18 |  | Chautara Sangachokgadhi | 9
18672 | Sindhupalchok | Kalika |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2016-08-01 |  | In clusterwise planning phase | Sunkoshi | 3
18673 | Sindhupalchok | Kiwool | All | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 27 | 27 | 2016-11-11 | 2016-11-17 |  | Helambu | 2
18674 | Sindhupalchok | Kiwool |  | OXFAM-GB | MANK | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Planned | 216 | 0 | 2016-06-01 |  |  | Helambu | 2
18675 | Sindhupalchok | Kiwool |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2017-08-25 |  | In clusterwise planning phase | Helambu | 2
18676 | Sindhupalchok | Kiwool |  | OXFAM-GB | MANK | OXFAM-GB | Training | Short training | Carpenter |  | # of trainees | Yes | Planned | 36 | 0 | 2016-08-15 |  | In clusterwise planning phase | Helambu | 2
18677 | Sindhupalchok | Kiwool |  | OXFAM-GB | MANK | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 41 days OJT mason training and construction model house | # of trainees | Yes | Completed | 20 | 18 |  |  |  | Helambu | 2
18678 | Sindhupalchok | Kiwool |  | OXFAM-GB | MANK | OXFAM-GB | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Helambu | 2
18679 | Sindhupalchok | kiwool | All | OXFAM-GB | MANK | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 268 | 268 | 2018-10-01 | 2018-03-30 |  | Helambu | 2
18680 | Sindhupalchok | Kunchok | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-05-18 | 2016-05-24 |  | Indrawati | 2
18681 | Sindhupalchok | Kunchok | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-18 | 2016-05-24 |  | Indrawati | 2
18682 | Sindhupalchok | Kunchok | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-05-18 | 2016-05-24 |  | Indrawati | 2
18683 | Sindhupalchok | Kunchok | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-18 | 2016-05-24 |  | Indrawati | 2
18684 | Sindhupalchok | Kunchok | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 1 | 1 | 2016-05-18 | 2016-05-24 |  | Indrawati | 2
18685 | Sindhupalchok | Kunchok | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-18 | 2016-05-24 |  | Indrawati | 2
18686 | Sindhupalchok | Kunchok | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-05-18 | 2016-05-24 |  | Indrawati | 2
18687 | Sindhupalchok | Kunchok | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-18 | 2016-05-24 |  | Indrawati | 2
18688 | Sindhupalchok | Kunchok | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-05-18 | 2016-05-24 |  | Indrawati | 3
18689 | Sindhupalchok | Kunchok | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-18 | 2016-05-24 |  | Indrawati | 3
18690 | Sindhupalchok | Kunchok | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-05-18 | 2016-05-24 |  | Indrawati | 3
18691 | Sindhupalchok | Kunchok | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-18 | 2016-05-24 |  | Indrawati | 3
18692 | Sindhupalchok | Kunchok | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-05-18 | 2016-05-24 |  | Indrawati | 3
18693 | Sindhupalchok | Kunchok | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-18 | 2016-05-24 |  | Indrawati | 3
18694 | Sindhupalchok | Kunchok | 8 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-05-18 | 2016-05-24 |  | Indrawati | 3
18695 | Sindhupalchok | Kunchok | 8 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-18 | 2016-05-24 |  | Indrawati | 3
18696 | Sindhupalchok | Kunchok | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-05-18 | 2016-05-24 |  | Indrawati | 3
18697 | Sindhupalchok | Kunchok | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-18 | 2016-05-24 |  | Indrawati | 3
18698 | Sindhupalchok | Kunchok |  | OXFAM-GB | MANK | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 458 | 458 | 2016-06-01 |  |  | Indrawati | 3
18699 | Sindhupalchok | Kunchok |  | OXFAM-GB | MANK | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2016-08-01 |  | In clusterwise planning phase | Indrawati | 3
18700 | Sindhupalchok | Kunchok |  | OXFAM-GB | MANK | OXFAM-GB | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Ongoing | 36 | 15 | 2016-08-15 |  | In clusterwise planning phase | Indrawati | 3
18701 | Sindhupalchok | Listikot |  | OXFAM-GB |  | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2017-08-25 |  |  | Bhotekoshi | 1
18702 | Sindhupalchok | Listikot | All | OXFAM-GB | GMSP | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 331 | 331 | 2017-07-01 | 2018-03-30 |  | Bhotekoshi | 1
18703 | Sindhupalchok | Mahankal |  | OXFAM-GB | MANK | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2017-08-25 |  |  | Helambu | 5
18704 | Sindhupalchok | Mahankal |  | OXFAM-GB | MANK | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 211 | 211 | 2017-10-01 | 2018-03-30 |  | Helambu | 5
18705 | Sindhupalchok | Marming |  | OXFAM-GB |  | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2017-08-25 |  |  | Bhotekoshi | 5
18706 | Sindhupalchok | Nawalpur |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 453 | 453 | 2016-06-01 |  |  | Indrawati | 4
18707 | Sindhupalchok | Nawalpur |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2016-08-01 |  | In clusterwise planning phase | Indrawati | 4
18708 | Sindhupalchok | Nawalpur |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Ongoing | 36 | 14 | 2016-08-15 |  | In clusterwise planning phase | Indrawati | 4
18709 | Sindhupalchok | Pagretar |  | OXFAM-GB | GMSP | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 150 | 141 | 2016-10-01 |  | In clusterwise planning phase | Sunkoshi | 7
18710 | Sindhupalchok | Pagretar |  | OXFAM-GB | GMSP | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 41 days OJT mason training and construction model house | # of trainees | Yes | Completed | 20 | 17 | 2016-01-01 | 2017-03-30 |  | Sunkoshi | 7
18711 | Sindhupalchok | Pagretar |  | OXFAM-GB | GMSP | OXFAM-GB | Technical Assistance | Demonstration Construction | House | 41 days OJT mason training and construction model house | # of constructions | Yes | Completed | 1 | 1 | 2017-01-01 | 2017-03-30 |  | Sunkoshi | 7
18712 | Sindhupalchok | Palchok |  | OXFAM-GB | MANK | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 400 | 0 | 2017-08-25 |  |  | Helambu | 3
18713 | Sindhupalchok | Palchok |  | OXFAM-GB | MANK | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 233 | 233 | 2017-10-01 | 2018-03-30 |  | Helambu | 3
18714 | Sindhupalchok | Pangtang |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 30 | 30 | 2016-06-09 | 2016-06-15 |  | Jugal | 4
18715 | Sindhupalchok | Pangtang |  | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 600 | 627 | 2016-11-12 | 2016-11-20 |  | Jugal | 4
18716 | Sindhupalchok | Pangtang |  | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-12-01 | 2017-01-15 |  | Jugal | 4
18717 | Sindhupalchok | Pangtang |  | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 350 | 344 | 2016-04-01 | 2017-03-30 | In clusterwise planning phase | Jugal | 4
18718 | Sindhupalchok | Pangtang |  | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 500 | 0 | 2017-08-25 | 2018-03-31 |  | Jugal | 4
18719 | Sindhupalchok | Pangtang |  | OXFAM-GB | JGSS | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 20 | 2016-06-09 | 2016-06-15 |  | Jugal | 4
18720 | Sindhupalchok | Pangtang |  | OXFAM-GB | JGSS | OXFAM-GB | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-12-12 | 2017-01-29 |  | Jugal | 4
18721 | Sindhupalchok | Pangtang |  | OXFAM-GB | JGSS | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 19 | 2016-02-03 | 2016-02-09 |  | Jugal | 4
18722 | Sindhupalchok | Pangtang | All | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 321 | 321 | 2017-07-01 | 2018-03-30 |  | #N/A | #N/A
18723 | Sindhupalchok | Ramche |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2016-08-01 |  | In clusterwise planning phase | Barhabise | 9
18724 | Sindhupalchok | Selang |  | OXFAM-GB |  | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2017-08-25 |  |  | Jugal | 1
18725 | Sindhupalchok | Selang |  | OXFAM-GB | JGSS | OXFAM-GB | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Ongoing | 40 | 0 | 2017-08-01 | 2018-03-31 |  | Jugal | 1
18726 | Sindhupalchok | Selang | All | OXFAM-GB | JGSS | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 342 | 342 | 2017-07-01 | 2018-03-30 |  | #N/A | #N/A
18727 | Sindhupalchok | Sunkhani |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 500 | 399 | 2016-10-01 |  | In clusterwise planning phase | Sunkoshi | 5
18728 | Sindhupalchok | Sunkhani |  | OXFAM-GB | GMSP | OXFAM-GB | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 20 | 19 | 2016-01-15 |  |  | Sunkoshi | 5
18729 | Sindhupalchok | Tatopani | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-05-27 | 2016-06-02 |  | Bhotekoshi | 2
18730 | Sindhupalchok | Tatopani | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-27 | 2016-06-02 |  | Bhotekoshi | 2
18731 | Sindhupalchok | Tatopani | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 5 | 5 | 2016-05-27 | 2016-06-02 |  | Bhotekoshi | 2
18732 | Sindhupalchok | Tatopani | 2 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-27 | 2016-06-02 |  | Bhotekoshi | 2
18733 | Sindhupalchok | Tatopani | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-05-27 | 2016-06-02 |  | Bhotekoshi | 2
18734 | Sindhupalchok | Tatopani | 3 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-27 | 2016-06-02 |  | Bhotekoshi | 2
18735 | Sindhupalchok | Tatopani | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 7 | 7 | 2016-05-27 | 2016-06-02 |  | Bhotekoshi | 2
18736 | Sindhupalchok | Tatopani | 4 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-27 | 2016-06-02 |  | Bhotekoshi | 2
18737 | Sindhupalchok | Tatopani | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-05-27 | 2016-06-02 |  | Bhotekoshi | 3
18738 | Sindhupalchok | Tatopani | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-27 | 2016-06-02 |  | Bhotekoshi | 3
18739 | Sindhupalchok | Tatopani | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-05-27 | 2016-06-02 |  | Bhotekoshi | 3
18740 | Sindhupalchok | Tatopani | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-27 | 2016-06-02 |  | Bhotekoshi | 3
18741 | Sindhupalchok | Tatopani | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-05-27 | 2016-06-02 |  | Bhotekoshi | 3
18742 | Sindhupalchok | Tatopani | 7 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-27 | 2016-06-02 |  | Bhotekoshi | 3
18743 | Sindhupalchok | Tatopani | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-05-27 | 2016-06-02 |  | Bhotekoshi | 3
18744 | Sindhupalchok | Tatopani | 9 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-27 | 2016-06-02 |  | Bhotekoshi | 3
18745 | Sindhupalchok | Tatopani |  | OXFAM-GB | OXFAM-GB | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2016-08-01 |  | In clusterwise planning phase | Bhotekoshi | 3
18746 | Sindhupalchok | Tatopani |  | OXFAM-GB | GMSP | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2017-08-25 |  |  | Bhotekoshi | 3
18747 | Sindhupalchok | Tatopani |  | OXFAM-GB | GMSP | OXFAM-GB | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 15 | 15 | 2016-09-01 |  |  | Bhotekoshi | 3
18748 | Sindhupalchok | Tatopani | All | OXFAM-GB | GMSP | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 142 | 142 | 2017-07-01 | 2018-03-30 |  | #N/A | #N/A
18749 | Sindhupalchok | Fulpingkatti |  | OXFAM-GB | GMSP | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-10-31 | 2017-11-06 |  | Bhotekoshi | 4
18750 | Sindhupalchok | Fulpingkatti | All | OXFAM-GB | GMSP | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 342 | 342 | 2017-07-01 | 2018-03-30 |  | #N/A | #N/A
18751 | Sindhupalchok | Badegau |  | PLAN | SSE | DFATD-C | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 262 | 262 | 2016-01-16 | 2016-01-22 |  | Indrawati | 6
18752 | Sindhupalchok | Gumba | 5 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Jugal | 3
18753 | Sindhupalchok | Choukati | 6 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Tripura Sundari | 2
18754 | Sindhupalchok | Chautara N.P. | 4 | OXFAM-GB | JGSS | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Repair and retrofit | Retrofitting in coordination with and technical support by Build Change | # of households | Yes | Ongoing | 1 | 1 | 2017-12-10 | 2017-01-15 |  | Chautara Sangachokgadhi | 5
18755 | Sindhupalchok | Helumbu | All | OXFAM-GB | MANK | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0 | 2017-01-15 |  |  | #N/A | #N/A
18756 | Sindhupalchok | Marming | All | OXFAM-GB | GMSP | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 187 | 187 | 2017-07-01 | 2018-03-30 |  | Bhotekoshi | 5
18757 | Sindhupalchok | Badegau |  | PLAN | SSE | DFATD-C | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-01-16 | 2016-01-22 | school for shelter and environment (SSE) Please add | Indrawati | 6
18758 | Sindhupalchok | Batase |  | PLAN | SSE | DFATD-C | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 234 | 234 | 2016-05-24 | 2016-05-30 |  | Chautara Sangachokgadhi | 3
18759 | Sindhupalchok | Batase |  | PLAN | SSE | DFATD-C | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 29 | 29 | 2016-05-24 | 2016-05-30 | school for shelter and environment (SSE) Please add | Chautara Sangachokgadhi | 3
18760 | Sindhupalchok | Bhotasipa |  | PLAN | SSE | DFATD-C | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 231 | 231 | 2016-05-12 | 2016-05-18 |  | Indrawati | 10
18761 | Sindhupalchok | Bhotasipa |  | PLAN | SSE | DFATD-C | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-12 | 2016-05-18 | school for shelter and environment (SSE) Please add | Indrawati | 10
18762 | Sindhupalchok | BhoteNamlang |  | PLAN | SSE | DFATD-C | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 150 | 150 | 2016-05-20 | 2016-05-27 |  | Panchpokhari Thangpal | 7
18763 | Sindhupalchok | BhoteNamlang |  | PLAN | SSE | DFATD-C | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-05-20 | 2016-05-27 |  | Panchpokhari Thangpal | 7
18764 | Sindhupalchok | Melamchi N.P. |  | PLAN | SSE | DFATD-C | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 372 | 372 | 2015-09-27 | 2015-10-04 |  | Melamchi | 13
18765 | Sindhupalchok | Melamchi N.P. |  | PLAN | SSE | DFATD-C | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 60 | 60 | 2015-09-27 | 2015-10-04 |  | Melamchi | 13
18766 | Sindhupalchok | SipalKavre |  | PLAN | SSE | DFATD-C | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 208 | 208 | 2016-01-04 | 2016-01-11 |  | Indrawati | 1
18767 | Sindhupalchok | SipalKavre |  | PLAN | SSE | DFATD-C | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-01-04 | 2016-01-11 |  | Indrawati | 1
18768 | Sindhupalchok | SyauleBazar |  | PLAN | SSE | DFATD-C | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 173 | 173 | 2015-12-24 | 2015-12-30 |  | Chautara Sangachokgadhi | 1
18769 | Sindhupalchok | SyauleBazar |  | PLAN | SSE | DFATD-C | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2015-12-24 | 2015-12-30 |  | Chautara Sangachokgadhi | 1
18770 | Sindhupalchok | Chautara N.P. | 2 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-08-26 | 2016-09-13 |  | Chautara Sangachokgadhi | 6
18771 | Sindhupalchok | Chautara N.P. | 2 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-01 | 2016-10-30 |  | Chautara Sangachokgadhi | 6
18772 | Sindhupalchok | Chautara N.P. | 8 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Relay of HDPE pipe at ward no.6 Melchaur | # of households | Yes | Completed | 200 | 200 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 7
18773 | Sindhupalchok | Chautara N.P. | 8 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake and Relay of HDPE pipe at ward no.6 Chaulagain Tol | # of households | Yes | Completed | 20 | 20 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 7
18774 | Sindhupalchok | Chautara N.P. | 8 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Relay of HDPE pipe at ward no.8 Bisauna Dada | # of households | Yes | Completed | 38 | 38 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 7
18775 | Sindhupalchok | Chautara N.P. | 8 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Relay of HDPE pipe at ward no.8 Tallo Arubote | # of households | Yes | Completed | 70 | 70 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 7
18776 | Sindhupalchok | Chautara N.P. | 8 | PWJ | ISAP | JP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2015-06-15 | 2015-11-30 | Model houses are in old Sanosirubari VDC, now in Chautara N.P | Chautara Sangachokgadhi | 7
18777 | Sindhupalchok | Chautara N.P. | 8 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 17 | 2015-06-15 | 2015-11-30 | 7 days training | Chautara Sangachokgadhi | 7
18778 | Sindhupalchok | Chautara N.P. | 8 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 17 | 17 | 2015-06-15 | 2015-11-30 | 50 days Training | Chautara Sangachokgadhi | 7
18779 | Sindhupalchok | Chautara N.P. | 9 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Ferro Cement Tank(18cum) at ward no.5 Nepane Gaun | # of households | Yes | Completed | 135 | 135 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 7
18780 | Sindhupalchok | Chautara N.P. | 9 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Ferro Cement Tank(10cum) at ward no.5 Jhyandi | # of households | Yes | Completed | 25 | 25 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 7
18781 | Sindhupalchok | Chautara N.P. | 9 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Lay Poles & Transformer for Lift Project at ward no.9 Pauwa | # of households | Yes | Completed | 160 | 160 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 7
18782 | Sindhupalchok | Chautara N.P. | 9 | PWJ | ISAP | JP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 6 | 6 | 2015-06-15 | 2015-11-30 | Model houses are in old Sanosirubari VDC, now in Chautara N.P | Chautara Sangachokgadhi | 7
18783 | Sindhupalchok | Chautara N.P. | 9 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 43 | 43 | 2015-06-15 | 2015-11-30 | 7 days training | Chautara Sangachokgadhi | 7
18784 | Sindhupalchok | Chautara N.P. | 9 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 43 | 43 | 2015-06-15 | 2015-11-30 |  | Chautara Sangachokgadhi | 7
18785 | Sindhupalchok | Chautara N.P. | 8 | PWJ | ISAP | JP | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 135 | 70 | 2015-06-15 | 2015-07-30 |  | Chautara Sangachokgadhi | 7
18786 | Sindhupalchok | Chautara N.P. | 9 | PWJ | ISAP | JP | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 270 | 227 | 2015-06-15 | 2015-07-30 |  | Chautara Sangachokgadhi | 7
18787 | Sindhupalchok | Irkhu | 1 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Relay of GI Pipe at ward no.1 Irkhu Bazar | # of households | Yes | Completed | 46 | 46 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18788 | Sindhupalchok | Irkhu | 1 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake and Relay of HDPE pipe at ward no.1 Mathillo Khadka Tole | # of households | Yes | Completed | 20 | 20 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18789 | Sindhupalchok | Irkhu | 1 | PWJ | ISAP | JP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-01 | 2016-10-30 |  | Chautara Sangachokgadhi | 8
18790 | Sindhupalchok | Irkhu | 1 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-08-26 | 2016-09-13 | 7 days training | Chautara Sangachokgadhi | 8
18791 | Sindhupalchok | Irkhu | 1 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-01 | 2016-10-30 | 50 days Training | Chautara Sangachokgadhi | 8
18792 | Sindhupalchok | Irkhu | 2 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake and Relay of HDPE pipe at ward no.2 Gaire Dhara | # of households | Yes | Completed | 16 | 16 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18793 | Sindhupalchok | Irkhu | 2 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-08-26 | 2016-09-13 |  | Chautara Sangachokgadhi | 8
18794 | Sindhupalchok | Irkhu | 2 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-01 | 2016-10-30 | 50 days Training | Chautara Sangachokgadhi | 8
18795 | Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake and Relay of HDPE pipe at ward no.3 Chhipichaur | # of households | Yes | Completed | 13 | 13 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18796 | Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake and Relay of HDPE pipe at ward no.3 kalimatikhola | # of households | Yes | Completed | 35 | 35 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18797 | Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake and Relay of HDPE pipe at ward no.3 sim khola Bisauna | # of households | Yes | Completed | 16 | 16 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18798 | Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake at ward no.3 sim khola Vasme | # of households | Yes | Completed | 6 | 6 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18799 | Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake at ward no.3 Sunar khola | # of households | Yes | Completed | 30 | 30 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18800 | Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Stone Masonry RVT(8cum),HDPE pipe and lift at ward no.3 Deurali Khola | # of households | Yes | Completed | 110 | 110 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18801 | Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-01 | 2016-10-30 |  | Chautara Sangachokgadhi | 8
18802 | Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-08-26 | 2016-09-13 |  | Chautara Sangachokgadhi | 8
18803 | Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-03-01 | 2016-10-30 | 50 days Training | Chautara Sangachokgadhi | 8
18804 | Sindhupalchok | Irkhu | 4 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Stone Masonry RVT(8cum) ,HDPE pipe & Intake at ward no.4 Batase dada | # of households | Yes | Completed | 16 | 16 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18805 | Sindhupalchok | Irkhu | 4 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Stone Masonry RVT(8cum) at ward no.4 Batase mul | # of households | Yes | Completed | 22 | 22 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18806 | Sindhupalchok | Irkhu | 4 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Relay of HDPE pipe at ward no.4 Chyandada | # of households | Yes | Completed | 8 | 8 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18807 | Sindhupalchok | Irkhu | 4 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Relay of HDPE pipe at ward no.4 Mijar tol | # of households | Yes | Completed | 10 | 10 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18808 | Sindhupalchok | Irkhu | 5 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake at ward no.5 Alumula bari | # of households | Yes | Completed | 11 | 11 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18809 | Sindhupalchok | Irkhu | 5 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Stone Masonry RVT(8cum) ,HDPE pipe and Intake at ward no.5 Bagar Mula Bari | # of households | Yes | Completed | 27 | 27 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18810 | Sindhupalchok | Irkhu | 5 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake at ward no.5 Dhande Gaun | # of households | Yes | Completed | 35 | 35 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18811 | Sindhupalchok | Irkhu | 5 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Stone Masonry RVT(8cum)+Intake at ward no.5 Dip Mula Bari | # of households | Yes | Completed | 19 | 19 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18812 | Sindhupalchok | Irkhu | 5 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake ,Relay of HDPE pipe & Tap Stand at ward no.5 Mane Dada | # of households | Yes | Completed | 9 | 9 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18813 | Sindhupalchok | Irkhu | 5 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-08-26 | 2016-09-13 |  | Chautara Sangachokgadhi | 8
18814 | Sindhupalchok | Irkhu | 5 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-10-30 | 50 days Training | Chautara Sangachokgadhi | 8
18815 | Sindhupalchok | Irkhu | 6 | PWJ | ISAP | JP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-01 | 2016-10-30 |  | Chautara Sangachokgadhi | 8
18816 | Sindhupalchok | Irkhu | 6 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-08-26 | 2016-09-13 |  | Chautara Sangachokgadhi | 8
18817 | Sindhupalchok | Irkhu | 6 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-03-01 | 2016-10-30 | 50 days Training | Chautara Sangachokgadhi | 8
18818 | Sindhupalchok | Irkhu | 7 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake and Relay of HDPE pipe at ward no.7 Juge khola | # of households | Yes | Completed | 1 | 10 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18819 | Sindhupalchok | Irkhu | 7 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake and Relay of HDPE pipe at ward no.7 Dada kanle | # of households | Yes | Completed | 40 | 40 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18820 | Sindhupalchok | Irkhu | 7 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Construction of Intake at ward no.7 Tin Dhara | # of households | Yes | Completed | 14 | 14 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18821 | Sindhupalchok | Irkhu | 7 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Stone Masonry RVT(8cum) ,Relay of HDPE pipe and lift at ward no.7 Harre | # of households | Yes | Completed | 20 | 20 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18822 | Sindhupalchok | Irkhu | 7 | PWJ | ISAP | JP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-01 | 2016-10-30 |  | Chautara Sangachokgadhi | 8
18823 | Sindhupalchok | Irkhu | 7 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-08-26 | 2016-09-13 |  | Chautara Sangachokgadhi | 8
18824 | Sindhupalchok | Irkhu | 7 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-03-01 | 2016-10-30 | 50 days Training | Chautara Sangachokgadhi | 8
18825 | Sindhupalchok | Irkhu | 8 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Stone Masonry RVT(8cum) , Relay of HDPE pipe and lift at ward no.8 Simkhet | # of households | Yes | Completed | 62 | 62 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18826 | Sindhupalchok | Irkhu | 8 | PWJ | ISAP | JP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-01 | 2016-10-30 |  | Chautara Sangachokgadhi | 8
18827 | Sindhupalchok | Irkhu | 8 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-08-26 | 2016-09-13 |  | Chautara Sangachokgadhi | 8
18828 | Sindhupalchok | Irkhu | 8 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-03-01 | 2016-10-30 | 50 days Training | Chautara Sangachokgadhi | 8
18829 | Sindhupalchok | Irkhu | 9 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Relay of HDPE pipe at ward no.9 Karkichhap | # of households | Yes | Completed | 15 | 15 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18830 | Sindhupalchok | Irkhu | 9 | PWJ | ISAP | JP | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply repair/rehabilitation | Stone Masonry RVT(8cum) and Relay of HDPE/GI pipe at ward no.9 Gaje Khola | # of households | Yes | Completed | 46 | 46 | 2016-06-05 | 2016-11-30 |  | Chautara Sangachokgadhi | 8
18831 | Sindhupalchok | Irkhu | 9 | PWJ | ISAP | JP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-08-26 | 2016-09-13 |  | Chautara Sangachokgadhi | 8
18832 | Sindhupalchok | Irkhu | 9 | PWJ | ISAP | JP | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-03-01 | 2016-10-30 | 50 days Training | Chautara Sangachokgadhi | 8
18833 | Sindhupalchok | Irkhu | 1 | PWJ | ISAP | JP | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 45 | 25 | 2016-08-15 | 2016-08-30 |  | Chautara Sangachokgadhi | 8
18834 | Sindhupalchok | Irkhu | 2 | PWJ | ISAP | JP | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 45 | 20 | 2016-08-15 | 2016-08-30 |  | Chautara Sangachokgadhi | 8
18835 | Sindhupalchok | Irkhu | 3 | PWJ | ISAP | JP | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 45 | 80 | 2016-08-15 | 2016-08-30 |  | Chautara Sangachokgadhi | 8
18836 | Sindhupalchok | Irkhu | 4 | PWJ | ISAP | JP | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 45 | 20 | 2016-08-15 | 2016-08-30 |  | Chautara Sangachokgadhi | 8
18837 | Sindhupalchok | Irkhu | 5 | PWJ | ISAP | JP | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 45 | 40 | 2016-08-15 | 2016-08-30 |  | Chautara Sangachokgadhi | 8
18838 | Sindhupalchok | Irkhu | 6 | PWJ | ISAP | JP | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 45 | 40 | 2016-08-15 | 2016-08-30 |  | Chautara Sangachokgadhi | 8
18839 | Sindhupalchok | Irkhu | 7 | PWJ | ISAP | JP | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 45 | 80 | 2016-08-15 | 2016-08-30 |  | Chautara Sangachokgadhi | 8
18840 | Sindhupalchok | Irkhu | 8 | PWJ | ISAP | JP | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 45 | 40 | 2016-08-15 | 2016-08-30 |  | Chautara Sangachokgadhi | 8
18841 | Sindhupalchok | Irkhu | 9 | PWJ | ISAP | JP | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 45 | 35 | 2016-08-15 | 2016-08-30 |  | Chautara Sangachokgadhi | 8
18842 | Sindhupalchok | Jalbire |  | PWJ | ISAP | PWJ | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 33 | 2017-08-09 | 2017-08-15 |  | Balefi | 2
18843 | Sindhupalchok | Jethal | 2 | PWJ | ISAP | PWJ | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-25 | 2017-06-20 |  | Lisangkhu Pakhar | 5
18844 | Sindhupalchok | Jethal | 5 | PWJ | ISAP | PWJ | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-25 | 2017-07-15 | Ward yet to confirm | Lisangkhu Pakhar | 5
18845 | Sindhupalchok | Jethal |  | PWJ | ISAP | PWJ | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Ongoing | 240 | 300 | 2017-05-24 | 2017-06-15 | Ward yet to confirm | Lisangkhu Pakhar | 5
18846 | Sindhupalchok | Jethal |  | PWJ | ISAP | PWJ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 32 | 16 | 2017-05-30 | 2017-06-05 | Ward yet to confirm | Lisangkhu Pakhar | 5
18847 | Sindhupalchok | Jethal |  | PWJ | ISAP | PWJ | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 20 | 14 | 2017-03-25 | 2017-05-01 | Ward yet to confirm | Lisangkhu Pakhar | 5
18848 | Sindhupalchok | Jethal |  | PWJ | ISAP | PWJ | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 200 | 147 | 2017-01-01 | 2017-05-01 |  | Lisangkhu Pakhar | 5
18849 | Sindhupalchok | ThuloPakhar | 1 | PWJ | ISAP | PWJ | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-25 | 2017-06-20 |  | Lisangkhu Pakhar | 7
18850 | Sindhupalchok | ThuloPakhar |  | PWJ | ISAP | PWJ | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-25 | 2017-07-15 | Ward yet to confirm | Lisangkhu Pakhar | 7
18851 | Sindhupalchok | ThuloPakhar |  | PWJ | ISAP | PWJ | Technical Assistance | Household reconstruction orientation | 1 session | Orientation in a public place with BBS messeges | # of households | Yes | Ongoing | 240 | 300 | 2017-05-15 | 2017-05-26 | Ward yet to confirm | Lisangkhu Pakhar | 7
18852 | Sindhupalchok | ThuloPakhar |  | PWJ | ISAP | PWJ | Training | Short training | Masons (7 days DUDBC, rural or urban) | Short training conducted in Thulopakhar ward No. 1 | # of trainees | Yes | Completed | 32 | 19 | 2017-05-30 | 2017-06-05 | Ward yet to confirm | Lisangkhu Pakhar | 7
18853 | Sindhupalchok | ThuloPakhar |  | PWJ | ISAP | PWJ | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 20 | 16 | 2017-03-25 | 2017-05-01 | Ward yet to confirm | Lisangkhu Pakhar | 7
18854 | Sindhupalchok | ThuloPakhar |  | PWJ | ISAP | PWJ | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 200 | 361 | 2017-01-01 | 2017-05-01 |  | Lisangkhu Pakhar | 7
18855 | Sindhupalchok | Bhotechaur | 1 | ROTARY | CDRA | ROTARY-BHU | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Planned | 50 | 0 |  |  | Date planning to fixed | Melamchi | 1
18856 | Sindhupalchok | Choukati | 5 | ROTARY | CDRA | ROTARY-BHU | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Planned | 30 | 0 |  |  | Date planning to fixed | Tripura Sundari | 2
18857 | Sindhupalchok | Jalbire |  | ROTARY | CDRA | ROTARY-BHU | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Planned | 30 | 0 |  |  | Date planning to fixed | Balefi | 2
18858 | Sindhupalchok | Melamchi N.P. | 12 | ROTARY | NTA | ROTARY | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 42 | 42 | 2016-02-01 | 2016-06-01 | Majhitar | Melamchi | 10
18859 | Sindhupalchok | Thokarpa | 4 | ROTARY | ROTARY | ROTARY-BHU | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Planned | 30 | 0 |  |  | Date planning to fixed | Sunkoshi | 1
18860 | Sindhupalchok | Atarpur | All | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 75 | 42 | 2016-07-25 | 2016-12-31 | 7 days Training | Lisangkhu Pakhar | 4
18861 | Sindhupalchok | Atarpur | All | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Completed | 40 | 43 | 2016-12-07 | 2017-01-28 | 50 days Training | Lisangkhu Pakhar | 4
18862 | Sindhupalchok | Badegau | All | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 180 hrs mason training in 2016 | # of trainees | Yes | Ongoing | 75 | 40 | 2016-06-25 | 2016-08-05 | 50 days Training | Indrawati | 6
18863 | Sindhupalchok | Badegau | All | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Completed | 40 | 37 | 2017-07-13 | 2017-09-07 |  | Indrawati | 6
18864 | Sindhupalchok | Bhimtar |  | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 2 lots (first in 8-Dec-16 - 23-Jan-17, second in 15-jan-17 - 6-Mar-17) | # of trainees | Yes | Completed | 80 | 67 | 2016-12-08 | 2017-03-06 | 50 days Training | Indrawati | 12
18865 | Sindhupalchok | Bhotasipa | All | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 75 | 53 | 2016-06-16 | 2016-12-31 | 7 days Training | Indrawati | 10
18866 | Sindhupalchok | Bhotasipa | All | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 52 | 52 | 2017-08-01 | 2017-09-22 |  | Indrawati | 10
18867 | Sindhupalchok | Dhuyang |  | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Completed | 40 | 35 | 2016-12-13 | 2017-02-04 | 50 days Training | Barhabise | 7
18868 | Sindhupalchok | Dubachour | All | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 180 hrs mason training in 2016 | # of trainees | Yes | Completed | 75 | 20 | 2016-06-01 | 2016-12-31 | 50 days Training | Melamchi | 8
18869 | Sindhupalchok | Fulpingkatti |  | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Completed | 40 | 40 | 2016-12-12 | 2017-01-20 | 50 days Training | Bhotekoshi | 4
18870 | Sindhupalchok | Ghuskun |  | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 40 | 69 | 2017-06-28 | 2017-07-04 |  | Tripura Sundari | 3
18871 | Sindhupalchok | Haibung | All | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 180 hrs mason training in 2016 | # of trainees | Yes | Completed | 75 | 40 | 2016-06-02 | 2017-07-14 | 50 days Training | Melamchi | 3
18872 | Sindhupalchok | Haibung |  | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 40 | 18 | 2017-06-06 | 2017-06-13 |  | Melamchi | 3
18873 | Sindhupalchok | Jalbire | All | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | 4 lots | # of trainees | Yes | Completed | 100 | 94 | 2017-06-05 | 2017-06-11 |  | Balefi | 2
18874 | Sindhupalchok | Jethal |  | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Completed | 40 | 43 | 2017-01-24 | 2017-03-16 | 50 days Training | Lisangkhu Pakhar | 5
18875 | Sindhupalchok | Kunchok | All | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots | # of trainees | Yes | Completed | 40 | 40 | 2016-12-20 | 2016-12-26 | 7 days Training | Indrawati | 3
18876 | Sindhupalchok | Kunchok | All | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Completed | 40 | 50 | 2017-01-04 | 2017-02-26 | 50 days Training | Indrawati | 3
18877 | Sindhupalchok | Kunchok | All | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 180 hrs mason training in 2016 | # of trainees | Yes | Completed | 40 | 40 | 2016-05-27 | 2016-07-19 |  | Indrawati | 3
18878 | Sindhupalchok | Lisankhu | All | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots | # of trainees | Yes | Completed | 75 | 40 | 2016-05-29 | 2016-12-31 | 7 days Training | Lisangkhu Pakhar | 3
18879 | Sindhupalchok | Lisankhu | All | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Completed | 40 | 31 | 2016-12-05 | 2017-01-25 | 50 days Training | Lisangkhu Pakhar | 3
18880 | Sindhupalchok | Listikot | All | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots | # of trainees | Yes | Completed | 40 | 34 | 2017-04-20 | 2017-04-27 |  | Bhotekoshi | 1
18881 | Sindhupalchok | Mankha | All | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots | # of trainees | Yes | Completed | 30 | 30 | 2017-07-02 | 2017-07-08 |  | Balefi | 7
18882 | Sindhupalchok | Marming | All | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots | # of trainees | Yes | Completed | 40 | 40 | 2016-12-12 | 2016-12-18 | 7 days Training | Bhotekoshi | 5
18883 | Sindhupalchok | Melamchi N.P. | 5 | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots | # of trainees | Yes | Completed | 75 | 40 | 2016-06-02 | 2016-12-31 | 7 days Training | Melamchi | 11
18884 | Sindhupalchok | Melamchi N.P. | 5 | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 180 hrs mason training in 2016 | # of trainees | Yes | Completed | 75 | 40 | 2016-05-29 | 2016-12-31 | 50 days Training | Melamchi | 11
18885 | Sindhupalchok | Melamchi N.P. |  | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 40 | 0 | 2017-06-15 |  |  | Melamchi | 13
18886 | Sindhupalchok | Motang | All | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots | # of trainees | Yes | Completed | 38 | 38 | 2017-07-21 | 2017-07-27 |  | Panchpokhari Thangpal | 3
18887 | Sindhupalchok | Nawalpur | All | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 180 hrs mason training in 2016 | # of trainees | Yes | Completed | 25 | 20 | 2016-05-28 | 2016-12-31 | 50 days Training | Indrawati | 4
18888 | Sindhupalchok | Petaku | All | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 lots | # of trainees | Yes | Completed | 60 | 37 | 2017-07-02 | 2017-07-08 |  | Lisangkhu Pakhar | 6
18889 | Sindhupalchok | Piskar | All | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 lots | # of trainees | Yes | Completed | 52 | 52 | 2017-06-01 | 2017-06-07 |  | Tripura Sundari | 4
18890 | Sindhupalchok | Piskar | All | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Completed | 42 | 42 | 2017-08-01 | 2017-09-22 |  | Tripura Sundari | 4
18891 | Sindhupalchok | SipalKavre |  | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 40 | 35 | 2016-12-20 | 2016-12-26 | 7 days Training | Indrawati | 1
18892 | Sindhupalchok | SipalKavre |  | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Completed | 40 | 30 | 2017-01-08 | 2017-02-28 | 50 days Training | Indrawati | 1
18893 | Sindhupalchok | SipaPokhare | All | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 75 | 47 | 2016-05-28 | 2016-12-31 | 7 days Training | Indrawati | 8
18894 | Sindhupalchok | Sunkhani |  | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 60 | 0 | 2017-06-15 |  |  | Sunkoshi | 5
18895 | Sindhupalchok | Tauthali | All | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | 3 groups | # of trainees | Yes | Completed | 66 | 66 | 2017-05-31 | 2017-06-06 |  | Tripura Sundari | 5
18896 | Sindhupalchok | Tauthali | All | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Completed | 40 | 40 | 2017-01-25 | 2017-03-15 | 50 days Training | Tripura Sundari | 5
18897 | Sindhupalchok | Thakani | All | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 26 | 2017-06-06 | 2017-06-12 |  | Melamchi | 4
18898 | Sindhupalchok | Thanpalkot | All | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 40 | 38 | 2017-03-01 | 2017-03-07 |  | Panchpokhari Thangpal | 4
18899 | Sindhupalchok | ThuloDhading | All | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | 2 groups | # of trainees | Yes | Completed | 75 | 38 | 2016-06-01 | 2016-12-31 | 7 days Training | Lisangkhu Pakhar | 1
18900 | Sindhupalchok | ThuloDhading | All | SABAL | UCEP-N | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 390 hours mason training based on CTEVT curriculum | # of trainees | Yes | Completed | 40 | 40 | 2016-12-06 | 2017-01-25 | 50 days Training | Lisangkhu Pakhar | 1
18901 | Sindhupalchok | ThumPakhar | All | SABAL | UCEP-N | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 groups | # of trainees | Yes | Completed | 91 | 90 | 2017-04-23 | 2017-04-29 |  | Sunkoshi | 6
18902 | Sindhupalchok | Thulodhading | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 28 | 28 | 2016-10-01 | 2017-09-30 |  | Lisangkhu Pakhar | 1
18903 | Sindhupalchok | Thulodhading | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 765 | 765 | 2016-10-01 | 2017-09-30 |  | Lisangkhu Pakhar | 1
18904 | Sindhupalchok | Tauthali | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 21 | 21 | 2016-10-01 | 2017-09-30 |  | Tripura Sundari | 5
18905 | Sindhupalchok | Tauthali | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 525 | 525 | 2016-10-01 | 2017-09-30 |  | Tripura Sundari | 5
18906 | Sindhupalchok | Jethal | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 19 | 19 | 2016-10-01 | 2017-09-30 |  | #N/A | #N/A
18907 | Sindhupalchok | Jethal | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 532 | 532 | 2016-10-01 | 2017-09-30 |  | #N/A | #N/A
18908 | Sindhupalchok | Fulpingkatti | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 29 | 29 | 2016-10-01 | 2017-09-30 |  | #N/A | #N/A
18909 | Sindhupalchok | Fulpingkatti | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 601 | 601 | 2016-10-01 | 2017-09-30 |  | #N/A | #N/A
18910 | Sindhupalchok | Dhuyang | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 31 | 31 | 2016-10-01 | 2017-09-30 |  | Barhabise | 7
18911 | Sindhupalchok | Dhuyang | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 703 | 703 | 2016-10-01 | 2017-09-30 |  | Barhabise | 7
18912 | Sindhupalchok | Atarpur | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 18 | 18 | 2016-10-01 | 2017-09-30 |  | Lisangkhu Pakhar | 4
18913 | Sindhupalchok | Atarpur | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 408 | 408 | 2016-10-01 | 2017-09-30 |  | Lisangkhu Pakhar | 4
18914 | Sindhupalchok | Marming | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 26 | 26 | 2016-10-01 | 2017-09-30 |  | Bhotekoshi | 5
18915 | Sindhupalchok | Marming | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 666 | 666 | 2016-10-01 | 2017-09-30 |  | Bhotekoshi | 5
18916 | Sindhupalchok | Listikot | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 22 | 22 | 2016-10-01 | 2017-09-30 |  | Bhotekoshi | 1
18917 | Sindhupalchok | Listikot | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 543 | 543 | 2016-10-01 | 2017-09-30 |  | Bhotekoshi | 1
18918 | Sindhupalchok | Lisankhu | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 31 | 31 | 2016-10-01 | 2017-09-30 |  | Lisangkhu Pakhar | 3
18919 | Sindhupalchok | Lisankhu | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 888 | 888 | 2016-10-01 | 2017-09-30 |  | Lisangkhu Pakhar | 3
18920 | Sindhupalchok | Sipalkavre | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 24 | 24 | 2016-10-01 | 2017-09-30 |  | #N/A | #N/A
18921 | Sindhupalchok | SipalKavre | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 498 | 498 | 2016-10-01 | 2017-09-30 |  | #N/A | #N/A
18922 | Sindhupalchok | Nawalpur | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 33 | 33 | 2016-10-01 | 2017-09-30 |  | Indrawati | 4
18923 | Sindhupalchok | Nawalpur | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 607 | 607 | 2016-10-01 | 2017-09-30 |  | Indrawati | 4
18924 | Sindhupalchok | Bhotasipa | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 32 | 32 | 2016-10-01 | 2017-09-30 |  | Indrawati | 10
18925 | Sindhupalchok | Bhotasipa | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 961 | 961 | 2016-10-01 | 2017-09-30 |  | Indrawati | 10
18926 | Sindhupalchok | Badegau | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 29 | 29 | 2016-10-01 | 2017-09-30 |  | Indrawati | 6
18927 | Sindhupalchok | Badegau | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 690 | 690 | 2016-10-01 | 2017-09-30 |  | Indrawati | 6
18928 | Sindhupalchok | SyauleBazar | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 33 | 33 | 2016-10-01 | 2017-09-30 |  | Chautara Sangachokgadhi | 1
18929 | Sindhupalchok | SyauleBazar | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 598 | 598 | 2016-10-01 | 2017-09-30 |  | Chautara Sangachokgadhi | 1
18930 | Sindhupalchok | SipaPokhare | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 36 | 36 | 2016-10-01 | 2017-09-30 |  | Indrawati | 8
18931 | Sindhupalchok | SipaPokhare | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 874 | 874 | 2016-10-01 | 2017-09-30 |  | Indrawati | 8
18932 | Sindhupalchok | Bhimtar | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 25 | 25 | 2016-10-01 | 2017-09-30 |  | #N/A | #N/A
18933 | Sindhupalchok | Bhimtar | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 876 | 876 | 2016-10-01 | 2017-09-30 |  | #N/A | #N/A
18934 | Sindhupalchok | Kunchok | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 31 | 31 | 2016-10-01 | 2017-09-30 |  | Indrawati | 3
18935 | Sindhupalchok | Kunchok | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 567 | 567 | 2016-10-01 | 2017-09-30 |  | Indrawati | 3
18936 | Sindhupalchok | Mahankal | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 32 | 32 | 2016-10-01 | 2017-09-30 |  | #N/A | #N/A
18937 | Sindhupalchok | Mahankal | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 709 | 709 | 2016-10-01 | 2017-09-30 |  | #N/A | #N/A
18938 | Sindhupalchok | Palchok | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 35 | 35 | 2016-10-01 | 2017-09-30 |  | #N/A | #N/A
18939 | Sindhupalchok | Palchok | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 423 | 423 | 2016-10-01 | 2017-09-30 |  | #N/A | #N/A
18940 | Sindhupalchok | Haibung | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 27 | 27 | 2016-10-01 | 2017-09-30 |  | Melamchi | 3
18941 | Sindhupalchok | Haibung | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 598 | 598 | 2016-10-01 | 2017-09-30 |  | Melamchi | 3
18942 | Sindhupalchok | Kiwool | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 31 | 31 | 2016-10-01 | 2017-09-30 |  | Helambu | 2
18943 | Sindhupalchok | Kiwool | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 590 | 590 | 2016-10-01 | 2017-09-30 |  | Helambu | 2
18944 | Sindhupalchok | Thakani | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 21 | 21 | 2016-10-01 | 2017-09-30 |  | Melamchi | 4
18945 | Sindhupalchok | Thakani | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 756 | 756 | 2016-10-01 | 2017-09-30 |  | Melamchi | 4
18946 | Sindhupalchok | Ichok | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 39 | 39 | 2016-10-01 | 2017-09-30 |  | #N/A | #N/A
18947 | Sindhupalchok | Ichok | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 988 | 988 | 2016-10-01 | 2017-09-30 |  | #N/A | #N/A
18948 | Sindhupalchok | Dubachour | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 22 | 22 | 2016-10-01 | 2017-09-30 |  | Melamchi | 8
18949 | Sindhupalchok | Dubachour | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 976 | 976 | 2016-10-01 | 2017-09-30 |  | Melamchi | 8
18950 | Sindhupalchok | Banskharka | All | SABAL | TUKI | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 31 | 31 | 2016-10-01 | 2017-09-30 |  | #N/A | #N/A
18951 | Sindhupalchok | Banskharka | All | SABAL | TUKI | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 879 | 879 | 2016-10-01 | 2017-09-30 |  | #N/A | #N/A
18952 | Sindhupalchok | Fulpingdandagau | 1 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 15 | 15 |  |  | Donor - DFID/DEC-II | Balefi | 4
18953 | Sindhupalchok | Fulpingdandagau | 1 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 10 | 10 | 2015-09-01 | 2016-04-30 |  | Balefi | 4
18954 | Sindhupalchok | Fulpingdandagau | 1 | SCI | TUKI | DEC-II | Technical Assistance | Demonstration Construction | House | Model house | # of constructions | Yes | Completed | 1 | 1 | 2016-03-01 | 2017-01-25 |  | Balefi | 4
18955 | Sindhupalchok | Fulpingdandagau | 1 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 10 | 10 | 2015-09-01 | 2016-04-30 |  | Balefi | 4
18956 | Sindhupalchok | Fulpingdandagau | 2 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 17 | 17 |  |  | Donor - DFID/DEC-II | Balefi | 4
18957 | Sindhupalchok | Fulpingdandagau | 2 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 13 | 13 | 2015-09-01 | 2016-04-30 |  | Balefi | 4
18958 | Sindhupalchok | Fulpingdandagau | 2 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 13 | 13 | 2015-09-01 | 2016-04-30 |  | Balefi | 4
18959 | Sindhupalchok | Fulpingdandagau | 3 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 11 | 11 |  |  | Donor - DFID/DEC-II | Balefi | 4
18960 | Sindhupalchok | Fulpingdandagau | 3 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 10 | 10 | 2015-09-01 | 2016-04-30 |  | Balefi | 4
18961 | Sindhupalchok | Fulpingdandagau | 3 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 10 | 10 | 2015-09-01 | 2016-04-30 |  | Balefi | 4
18962 | Sindhupalchok | Fulpingdandagau | 4 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 8 | 8 |  |  | Donor - DFID/DEC-II | Balefi | 4
18963 | Sindhupalchok | Fulpingdandagau | 4 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 10 | 10 | 2015-09-01 | 2016-04-30 |  | Balefi | 4
18964 | Sindhupalchok | Fulpingdandagau | 4 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 10 | 10 | 2015-09-01 | 2016-04-30 |  | Balefi | 4
18965 | Sindhupalchok | Fulpingdandagau | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 15 | 15 |  |  | Donor - DFID/DEC-II | Balefi | 5
18966 | Sindhupalchok | Fulpingdandagau | 5 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 18 | 18 | 2015-09-01 | 2016-04-30 |  | Balefi | 5
18967 | Sindhupalchok | Fulpingdandagau | 5 | SCI | TUKI | DEC-II | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 500 | 100 | 2017-08-01 |  |  | Balefi | 5
18968 | Sindhupalchok | Fulpingdandagau | 5 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 18 | 18 | 2015-09-01 | 2016-04-30 |  | Balefi | 5
18969 | Sindhupalchok | Fulpingdandagau | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 14 | 14 |  |  | Donor - DFID/DEC-II | Balefi | 5
18970 | Sindhupalchok | Fulpingdandagau | 6 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 9 | 9 | 2015-09-01 | 2016-04-30 |  | Balefi | 5
18971 | Sindhupalchok | Fulpingdandagau | 6 | SCI | TUKI | DEC-II | Technical Assistance | Demonstration Construction | House | Model house | # of constructions | Yes | Completed | 1 | 1 | 2016-03-01 | 2017-01-25 |  | Balefi | 5
18972 | Sindhupalchok | Fulpingdandagau | 6 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 9 | 9 | 2015-09-01 | 2016-04-30 |  | Balefi | 5
18973 | Sindhupalchok | Fulpingdandagau | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 10 | 10 |  |  | Donor - DFID/DEC-II | Balefi | 5
18974 | Sindhupalchok | Fulpingdandagau | 7 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 7 | 7 | 2015-09-01 | 2016-04-30 |  | Balefi | 5
18975 | Sindhupalchok | Fulpingdandagau | 7 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 7 | 7 | 2015-09-01 | 2016-04-30 |  | Balefi | 5
18976 | Sindhupalchok | Fulpingdandagau | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 9 | 9 |  |  | Donor - DFID/DEC-II | Balefi | 4
18977 | Sindhupalchok | Fulpingdandagau | 8 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 7 | 7 | 2015-09-01 | 2016-04-30 |  | Balefi | 4
18978 | Sindhupalchok | Fulpingdandagau | 8 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 7 | 7 | 2015-09-01 | 2016-04-30 |  | Balefi | 4
18979 | Sindhupalchok | Fulpingdandagau | 9 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 11 | 11 |  |  | Donor - DFID/DEC-II | Balefi | 5
18980 | Sindhupalchok | Fulpingdandagau | 9 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 7 | 7 | 2015-09-01 | 2016-04-30 |  | Balefi | 5
18981 | Sindhupalchok | Fulpingdandagau | 9 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2015-09-01 | 2016-04-30 |  | Balefi | 5
18982 | Sindhupalchok | Fulpingdandagau | All | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Completed | 110 | 110 | 2017-02-21 | 2017-09-18 |  | Balefi | 5
18983 | Sindhupalchok | Fulpingdandagau | All | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 110 | 107 | 2017-06-21 | 2017-12-20 | 3 beneficiaries did not receive 3rd tranche until project closed of SCI that will be provided by TUKI when they completed house | Balefi | 5
18984 | Sindhupalchok | Fulpingdandagau | All | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 25 | 0 | 2017-04-15 |  |  | Balefi | 5
18985 | Sindhupalchok | Fulpingdandagau |  | SCI | TUKI | DEC-II | Technical Assistance | Communication and Outreach | PSA Radio broadcasting |  | # of episodes | Yes | Ongoing | 3 | 3 | 2016-03-01 | 2017-03-30 |  | Balefi | 5
18986 | Sindhupalchok | Gloche | 1 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 14 | 14 |  |  |  | Jugal | 2
18987 | Sindhupalchok | Gloche | 1 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 14 | 14 | 2017-02-08 | 2017-10-15 |  | Jugal | 2
18988 | Sindhupalchok | Gloche | 1 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 12 | 12 | 2016-05-12 | 2016-05-18 |  | Jugal | 2
18989 | Sindhupalchok | Gloche | 1 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-05-12 | 2016-05-18 |  | Jugal | 2
18990 | Sindhupalchok | Gloche | 2 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 11 | 11 |  |  |  | Jugal | 2
18991 | Sindhupalchok | Gloche | 2 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 11 | 11 | 2017-02-08 | 2017-03-03 |  | Jugal | 2
18992 | Sindhupalchok | Gloche | 2 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 9 | 9 | 2016-05-12 | 2016-05-18 |  | Jugal | 2
18993 | Sindhupalchok | Gloche | 2 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09 |  | Jugal | 2
18994 | Sindhupalchok | Gloche | 2 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-05-12 | 2016-05-18 |  | Jugal | 2
18995 | Sindhupalchok | Gloche | 2 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09 |  | Jugal | 2
18996 | Sindhupalchok | Gloche | 3 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 13 | 13 |  |  |  | Jugal | 2
18997 | Sindhupalchok | Gloche | 3 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 13 | 13 | 2017-02-08 | 2017-10-15 |  | Jugal | 2
18998 | Sindhupalchok | Gloche | 3 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 9 | 9 | 2016-05-12 | 2016-05-18 |  | Jugal | 2
18999 | Sindhupalchok | Gloche | 3 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09 |  | Jugal | 2
19000 | Sindhupalchok | Gloche | 3 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 9 | 9 | 2016-05-12 | 2016-05-18 |  | Jugal | 2
19001 | Sindhupalchok | Gloche | 3 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09 |  | Jugal | 2
19002 | Sindhupalchok | Gloche | 4 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 7 | 7 |  |  |  | Jugal | 2
19003 | Sindhupalchok | Gloche | 4 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 8 | 8 | 2017-02-08 | 2017-10-15 |  | Jugal | 2
19004 | Sindhupalchok | Gloche | 4 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 3 | 3 | 2016-05-12 | 2016-05-18 |  | Jugal | 2
19005 | Sindhupalchok | Gloche | 4 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 2 | 2 | 2016-06-03 | 2016-06-09 |  | Jugal | 2
19006 | Sindhupalchok | Gloche | 4 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 3 | 3 | 2016-05-12 | 2016-05-18 |  | Jugal | 2
19007 | Sindhupalchok | Gloche | 4 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 2 | 2 | 2016-06-03 | 2016-06-09 |  | Jugal | 2
19008 | Sindhupalchok | Gloche | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 11 | 11 |  |  |  | Jugal | 2
19009 | Sindhupalchok | Gloche | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 10 | 10 | 2017-03-03 | 2017-10-15 |  | Jugal | 2
19010 | Sindhupalchok | Gloche | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 7 | 7 | 2016-05-12 | 2016-05-18 |  | Jugal | 2
19011 | Sindhupalchok | Gloche | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 7 | 7 | 2016-06-03 | 2016-06-09 |  | Jugal | 2
19012 | Sindhupalchok | Gloche | 5 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 7 | 7 | 2016-05-12 | 2016-05-18 |  | Jugal | 2
19013 | Sindhupalchok | Gloche | 5 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 7 | 7 | 2016-06-03 | 2016-06-09 |  | Jugal | 2
19014 | Sindhupalchok | Gloche | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 17 | 17 |  |  |  | Jugal | 2
19015 | Sindhupalchok | Gloche | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 17 | 17 | 2017-02-08 | 2017-10-15 |  | Jugal | 2
19016 | Sindhupalchok | Gloche | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 4 | 4 | 2016-05-12 | 2016-05-18 |  | Jugal | 2
19017 | Sindhupalchok | Gloche | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 4 | 4 | 2016-06-03 | 2016-06-09 |  | Jugal | 2
19018 | Sindhupalchok | Gloche | 6 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 4 | 4 | 2016-05-12 | 2016-05-18 |  | Jugal | 2
19019 | Sindhupalchok | Gloche | 6 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 4 | 4 | 2016-06-03 | 2016-06-09 |  | Jugal | 2
19020 | Sindhupalchok | Gloche | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 13 | 13 |  |  |  | Jugal | 2
19021 | Sindhupalchok | Gloche | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 13 | 13 | 2017-03-03 | 2017-10-15 |  | Jugal | 2
19022 | Sindhupalchok | Gloche | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 11 | 11 | 2016-05-12 | 2016-05-18 |  | Jugal | 2
19023 | Sindhupalchok | Gloche | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09 |  | Jugal | 2
19024 | Sindhupalchok | Gloche | 7 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 11 | 11 | 2016-05-12 | 2016-05-18 |  | Jugal | 2
19025 | Sindhupalchok | Gloche | 7 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09 |  | Jugal | 2
19026 | Sindhupalchok | Gloche | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 10 | 10 |  |  |  | Jugal | 2
19027 | Sindhupalchok | Gloche | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 10 | 10 | 2017-02-08 | 2017-10-15 |  | Jugal | 2
19028 | Sindhupalchok | Gloche | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 2 | 2 | 2016-05-12 | 2016-05-18 |  | Jugal | 2
19029 | Sindhupalchok | Gloche | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 4 | 4 | 2016-06-03 | 2016-06-09 |  | Jugal | 2
19030 | Sindhupalchok | Gloche | 8 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 2 | 2 | 2016-05-12 | 2016-05-18 |  | Jugal | 2
19031 | Sindhupalchok | Gloche | 8 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 4 | 4 | 2016-06-03 | 2016-06-09 |  | Jugal | 2
19032 | Sindhupalchok | Gloche | 9 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 4 | 4 |  |  |  | Jugal | 2
19033 | Sindhupalchok | Gloche | 9 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 4 | 4 | 2017-02-08 | 2017-03-03 |  | Jugal | 2
19034 | Sindhupalchok | Gloche | 9 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 8 | 8 | 2016-05-12 | 2016-05-18 |  | Jugal | 2
19035 | Sindhupalchok | Gloche | 9 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09 |  | Jugal | 2
19036 | Sindhupalchok | Gloche | 9 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 8 | 8 | 2016-05-12 | 2016-05-18 |  | Jugal | 2
19037 | Sindhupalchok | Gloche | 9 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09 |  | Jugal | 2
19038 | Sindhupalchok | Gloche | All | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 100 | 100 | 2017-04-27 |  |  | Jugal | 2
19039 | Sindhupalchok | Gloche |  | SCI | TUKI | DEC-II | Technical Assistance | Communication and Outreach | PSA Radio broadcasting | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of episodes | Yes | Ongoing | 3 | 3 | 2016-03-01 | 2017-03-30 |  | Jugal | 2
19040 | Sindhupalchok | Gloche |  | SCI | TUKI | DEC-II | Technical Assistance | Demonstration Construction | House | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of constructions | Yes | Ongoing | 2 | 1 | 2016-03-01 | 2017-03-30 |  | Jugal | 2
19041 | Sindhupalchok | Gloche |  | SCI | TUKI | DEC-II | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 500 | 100 | 2017-08-01 |  |  | Jugal | 2
19042 | Sindhupalchok | Gloche |  | SCI | TUKI | DEC-II | Training | Vocational training | New masons (50 days OJT CTEVT) | 40 days mason training of CTEVT curriculum | # of trainees | Yes | Completed | 11 | 11 | 2017-02-21 | 2017-04-15 |  | Jugal | 2
19043 | Sindhupalchok | Gumba | 1 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 9 | 9 |  |  |  | Jugal | 3
19044 | Sindhupalchok | Gumba | 1 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 9 | 8 | 2017-02-08 | 2017-12-20 | one beneficiary did not receive until project closed of SCI | Jugal | 3
19045 | Sindhupalchok | Gumba | 1 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 10 | 10 | 2016-05-12 | 2016-05-18 |  | Jugal | 3
19046 | Sindhupalchok | Gumba | 1 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09 |  | Jugal | 3
19047 | Sindhupalchok | Gumba | 1 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 10 | 10 | 2016-05-12 | 2016-05-18 |  | Jugal | 3
19048 | Sindhupalchok | Gumba | 1 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09 |  | Jugal | 3
19049 | Sindhupalchok | Gumba | 2 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 5 | 5 |  |  |  | Jugal | 3
19050 | Sindhupalchok | Gumba | 2 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 5 | 5 | 2017-02-08 | 2017-10-15 |  | Jugal | 3
19051 | Sindhupalchok | Gumba | 2 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 3 | 3 | 2016-05-12 | 2016-05-18 |  | Jugal | 3
19052 | Sindhupalchok | Gumba | 2 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09 |  | Jugal | 3
19053 | Sindhupalchok | Gumba | 2 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 3 | 3 | 2016-05-12 | 2016-05-18 |  | Jugal | 3
19054 | Sindhupalchok | Gumba | 2 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09 |  | Jugal | 3
19055 | Sindhupalchok | Gumba | 3 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 12 | 12 |  |  |  | Jugal | 3
19056 | Sindhupalchok | Gumba | 3 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 12 | 12 | 2017-02-08 | 2017-10-15 |  | Jugal | 3
19057 | Sindhupalchok | Gumba | 3 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 8 | 8 | 2016-05-12 | 2016-05-18 |  | Jugal | 3
19058 | Sindhupalchok | Gumba | 3 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 4 | 4 | 2016-06-03 | 2016-06-09 |  | Jugal | 3
19059 | Sindhupalchok | Gumba | 3 | SCI | TUKI | DEC-II | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 500 | 100 | 2017-08-01 |  |  | Jugal | 3
19060 | Sindhupalchok | Gumba | 3 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 8 | 8 | 2016-05-12 | 2016-05-18 |  | Jugal | 3
19061 | Sindhupalchok | Gumba | 3 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 4 | 4 | 2016-06-03 | 2016-06-09 |  | Jugal | 3
19062 | Sindhupalchok | Gumba | 4 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 11 | 11 |  |  |  | Jugal | 3
19063 | Sindhupalchok | Gumba | 4 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 11 | 11 | 2017-02-08 | 2017-10-15 |  | Jugal | 3
19064 | Sindhupalchok | Gumba | 4 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 1 | 1 | 2016-05-12 | 2016-05-18 |  | Jugal | 3
19065 | Sindhupalchok | Gumba | 4 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 2 | 2 | 2016-06-03 | 2016-06-09 |  | Jugal | 3
19066 | Sindhupalchok | Gumba | 4 | SCI | TUKI | DEC-II | Technical Assistance | Demonstration Construction | House | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of constructions | Yes | Completed | 1 | 1 | 2016-03-01 | 2017-01-25 |  | Jugal | 3
19067 | Sindhupalchok | Gumba | 4 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 1 | 1 | 2016-05-12 | 2016-05-18 |  | Jugal | 3
19068 | Sindhupalchok | Gumba | 4 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 2 | 2 | 2016-06-03 | 2016-06-09 |  | Jugal | 3
19069 | Sindhupalchok | Gumba | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 9 | 9 |  |  |  | Jugal | 3
19070 | Sindhupalchok | Gumba | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 9 | 9 | 2017-02-08 | 2017-10-15 |  | Jugal | 3
19071 | Sindhupalchok | Gumba | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 7 | 7 | 2016-05-12 | 2016-05-18 |  | Jugal | 3
19072 | Sindhupalchok | Gumba | 5 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 4 | 4 | 2016-06-03 | 2016-06-09 |  | Jugal | 3
19073 | Sindhupalchok | Gumba | 5 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 7 | 7 | 2016-05-12 | 2016-05-18 |  | Jugal | 3
19074 | Sindhupalchok | Gumba | 5 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 4 | 4 | 2016-06-03 | 2016-06-09 |  | Jugal | 3
19075 | Sindhupalchok | Gumba | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 12 | 12 |  |  |  | Jugal | 3
19076 | Sindhupalchok | Gumba | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 12 | 12 | 2017-02-08 | 2017-10-15 |  | Jugal | 3
19077 | Sindhupalchok | Gumba | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 8 | 8 | 2016-05-12 | 2016-05-18 |  | Jugal | 3
19078 | Sindhupalchok | Gumba | 6 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09 |  | Jugal | 3
19079 | Sindhupalchok | Gumba | 6 | SCI | TUKI | DEC-II | Technical Assistance | Demonstration Construction | House | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of constructions | Yes | Completed | 1 | 1 | 2016-03-01 | 2017-01-25 |  | Jugal | 3
19080 | Sindhupalchok | Gumba | 6 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 8 | 8 | 2016-05-12 | 2016-05-18 |  | Jugal | 3
19081 | Sindhupalchok | Gumba | 6 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09 |  | Jugal | 3
19082 | Sindhupalchok | Gumba | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 9 | 9 |  |  |  | Jugal | 3
19083 | Sindhupalchok | Gumba | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 16 | 16 | 2017-02-08 | 2017-11-01 |  | Jugal | 3
19084 | Sindhupalchok | Gumba | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 8 | 8 | 2016-05-12 | 2016-05-18 |  | Jugal | 3
19085 | Sindhupalchok | Gumba | 7 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09 |  | Jugal | 3
19086 | Sindhupalchok | Gumba | 7 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 8 | 8 | 2016-05-12 | 2016-05-18 |  | Jugal | 3
19087 | Sindhupalchok | Gumba | 7 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09 |  | Jugal | 3
19088 | Sindhupalchok | Gumba | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 33 | 33 |  |  |  | Jugal | 3
19089 | Sindhupalchok | Gumba | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Completed | 54 | 54 | 2017-02-08 | 2017-11-01 |  | Jugal | 3
19090 | Sindhupalchok | Gumba | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 11 | 11 | 2016-05-12 | 2016-05-18 |  | Jugal | 3
19091 | Sindhupalchok | Gumba | 8 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 7 | 7 | 2016-06-03 | 2016-06-09 |  | Jugal | 3
19092 | Sindhupalchok | Gumba | 8 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 11 | 11 | 2016-05-12 | 2016-05-18 |  | Jugal | 3
19093 | Sindhupalchok | Gumba | 8 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 7 | 7 | 2016-06-03 | 2016-06-09 |  | Jugal | 3
19094 | Sindhupalchok | Gumba | 9 | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 5 | 5 | 2016-05-12 | 2016-05-18 |  | Jugal | 3
19095 | Sindhupalchok | Gumba | 9 | SCI | TUKI | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 5 | 5 | 2016-05-12 | 2016-05-18 |  | Jugal | 3
19096 | Sindhupalchok | Gumba | All | SCI | TUKI | DEC-II | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of households | Yes | Ongoing | 128 | 127 | 2017-06-21 | 2017-12-20 | 1 beneficiary did not receive 2nd tranche until project closed of SCI | Jugal | 3
19097 | Sindhupalchok | Gumba |  | SCI | TUKI | DEC-II | Technical Assistance | Communication and Outreach | PSA Radio broadcasting | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of episodes | Yes | Ongoing | 3 | 3 | 2016-03-01 | 2017-03-30 |  | Jugal | 3
19098 | Sindhupalchok | Gumba | All | SCI | TUKI | DEC-II | Training | Vocational training | New masons (50 days OJT CTEVT) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 10 | 7 | 2017-02-21 | 2017-04-15 |  | Jugal | 3
19099 | Sindhupalchok | Mankha | 2 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 3 | 3 | 2016-04-03 | 2016-04-09 |  | Balefi | 8
19100 | Sindhupalchok | Mankha | 2 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 4 | 4 | 2016-04-17 | 2016-04-23 |  | Balefi | 8
19101 | Sindhupalchok | Mankha | 2 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 3 | 3 | 2016-04-03 | 2016-04-09 |  | Balefi | 8
19102 | Sindhupalchok | Mankha | 2 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 4 | 4 | 2016-04-17 | 2016-04-23 |  | Balefi | 8
19103 | Sindhupalchok | Mankha | 3 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 1 | 1 | 2016-04-17 | 2016-04-23 |  | Balefi | 7
19104 | Sindhupalchok | Mankha | 3 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 1 | 1 | 2016-04-17 | 2016-04-23 |  | Balefi | 7
19105 | Sindhupalchok | Mankha | 4 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 4 | 4 | 2016-04-03 | 2016-04-09 |  | Balefi | 7
19106 | Sindhupalchok | Mankha | 4 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 9 | 9 | 2016-04-17 | 2016-04-23 |  | Balefi | 7
19107 | Sindhupalchok | Mankha | 4 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 4 | 4 | 2016-04-03 | 2016-04-09 |  | Balefi | 7
19108 | Sindhupalchok | Mankha | 4 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 9 | 9 | 2016-04-17 | 2016-04-23 |  | Balefi | 7
19109 | Sindhupalchok | Mankha | 5 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 4 | 4 | 2016-04-03 | 2016-04-09 |  | Balefi | 7
19110 | Sindhupalchok | Mankha | 5 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 6 | 6 | 2016-04-17 | 2016-04-23 |  | Balefi | 7
19111 | Sindhupalchok | Mankha | 5 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 4 | 4 | 2016-04-03 | 2016-04-09 |  | Balefi | 7
19112 | Sindhupalchok | Mankha | 5 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 6 | 6 | 2016-04-17 | 2016-04-23 |  | Balefi | 7
19113 | Sindhupalchok | Mankha | 6 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 8 | 8 | 2016-04-03 | 2016-04-09 |  | Balefi | 7
19114 | Sindhupalchok | Mankha | 6 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 9 | 9 | 2016-04-17 | 2016-04-23 |  | Balefi | 7
19115 | Sindhupalchok | Mankha | 6 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 8 | 8 | 2016-04-03 | 2016-04-09 |  | Balefi | 7
19116 | Sindhupalchok | Mankha | 6 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 9 | 9 | 2016-04-17 | 2016-04-23 |  | Balefi | 7
19117 | Sindhupalchok | Mankha | 8 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 1 | 1 | 2016-04-17 | 2016-04-23 |  | Balefi | 6
19118 | Sindhupalchok | Mankha | 8 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 1 | 1 | 2016-04-17 | 2016-04-23 |  | Balefi | 6
19119 | Sindhupalchok | Mankha | 9 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 3 | 3 | 2016-04-03 | 2016-04-09 |  | Balefi | 6
19120 | Sindhupalchok | Mankha | 9 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 3 | 3 | 2016-04-03 | 2016-04-09 |  | Balefi | 6
19121 | Sindhupalchok | Melamchi N.P. | 8 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 11 | 11 | 2016-04-03 | 2016-04-09 |  | Melamchi | 12
19122 | Sindhupalchok | Melamchi N.P. | 8 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 13 | 13 | 2016-04-17 | 2016-04-23 |  | Melamchi | 12
19123 | Sindhupalchok | Melamchi N.P. | 8 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 24 | 24 | 2016-04-03 | 2016-04-09 |  | Melamchi | 12
19124 | Sindhupalchok | Melamchi N.P. | 9 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 12 | 12 | 2016-04-03 | 2016-04-09 |  | Melamchi | 12
19125 | Sindhupalchok | Melamchi N.P. | 9 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 20 | 20 | 2016-04-17 | 2016-04-23 |  | Melamchi | 12
19126 | Sindhupalchok | Melamchi N.P. | 9 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 32 | 32 | 2016-04-03 | 2016-04-09 |  | Melamchi | 12
19127 | Sindhupalchok | Melamchi N.P. | 10 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 3 | 3 | 2016-04-17 | 2016-04-23 |  | Melamchi | 13
19128 | Sindhupalchok | Melamchi N.P. | 10 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 21 | 21 | 2016-04-06 | 2016-04-12 |  | Melamchi | 13
19129 | Sindhupalchok | Melamchi N.P. | 10 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 24 | 24 | 2016-04-06 | 2016-04-12 |  | Melamchi | 13
19130 | Sindhupalchok | Melamchi N.P. | 11 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 6 | 6 | 2016-04-17 | 2016-04-23 |  | Melamchi | 13
19131 | Sindhupalchok | Melamchi N.P. | 11 | SCI | TUKI | DFID | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 3 | 3 | 2016-04-06 | 2016-04-12 |  | Melamchi | 13
19132 | Sindhupalchok | Melamchi N.P. | 11 | SCI | TUKI | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-04-06 | 2016-04-12 |  | Melamchi | 13
19133 | Sindhupalchok | Sangachok | 3 | SCI | TUKI | ITV | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 143 | 143 | 2016-08-15 |  |  | Chautara Sangachokgadhi | 12
19134 | Sindhupalchok | Sangachok | 8 | SCI | TUKI | ITV | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | ward coverage | # of households | Yes | Completed | 75 | 75 | 2016-11-24 | 2017-02-10 |  | Chautara Sangachokgadhi | 11
19135 | Sindhupalchok | Sangachok | 8 | SCI | TUKI | ITV | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 10 | 10 | 2016-09-13 | 2016-09-19 |  | Chautara Sangachokgadhi | 11
19136 | Sindhupalchok | Sangachok | 8 | SCI | TUKI | ITV | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 75 | 75 | 2016-08-01 |  |  | Chautara Sangachokgadhi | 11
19137 | Sindhupalchok | Sangachok | 8 | SCI | TUKI | ITV | Technical Assistance | Demonstration Construction | House | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of constructions | Yes | Ongoing | 3 | 0 | 2016-04-01 | 2017-02-28 | 5 in 8,9 | Chautara Sangachokgadhi | 11
19138 | Sindhupalchok | Sangachok | 8 | SCI | TUKI | ITV | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 10 | 10 | 2016-09-13 | 2016-09-19 |  | Chautara Sangachokgadhi | 11
19139 | Sindhupalchok | Sangachok | 8 | SCI | TUKI | ITV | Training | Vocational training | New masons (50 days OJT CTEVT) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 10 | 11 | 2016-11-20 | 2016-12-30 |  | Chautara Sangachokgadhi | 11
19140 | Sindhupalchok | Sangachok | 9 | SCI | TUKI | ITV | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | ward coverage | # of households | Yes | Completed | 68 | 68 | 2016-11-25 | 2017-02-10 |  | Chautara Sangachokgadhi | 11
19141 | Sindhupalchok | Sangachok | 9 | SCI | TUKI | ITV | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of kits | Yes | Completed | 10 | 10 | 2016-09-13 | 2016-09-19 |  | Chautara Sangachokgadhi | 11
19142 | Sindhupalchok | Sangachok | 9 | SCI | TUKI | ITV | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 68 | 68 | 2016-08-01 |  |  | Chautara Sangachokgadhi | 11
19143 | Sindhupalchok | Sangachok | 9 | SCI | TUKI | ITV | Technical Assistance | Demonstration Construction | House | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of constructions | Yes | Ongoing | 2 | 0 | 2016-04-01 | 2017-02-28 | 5 in 8,9 | Chautara Sangachokgadhi | 11
19144 | Sindhupalchok | Sangachok | 9 | SCI | TUKI | ITV | Training | Short training | Masons (7 days DUDBC, rural or urban) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 10 | 10 | 2016-09-13 | 2016-09-19 |  | Chautara Sangachokgadhi | 11
19145 | Sindhupalchok | Sangachok | 9 | SCI | TUKI | ITV | Training | Vocational training | New masons (50 days OJT CTEVT) | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of trainees | Yes | Completed | 10 | 9 | 2016-11-20 | 2016-12-30 |  | Chautara Sangachokgadhi | 11
19146 | Sindhupalchok | Sangachok | 8,9 | SCI | TUKI | ITV | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Completed | 143 | 143 | 2017-02-10 | 2017-07-15 |  | Chautara Sangachokgadhi | 12
19147 | Sindhupalchok | Sangachok | 8,9 | SCI | TUKI | ITV | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 143 | 143 | 2017-04-26 |  |  | Chautara Sangachokgadhi | 12
19148 | Sindhupalchok | Sangachok |  | SCI | TUKI | ITV | Technical Assistance | Communication and Outreach | PSA Radio broadcasting | To the most vulnerable beneficiaries who was fairly selected by VDC sec, ward citizen forum | # of episodes | Yes | Ongoing | 1 | 1 | 2016-04-01 | 2016-02-28 |  | Chautara Sangachokgadhi | 12
19149 | Sindhupalchok | Bhimtar | 6 | SoS | SoS | SoS | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | house construction | # of households | Yes | Completed | 51 | 51 | 2016-10-15 |  |  | Indrawati | 12
19150 | Sindhupalchok | Bhimtar | 7 | SoS | SoS | SoS | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | house construction | # of households | Yes | Completed | 41 | 41 | 2016-10-15 |  |  | Indrawati | 12
19151 | Sindhupalchok | Bhimtar | 8 | SoS | SoS | SoS | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | house construction | # of households | Yes | Completed | 85 | 85 | 2016-10-15 |  |  | Indrawati | 12
19152 | Sindhupalchok | Atarpur | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 44 |  |  |  | Lisangkhu Pakhar | 4
19153 | Sindhupalchok | Badegau | 1 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Ongoing | 1 | 1 |  |  |  | Indrawati | 6
19154 | Sindhupalchok | Badegau | 1 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  | 2017-03-20 | As per CTEVT/NRA guideline | Indrawati | 6
19155 | Sindhupalchok | Badegau | 1 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 123 |  |  |  | Indrawati | 6
19156 | Sindhupalchok | Badegau | 1 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 11 | 10 | 2017-05-31 | 2017-07-09 | As per CTEVT/NRA guideline | Indrawati | 6
19157 | Sindhupalchok | Badegau | 2 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Planned | 1 | 0 |  |  |  | Indrawati | 6
19158 | Sindhupalchok | Badegau | 2 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-09 | 2017-07-09 | As per CTEVT/NRA guideline | Indrawati | 6
19159 | Sindhupalchok | Badegau | 2 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 13 | 11 | 2017-03-18 | 2017-07-09 | As per CTEVT/NRA guideline | Indrawati | 6
19160 | Sindhupalchok | Badegau | 3 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 82 |  |  |  | Indrawati | 6
19161 | Sindhupalchok | Badegau | 6 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Planned | 1 | 0 |  |  |  | Indrawati | 5
19162 | Sindhupalchok | Badegau | 6 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-08 | 2017-07-25 | As per CTEVT/NRA guideline | Indrawati | 5
19163 | Sindhupalchok | Badegau | 6 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 5 | 7 | 2017-04-12 | 2017-06-15 | As per CTEVT/NRA guideline | Indrawati | 5
19164 | Sindhupalchok | Badegau | 8 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Planned | 1 | 0 |  |  |  | Indrawati | 6
19165 | Sindhupalchok | Badegau | 8 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-10 | 2017-07-28 | As per CTEVT/NRA guideline | Indrawati | 6
19166 | Sindhupalchok | Badegau | 8 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 6 | 11 | 2017-04-27 | 2017-07-09 | As per CTEVT/NRA guideline | Indrawati | 6
19167 | Sindhupalchok | Badegau | All | UNDP | SUK-N | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support over house completion under direct superivision | # of households | Yes | Ongoing | 300 | 108 | 2016-10-15 |  |  | Indrawati | 6
19168 | Sindhupalchok | Badegau | All | UNDP | UNDP | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Provide materials/tool kits equal to RS. 50 thousands/HH | # of households | Yes | Ongoing | 10 | 10 | 2017-11-01 |  |  | Indrawati | 6
19169 | Sindhupalchok | Baramchi |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 60 |  |  |  | Jugal | 5
19170 | Sindhupalchok | Batase |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 31 |  |  |  | Chautara Sangachokgadhi | 3
19171 | Sindhupalchok | Batase |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 40 |  |  |  | Chautara Sangachokgadhi | 3
19172 | Sindhupalchok | Batase |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 55 |  |  |  | Chautara Sangachokgadhi | 3
19173 | Sindhupalchok | Bhotasipa | 1 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 62 |  |  |  | Indrawati | 9
19174 | Sindhupalchok | Bhotasipa | 2 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 34 |  |  |  | Indrawati | 9
19175 | Sindhupalchok | Bhotasipa | 3 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Planned | 1 | 0 |  |  |  | Indrawati | 9
19176 | Sindhupalchok | Bhotasipa | 3 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-21 | 2017-07-05 | As per CTEVT/NRA guideline | Indrawati | 9
19177 | Sindhupalchok | Bhotasipa | 3 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 39 |  |  |  | Indrawati | 9
19178 | Sindhupalchok | Bhotasipa | 3 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 11 | 11 | 2017-03-21 | 2017-07-09 | As per CTEVT/NRA guideline | Indrawati | 9
19179 | Sindhupalchok | Bhotasipa | 4 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 80 |  |  |  | Indrawati | 9
19180 | Sindhupalchok | Bhotasipa | 6 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Planned | 1 | 0 |  |  |  | Indrawati | 10
19181 | Sindhupalchok | Bhotasipa | 6 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-23 | 2017-07-06 | As per CTEVT/NRA guideline | Indrawati | 10
19182 | Sindhupalchok | Bhotasipa | 6 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 33 |  |  |  | Indrawati | 10
19183 | Sindhupalchok | Bhotasipa | 6 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 11 | 11 | 2017-03-23 | 2017-07-09 | As per CTEVT/NRA guideline | Indrawati | 10
19184 | Sindhupalchok | Bhotasipa | 7 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 102 |  |  |  | Indrawati | 10
19185 | Sindhupalchok | Bhotasipa | 8 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Planned | 1 | 0 |  |  |  | Indrawati | 10
19186 | Sindhupalchok | Bhotasipa | 8 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-25 | 2017-07-07 | As per CTEVT/NRA guideline | Indrawati | 10
19187 | Sindhupalchok | Bhotasipa | 8 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 11 | 8 | 2017-04-24 | 2017-07-09 | As per CTEVT/NRA guideline | Indrawati | 10
19188 | Sindhupalchok | Bhotasipa | 9 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Planned | 1 | 0 |  |  |  | Indrawati | 10
19189 | Sindhupalchok | Bhotasipa | 9 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  | As per CTEVT/NRA guideline | Indrawati | 10
19190 | Sindhupalchok | Bhotasipa | 9 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 11 | 11 | 2017-04-13 | 2017-07-09 | As per CTEVT/NRA guideline | Indrawati | 10
19191 | Sindhupalchok | Bhotasipa | All | UNDP | SUK-N | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support over house completion under direct superivision | # of households | Yes | Ongoing | 100 | 80 | 2016-10-15 |  |  | Indrawati | 10
19192 | Sindhupalchok | Bhotasipa | All | UNDP | UNDP | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Provide materials/tool kits equal to RS. 50 thousands/HH | # of households | Yes | Ongoing | 10 | 10 | 2017-11-01 |  |  | Indrawati | 10
19193 | Sindhupalchok | Chautara N.P. | 1 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 11 |  |  |  | Chautara Sangachokgadhi | 6
19194 | Sindhupalchok | Chautara N.P. | 1 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 11 |  |  |  | Chautara Sangachokgadhi | 6
19195 | Sindhupalchok | Chautara N.P. | 1 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 46 |  |  |  | Chautara Sangachokgadhi | 6
19196 | Sindhupalchok | Chautara N.P. | 2 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 116 |  |  |  | Chautara Sangachokgadhi | 6
19197 | Sindhupalchok | Chautara N.P. | 2 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Ongoing | 1 | 1 |  |  | This activity covers 70% of community participation in the respective demosntration houses construction sites | Chautara Sangachokgadhi | 6
19198 | Sindhupalchok | Chautara N.P. | 2 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 116 |  |  |  | Chautara Sangachokgadhi | 6
19199 | Sindhupalchok | Chautara N.P. | 5 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-05 | 2017-08-01 | As per CTEVT/NRA guideline | Chautara Sangachokgadhi | 4
19200 | Sindhupalchok | Chautara N.P. | 2 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 86 |  |  |  | Chautara Sangachokgadhi | 6
19201 | Sindhupalchok | Chautara N.P. | 5 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 11 | 9 | 2017-03-05 | 2017-04-15 | As per CTEVT/NRA guideline | Chautara Sangachokgadhi | 4
19202 | Sindhupalchok | Chautara N.P. | 3 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 15 |  |  |  | Chautara Sangachokgadhi | 5
19203 | Sindhupalchok | Chautara N.P. | 6 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House | Brick masonry with cement mortar technology house with 1 room | # of constructions | Yes | Completed | 1 | 1 | 2016-11-20 | 2016-12-31 | As per CTEVT/NRA guideline | Chautara Sangachokgadhi | 4
19204 | Sindhupalchok | Chautara N.P. | 5 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 3 | 3 | 2017-10-17 | 2017-12-22 | As per CTEVT/NRA guideline | Chautara Sangachokgadhi | 4
19205 | Sindhupalchok | Chautara N.P. | 4 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 17 |  |  |  | Chautara Sangachokgadhi | 5
19206 | Sindhupalchok | Chautara N.P. | 4 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Ongoing | 1 | 1 |  |  |  | Chautara Sangachokgadhi | 5
19207 | Sindhupalchok | Chautara N.P. | 4 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 17 |  |  |  | Chautara Sangachokgadhi | 5
19208 | Sindhupalchok | Chautara N.P. | 6 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-01-11 | 2017-04-11 | As per CTEVT/NRA guideline | Chautara Sangachokgadhi | 4
19209 | Sindhupalchok | Chautara N.P. | 6 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 11 | 9 | 2017-02-11 | 2017-03-27 | As per CTEVT/NRA guideline | Chautara Sangachokgadhi | 4
19210 | Sindhupalchok | Chautara N.P. | 5 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 59 |  |  |  | Chautara Sangachokgadhi | 4
19211 | Sindhupalchok | Chautara N.P. | 5 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 59 |  |  |  | Chautara Sangachokgadhi | 4
19212 | Sindhupalchok | Chautara N.P. | 5 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 61 |  |  |  | Chautara Sangachokgadhi | 4
19213 | Sindhupalchok | Chautara N.P. | 5 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 65 |  |  |  | Chautara Sangachokgadhi | 4
19214 | Sindhupalchok | Chautara N.P. | 5 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 26 |  |  |  | Chautara Sangachokgadhi | 4
19215 | Sindhupalchok | Chautara N.P. | 6 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 45 |  |  |  | Chautara Sangachokgadhi | 4
19216 | Sindhupalchok | Chautara N.P. | 6 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Completed | 1 | 1 |  |  |  | Chautara Sangachokgadhi | 4
19217 | Sindhupalchok | Chautara N.P. | 6 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 45 |  |  |  | Chautara Sangachokgadhi | 4
19218 | Sindhupalchok | Chautara N.P. | 5 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-02-17 | 2017-04-05 | As per CTEVT/NRA guideline | Chautara Sangachokgadhi | 4
19219 | Sindhupalchok | Chautara N.P. | 6 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 42 |  |  |  | Chautara Sangachokgadhi | 4
19220 | Sindhupalchok | Chautara N.P. | 6 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 45 |  |  |  | Chautara Sangachokgadhi | 4
19221 | Sindhupalchok | Chautara N.P. | 6 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 42 |  |  |  | Chautara Sangachokgadhi | 4
19222 | Sindhupalchok | Chautara N.P. | 6 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 29 |  |  |  | Chautara Sangachokgadhi | 4
19223 | Sindhupalchok | Chautara N.P. | 7 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 73 |  |  |  | Chautara Sangachokgadhi | 5
19224 | Sindhupalchok | Chautara N.P. | 8 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 73 |  |  |  | Chautara Sangachokgadhi | 7
19225 | Sindhupalchok | Chautara N.P. | 8 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Ongoing | 1 | 1 |  |  |  | Chautara Sangachokgadhi | 7
19226 | Sindhupalchok | Chautara N.P. | 8 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 34 |  |  |  | Chautara Sangachokgadhi | 7
19227 | Sindhupalchok | Chautara N.P. | 8 | UNDP | CTEVT | KOICA | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-09 | 2017-04-10 | As per CTEVT/NRA guideline | Chautara Sangachokgadhi | 7
19228 | Sindhupalchok | Chautara N.P. | 8 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 18 |  |  |  | Chautara Sangachokgadhi | 7
19229 | Sindhupalchok | Chautara N.P. | 6 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 14 | 9 | 2017-02-09 | 2017-03-24 | As per CTEVT/NRA guideline | Chautara Sangachokgadhi | 4
19230 | Sindhupalchok | Chautara N.P. | 9 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 34 |  |  |  | Chautara Sangachokgadhi | 7
19231 | Sindhupalchok | Chautara N.P. | 9 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 6 |  |  |  | Chautara Sangachokgadhi | 7
19232 | Sindhupalchok | Chautara N.P. | 9 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 41 |  |  |  | Chautara Sangachokgadhi | 7
19233 | Sindhupalchok | Chautara N.P. | 9 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 43 |  |  |  | Chautara Sangachokgadhi | 7
19234 | Sindhupalchok | Chautara N.P. | 3,7 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 21 |  |  |  | Chautara Sangachokgadhi | 7
19235 | Sindhupalchok | Chautara N.P. | All | UNDP | UNDP | UNDP | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support over house completion under direct superivision | # of households | Yes | Ongoing | 200 | 84 | 2016-10-15 |  |  | Chautara Sangachokgadhi | 7
19236 | Sindhupalchok | Chautara N.P. |  | UNDP | GENESIS | GENESIS | Others | Others | (Please specify in Activity Detail) | Preparation of Risk Sensitive Land Use Planning for Choutara Municipality | # of trainees | Yes | Planned | 0 | 0 | 2016-04-20 | 2016-11-10 |  | Chautara Sangachokgadhi | 7
19237 | Sindhupalchok | Chautara N.P. |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 32 |  |  |  | Chautara Sangachokgadhi | 7
19238 | Sindhupalchok | Chautara N.P. |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 47 |  |  |  | Chautara Sangachokgadhi | 7
19239 | Sindhupalchok | Chautara N.P. |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 110 |  |  |  | Chautara Sangachokgadhi | 7
19240 | Sindhupalchok | Chautara N.P. |  | UNDP | CTEVT | GOJ | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 Days training,CTEVT,Batch 1 | # of trainees | Yes | Completed | 30 | 30 | 2016-09-21 | 2016-09-25 |  | Chautara Sangachokgadhi | 7
19241 | Sindhupalchok | Chautara N.P. |  | UNDP | CTEVT | GOJ | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 Days training,CTEVT,Batch 2 | # of trainees | Yes | Completed | 30 | 30 | 2016-09-26 | 2016-09-30 |  | Chautara Sangachokgadhi | 7
19242 | Sindhupalchok | Chautara N.P. |  | UNDP | CTEVT | GOJ | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 Days training,CTEVT,Batch 3 | # of trainees | Yes | Completed | 30 | 30 | 2016-10-01 | 2016-10-05 |  | Chautara Sangachokgadhi | 7
19243 | Sindhupalchok | Chautara N.P. | 5 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | OJT during the demo house | # of trainees | Yes | Completed | 12 | 9 | 2017-02-09 | 2017-03-24 |  | Chautara Sangachokgadhi | 4
19244 | Sindhupalchok | Chautara N.P. | 6 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | OJT during the demo house | # of trainees | Yes | Completed | 14 | 9 | 2017-02-09 | 2017-03-24 |  | Chautara Sangachokgadhi | 4
19245 | Sindhupalchok | Chautara N.P. | 6 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-10-17 | 2017-12-22 |  | Chautara Sangachokgadhi | 4
19246 | Sindhupalchok | Chautara N.P. | 5 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | OJT during the demo house | # of trainees | Yes | Completed | 15 | 15 | 2017-10-17 | 2017-12-15 |  | Chautara Sangachokgadhi | 4
19247 | Sindhupalchok | Chautara N.P. | 6 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | OJT during the demo house | # of trainees | Yes | Completed | 15 | 15 | 2017-10-17 | 2017-12-15 |  | Chautara Sangachokgadhi | 4
19248 | Sindhupalchok | Chautara N.P. | 5 | UNDP | UNDP | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Provide materials/tool kits equal to RS. 50 thousands/HH | # of households | Yes | Ongoing | 10 | 10 | 2017-11-01 |  |  | Chautara Sangachokgadhi | 4
19249 | Sindhupalchok | Choukati | 2 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 116 |  |  |  | Tripura Sundari | 2
19250 | Sindhupalchok | Dhuyang | 3 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 100 |  |  |  | Barhabise | 7
19251 | Sindhupalchok | Dubachour | 3 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 32 |  |  |  | Melamchi | 7
19252 | Sindhupalchok | Dubachour |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 62 |  |  |  | Melamchi | 8
19253 | Sindhupalchok | Fulpingdandagau | 7 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 29 |  |  |  | Balefi | 5
19254 | Sindhupalchok | Fulpingkot | 1 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 25 |  |  |  | Balefi | 2
19255 | Sindhupalchok | Fulpingkot | 6 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 61 |  |  |  | Balefi | 3
19256 | Sindhupalchok | Fulpingkot | 7 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 40 |  |  |  | Balefi | 3
19257 | Sindhupalchok | Gati | 7 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 162 |  |  |  | Barhabise | 6
19258 | Sindhupalchok | Gati |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 103 |  |  |  | Barhabise | 6
19259 | Sindhupalchok | Gumba |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 39 |  |  |  | Jugal | 3
19260 | Sindhupalchok | Gumba |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 70 |  |  |  | Jugal | 3
19261 | Sindhupalchok | Gumba |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 38 |  |  |  | Jugal | 3
19262 | Sindhupalchok | Hagam | 9 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 40 |  |  |  | Jugal | 7
19263 | Sindhupalchok | Irkhu | 1 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Ongoing | 1 | 1 |  |  |  | Chautara Sangachokgadhi | 8
19264 | Sindhupalchok | Irkhu | 1 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-01-13 | 2017-08-30 | As per CTEVT/NRA guideline | Chautara Sangachokgadhi | 8
19265 | Sindhupalchok | Irkhu | 1 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 11 | 16 | 2017-01-13 | 2017-04-05 | As per CTEVT/NRA guideline | Chautara Sangachokgadhi | 8
19266 | Sindhupalchok | Irkhu | 2 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Completed | 1 | 1 |  |  |  | Chautara Sangachokgadhi | 8
19267 | Sindhupalchok | Irkhu | 2 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-12-06 | 2017-04-01 | As per CTEVT/NRA guideline | Chautara Sangachokgadhi | 8
19268 | Sindhupalchok | Irkhu | 2 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 12 | 13 | 2017-01-05 | 2017-03-25 | As per CTEVT/NRA guideline | Chautara Sangachokgadhi | 8
19269 | Sindhupalchok | Irkhu | 3 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Ongoing | 1 | 1 |  |  |  | Chautara Sangachokgadhi | 8
19270 | Sindhupalchok | Irkhu | 3 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-12-07 | 2016-04-02 | As per CTEVT/NRA guideline | Chautara Sangachokgadhi | 8
19271 | Sindhupalchok | Irkhu | 3 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 12 | 12 | 2017-01-06 | 2017-04-02 | As per CTEVT/NRA guideline | Chautara Sangachokgadhi | 8
19272 | Sindhupalchok | Irkhu | 4 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Ongoing | 1 | 1 |  |  |  | Chautara Sangachokgadhi | 8
19273 | Sindhupalchok | Irkhu | 4 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-01-27 | 2017-03-07 | As per CTEVT/NRA guideline | Chautara Sangachokgadhi | 8
19274 | Sindhupalchok | Irkhu | 4 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 12 | 13 | 2017-01-27 | 2017-03-24 | As per CTEVT/NRA guideline | Chautara Sangachokgadhi | 8
19275 | Sindhupalchok | Irkhu | 5 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 6 | 7 | 2017-01-27 | 2017-03-24 |  | Chautara Sangachokgadhi | 8
19276 | Sindhupalchok | Irkhu | 5 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 72 |  |  |  | Chautara Sangachokgadhi | 8
19277 | Sindhupalchok | Irkhu | 6 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 5 | 6 | 2017-01-27 | 2017-03-24 |  | Chautara Sangachokgadhi | 8
19278 | Sindhupalchok | Irkhu | 7 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 5 | 7 | 2017-01-27 | 2017-03-24 |  | Chautara Sangachokgadhi | 8
19279 | Sindhupalchok | Irkhu | 9 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 6 | 6 | 2017-01-27 | 2017-03-24 |  | Chautara Sangachokgadhi | 8
19280 | Sindhupalchok | Irkhu | 6 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 55 |  |  |  | Chautara Sangachokgadhi | 8
19281 | Sindhupalchok | Irkhu | 9 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 117 |  |  |  | Chautara Sangachokgadhi | 8
19282 | Sindhupalchok | Irkhu | All | UNDP | SUK-N | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support over house completion under direct superivision | # of households | Yes | Ongoing | 200 | 60 | 2016-10-15 |  |  | Chautara Sangachokgadhi | 8
19283 | Sindhupalchok | Irkhu | 5 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-10-17 | 2017-12-20 |  | Chautara Sangachokgadhi | 8
19284 | Sindhupalchok | Irkhu | 6 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-10-17 | 2017-12-20 |  | Chautara Sangachokgadhi | 8
19285 | Sindhupalchok | Irkhu | 7 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-10-26 | 2017-12-20 |  | Chautara Sangachokgadhi | 8
19286 | Sindhupalchok | Irkhu | 8 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-10-06 | 2017-12-20 |  | Chautara Sangachokgadhi | 8
19287 | Sindhupalchok | Irkhu | 9 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-10-25 | 2017-12-20 |  | Chautara Sangachokgadhi | 8
19288 | Sindhupalchok | Irkhu | All | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | OJT during the demo house | # of trainees | Yes | Completed | 30 | 7 | 2017-10-17 | 2017-12-20 |  | Chautara Sangachokgadhi | 8
19289 | Sindhupalchok | Irkhu |  | UNDP | SUK-N | ECHO | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Safer Reconstruction Clinic | # of households supported | Yes | Planned | 100 | 0 | 2017-11-15 |  |  | Chautara Sangachokgadhi | 8
19290 | Sindhupalchok | Irkhu | All | UNDP | UNDP | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Provide materials/tool kits equal to RS. 50 thousands/HH | # of households | Yes | Ongoing | 10 | 10 | 2017-11-01 |  |  | Chautara Sangachokgadhi | 8
19291 | Sindhupalchok | Jalbire |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 43 |  |  |  | Balefi | 2
19292 | Sindhupalchok | Lisankhu |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 36 |  |  |  | Lisangkhu Pakhar | 3
19293 | Sindhupalchok | Listikot |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 25 |  |  |  | Bhotekoshi | 1
19294 | Sindhupalchok | Mahankal | 3 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 66 |  |  |  | Helambu | 5
19295 | Sindhupalchok | Mahankal | 9 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 43 |  |  |  | Helambu | 4
19296 | Sindhupalchok | Maneswor |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 40 |  |  |  | Barhabise | 8
19297 | Sindhupalchok | Maneswor |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 85 |  |  |  | Barhabise | 8
19298 | Sindhupalchok | Mankha |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 38 |  |  |  | Balefi | 7
19299 | Sindhupalchok | Mankha |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 87 |  |  |  | Balefi | 7
19300 | Sindhupalchok | Marming |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 58 |  |  |  | Bhotekoshi | 5
19301 | Sindhupalchok | Melamchi N.P. | 1 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 35 |  |  |  | Melamchi | 6
19302 | Sindhupalchok | Melamchi N.P. | 1 | UNDP | CTEVT | GOJ | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 7 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch | Melamchi | 6
19303 | Sindhupalchok | Melamchi N.P. | 2 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 75 |  | 2016-12-22 |  | Melamchi | 6
19304 | Sindhupalchok | Melamchi N.P. | 2 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 75 |  | 2016-12-22 |  | Melamchi | 6
19305 | Sindhupalchok | Melamchi N.P. | 2 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 93 |  |  |  | Melamchi | 6
19306 | Sindhupalchok | Melamchi N.P. | 2 | UNDP | CTEVT | GOJ | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 14 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch | Melamchi | 6
19307 | Sindhupalchok | Melamchi N.P. | 3 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 29 |  | 2016-12-11 |  | Melamchi | 5
19308 | Sindhupalchok | Melamchi N.P. | 3 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 29 |  | 2016-12-11 |  | Melamchi | 5
19309 | Sindhupalchok | Melamchi N.P. | 3 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 28 |  |  |  | Melamchi | 5
19310 | Sindhupalchok | Melamchi N.P. | 3 | UNDP | CTEVT | GOJ | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 2 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch | Melamchi | 5
19311 | Sindhupalchok | Melamchi N.P. | 4 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 105 |  | 2016-09-11 |  | Melamchi | 5
19312 | Sindhupalchok | Melamchi N.P. | 4 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 105 |  | 2016-09-11 |  | Melamchi | 5
19313 | Sindhupalchok | Melamchi N.P. | 4 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 36 |  |  |  | Melamchi | 5
19314 | Sindhupalchok | Melamchi N.P. | 4 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 34 |  |  |  | Melamchi | 5
19315 | Sindhupalchok | Melamchi N.P. | 4 | UNDP | CTEVT | GOJ | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 10 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch | Melamchi | 5
19316 | Sindhupalchok | Melamchi N.P. | 5 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 44 |  |  |  | Melamchi | 11
19317 | Sindhupalchok | Melamchi N.P. | 5 | UNDP | CTEVT | GOJ | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 3 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch | Melamchi | 11
19318 | Sindhupalchok | Melamchi N.P. | 6 | UNDP | CTEVT | GOJ | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 18 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch | Melamchi | 11
19319 | Sindhupalchok | Melamchi N.P. | 7 | UNDP | CTEVT | KOICA | Technical Assistance | Demonstration Construction | House | Brick masonry with cement mortar technology house with 1 room | # of constructions | Yes | Completed | 1 | 1 | 2016-11-20 | 2016-12-31 |  | Melamchi | 11
19320 | Sindhupalchok | Melamchi N.P. | 7 | UNDP | CTEVT | GOJ | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 6 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch | Melamchi | 11
19321 | Sindhupalchok | Melamchi N.P. | 8 | UNDP | CTEVT | GOJ | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 1 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch | Melamchi | 12
19322 | Sindhupalchok | Melamchi N.P. | 9 | UNDP | CTEVT | GOJ | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 1 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch | Melamchi | 12
19323 | Sindhupalchok | Melamchi N.P. | 12 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 154 |  | 2016-12-08 |  | Melamchi | 10
19324 | Sindhupalchok | Melamchi N.P. | 12 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 154 |  | 2016-12-08 |  | Melamchi | 10
19325 | Sindhupalchok | Melamchi N.P. | 12 | UNDP | CTEVT | KOICA | Technical Assistance | Demonstration Construction | House | GI wire containment technology house with 1 room | # of constructions | Yes | Completed | 1 | 1 | 2016-11-20 | 2017-01-31 |  | Melamchi | 10
19326 | Sindhupalchok | Melamchi N.P. | 12 | UNDP | CTEVT | GOJ | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 22 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch | Melamchi | 10
19327 | Sindhupalchok | Melamchi N.P. | 13 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 100 |  | 2016-12-12 |  | Melamchi | 10
19328 | Sindhupalchok | Melamchi N.P. | 13 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 100 |  | 2016-12-12 |  | Melamchi | 10
19329 | Sindhupalchok | Melamchi N.P. | 13 | UNDP | CTEVT | GOJ | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 6 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch | Melamchi | 10
19330 | Sindhupalchok | Melamchi N.P. | 15 | UNDP | UNDP | GOJ | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 88 |  | 2016-12-14 |  | Melamchi | 9
19331 | Sindhupalchok | Melamchi N.P. | 15 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Community orientation at ward level on National Building code and safer building construction(3 - 4 hours) | # of participants | Yes | Completed | 50 | 88 |  | 2016-12-14 |  | Melamchi | 9
19332 | Sindhupalchok | Melamchi N.P. | 15 | UNDP | CTEVT | GOJ | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 Days training,CTEVT | # of trainees | Yes | Completed | 6 | 1 | 2016-09-21 | 2016-11-25 | 5 days training for 3 batch | Melamchi | 9
19333 | Sindhupalchok | Melamchi N.P. |  | UNDP | UNDP | UNDP | Others | Others | (Please specify in Activity Detail) | Support to develop housing models/ settlement plans for Economically Weaker Sections through Design Contest | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Melamchi | 13
19334 | Sindhupalchok | Pangtang |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 56 |  |  |  | Jugal | 4
19335 | Sindhupalchok | Pangtang |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 34 |  |  |  | Jugal | 4
19336 | Sindhupalchok | Piskar | 6 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 132 |  |  |  | Tripura Sundari | 4
19337 | Sindhupalchok | Ramche |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 90 |  |  |  | Barhabise | 9
19338 | Sindhupalchok | Sangachok | 4 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 34 |  |  |  | Chautara Sangachokgadhi | 12
19339 | Sindhupalchok | SipaPokhare | 1 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Planned | 1 | 0 |  |  |  | Indrawati | 7
19340 | Sindhupalchok | SipaPokhare | 1 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 49 |  |  |  | Indrawati | 7
19341 | Sindhupalchok | SipaPokhare | 2 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-05-20 | 2017-06-26 | As per CTEVT/NRA guideline | Indrawati | 8
19342 | Sindhupalchok | SipaPokhare | 2 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 18 |  |  |  | Indrawati | 8
19343 | Sindhupalchok | SipaPokhare | 2 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 11 | 8 | 2017-05-07 | 2017-07-09 | As per CTEVT/NRA guideline | Indrawati | 8
19344 | Sindhupalchok | SipaPokhare | 6 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Planned | 1 | 0 |  |  |  | Indrawati | 7
19345 | Sindhupalchok | SipaPokhare | 6 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-08 | 2017-06-27 | As per CTEVT/NRA guideline | Indrawati | 7
19346 | Sindhupalchok | SipaPokhare | 6 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 11 | 10 | 2017-05-31 | 2017-07-09 | As per CTEVT/NRA guideline | Indrawati | 7
19347 | Sindhupalchok | SipaPokhare | 8 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Planned | 1 | 0 |  |  |  | Indrawati | 7
19348 | Sindhupalchok | SipaPokhare | 8 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-09 | 2017-07-05 | As per CTEVT/NRA guideline | Indrawati | 7
19349 | Sindhupalchok | SipaPokhare | 8 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 64 |  |  |  | Indrawati | 7
19350 | Sindhupalchok | SipaPokhare | 8 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 7 | 11 | 2017-04-19 | 2017-07-09 | As per CTEVT/NRA guideline | Indrawati | 7
19351 | Sindhupalchok | SipaPokhare | 9 | UNDP | UNDP | UNDP | Technical Assistance | Community reconstruction orientation | 1 session | Key Stages orientation to community people during Demonstartion houses construction | # of participants | Yes | Ongoing | 1 | 1 |  |  |  | Indrawati | 8
19352 | Sindhupalchok | SipaPokhare | 9 | UNDP | SUK-N | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-21 | 2017-07-05 | As per CTEVT/NRA guideline | Indrawati | 8
19353 | Sindhupalchok | SipaPokhare | 9 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 57 |  |  |  | Indrawati | 8
19354 | Sindhupalchok | SipaPokhare | 9 | UNDP | SUK-N | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | On the job training to local artisan (both new and old) | # of trainees | Yes | Completed | 8 | 11 | 2017-03-21 | 2017-04-15 | As per CTEVT/NRA guideline | Indrawati | 8
19355 | Sindhupalchok | SipaPokhare | All | UNDP | SUK-N | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support over house completion under direct superivision | # of households | Yes | Ongoing | 100 | 83 | 2016-10-15 |  |  | Indrawati | 8
19356 | Sindhupalchok | SipaPokhare |  | UNDP | SUK-N | ECHO | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Safer Reconstruction Clinic | # of households supported | Yes | Planned | 100 | 0 | 2017-11-15 |  |  | Indrawati | 8
19357 | Sindhupalchok | SipaPokhare | All | UNDP | UNDP | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Provide materials/tool kits equal to RS. 50 thousands/HH | # of households | Yes | Ongoing | 10 | 10 | 2017-11-01 |  |  | Indrawati | 8
19358 | Sindhupalchok | Tatopani | 7 | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 65 |  |  |  | Bhotekoshi | 3
19359 | Sindhupalchok | Thakani |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 57 |  |  |  | Melamchi | 4
19360 | Sindhupalchok | Thulosirubari |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 53 |  |  |  | Chautara Sangachokgadhi | 13
19361 | Sindhupalchok | Chautara N.P. |  | UNWOMEN | Sathi | UNWOMEN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 27 | 27 | 2017-05-15 | 2017-06-26 |  | Chautara Sangachokgadhi | 7
19362 | Sindhupalchok | Irkhu |  | UNWOMEN | Sathi | UNWOMEN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-05-15 | 2017-06-26 |  | Chautara Sangachokgadhi | 8
19363 | Sindhupalchok | Sangachok |  | UNWOMEN | Sathi | UNWOMEN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-05-15 | 2017-06-26 |  | Chautara Sangachokgadhi | 12
19364 | Sindhupalchok | Thulosirubari |  | UNWOMEN | Sathi | UNWOMEN | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 12 | 12 | 2017-05-15 | 2017-06-26 |  | Chautara Sangachokgadhi | 13
19365 | Sindhupalchok | Bhimtar | 9 | WOREC-N | WOREC-N | AEIN | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Support - GoN reconstruction grant (Tranche I) | # of households | Yes | Completed | 54 | 46 |  |  |  | Indrawati | 11
19366 | Sindhupalchok | Bhimtar | 9 | WOREC-N | WOREC-N | AEIN | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Planned | 54 | 0 | 2016-08-04 | 2018-12-31 |  | Indrawati | 11
19367 | Sindhupalchok | Bhimtar | 9 | WOREC-N | WOREC-N | AEIN | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 61 | 46 | 2016-01-02 | 2017-12-31 |  | Indrawati | 11
19368 | Sindhupalchok | Bhimtar | 9 | WOREC-N | WOREC-N | AEIN | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 51 | 51 | 2016-11-01 | 2016-12-30 |  | Indrawati | 11
19369 | Sindhupalchok | Bhimtar |  | WOREC-N | WOREC-N | AEIN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 31 | 31 | 2016-12-15 | 2016-12-22 |  | Indrawati | 12
19370 | Sindhupalchok | Bhotechaur | 1 | WVIN |  | ADH | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Completed | 252 | 252 | 2016-01-07 | 2016-01-07 |  | Melamchi | 1
19371 | Sindhupalchok | Haibung | 9 | WVIN |  | ADH | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 594 | 594 | 2016-01-07 | 2016-01-08 |  | Melamchi | 3
19372 | Sindhupalchok | Sangachok | 5 | WVIN | DEPROSC | WVIN | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 136 | 136 | 2016-10-25 |  |  | Chautara Sangachokgadhi | 11
19373 | Sindhupalchok | Sangachok | 8 | WVIN | DEPROSC | WVIN | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 40 | 39 | 2016-10-25 |  |  | Chautara Sangachokgadhi | 11
19374 | Sindhupalchok | Sangachok | 5,8,9 | WVIN | ARSOW-N | WVIN | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Assisted for drawing approval and Technical assistance | # of households | Yes | Ongoing | 274 | 220 | 2017-04-04 |  |  | Chautara Sangachokgadhi | 12
19375 | Sindhupalchok | Sangachok | 9 | WVIN | DEPROSC | WVIN | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 131 | 131 | 2016-10-25 |  |  | Chautara Sangachokgadhi | 11
19376 | Sindhupalchok | Sangachok | 5,8,9 | WVIN | ARSOW-N | WVIN | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 274 | 118 | 2017-08-23 |  |  | Chautara Sangachokgadhi | 12
19377 | Sindhupalchok | Sangachok | 5,8,9 | WVIN | ARSOW-N | WVIN | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 307 | 307 | 2017-01-01 |  |  | Chautara Sangachokgadhi | 12
19378 | Sindhupalchok | Tekanpur | All | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-12-14 | 2017-12-20 |  | Tripura Sundari | 6
19379 | Sindhupalchok | Lisankhu | All | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-12-19 | 2017-12-25 |  | Lisangkhu Pakhar | 3
19380 | Sindhupalchok | Listikot | All | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-12-15 | 2017-12-21 |  | Bhotekoshi | 1
19381 | Sindhupalchok | Fulpingkatti | All | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 25 | 25 | 2018-01-05 |  |  | #N/A | #N/A
19382 | Sindhupalchok | Kiwool | All | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 25 | 25 | 2018-01-07 |  |  | Helambu | 2
19383 | Sindhupalchok | ThampalChhap | 4 | NRCS | NRCS | JRCS | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Planned | 20 | 0 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19384 | Sindhupalchok | Thanpalkot | 3 | NRCS | NRCS | JRCS | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Planned | 20 | 0 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19385 | Sindhupalchok | Thanpalkot | 5 | NRCS | NRCS | JRCS | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Planned | 20 | 0 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19386 | Sindhupalchok | Badegau | 1 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 50 | 61 | 2016-01-01 | 2018-12-31 |  | Indrawati | 6
19387 | Sindhupalchok | Badegau | 2 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 22 | 23 | 2016-01-01 | 2018-12-31 |  | Indrawati | 6
19388 | Sindhupalchok | Badegau | 3 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 22 | 26 | 2016-01-01 | 2018-12-31 |  | Indrawati | 6
19389 | Sindhupalchok | Badegau | 4 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 34 | 34 | 2016-01-01 | 2018-12-31 |  | Indrawati | 5
19390 | Sindhupalchok | Badegau | 5 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 21 | 21 | 2016-01-01 | 2018-12-31 |  | Indrawati | 6
19391 | Sindhupalchok | Badegau | 6 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 47 | 50 | 2016-01-01 | 2018-12-31 |  | Indrawati | 5
19392 | Sindhupalchok | Badegau | 7 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 18 | 19 | 2016-01-01 | 2018-12-31 |  | Indrawati | 6
19393 | Sindhupalchok | Badegau | 8 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 40 | 42 | 2016-01-01 | 2018-12-31 |  | Indrawati | 6
19394 | Sindhupalchok | Badegau | 9 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 20 | 27 | 2016-01-01 | 2018-12-31 |  | Indrawati | 5
19395 | Sindhupalchok | Kunchok | 1 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 45 | 45 | 2016-01-01 | 2018-12-31 |  | Indrawati | 2
19396 | Sindhupalchok | Kunchok | 2 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 73 | 73 | 2016-01-01 | 2018-12-31 |  | Indrawati | 2
19397 | Sindhupalchok | Kunchok | 3 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 36 | 36 | 2016-01-01 | 2018-12-31 |  | Indrawati | 2
19398 | Sindhupalchok | Kunchok | 4 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 57 | 57 | 2016-01-01 | 2018-12-31 |  | Indrawati | 2
19399 | Sindhupalchok | Kunchok | 5 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 12 | 12 | 2016-01-01 | 2018-12-31 |  | Indrawati | 3
19400 | Sindhupalchok | Kunchok | 6 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 21 | 21 | 2016-01-01 | 2018-12-31 |  | Indrawati | 3
19401 | Sindhupalchok | Kunchok | 7 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 22 | 22 | 2016-01-01 | 2018-12-31 |  | Indrawati | 3
19402 | Sindhupalchok | Kunchok | 8 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 21 | 21 | 2016-01-01 | 2018-12-31 |  | Indrawati | 3
19403 | Sindhupalchok | Kunchok | 9 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 14 | 14 | 2016-01-01 | 2018-12-31 |  | Indrawati | 3
19404 | Sindhupalchok | Melamchi N.P. | 12 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 65 | 95 | 2016-01-01 | 2018-12-31 |  | Melamchi | 10
19405 | Sindhupalchok | Melamchi N.P. | 13 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 25 | 55 | 2016-01-01 | 2018-12-31 |  | Melamchi | 10
19406 | Sindhupalchok | Nawalpur | 1 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 17 | 21 | 2016-01-01 | 2018-12-31 |  | Indrawati | 4
19407 | Sindhupalchok | Nawalpur | 2 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 15 | 22 | 2016-01-01 | 2018-12-31 |  | Indrawati | 4
19408 | Sindhupalchok | Nawalpur | 3 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 15 | 22 | 2016-01-01 | 2018-12-31 |  | Indrawati | 4
19409 | Sindhupalchok | Nawalpur | 4 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 23 | 26 | 2016-01-01 | 2018-12-31 |  | Indrawati | 4
19410 | Sindhupalchok | Nawalpur | 5 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 15 | 2016-01-01 | 2018-12-31 |  | Indrawati | 4
19411 | Sindhupalchok | Nawalpur | 6 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 22 | 22 | 2016-01-01 | 2018-12-31 |  | Indrawati | 4
19412 | Sindhupalchok | Nawalpur | 7 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 18 | 18 | 2016-01-01 | 2018-12-31 |  | Indrawati | 4
19413 | Sindhupalchok | Nawalpur | 8 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 8 | 9 | 2016-01-01 | 2018-12-31 |  | Indrawati | 4
19414 | Sindhupalchok | Nawalpur | 9 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 52 | 52 | 2016-01-01 | 2018-12-31 |  | Indrawati | 4
19415 | Sindhupalchok | ThampalChhap | 1 | NRCS | NRCS | JRCS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 13 | 3 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19416 | Sindhupalchok | ThampalChhap | 2 | NRCS | NRCS | JRCS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 13 | 5 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19417 | Sindhupalchok | ThampalChhap | 3 | NRCS | NRCS | JRCS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 13 | 6 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19418 | Sindhupalchok | ThampalChhap | 4 | NRCS | NRCS | JRCS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 13 | 1 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19419 | Sindhupalchok | ThampalChhap | 5 | NRCS | NRCS | JRCS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 13 | 7 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19420 | Sindhupalchok | ThampalChhap | 6 | NRCS | NRCS | JRCS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 13 | 0 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19421 | Sindhupalchok | ThampalChhap | 7 | NRCS | NRCS | JRCS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 13 | 1 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19422 | Sindhupalchok | ThampalChhap | 8 | NRCS | NRCS | JRCS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 14 | 4 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19423 | Sindhupalchok | ThampalChhap | 9 | NRCS | NRCS | JRCS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 15 | 3 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19424 | Sindhupalchok | Thanpalkot | 1 | NRCS | NRCS | JRCS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 10 | 3 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19425 | Sindhupalchok | Thanpalkot | 2 | NRCS | NRCS | JRCS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 10 | 5 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19426 | Sindhupalchok | Thanpalkot | 3 | NRCS | NRCS | JRCS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 10 | 2 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19427 | Sindhupalchok | Thanpalkot | 4 | NRCS | NRCS | JRCS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19428 | Sindhupalchok | Thanpalkot | 5 | NRCS | NRCS | JRCS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 10 | 1 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19429 | Sindhupalchok | Thanpalkot | 6 | NRCS | NRCS | JRCS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 10 | 0 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19430 | Sindhupalchok | Thanpalkot | 7 | NRCS | NRCS | JRCS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 10 | 1 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19431 | Sindhupalchok | Thanpalkot | 8 | NRCS | NRCS | JRCS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 10 | 4 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19432 | Sindhupalchok | Thanpalkot | 9 | NRCS | NRCS | JRCS | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 10 | 1 | 2016-01-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19433 | Sindhupalchok | Nawalpur | 5 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 12 | 12 | 2016-01-01 | 2018-12-31 |  | Indrawati | 4
19434 | Sindhupalchok | Melamchi N.P. | 12 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Ongoing | 41 | 41 | 2016-01-01 | 2018-12-31 |  | Melamchi | 10
19435 | Sindhupalchok | Melamchi N.P. | 13 | NRCS | NRCS | NRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Ongoing | 23 | 23 | 2016-01-01 | 2018-12-31 |  | Melamchi | 10
19436 | Sindhupalchok | ThampalChhap | 1 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 80 | 74 | 2017-06-09 | 2018-01-08 |  | Panchpokhari Thangpal | 6
19437 | Sindhupalchok | ThampalChhap | 2 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 53 | 53 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19438 | Sindhupalchok | ThampalChhap | 3 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 58 | 52 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19439 | Sindhupalchok | ThampalChhap | 4 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 34 | 58 | 2017-06-11 | 2018-01-10 |  | Panchpokhari Thangpal | 6
19440 | Sindhupalchok | ThampalChhap | 5 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 145 | 110 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19441 | Sindhupalchok | ThampalChhap | 6 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 67 | 65 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19442 | Sindhupalchok | ThampalChhap | 7 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 137 | 132 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19443 | Sindhupalchok | ThampalChhap | 8 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 115 | 107 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19444 | Sindhupalchok | ThampalChhap | 9 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 121 | 114 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19445 | Sindhupalchok | Thanpalkot | 1 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 66 | 54 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19446 | Sindhupalchok | Thanpalkot | 2 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 126 | 114 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19447 | Sindhupalchok | Thanpalkot | 3 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 111 | 100 | 2017-06-10 | 2018-01-09 |  | Panchpokhari Thangpal | 4
19448 | Sindhupalchok | Thanpalkot | 4 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 93 | 87 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19449 | Sindhupalchok | Thanpalkot | 5 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 44 | 42 | 2017-06-12 | 2018-01-11 |  | Panchpokhari Thangpal | 4
19450 | Sindhupalchok | Thanpalkot | 6 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 109 | 97 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19451 | Sindhupalchok | Thanpalkot | 7 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 46 | 41 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19452 | Sindhupalchok | Thanpalkot | 8 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 77 | 71 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19453 | Sindhupalchok | Thanpalkot | 9 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 11 | 11 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19454 | Sindhupalchok | ThampalChhap | 1 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 80 | 4 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19455 | Sindhupalchok | ThampalChhap | 2 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 53 | 1 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19456 | Sindhupalchok | ThampalChhap | 3 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 58 | 4 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19457 | Sindhupalchok | ThampalChhap | 4 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Planned | 34 | 0 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19458 | Sindhupalchok | ThampalChhap | 5 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 145 | 11 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19459 | Sindhupalchok | ThampalChhap | 6 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 67 | 11 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19460 | Sindhupalchok | ThampalChhap | 7 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 137 | 9 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19461 | Sindhupalchok | ThampalChhap | 8 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 115 | 5 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19462 | Sindhupalchok | ThampalChhap | 9 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 121 | 8 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19463 | Sindhupalchok | Thanpalkot | 1 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 66 | 16 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19464 | Sindhupalchok | Thanpalkot | 2 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 126 | 29 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19465 | Sindhupalchok | Thanpalkot | 3 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 111 | 23 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19466 | Sindhupalchok | Thanpalkot | 4 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 93 | 9 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19467 | Sindhupalchok | Thanpalkot | 5 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 44 | 17 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19468 | Sindhupalchok | Thanpalkot | 6 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 109 | 7 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19469 | Sindhupalchok | Thanpalkot | 7 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 46 | 10 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19470 | Sindhupalchok | Thanpalkot | 8 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 77 | 2 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19471 | Sindhupalchok | Thanpalkot | 9 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 11 | 1 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19472 | Sindhupalchok | ThampalChhap | 1 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 80 | 0 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19473 | Sindhupalchok | ThampalChhap | 2 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 53 | 0 | 2017-01-15 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19474 | Sindhupalchok | ThampalChhap | 3 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 58 | 3 | 2017-01-15 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19475 | Sindhupalchok | ThampalChhap | 4 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 34 | 0 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19476 | Sindhupalchok | ThampalChhap | 5 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 145 | 5 | 2017-01-15 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19477 | Sindhupalchok | ThampalChhap | 6 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 67 | 6 | 2017-01-15 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19478 | Sindhupalchok | ThampalChhap | 7 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 137 | 6 | 2017-01-15 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19479 | Sindhupalchok | ThampalChhap | 8 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 115 | 1 | 2017-01-15 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19480 | Sindhupalchok | ThampalChhap | 9 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 121 | 2 | 2017-01-15 | 2018-12-31 |  | Panchpokhari Thangpal | 6
19481 | Sindhupalchok | Thanpalkot | 1 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 66 | 15 | 2017-01-15 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19482 | Sindhupalchok | Thanpalkot | 2 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 126 | 21 | 2017-01-15 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19483 | Sindhupalchok | Thanpalkot | 3 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 111 | 16 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19484 | Sindhupalchok | Thanpalkot | 4 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 93 | 5 | 2017-01-15 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19485 | Sindhupalchok | Thanpalkot | 5 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 44 | 11 | 2016-09-01 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19486 | Sindhupalchok | Thanpalkot | 6 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 109 | 4 | 2017-01-15 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19487 | Sindhupalchok | Thanpalkot | 7 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 46 | 6 | 2017-01-15 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19488 | Sindhupalchok | Thanpalkot | 8 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 77 | 2 | 2017-01-15 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19489 | Sindhupalchok | Thanpalkot | 9 | NRCS | NRCS | JRCS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 11 | 1 | 2017-01-15 | 2018-12-31 |  | Panchpokhari Thangpal | 4
19490 | Sindhupalchok | Nawalpur | 1 | NRCS | NRCS | NRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 | 2017-01-01 | 2018-12-31 |  | Indrawati | 4
19491 | Sindhupalchok | Badegau | 1 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 131 | 131 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 6
19492 | Sindhupalchok | Badegau | 2 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 116 | 116 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 6
19493 | Sindhupalchok | Badegau | 3 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 116 | 116 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 6
19494 | Sindhupalchok | Badegau | 4 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 241 | 241 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 5
19495 | Sindhupalchok | Badegau | 5 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 86 | 86 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 6
19496 | Sindhupalchok | Badegau | 6 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 221 | 221 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 5
19497 | Sindhupalchok | Badegau | 7 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 64 | 64 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 6
19498 | Sindhupalchok | Badegau | 8 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 185 | 185 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 6
19499 | Sindhupalchok | Badegau | 9 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 124 | 124 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 5
19500 | Sindhupalchok | Kunchok | 1 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 145 | 145 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 2
19501 | Sindhupalchok | Kunchok | 2 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 209 | 209 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 2
19502 | Sindhupalchok | Kunchok | 3 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 170 | 170 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 2
19503 | Sindhupalchok | Kunchok | 4 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 209 | 209 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 2
19504 | Sindhupalchok | Kunchok | 5 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 112 | 112 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 3
19505 | Sindhupalchok | Kunchok | 6 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 108 | 108 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 3
19506 | Sindhupalchok | Kunchok | 7 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 125 | 125 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 3
19507 | Sindhupalchok | Kunchok | 8 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 85 | 85 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 3
19508 | Sindhupalchok | Kunchok | 9 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 134 | 134 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 3
19509 | Sindhupalchok | Melamchi N.P. | 12 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 102 | 102 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Melamchi | 10
19510 | Sindhupalchok | Melamchi N.P. | 13 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 47 | 47 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Melamchi | 10
19511 | Sindhupalchok | Nawalpur | 1 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 62 | 62 | 2016-06-17 | 2016-08-28 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 4
19512 | Sindhupalchok | Nawalpur | 2 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 63 | 63 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 4
19513 | Sindhupalchok | Nawalpur | 3 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 62 | 62 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 4
19514 | Sindhupalchok | Nawalpur | 4 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 11 | 11 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 4
19515 | Sindhupalchok | Nawalpur | 5 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 63 | 63 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 4
19516 | Sindhupalchok | Nawalpur | 6 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 104 | 104 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 4
19517 | Sindhupalchok | Nawalpur | 7 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 53 | 53 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 4
19518 | Sindhupalchok | Nawalpur | 8 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 90 | 90 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 4
19519 | Sindhupalchok | Nawalpur | 9 | NRCS | NRCS | NRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 137 | 137 | 2017-01-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Indrawati | 4
19520 | Sindhupalchok | ThampalChhap | 1 | NRCS | NRCS | JRCS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 80 | 80 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Panchpokhari Thangpal | 6
19521 | Sindhupalchok | ThampalChhap | 2 | NRCS | NRCS | JRCS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 53 | 53 | 2017-03-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Panchpokhari Thangpal | 6
19522 | Sindhupalchok | ThampalChhap | 3 | NRCS | NRCS | JRCS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 58 | 58 | 2017-03-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Panchpokhari Thangpal | 6
19523 | Sindhupalchok | ThampalChhap | 4 | NRCS | NRCS | JRCS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 34 | 34 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Panchpokhari Thangpal | 6
19524 | Sindhupalchok | ThampalChhap | 5 | NRCS | NRCS | JRCS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 145 | 145 | 2017-03-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Panchpokhari Thangpal | 6
19525 | Sindhupalchok | ThampalChhap | 6 | NRCS | NRCS | JRCS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 67 | 67 | 2017-03-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Panchpokhari Thangpal | 6
19526 | Sindhupalchok | ThampalChhap | 7 | NRCS | NRCS | JRCS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 137 | 137 | 2017-03-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Panchpokhari Thangpal | 6
19527 | Sindhupalchok | ThampalChhap | 8 | NRCS | NRCS | JRCS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 115 | 115 | 2017-03-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Panchpokhari Thangpal | 6
19528 | Sindhupalchok | ThampalChhap | 9 | NRCS | NRCS | JRCS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 121 | 121 | 2017-03-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Panchpokhari Thangpal | 6
19529 | Sindhupalchok | Thanpalkot | 1 | NRCS | NRCS | JRCS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 66 | 66 | 2017-03-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Panchpokhari Thangpal | 4
19530 | Sindhupalchok | Thanpalkot | 2 | NRCS | NRCS | JRCS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 126 | 126 | 2017-03-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Panchpokhari Thangpal | 4
19531 | Sindhupalchok | Thanpalkot | 3 | NRCS | NRCS | JRCS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 111 | 111 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Panchpokhari Thangpal | 4
19532 | Sindhupalchok | Thanpalkot | 4 | NRCS | NRCS | JRCS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 93 | 93 | 2017-03-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Panchpokhari Thangpal | 4
19533 | Sindhupalchok | Thanpalkot | 5 | NRCS | NRCS | JRCS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 44 | 44 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Panchpokhari Thangpal | 4
19534 | Sindhupalchok | Thanpalkot | 6 | NRCS | NRCS | JRCS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 109 | 109 | 2017-03-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Panchpokhari Thangpal | 4
19535 | Sindhupalchok | Thanpalkot | 7 | NRCS | NRCS | JRCS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 46 | 46 | 2017-03-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Panchpokhari Thangpal | 4
19536 | Sindhupalchok | Thanpalkot | 8 | NRCS | NRCS | JRCS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 77 | 77 | 2017-03-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Panchpokhari Thangpal | 4
19537 | Sindhupalchok | Thanpalkot | 9 | NRCS | NRCS | JRCS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 11 | 11 | 2017-03-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Panchpokhari Thangpal | 4
19538 | Sindhupalchok | Irkhu | 1 | JICA | JICA | JICA | Training | ToT | Engineers, sub engineers (7 days DUDBC) | Training for DLPIU technical professionals on earthquake resilient building construction | # of trainees | Yes | Ongoing | 91 | 39 | 2018-05-06 | 2018-05-26 |  | Chautara Sangachokgadhi | 8

## Activity_Index
Type | Sub_Type | Activity_Name | Activity_Detail | Unit | Description | Guidance for District Team
Technical Assistance | Demonstration Construction | House | No. of rooms, materials used, communications activities carried out | # of constructions | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | No. of constructions, details of demonstration houses (no. of rooms, communication activities and material used) captured
|  | Toilet | type of toilet, communications activities carried out | # of constructions | Demonstration construction toilets provide a practical demonstration of various sanitation options and earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | No. of constructions, details of demonstration houses (no. of rooms, communication activities and material used) captured
|  | House & Toilet | No. of rooms, materials used, type of toilet, communications activities carried out | # of constructions | Demonstration construction houses and toilets provide a practical demonstration of earthquake resilient construction elements and various sanitation options. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | No. of constructions, details of demonstration houses (no. of rooms, communication activities and material used) captured
| Community reconstruction orientation | 1 session | hours per session | # of participants | Community reconstruction orientation should as a minimum cover the inspection SOP and associated compliance criteria, the process for the disbursement of the housing grant, grievance redressal mechanism, seismic construction elements, earthquake preparedness (go bags, ‘drop, cover, hold’, etc.), household WASH, and relevant contact people (GoN and POs). Content should be updated regularly to reflect changes to policy / procedures, as well as the progress through the reconstruction process. Materials such as posters, leaflets, and booklets which can be taken away after the orientation sessions should be available to households. Participatory Approach for Safe Shelter Awareness (PASSA) is one form of this. Conducted as one-off session | Frequency of the orientation (1 session, 2-3 sessions and 4-5 sessions), duration (hours) per session and no. of participants are captured.
|  | 2-3 sessions | hours per session | # of participants | Community reconstruction orientation should as a minimum cover the inspection SOP and associated compliance criteria, the process for the disbursement of the housing grant, grievance redressal mechanism, seismic construction elements, earthquake preparedness (go bags, ‘drop, cover, hold’, etc.), household WASH, and relevant contact people (GoN and POs). Content should be updated regularly to reflect changes to policy / procedures, as well as the progress through the reconstruction process. Materials such as posters, leaflets, and booklets which can be taken away after the orientation sessions should be available to households.. Participatory Approach for Safe Shelter Awareness (PASSA) is one form of this. Two to three sessions are conducted with the same community | Frequency of the orientation (1 session, 2-3 sessions and 4-5 sessions), duration (hours) per session and no. of participants are captured.
|  | 4-5 sessions | hours per session | # of participants | Community reconstruction orientation should as a minimum cover the inspection SOP and associated compliance criteria, the process for the disbursement of the housing grant, grievance redressal mechanism, seismic construction elements, earthquake preparedness (go bags, ‘drop, cover, hold’, etc.), household WASH, and relevant contact people (GoN and POs). Content should be updated regularly to reflect changes to policy / procedures, as well as the progress through the reconstruction process. Materials such as posters, leaflets, and booklets which can be taken away after the orientation sessions should be available to households.. Participatory Approach for Safe Shelter Awareness (PASSA) is one form of this. Four to five sessions are conducted with the same community | Frequency of the orientation (1 session, 2-3 sessions and 4-5 sessions), duration (hours) per session and no. of participants are captured.
| Household reconstruction orientation | 1 session | hours per session | # of households | Household reconstruction orientation should as a minimum cover the inspection SOP and associated compliance criteria, the process for the disbursement of the housing grant, grievance redressal mechanism, seismic construction elements, earthquake preparedness (go bags, ‘drop, cover, hold’, etc.), household WASH, and relevant contact people (GoN and POs). Content should be updated regularly to reflect changes to policy / procedures, as well as the progress through the reconstruction process. Materials such as posters, leaflets, and booklets which can be taken away after the orientation sessions should be available to households. The mobile technical assistance teams or other technical resource person(s) are normally responsible for delivering the sessions by moving through each households of each ward on a repeat cycle. | Frequency of the orientation (1 session, 2-3 sessions and 4-5 sessions), duration (hours) per session and no. of households are captured.
|  | 2-3 sessions | hours per session | # of households | Household reconstruction orientation should as a minimum cover the inspection SOP and associated compliance criteria, the process for the disbursement of the housing grant, grievance redressal mechanism, seismic construction elements, earthquake preparedness (go bags, ‘drop, cover, hold’, etc.), household WASH, and relevant contact people (GoN and POs). Content should be updated regularly to reflect changes to policy / procedures, as well as the progress through the reconstruction process. Materials such as posters, leaflets, and booklets which can be taken away after the orientation sessions should be available to households. The mobile technical assistance teams or other technical resource person(s) are normally responsible for delivering the sessions by moving through each households of each ward on a repeat cycle. | Frequency of the orientation (1 session, 2-3 sessions and 4-5 sessions), duration (hours) per session and no. of households are captured.
|  | 4-5 sessions | hours per session | # of households | Household reconstruction orientation should as a minimum cover the inspection SOP and associated compliance criteria, the process for the disbursement of the housing grant, grievance redressal mechanism, seismic construction elements, earthquake preparedness (go bags, ‘drop, cover, hold’, etc.), household WASH, and relevant contact people (GoN and POs). Content should be updated regularly to reflect changes to policy / procedures, as well as the progress through the reconstruction process. Materials such as posters, leaflets, and booklets which can be taken away after the orientation sessions should be available to households. The mobile technical assistance teams or other technical resource person(s) are normally responsible for delivering the sessions by moving through each households of each ward on a repeat cycle. | Frequency of the orientation (1 session, 2-3 sessions and 4-5 sessions), duration (hours) per session and no. of households are captured.
| Door-to-door technical assistance | One-off | team composition Ex: 1 eng, 1 smb etc. | # of households | Door-to-door technical assistance is a household level supervision/technical support carried out by mobile TA team (including technical resources person(s) and social mobilization resource person(s)). TA teams will be responsible for providing door to door, household level technical support through all stages of construction (site clearing/layout; foundation; wall/bands/columns; windows and door installation; Roofing), and should cover technical, social, financial, and policy / procedure aspects of the reconstruction. In order to ensure compliance, households are also supported with technical advice / solutions such as site selection, drawings, BOQ, material estimate and supervision of house reconstruction. Select if TA teams conducted one-off visits | Frequency of the assistance (one-off or continuous), composition of the team and no. of households are captured.
|  | Continuous | team composition Ex: 1 eng, 1 smb etc. | # of households | Door-to-door technical assistance is a household level supervision/technical support carried out by mobile TA team (including technical resources person(s) and social mobilization resource person(s)). TA teams will be responsible for providing door to door, household level technical support through all stages of construction (site clearing/layout; foundation; wall/bands/columns; windows and door installation; Roofing), and should cover technical, social, financial, and policy / procedure aspects of the reconstruction. In order to ensure compliance, households are also supported with technical advice / solutions such as site selection, drawings, BOQ, material estimate and supervision of house reconstruction. Select if TA teams are continuously present in VDCs and wards | Frequency of the assistance (one-off or continuous), composition of the team and no. of households are captured.
| Helpdesk/technical support center | Helpdesk/technical support center | staffing | # of households supported | Helpdesk/technical support center provides technical assistance, information and consultation on house designs, site surveys cost calculation, orientation on building codes and SOPs, IEC materials. The center is staffed with engineers or other technical resource persons(s) that monitor and support the households in building compliant houses. The centre should also have social mobilisation resource person(s) available to support with social aspects of the reconstruction. | Staffing of the center (Ex: engineers, master masons etc.) and no. of the visits by households are captured.
| Interactive mobile van/theatre | Interactive mobile van/theatre | material used | # of participants | Interactive mobile vans/theatre is an interactive platform that disseminates relevant IEC materials, plays prepared audio visual or dramatic content on safer construction, organizes discussions, disseminates information on building designs, Q&As and additional entertainment and educational content. | No.of participants are captured. Content of the materials used needs to be shared with HRRP.
| Communication and Outreach | Production of IEC materials/manual | material produced | # of copies | Production of IEC materials and other technical manuals to support the reconstruction process. | No. of copies produced is captured. Content of the IEC materials needs to be shared with HRRP.
|  | PSA Radio broadcasting | content of PSA, location of radio stations playing PSAs | # of episodes | Supporting in recording and broadcasting of PSA on safe building techniques and reconstruction messages via local media. | No. of episodes is captured. Content of the PSA needs to be shared with HRRP + location of radio stations playing the PSAs
| Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Formation of Reconstruction Coordination Committees (RCC) in VDC/ward/community/tole level. The RCC is responsible for coordinating and facilitating the reconstruction and rehabilitation of earthquake affected structures. Committee members and housing beneficiaries will be trained on the steps and processes of construction, EQ-resistant techniques etc. The committee overlooks the construction activities under the technical supervision of implementing partners, as well as mobilising households, defusing tension, etc. | No. of committees is captured.
| Community orientation on toilet construction | 1 session | hours per session | # of participants | Community orientation on toilet construction is delivered in communities or groups on safe construction of toilet. Should provide information on multiple options for safe sanitation, including costing information and comparison of the various options | Frequency of the orientation (1 session, 2-3 sessions and 4-5 sessions), duration (hours) per session and no. of participants are captured.
|  | 2-3 sessions | hours per session | # of participants | Community orientation on toilet construction is delivered in communities or groups on safe construction of toilet. Should provide information on multiple options for safe sanitation, including costing information and comparison of the various options | Frequency of the orientation (1 session, 2-3 sessions and 4-5 sessions), duration (hours) per session and no. of participants are captured.
|  | 4-5 sessions | hours per session | # of participants | Community orientation on toilet construction is delivered in communities or groups on safe construction of toilet. Should provide information on multiple options for safe sanitation, including costing information and comparison of the various options | Frequency of the orientation (1 session, 2-3 sessions and 4-5 sessions), duration (hours) per session and no. of participants are captured.
| Household orientation on toilet construction | 1 session | hours per session | # of households | Household orientation on toilet construction is delivered on safe/compliant construction of toilet. Should provide information on multiple options for safe sanitation, including costing information and comparison of the various options | Frequency of the orientation (1 session, 2-3 sessions and 4-5 sessions), duration (hours) per session and no. of households are captured.
|  | 2-3 sessions | hours per session | # of households | Household orientation on toilet construction is delivered on safe/compliant construction of toilet. Should provide information on multiple options for safe sanitation, including costing information and comparison of the various options | Frequency of the orientation (1 session, 2-3 sessions and 4-5 sessions), duration (hours) per session and no. of households are captured.
|  | 4-5 sessions | hours per session | # of households | Household orientation on toilet construction is delivered on safe/compliant construction of toilet. Should provide information on multiple options for safe sanitation, including costing information and comparison of the various options | Frequency of the orientation (1 session, 2-3 sessions and 4-5 sessions), duration (hours) per session and no. of households are captured.
| Household drinking water schemes | Household drinking water schemes |  | # of households | Technical assistance on household drinking water schemes, including planning, costing, and providing technical support for the implementation of the scheme. | No. of households is captured
| Community toilet construction | Community toilet construction |  | # of constructions
| Household toilet construction | Household toilet construction | team composition, material used, type of assistance | # of households | Technical assistance on household toilet construction, providing door-to-door technical assistance regarding safe toilet construction, both in terms of earthquake resistant element and safe sanitation practices. TA should be provided on an on-going basis throughout the construction process. | No. of households is captured. Type of assistance is encouraged to capture. Materials used needs to be shared with HRRP.
| Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | material used | # of households | Hygiene and sanitation promotion for households, including community or household sessions and special events targeting improved sanitation and hygiene practices | No. of households is captured. Content of the promotion is encouraged to capture.
Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | 7 days short training on skilled masons according to DUDBC curriculum | No. of trainees is captured
|  | Masons (other curriculums, specify in Activity Detail) | curriculum | # of trainees
|  | Carpenter | curriculum | # of trainees |  | No. of trainees and curriculum are captured.
|  | Plumber | curriculum | # of trainees |  | No. of trainees and curriculum are captured.
|  | Electrician | curriculum | # of trainees |  | No. of trainees and curriculum are captured.
|  | Bar bender | curriculum | # of trainees |  | No. of trainees and curriculum are captured.
|  | Social mobilizer | curriculum | # of trainees |  | No. of trainees and curriculum are captured.
| Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | No. of trainees is captured
|  | New masons (other curriculum, specify in Activity Detail) | curriculum | # of trainees | Vocational training for new masons according to other curriculums. | No. of trainees is captured
|  | Carpenter (CTEVT) |  | # of trainees | Vocational training for carpenters according to CTEVT curriculum. | No. of trainees is captured
|  | Plumber (CTEVT) |  | # of trainees | Vocational training for plumber according to CTEVT curriculum. | No. of trainees is captured
|  | Electrician (CTEVT) |  | # of trainees | Vocational training for electrician according to CTEVT curriculum. | No. of trainees is captured
|  | Semiskilled construction workers (CTEVT) |  | # of trainees | Vocational training semiskilled construction workers according to CTEVT curriculum. | No. of trainees is captured
| ToT | Skilled masons | curriculum | # of trainees | ToT for skilled masons | No. of trainees is captured
|  | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | 7 days ToT for engineers and sub engineers according to DUDBC curriculum | No. of trainees is captured
|  | Social mobilizer (curriculum, specify in Activity Detail) | curriculum | # of trainees | Training trainers to train social mobilisers | No. of trainees and curriculum are captured.
| Retrofitting training | Engineers, sub-engineers | curriculum | # of trainees |  | No. of trainees and curriculum are captured.
|  | Skilled construction workers | curriculum | # of trainees |  | No. of trainees and curriculum are captured.
| Other trainings | Village maintenance worker | curriculum | # of trainees | Village maintanance workers are trained to take care of the community infrastructure such as community water schemes | No. of trainees and curriculum are captured.
|  | Other trainings | curriculum | # of trainees
Financial/Material/labour Assistance | GoN Housing Grants | Tranche I | financial amount per beneficiary | # of households | Providing Housing grant - Tranche I to eligible households | No. of households and financial amount per beneficiary are captured
|  | Tranche II | financial amount per beneficiary | # of households | Providing Housing grant - Tranche II to eligible households | No. of households and financial amount per beneficiary are captured
|  | Tranche III | financial amount per beneficiary | # of households | Providing Housing grant - Tranche III to eligible households | No. of households and financial amount per beneficiary are captured
|  | Retrofitting | financial amount per beneficiary | # of households | Providing retrofitting grant to eligible households | No. of households and financial amount per beneficiary are captured
| Top Ups | Resettlement/Settlement relocation top-up | financial amount per beneficiary | # of households | Providing relocation top-up to targeted households | No. of households and financial amount per beneficiary are captured
|  | Vulnerable HHs | financial amount per beneficiary | # of households | Providing vulnerable top-up to targeted households | No. of households and financial amount per beneficiary are captured
|  | Transportation for remote areas | financial amount per beneficiary | # of households | Providing transportation top-up for remote areas to targeted households | No. of households and financial amount per beneficiary are captured
| In kind/material support in housing | Repair and retrofit | financial amount per beneficiary | # of households | Providing materials, labour, or transport support for repair / retrofit of houses | No. of households and financial amount per beneficiary are captured
|  | Construction | financial amount per beneficiary | # of households | Providing materials, labour, or transport support for construction of houses | No. of households and financial amount per beneficiary are captured
|  | Labour | financial amount per beneficiary | # of households | Providing labour or covering the costs of labour for construction work | No. of households and financial amount per beneficiary are captured
|  | Household toolkits | financial amount per beneficiary | # of households | Toolkits for households should include as a minimum XX | No. of households and financial amount per beneficiary are captured
|  | Builder toolkits | financial amount per beneficiary | # of kits | Toolkits for builders should include as a minimum XX | No. of toolkits and financial amount per kit are captured
| Financial support on household WASH | HH water supply new | financial amount per beneficiary | # of households |  | No. of households and financial amount per beneficiary are captured
|  | HH water supply repair/rehabilitation | financial amount per beneficiary | # of households |  | No. of households and financial amount per beneficiary are captured
|  | HH toilet construction | financial amount per beneficiary | # of households |  | No. of households and financial amount per beneficiary are captured
|  | HH toilet repair/rehabilitation | financial amount per beneficiary | # of households |  | No. of households and financial amount per beneficiary are captured
|  | HH Rain Water Harvesting | financial amount per beneficiary | # of households |  | No. of households and financial amount per beneficiary are captured
|  | Community water scheme | financial amount per beneficiary | # of households |  | No. of households and financial amount per beneficiary are captured
| Material support on household WASH | Household toilet construction | financial amount per beneficiary | # of households |  | No. of households and financial amount per beneficiary are captured
|  | Household toilet/hygiene kits | financial amount per beneficiary | # of households |  | No. of households and financial amount per beneficiary are captured
|  | HH toilet repair/rehabilitation | financial amount per beneficiary | # of households |  | No. of households and financial amount per beneficiary are captured
|  | HH water supply new | financial amount per beneficiary | # of households |  | No. of households and financial amount per beneficiary are captured
|  | HH water supply repair/rehabilitation | financial amount per beneficiary | # of households |  | No. of households and financial amount per beneficiary are captured
|  | HH Rain Water Harvesting | financial amount per beneficiary | # of households |  | No. of households and financial amount per beneficiary are captured
|  | Community water scheme | financial amount per beneficiary | # of households |  | No. of households and financial amount per beneficiary are captured
| Other assistance | (Please specify in Activity Detail)
Reconstruction through contractors | Construction | Private house |  | # of constructions | Construction of private houses through contractors | No. of constructions is captured
|  | Household toilet |  | # of constructions | Construction of household toilets through contractors | No. of constructions is captured
Others | Others | (Please specify in Activity Detail)

## PO_List
Acronym | Partner Organisation
AA | ActionAid
AAA | Aussie Action Abroad
AAR-J | AAR Japan
ABARI | Abari
AC | Architectural Consultant
ACF | Action Contre La Faim
ACN | Asal Chhimekee Nepal
ACT ALLIANCE | ACT Alliance
ACTED | Agency for Technical Cooperation and Development
ACTION-N | Action Nepal
AD | Architecture & Development
ADB | Asian Development Bank
ADH | ADH, Germany Grant
ADRA | ADRA Nepal
AEIN | Aide a' I'Enfance de I'Inde et du Nepal (AEIN)
AFD | Action for Development
AH | All Hands
AHV | All Hands Volunteers
AJJDC | American Jewish Joint Distribution Committee
AKF | AKF
AL | Accountability Lab
ALLIANCE-N | Alliance for Social Mobilization
AMDA-M | AMDA-MINDS
AMERICARES | Americares
AN | AN
ANS | Associate Nepal Synergy
ANSAB-RI | ANSAB-Relief Intl
APAD | Asia Pacific Alliance for Disaster Management
ARC | ARC
ARSOW-ASF | ARSOW-ASF
ARSOW-N | ARSOW Nepal
ARSOW-TGH | ARSOW Triangle Génération Humanitaire
AS-ASIA | Association for Solidarity in ASIA
ASB | Arbeiter-Samariter-Bund Nepal
ASF | Architecture Sans Frontieres Nepal (ASF Nepal)
ASIA ONLUS | Association for International Solidarity in Asia
AU | Architects Urgent
AWOI | AWO International
AYTHOS | Aythos
BATAS | Batas Foundation
BC | Build Change
BCC
BDCC | Business Development and Consultancy Center
BG | Baliyo Ghar
B-GRC | Belgian-German RC
BKF | Buddha Kumari Foundation
BLF | Big Lottary Fund
BMZ-WHH | BMZ-WHH
BNMT | Birat Nepal Medical Trust
BRAC | BRAC
BRC | British Red Cross
BRC FL | Belgian RC-Flanders
Brot | Bread for the World
BUILDUP-N | Build Up Nepal
CA | Christian Aid
CAFOD | CAFOD
CARD | Center for Applied research and Development
CARDSN | Community and rural development society nepal
CARE-F | Care France
CARE-N | CARE Nepal
CARITAS | Caritas
CARITAS-A | Caritas Austria
CARITAS-G | Caritas Germany
CARITAS-L | Caritas Luxemborg
CARITAS-N | Caritas Nepal
CARITAS-S | Caritas Switzerland
CC | Creative Cooperative
CCC | Conscious Connections Foundation
CCDN | CCDN
CDC | Community Development Center
CDECF | CDECF
CDF | CDF Nepal
CDRA | CDRA Nepal
CDRA-C-GGC | CDRA Nepal-Creative-GGC Nepal
CDS | Community Development Society
CEAD | Centre for Environmental Action and Development
CEDAR | CEDAR
CEED | Center for Energy and Environment Development
CEEDF | Community for Energy and Ecology Development Forum
CEEPAARD | Community Environment Education and Public Awareness Association for Rural Development
CEN | Clean Energy Nepal
CESVI | Cesvi
CF | Chaudhary Foundation
CFN | Childspace Foundation Nepal
CG | Chaudhary Group
CHDP | Center for Helpless and Disabled People
CHESS | CHESS Gorkha
CHRDP | Community human resource development programe
CIDEC | Community Development And Environment Conservation Forum
CIRDS | Chandra Joyti Integrated Rular Development Society.
CISCN | Centre For International Studies And Cooperation Nepal
CL | Centum Learning
CMEA | CanadaMEA
CMES | Creative Service & Sales Center (CMES)
CO-C | Colorado College
COE | CoE
Comfortc | Community Forestry Research and Training Center
CORDAID | Cordaid
COSOC | COSOC
CREASION | Creasion Nepal
CRS | Catholic Relief Services
CS | Creative Skills
CSIDB | Samall Cottage Industry Development Board
CSON | CSON
CSRC | Community Self-reliance Center
CSSS
CTEVT | Council for Technical Education and Vocational Training
CUN | Clean Up Nepal
CW | Concern Worldwide
CWIN-TUKI | CWIN-TUKI
DCA | Dan Church Aid
DCI | Disaster Corps Int'l
DCU | DCU
DDRC | District Disaster Relief Committee
DEC | DEC
DEC-II | DEC-II
DEO | District Education Office
DEPROSC | Development Project Service Centre (Local NGO)
DFAT | DFAT
DFATD-C | DFATD (Canada)
DFID | Department for International Development
DHN | Digital Humanitarian Network
DPO | District Police Office
DRC | Danish Red Cross
DSSS | Deepjyoti Samaj Sundar Sangh
DTO | District Technical Office
EA | Emergency Architects
EC | Educate the Children
ECARDS | ECARDS
ECCA | Environmental Camps for Conservation Awareness
ECCO | Environment and Child Concern Organization
ECHO | European Commission's Humanitarian Aid Office
ECHO-JAP-NOR | ECHO-JAPAN-NORWAY
ECO-N | ECO-Nepal
EMI | Engineering Ministries Internationl
ENPHO | Environment and Public Health Organization
EOI | Embassy of India Kathmandu
EPF | Ecological Protection Forum
ERO | ERO
ERTECH | Ertech
ESF | ESF
EWB-GER | Engineers without Borders Germany
EWB-USA | Engineers without Borders USA
EWDE-DKH-N | EWDE - Diakonie Katastrophenhilfe (DKH) Nepal
FAYA | FAYA
FBPN | Federation of Business and Professional Nepal
FDF | Fondation De France
FECOFUN | Federation of Community Forest User Group Nepal
FIDA-I | Fida International
FIU | Florida international university
FNA | Friends of Nepal Association
FOCUS | Forum for community Upliftment System
FORD-N | Ford Nepal
FSCN | Friends Service Council Nepal
F-SKILL | F-SKILL
GAN | Global Action Nepal
GC | Global Communities
GCF GLOBAL-U | GCF Global-USA
GCS | Gorkhali Christian Society
GDA | Govinda Development Aid
GDAA | Govinda Development Aid Association
GENESIS | GENESIS
GH | Good Helpers
GIZ | GIZ Germany
GMSP | GMSP
GMTI | Genius Multi Technical Institute
GNI | Good Neighbors International
GNZ | GNZ
GOAL | GOAL
GOJ | Government of Japan
GON | Government of Nepal
GON - DLPIU | District Level Project Implementation Unit
GON - DUDBC | Department for Urban Development & Building Constuction
GON - PAF | Poverty Alleviation Fund
GORETO GORKHA | GORETO Gorkha
GYEC | ?? Call Nuwakot
HADC | Himalayan Area Development Center
HAM FN | Ham Foundation
HCI | Himalayan Climate Initiative
HDSC | Holistic Development Service Center(SAMAGRA)
HELP | Help - Hilfe zur Selbsthilfe
HELPAGE | Helpage Interantional Nepal
HELVETAS | HELVETAS Swiss Intercooperation Nepal
HFH | Habitat for Humanity International
HHI | Himalayan Healthcare Inc.
HI | Handicap International
HIMS | HIMS
HSS | Housing Subsidy System
HUMEDICA | Humedica
HURADEC | HURADEC Nepal
ICCO | ICCO Cooperation
ICDC | Integrated Community Development Campaign
ICDO | Ask with Lalitpur??
ICMOD | ICMOD
IDRC | International development research center
IDV | International Disaster Volunteers
IFRC | International Federation of Red Cross
IINET | IINET
IMC | International Medical Corps
INCLUSIVE | INCLUSIVE
INF- B | INF Baglung
INF International | INF International
INF-N | International Nepal Fellowship-Nepal
INFUK-GZB-OTHERS | International Nepal Fellowship-GZB-Others
INSAF | Insaf Malaysia
INTERACTION | InterAction
IOM | International Organization for Migration
ISAP | Institution for Suitable Actions for Prosperity
ISLAMIC RELIEF | Islamic Relief
ISRAAID | IsraAID
ITDSN | Integrated Tadi Development Society Nepal
ITV | Independent Television
JANAHIT | Janahit
JAYAN | Jayan Technical College of Technology
JGSS | Janahit Gramin Sewa Samiti
JICA | Japan International Cooperation Agency
JJMS | Janajagriti Mahila Samuha
JP | Japan Platform
JRCS | Japanese Red Cross Society
JTI | Jhapa technical Institute
JYC | Janbhawana Youth Club
JYSP | Joint Youth and Students Platform
KANTIPUR | Kantipur
KBPS | Kantipur Bahupravidhik Sikshalaya
KCDC | Kakani center for development of community
KF | Karuna Foundation
KFS | Kam For Sud
KIT-CEDIM | KIT (CEDIM)
KITE | Kohalpur Institute of Technical Education
KIT-SAI | KIT-South Asian Institute
KKS Germany | KarlKonrad Germany
KOICA | Korean Internation Cooperation Agencies
KOSIS-N | Kosis Nepal
KRC | Korean Red Cross
KW | Knowledge Works
LACCOS | LACCoS
LCDF | Likhudemba Community Devlopment Forum
LCD-SIN | LCD SINGAPORE
LDF | Local Development Fund
LDO | Local Development Officer
LIG | Local Interventions Group
LLCSC | Lig Lig Credit and Saving Cooperation Ltd
LRC | Luxemburg Red Cross
LRMC | Langtang Reconstruction and Management Committee
LUMANTI | LUMANTI
LWF | The Lutheran World Federation
LWR | Lutheran World Relief
MANEKOR | Manekor Society Nepal
MANK | Mahila Atma Nirvarta Kendra
MC | Mercy Corps
MCAP | Manaslu Conservation Area Project (MCAP)
MCC | Mennonite Central Committee
MCC | Mennonite Centre Committee, Nepal
MDM | MDM
MEDAIR | MedAir
MEDICO-I | Medico International
MI | Malteser International
MINERGY | Minergy Pvt. Ltd
MISSIONEAST | Mission East Nepal
MOUD | MoUD
MSED | Multi Skill & Environment Development Pvt. Ltd
MSEREOR | MISEREOR
MSF-OCB | MSF OCB
MSWC | updates pending from Ramechhap
MTS | More Than Shelters
MTSDI | Manakamana Training and Skill Development Institute
NA | Nangshal Association
NAF | Nepal Agroforestry Foundation
NAVJYOTI | Navjyoti Centre ( Nepal Nazareth Society)
NC | Narjyoti Center
NCA | Norwegian Church Aid
NCM | Nazarene Compassionate Ministries
NCRS | Nepal Christian Relief Services
NCV | NCV
ND | Nepal Delegate
NDS | Nepal Development Society
NDWA | Nepal Disabled Women Association
NEFA | EDUCATION for ALL (NEfA) Switzerland
NEPAN | Nepal Participatory Action Network
NETSA | Nepal Engineering and Technical Science of Academy
NFDN | NFDN
NFN | Nepali for Nepali
NGOF | NGO Federation
NHA | Nepalhilfe Aachen
NJS | NJS
NMC | Nepal MSR Center
NMSRC | updates pending from Ramechhap
NN | Namaste Nepal
Norlang SAHAS | Norlang SAHAS
NR | Nepal Rises
NRA | Nepal Reconstruction Authority
NRC | Norwegian Red Cross
NRCS | Nepal Red Cross Society
NRDS | NRDS
NS | Nepal Share
NSET | NSET-Nepal
NSSS | Nepal Samaj Sewa Sangh
NTA | Nepal Thai Association
NTA-ROTARY | Nepal Thai association and Rotary International District 3292
NTRC | Nepal Training Center
NYAYIK S | Nyayik Sansar
NYF | Nepal Youth Foundation
NYF-US | Nepal Youth Foundation - US
OFDA | Office of Foreign Disaster Assistance
OM-N | OM Nepal
OPA | Old People Association
OXFAM-GB | OXFAM GB
PA | Practical Action
PANCHA KANYA | Pancha Kanya
PA-UK | Practical Action-UK
PDF | Progressive Disable's Forum
PHA | Polish Humanitarian Action
PHASE | PHASE Nepal
PHPI | Pathibhara Himalayan Polytechnic Institute Pvt. Ltd.
PIN | People In Need
PIPALTAR | Pipaltar Community
PJPC | Peace and Justice Promotion Center
PLAN | Plan International
PLAN-GER | PLAN International Germany National Office
PM-AO | PM & AO
PN | PN
POURAKHI | POURAKHI NEPAL
PPY | Paldarpik Youth Society
PRAYASH | Prayatnashil Community development Society
PRAYAS-N | Prayas Nepal
PSBS | Prayantnashil Samudaik Bikash Samaj
PSD-N | PSD Nepal
PSKK | Pahadi Samaj Kalayan Kendra
PTI | Panchakanya Training Institute Pvt. Ltd
PWJ | Peace Wind Japan
RADO | Rural Awareness and Development Organization
RCE | Resource Center Engineer
RDTA | Rural Development TUKI Association
RD-TA | Ruler Development TUKI Association
REACH | REACH
REAL RELIEF | Real Relief
REDC
REDR-I | RedR India
RELIEF ERU | Relief ERU
RI | Relief International
RICOD | RURAL INSTITUTION FOR COMMUNITY DEVELOPMENT
RIMC | Rural Infrastructure and Management Consultant Pvt Ltd
RIMS | RIMS
RMD | Rural Mutual Development
ROTARY | Rotary International
ROTARY-BHU | Rotary International District 3292 Nepal-Bhutan
ROTARY-DHULIKHEL | Rotary Club of Dhulikhel
ROTARY-NRC | Rotary Club of New Road City
ROTARY-RASUWA | Rotary Club of Rasuwa
RPI | Rensselaer Polytechnic Institute
RR | Rasuwa Relief
RRN | Rural Reconstruction Nepal
RSDC | Rural Self Reliance Development Center
RUDEC | Rural Development and Empowerment Center
SA | Salvation Army
SABAL | SABAL
SAGARMATHA | Sagarmatha International
SAGUN | SAGUN
SAHAS | SAHAS NEPAL
SAHAYATRI | SAHAYATRI
SAMATA | Samata Foundation
SATHI | Sathi
SB | ShelterBox
SBPK | Sana Byabasay Paramarsh Kendra
SCI | Save the Children
SCSS | Shree Charghar Sewa Samithi
SDC | Swiss Agency for Development and Cooperation
SDO | Social Development Officer
SDSC | System Development Service Center
SEEDS | SEEDS
SEERI | Structural and Earthquake Engineering Research Institute
SFTC | Swiss Foundation for Technical Cooperation
SHANGRILA ORP | Shangrila Orphanage
SIDEC | Sindhu Development Center
SIF | SIF
SJASK | Shanti Jana Adarsha Sewa kendra
SJBYC | updates pending from Ramechhap
SK | Sneha Krishnan
SLM-REDDPC | SLM-REDD Plus Coordinator
SMF | Smart Shelter Foundation
SNA | Society of Nepalese Architects
SODEC-N | SODEC Nepal
SOLIDARITES | Solidarites International
Solve-N | Solve Nepal
SOS | SOS Balgram
SP | Samaritan Purse
SPC | Shelter Project Coordinator
SPO | SPO
SPSWO | SPSWO
SRC | Swiss Red Cross
SRRLS | Seismic Resistant Related Legal System
SSE | School for shelter and environment
SSICDC | SSICDC Gorkha
SSS | Samaj Sewa Samuha
STEADFAST-N | Stead Fast Nepal
SUK-N | SUK Nepal
SW Nepal | Scout Wilinston
SWISSCONTACT | Swisscontact - Swiss Foundation for Technical Cooperation
Swostik | Ask Gorkha??
SWS | Swiss Solidarity
SWS-SWISSCONTACT | Swiss Solidarity- SwissContact
SYC | Samajsebi Youth Club
SYS | updates pending from Ramechhap
TAJJDC | The American Jewish Joint Distribution Committee
TCCEE | Training & Consultancy Center for Employment & Enterprising
TCM | TCM
TCN | Training center Nepal
TCN-AN | The Committed Society for Change Nepal(TCN)-ACTION Nepal(AN)
TCN-PN | The Committed Society for Change Nepal(TCN)-Prayash Nepal(PN)
TDH | Terre des hommes
TDH-GER | Terre des hommes - Germany
TDH-GER-CARITAS-ITA | TDH Germany, Caritas Italiana
TEARFUND | Tearfund
TEAR-NET | Tear Neatherland
TEVEL | Tevel
TFCH | The Fuller Center for Housing
TMF | The Mobile Factory
TMI | The Mountain Institute
TMN | Tono Magokoro Net
TMUC | TMUC
TPIS-ERP | TPIS-ERP
TRACE | TRACE
TSA | The Salvation Army
TUKI | Tuki Association
UCEP-N | UCEP Nepal
UF-SRDP | Usthi Foundation - SRDP Project
UMN | United Mission to Nepal
UNDAC | UNDAC
UNDP | United Nations Development Programme
UNFPA | United Nations Population Fund
UNHABITAT | UN-HABIBAT
UNHCR | United Nations High Commissioner for Refugees
UNICEF | United Nations Children's Fund
UNIFICATION-N | Unification Nepal
UNOCHA | United Nations Office for the Coordination of Humanitarian Affairs
UNOPS | United Nations Office for Project Services
UNRCO | UNRCO
UNWOMEN | UNWomen
UON | Umbrella Organization Nepal
USAID | USAID
USAID-SABAL | Usaid Sabal Nepal
UVN | United Vision Nepal
UWA | University of Western Australia
VG | VG Group
VIN | Volunteers Initiative nepal (VIN)
VO | Village Organization
VSO | VSO Nepal
W4C | Wes 4 Christ
WB | World Bank
WDAC | Women Development Advocacy Center
WFP | World Food Programme
WHO | World Health Organization
WHR | Women human right
WJR | World Jewish Relief
WOREC-N | Women's Rehabilitation Centre Nepal
WR | World Renew
WSSDO | WSSDO
WVIN | World Vision International
XPSI | XPS International
YFN | Youthspace Foundation Nepal
YIW | Yes I Will
YSC | Young Star Club
YSP | YSP Nepal
ZOA | ZOA