## Round-58
SN | District | VDC | Ward | Partner Organisation | Implementing Partner | Funding Organisation | Activity Type | Activity Sub-Type | Activity Name | Activity Detail | Units | Funding Status | Activity Status | Total Planned | Total Reached | Activity Start Date | Activity End Date | Comments | GaPaNa_Name | GaPaNa_Ward
1 | Dhading | Aginchok | 1 | CARE-N | SAHAYATRI | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 109 | 2016-09-18 | 2016-09-18 |  | Tripura Sundari | 6
2 | Dhading | Aginchok | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 6
3 | Dhading | Aginchok | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 13 | 13 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 6
4 | Dhading | Aginchok | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 6
5 | Dhading | Aginchok | 2 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 68 | 2016-09-17 | 2016-09-17 |  | Tripura Sundari | 6
6 | Dhading | Aginchok | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 6
7 | Dhading | Aginchok | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 6
8 | Dhading | Aginchok | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 6
9 | Dhading | Aginchok | 3 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 76 | 2016-09-16 | 2016-09-16 |  | Tripura Sundari | 6
10 | Dhading | Aginchok | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 6
11 | Dhading | Aginchok | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 6
12 | Dhading | Aginchok | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 6
13 | Dhading | Aginchok | 4 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 56 | 2016-09-15 | 2016-09-15 |  | Tripura Sundari | 6
14 | Dhading | Aginchok | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 6
15 | Dhading | Aginchok | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 6
16 | Dhading | Aginchok | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 6
17 | Dhading | Aginchok | 5 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 41 | 2016-09-13 | 2016-09-13 |  | Tripura Sundari | 6
18 | Dhading | Aginchok | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 6
19 | Dhading | Aginchok | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 6
20 | Dhading | Aginchok | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 6
21 | Dhading | Aginchok | 6 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 32 | 2016-09-12 | 2016-09-12 |  | Tripura Sundari | 6
22 | Dhading | Aginchok | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 6
23 | Dhading | Aginchok | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 6
24 | Dhading | Aginchok | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 6
25 | Dhading | Aginchok | 7 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 52 | 2016-09-11 | 2016-09-11 |  | Tripura Sundari | 6
26 | Dhading | Aginchok | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 6
27 | Dhading | Aginchok | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 6
28 | Dhading | Aginchok | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 6
29 | Dhading | Aginchok | 8 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 41 | 2016-09-14 | 2016-09-14 |  | Tripura Sundari | 5
30 | Dhading | Aginchok | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 5
31 | Dhading | Aginchok | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 5
32 | Dhading | Aginchok | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 5
33 | Dhading | Aginchok | 9 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 59 | 2016-09-10 | 2016-09-10 |  | Tripura Sundari | 5
34 | Dhading | Aginchok | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 5
35 | Dhading | Aginchok | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 5
36 | Dhading | Aginchok | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 5
37 | Dhading | Aginchok | All | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 75 | 75 | 2016-10-22 | 2016-10-28 |  | Tripura Sundari | 6
38 | Dhading | Aginchok | All | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 75 | 75 | 2016-10-22 | 2016-10-28 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 6
39 | Dhading | Baireni | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 4
40 | Dhading | Baireni | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 4
41 | Dhading | Baireni | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 5
42 | Dhading | Baireni | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 5
43 | Dhading | Baireni | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 4
44 | Dhading | Baireni | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 4
45 | Dhading | Baireni | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 5
46 | Dhading | Baireni | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 5
47 | Dhading | Baireni | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 5
48 | Dhading | Baireni | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 5
49 | Dhading | Baireni | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 5
50 | Dhading | Baireni | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 5
51 | Dhading | Baireni | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 4
52 | Dhading | Baireni | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 4
53 | Dhading | Baireni | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 7
54 | Dhading | Baireni | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 7
55 | Dhading | Baireni | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 6
56 | Dhading | Baireni | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 6
57 | Dhading | Baireni | All | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 20 | 22 | 2016-05-08 | 2016-06-23 | Submit next round of 4W | Galchhi | 7
58 | Dhading | Baireni | ALL | GON - DUDBC | GON - DUDBC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 28 | 28 | 2017-02-23 | 2017-03-01 | Training location is Pida VDC Hall | Galchhi | 7
59 | Dhading | Baseri | 1 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 4 | 4 | 2016-11-18 | 2016-11-24 |  | Gangajamuna | 6
60 | Dhading | Baseri | 1 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 57 | 2016-09-13 | 2016-09-13 |  | Gangajamuna | 6
61 | Dhading | Baseri | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 6
62 | Dhading | Baseri | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 6
63 | Dhading | Baseri | 1 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-11-18 | 2016-11-24 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 6
64 | Dhading | Baseri | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 6
65 | Dhading | Baseri | 2 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 7 | 7 | 2016-11-18 | 2016-11-24 |  | Gangajamuna | 6
66 | Dhading | Baseri | 2 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 42 | 2016-09-12 | 2016-09-12 |  | Gangajamuna | 6
67 | Dhading | Baseri | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 6
68 | Dhading | Baseri | 2 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-11-18 | 2016-11-24 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 6
69 | Dhading | Baseri | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 6
70 | Dhading | Baseri | 3 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-11-18 | 2016-11-24 |  | Gangajamuna | 6
71 | Dhading | Baseri | 3 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 46 | 2016-09-11 | 2016-09-11 |  | Gangajamuna | 6
72 | Dhading | Baseri | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 6
73 | Dhading | Baseri | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 6
74 | Dhading | Baseri | 3 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-11-18 | 2016-11-24 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 6
75 | Dhading | Baseri | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 6
76 | Dhading | Baseri | 4 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 12 | 12 | 2016-11-18 | 2016-11-24 |  | Gangajamuna | 6
77 | Dhading | Baseri | 4 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 63 | 2016-09-18 | 2016-09-18 |  | Gangajamuna | 6
78 | Dhading | Baseri | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 6
79 | Dhading | Baseri | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 6
80 | Dhading | Baseri | 4 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 12 | 12 | 2016-11-18 | 2016-11-24 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 6
81 | Dhading | Baseri | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 6
82 | Dhading | Baseri | 5 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 9 | 9 | 2016-11-18 | 2016-11-24 |  | Gangajamuna | 6
83 | Dhading | Baseri | 5 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 59 | 2016-09-19 | 2016-09-19 |  | Gangajamuna | 6
84 | Dhading | Baseri | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 6
85 | Dhading | Baseri | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 6
86 | Dhading | Baseri | 5 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 9 | 9 | 2016-11-18 | 2016-11-24 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 6
87 | Dhading | Baseri | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 6
88 | Dhading | Baseri | 6 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 12 | 12 | 2016-11-18 | 2016-11-24 |  | Gangajamuna | 6
89 | Dhading | Baseri | 6 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 77 | 2016-09-14 | 2016-09-14 |  | Gangajamuna | 6
90 | Dhading | Baseri | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 6
91 | Dhading | Baseri | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 6
92 | Dhading | Baseri | 6 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 12 | 12 | 2016-11-18 | 2016-11-24 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 6
93 | Dhading | Baseri | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 6
94 | Dhading | Baseri | 7 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-11-18 | 2016-11-24 |  | Gangajamuna | 6
95 | Dhading | Baseri | 7 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 103 | 2016-09-17 | 2016-09-17 |  | Gangajamuna | 6
96 | Dhading | Baseri | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 6
97 | Dhading | Baseri | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 6
98 | Dhading | Baseri | 7 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-11-18 | 2016-11-24 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 6
99 | Dhading | Baseri | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 6
100 | Dhading | Baseri | 8 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 7 | 7 | 2016-11-18 | 2016-11-24 |  | Gangajamuna | 6
101 | Dhading | Baseri | 8 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 74 | 2016-09-16 | 2016-09-16 |  | Gangajamuna | 6
102 | Dhading | Baseri | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 6
103 | Dhading | Baseri | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 6
104 | Dhading | Baseri | 8 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-11-18 | 2016-11-24 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 6
105 | Dhading | Baseri | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 6
106 | Dhading | Baseri | 9 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 4 | 4 | 2016-11-18 | 2016-11-24 |  | Gangajamuna | 6
107 | Dhading | Baseri | 9 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 56 | 2016-09-15 | 2016-09-15 |  | Gangajamuna | 6
108 | Dhading | Baseri | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 6
109 | Dhading | Baseri | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 6
110 | Dhading | Baseri | 9 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-11-18 | 2016-11-24 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 6
111 | Dhading | Baseri | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 6
112 | Dhading | Benighat | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 3
113 | Dhading | Benighat | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 3
114 | Dhading | Benighat | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 3
115 | Dhading | Benighat | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 3
116 | Dhading | Benighat | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 4
117 | Dhading | Benighat | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 4
118 | Dhading | Benighat | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 4
119 | Dhading | Benighat | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 4
120 | Dhading | Benighat | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 4
121 | Dhading | Benighat | 5 | GON - PAF | ICDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-26 | 2017-07-04 | PAF:Poverty Alleviation Fund | Benighat Rorang | 4
122 | Dhading | Benighat | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 4
123 | Dhading | Benighat | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 5
124 | Dhading | Benighat | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 5
125 | Dhading | Benighat | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 5
126 | Dhading | Benighat | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 5
127 | Dhading | Benighat | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 5
128 | Dhading | Benighat | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 5
129 | Dhading | Benighat | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 3
130 | Dhading | Benighat | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 3
131 | Dhading | Benighat | ALL | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 29 | 29 | 2017-01-17 | 2017-01-23 |  | Benighat Rorang | 5
132 | Dhading | Bhumesthan | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 3
133 | Dhading | Bhumesthan | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 3
134 | Dhading | Bhumesthan | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 3
135 | Dhading | Bhumesthan | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 3
136 | Dhading | Bhumesthan | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 3
137 | Dhading | Bhumesthan | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 3
138 | Dhading | Bhumesthan | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 2
139 | Dhading | Bhumesthan | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 2
140 | Dhading | Bhumesthan | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 4
141 | Dhading | Bhumesthan | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 4
142 | Dhading | Bhumesthan | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 2
143 | Dhading | Bhumesthan | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 2
144 | Dhading | Bhumesthan | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 2
145 | Dhading | Bhumesthan | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 2
146 | Dhading | Bhumesthan | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 1
147 | Dhading | Bhumesthan | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 1
148 | Dhading | Bhumesthan | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 1
149 | Dhading | Bhumesthan | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 1
150 | Dhading | Budhathum | 1 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 6 | 6 | 2016-02-21 | 2016-05-30 |  | Gangajamuna | 7
151 | Dhading | Budhathum | 1 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 90 | 2016-04-02 | 2016-04-02 |  | Gangajamuna | 7
152 | Dhading | Budhathum | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 7
153 | Dhading | Budhathum | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 7
154 | Dhading | Budhathum | 1 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-02-21 | 2016-05-30 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 7
155 | Dhading | Budhathum | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 7
156 | Dhading | Budhathum | 2 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 6 | 6 | 2016-02-21 | 2016-05-30 |  | Gangajamuna | 7
157 | Dhading | Budhathum | 2 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 60 | 2016-04-01 | 2016-04-01 |  | Gangajamuna | 7
158 | Dhading | Budhathum | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 7
159 | Dhading | Budhathum | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 7
160 | Dhading | Budhathum | 2 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-02-21 | 2016-05-30 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 7
161 | Dhading | Budhathum | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 7
162 | Dhading | Budhathum | 3 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 12 | 12 | 2016-02-21 | 2016-05-30 |  | Gangajamuna | 7
163 | Dhading | Budhathum | 3 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 48 | 2016-03-27 | 2016-03-27 |  | Gangajamuna | 7
164 | Dhading | Budhathum | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 7
165 | Dhading | Budhathum | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 7
166 | Dhading | Budhathum | 3 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 12 | 12 | 2016-02-21 | 2016-05-30 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 7
167 | Dhading | Budhathum | 3 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 2 | 2 | 2016-04-21 | 2016-06-05 | District Small Cottage Industry | Gangajamuna | 7
168 | Dhading | Budhathum | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 7
169 | Dhading | Budhathum | 4 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-02-21 | 2016-05-30 |  | Gangajamuna | 7
170 | Dhading | Budhathum | 4 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 54 | 2016-03-25 | 2016-03-25 |  | Gangajamuna | 7
171 | Dhading | Budhathum | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 7
172 | Dhading | Budhathum | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 7
173 | Dhading | Budhathum | 4 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-02-21 | 2016-05-30 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 7
174 | Dhading | Budhathum | 4 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 1 | 1 | 2016-04-21 | 2016-06-05 |  | Gangajamuna | 7
175 | Dhading | Budhathum | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 7
176 | Dhading | Budhathum | 5 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-02-21 | 2016-05-30 |  | Gangajamuna | 7
177 | Dhading | Budhathum | 5 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 42 | 2016-03-26 | 2016-03-26 |  | Gangajamuna | 7
178 | Dhading | Budhathum | 5 | CARE-N | SAHAS | CARE-F | Technical Assistance | Demonstration Construction | House | After completion of mason training house is constructed | # of constructions | Yes | Completed | 1 | 1 | 2016-02-01 | 2016-08-15 | Mason training and democonstruction held Deurali tole of this vdc. | Gangajamuna | 7
179 | Dhading | Budhathum | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 7
180 | Dhading | Budhathum | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 7
181 | Dhading | Budhathum | 5 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-02-21 | 2016-05-30 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 7
182 | Dhading | Budhathum | 5 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 1 | 1 | 2016-04-21 | 2016-06-05 |  | Gangajamuna | 7
183 | Dhading | Budhathum | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 7
184 | Dhading | Budhathum | 6 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-02-21 | 2016-05-30 |  | Gangajamuna | 7
185 | Dhading | Budhathum | 6 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 92 | 2016-03-31 | 2016-03-31 |  | Gangajamuna | 7
186 | Dhading | Budhathum | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 7
187 | Dhading | Budhathum | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 7
188 | Dhading | Budhathum | 6 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-02-21 | 2016-05-30 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 7
189 | Dhading | Budhathum | 6 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 1 | 1 | 2016-04-21 | 2016-06-05 |  | Gangajamuna | 7
190 | Dhading | Budhathum | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 7
191 | Dhading | Budhathum | 7 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-02-21 | 2016-05-30 |  | Gangajamuna | 7
192 | Dhading | Budhathum | 7 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 73 | 2016-03-30 | 2016-03-30 |  | Gangajamuna | 7
193 | Dhading | Budhathum | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 7
194 | Dhading | Budhathum | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 7
195 | Dhading | Budhathum | 7 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-02-21 | 2016-05-30 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 7
196 | Dhading | Budhathum | 7 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 14 | 14 | 2016-04-21 | 2016-06-05 |  | Gangajamuna | 7
197 | Dhading | Budhathum | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 7
198 | Dhading | Budhathum | 8 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-02-21 | 2016-05-30 |  | Gangajamuna | 7
199 | Dhading | Budhathum | 8 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 58 | 2016-03-28 | 2016-03-28 |  | Gangajamuna | 7
200 | Dhading | Budhathum | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 7
201 | Dhading | Budhathum | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 7
202 | Dhading | Budhathum | 8 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-02-21 | 2016-05-30 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 7
203 | Dhading | Budhathum | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 7
204 | Dhading | Budhathum | 9 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-02-21 | 2016-05-30 |  | Gangajamuna | 7
205 | Dhading | Budhathum | 9 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 77 | 2016-03-29 | 2016-03-29 |  | Gangajamuna | 7
206 | Dhading | Budhathum | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 7
207 | Dhading | Budhathum | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 7
208 | Dhading | Budhathum | 9 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-02-21 | 2016-05-30 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 7
209 | Dhading | Budhathum | 9 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 1 | 1 | 2016-04-21 | 2016-06-05 |  | Gangajamuna | 7
210 | Dhading | Budhathum | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 7
211 | Dhading | Chainpur | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 7
212 | Dhading | Chainpur | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 7
213 | Dhading | Chainpur | 2 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 1 | 1 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 7
214 | Dhading | Chainpur | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 7
215 | Dhading | Chainpur | 2 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 7
216 | Dhading | Chainpur | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 7
217 | Dhading | Chainpur | 3 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 9 | 9 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 7
218 | Dhading | Chainpur | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 7
219 | Dhading | Chainpur | 3 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 9 | 9 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 7
220 | Dhading | Chainpur | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 7
221 | Dhading | Chainpur | 4 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 8 | 8 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 7
222 | Dhading | Chainpur | 4 | CA | FOCUS | CA | Technical Assistance | Demonstration Construction | House | House constructed for Single and Disabled male | # of constructions | Yes | Completed | 1 | 1 | 2016-11-14 | 2016-12-28 | House is made for single and disable male | Jwalamukhi | 7
223 | Dhading | Chainpur | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 7
224 | Dhading | Chainpur | 4 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 7
225 | Dhading | Chainpur | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 7
226 | Dhading | Chainpur | 5 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 14 | 14 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 6
227 | Dhading | Chainpur | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 6
228 | Dhading | Chainpur | 5 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 14 | 14 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 6
229 | Dhading | Chainpur | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 6
230 | Dhading | Chainpur | 6 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 12 | 12 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 6
231 | Dhading | Chainpur | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 6
232 | Dhading | Chainpur | 6 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 12 | 12 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 6
233 | Dhading | Chainpur | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 6
234 | Dhading | Chainpur | 7 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 12 | 12 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 6
235 | Dhading | Chainpur | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 6
236 | Dhading | Chainpur | 7 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 12 | 12 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 6
237 | Dhading | Chainpur | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 6
238 | Dhading | Chainpur | 8 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 9 | 9 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 6
239 | Dhading | Chainpur | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 6
240 | Dhading | Chainpur | 8 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 9 | 9 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 6
241 | Dhading | Chainpur | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 6
242 | Dhading | Chainpur | 9 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 10 | 10 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 6
243 | Dhading | Chainpur | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 6
244 | Dhading | Chainpur | 9 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 6
245 | Dhading | Chainpur | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 6
246 | Dhading | Chainpur | ALL | GON - DUDBC | GON - DUDBC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 36 | 36 | 2017-05-30 | 2017-06-05 | Training location is Jewwanpur VDC hall | Jwalamukhi | 7
247 | Dhading | ChhatreDyaurali | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 2
248 | Dhading | ChhatreDyaurali | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 2
249 | Dhading | ChhatreDyaurali | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 2
250 | Dhading | ChhatreDyaurali | 2 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 4 | 4 | 2016-04-05 | 2016-05-20 |  | Dhunibesi | 2
251 | Dhading | ChhatreDyaurali | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 2
252 | Dhading | ChhatreDyaurali | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 2
253 | Dhading | ChhatreDyaurali | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 2
254 | Dhading | ChhatreDyaurali | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 2
255 | Dhading | ChhatreDyaurali | 4 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 3 | 3 | 2016-04-05 | 2016-05-20 |  | Dhunibesi | 2
256 | Dhading | ChhatreDyaurali | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 2
257 | Dhading | ChhatreDyaurali | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 2
258 | Dhading | ChhatreDyaurali | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 2
259 | Dhading | ChhatreDyaurali | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 1
260 | Dhading | ChhatreDyaurali | 6 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 2 | 2 | 2016-04-05 | 2016-05-20 |  | Dhunibesi | 1
261 | Dhading | ChhatreDyaurali | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 1
262 | Dhading | ChhatreDyaurali | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 1
263 | Dhading | ChhatreDyaurali | 7 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 8 | 8 | 2016-04-05 | 2016-05-20 |  | Dhunibesi | 1
264 | Dhading | ChhatreDyaurali | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 1
265 | Dhading | ChhatreDyaurali | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 1
266 | Dhading | ChhatreDyaurali | 8 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 2 | 2 | 2016-04-05 | 2016-05-20 |  | Dhunibesi | 1
267 | Dhading | ChhatreDyaurali | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 1
268 | Dhading | ChhatreDyaurali | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 1
269 | Dhading | ChhatreDyaurali | 9 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 3 | 3 | 2016-04-05 | 2016-05-20 |  | Dhunibesi | 1
270 | Dhading | ChhatreDyaurali | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 1
271 | Dhading | ChhatreDyaurali | All | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 60 | 49 | 2015-11-24 | 2015-11-28 | Ward wise data not avialbale | Dhunibesi | 2
272 | Dhading | Darkha | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 183 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
273 | Dhading | Darkha | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
274 | Dhading | Darkha | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 174 | 31 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
275 | Dhading | Darkha | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 174 | 62 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
276 | Dhading | Darkha | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 4
277 | Dhading | Darkha | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
278 | Dhading | Darkha | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
279 | Dhading | Darkha | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 144 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
280 | Dhading | Darkha | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
281 | Dhading | Darkha | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 174 | 11 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
282 | Dhading | Darkha | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 174 | 7 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
283 | Dhading | Darkha | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 3
284 | Dhading | Darkha | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
285 | Dhading | Darkha | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
286 | Dhading | Darkha | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 158 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
287 | Dhading | Darkha | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
288 | Dhading | Darkha | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 147 | 7 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
289 | Dhading | Darkha | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 147 | 7 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
290 | Dhading | Darkha | 3 | GON - PAF | CIRDS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-06-10 | 2017-06-16 | CIRDS:Chandra Jyoti Integreted Rular Development Society | Khaniyabash | 3
291 | Dhading | Darkha | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 3
292 | Dhading | Darkha | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
293 | Dhading | Darkha | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
294 | Dhading | Darkha | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 125 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
295 | Dhading | Darkha | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
296 | Dhading | Darkha | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 204 | 8 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
297 | Dhading | Darkha | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 204 | 4 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
298 | Dhading | Darkha | 4 | GON - PAF | CIRDS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 18 | 18 | 2017-06-10 | 2017-06-16 | CIRDS:Chandra Jyoti Integreted Rular Development Society | Khaniyabash | 3
299 | Dhading | Darkha | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 3
300 | Dhading | Darkha | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
301 | Dhading | Darkha | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
302 | Dhading | Darkha | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 262 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
303 | Dhading | Darkha | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
304 | Dhading | Darkha | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 133 | 4 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
305 | Dhading | Darkha | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 133 | 5 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
306 | Dhading | Darkha | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 3
307 | Dhading | Darkha | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
308 | Dhading | Darkha | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
309 | Dhading | Darkha | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 132 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
310 | Dhading | Darkha | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
311 | Dhading | Darkha | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 111 | 4 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
312 | Dhading | Darkha | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 111 | 2 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
313 | Dhading | Darkha | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 3
314 | Dhading | Darkha | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
315 | Dhading | Darkha | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 3
316 | Dhading | Darkha | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 365 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
317 | Dhading | Darkha | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
318 | Dhading | Darkha | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 135 | 14 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
319 | Dhading | Darkha | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 135 | 2 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
320 | Dhading | Darkha | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 4
321 | Dhading | Darkha | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 36 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
322 | Dhading | Darkha | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
323 | Dhading | Darkha | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 338 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
324 | Dhading | Darkha | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
325 | Dhading | Darkha | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 242 | 18 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
326 | Dhading | Darkha | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 242 | 1 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
327 | Dhading | Darkha | 8 | GON - PAF | CIRDS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-06-10 | 2017-06-16 | CIRDS:Chandra Jyoti Integreted Rular Development Society | Khaniyabash | 4
328 | Dhading | Darkha | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 12 | 12 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 4
329 | Dhading | Darkha | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 26 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
330 | Dhading | Darkha | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
331 | Dhading | Darkha | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 183 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
332 | Dhading | Darkha | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
333 | Dhading | Darkha | 9 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Demonstration Construction | House & Toilet |  | # of constructions | Yes | Planned | 1 | 0 |  |  | Not confirm yet | Khaniyabash | 4
334 | Dhading | Darkha | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 111 | 11 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
335 | Dhading | Darkha | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 111 | 2 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
336 | Dhading | Darkha | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 4
337 | Dhading | Darkha | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 2 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
338 | Dhading | Darkha | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 4
339 | Dhading | Dhola | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 4
340 | Dhading | Dhola | 1 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-08-05 | 2016-08-11 |  | Jwalamukhi | 4
341 | Dhading | Dhola | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 4
342 | Dhading | Dhola | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 4
343 | Dhading | Dhola | 2 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-08-05 | 2016-08-11 |  | Jwalamukhi | 4
344 | Dhading | Dhola | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 4
345 | Dhading | Dhola | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 4
346 | Dhading | Dhola | 3 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-08-05 | 2016-08-11 |  | Jwalamukhi | 4
347 | Dhading | Dhola | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 4
348 | Dhading | Dhola | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 4
349 | Dhading | Dhola | 4 | GON - PAF | CIRDS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-19 | 2017-06-25 |  | Jwalamukhi | 4
350 | Dhading | Dhola | 4 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-08-05 | 2016-08-11 |  | Jwalamukhi | 4
351 | Dhading | Dhola | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 4
352 | Dhading | Dhola | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 4
353 | Dhading | Dhola | 5 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-08-05 | 2016-08-11 |  | Jwalamukhi | 4
354 | Dhading | Dhola | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 4
355 | Dhading | Dhola | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 4
356 | Dhading | Dhola | 6 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-08-05 | 2016-08-11 |  | Jwalamukhi | 4
357 | Dhading | Dhola | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 4
358 | Dhading | Dhola | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 4
359 | Dhading | Dhola | 7 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 7 | 2016-08-05 | 2016-08-11 |  | Jwalamukhi | 4
360 | Dhading | Dhola | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 4
361 | Dhading | Dhola | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 4
362 | Dhading | Dhola | 8 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-08-05 | 2016-08-11 |  | Jwalamukhi | 4
363 | Dhading | Dhola | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 4
364 | Dhading | Dhola | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 4
365 | Dhading | Dhola | 9 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-08-05 | 2016-08-11 |  | Jwalamukhi | 4
366 | Dhading | Dhola | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 4
367 | Dhading | Dhussa | 1 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-07-07 | 2016-07-28 |  | Benighat Rorang | 7
368 | Dhading | Dhussa | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 7
369 | Dhading | Dhussa | 1 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Demonstration Construction | House & Toilet |  | # of constructions | Yes | Completed | 1 | 1 | 2016-09-20 | 2017-05-15 |  | Benighat Rorang | 7
370 | Dhading | Dhussa | 1 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 35 | 2016-04-01 |  |  | Benighat Rorang | 7
371 | Dhading | Dhussa | 1 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-07-07 | 2016-07-28 |  | Benighat Rorang | 7
372 | Dhading | Dhussa | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 7
373 | Dhading | Dhussa | 2 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 9 | 9 | 2016-07-07 | 2016-07-28 |  | Benighat Rorang | 7
374 | Dhading | Dhussa | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 7
375 | Dhading | Dhussa | 2 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 25 | 2016-04-01 |  |  | Benighat Rorang | 7
376 | Dhading | Dhussa | 2 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 9 | 9 | 2016-07-07 | 2016-07-28 |  | Benighat Rorang | 7
377 | Dhading | Dhussa | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 7
378 | Dhading | Dhussa | 3 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 4 | 4 | 2016-07-07 | 2016-07-28 |  | Benighat Rorang | 8
379 | Dhading | Dhussa | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 8
380 | Dhading | Dhussa | 3 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 28 | 2016-04-01 |  |  | Benighat Rorang | 8
381 | Dhading | Dhussa | 3 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-07-07 | 2016-07-28 |  | Benighat Rorang | 8
382 | Dhading | Dhussa | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 8
383 | Dhading | Dhussa | 4 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 6 | 6 | 2016-07-07 | 2016-07-28 |  | Benighat Rorang | 8
384 | Dhading | Dhussa | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 8
385 | Dhading | Dhussa | 4 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 31 | 2016-04-01 |  |  | Benighat Rorang | 8
386 | Dhading | Dhussa | 4 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-07-07 | 2016-07-28 |  | Benighat Rorang | 8
387 | Dhading | Dhussa | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 8
388 | Dhading | Dhussa | 5 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 4 | 4 | 2016-07-07 | 2016-07-28 |  | Benighat Rorang | 8
389 | Dhading | Dhussa | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 8
390 | Dhading | Dhussa | 5 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 22 | 2016-04-01 |  |  | Benighat Rorang | 8
391 | Dhading | Dhussa | 5 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-07-07 | 2016-07-28 |  | Benighat Rorang | 8
392 | Dhading | Dhussa | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 8
393 | Dhading | Dhussa | 6 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 26 | 26 | 2016-07-07 | 2016-07-28 |  | Benighat Rorang | 8
394 | Dhading | Dhussa | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 8
395 | Dhading | Dhussa | 6 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 20 | 2016-04-01 |  |  | Benighat Rorang | 8
396 | Dhading | Dhussa | 6 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 26 | 26 | 2016-07-07 | 2016-07-28 |  | Benighat Rorang | 8
397 | Dhading | Dhussa | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 8
398 | Dhading | Dhussa | 7 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 2 | 2 | 2016-07-07 | 2016-07-28 |  | Benighat Rorang | 6
399 | Dhading | Dhussa | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 6
400 | Dhading | Dhussa | 7 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 40 | 2016-04-01 |  |  | Benighat Rorang | 6
401 | Dhading | Dhussa | 7 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-07-07 | 2016-07-28 |  | Benighat Rorang | 6
402 | Dhading | Dhussa | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 6
403 | Dhading | Dhussa | 8 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 1 | 1 | 2016-07-07 | 2016-07-28 |  | Benighat Rorang | 6
404 | Dhading | Dhussa | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 6
405 | Dhading | Dhussa | 8 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 32 | 2016-04-01 |  |  | Benighat Rorang | 6
406 | Dhading | Dhussa | 8 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-07 | 2016-07-28 |  | Benighat Rorang | 6
407 | Dhading | Dhussa | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 6
408 | Dhading | Dhussa | 9 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 1 | 1 | 2016-07-07 | 2016-07-28 |  | Benighat Rorang | 6
409 | Dhading | Dhussa | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 6
410 | Dhading | Dhussa | 9 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 40 | 2016-04-01 |  |  | Benighat Rorang | 6
411 | Dhading | Dhussa | 9 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-07 | 2016-07-28 |  | Benighat Rorang | 6
412 | Dhading | Dhussa | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 6
413 | Dhading | Dhussa | All | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | BBS orintation 2 session in eah ward | # of participants | Yes | Ongoing | 600 | 150 | 2016-04-01 |  |  | Benighat Rorang | 8
414 | Dhading | Dhussa |  | GON - PAF | NRCS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-22 | 2017-06-28 |  | Benighat Rorang | 8
415 | Dhading | Dhuwakot | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 161 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
416 | Dhading | Dhuwakot | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
417 | Dhading | Dhuwakot | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 143 | 7 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
418 | Dhading | Dhuwakot | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 143 | 40 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
419 | Dhading | Dhuwakot | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
420 | Dhading | Dhuwakot | 1 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 4 | 4 | 2015-12-22 | 2016-02-22 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Nilakantha | 14
421 | Dhading | Dhuwakot | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
422 | Dhading | Dhuwakot | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 349 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
423 | Dhading | Dhuwakot | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
424 | Dhading | Dhuwakot | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 256 | 10 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
425 | Dhading | Dhuwakot | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 256 | 27 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
426 | Dhading | Dhuwakot | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 41 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
427 | Dhading | Dhuwakot | 2 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 9 | 9 | 2015-12-22 | 2016-02-22 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Nilakantha | 14
428 | Dhading | Dhuwakot | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
429 | Dhading | Dhuwakot | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 159 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
430 | Dhading | Dhuwakot | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
431 | Dhading | Dhuwakot | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 87 | 11 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
432 | Dhading | Dhuwakot | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 87 | 15 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
433 | Dhading | Dhuwakot | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-10-18 | 2016-12-26 |  | Nilakantha | 14
434 | Dhading | Dhuwakot | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
435 | Dhading | Dhuwakot | 3 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-22 | 2016-02-22 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Nilakantha | 14
436 | Dhading | Dhuwakot | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
437 | Dhading | Dhuwakot | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 259 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
438 | Dhading | Dhuwakot | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
439 | Dhading | Dhuwakot | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 230 | 5 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
440 | Dhading | Dhuwakot | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 230 | 25 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
441 | Dhading | Dhuwakot | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 35 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
442 | Dhading | Dhuwakot | 4 | HELVETAS | RIMC | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 10 | 10 | 2015-12-22 | 2016-02-22 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Nilakantha | 14
443 | Dhading | Dhuwakot | 4 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 7 | 7 | 2015-12-22 | 2016-02-22 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Nilakantha | 14
444 | Dhading | Dhuwakot | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
445 | Dhading | Dhuwakot | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 185 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
446 | Dhading | Dhuwakot | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
447 | Dhading | Dhuwakot | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 99 | 16 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
448 | Dhading | Dhuwakot | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 99 | 17 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
449 | Dhading | Dhuwakot | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
450 | Dhading | Dhuwakot | 5 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-02-22 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Nilakantha | 14
451 | Dhading | Dhuwakot | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
452 | Dhading | Dhuwakot | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 97 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
453 | Dhading | Dhuwakot | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
454 | Dhading | Dhuwakot | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 85 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
455 | Dhading | Dhuwakot | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 85 | 10 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
456 | Dhading | Dhuwakot | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-10-18 | 2016-12-26 |  | Nilakantha | 14
457 | Dhading | Dhuwakot | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 9 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
458 | Dhading | Dhuwakot | 6 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-02-22 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Nilakantha | 14
459 | Dhading | Dhuwakot | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
460 | Dhading | Dhuwakot | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 145 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
461 | Dhading | Dhuwakot | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
462 | Dhading | Dhuwakot | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 100 | 4 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
463 | Dhading | Dhuwakot | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 100 | 12 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
464 | Dhading | Dhuwakot | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-18 | 2016-12-26 |  | Nilakantha | 14
465 | Dhading | Dhuwakot | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
466 | Dhading | Dhuwakot | 7 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-22 | 2016-02-22 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Nilakantha | 14
467 | Dhading | Dhuwakot | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
468 | Dhading | Dhuwakot | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 111 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
469 | Dhading | Dhuwakot | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
470 | Dhading | Dhuwakot | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 93 | 8 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
471 | Dhading | Dhuwakot | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 93 | 40 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
472 | Dhading | Dhuwakot | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-10-18 | 2016-12-26 |  | Nilakantha | 14
473 | Dhading | Dhuwakot | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
474 | Dhading | Dhuwakot | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
475 | Dhading | Dhuwakot | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 138 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
476 | Dhading | Dhuwakot | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
477 | Dhading | Dhuwakot | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 135 | 8 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
478 | Dhading | Dhuwakot | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 135 | 14 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
479 | Dhading | Dhuwakot | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 17 | 17 | 2016-10-18 | 2016-12-26 |  | Nilakantha | 14
480 | Dhading | Dhuwakot | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 20 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
481 | Dhading | Dhuwakot | 9 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-02-22 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Nilakantha | 14
482 | Dhading | Dhuwakot | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 14
483 | Dhading | Gajuri | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 1
484 | Dhading | Gajuri | 1 | GON - PAF | COSOC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2017-06-25 | 2017-07-01 |  | Gajuri | 1
485 | Dhading | Gajuri | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 1
486 | Dhading | Gajuri | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 2
487 | Dhading | Gajuri | 2 | GON - PAF | COSOC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-06-25 | 2017-07-01 |  | Gajuri | 2
488 | Dhading | Gajuri | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 2
489 | Dhading | Gajuri | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 1
490 | Dhading | Gajuri | 3 | GON - PAF | COSOC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-25 | 2017-07-01 |  | Gajuri | 1
491 | Dhading | Gajuri | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 1
492 | Dhading | Gajuri | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 2
493 | Dhading | Gajuri | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 2
494 | Dhading | Gajuri | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 3
495 | Dhading | Gajuri | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 3
496 | Dhading | Gajuri | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 3
497 | Dhading | Gajuri | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 3
498 | Dhading | Gajuri | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 3
499 | Dhading | Gajuri | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 3
500 | Dhading | Gajuri | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 2
501 | Dhading | Gajuri | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 2
502 | Dhading | Gajuri | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 3
503 | Dhading | Gajuri | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 3
504 | Dhading | Gajuri | ALL | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 32 | 32 | 2017-01-25 | 2017-01-31 |  | Gajuri | 3
505 | Dhading | Gajuri | All | GON - DUDBC | GON - DUDBC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 38 | 38 | 2017-06-12 | 2017-06-18 | Training location is Thakre VDC hall | Gajuri | 3
506 | Dhading | Goganpani | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 8
507 | Dhading | Goganpani | 1 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 4 | 4 | 2015-12-08 | 2015-12-12 |  | Galchhi | 8
508 | Dhading | Goganpani | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 8
509 | Dhading | Goganpani | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 8
510 | Dhading | Goganpani | 2 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 5 | 5 | 2015-12-08 | 2015-12-12 |  | Galchhi | 8
511 | Dhading | Goganpani | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 8
512 | Dhading | Goganpani | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 8
513 | Dhading | Goganpani | 3 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 8 | 8 | 2015-12-08 | 2015-12-12 |  | Galchhi | 8
514 | Dhading | Goganpani | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 8
515 | Dhading | Goganpani | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 8
516 | Dhading | Goganpani | 4 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-08 | 2015-12-12 |  | Galchhi | 8
517 | Dhading | Goganpani | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 8
518 | Dhading | Goganpani | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 11
519 | Dhading | Goganpani | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 11
520 | Dhading | Goganpani | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 11
521 | Dhading | Goganpani | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 11
522 | Dhading | Goganpani | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 11
523 | Dhading | Goganpani | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 11
524 | Dhading | Goganpani | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 11
525 | Dhading | Goganpani | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 11
526 | Dhading | Goganpani | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 8
527 | Dhading | Goganpani | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 8
528 | Dhading | Goganpani | All | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 31 | 31 | 2015-12-08 | 2015-12-12 | Ward wise data not avialbale | Galchhi | 8
529 | Dhading | Gumdi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 3
530 | Dhading | Gumdi | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 3
531 | Dhading | Gumdi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 3
532 | Dhading | Gumdi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 3
533 | Dhading | Gumdi | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 3
534 | Dhading | Gumdi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 3
535 | Dhading | Gumdi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 3
536 | Dhading | Gumdi | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 3
537 | Dhading | Gumdi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 3
538 | Dhading | Gumdi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 3
539 | Dhading | Gumdi | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 3
540 | Dhading | Gumdi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 3
541 | Dhading | Gumdi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 3
542 | Dhading | Gumdi | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 3
543 | Dhading | Gumdi | 5 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 3 | 3 | 2016-02-13 | 2016-03-28 | District Small Cottage Industry | Gangajamuna | 3
544 | Dhading | Gumdi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 3
545 | Dhading | Gumdi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 4
546 | Dhading | Gumdi | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 4
547 | Dhading | Gumdi | 6 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 4 | 4 | 2016-02-13 | 2016-03-28 |  | Gangajamuna | 4
548 | Dhading | Gumdi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 4
549 | Dhading | Gumdi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 4
550 | Dhading | Gumdi | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 4
551 | Dhading | Gumdi | 7 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 6 | 6 | 2016-02-13 | 2016-03-28 |  | Gangajamuna | 4
552 | Dhading | Gumdi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 4
553 | Dhading | Gumdi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 4
554 | Dhading | Gumdi | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 4
555 | Dhading | Gumdi | 8 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 2 | 2 | 2016-02-13 | 2016-03-28 |  | Gangajamuna | 4
556 | Dhading | Gumdi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 4
557 | Dhading | Gumdi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 4
558 | Dhading | Gumdi | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 4
559 | Dhading | Gumdi | 9 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 3 | 3 | 2016-02-13 | 2016-03-28 |  | Gangajamuna | 4
560 | Dhading | Gumdi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 4
561 | Dhading | Jeewanpur | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 4
562 | Dhading | Jeewanpur | 1 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 1 | 1 | 2015-11-30 | 2015-12-09 |  | Dhunibesi | 4
563 | Dhading | Jeewanpur | 1 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 3 | 3 | 2016-02-15 | 2016-03-10 |  | Dhunibesi | 4
564 | Dhading | Jeewanpur | 1 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-02-15 | 2016-03-10 |  | Dhunibesi | 4
565 | Dhading | Jeewanpur | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 4
566 | Dhading | Jeewanpur | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 4
567 | Dhading | Jeewanpur | 2 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 5 | 5 | 2015-11-30 | 2015-12-09 |  | Dhunibesi | 4
568 | Dhading | Jeewanpur | 2 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 6 | 6 | 2016-02-15 | 2016-03-10 |  | Dhunibesi | 4
569 | Dhading | Jeewanpur | 2 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-02-15 | 2016-03-10 |  | Dhunibesi | 4
570 | Dhading | Jeewanpur | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 4
571 | Dhading | Jeewanpur | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 4
572 | Dhading | Jeewanpur | 3 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 3 | 3 | 2015-11-30 | 2015-12-09 |  | Dhunibesi | 4
573 | Dhading | Jeewanpur | 3 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-02-15 | 2016-03-10 |  | Dhunibesi | 4
574 | Dhading | Jeewanpur | 3 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-02-15 | 2016-03-10 |  | Dhunibesi | 4
575 | Dhading | Jeewanpur | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 4
576 | Dhading | Jeewanpur | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 4
577 | Dhading | Jeewanpur | 4 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 7 | 7 | 2015-11-30 | 2015-12-09 |  | Dhunibesi | 4
578 | Dhading | Jeewanpur | 4 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-02-15 | 2016-03-10 |  | Dhunibesi | 4
579 | Dhading | Jeewanpur | 4 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-02-15 | 2016-03-10 |  | Dhunibesi | 4
580 | Dhading | Jeewanpur | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 4
581 | Dhading | Jeewanpur | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 3
582 | Dhading | Jeewanpur | 5 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 3 | 3 | 2015-11-30 | 2015-12-09 |  | Dhunibesi | 3
583 | Dhading | Jeewanpur | 5 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-02-15 | 2016-03-10 |  | Dhunibesi | 3
584 | Dhading | Jeewanpur | 5 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 3 | 3 | 2016-02-15 | 2016-03-10 |  | Dhunibesi | 3
585 | Dhading | Jeewanpur | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 3
586 | Dhading | Jeewanpur | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 3
587 | Dhading | Jeewanpur | 6 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 2 | 2 | 2015-11-30 | 2015-12-09 |  | Dhunibesi | 3
588 | Dhading | Jeewanpur | 6 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 1 | 1 | 2016-02-15 | 2016-03-10 |  | Dhunibesi | 3
589 | Dhading | Jeewanpur | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 3
590 | Dhading | Jeewanpur | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 3
591 | Dhading | Jeewanpur | 7 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 3 | 3 | 2015-11-30 | 2015-12-09 |  | Dhunibesi | 3
592 | Dhading | Jeewanpur | 7 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 5 | 5 | 2016-02-15 | 2016-03-10 |  | Dhunibesi | 3
593 | Dhading | Jeewanpur | 7 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 5 | 5 | 2016-02-15 | 2016-03-10 |  | Dhunibesi | 3
594 | Dhading | Jeewanpur | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 3
595 | Dhading | Jeewanpur | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 5
596 | Dhading | Jeewanpur | 8 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 4 | 4 | 2015-11-30 | 2015-12-09 |  | Dhunibesi | 5
597 | Dhading | Jeewanpur | 8 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-02-15 | 2016-03-10 |  | Dhunibesi | 5
598 | Dhading | Jeewanpur | 8 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 3 | 3 | 2016-02-15 | 2016-03-10 |  | Dhunibesi | 5
599 | Dhading | Jeewanpur | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 5
600 | Dhading | Jeewanpur | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 5
601 | Dhading | Jeewanpur | 9 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 2 | 2 | 2015-11-30 | 2015-12-09 |  | Dhunibesi | 5
602 | Dhading | Jeewanpur | 9 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 2 | 2 | 2016-02-15 | 2016-03-10 |  | Dhunibesi | 5
603 | Dhading | Jeewanpur | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 5
604 | Dhading | Jeewanpur | ALL | GON - DUDBC | GON - DUDBC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 27 | 27 | 2017-03-05 | 2017-03-11 | Training location is Baireni VDC hall | Dhunibesi | 4
605 | Dhading | Jeewanpur | All | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 20 | 22 | 2016-04-27 | 2016-06-11 | Submit next round of 4W | Dhunibesi | 4
606 | Dhading | Jharlang | 1 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 10 | 10 | 2016-02-11 | 2016-04-17 | Phase wise training | Khaniyabash | 1
607 | Dhading | Jharlang | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 1
608 | Dhading | Jharlang | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 1
609 | Dhading | Jharlang | 1 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-02-11 | 2016-04-17 | Phase wise training | Khaniyabash | 1
610 | Dhading | Jharlang | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 1
611 | Dhading | Jharlang | 2 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 12 | 12 | 2016-02-11 | 2016-04-17 | Phase wise training | Khaniyabash | 1
612 | Dhading | Jharlang | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 1
613 | Dhading | Jharlang | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 1
614 | Dhading | Jharlang | 2 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 12 | 12 | 2016-02-11 | 2016-04-17 | Phase wise training | Khaniyabash | 1
615 | Dhading | Jharlang | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 1
616 | Dhading | Jharlang | 3 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 28 | 28 | 2016-02-11 | 2016-04-17 | Phase wise training | Khaniyabash | 2
617 | Dhading | Jharlang | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 2
618 | Dhading | Jharlang | 3 | UMN | HIMS | UMN | Technical Assistance | Demonstration Construction | House | Demo house construction is copleted in Myminee tole of Jharlang-9 | # of constructions | Yes | Completed | 1 | 1 | 2016-06-01 | 2017-01-20 |  | Khaniyabash | 2
619 | Dhading | Jharlang | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 2
620 | Dhading | Jharlang | 3 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 28 | 28 | 2016-02-11 | 2016-04-17 | Phase wise training | Khaniyabash | 2
621 | Dhading | Jharlang | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 2
622 | Dhading | Jharlang | 4 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 1 | 1 | 2016-02-11 | 2016-04-17 | Phase wise training | Khaniyabash | 2
623 | Dhading | Jharlang | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 2
624 | Dhading | Jharlang | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 2
625 | Dhading | Jharlang | 4 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-02-11 | 2016-04-17 | Phase wise training | Khaniyabash | 2
626 | Dhading | Jharlang | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 2
627 | Dhading | Jharlang | 5 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-17 | Phase wise training | Khaniyabash | 2
628 | Dhading | Jharlang | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 2
629 | Dhading | Jharlang | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 2
630 | Dhading | Jharlang | 5 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-17 | Phase wise training | Khaniyabash | 2
631 | Dhading | Jharlang | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 2
632 | Dhading | Jharlang | 6 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-17 | Phase wise training | Khaniyabash | 2
633 | Dhading | Jharlang | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 2
634 | Dhading | Jharlang | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 2
635 | Dhading | Jharlang | 6 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-17 | Phase wise training | Khaniyabash | 2
636 | Dhading | Jharlang | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 2
637 | Dhading | Jharlang | 7 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-17 | Phase wise training | Khaniyabash | 2
638 | Dhading | Jharlang | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 2
639 | Dhading | Jharlang | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 2
640 | Dhading | Jharlang | 7 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-17 | Phase wise training | Khaniyabash | 2
641 | Dhading | Jharlang | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 2
642 | Dhading | Jharlang | 8 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 25 | 25 | 2016-02-11 | 2016-04-17 | Phase wise training | Khaniyabash | 2
643 | Dhading | Jharlang | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 2
644 | Dhading | Jharlang | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 2
645 | Dhading | Jharlang | 8 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 25 | 25 | 2016-02-11 | 2016-04-17 | Phase wise training | Khaniyabash | 2
646 | Dhading | Jharlang | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 2
647 | Dhading | Jharlang | 9 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-17 | Phase wise training | Khaniyabash | 2
648 | Dhading | Jharlang | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 2
649 | Dhading | Jharlang | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 2
650 | Dhading | Jharlang | 9 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-17 | Phase wise training | Khaniyabash | 2
651 | Dhading | Jharlang | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 2
652 | Dhading | Jharlang | All | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-17 | Ward wise data are not available | Khaniyabash | 2
653 | Dhading | Jharlang | All | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-17 | Ward wise data are not available | Khaniyabash | 2
654 | Dhading | Jogimara | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 10
655 | Dhading | Jogimara | 1 | GON - PAF | HDSC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-06-29 | 2017-07-05 |  | Benighat Rorang | 10
656 | Dhading | Jogimara | 1 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 5 | 5 | 2017-01-17 | 2017-01-23 |  | Benighat Rorang | 10
657 | Dhading | Jogimara | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 10
658 | Dhading | Jogimara | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 10
659 | Dhading | Jogimara | 2 | GON - PAF | HDSC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2017-06-29 | 2017-07-05 |  | Benighat Rorang | 10
660 | Dhading | Jogimara | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 10
661 | Dhading | Jogimara | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 10
662 | Dhading | Jogimara | 3 | GON - PAF | HDSC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-06-29 | 2017-07-05 |  | Benighat Rorang | 10
663 | Dhading | Jogimara | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 10
664 | Dhading | Jogimara | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 10
665 | Dhading | Jogimara | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 10
666 | Dhading | Jogimara | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 10
667 | Dhading | Jogimara | 5 | GON - PAF | HDSC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-06-29 | 2017-07-05 |  | Benighat Rorang | 10
668 | Dhading | Jogimara | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 10
669 | Dhading | Jogimara | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 9
670 | Dhading | Jogimara | 6 | GON - PAF | HDSC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-06-29 | 2017-07-05 |  | Benighat Rorang | 9
671 | Dhading | Jogimara | 6 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 5 | 4 | 2017-01-17 | 2017-01-23 |  | Benighat Rorang | 9
672 | Dhading | Jogimara | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 9
673 | Dhading | Jogimara | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 9
674 | Dhading | Jogimara | 7 | GON - PAF | HDSC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-06-29 | 2017-07-05 |  | Benighat Rorang | 9
675 | Dhading | Jogimara | 7 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 5 | 7 | 2017-01-17 | 2017-01-23 |  | Benighat Rorang | 9
676 | Dhading | Jogimara | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 9
677 | Dhading | Jogimara | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 9
678 | Dhading | Jogimara | 8 | GON - PAF | HDSC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-06-29 | 2017-07-05 |  | Benighat Rorang | 9
679 | Dhading | Jogimara | 8 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 5 | 5 | 2017-01-17 | 2017-01-23 |  | Benighat Rorang | 9
680 | Dhading | Jogimara | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 9
681 | Dhading | Jogimara | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 9
682 | Dhading | Jogimara | 9 | GON - PAF | HDSC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 26 | 26 | 2017-06-21 | 2017-06-27 |  | Benighat Rorang | 9
683 | Dhading | Jogimara | 9 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 5 | 3 | 2017-01-17 | 2017-01-23 |  | Benighat Rorang | 9
684 | Dhading | Jogimara | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 9
685 | Dhading | Jogimara | ALL | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 30 | 30 | 2017-01-22 | 2017-01-28 |  | Benighat Rorang | 10
686 | Dhading | Jyamrung | 1 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 4 | 4 | 2016-10-22 | 2016-11-12 |  | Nilakantha | 11
687 | Dhading | Jyamrung | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 229 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
688 | Dhading | Jyamrung | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
689 | Dhading | Jyamrung | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 194 | 5 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
690 | Dhading | Jyamrung | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 194 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
691 | Dhading | Jyamrung | 1 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-22 | 2016-11-12 |  | Nilakantha | 11
692 | Dhading | Jyamrung | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 16 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
693 | Dhading | Jyamrung | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
694 | Dhading | Jyamrung | 2 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 16 | 16 | 2016-10-22 | 2016-11-12 |  | Nilakantha | 11
695 | Dhading | Jyamrung | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 135 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
696 | Dhading | Jyamrung | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
697 | Dhading | Jyamrung | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 194 | 8 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
698 | Dhading | Jyamrung | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 194 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
699 | Dhading | Jyamrung | 2 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 16 | 16 | 2016-10-22 | 2016-11-12 |  | Nilakantha | 11
700 | Dhading | Jyamrung | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
701 | Dhading | Jyamrung | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
702 | Dhading | Jyamrung | 3 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 3 | 3 | 2016-10-22 | 2016-11-12 |  | Nilakantha | 11
703 | Dhading | Jyamrung | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 184 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
704 | Dhading | Jyamrung | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
705 | Dhading | Jyamrung | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 157 | 10 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
706 | Dhading | Jyamrung | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 157 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
707 | Dhading | Jyamrung | 3 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-10-22 | 2016-11-12 |  | Nilakantha | 11
708 | Dhading | Jyamrung | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
709 | Dhading | Jyamrung | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
710 | Dhading | Jyamrung | 4 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 5 | 5 | 2016-10-22 | 2016-11-12 |  | Nilakantha | 10
711 | Dhading | Jyamrung | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 160 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
712 | Dhading | Jyamrung | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
713 | Dhading | Jyamrung | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 278 | 25 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
714 | Dhading | Jyamrung | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 278 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
715 | Dhading | Jyamrung | 4 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-22 | 2016-11-12 |  | Nilakantha | 10
716 | Dhading | Jyamrung | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 35 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
717 | Dhading | Jyamrung | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
718 | Dhading | Jyamrung | 5 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 2 | 2 | 2016-10-22 | 2016-11-12 |  | Nilakantha | 10
719 | Dhading | Jyamrung | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 87 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
720 | Dhading | Jyamrung | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
721 | Dhading | Jyamrung | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 175 | 14 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
722 | Dhading | Jyamrung | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 175 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
723 | Dhading | Jyamrung | 5 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-10-22 | 2016-11-12 |  | Nilakantha | 10
724 | Dhading | Jyamrung | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
725 | Dhading | Jyamrung | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
726 | Dhading | Jyamrung | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 129 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
727 | Dhading | Jyamrung | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
728 | Dhading | Jyamrung | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 252 | 5 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
729 | Dhading | Jyamrung | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 252 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
730 | Dhading | Jyamrung | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
731 | Dhading | Jyamrung | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
732 | Dhading | Jyamrung | 7 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 4 | 4 | 2016-10-22 | 2016-11-12 |  | Nilakantha | 10
733 | Dhading | Jyamrung | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 147 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
734 | Dhading | Jyamrung | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
735 | Dhading | Jyamrung | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 130 | 14 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
736 | Dhading | Jyamrung | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 130 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
737 | Dhading | Jyamrung | 7 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-22 | 2016-11-12 |  | Nilakantha | 10
738 | Dhading | Jyamrung | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
739 | Dhading | Jyamrung | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 10
740 | Dhading | Jyamrung | 8 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 9 | 9 | 2016-10-22 | 2016-11-12 |  | Nilakantha | 11
741 | Dhading | Jyamrung | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 310 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
742 | Dhading | Jyamrung | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
743 | Dhading | Jyamrung | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 246 | 13 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
744 | Dhading | Jyamrung | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 246 | 31 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
745 | Dhading | Jyamrung | 8 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 9 | 9 | 2016-10-22 | 2016-11-12 |  | Nilakantha | 11
746 | Dhading | Jyamrung | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 14 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
747 | Dhading | Jyamrung | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
748 | Dhading | Jyamrung | 9 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-11-12 |  | Nilakantha | 11
749 | Dhading | Jyamrung | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 150 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
750 | Dhading | Jyamrung | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
751 | Dhading | Jyamrung | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 225 | 22 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
752 | Dhading | Jyamrung | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 225 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
753 | Dhading | Jyamrung | 9 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-11-12 |  | Nilakantha | 11
754 | Dhading | Jyamrung | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 14 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
755 | Dhading | Jyamrung | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 11
756 | Dhading | Kalleri | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 178 | 2015-10-01 | 2020-09-30 |  | Galchhi | 1
757 | Dhading | Kalleri | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 1
758 | Dhading | Kalleri | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 232 | 3 | 2015-10-01 | 2020-09-30 |  | Galchhi | 1
759 | Dhading | Kalleri | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 232 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 1
760 | Dhading | Kalleri | 1 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-11-25 | 2015-11-29 |  | Galchhi | 1
761 | Dhading | Kalleri | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30 |  | Galchhi | 1
762 | Dhading | Kalleri | 1 | HELVETAS | RIMC | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Galchhi | 1
763 | Dhading | Kalleri | 1 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 10 | 10 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Galchhi | 1
764 | Dhading | Kalleri | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 1
765 | Dhading | Kalleri | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 136 | 2015-10-01 | 2020-09-30 |  | Galchhi | 1
766 | Dhading | Kalleri | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 1
767 | Dhading | Kalleri | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 282 | 1 | 2015-10-01 | 2020-09-30 |  | Galchhi | 1
768 | Dhading | Kalleri | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 282 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 1
769 | Dhading | Kalleri | 2 | GON - PAF | ICDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-06-17 | 2017-06-23 |  | Galchhi | 1
770 | Dhading | Kalleri | 2 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 2 | 2 | 2015-11-25 | 2015-11-29 |  | Galchhi | 1
771 | Dhading | Kalleri | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30 |  | Galchhi | 1
772 | Dhading | Kalleri | 2 | HELVETAS | RIMC | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 12 | 12 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Galchhi | 1
773 | Dhading | Kalleri | 2 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 17 | 17 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Galchhi | 1
774 | Dhading | Kalleri | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 1
775 | Dhading | Kalleri | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 165 | 2015-10-01 | 2020-09-30 |  | Galchhi | 1
776 | Dhading | Kalleri | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 1
777 | Dhading | Kalleri | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 324 | 6 | 2015-10-01 | 2020-09-30 |  | Galchhi | 1
778 | Dhading | Kalleri | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 324 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 1
779 | Dhading | Kalleri | 3 | GON - PAF | ICDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-06-17 | 2017-06-23 |  | Galchhi | 1
780 | Dhading | Kalleri | 3 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 5 | 5 | 2015-11-25 | 2015-11-29 |  | Galchhi | 1
781 | Dhading | Kalleri | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30 |  | Galchhi | 1
782 | Dhading | Kalleri | 3 | HELVETAS | RIMC | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 6 | 6 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Galchhi | 1
783 | Dhading | Kalleri | 3 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 4 | 4 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Galchhi | 1
784 | Dhading | Kalleri | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 1
785 | Dhading | Kalleri | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 370 | 2015-10-01 | 2020-09-30 |  | Galchhi | 2
786 | Dhading | Kalleri | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 2
787 | Dhading | Kalleri | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 305 | 33 | 2015-10-01 | 2020-09-30 |  | Galchhi | 2
788 | Dhading | Kalleri | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 305 | 35 | 2015-10-01 | 2020-09-30 |  | Galchhi | 2
789 | Dhading | Kalleri | 4 | GON - PAF | ICDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-06-17 | 2017-06-23 |  | Galchhi | 2
790 | Dhading | Kalleri | 4 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 12 | 12 | 2015-11-25 | 2015-11-29 |  | Galchhi | 2
791 | Dhading | Kalleri | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 17 | 2015-10-01 | 2020-09-30 |  | Galchhi | 2
792 | Dhading | Kalleri | 4 | HELVETAS | RIMC | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 10 | 10 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Galchhi | 2
793 | Dhading | Kalleri | 4 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 22 | 22 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Galchhi | 2
794 | Dhading | Kalleri | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 2
795 | Dhading | Kalleri | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 225 | 2015-10-01 | 2020-09-30 |  | Galchhi | 2
796 | Dhading | Kalleri | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 2
797 | Dhading | Kalleri | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 161 | 16 | 2015-10-01 | 2020-09-30 |  | Galchhi | 2
798 | Dhading | Kalleri | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 161 | 15 | 2015-10-01 | 2020-09-30 |  | Galchhi | 2
799 | Dhading | Kalleri | 5 | GON - PAF | ICDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2017-06-17 | 2017-06-23 |  | Galchhi | 2
800 | Dhading | Kalleri | 5 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 10 | 10 | 2015-11-25 | 2015-11-29 |  | Galchhi | 2
801 | Dhading | Kalleri | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 14 | 2015-10-01 | 2020-09-30 |  | Galchhi | 2
802 | Dhading | Kalleri | 5 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 6 | 6 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Galchhi | 2
803 | Dhading | Kalleri | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 2
804 | Dhading | Kalleri | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 159 | 2015-10-01 | 2020-09-30 |  | Galchhi | 2
805 | Dhading | Kalleri | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 2
806 | Dhading | Kalleri | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 339 | 26 | 2015-10-01 | 2020-09-30 |  | Galchhi | 2
807 | Dhading | Kalleri | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 339 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 2
808 | Dhading | Kalleri | 6 | GON - PAF | ICDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2017-06-17 | 2017-06-23 |  | Galchhi | 2
809 | Dhading | Kalleri | 6 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 3 | 3 | 2015-11-25 | 2015-11-29 |  | Galchhi | 2
810 | Dhading | Kalleri | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 11 | 2015-10-01 | 2020-09-30 |  | Galchhi | 2
811 | Dhading | Kalleri | 6 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 16 | 16 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Galchhi | 2
812 | Dhading | Kalleri | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 2
813 | Dhading | Kalleri | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 100 | 2015-10-01 | 2020-09-30 |  | Galchhi | 3
814 | Dhading | Kalleri | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 3
815 | Dhading | Kalleri | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 126 | 13 | 2015-10-01 | 2020-09-30 |  | Galchhi | 3
816 | Dhading | Kalleri | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 126 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 3
817 | Dhading | Kalleri | 7 | GON - PAF | ICDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-06-17 | 2017-06-23 |  | Galchhi | 3
818 | Dhading | Kalleri | 7 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 12 | 12 | 2015-11-25 | 2015-11-29 |  | Galchhi | 3
819 | Dhading | Kalleri | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 16 | 2015-10-01 | 2020-09-30 |  | Galchhi | 3
820 | Dhading | Kalleri | 7 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 5 | 5 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Galchhi | 3
821 | Dhading | Kalleri | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 3
822 | Dhading | Kalleri | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 173 | 2015-10-01 | 2020-09-30 |  | Galchhi | 3
823 | Dhading | Kalleri | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 3
824 | Dhading | Kalleri | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 225 | 10 | 2015-10-01 | 2020-09-30 |  | Galchhi | 3
825 | Dhading | Kalleri | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 225 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 3
826 | Dhading | Kalleri | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 26 | 2015-10-01 | 2020-09-30 |  | Galchhi | 3
827 | Dhading | Kalleri | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 3
828 | Dhading | Kalleri | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 46 | 2015-10-01 | 2020-09-30 |  | Galchhi | 3
829 | Dhading | Kalleri | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 3
830 | Dhading | Kalleri | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 174 | 7 | 2015-10-01 | 2020-09-30 |  | Galchhi | 3
831 | Dhading | Kalleri | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 174 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 3
832 | Dhading | Kalleri | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 7 | 2015-10-01 | 2020-09-30 |  | Galchhi | 3
833 | Dhading | Kalleri | 9 | HELVETAS | RIMC | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Galchhi | 3
834 | Dhading | Kalleri | 9 | HELVETAS | RIMC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-25 | 2016-08-18 | Implementing partner = Rural Infrastructure and Management Consultant (RIMC) Pvt Ltd | Galchhi | 3
835 | Dhading | Kalleri | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Galchhi | 3
836 | Dhading | Kalleri | All | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-11-25 | 2015-11-29 | Ward wise data not avialbale | Galchhi | 3
837 | Dhading | Katunje | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 4
838 | Dhading | Katunje | 1 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 4
839 | Dhading | Katunje | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 4
840 | Dhading | Katunje | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 4
841 | Dhading | Katunje | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-10-18 | 2016-12-26 |  | Netrawati | 4
842 | Dhading | Katunje | 2 | HELVETAS | JAYAN | SDC | Training | Vocational training | Electrician (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 6 | 6 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 4
843 | Dhading | Katunje | 2 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 12 | 12 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 4
844 | Dhading | Katunje | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 4
845 | Dhading | Katunje | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 4
846 | Dhading | Katunje | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-10-18 | 2016-12-26 |  | Netrawati | 4
847 | Dhading | Katunje | 3 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 4
848 | Dhading | Katunje | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 4
849 | Dhading | Katunje | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 4
850 | Dhading | Katunje | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 23 | 23 | 2016-10-18 | 2016-12-26 |  | Netrawati | 4
851 | Dhading | Katunje | 4 | HELVETAS | JAYAN | SDC | Training | Vocational training | Electrician (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 4
852 | Dhading | Katunje | 4 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 13 | 13 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 4
853 | Dhading | Katunje | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 4
854 | Dhading | Katunje | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 5
855 | Dhading | Katunje | 7 | ASF | POURAKHI | CARITAS-L | Technical Assistance | Demonstration Construction | House & Toilet |  | # of constructions | Yes | Completed | 1 | 1 | 2017-05-18 | 2017-06-18 |  | Netrawati | 5
856 | Dhading | Katunje | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Netrawati | 5
857 | Dhading | Katunje | 5 | HELVETAS | JAYAN | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 8 | 8 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 5
858 | Dhading | Katunje | 5 | HELVETAS | JAYAN | SDC | Training | Vocational training | Electrician (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 5
859 | Dhading | Katunje | 5 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 11 | 11 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 5
860 | Dhading | Katunje | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 5
861 | Dhading | Katunje | 7 | ASF | POURAKHI | CARITAS-L | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 25 | 2017-05-18 | 2017-07-18 |  | Netrawati | 5
862 | Dhading | Katunje | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 5
863 | Dhading | Katunje | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 37 | 37 | 2016-10-18 | 2016-12-26 |  | Netrawati | 5
864 | Dhading | Katunje | 6 | HELVETAS | JAYAN | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 10 | 10 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 5
865 | Dhading | Katunje | 6 | HELVETAS | JAYAN | SDC | Training | Vocational training | Electrician (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 5
866 | Dhading | Katunje | 6 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 33 | 33 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 5
867 | Dhading | Katunje | 6 | HELVETAS | JAYAN | SDC | Training | Vocational training | Plumber (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 5
868 | Dhading | Katunje | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 5
869 | Dhading | Katunje | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 5
870 | Dhading | Katunje | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Netrawati | 5
871 | Dhading | Katunje | 7 | HELVETAS | JAYAN | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 5
872 | Dhading | Katunje | 7 | HELVETAS | JAYAN | SDC | Training | Vocational training | Electrician (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 5
873 | Dhading | Katunje | 7 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 12 | 12 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 5
874 | Dhading | Katunje | 7 | HELVETAS | JAYAN | SDC | Training | Vocational training | Plumber (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 4 | 4 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 5
875 | Dhading | Katunje | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 5
876 | Dhading | Katunje | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 5
877 | Dhading | Katunje | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Netrawati | 5
878 | Dhading | Katunje | 8 | HELVETAS | JAYAN | SDC | Training | Vocational training | Electrician (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 5
879 | Dhading | Katunje | 8 | HELVETAS | JAYAN | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 22 | 22 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 5
880 | Dhading | Katunje | 8 | HELVETAS | JAYAN | SDC | Training | Vocational training | Plumber (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 5
881 | Dhading | Katunje | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 5
882 | Dhading | Katunje | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 5
883 | Dhading | Katunje | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Netrawati | 5
884 | Dhading | Katunje | 9 | HELVETAS | JAYAN | SDC | Training | Vocational training | Electrician (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 5
885 | Dhading | Katunje | 9 | HELVETAS | JAYAN | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 4 | 4 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 5
886 | Dhading | Katunje | 9 | HELVETAS | JAYAN | SDC | Training | Vocational training | Plumber (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-08-30 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Netrawati | 5
887 | Dhading | Katunje | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 5
888 | Dhading | Kewalpur | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 9
889 | Dhading | Kewalpur | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 9
890 | Dhading | Kewalpur | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 9
891 | Dhading | Kewalpur | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 9
892 | Dhading | Kewalpur | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 10
893 | Dhading | Kewalpur | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 10
894 | Dhading | Kewalpur | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 10
895 | Dhading | Kewalpur | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 10
896 | Dhading | Kewalpur | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 10
897 | Dhading | Kewalpur | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 10
898 | Dhading | Kewalpur | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 10
899 | Dhading | Kewalpur | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 10
900 | Dhading | Kewalpur | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 10
901 | Dhading | Kewalpur | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 10
902 | Dhading | Kewalpur | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 9
903 | Dhading | Kewalpur | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 9
904 | Dhading | Kewalpur | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 9
905 | Dhading | Kewalpur | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 9
906 | Dhading | Kewalpur | All | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 60 | 58 | 2015-11-24 | 2015-11-28 | Ward wise data not avialbale | Thakre | 10
907 | Dhading | Khalte | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 64 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
908 | Dhading | Khalte | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
909 | Dhading | Khalte | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 147 | 15 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
910 | Dhading | Khalte | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 147 | 10 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
911 | Dhading | Khalte | 1 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-12-01 | 2015-12-05 |  | Nilakantha | 1
912 | Dhading | Khalte | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
913 | Dhading | Khalte | 1 | HELVETAS | JAYAN | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN) | Nilakantha | 1
914 | Dhading | Khalte | 1 | HELVETAS | JAYAN | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 8 | 8 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN) | Nilakantha | 1
915 | Dhading | Khalte | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
916 | Dhading | Khalte | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 142 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
917 | Dhading | Khalte | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
918 | Dhading | Khalte | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 117 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
919 | Dhading | Khalte | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 117 | 15 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
920 | Dhading | Khalte | 2 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-01 | 2015-12-05 |  | Nilakantha | 5
921 | Dhading | Khalte | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
922 | Dhading | Khalte | 2 | HELVETAS | JAYAN | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 5 | 5 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN) | Nilakantha | 5
923 | Dhading | Khalte | 2 | HELVETAS | JAYAN | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN) | Nilakantha | 5
924 | Dhading | Khalte | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
925 | Dhading | Khalte | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 134 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
926 | Dhading | Khalte | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
927 | Dhading | Khalte | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 168 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
928 | Dhading | Khalte | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 168 | 8 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
929 | Dhading | Khalte | 3 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-01 | 2015-12-05 |  | Nilakantha | 5
930 | Dhading | Khalte | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
931 | Dhading | Khalte | 3 | HELVETAS | JAYAN | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN) | Nilakantha | 5
932 | Dhading | Khalte | 3 | HELVETAS | JAYAN | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN) | Nilakantha | 5
933 | Dhading | Khalte | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
934 | Dhading | Khalte | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 92 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
935 | Dhading | Khalte | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
936 | Dhading | Khalte | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 223 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
937 | Dhading | Khalte | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 223 | 5 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
938 | Dhading | Khalte | 4 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 8 | 8 | 2015-12-01 | 2015-12-05 |  | Nilakantha | 5
939 | Dhading | Khalte | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 1 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
940 | Dhading | Khalte | 4 | HELVETAS | JAYAN | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 4 | 4 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN) | Nilakantha | 5
941 | Dhading | Khalte | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
942 | Dhading | Khalte | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 214 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
943 | Dhading | Khalte | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
944 | Dhading | Khalte | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 251 | 41 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
945 | Dhading | Khalte | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 251 | 20 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
946 | Dhading | Khalte | 5 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-01 | 2015-12-05 |  | Nilakantha | 5
947 | Dhading | Khalte | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 41 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
948 | Dhading | Khalte | 5 | HELVETAS | JAYAN | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 4 | 4 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN) | Nilakantha | 5
949 | Dhading | Khalte | 5 | HELVETAS | JAYAN | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 19 | 19 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN) | Nilakantha | 5
950 | Dhading | Khalte | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
951 | Dhading | Khalte | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 307 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
952 | Dhading | Khalte | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
953 | Dhading | Khalte | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 293 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
954 | Dhading | Khalte | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 293 | 69 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
955 | Dhading | Khalte | 6 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 9 | 9 | 2015-12-01 | 2015-12-05 |  | Nilakantha | 5
956 | Dhading | Khalte | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 10 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
957 | Dhading | Khalte | 6 | HELVETAS | JAYAN | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 7 | 7 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN) | Nilakantha | 5
958 | Dhading | Khalte | 6 | HELVETAS | JAYAN | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 29 | 29 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN) | Nilakantha | 5
959 | Dhading | Khalte | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 5
960 | Dhading | Khalte | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 125 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
961 | Dhading | Khalte | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
962 | Dhading | Khalte | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 107 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
963 | Dhading | Khalte | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 107 | 12 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
964 | Dhading | Khalte | 7 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-12-01 | 2015-12-05 |  | Nilakantha | 1
965 | Dhading | Khalte | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 33 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
966 | Dhading | Khalte | 7 | HELVETAS | JAYAN | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 4 | 4 | 2015-12-22 | 2016-08-30 | Imlementing Partner = Jayan Technical College of Technology (JAYAN) | Nilakantha | 1
967 | Dhading | Khalte | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
968 | Dhading | Khalte | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 84 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
969 | Dhading | Khalte | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
970 | Dhading | Khalte | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 72 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
971 | Dhading | Khalte | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 72 | 15 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
972 | Dhading | Khalte | 8 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-12-01 | 2015-12-05 |  | Nilakantha | 1
973 | Dhading | Khalte | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
974 | Dhading | Khalte | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
975 | Dhading | Khalte | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 51 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
976 | Dhading | Khalte | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
977 | Dhading | Khalte | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 116 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
978 | Dhading | Khalte | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 116 | 12 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
979 | Dhading | Khalte | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 33 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
980 | Dhading | Khalte | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 1
981 | Dhading | Khari | 1 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 15 | 15 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 5
982 | Dhading | Khari | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 5
983 | Dhading | Khari | 1 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 15 | 15 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 5
984 | Dhading | Khari | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 5
985 | Dhading | Khari | 2 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 5
986 | Dhading | Khari | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 5
987 | Dhading | Khari | 2 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 5
988 | Dhading | Khari | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 5
989 | Dhading | Khari | 3 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 11 | 11 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 5
990 | Dhading | Khari | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 5
991 | Dhading | Khari | 3 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 5
992 | Dhading | Khari | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 5
993 | Dhading | Khari | 4 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 5
994 | Dhading | Khari | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 5
995 | Dhading | Khari | 4 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 5
996 | Dhading | Khari | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 5
997 | Dhading | Khari | 5 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 8 | 8 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 5
998 | Dhading | Khari | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 5
999 | Dhading | Khari | 5 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 5
1000 | Dhading | Khari | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 5
1001 | Dhading | Khari | 6 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 6 | 6 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 5
1002 | Dhading | Khari | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 5
1003 | Dhading | Khari | 6 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 5
1004 | Dhading | Khari | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 5
1005 | Dhading | Khari | 7 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 6 | 6 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 5
1006 | Dhading | Khari | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 5
1007 | Dhading | Khari | 7 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 5
1008 | Dhading | Khari | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 5
1009 | Dhading | Khari | 8 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 5
1010 | Dhading | Khari | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 5
1011 | Dhading | Khari | 8 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 5
1012 | Dhading | Khari | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 5
1013 | Dhading | Khari | 9 | CA | FOCUS | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkit is distributed after mason training | # of kits | Yes | Completed | 8 | 8 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 5
1014 | Dhading | Khari | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 5
1015 | Dhading | Khari | 9 | CA | FOCUS | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (7 days DUDBC, Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-10-22 | 2016-11-12 |  | Jwalamukhi | 5
1016 | Dhading | Khari | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 5
1017 | Dhading | Kiranchok | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 8
1018 | Dhading | Kiranchok | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 8
1019 | Dhading | Kiranchok | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 8
1020 | Dhading | Kiranchok | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 8
1021 | Dhading | Kiranchok | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 8
1022 | Dhading | Kiranchok | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 8
1023 | Dhading | Kiranchok | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 8
1024 | Dhading | Kiranchok | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 8
1025 | Dhading | Kiranchok | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 8
1026 | Dhading | Kiranchok | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 8
1027 | Dhading | Kiranchok | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 7
1028 | Dhading | Kiranchok | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 7
1029 | Dhading | Kiranchok | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 7
1030 | Dhading | Kiranchok | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 7
1031 | Dhading | Kiranchok | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 7
1032 | Dhading | Kiranchok | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 7
1033 | Dhading | Kiranchok | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 7
1034 | Dhading | Kiranchok | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 7
1035 | Dhading | Kumpur | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 42 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 6
1036 | Dhading | Kumpur | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 6
1037 | Dhading | Kumpur | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 130 | 9 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 6
1038 | Dhading | Kumpur | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 130 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 6
1039 | Dhading | Kumpur | 1 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-12-01 | 2015-12-04 |  | Siddhalek | 6
1040 | Dhading | Kumpur | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 6
1041 | Dhading | Kumpur | 1 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 19 | 19 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Siddhalek | 6
1042 | Dhading | Kumpur | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 6
1043 | Dhading | Kumpur | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 229 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 5
1044 | Dhading | Kumpur | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 5
1045 | Dhading | Kumpur | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 271 | 11 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 5
1046 | Dhading | Kumpur | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 271 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 5
1047 | Dhading | Kumpur | 2 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-01 | 2015-12-04 |  | Siddhalek | 5
1048 | Dhading | Kumpur | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 33 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 5
1049 | Dhading | Kumpur | 2 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 11 | 11 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Siddhalek | 5
1050 | Dhading | Kumpur | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 5
1051 | Dhading | Kumpur | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 203 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 6
1052 | Dhading | Kumpur | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 6
1053 | Dhading | Kumpur | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 261 | 18 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 6
1054 | Dhading | Kumpur | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 261 | 50 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 6
1055 | Dhading | Kumpur | 3 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 5 | 5 | 2015-12-01 | 2015-12-04 |  | Siddhalek | 6
1056 | Dhading | Kumpur | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 6
1057 | Dhading | Kumpur | 3 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Siddhalek | 6
1058 | Dhading | Kumpur | 3 | HELVETAS | MSED | SDC | Training | Vocational training | Plumber (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Siddhalek | 6
1059 | Dhading | Kumpur | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 6
1060 | Dhading | Kumpur | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 193 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 6
1061 | Dhading | Kumpur | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 6
1062 | Dhading | Kumpur | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 275 | 3 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 6
1063 | Dhading | Kumpur | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 275 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 6
1064 | Dhading | Kumpur | 4 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-01 | 2015-12-04 |  | Siddhalek | 6
1065 | Dhading | Kumpur | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 6
1066 | Dhading | Kumpur | 4 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 5 | 5 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Siddhalek | 6
1067 | Dhading | Kumpur | 4 | HELVETAS | MSED | SDC | Training | Vocational training | Plumber (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 6 | 6 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Siddhalek | 6
1068 | Dhading | Kumpur | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 6
1069 | Dhading | Kumpur | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 162 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 7
1070 | Dhading | Kumpur | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 7
1071 | Dhading | Kumpur | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 381 | 8 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 7
1072 | Dhading | Kumpur | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 381 | 29 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 7
1073 | Dhading | Kumpur | 5 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-12-01 | 2015-12-04 |  | Siddhalek | 7
1074 | Dhading | Kumpur | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 7
1075 | Dhading | Kumpur | 5 | HELVETAS | MSED | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 9 | 9 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Siddhalek | 7
1076 | Dhading | Kumpur | 5 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 10 | 10 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Siddhalek | 7
1077 | Dhading | Kumpur | 5 | HELVETAS | MSED | SDC | Training | Vocational training | Plumber (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Siddhalek | 7
1078 | Dhading | Kumpur | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 7
1079 | Dhading | Kumpur | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 41 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 7
1080 | Dhading | Kumpur | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 7
1081 | Dhading | Kumpur | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 228 | 33 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 7
1082 | Dhading | Kumpur | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 228 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 7
1083 | Dhading | Kumpur | 6 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-12-01 | 2015-12-04 |  | Siddhalek | 7
1084 | Dhading | Kumpur | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 6 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 7
1085 | Dhading | Kumpur | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 7
1086 | Dhading | Kumpur | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 370 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 7
1087 | Dhading | Kumpur | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 7
1088 | Dhading | Kumpur | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 396 | 31 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 7
1089 | Dhading | Kumpur | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 396 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 7
1090 | Dhading | Kumpur | 7 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 8 | 8 | 2015-12-01 | 2015-12-04 |  | Siddhalek | 7
1091 | Dhading | Kumpur | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 7
1092 | Dhading | Kumpur | 7 | HELVETAS | MSED | SDC | Training | Vocational training | Carpenter (CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 1 | 1 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Siddhalek | 7
1093 | Dhading | Kumpur | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 7
1094 | Dhading | Kumpur | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 217 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 5
1095 | Dhading | Kumpur | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 5
1096 | Dhading | Kumpur | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 226 | 7 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 5
1097 | Dhading | Kumpur | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 226 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 5
1098 | Dhading | Kumpur | 8 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-12-01 | 2015-12-04 |  | Siddhalek | 5
1099 | Dhading | Kumpur | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 38 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 5
1100 | Dhading | Kumpur | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 5
1101 | Dhading | Kumpur | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 114 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 5
1102 | Dhading | Kumpur | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 5
1103 | Dhading | Kumpur | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 183 | 11 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 5
1104 | Dhading | Kumpur | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 183 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 5
1105 | Dhading | Kumpur | 9 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-01 | 2015-12-04 |  | Siddhalek | 5
1106 | Dhading | Kumpur | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 8 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 5
1107 | Dhading | Kumpur | 9 | HELVETAS | MSED | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days 320 Hrs Vocational skill Training EQ Resilient | # of trainees | Yes | Completed | 3 | 3 | 2015-12-22 | 2016-08-10 | Implementing Partner = Multi Skill & Environment Development Pvt. Ltd. (MSED) | Siddhalek | 5
1108 | Dhading | Kumpur | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 5
1109 | Dhading | Lapa | 1 | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 11 | 11 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day | Rubi Valley | 5
1110 | Dhading | Lapa | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 5
1111 | Dhading | Lapa | 1 | UMN | NRDS | UMN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-12-10 | 2017-06-02 |  | Rubi Valley | 5
1112 | Dhading | Lapa | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 5
1113 | Dhading | Lapa | 1 | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day | Rubi Valley | 5
1114 | Dhading | Lapa | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 5
1115 | Dhading | Lapa | 2 | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 27 | 27 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day | Rubi Valley | 5
1116 | Dhading | Lapa | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 5
1117 | Dhading | Lapa | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 5
1118 | Dhading | Lapa | 2 | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 27 | 27 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day | Rubi Valley | 5
1119 | Dhading | Lapa | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 5
1120 | Dhading | Lapa | 3 | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 16 | 16 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day | Rubi Valley | 5
1121 | Dhading | Lapa | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 5
1122 | Dhading | Lapa | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 5
1123 | Dhading | Lapa | 3 | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 16 | 16 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day | Rubi Valley | 5
1124 | Dhading | Lapa | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 5
1125 | Dhading | Lapa | 4 | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 3 | 3 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day | Rubi Valley | 5
1126 | Dhading | Lapa | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 5
1127 | Dhading | Lapa | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 5
1128 | Dhading | Lapa | 4 | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day | Rubi Valley | 5
1129 | Dhading | Lapa | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 5
1130 | Dhading | Lapa | 5 | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 1 | 1 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day | Rubi Valley | 5
1131 | Dhading | Lapa | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 5
1132 | Dhading | Lapa | 5 | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day | Rubi Valley | 5
1133 | Dhading | Lapa | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 5
1134 | Dhading | Lapa | 6 | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day | Rubi Valley | 5
1135 | Dhading | Lapa | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 5
1136 | Dhading | Lapa | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 5
1137 | Dhading | Lapa | 6 | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day | Rubi Valley | 5
1138 | Dhading | Lapa | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 5
1139 | Dhading | Lapa | 7 | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 27 | 27 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day | Rubi Valley | 6
1140 | Dhading | Lapa | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 6
1141 | Dhading | Lapa | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 6
1142 | Dhading | Lapa | 7 | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 27 | 27 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day | Rubi Valley | 6
1143 | Dhading | Lapa | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 6
1144 | Dhading | Lapa | 8 | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day | Rubi Valley | 6
1145 | Dhading | Lapa | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 6
1146 | Dhading | Lapa | 8 | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day | Rubi Valley | 6
1147 | Dhading | Lapa | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 6
1148 | Dhading | Lapa | 9 | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day | Rubi Valley | 6
1149 | Dhading | Lapa | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 6
1150 | Dhading | Lapa | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 6
1151 | Dhading | Lapa | 9 | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-04-16 | Phase wise training of 7 day | Rubi Valley | 6
1152 | Dhading | Lapa | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 6
1153 | Dhading | Lapa | All | UMN | NRDS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 1 | 1 | 2016-02-11 | 2016-04-16 | Ward wise data are not available | Rubi Valley | 5
1154 | Dhading | Lapa | All | UMN | NRDS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-02-11 | 2016-04-16 | Ward wise data are not available | Rubi Valley | 5
1155 | Dhading | Mahadevsthan | 1 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Benighat Rorang | 2
1156 | Dhading | Mahadevsthan | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 2
1157 | Dhading | Mahadevsthan | 1 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 27 | 27 | 2015-12-03 | 2015-12-07 |  | Benighat Rorang | 2
1158 | Dhading | Mahadevsthan | 1 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Benighat Rorang | 2
1159 | Dhading | Mahadevsthan | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 2
1160 | Dhading | Mahadevsthan | 2 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Benighat Rorang | 2
1161 | Dhading | Mahadevsthan | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 2
1162 | Dhading | Mahadevsthan | 2 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 4 | 4 | 2015-12-03 | 2015-12-07 |  | Benighat Rorang | 2
1163 | Dhading | Mahadevsthan | 2 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Benighat Rorang | 2
1164 | Dhading | Mahadevsthan | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 2
1165 | Dhading | Mahadevsthan | 3 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Benighat Rorang | 2
1166 | Dhading | Mahadevsthan | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 2
1167 | Dhading | Mahadevsthan | 3 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 2 | 2 | 2015-12-03 | 2015-12-07 |  | Benighat Rorang | 2
1168 | Dhading | Mahadevsthan | 3 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Benighat Rorang | 2
1169 | Dhading | Mahadevsthan | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 2
1170 | Dhading | Mahadevsthan | 4 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 16 | 16 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Benighat Rorang | 2
1171 | Dhading | Mahadevsthan | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 2
1172 | Dhading | Mahadevsthan | 4 | UMN | PRAYAS-N | UMN | Technical Assistance | Demonstration Construction | House | Demo house construction is copleted in Talti tole of Mahadevsthan-4 | # of constructions | Yes | Completed | 1 | 1 | 2016-08-10 | 2016-12-15 |  | Benighat Rorang | 2
1173 | Dhading | Mahadevsthan | 4 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 4 | 4 | 2015-12-03 | 2015-12-07 |  | Benighat Rorang | 2
1174 | Dhading | Mahadevsthan | 4 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 16 | 16 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Benighat Rorang | 2
1175 | Dhading | Mahadevsthan | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 2
1176 | Dhading | Mahadevsthan | 5 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Benighat Rorang | 2
1177 | Dhading | Mahadevsthan | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 2
1178 | Dhading | Mahadevsthan | 5 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 4 | 4 | 2015-12-03 | 2015-12-07 |  | Benighat Rorang | 2
1179 | Dhading | Mahadevsthan | 5 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Benighat Rorang | 2
1180 | Dhading | Mahadevsthan | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 2
1181 | Dhading | Mahadevsthan | 6 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 26 | 26 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Benighat Rorang | 1
1182 | Dhading | Mahadevsthan | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 1
1183 | Dhading | Mahadevsthan | 6 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 4 | 4 | 2015-12-03 | 2015-12-07 |  | Benighat Rorang | 1
1184 | Dhading | Mahadevsthan | 6 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 26 | 26 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Benighat Rorang | 1
1185 | Dhading | Mahadevsthan | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 1
1186 | Dhading | Mahadevsthan | 7 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Benighat Rorang | 1
1187 | Dhading | Mahadevsthan | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 1
1188 | Dhading | Mahadevsthan | 7 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-03 | 2015-12-07 |  | Benighat Rorang | 1
1189 | Dhading | Mahadevsthan | 7 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Benighat Rorang | 1
1190 | Dhading | Mahadevsthan | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 1
1191 | Dhading | Mahadevsthan | 8 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 10 | 10 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Benighat Rorang | 1
1192 | Dhading | Mahadevsthan | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 1
1193 | Dhading | Mahadevsthan | 8 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 4 | 4 | 2015-12-03 | 2015-12-07 |  | Benighat Rorang | 1
1194 | Dhading | Mahadevsthan | 8 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Benighat Rorang | 1
1195 | Dhading | Mahadevsthan | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 1
1196 | Dhading | Mahadevsthan | 9 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 14 | 14 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Benighat Rorang | 1
1197 | Dhading | Mahadevsthan | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 1
1198 | Dhading | Mahadevsthan | 9 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 3 | 3 | 2015-12-03 | 2015-12-07 |  | Benighat Rorang | 1
1199 | Dhading | Mahadevsthan | 9 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 14 | 14 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Benighat Rorang | 1
1200 | Dhading | Mahadevsthan | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Benighat Rorang | 1
1201 | Dhading | Mahadevsthan | ALL | GON - DUDBC | GON - DUDBC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 60 | 60 | 2017-03-06 | 2017-03-28 | Training location is Jewwanpur VDC hall | Benighat Rorang | 2
1202 | Dhading | Mahadevsthan |  | GON - PAF | PSBS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-10 | 2017-06-16 |  | Benighat Rorang | 2
1203 | Dhading | Maidi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 3
1204 | Dhading | Maidi | 1 | GON - PAF | COSOC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2017-06-21 | 2017-06-27 |  | Jwalamukhi | 3
1205 | Dhading | Maidi | 1 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 4 | 4 | 2015-12-08 | 2015-12-12 |  | Jwalamukhi | 3
1206 | Dhading | Maidi | 1 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 8 | 3 | 2016-12-05 | 2017-01-23 |  | Jwalamukhi | 3
1207 | Dhading | Maidi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 3
1208 | Dhading | Maidi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 3
1209 | Dhading | Maidi | 2 | GON - PAF | COSOC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 18 | 18 | 2017-06-21 | 2017-06-27 |  | Jwalamukhi | 3
1210 | Dhading | Maidi | 2 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 4 | 4 | 2015-12-08 | 2015-12-12 |  | Jwalamukhi | 3
1211 | Dhading | Maidi | 2 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 8 | 2 | 2016-12-05 | 2017-01-23 |  | Jwalamukhi | 3
1212 | Dhading | Maidi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 3
1213 | Dhading | Maidi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 3
1214 | Dhading | Maidi | 3 | GON - PAF | COSOC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-21 | 2017-06-27 |  | Jwalamukhi | 3
1215 | Dhading | Maidi | 3 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 13 | 13 | 2015-12-08 | 2015-12-12 |  | Jwalamukhi | 3
1216 | Dhading | Maidi | 3 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 8 | 3 | 2016-12-05 | 2017-01-23 |  | Jwalamukhi | 3
1217 | Dhading | Maidi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 3
1218 | Dhading | Maidi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 2
1219 | Dhading | Maidi | 4 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 11 | 11 | 2015-12-08 | 2015-12-12 |  | Jwalamukhi | 2
1220 | Dhading | Maidi | 4 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 8 | 3 | 2016-12-05 | 2017-01-23 |  | Jwalamukhi | 2
1221 | Dhading | Maidi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 2
1222 | Dhading | Maidi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 2
1223 | Dhading | Maidi | 5 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 2 | 2 | 2015-12-08 | 2015-12-12 |  | Jwalamukhi | 2
1224 | Dhading | Maidi | 5 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 8 | 4 | 2016-12-05 | 2017-01-23 |  | Jwalamukhi | 2
1225 | Dhading | Maidi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 2
1226 | Dhading | Maidi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 2
1227 | Dhading | Maidi | 6 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 8 | 8 | 2015-12-08 | 2015-12-12 |  | Jwalamukhi | 2
1228 | Dhading | Maidi | 6 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 8 | 3 | 2016-12-05 | 2017-01-23 |  | Jwalamukhi | 2
1229 | Dhading | Maidi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 2
1230 | Dhading | Maidi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 2
1231 | Dhading | Maidi | 7 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 5 | 5 | 2015-12-08 | 2015-12-12 |  | Jwalamukhi | 2
1232 | Dhading | Maidi | 7 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 8 | 3 | 2016-12-05 | 2017-01-23 |  | Jwalamukhi | 2
1233 | Dhading | Maidi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 2
1234 | Dhading | Maidi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 1
1235 | Dhading | Maidi | 8 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 8 | 8 | 2015-12-08 | 2015-12-12 |  | Jwalamukhi | 1
1236 | Dhading | Maidi | 8 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 8 | 4 | 2016-12-05 | 2017-01-23 |  | Jwalamukhi | 1
1237 | Dhading | Maidi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 1
1238 | Dhading | Maidi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 1
1239 | Dhading | Maidi | 9 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 8 | 8 | 2015-12-08 | 2015-12-12 |  | Jwalamukhi | 1
1240 | Dhading | Maidi | 9 | DCA | AN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 8 | 4 | 2016-12-05 | 2017-01-23 |  | Jwalamukhi | 1
1241 | Dhading | Maidi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jwalamukhi | 1
1242 | Dhading | Marpak | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 123 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1243 | Dhading | Marpak | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1244 | Dhading | Marpak | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 74 | 6 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1245 | Dhading | Marpak | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 74 | 89 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1246 | Dhading | Marpak | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1247 | Dhading | Marpak | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1248 | Dhading | Marpak | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 117 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1249 | Dhading | Marpak | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1250 | Dhading | Marpak | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 96 | 14 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1251 | Dhading | Marpak | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 96 | 7 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1252 | Dhading | Marpak | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 16 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1253 | Dhading | Marpak | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1254 | Dhading | Marpak | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 197 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1255 | Dhading | Marpak | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1256 | Dhading | Marpak | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 137 | 28 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1257 | Dhading | Marpak | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 137 | 7 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1258 | Dhading | Marpak | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1259 | Dhading | Marpak | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1260 | Dhading | Marpak | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 188 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1261 | Dhading | Marpak | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1262 | Dhading | Marpak | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 139 | 13 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1263 | Dhading | Marpak | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 139 | 8 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1264 | Dhading | Marpak | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 15 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1265 | Dhading | Marpak | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1266 | Dhading | Marpak | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 223 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1267 | Dhading | Marpak | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1268 | Dhading | Marpak | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 123 | 13 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1269 | Dhading | Marpak | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 123 | 4 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1270 | Dhading | Marpak | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Netrawati | 1
1271 | Dhading | Marpak | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1272 | Dhading | Marpak | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1273 | Dhading | Marpak | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 109 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1274 | Dhading | Marpak | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1275 | Dhading | Marpak | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 71 | 6 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1276 | Dhading | Marpak | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 71 | 5 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1277 | Dhading | Marpak | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-18 | 2016-12-26 |  | Netrawati | 1
1278 | Dhading | Marpak | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1279 | Dhading | Marpak | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1280 | Dhading | Marpak | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 148 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1281 | Dhading | Marpak | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1282 | Dhading | Marpak | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 156 | 15 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1283 | Dhading | Marpak | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 156 | 1 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1284 | Dhading | Marpak | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 15 | 15 | 2016-10-18 | 2016-12-26 |  | Netrawati | 1
1285 | Dhading | Marpak | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 20 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1286 | Dhading | Marpak | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1287 | Dhading | Marpak | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 6 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1288 | Dhading | Marpak | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1289 | Dhading | Marpak | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 40 | 2 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1290 | Dhading | Marpak | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 40 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1291 | Dhading | Marpak | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1292 | Dhading | Marpak | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 1
1293 | Dhading | Marpak | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 327 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1294 | Dhading | Marpak | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1295 | Dhading | Marpak | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 167 | 6 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1296 | Dhading | Marpak | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 167 | 3 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1297 | Dhading | Marpak | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-10-18 | 2016-12-26 |  | Netrawati | 2
1298 | Dhading | Marpak | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 38 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1299 | Dhading | Marpak | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1300 | Dhading | Mulpani | 1 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-03-01 | 2016-05-14 |  | Tripura Sundari | 3
1301 | Dhading | Mulpani | 1 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 38 | 2016-03-23 | 2016-03-23 |  | Tripura Sundari | 3
1302 | Dhading | Mulpani | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 3
1303 | Dhading | Mulpani | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 3
1304 | Dhading | Mulpani | 1 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-03-01 | 2016-05-14 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 3
1305 | Dhading | Mulpani | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 3
1306 | Dhading | Mulpani | 2 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 6 | 6 | 2016-03-01 | 2016-05-14 |  | Tripura Sundari | 3
1307 | Dhading | Mulpani | 2 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 88 | 2016-03-24 | 2016-03-24 |  | Tripura Sundari | 3
1308 | Dhading | Mulpani | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 3
1309 | Dhading | Mulpani | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 3
1310 | Dhading | Mulpani | 2 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-03-01 | 2016-05-14 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 3
1311 | Dhading | Mulpani | 2 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 7 | 7 | 2016-02-12 | 2016-03-26 |  | Tripura Sundari | 3
1312 | Dhading | Mulpani | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 3
1313 | Dhading | Mulpani | 3 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 16 | 16 | 2016-03-01 | 2016-05-14 |  | Tripura Sundari | 3
1314 | Dhading | Mulpani | 3 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 83 | 2016-03-26 | 2016-03-26 |  | Tripura Sundari | 3
1315 | Dhading | Mulpani | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 3
1316 | Dhading | Mulpani | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 3
1317 | Dhading | Mulpani | 3 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 16 | 16 | 2016-03-01 | 2016-05-14 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 3
1318 | Dhading | Mulpani | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 3
1319 | Dhading | Mulpani | 4 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-03-01 | 2016-05-14 |  | Tripura Sundari | 3
1320 | Dhading | Mulpani | 4 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 58 | 2016-03-25 | 2016-03-25 |  | Tripura Sundari | 3
1321 | Dhading | Mulpani | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 3
1322 | Dhading | Mulpani | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 3
1323 | Dhading | Mulpani | 4 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-03-01 | 2016-05-14 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 3
1324 | Dhading | Mulpani | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 3
1325 | Dhading | Mulpani | 5 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-03-01 | 2016-05-14 |  | Tripura Sundari | 3
1326 | Dhading | Mulpani | 5 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 48 | 2016-03-28 | 2016-03-28 |  | Tripura Sundari | 3
1327 | Dhading | Mulpani | 5 | CARE-N | SAHAS | CARE-F | Technical Assistance | Demonstration Construction | House | After completion of mason training house is constructed in Mathilo Mulabari | # of constructions | Yes | Completed | 1 | 1 | 2016-02-01 | 2016-08-15 |  | Tripura Sundari | 3
1328 | Dhading | Mulpani | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 3
1329 | Dhading | Mulpani | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 3
1330 | Dhading | Mulpani | 5 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-03-01 | 2016-05-14 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 3
1331 | Dhading | Mulpani | 5 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 2 | 2 | 2016-02-12 | 2016-03-26 |  | Tripura Sundari | 3
1332 | Dhading | Mulpani | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 3
1333 | Dhading | Mulpani | 6 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 9 | 9 | 2016-03-01 | 2016-05-14 |  | Tripura Sundari | 3
1334 | Dhading | Mulpani | 6 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 35 | 2016-03-31 | 2016-03-31 |  | Tripura Sundari | 3
1335 | Dhading | Mulpani | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 3
1336 | Dhading | Mulpani | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 3
1337 | Dhading | Mulpani | 6 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 9 | 9 | 2016-03-01 | 2016-05-14 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 3
1338 | Dhading | Mulpani | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 3
1339 | Dhading | Mulpani | 7 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 5 | 5 | 2016-03-01 | 2016-05-14 |  | Tripura Sundari | 3
1340 | Dhading | Mulpani | 7 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 60 | 2016-03-29 | 2016-03-29 |  | Tripura Sundari | 3
1341 | Dhading | Mulpani | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 3
1342 | Dhading | Mulpani | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 3
1343 | Dhading | Mulpani | 7 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-03-01 | 2016-05-14 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 3
1344 | Dhading | Mulpani | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 3
1345 | Dhading | Mulpani | 8 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-03-01 | 2016-05-14 |  | Tripura Sundari | 3
1346 | Dhading | Mulpani | 8 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 78 | 2016-03-27 | 2016-03-27 |  | Tripura Sundari | 3
1347 | Dhading | Mulpani | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 3
1348 | Dhading | Mulpani | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 3
1349 | Dhading | Mulpani | 8 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-03-01 | 2016-05-14 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 3
1350 | Dhading | Mulpani | 8 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 1 | 1 | 2016-02-12 | 2016-03-26 |  | Tripura Sundari | 3
1351 | Dhading | Mulpani | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 3
1352 | Dhading | Mulpani | 9 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-03-01 | 2016-05-14 |  | Tripura Sundari | 3
1353 | Dhading | Mulpani | 9 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 44 | 2016-04-01 | 2016-04-01 |  | Tripura Sundari | 3
1354 | Dhading | Mulpani | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 3
1355 | Dhading | Mulpani | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 3
1356 | Dhading | Mulpani | 9 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-03-01 | 2016-05-14 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 3
1357 | Dhading | Mulpani | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 3
1358 | Dhading | Mulpani | All | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 10 | 10 | 2016-02-12 | 2016-03-26 | District Small Cottage Industry | Tripura Sundari | 3
1359 | Dhading | Nalang | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 41 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1360 | Dhading | Nalang | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1361 | Dhading | Nalang | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 66 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1362 | Dhading | Nalang | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 66 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1363 | Dhading | Nalang | 1 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 5 | 8 | 2016-11-23 | 2016-11-29 |  | Siddhalek | 2
1364 | Dhading | Nalang | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1365 | Dhading | Nalang | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1366 | Dhading | Nalang | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 168 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1367 | Dhading | Nalang | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1368 | Dhading | Nalang | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 156 | 11 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1369 | Dhading | Nalang | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 156 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1370 | Dhading | Nalang | 2 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-11-23 | 2016-11-29 |  | Siddhalek | 2
1371 | Dhading | Nalang | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1372 | Dhading | Nalang | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1373 | Dhading | Nalang | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 244 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1374 | Dhading | Nalang | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1375 | Dhading | Nalang | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 286 | 14 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1376 | Dhading | Nalang | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 286 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1377 | Dhading | Nalang | 3 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 4 | 6 | 2016-11-23 | 2016-11-29 |  | Siddhalek | 2
1378 | Dhading | Nalang | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 9 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1379 | Dhading | Nalang | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1380 | Dhading | Nalang | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 74 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1381 | Dhading | Nalang | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1382 | Dhading | Nalang | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 50 | 13 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1383 | Dhading | Nalang | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 50 | 29 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1384 | Dhading | Nalang | 4 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 4 | 2 | 2016-11-23 | 2016-11-29 |  | Siddhalek | 2
1385 | Dhading | Nalang | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1386 | Dhading | Nalang | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1387 | Dhading | Nalang | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 110 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1388 | Dhading | Nalang | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1389 | Dhading | Nalang | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 107 | 8 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1390 | Dhading | Nalang | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 107 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1391 | Dhading | Nalang | 5 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 4 | 5 | 2016-11-23 | 2016-11-29 |  | Siddhalek | 2
1392 | Dhading | Nalang | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1393 | Dhading | Nalang | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 2
1394 | Dhading | Nalang | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 288 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1395 | Dhading | Nalang | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1396 | Dhading | Nalang | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 393 | 45 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1397 | Dhading | Nalang | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 393 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1398 | Dhading | Nalang | 6 | EPF | EPF | ASB | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2017-04-01 |  |  | Siddhalek | 1
1399 | Dhading | Nalang | 6 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 3 | 4 | 2016-11-23 | 2016-11-29 |  | Siddhalek | 1
1400 | Dhading | Nalang | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 23 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1401 | Dhading | Nalang | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1402 | Dhading | Nalang | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 150 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1403 | Dhading | Nalang | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1404 | Dhading | Nalang | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 206 | 16 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1405 | Dhading | Nalang | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 206 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1406 | Dhading | Nalang | 7 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 30 | 30 | 2016-11-23 | 2017-06-01 | Reached figure will confirm in next round | Siddhalek | 1
1407 | Dhading | Nalang | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1408 | Dhading | Nalang | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1409 | Dhading | Nalang | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 49 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1410 | Dhading | Nalang | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1411 | Dhading | Nalang | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 115 | 5 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1412 | Dhading | Nalang | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 115 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1413 | Dhading | Nalang | 8 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 3 | 1 | 2016-11-23 | 2016-11-29 |  | Siddhalek | 1
1414 | Dhading | Nalang | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1415 | Dhading | Nalang | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1416 | Dhading | Nalang | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 147 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1417 | Dhading | Nalang | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1418 | Dhading | Nalang | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 174 | 12 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1419 | Dhading | Nalang | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 174 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1420 | Dhading | Nalang | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 35 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1421 | Dhading | Nalang | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 1
1422 | Dhading | Nalang | 9 | DCA | AN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-11-23 | 2017-11-30 | Reached figure will confirm in next round | Siddhalek | 1
1423 | Dhading | Naubise | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 6
1424 | Dhading | Naubise | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 6
1425 | Dhading | Naubise | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 8
1426 | Dhading | Naubise | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 8
1427 | Dhading | Naubise | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 9
1428 | Dhading | Naubise | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 9
1429 | Dhading | Naubise | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 9
1430 | Dhading | Naubise | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 9
1431 | Dhading | Naubise | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 9
1432 | Dhading | Naubise | 5 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 2 | 2 | 2015-12-08 | 2015-12-12 |  | Dhunibesi | 9
1433 | Dhading | Naubise | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 9
1434 | Dhading | Naubise | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 8
1435 | Dhading | Naubise | 6 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 3 | 3 | 2015-12-08 | 2015-12-12 |  | Dhunibesi | 8
1436 | Dhading | Naubise | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 8
1437 | Dhading | Naubise | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 7
1438 | Dhading | Naubise | 7 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 9 | 9 | 2015-12-08 | 2015-12-12 |  | Dhunibesi | 7
1439 | Dhading | Naubise | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 7
1440 | Dhading | Naubise | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 7
1441 | Dhading | Naubise | 8 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 9 | 9 | 2015-12-08 | 2015-12-12 |  | Dhunibesi | 7
1442 | Dhading | Naubise | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 7
1443 | Dhading | Naubise | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 6
1444 | Dhading | Naubise | 9 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-08 | 2015-12-12 |  | Dhunibesi | 6
1445 | Dhading | Naubise | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Dhunibesi | 6
1446 | Dhading | Naubise | All | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 29 | 29 | 2015-12-08 | 2015-12-12 | Ward wise data not avialbale | Dhunibesi | 9
1447 | Dhading | Nilkantha N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 682 | 66 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 2
1448 | Dhading | Nilkantha N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 2
1449 | Dhading | Nilkantha N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 539 | 8 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 2
1450 | Dhading | Nilkantha N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 539 | 100 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 2
1451 | Dhading | Nilkantha N.P. | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 28 | 38 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 2
1452 | Dhading | Nilkantha N.P. | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 2
1453 | Dhading | Nilkantha N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 682 | 459 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 2
1454 | Dhading | Nilkantha N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 2
1455 | Dhading | Nilkantha N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 825 | 39 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 2
1456 | Dhading | Nilkantha N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 825 | 70 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 2
1457 | Dhading | Nilkantha N.P. | 2 | GON - PAF | ICDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-21 | 2017-05-27 |  | Nilakantha | 2
1458 | Dhading | Nilkantha N.P. | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 28 | 57 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 2
1459 | Dhading | Nilkantha N.P. | 2 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-05-24 |  | Nilakantha | 2
1460 | Dhading | Nilkantha N.P. | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 2
1461 | Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 682 | 156 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 3
1462 | Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 3
1463 | Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 413 | 9 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 3
1464 | Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 413 | 402 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 3
1465 | Dhading | Nilkantha N.P. | 3 | GON - PAF | ICDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2017-05-21 | 2017-05-27 |  | Nilakantha | 3
1466 | Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Training | Other trainings | Other trainings (specify in Activity Detail) | Social mobilizer (curriculum, specify in comment) | # of trainees | Yes | Ongoing | 32 | 33 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 3
1467 | Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Training | Other trainings | Other trainings (specify in Activity Detail) | Training for Instructor | # of trainees | Yes | Ongoing | 50 | 28 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 3
1468 | Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Training | Other trainings | Basic Engineers Training |  | # of trainees | Yes | Ongoing | 28 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 3
1469 | Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Training | Retrofitting training | Engineers, sub-engineers |  | # of trainees | Yes | Ongoing | 32 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 3
1470 | Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 28 | 16 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 3
1471 | Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Ongoing | 512 | 256 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 3
1472 | Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Training | ToT | Social mobilizer (curriculum, specify in comment) |  | # of trainees | Yes | Ongoing | 50 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 3
1473 | Dhading | Nilkantha N.P. | 3 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 2 | 2 | 2016-03-15 | 2016-05-24 |  | Nilakantha | 3
1474 | Dhading | Nilkantha N.P. | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 3
1475 | Dhading | Nilkantha N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 682 | 251 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 4
1476 | Dhading | Nilkantha N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 4
1477 | Dhading | Nilkantha N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 642 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 4
1478 | Dhading | Nilkantha N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 642 | 80 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 4
1479 | Dhading | Nilkantha N.P. | 4 | GON - PAF | ICDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-05-21 | 2017-05-27 |  | Nilakantha | 4
1480 | Dhading | Nilkantha N.P. | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 30 | 35 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 4
1481 | Dhading | Nilkantha N.P. | 4 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 3 | 3 | 2016-03-15 | 2016-05-24 |  | Nilakantha | 4
1482 | Dhading | Nilkantha N.P. | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 4
1483 | Dhading | Nilkantha N.P. | 5 | ACTED | ACTED | ACTED | Others | Others | (Please specify in Activity Detail) | Social Mobilization Training on Enrollment | # of trainees | Yes | Completed | 25 | 24 | 2016-04-27 | 2016-04-29 |  | Nilakantha | 6
1484 | Dhading | Nilkantha N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 682 | 583 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 6
1485 | Dhading | Nilkantha N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 6
1486 | Dhading | Nilkantha N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 292 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 6
1487 | Dhading | Nilkantha N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 292 | 132 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 6
1488 | Dhading | Nilkantha N.P. | 5 | GON - PAF | ICDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-05-21 | 2017-05-27 |  | Nilakantha | 6
1489 | Dhading | Nilkantha N.P. | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 30 | 3 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 6
1490 | Dhading | Nilkantha N.P. | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 6
1491 | Dhading | Nilkantha N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 682 | 447 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 6
1492 | Dhading | Nilkantha N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 6
1493 | Dhading | Nilkantha N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 355 | 92 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 6
1494 | Dhading | Nilkantha N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 355 | 12 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 6
1495 | Dhading | Nilkantha N.P. | 6 | GON - PAF | ICDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-05-21 | 2017-05-27 |  | Nilakantha | 6
1496 | Dhading | Nilkantha N.P. | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 30 | 34 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 6
1497 | Dhading | Nilkantha N.P. | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 6
1498 | Dhading | Nilkantha N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 682 | 558 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 7
1499 | Dhading | Nilkantha N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 7
1500 | Dhading | Nilkantha N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 807 | 13 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 7
1501 | Dhading | Nilkantha N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 807 | 70 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 7
1502 | Dhading | Nilkantha N.P. | 7 | GON - PAF | ICDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2017-05-21 | 2017-05-27 |  | Nilakantha | 7
1503 | Dhading | Nilkantha N.P. | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 30 | 55 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 7
1504 | Dhading | Nilkantha N.P. | 7 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 5 | 5 | 2016-03-15 | 2016-05-24 |  | Nilakantha | 7
1505 | Dhading | Nilkantha N.P. | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 7
1506 | Dhading | Nilkantha N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 682 | 192 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 8
1507 | Dhading | Nilkantha N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 8
1508 | Dhading | Nilkantha N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 707 | 25 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 8
1509 | Dhading | Nilkantha N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 707 | 60 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 8
1510 | Dhading | Nilkantha N.P. | 8 | GON - PAF | ICDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2017-05-21 | 2017-05-27 |  | Nilakantha | 8
1511 | Dhading | Nilkantha N.P. | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 30 | 19 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 8
1512 | Dhading | Nilkantha N.P. | 8 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 6 | 6 | 2016-03-15 | 2016-05-24 | District Small Cottage Industry | Nilakantha | 8
1513 | Dhading | Nilkantha N.P. | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 8
1514 | Dhading | Nilkantha N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 682 | 20 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 9
1515 | Dhading | Nilkantha N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 9
1516 | Dhading | Nilkantha N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 611 | 25 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 9
1517 | Dhading | Nilkantha N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 611 | 52 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 9
1518 | Dhading | Nilkantha N.P. | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 30 | 95 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 9
1519 | Dhading | Nilkantha N.P. | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 9
1520 | Dhading | Nilkantha N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 682 | 186 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 9
1521 | Dhading | Nilkantha N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 9
1522 | Dhading | Nilkantha N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 511 | 14 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 9
1523 | Dhading | Nilkantha N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 511 | 48 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 9
1524 | Dhading | Nilkantha N.P. | 10 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 30 | 22 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 9
1525 | Dhading | Nilkantha N.P. | 10 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 9
1526 | Dhading | Nilkantha N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 682 | 178 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 13
1527 | Dhading | Nilkantha N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 13
1528 | Dhading | Nilkantha N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 391 | 15 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 13
1529 | Dhading | Nilkantha N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 391 | 20 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 13
1530 | Dhading | Nilkantha N.P. | 11 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 30 | 39 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 13
1531 | Dhading | Nilkantha N.P. | 11 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 13
1532 | Dhading | Nilkantha N.P. | 12 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 682 | 270 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 12
1533 | Dhading | Nilkantha N.P. | 12 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 12
1534 | Dhading | Nilkantha N.P. | 12 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 673 | 45 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 12
1535 | Dhading | Nilkantha N.P. | 12 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 673 | 100 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 12
1536 | Dhading | Nilkantha N.P. | 12 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 30 | 30 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 12
1537 | Dhading | Nilkantha N.P. | 12 | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-05-24 |  | Nilakantha | 12
1538 | Dhading | Nilkantha N.P. | 12 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 12
1539 | Dhading | Nilkantha N.P. | 13 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 692 | 112 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 13
1540 | Dhading | Nilkantha N.P. | 13 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 13
1541 | Dhading | Nilkantha N.P. | 13 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 324 | 8 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 13
1542 | Dhading | Nilkantha N.P. | 13 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 324 | 6 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 13
1543 | Dhading | Nilkantha N.P. | 13 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 30 | 15 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 13
1544 | Dhading | Nilkantha N.P. | 13 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Nilakantha | 13
1545 | Dhading | Nilkantha N.P. | ALL | GON - DUDBC | GON - DUDBC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-06-10 | 2017-06-16 | Training location is Baireni VDC hall | Nilakantha | 13
1546 | Dhading | Nilkantha N.P. | All | GoN | GoN | GoN | Training | Vocational training | Electrician (CTEVT) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 20 | 19 | 2015-12-06 | 2016-01-23 | Submit next round of 4W | Nilakantha | 13
1547 | Dhading | Nilkantha N.P. | All | GoN | GoN | GoN | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 20 | 20 | 2016-12-06 | 2016-01-22 | Submit next round of 4W | Nilakantha | 13
1548 | Dhading | Phulkhark | 1 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01 |  | Gangajamuna | 5
1549 | Dhading | Phulkhark | 1 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 116 | 2016-09-19 | 2016-09-19 |  | Gangajamuna | 5
1550 | Dhading | Phulkhark | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 5
1551 | Dhading | Phulkhark | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 5
1552 | Dhading | Phulkhark | 1 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 5
1553 | Dhading | Phulkhark | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 5
1554 | Dhading | Phulkhark | 2 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-09-25 | 2016-10-01 |  | Gangajamuna | 5
1555 | Dhading | Phulkhark | 2 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 92 | 2016-09-18 | 2016-09-18 |  | Gangajamuna | 5
1556 | Dhading | Phulkhark | 2 | CARE-N | SAHAS | CARE-F | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-09-12 | 2017-03-01 |  | Gangajamuna | 5
1557 | Dhading | Phulkhark | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 5
1558 | Dhading | Phulkhark | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 5
1559 | Dhading | Phulkhark | 2 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 5
1560 | Dhading | Phulkhark | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 5
1561 | Dhading | Phulkhark | 3 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 8 | 8 | 2016-09-25 | 2016-10-01 |  | Gangajamuna | 5
1562 | Dhading | Phulkhark | 3 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 87 | 2016-09-17 | 2016-09-17 |  | Gangajamuna | 5
1563 | Dhading | Phulkhark | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 5
1564 | Dhading | Phulkhark | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 5
1565 | Dhading | Phulkhark | 3 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 5
1566 | Dhading | Phulkhark | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 5
1567 | Dhading | Phulkhark | 4 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-09-25 | 2016-10-01 |  | Gangajamuna | 5
1568 | Dhading | Phulkhark | 4 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 80 | 2016-09-15 | 2016-09-15 |  | Gangajamuna | 5
1569 | Dhading | Phulkhark | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 5
1570 | Dhading | Phulkhark | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 5
1571 | Dhading | Phulkhark | 4 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 5
1572 | Dhading | Phulkhark | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 5
1573 | Dhading | Phulkhark | 5 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 11 | 11 | 2016-09-25 | 2016-10-01 |  | Gangajamuna | 5
1574 | Dhading | Phulkhark | 5 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 89 | 2016-09-16 | 2016-09-16 |  | Gangajamuna | 5
1575 | Dhading | Phulkhark | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 5
1576 | Dhading | Phulkhark | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 5
1577 | Dhading | Phulkhark | 5 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 11 | 11 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 5
1578 | Dhading | Phulkhark | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 5
1579 | Dhading | Phulkhark | 6 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 8 | 8 | 2016-09-25 | 2016-10-01 |  | Gangajamuna | 5
1580 | Dhading | Phulkhark | 6 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 49 | 2016-09-13 | 2016-09-13 |  | Gangajamuna | 5
1581 | Dhading | Phulkhark | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 5
1582 | Dhading | Phulkhark | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 5
1583 | Dhading | Phulkhark | 6 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 5
1584 | Dhading | Phulkhark | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 5
1585 | Dhading | Phulkhark | 7 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 6 | 6 | 2016-09-25 | 2016-10-01 |  | Gangajamuna | 5
1586 | Dhading | Phulkhark | 7 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 61 | 2016-09-11 | 2016-09-11 |  | Gangajamuna | 5
1587 | Dhading | Phulkhark | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 5
1588 | Dhading | Phulkhark | 7 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 5
1589 | Dhading | Phulkhark | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 5
1590 | Dhading | Phulkhark | 8 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-09-25 | 2016-10-01 |  | Gangajamuna | 5
1591 | Dhading | Phulkhark | 8 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 86 | 2016-09-12 | 2016-09-12 |  | Gangajamuna | 5
1592 | Dhading | Phulkhark | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 5
1593 | Dhading | Phulkhark | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 5
1594 | Dhading | Phulkhark | 8 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 5
1595 | Dhading | Phulkhark | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 5
1596 | Dhading | Phulkhark | 9 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 6 | 6 | 2016-09-25 | 2016-10-01 |  | Gangajamuna | 5
1597 | Dhading | Phulkhark | 9 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 40 | 67 | 2016-09-14 | 2016-09-14 |  | Gangajamuna | 5
1598 | Dhading | Phulkhark | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 5
1599 | Dhading | Phulkhark | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 5
1600 | Dhading | Phulkhark | 9 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 Days DUDBC, Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 5
1601 | Dhading | Phulkhark | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 5
1602 | Dhading | Phulkhark | All | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 1 | 1 | 2016-09-25 | 2016-10-01 |  | Gangajamuna | 5
1603 | Dhading | Phulkhark | All | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-09-25 | 2016-10-01 | Trainng was given to 25-30 participants for 5-7 days only. | Gangajamuna | 5
1604 | Dhading | Pida | 1 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Gajuri | 6
1605 | Dhading | Pida | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 6
1606 | Dhading | Pida | 1 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Gajuri | 6
1607 | Dhading | Pida | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 6
1608 | Dhading | Pida | 2 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 19 | 19 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Gajuri | 5
1609 | Dhading | Pida | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 5
1610 | Dhading | Pida | 2 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 19 | 19 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Gajuri | 5
1611 | Dhading | Pida | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 5
1612 | Dhading | Pida | 3 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Gajuri | 6
1613 | Dhading | Pida | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 6
1614 | Dhading | Pida | 3 | UMN | PRAYAS-N | UMN | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-06-03 | 2017-06-02 |  | Gajuri | 6
1615 | Dhading | Pida | 3 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Gajuri | 6
1616 | Dhading | Pida | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 6
1617 | Dhading | Pida | 4 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 25 | 25 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Gajuri | 5
1618 | Dhading | Pida | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 5
1619 | Dhading | Pida | 4 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 25 | 25 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Gajuri | 5
1620 | Dhading | Pida | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 5
1621 | Dhading | Pida | 5 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 16 | 16 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Gajuri | 5
1622 | Dhading | Pida | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 5
1623 | Dhading | Pida | 5 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 16 | 16 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Gajuri | 5
1624 | Dhading | Pida | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 5
1625 | Dhading | Pida | 6 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Gajuri | 6
1626 | Dhading | Pida | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 6
1627 | Dhading | Pida | 6 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Gajuri | 6
1628 | Dhading | Pida | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 6
1629 | Dhading | Pida | 7 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Gajuri | 4
1630 | Dhading | Pida | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 4
1631 | Dhading | Pida | 7 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Gajuri | 4
1632 | Dhading | Pida | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 4
1633 | Dhading | Pida | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 4
1634 | Dhading | Pida | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 4
1635 | Dhading | Pida | 9 | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Gajuri | 4
1636 | Dhading | Pida | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 4
1637 | Dhading | Pida | 9 | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-02-11 | 2016-04-27 | Phase wise training of 7 day | Gajuri | 4
1638 | Dhading | Pida | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gajuri | 4
1639 | Dhading | Pida | All | UMN | PRAYAS-N | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-27 | Ward wise data are not available | Gajuri | 6
1640 | Dhading | Pida | ALL | GON - DUDBC | GON - DUDBC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 22 | 22 | 2017-02-07 | 2017-02-13 | Training location is Pida VDC Hall | Gajuri | 6
1641 | Dhading | Pida | All | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-02-11 | 2016-04-27 | Ward wise data are not available | Gajuri | 6
1642 | Dhading | ReeGaun | 1 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 8 | 8 | 2016-02-10 | 2016-04-10 |  | Gangajamuna | 2
1643 | Dhading | ReeGaun | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 2
1644 | Dhading | ReeGaun | 1 | GON - PAF | HDSC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-06-11 | 2017-06-18 |  | Gangajamuna | 2
1645 | Dhading | ReeGaun | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 13 | 13 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 2
1646 | Dhading | ReeGaun | 1 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-02-10 | 2016-04-10 |  | Gangajamuna | 2
1647 | Dhading | ReeGaun | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 2
1648 | Dhading | ReeGaun | 2 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 16 | 16 | 2016-02-10 | 2016-04-10 |  | Gangajamuna | 2
1649 | Dhading | ReeGaun | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 2
1650 | Dhading | ReeGaun | 2 | UMN | NRDS | UMN | Technical Assistance | Demonstration Construction | House | Demo house construction is copleted in Salleri tole of Reegaun-2 | # of constructions | Yes | Completed | 1 | 1 | 2016-08-10 | 2016-12-15 |  | Gangajamuna | 2
1651 | Dhading | ReeGaun | 2 | GON - PAF | HDSC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-11 | 2017-06-18 |  | Gangajamuna | 2
1652 | Dhading | ReeGaun | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 2
1653 | Dhading | ReeGaun | 2 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 16 | 16 | 2016-02-10 | 2016-04-10 |  | Gangajamuna | 2
1654 | Dhading | ReeGaun | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 2
1655 | Dhading | ReeGaun | 3 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 2 | 2 | 2016-02-10 | 2016-04-10 |  | Gangajamuna | 2
1656 | Dhading | ReeGaun | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 2
1657 | Dhading | ReeGaun | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 2
1658 | Dhading | ReeGaun | 3 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-02-10 | 2016-04-10 |  | Gangajamuna | 2
1659 | Dhading | ReeGaun | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 2
1660 | Dhading | ReeGaun | 4 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 28 | 28 | 2016-02-10 | 2016-04-10 |  | Gangajamuna | 1
1661 | Dhading | ReeGaun | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 1
1662 | Dhading | ReeGaun | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 1
1663 | Dhading | ReeGaun | 4 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 28 | 28 | 2016-02-10 | 2016-04-10 |  | Gangajamuna | 1
1664 | Dhading | ReeGaun | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 1
1665 | Dhading | ReeGaun | 5 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 10 | 10 | 2016-02-10 | 2016-04-10 |  | Gangajamuna | 1
1666 | Dhading | ReeGaun | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 1
1667 | Dhading | ReeGaun | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 1
1668 | Dhading | ReeGaun | 5 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-02-10 | 2016-04-10 |  | Gangajamuna | 1
1669 | Dhading | ReeGaun | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 1
1670 | Dhading | ReeGaun | 6 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-02-10 | 2016-04-10 |  | Gangajamuna | 2
1671 | Dhading | ReeGaun | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 2
1672 | Dhading | ReeGaun | 6 | GON - PAF | HDSC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-06-11 | 2017-06-18 |  | Gangajamuna | 2
1673 | Dhading | ReeGaun | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 2
1674 | Dhading | ReeGaun | 6 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-02-10 | 2016-04-10 |  | Gangajamuna | 2
1675 | Dhading | ReeGaun | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 2
1676 | Dhading | ReeGaun | 7 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 21 | 21 | 2016-02-10 | 2016-04-10 |  | Gangajamuna | 1
1677 | Dhading | ReeGaun | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 1
1678 | Dhading | ReeGaun | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 1
1679 | Dhading | ReeGaun | 7 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 21 | 21 | 2016-02-10 | 2016-04-10 |  | Gangajamuna | 1
1680 | Dhading | ReeGaun | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 1
1681 | Dhading | ReeGaun | 8 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 4 | 4 | 2016-02-10 | 2016-04-10 |  | Gangajamuna | 2
1682 | Dhading | ReeGaun | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 2
1683 | Dhading | ReeGaun | 8 | GON - PAF | HDSC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-06-11 | 2017-06-18 |  | Gangajamuna | 2
1684 | Dhading | ReeGaun | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 2
1685 | Dhading | ReeGaun | 8 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-02-10 | 2016-04-10 |  | Gangajamuna | 2
1686 | Dhading | ReeGaun | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 2
1687 | Dhading | ReeGaun | 9 | UMN | HIMS | UMN | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 10 | 10 | 2016-02-10 | 2016-04-10 |  | Gangajamuna | 1
1688 | Dhading | ReeGaun | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 1
1689 | Dhading | ReeGaun | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Gangajamuna | 1
1690 | Dhading | ReeGaun | 9 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-02-10 | 2016-04-10 |  | Gangajamuna | 1
1691 | Dhading | ReeGaun | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gangajamuna | 1
1692 | Dhading | Salang | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 3
1693 | Dhading | Salang | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 3
1694 | Dhading | Salang | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 3
1695 | Dhading | Salang | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 3
1696 | Dhading | Salang | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 3
1697 | Dhading | Salang | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 3
1698 | Dhading | Salang | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 3
1699 | Dhading | Salang | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 3
1700 | Dhading | Salang | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 3
1701 | Dhading | Salang | 5 | GoN | GoN | GoN | Training | Vocational training | Electrician (CTEVT) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 6 | 6 | 2016-05-29 | 2016-06-13 |  | Siddhalek | 3
1702 | Dhading | Salang | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 3
1703 | Dhading | Salang | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 4
1704 | Dhading | Salang | 6 | GoN | GoN | GoN | Training | Vocational training | Electrician (CTEVT) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 6 | 6 | 2016-05-29 | 2016-06-13 |  | Siddhalek | 4
1705 | Dhading | Salang | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 4
1706 | Dhading | Salang | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 4
1707 | Dhading | Salang | 7 | GoN | GoN | GoN | Training | Vocational training | Electrician (CTEVT) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 2 | 2 | 2016-05-29 | 2016-06-13 |  | Siddhalek | 4
1708 | Dhading | Salang | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 4
1709 | Dhading | Salang | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 4
1710 | Dhading | Salang | 8 | GoN | GoN | GoN | Training | Vocational training | Electrician (CTEVT) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 1 | 1 | 2016-05-29 | 2016-06-13 |  | Siddhalek | 4
1711 | Dhading | Salang | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 4
1712 | Dhading | Salang | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 4
1713 | Dhading | Salang | 9 | GoN | GoN | GoN | Training | Vocational training | Electrician (CTEVT) | 45 Days Training District Small Cottage Industry | # of trainees | Yes | Completed | 3 | 3 | 2016-05-29 | 2016-06-13 |  | Siddhalek | 4
1714 | Dhading | Salang | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Siddhalek | 4
1715 | Dhading | salang | All | ICDC | ICDC | KKS Germany | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason(7 days DUDBC , Rural) | # of trainees | Yes | Completed | 36 | 36 | 2017-06-15 | 2017-06-22 | Integrated Community Development Campaign & karl konrad Germany | Siddhalek | 3
1716 | Dhading | Salyankot | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 5
1717 | Dhading | Salyankot | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 15 | 15 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 5
1718 | Dhading | Salyankot | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 5
1719 | Dhading | Salyankot | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 5
1720 | Dhading | Salyankot | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 5
1721 | Dhading | Salyankot | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 5
1722 | Dhading | Salyankot | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 5
1723 | Dhading | Salyankot | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 5
1724 | Dhading | Salyankot | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 5
1725 | Dhading | Salyankot | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 5
1726 | Dhading | Salyankot | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 5
1727 | Dhading | Salyankot | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 4
1728 | Dhading | Salyankot | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 4
1729 | Dhading | Salyankot | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 4
1730 | Dhading | Salyankot | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 4
1731 | Dhading | Salyankot | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 4
1732 | Dhading | Salyankot | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 4
1733 | Dhading | Salyankot | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 4
1734 | Dhading | Salyankot | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 4
1735 | Dhading | Salyankot | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 4
1736 | Dhading | Salyankot | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 4
1737 | Dhading | Salyankot | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 4
1738 | Dhading | Salyankot | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 4
1739 | Dhading | Salyankot | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 4
1740 | Dhading | Salyankot | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 4
1741 | Dhading | Salyankot | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 4
1742 | Dhading | Salyantar | 1 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17 |  | Tripura Sundari | 1
1743 | Dhading | Salyantar | 1 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 66 | 2016-01-21 | 2016-01-21 |  | Tripura Sundari | 1
1744 | Dhading | Salyantar | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 1
1745 | Dhading | Salyantar | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 1
1746 | Dhading | Salyantar | 1 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 1
1747 | Dhading | Salyantar | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 1
1748 | Dhading | Salyantar | 2 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 12 | 12 | 2016-01-21 | 2016-09-17 |  | Tripura Sundari | 1
1749 | Dhading | Salyantar | 2 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 93 | 2016-03-16 | 2016-03-16 |  | Tripura Sundari | 1
1750 | Dhading | Salyantar | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 1
1751 | Dhading | Salyantar | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 1
1752 | Dhading | Salyantar | 2 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 12 | 12 | 2016-01-21 | 2016-09-17 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 1
1753 | Dhading | Salyantar | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 1
1754 | Dhading | Salyantar | 3 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17 |  | Tripura Sundari | 1
1755 | Dhading | Salyantar | 3 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 58 | 2016-03-17 | 2016-03-17 |  | Tripura Sundari | 1
1756 | Dhading | Salyantar | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 1
1757 | Dhading | Salyantar | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 1
1758 | Dhading | Salyantar | 3 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 1
1759 | Dhading | Salyantar | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 1
1760 | Dhading | Salyantar | 4 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17 |  | Tripura Sundari | 1
1761 | Dhading | Salyantar | 4 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 45 | 2016-03-18 | 2016-03-18 |  | Tripura Sundari | 1
1762 | Dhading | Salyantar | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 1
1763 | Dhading | Salyantar | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 1
1764 | Dhading | Salyantar | 4 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 1
1765 | Dhading | Salyantar | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 1
1766 | Dhading | Salyantar | 5 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17 |  | Tripura Sundari | 1
1767 | Dhading | Salyantar | 5 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 94 | 2016-03-13 | 2016-03-13 |  | Tripura Sundari | 1
1768 | Dhading | Salyantar | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 1
1769 | Dhading | Salyantar | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 1
1770 | Dhading | Salyantar | 5 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 1
1771 | Dhading | Salyantar | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 1
1772 | Dhading | Salyantar | 6 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 16 | 16 | 2016-01-21 | 2016-09-17 |  | Tripura Sundari | 2
1773 | Dhading | Salyantar | 6 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 47 | 2016-03-14 | 2016-03-14 |  | Tripura Sundari | 2
1774 | Dhading | Salyantar | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 2
1775 | Dhading | Salyantar | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 13 | 13 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 2
1776 | Dhading | Salyantar | 6 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 16 | 16 | 2016-01-21 | 2016-09-17 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 2
1777 | Dhading | Salyantar | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 2
1778 | Dhading | Salyantar | 7 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 15 | 15 | 2016-01-21 | 2016-09-17 |  | Tripura Sundari | 2
1779 | Dhading | Salyantar | 7 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 32 | 2016-03-15 | 2016-03-15 |  | Tripura Sundari | 2
1780 | Dhading | Salyantar | 7 | CARE-N | SAHAS | CARE-F | Technical Assistance | Demonstration Construction | House | After completion of mason training house is constructed at Bagaicha tole | # of constructions | Yes | Completed | 1 | 1 | 2016-02-01 | 2016-08-15 |  | Tripura Sundari | 2
1781 | Dhading | Salyantar | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 2
1782 | Dhading | Salyantar | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 2
1783 | Dhading | Salyantar | 7 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 15 | 15 | 2016-01-21 | 2016-09-17 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 2
1784 | Dhading | Salyantar | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 2
1785 | Dhading | Salyantar | 8 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 16 | 16 | 2016-01-21 | 2016-09-17 |  | Tripura Sundari | 2
1786 | Dhading | Salyantar | 8 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 85 | 2016-03-11 | 2016-03-11 |  | Tripura Sundari | 2
1787 | Dhading | Salyantar | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 2
1788 | Dhading | Salyantar | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 2
1789 | Dhading | Salyantar | 8 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 16 | 16 | 2016-01-21 | 2016-09-17 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 2
1790 | Dhading | Salyantar | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 2
1791 | Dhading | Salyantar | 9 | CARE-N | SAHAS | CARE-F | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After training toolkit are distributed for each mason(Stone Cutting Hammer,Mason Pan (Karai),Trowel,Measuring Tape-5m,Carpenter Saw,Plier,Plumbers with Thread,Trasparent Level, pipe-6m,Scissor for Cutting CGIs ,Tarkas,Hand Book ,HI Tool Kits) | # of kits | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17 |  | Tripura Sundari | 2
1792 | Dhading | Salyantar | 9 | CARE-N | SAHAS | CARE-F | Technical Assistance | Community reconstruction orientation | 1 session | Orientation about 10 key message and safe housing construction | # of participants | Yes | Completed | 45 | 56 | 2016-03-23 | 2016-03-23 |  | Tripura Sundari | 2
1793 | Dhading | Salyantar | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 2
1794 | Dhading | Salyantar | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 2
1795 | Dhading | Salyantar | 9 | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 5 Days DUDBC, Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-01-21 | 2016-09-17 | Trainng was given to 25-30 participants for 5-7 days only. | Tripura Sundari | 2
1796 | Dhading | Salyantar | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 2
1797 | Dhading | Salyantar | ALL | GON - DUDBC | GON - DUDBC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 44 | 44 | 2017-05-04 | 2017-05-11 | Training location is Baireni VDC hall | Tripura Sundari | 1
1798 | Dhading | Satyadevi | 1 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11 |  | Khaniyabash | 5
1799 | Dhading | Satyadevi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 5
1800 | Dhading | Satyadevi | 1 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01 |  |  | Khaniyabash | 5
1801 | Dhading | Satyadevi | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 5
1802 | Dhading | Satyadevi | 1 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11 | ACTION-N is Local partner of Oxfam | Khaniyabash | 5
1803 | Dhading | Satyadevi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 5
1804 | Dhading | Satyadevi | 2 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11 |  | Khaniyabash | 5
1805 | Dhading | Satyadevi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 5
1806 | Dhading | Satyadevi | 2 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 45 | 2016-04-01 |  |  | Khaniyabash | 5
1807 | Dhading | Satyadevi | 2 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11 | PARYAS-N is local partner of Oxfam | Khaniyabash | 5
1808 | Dhading | Satyadevi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 5
1809 | Dhading | Satyadevi | 3 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11 |  | Khaniyabash | 5
1810 | Dhading | Satyadevi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 5
1811 | Dhading | Satyadevi | 3 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 45 | 2016-04-01 |  |  | Khaniyabash | 5
1812 | Dhading | Satyadevi | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 13 | 13 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 5
1813 | Dhading | Satyadevi | 3 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11 |  | Khaniyabash | 5
1814 | Dhading | Satyadevi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 5
1815 | Dhading | Satyadevi | 4 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 5 | 5 | 2016-05-13 | 2016-06-11 |  | Khaniyabash | 5
1816 | Dhading | Satyadevi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 5
1817 | Dhading | Satyadevi | 4 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 45 | 2016-04-01 |  |  | Khaniyabash | 5
1818 | Dhading | Satyadevi | 4 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-05-13 | 2016-06-11 |  | Khaniyabash | 5
1819 | Dhading | Satyadevi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 5
1820 | Dhading | Satyadevi | 5 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11 |  | Khaniyabash | 5
1821 | Dhading | Satyadevi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 5
1822 | Dhading | Satyadevi | 5 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01 |  |  | Khaniyabash | 5
1823 | Dhading | Satyadevi | 5 | GON - PAF | COSOC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-10 | 2017-06-16 |  | Khaniyabash | 5
1824 | Dhading | Satyadevi | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 5
1825 | Dhading | Satyadevi | 5 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11 |  | Khaniyabash | 5
1826 | Dhading | Satyadevi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 5
1827 | Dhading | Satyadevi | 6 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 6 | 6 | 2016-05-13 | 2016-06-11 |  | Khaniyabash | 5
1828 | Dhading | Satyadevi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 5
1829 | Dhading | Satyadevi | 6 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01 |  |  | Khaniyabash | 5
1830 | Dhading | Satyadevi | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 5
1831 | Dhading | Satyadevi | 6 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-05-13 | 2016-06-11 |  | Khaniyabash | 5
1832 | Dhading | Satyadevi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 5
1833 | Dhading | Satyadevi | 7 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 6 | 6 | 2016-05-13 | 2016-06-11 |  | Khaniyabash | 5
1834 | Dhading | Satyadevi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 5
1835 | Dhading | Satyadevi | 7 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01 |  |  | Khaniyabash | 5
1836 | Dhading | Satyadevi | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 5
1837 | Dhading | Satyadevi | 7 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-05-13 | 2016-06-11 |  | Khaniyabash | 5
1838 | Dhading | Satyadevi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 5
1839 | Dhading | Satyadevi | 8 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 8 | 8 | 2016-05-13 | 2016-06-11 |  | Khaniyabash | 5
1840 | Dhading | Satyadevi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 5
1841 | Dhading | Satyadevi | 8 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01 |  |  | Khaniyabash | 5
1842 | Dhading | Satyadevi | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 5
1843 | Dhading | Satyadevi | 8 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-05-13 | 2016-06-11 |  | Khaniyabash | 5
1844 | Dhading | Satyadevi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 5
1845 | Dhading | Satyadevi | 9 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11 |  | Khaniyabash | 5
1846 | Dhading | Satyadevi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 5
1847 | Dhading | Satyadevi | 9 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Demonstration Construction | House & Toilet |  | # of constructions | Yes | Completed | 1 | 1 | 2016-10-14 | 2017-05-15 |  | Khaniyabash | 5
1848 | Dhading | Satyadevi | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-10-18 | 2016-12-26 |  | Khaniyabash | 5
1849 | Dhading | Satyadevi | 9 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-11 |  | Khaniyabash | 5
1850 | Dhading | Satyadevi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Khaniyabash | 5
1851 | Dhading | Satyadevi | ALL | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | BBS orintation 2 session in eah ward | # of participants | Yes | Ongoing | 600 | 150 | 2016-04-01 |  |  | Khaniyabash | 5
1852 | Dhading | Satyadevi | all | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 30 | 30 | 2016-12-17 | 2016-12-23 |  | Khaniyabash | 5
1853 | Dhading | Semjong | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 114 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1854 | Dhading | Semjong | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1855 | Dhading | Semjong | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 117 | 7 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1856 | Dhading | Semjong | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 117 | 7 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1857 | Dhading | Semjong | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1858 | Dhading | Semjong | 1 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 1 | 1 | 2016-02-22 | 2016-03-21 |  | Netrawati | 3
1859 | Dhading | Semjong | 1 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-03-29 |  | Netrawati | 3
1860 | Dhading | Semjong | 1 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 1 | 1 | 2016-08-06 | 2016-09-30 | 45 days mason training is specially organized for skilled specific cooperative woman | Netrawati | 3
1861 | Dhading | Semjong | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1862 | Dhading | Semjong | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 64 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1863 | Dhading | Semjong | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1864 | Dhading | Semjong | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 99 | 15 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1865 | Dhading | Semjong | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 99 | 10 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1866 | Dhading | Semjong | 2 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 1 | 1 | 2015-11-27 | 2015-12-06 |  | Netrawati | 3
1867 | Dhading | Semjong | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1868 | Dhading | Semjong | 2 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-03-29 |  | Netrawati | 3
1869 | Dhading | Semjong | 2 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 1 | 1 | 2016-08-06 | 2016-09-30 | 45 days mason training is specially organized for skilled specific cooperative woman | Netrawati | 3
1870 | Dhading | Semjong | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1871 | Dhading | Semjong | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 130 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1872 | Dhading | Semjong | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1873 | Dhading | Semjong | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 91 | 11 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1874 | Dhading | Semjong | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 91 | 9 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1875 | Dhading | Semjong | 3 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 4 | 4 | 2015-11-27 | 2015-12-06 |  | Netrawati | 3
1876 | Dhading | Semjong | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1877 | Dhading | Semjong | 3 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 1 | 1 | 2016-02-22 | 2016-03-21 |  | Netrawati | 3
1878 | Dhading | Semjong | 3 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-03-29 |  | Netrawati | 3
1879 | Dhading | Semjong | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1880 | Dhading | Semjong | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 158 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1881 | Dhading | Semjong | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1882 | Dhading | Semjong | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 115 | 18 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1883 | Dhading | Semjong | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 115 | 16 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1884 | Dhading | Semjong | 4 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 4 | 4 | 2015-11-27 | 2015-12-06 |  | Netrawati | 3
1885 | Dhading | Semjong | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 12 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1886 | Dhading | Semjong | 4 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 6 | 6 | 2016-02-22 | 2016-03-21 |  | Netrawati | 3
1887 | Dhading | Semjong | 4 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 6 | 6 | 2016-03-01 | 2016-03-29 |  | Netrawati | 3
1888 | Dhading | Semjong | 4 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 10 | 10 | 2016-08-06 | 2016-09-30 | 45 days mason training is specially organized for skilled specific cooperative woman | Netrawati | 3
1889 | Dhading | Semjong | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1890 | Dhading | Semjong | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 228 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1891 | Dhading | Semjong | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1892 | Dhading | Semjong | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 139 | 13 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1893 | Dhading | Semjong | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 139 | 12 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1894 | Dhading | Semjong | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-10-18 | 2016-12-26 |  | Netrawati | 3
1895 | Dhading | Semjong | 5 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 6 | 6 | 2015-11-27 | 2015-12-06 |  | Netrawati | 3
1896 | Dhading | Semjong | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 17 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1897 | Dhading | Semjong | 5 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 6 | 6 | 2016-02-22 | 2016-03-21 |  | Netrawati | 3
1898 | Dhading | Semjong | 5 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-03-29 |  | Netrawati | 3
1899 | Dhading | Semjong | 5 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 8 | 8 | 2016-08-06 | 2016-09-30 | 45 days mason training is specially organized for skilled specific cooperative woman | Netrawati | 3
1900 | Dhading | Semjong | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1901 | Dhading | Semjong | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 129 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1902 | Dhading | Semjong | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1903 | Dhading | Semjong | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 112 | 11 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1904 | Dhading | Semjong | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 112 | 12 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1905 | Dhading | Semjong | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Netrawati | 3
1906 | Dhading | Semjong | 6 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 7 | 7 | 2015-11-27 | 2015-12-06 |  | Netrawati | 3
1907 | Dhading | Semjong | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 9 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1908 | Dhading | Semjong | 6 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 5 | 5 | 2016-02-22 | 2016-03-21 |  | Netrawati | 3
1909 | Dhading | Semjong | 6 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 45 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 1 | 1 | 2016-08-06 | 2016-09-30 | 45 days mason training is specially organized for skilled specific cooperative woman | Netrawati | 3
1910 | Dhading | Semjong | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 3
1911 | Dhading | Semjong | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 161 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1912 | Dhading | Semjong | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1913 | Dhading | Semjong | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 72 | 8 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1914 | Dhading | Semjong | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 72 | 11 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1915 | Dhading | Semjong | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Netrawati | 2
1916 | Dhading | Semjong | 7 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 4 | 4 | 2015-11-27 | 2015-12-06 |  | Netrawati | 2
1917 | Dhading | Semjong | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 9 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1918 | Dhading | Semjong | 7 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 5 | 5 | 2016-02-22 | 2016-03-21 |  | Netrawati | 2
1919 | Dhading | Semjong | 7 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 2 | 2 | 2016-03-01 | 2016-03-29 |  | Netrawati | 2
1920 | Dhading | Semjong | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1921 | Dhading | Semjong | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 211 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1922 | Dhading | Semjong | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1923 | Dhading | Semjong | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 135 | 14 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1924 | Dhading | Semjong | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 135 | 8 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1925 | Dhading | Semjong | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-10-18 | 2016-12-26 |  | Netrawati | 2
1926 | Dhading | Semjong | 8 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 2 | 2 | 2015-11-27 | 2015-12-06 |  | Netrawati | 2
1927 | Dhading | Semjong | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 20 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1928 | Dhading | Semjong | 8 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 4 | 4 | 2016-02-22 | 2016-03-21 |  | Netrawati | 2
1929 | Dhading | Semjong | 8 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 3 | 3 | 2016-03-01 | 2016-03-29 |  | Netrawati | 2
1930 | Dhading | Semjong | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1931 | Dhading | Semjong | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 172 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1932 | Dhading | Semjong | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1933 | Dhading | Semjong | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 112 | 19 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1934 | Dhading | Semjong | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 112 | 15 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1935 | Dhading | Semjong | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-10-18 | 2016-12-26 |  | Netrawati | 2
1936 | Dhading | Semjong | 9 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training as per CTEVT Curiculam and approval is taken from DUDBC | # of trainees | Yes | Completed | 2 | 2 | 2015-11-27 | 2015-12-06 |  | Netrawati | 2
1937 | Dhading | Semjong | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 10 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1938 | Dhading | Semjong | 9 | GIZ | GIZ | GIZ | Training | Vocational training | Carpenter (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 2 | 2 | 2016-02-22 | 2016-03-21 |  | Netrawati | 2
1939 | Dhading | Semjong | 9 | GIZ | GIZ | GIZ | Training | Vocational training | Electrician (CTEVT) | 25 days training as per CTEVT Curiculam and approval is taken from DUDBC and DDRC . | # of trainees | Yes | Completed | 3 | 3 | 2016-03-01 | 2016-03-29 |  | Netrawati | 2
1940 | Dhading | Semjong | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Netrawati | 2
1941 | Dhading | Sertung | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 392 | 119 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1942 | Dhading | Sertung | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1943 | Dhading | Sertung | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 118 | 1 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1944 | Dhading | Sertung | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 118 | 4 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1945 | Dhading | Sertung | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 4
1946 | Dhading | Sertung | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 8 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1947 | Dhading | Sertung | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1948 | Dhading | Sertung | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 392 | 26 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1949 | Dhading | Sertung | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1950 | Dhading | Sertung | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 123 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1951 | Dhading | Sertung | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 123 | 4 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1952 | Dhading | Sertung | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 4
1953 | Dhading | Sertung | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1954 | Dhading | Sertung | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1955 | Dhading | Sertung | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 392 | 72 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1956 | Dhading | Sertung | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1957 | Dhading | Sertung | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 76 | 10 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1958 | Dhading | Sertung | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 76 | 7 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1959 | Dhading | Sertung | 3 | GON - PAF | NRCS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-06-16 | 2017-06-22 |  | Rubi Valley | 4
1960 | Dhading | Sertung | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 4
1961 | Dhading | Sertung | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1962 | Dhading | Sertung | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1963 | Dhading | Sertung | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 392 | 88 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1964 | Dhading | Sertung | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1965 | Dhading | Sertung | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 68 | 7 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1966 | Dhading | Sertung | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 68 | 2 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1967 | Dhading | Sertung | 4 | GON - PAF | NRCS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2017-06-16 | 2017-06-22 |  | Rubi Valley | 4
1968 | Dhading | Sertung | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 4
1969 | Dhading | Sertung | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1970 | Dhading | Sertung | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
1971 | Dhading | Sertung | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 392 | 80 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1972 | Dhading | Sertung | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1973 | Dhading | Sertung | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 72 | 3 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1974 | Dhading | Sertung | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 72 | 1 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1975 | Dhading | Sertung | 5 | GON - PAF | NRCS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-06-16 | 2017-06-22 |  | Rubi Valley | 3
1976 | Dhading | Sertung | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 3
1977 | Dhading | Sertung | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1978 | Dhading | Sertung | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1979 | Dhading | Sertung | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 392 | 46 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1980 | Dhading | Sertung | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1981 | Dhading | Sertung | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 60 | 8 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1982 | Dhading | Sertung | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 60 | 20 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1983 | Dhading | Sertung | 6 | GON - PAF | NRCS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-06-16 | 2017-06-22 |  | Rubi Valley | 3
1984 | Dhading | Sertung | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 3
1985 | Dhading | Sertung | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 7 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1986 | Dhading | Sertung | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1987 | Dhading | Sertung | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 392 | 132 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1988 | Dhading | Sertung | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1989 | Dhading | Sertung | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 47 | 4 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1990 | Dhading | Sertung | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 47 | 25 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1991 | Dhading | Sertung | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 3
1992 | Dhading | Sertung | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 37 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1993 | Dhading | Sertung | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1994 | Dhading | Sertung | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 392 | 33 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1995 | Dhading | Sertung | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1996 | Dhading | Sertung | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 88 | 2 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1997 | Dhading | Sertung | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 88 | 15 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
1998 | Dhading | Sertung | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 3
1999 | Dhading | Sertung | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 5 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
2000 | Dhading | Sertung | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 3
2001 | Dhading | Sertung | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 392 | 16 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
2002 | Dhading | Sertung | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
2003 | Dhading | Sertung | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 26 | 1 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
2004 | Dhading | Sertung | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 26 | 2 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
2005 | Dhading | Sertung | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 4
2006 | Dhading | Sertung | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
2007 | Dhading | Sertung | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 4
2008 | Dhading | Tasarpu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 4
2009 | Dhading | Tasarpu | 1 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-08 | 2015-12-12 |  | Thakre | 4
2010 | Dhading | Tasarpu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 4
2011 | Dhading | Tasarpu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 4
2012 | Dhading | Tasarpu | 2 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 4 | 4 | 2015-12-08 | 2015-12-12 |  | Thakre | 4
2013 | Dhading | Tasarpu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 4
2014 | Dhading | Tasarpu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 4
2015 | Dhading | Tasarpu | 3 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 8 | 8 | 2015-12-08 | 2015-12-12 |  | Thakre | 4
2016 | Dhading | Tasarpu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 4
2017 | Dhading | Tasarpu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 4
2018 | Dhading | Tasarpu | 4 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-08 | 2015-12-12 |  | Thakre | 4
2019 | Dhading | Tasarpu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 4
2020 | Dhading | Tasarpu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 5
2021 | Dhading | Tasarpu | 5 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-08 | 2015-12-12 |  | Thakre | 5
2022 | Dhading | Tasarpu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 5
2023 | Dhading | Tasarpu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 5
2024 | Dhading | Tasarpu | 6 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-08 | 2015-12-12 |  | Thakre | 5
2025 | Dhading | Tasarpu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 5
2026 | Dhading | Tasarpu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 5
2027 | Dhading | Tasarpu | 7 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 7 | 7 | 2015-12-08 | 2015-12-12 |  | Thakre | 5
2028 | Dhading | Tasarpu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 5
2029 | Dhading | Tasarpu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 4
2030 | Dhading | Tasarpu | 8 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-08 | 2015-12-12 |  | Thakre | 4
2031 | Dhading | Tasarpu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 4
2032 | Dhading | Tasarpu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 5
2033 | Dhading | Tasarpu | 9 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 8 | 8 | 2015-12-08 | 2015-12-12 |  | Thakre | 5
2034 | Dhading | Tasarpu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 5
2035 | Dhading | Thakre | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 8
2036 | Dhading | Thakre | 1 | GON - PAF | CIRDS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-06-26 | 2017-07-03 |  | Thakre | 8
2037 | Dhading | Thakre | 1 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 6 | 6 | 2015-12-21 | 2015-12-25 |  | Thakre | 8
2038 | Dhading | Thakre | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 8
2039 | Dhading | Thakre | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 8
2040 | Dhading | Thakre | 2 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 2 | 2 | 2015-12-21 | 2015-12-25 |  | Thakre | 8
2041 | Dhading | Thakre | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 8
2042 | Dhading | Thakre | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 6
2043 | Dhading | Thakre | 3 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 2 | 2 | 2015-12-21 | 2015-12-25 |  | Thakre | 6
2044 | Dhading | Thakre | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 6
2045 | Dhading | Thakre | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 7
2046 | Dhading | Thakre | 4 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 15 | 15 | 2015-12-21 | 2015-12-25 |  | Thakre | 7
2047 | Dhading | Thakre | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 7
2048 | Dhading | Thakre | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 7
2049 | Dhading | Thakre | 5 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 3 | 3 | 2015-12-21 | 2015-12-25 |  | Thakre | 7
2050 | Dhading | Thakre | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 7
2051 | Dhading | Thakre | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 7
2052 | Dhading | Thakre | 6 | GON - PAF | CIRDS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-06-26 | 2017-07-03 |  | Thakre | 7
2053 | Dhading | Thakre | 6 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 11 | 11 | 2015-12-21 | 2015-12-25 |  | Thakre | 7
2054 | Dhading | Thakre | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 7
2055 | Dhading | Thakre | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 7
2056 | Dhading | Thakre | 7 | GON - PAF | CIRDS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2017-06-26 | 2017-07-03 |  | Thakre | 7
2057 | Dhading | Thakre | 7 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 12 | 12 | 2015-12-21 | 2015-12-25 |  | Thakre | 7
2058 | Dhading | Thakre | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 7
2059 | Dhading | Thakre | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 7
2060 | Dhading | Thakre | 8 | GON - PAF | CIRDS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-06-26 | 2017-07-03 |  | Thakre | 7
2061 | Dhading | Thakre | 8 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 2 | 2 | 2015-12-21 | 2015-12-25 |  | Thakre | 7
2062 | Dhading | Thakre | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 7
2063 | Dhading | Thakre | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 8
2064 | Dhading | Thakre | 9 | ADRA | RIMS | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason (5 Dyas DUDBC ,Rural) | # of trainees | Yes | Completed | 5 | 5 | 2015-12-21 | 2015-12-25 |  | Thakre | 8
2065 | Dhading | Thakre | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Thakre | 8
2066 | Dhading | Thakre | All | GON - DUDBC | GON - DUDBC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 22 | 22 | 2017-03-05 | 2017-03-11 | Training location is Jewwanpur VDC hall | Thakre | 7
2067 | Dhading | Tipling | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 392 | 38 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2068 | Dhading | Tipling | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2069 | Dhading | Tipling | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 37 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2070 | Dhading | Tipling | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 37 | 9 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2071 | Dhading | Tipling | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 2
2072 | Dhading | Tipling | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 3 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2073 | Dhading | Tipling | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2074 | Dhading | Tipling | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 392 | 62 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2075 | Dhading | Tipling | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2076 | Dhading | Tipling | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 47 | 1 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2077 | Dhading | Tipling | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 47 | 4 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2078 | Dhading | Tipling | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 2
2079 | Dhading | Tipling | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 1 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2080 | Dhading | Tipling | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2081 | Dhading | Tipling | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 392 | 141 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2082 | Dhading | Tipling | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2083 | Dhading | Tipling | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 66 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2084 | Dhading | Tipling | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 66 | 3 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2085 | Dhading | Tipling | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 2
2086 | Dhading | Tipling | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 1 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2087 | Dhading | Tipling | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2088 | Dhading | Tipling | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 392 | 91 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2089 | Dhading | Tipling | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2090 | Dhading | Tipling | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 78 | 2 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2091 | Dhading | Tipling | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 78 | 5 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2092 | Dhading | Tipling | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 2
2093 | Dhading | Tipling | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 2 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2094 | Dhading | Tipling | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2095 | Dhading | Tipling | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 392 | 44 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2096 | Dhading | Tipling | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2097 | Dhading | Tipling | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 65 | 2 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2098 | Dhading | Tipling | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 65 | 10 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2099 | Dhading | Tipling | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 2
2100 | Dhading | Tipling | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 4 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2101 | Dhading | Tipling | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 2
2102 | Dhading | Tipling | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 392 | 160 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2103 | Dhading | Tipling | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2104 | Dhading | Tipling | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 67 | 8 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2105 | Dhading | Tipling | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 67 | 7 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2106 | Dhading | Tipling | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 1
2107 | Dhading | Tipling | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 38 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2108 | Dhading | Tipling | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2109 | Dhading | Tipling | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 392 | 99 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2110 | Dhading | Tipling | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2111 | Dhading | Tipling | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 164 | 32 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2112 | Dhading | Tipling | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 164 | 5 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2113 | Dhading | Tipling | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 15 | 15 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 1
2114 | Dhading | Tipling | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 16 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2115 | Dhading | Tipling | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2116 | Dhading | Tipling | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 392 | 110 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2117 | Dhading | Tipling | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2118 | Dhading | Tipling | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 100 | 1 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2119 | Dhading | Tipling | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 100 | 3 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2120 | Dhading | Tipling | 8 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 1
2121 | Dhading | Tipling | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 17 | 1 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2122 | Dhading | Tipling | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2123 | Dhading | Tipling | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 392 | 224 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2124 | Dhading | Tipling | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2125 | Dhading | Tipling | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 143 | 1 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2126 | Dhading | Tipling | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 143 | 4 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2127 | Dhading | Tipling | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-18 | 2016-12-26 |  | Rubi Valley | 1
2128 | Dhading | Tipling | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 20 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2129 | Dhading | Tipling | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Rubi Valley | 1
2130 | Dhading | Tripureswor | 1 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-06-29 | 2016-07-28 |  | Tripura Sundari | 7
2131 | Dhading | Tripureswor | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 7
2132 | Dhading | Tripureswor | 1 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01 |  |  | Tripura Sundari | 7
2133 | Dhading | Tripureswor | 1 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 7
2134 | Dhading | Tripureswor | 1 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-06-29 | 2016-07-28 |  | Tripura Sundari | 7
2135 | Dhading | Tripureswor | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 7
2136 | Dhading | Tripureswor | 2 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 9 | 9 | 2016-06-29 | 2016-07-28 |  | Tripura Sundari | 7
2137 | Dhading | Tripureswor | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 7
2138 | Dhading | Tripureswor | 2 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01 |  |  | Tripura Sundari | 7
2139 | Dhading | Tripureswor | 2 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 7
2140 | Dhading | Tripureswor | 2 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 9 | 9 | 2016-06-29 | 2016-07-28 |  | Tripura Sundari | 7
2141 | Dhading | Tripureswor | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 7
2142 | Dhading | Tripureswor | 3 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 8 | 8 | 2016-06-29 | 2016-07-28 |  | Tripura Sundari | 7
2143 | Dhading | Tripureswor | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 7
2144 | Dhading | Tripureswor | 3 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Demonstration Construction | House & Toilet |  | # of constructions | Yes | Completed | 1 | 1 | 2016-10-14 | 2017-05-15 |  | Tripura Sundari | 7
2145 | Dhading | Tripureswor | 3 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01 |  |  | Tripura Sundari | 7
2146 | Dhading | Tripureswor | 3 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 7
2147 | Dhading | Tripureswor | 3 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 8 | 8 | 2016-06-29 | 2016-07-28 |  | Tripura Sundari | 7
2148 | Dhading | Tripureswor | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 7
2149 | Dhading | Tripureswor | 4 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 6 | 6 | 2016-06-29 | 2016-07-28 |  | Tripura Sundari | 7
2150 | Dhading | Tripureswor | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 7
2151 | Dhading | Tripureswor | 4 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01 |  |  | Tripura Sundari | 7
2152 | Dhading | Tripureswor | 4 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 7
2153 | Dhading | Tripureswor | 4 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-06-29 | 2016-07-28 |  | Tripura Sundari | 7
2154 | Dhading | Tripureswor | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 7
2155 | Dhading | Tripureswor | 5 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 3 | 3 | 2016-06-29 | 2016-07-28 |  | Tripura Sundari | 7
2156 | Dhading | Tripureswor | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 7
2157 | Dhading | Tripureswor | 5 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01 |  |  | Tripura Sundari | 7
2158 | Dhading | Tripureswor | 5 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 1 | 1 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 7
2159 | Dhading | Tripureswor | 5 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 3 | 3 | 2016-06-29 | 2016-07-28 |  | Tripura Sundari | 7
2160 | Dhading | Tripureswor | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 7
2161 | Dhading | Tripureswor | 6 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 5 | 5 | 2016-06-29 | 2016-07-28 |  | Tripura Sundari | 7
2162 | Dhading | Tripureswor | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 7
2163 | Dhading | Tripureswor | 6 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01 |  |  | Tripura Sundari | 7
2164 | Dhading | Tripureswor | 6 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 7
2165 | Dhading | Tripureswor | 6 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-06-29 | 2016-07-28 |  | Tripura Sundari | 7
2166 | Dhading | Tripureswor | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 7
2167 | Dhading | Tripureswor | 7 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 10 | 10 | 2016-06-29 | 2016-07-28 |  | Tripura Sundari | 7
2168 | Dhading | Tripureswor | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 7
2169 | Dhading | Tripureswor | 7 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01 |  |  | Tripura Sundari | 7
2170 | Dhading | Tripureswor | 7 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 7
2171 | Dhading | Tripureswor | 7 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-06-29 | 2016-07-28 |  | Tripura Sundari | 7
2172 | Dhading | Tripureswor | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 7
2173 | Dhading | Tripureswor | 8 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 5 | 5 | 2016-06-29 | 2016-07-28 |  | Tripura Sundari | 7
2174 | Dhading | Tripureswor | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 7
2175 | Dhading | Tripureswor | 8 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01 |  |  | Tripura Sundari | 7
2176 | Dhading | Tripureswor | 8 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-06-29 | 2016-07-28 |  | Tripura Sundari | 7
2177 | Dhading | Tripureswor | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 7
2178 | Dhading | Tripureswor | 9 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | After Completion of mason training distribute 1 tool kit for each mason | # of kits | Yes | Completed | 5 | 5 | 2016-06-29 | 2016-07-28 |  | Tripura Sundari | 7
2179 | Dhading | Tripureswor | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 7
2180 | Dhading | Tripureswor | 9 | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Establishment of one technical helpdesk in each VDC consist of one sub engineer & one SM for technical assistance | # of households supported | Yes | Ongoing | 75 | 50 | 2016-04-01 |  |  | Tripura Sundari | 7
2181 | Dhading | Tripureswor | 9 | AMDA-M |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-10-18 | 2016-12-26 |  | Tripura Sundari | 7
2182 | Dhading | Tripureswor | 9 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-06-29 | 2016-07-28 |  | Tripura Sundari | 7
2183 | Dhading | Tripureswor | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tripura Sundari | 7
2184 | Dhading | Tripureswor | ALL | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | BBS orintation 2 session in eah ward | # of participants | Yes | Ongoing | 600 | 150 | 2016-04-01 |  |  | Tripura Sundari | 7
2185 | Dhading | Tripureswor | ALL | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Mason ( 7 days DUDBC , Rural) | # of trainees | Yes | Completed | 30 | 29 | 2016-11-30 | 2016-12-06 |  | Tripura Sundari | 7
2186 | Dhading | Kiranchok |  | UMN | PRAYAS-N | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0 | 2017-10-21 | 2016-04-10 |  | Gajuri | 8
2187 | Dhading | Gumdi |  | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0 | 2017-10-22 | 2016-04-10 |  | Gangajamuna | 3
2188 | Dhading | Katunje | 7 | ASF | POURAKHI | CARITAS-L | Financial/Material/Labour Assistance | Top Ups | Vulnerable HHs |  | # of households | Yes | Planned | 25 | 0 |  |  |  | Netrawati | 5
2189 | Dhading | Benighat | All | OXFAM-GB | FOCUS | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Mobile Team consisting of Sub Engineer, Asst. Sub Engineer and SM | # of households | Yes | Ongoing | 935 | 680 | 2017-07-15 | 2018-03-31 |  | Benighat Rorang | 5
2190 | Dhading | Dhussa | All | OXFAM-GB | FOCUS | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Mobile Team consisting of Sub Engineer, Asst. Sub Engineer and SM | # of households | Yes | Ongoing | 525 | 384 | 2017-07-15 | 2018-03-31 |  | Benighat Rorang | 8
2191 | Dhading | Gajuri | All | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Mobile Team consisting of Sub Engineer, Asst. Sub Engineer and SM | # of households | Yes | Ongoing | 1055 | 756 | 2017-07-15 | 2018-03-31 |  | Gajuri | 3
2192 | Dhading | Kiranchok | All | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Mobile Team consisting of Sub Engineer, Asst. Sub Engineer and SM | # of households | Yes | Ongoing | 665 | 486 | 2017-07-15 | 2018-03-31 |  | Gajuri | 8
2193 | Dhading | Pida | All | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Mobile Team consisting of Sub Engineer, Asst. Sub Engineer and SM | # of households | Yes | Ongoing | 1178 | 674 | 2017-07-15 | 2018-03-31 |  | Gajuri | 6
2194 | Dhading | Satyadevi | All | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Mobile Team consisting of Sub Engineer, Asst. Sub Engineer and SM | # of households | Yes | Ongoing | 542 | 348 | 2017-07-15 | 2018-03-31 |  | Khaniyabash | 5
2195 | Dhading | Benighat | All | OXFAM-GB | FOCUS | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Social mobiliser as focal person | # of households supported | Yes | Ongoing | 576 | 265 | 2017-08-01 | 2018-03-31 |  | Benighat Rorang | 5
2196 | Dhading | Dhussa | All | OXFAM-GB | FOCUS | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Social mobiliser as focal person | # of households supported | Yes | Ongoing | 496 | 285 | 2017-08-01 | 2018-03-31 |  | Benighat Rorang | 8
2197 | Dhading | Gajuri | All | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Social mobiliser as focal person | # of households supported | Yes | Ongoing | 680 | 462 | 2017-08-01 | 2018-03-31 |  | Gajuri | 3
2198 | Dhading | Kiranchok | All | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Social mobiliser as focal person | # of households supported | Yes | Ongoing | 360 | 248 | 2017-08-01 | 2018-03-31 |  | Gajuri | 8
2199 | Dhading | Pida | All | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Social mobiliser as focal person | # of households supported | Yes | Ongoing | 364 | 216 | 2017-08-01 | 2018-03-31 |  | Gajuri | 6
2200 | Dhading | Satyadevi | All | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Social mobiliser as focal person | # of households supported | Yes | Planned | 304 | 234 | 2017-08-01 | 2018-03-31 |  | Khaniyabash | 5
2201 | Dhading | Benighat | All | OXFAM-GB | FOCUS | OXFAM-GB | Technical Assistance | Communication and Outreach | Production of IEC materials/manual | Production of IEC materials to support the reconstruction process. | # of copies | Yes | Ongoing | 320 | 274 | 2017-08-01 | 2018-03-31 |  | Benighat Rorang | 5
2202 | Dhading | Dhussa | All | OXFAM-GB | FOCUS | OXFAM-GB | Technical Assistance | Communication and Outreach | Production of IEC materials/manual | Production of IEC materials to support the reconstruction process. | # of copies | Yes | Ongoing | 320 | 218 | 2017-08-01 | 2018-03-31 |  | Benighat Rorang | 8
2203 | Dhading | Gajuri | All | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Communication and Outreach | Production of IEC materials/manual | Production of IEC materials to support the reconstruction process. | # of copies | Yes | Ongoing | 320 | 275 | 2017-08-01 | 2018-03-31 |  | Gajuri | 3
2204 | Dhading | Kiranchok | All | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Communication and Outreach | Production of IEC materials/manual | Production of IEC materials to support the reconstruction process. | # of copies | Yes | Ongoing | 320 | 246 | 2017-08-01 | 2018-03-31 |  | Gajuri | 8
2205 | Dhading | Pida | All | OXFAM-GB | PRAYAS-N | OXFAM-GB | Technical Assistance | Communication and Outreach | Production of IEC materials/manual | Production of IEC materials to support the reconstruction process. | # of copies | Yes | Ongoing | 320 | 268 | 2017-08-01 | 2018-03-31 |  | Gajuri | 6
2206 | Dhading | Satyadevi | All | OXFAM-GB | ACTION-N | OXFAM-GB | Technical Assistance | Communication and Outreach | Production of IEC materials/manual | Production of IEC materials to support the reconstruction process. | # of copies | Yes | Ongoing | 320 | 86 | 2017-08-01 | 2018-03-31 |  | Khaniyabash | 5
2207 | Dhading | Benighat | All | OXFAM-GB | FOCUS | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training on skilled masons according to DUDBC curriculum | # of trainees | Yes | Completed | 30 | 27 | 2017-10-01 | 2018-01-30 |  | Benighat Rorang | 5
2208 | Dhading | Dhussa | All | OXFAM-GB | FOCUS | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 days short training on skilled masons according to DUDBC curriculum | # of trainees | Yes | Completed | 30 | 29 | 2017-10-01 | 2018-01-30 |  | Benighat Rorang | 8
2209 | Dhading | Gajuri | All | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 days short training on skilled masons according to DUDBC curriculum | # of trainees | Yes | Completed | 30 | 27 | 2017-10-01 | 2017-12-30 |  | Gajuri | 3
2210 | Dhading | Kiranchok | All | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 days short training on skilled masons according to DUDBC curriculum | # of trainees | Yes | Completed | 60 | 31 | 2017-08-01 | 2017-12-30 |  | Gajuri | 8
2211 | Dhading | Pida | All | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 days short training on skilled masons according to DUDBC curriculum | # of trainees | Yes | Completed | 30 | 59 | 2017-08-01 | 2017-12-30 |  | Gajuri | 6
2212 | Dhading | Benighat | 3 | OXFAM-GB | FOCUS | OXFAM-GB | Training | Retrofitting training | Skilled construction workers | OJT for the mason on retrofitting | # of trainees | Yes | Completed | 10 | 8 | 2017-09-01 | 2017-12-30 |  | Benighat Rorang | 4
2213 | Dhading | Gajuri | 1 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Retrofitting training | Skilled construction workers | OJT for the mason on retrofitting | # of trainees | Yes | Completed | 10 | 7 | 2017-09-01 | 2017-12-30 |  | Gajuri | 1
2214 | Dhading | Nilkantha N.P. | 8 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Retrofitting training | Skilled construction workers | OJT for the mason on retrofitting | # of trainees | Yes | Completed | 10 | 8 | 2017-09-01 | 2017-12-30 |  | Nilakantha | 8
2215 | Dhading | Nilkantha N.P. | 8 & 9 | OXFAM-GB | ACTION-N | OXFAM-GB | Reconstruction through contractors | Construction | Private house | Construction of private houses for the vulnerable HHs | # of constructions | Yes | Ongoing | 32 | 35 | 2017-09-01 | 2018-03-30 |  | Nilakantha | 9
2216 | Dhading | Nilkantha N.P. | 8 | OXFAM-GB | PRAYAS-N | OXFAM-GB | Training | Other trainings | Other trainings (specify in Activity Detail) | Training on the alternative construction mterials (CSEB) | # of trainees | Yes | Completed | 10 | 20 | 2017-09-01 | 2018-01-31 |  | Nilakantha | 8
2217 | Dhading | Salyantar | all | CARE-N | SAHAS | CARE-F | Training | Short training | Masons (7 days DUDBC, rural or urban) | 28 Women from six different Working VDC Participated | # of trainees | Yes | Completed | 28 | 28 | 2017-11-01 | 2017-11-07 |  | Tripura Sundari | 1
2218 | Dhading | Gumdi | 3 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 24 | 24 | 2017-11-01 | 2017-11-07 |  | Gangajamuna | 3
2219 | Dhading | Gumdi | 4 | UMN | HIMS | UMN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-11-01 | 2017-11-07 |  | Gangajamuna | 3
2220 | Dhading | Nilkantha N.P. | 8 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Construction of private houses for the vulnerable HHs | # of households | Yes | Ongoing | 15 | 0 | 2017-09-01 | 2018-03-31 |  | Nilakantha | 8
2221 | Dhading | Nilkantha N.P. | 9 | OXFAM-GB | ACTION-N | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Construction of private houses for the vulnerable HHs | # of households | Yes | Ongoing | 20 | 0 | 2017-09-01 | 2018-03-31 |  | Nilakantha | 9
2222 | Dhading | Nilkantha N.P. | 9 | OXFAM-GB | ACTION-N | OXFAM-GB | Training | Other trainings | Other trainings (specify in Activity Detail) | Training on the alternative construction mterials (CSEB) | # of trainees | Yes | Completed | 10 | 24 | 2017-09-01 | 2018-01-31 |  | Nilakantha | 9
2223 | Dhading | Kalleri | 1 | NRCS | NRCS | KRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 5 | 2016-01-01 | 2017-12-31 |  | Galchhi | 1
2224 | Dhading | Katunje | 1 | NRCS | NRCS | LRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 11 | 5 | 2016-01-01 | 2017-12-31 |  | Netrawati | 4
2225 | Dhading | Kalleri | 2 | NRCS | NRCS | KRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 4 | 2016-01-01 | 2017-12-31 |  | Galchhi | 1
2226 | Dhading | Katunje | 2 | NRCS | NRCS | LRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 11 | 10 | 2016-01-01 | 2017-12-31 |  | Netrawati | 4
2227 | Dhading | Kalleri | 3 | NRCS | NRCS | KRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 5 | 2016-01-01 | 2017-12-31 |  | Galchhi | 1
2228 | Dhading | Katunje | 3 | NRCS | NRCS | LRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 9 | 1 | 2016-01-01 | 2017-12-31 |  | Netrawati | 4
2229 | Dhading | Kalleri | 4 | NRCS | NRCS | KRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 7 | 2016-01-01 | 2017-12-31 |  | Galchhi | 2
2230 | Dhading | Katunje | 4 | NRCS | NRCS | LRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 42 | 2016-01-01 | 2017-12-31 |  | Netrawati | 4
2231 | Dhading | Kalleri | 5 | NRCS | NRCS | KRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 11 | 2016-01-01 | 2017-12-31 |  | Galchhi | 2
2232 | Dhading | Katunje | 5 | NRCS | NRCS | LRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 9 | 9 | 2016-01-01 | 2017-12-31 |  | Netrawati | 5
2233 | Dhading | Kalleri | 6 | NRCS | NRCS | KRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 6 | 2016-01-01 | 2017-12-31 |  | Galchhi | 2
2234 | Dhading | Katunje | 6 | NRCS | NRCS | LRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 9 | 11 | 2016-01-01 | 2017-12-31 |  | Netrawati | 5
2235 | Dhading | Kalleri | 7 | NRCS | NRCS | KRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 14 | 2016-01-01 | 2017-12-31 |  | Galchhi | 3
2236 | Dhading | Katunje | 7 | NRCS | NRCS | LRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 11 | 4 | 2016-01-01 | 2017-12-31 |  | Netrawati | 5
2237 | Dhading | Kalleri | 8 | NRCS | NRCS | KRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 4 | 2016-01-01 | 2017-12-31 |  | Galchhi | 3
2238 | Dhading | Katunje | 8 | NRCS | NRCS | LRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 9 | 1 | 2016-01-01 | 2017-12-31 |  | Netrawati | 5
2239 | Dhading | Kalleri | 9 | NRCS | NRCS | KRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 4 | 2016-01-01 | 2017-12-31 |  | Galchhi | 3
2240 | Dhading | Katunje | 9 | NRCS | NRCS | LRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 11 | 7 | 2016-01-01 | 2017-12-31 |  | Netrawati | 5
2241 | Dhading | Kalleri | 1 | NRCS | NRCS | KRC | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Ongoing | 44 | 8 | 2016-11-25 | 2016-11-25 | 7-Days Mason Training with tool kits support | Galchhi | 1
2242 | Dhading | Kalleri | 2 | NRCS | NRCS | KRC | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Ongoing | 44 | 28 | 2016-11-26 | 2016-11-26 | 7-Days Mason Training with tool kits support | Galchhi | 1
2243 | Dhading | Kalleri | 3 | NRCS | NRCS | KRC | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Ongoing | 44 | 28 | 2016-11-27 | 2016-11-27 | 7-Days Mason Training with tool kits support | Galchhi | 1
2244 | Dhading | Kalleri | 4 | NRCS | NRCS | KRC | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Ongoing | 45 | 33 | 2016-11-28 | 2016-11-28 | 7-Days Mason Training with tool kits support | Galchhi | 2
2245 | Dhading | Kalleri | 5 | NRCS | NRCS | KRC | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Ongoing | 45 | 4 | 2016-11-29 | 2016-11-29 | 7-Days Mason Training with tool kits support | Galchhi | 2
2246 | Dhading | Kalleri | 6 | NRCS | NRCS | KRC | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Ongoing | 44 | 4 | 2016-11-30 | 2016-11-30 | 7-Days Mason Training with tool kits support | Galchhi | 2
2247 | Dhading | Kalleri | 7 | NRCS | NRCS | KRC | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Ongoing | 45 | 4 | 2016-12-02 | 2016-12-02 | Semi-permanent Truss Building (Model House) | Galchhi | 3
2248 | Dhading | Kalleri | 8 | NRCS | NRCS | KRC | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Ongoing | 45 | 4 | 2016-12-03 | 2016-12-03 | 7-Days Mason Training with tool kits support | Galchhi | 3
2249 | Dhading | Kalleri | 9 | NRCS | NRCS | KRC | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Ongoing | 44 | 4 | 2016-12-04 | 2016-12-04 | 7-Days Mason Training with tool kits support | Galchhi | 3
2250 | Dhading | Katunje | 1 | NRCS | NRCS | LRC | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Ongoing | 8 | 4 | 2016-12-07 | 2016-12-07 | 7-Days Mason Training with tool kits support | Netrawati | 4
2251 | Dhading | Katunje | 2 | NRCS | NRCS | LRC | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Ongoing | 8 | 6 | 2016-12-08 | 2016-12-08 | 7-Days Mason Training with tool kits support | Netrawati | 4
2252 | Dhading | Katunje | 3 | NRCS | NRCS | LRC | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Completed | 8 | 8 | 2016-12-09 | 2016-12-09 | 7-Days Mason Training with tool kits support | Netrawati | 4
2253 | Dhading | Katunje | 4 | NRCS | NRCS | LRC | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Completed | 12 | 12 | 2016-12-11 | 2016-12-11 | 7-Days Mason Training with tool kits support | Netrawati | 4
2254 | Dhading | Katunje | 5 | NRCS | NRCS | LRC | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Completed | 10 | 10 | 2016-12-12 | 2016-12-12 | 7-Days Mason Training with tool kits support | Netrawati | 5
2255 | Dhading | Katunje | 6 | NRCS | NRCS | LRC | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Completed | 8 | 8 | 2016-12-13 | 2016-12-13 | 7-Days Mason Training with tool kits support | Netrawati | 5
2256 | Dhading | Katunje | 7 | NRCS | NRCS | LRC | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Completed | 8 | 8 | 2016-12-15 | 2016-12-15 | 7-Days Mason Training with tool kits support | Netrawati | 5
2257 | Dhading | Katunje | 8 | NRCS | NRCS | LRC | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Completed | 10 | 10 | 2016-12-16 | 2016-12-16 | 7-Days Mason Training with tool kits support | Netrawati | 5
2258 | Dhading | Katunje | 9 | NRCS | NRCS | LRC | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Completed | 8 | 8 | 2016-12-18 | 2016-12-18 | 7-Days Mason Training with tool kits support | Netrawati | 5
2259 | Dhading | Kalleri | 1 | NRCS | NRCS | KRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 111 | 24 | 2016-12-21 | 2017-12-31 | 3-days PASSA roll out at community (Shelter Cluster) | Galchhi | 1
2260 | Dhading | Kalleri | 2 | NRCS | NRCS | KRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 111 | 29 | 2016-12-24 | 2017-12-31 | 3-days PASSA roll out at community (Shelter Cluster) | Galchhi | 1
2261 | Dhading | Kalleri | 3 | NRCS | NRCS | KRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 111 | 28 | 2016-12-25 | 2017-12-31 | 3-days PASSA roll out at community (Shelter Cluster) | Galchhi | 1
2262 | Dhading | Kalleri | 4 | NRCS | NRCS | KRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 111 | 28 | 2016-12-28 | 2017-12-31 | 3-days PASSA roll out at community (Shelter Cluster) | Galchhi | 2
2263 | Dhading | Kalleri | 5 | NRCS | NRCS | KRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 111 | 29 | 2017-01-11 | 2017-12-31 | 3-days PASSA roll out at community (Shelter Cluster) | Galchhi | 2
2264 | Dhading | Kalleri | 6 | NRCS | NRCS | KRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 111 | 28 | 2017-01-15 | 2017-12-31 | 3-days PASSA roll out at community (Shelter Cluster) | Galchhi | 2
2265 | Dhading | Kalleri | 7 | NRCS | NRCS | KRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 111 | 28 | 2017-01-18 | 2017-12-31 | 7-Days Mason Training with tool kits support | Galchhi | 3
2266 | Dhading | Kalleri | 8 | NRCS | NRCS | KRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 111 | 29 | 2017-01-23 | 2017-12-31 | 3-days PASSA roll out at community (Shelter Cluster) | Galchhi | 3
2267 | Dhading | Kalleri | 9 | NRCS | NRCS | KRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 112 | 33 | 2017-01-26 | 2017-12-31 | 3-days PASSA roll out at community (Shelter Cluster) | Galchhi | 3
2268 | Dhading | Katunje | 1 | NRCS | NRCS | LRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 177 | 30 | 2016-12-11 | 2017-12-31 | 3-days PASSA roll out at community (Shelter Cluster) | Netrawati | 4
2269 | Dhading | Katunje | 2 | NRCS | NRCS | LRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 177 | 27 | 2016-12-14 | 2017-12-31 | 3-days PASSA roll out at community (Shelter Cluster) | Netrawati | 4
2270 | Dhading | Katunje | 3 | NRCS | NRCS | LRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 178 | 33 | 2016-12-17 | 2017-12-31 | 3-days PASSA roll out at community (Shelter Cluster) | Netrawati | 4
2271 | Dhading | Katunje | 4 | NRCS | NRCS | LRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 178 | 28 | 2017-01-07 | 2017-12-31 | 3-days PASSA roll out at community (Shelter Cluster) | Netrawati | 4
2272 | Dhading | Katunje | 5 | NRCS | NRCS | LRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 178 | 33 | 2017-01-16 | 2017-12-31 | 3-days PASSA roll out at community (Shelter Cluster) | Netrawati | 5
2273 | Dhading | Katunje | 6 | NRCS | NRCS | LRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 178 | 29 | 2017-01-18 | 2017-12-31 | 3-days PASSA roll out at community (Shelter Cluster) | Netrawati | 5
2274 | Dhading | Katunje | 7 | NRCS | NRCS | LRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 178 | 24 | 2017-01-20 | 2017-12-31 | 3-days PASSA roll out at community (Shelter Cluster) | Netrawati | 5
2275 | Dhading | Katunje | 8 | NRCS | NRCS | LRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 178 | 28 | 2017-01-23 | 2017-12-31 | 3-days PASSA roll out at community (Shelter Cluster) | Netrawati | 5
2276 | Dhading | Katunje | 9 | NRCS | NRCS | LRC | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 178 | 31 | 2017-01-19 | 2017-12-31 | 3-days PASSA roll out at community (Shelter Cluster) | Netrawati | 5
2277 | Dhading | Kalleri | 7 | NRCS | NRCS | KRC | Technical Assistance | Demonstration Construction | House | Semi-permanent Truss Building (Model House) | # of constructions | Yes | Completed | 1 | 1 | 2017-07-29 | 2016-12-31 |  | Galchhi | 3
2278 | Sindhuli | Baseshwor | 4 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-06 | 2017-04-24 |  | Golanjor | 6
2279 | Sindhuli | Baseshwor | 7 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-06 | 2017-04-24 |  | Golanjor | 6
2280 | Sindhuli | Baseshwor | 5 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-06 | 2017-04-24 |  | Golanjor | 6
2281 | Sindhuli | Baseshwor | 6 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-06 | 2017-04-24 |  | Golanjor | 6
2282 | Sindhuli | Bastipur | 2 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-28 | 2017-05-16 |  | Ghanglekh | 2
2283 | Sindhuli | Bastipur | 3 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-28 | 2017-05-16 |  | Ghanglekh | 2
2284 | Sindhuli | Bastipur | 5 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-27 | 2017-05-15 |  | Ghanglekh | 2
2285 | Sindhuli | Bastipur | 6 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-19 | 2017-05-08 |  | Ghanglekh | 2
2286 | Sindhuli | Bastipur | 4 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-23 | 2017-06-13 |  | Ghanglekh | 2
2287 | Sindhuli | Bastipur | 5 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-23 | 2017-06-13 |  | Ghanglekh | 2
2288 | Sindhuli | Bastipur | 3 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-13 | 2017-08-02 |  | Ghanglekh | 2
2289 | Sindhuli | Bastipur | 5 | HELVETAS | BDCC | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-07-01 | 2017-07-07 |  | Ghanglekh | 2
2290 | Sindhuli | Bastipur | 2 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-28 | 2017-05-16 |  | Ghanglekh | 2
2291 | Sindhuli | Bastipur | 3 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-28 | 2017-05-16 |  | Ghanglekh | 2
2292 | Sindhuli | Bastipur | 5 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-27 | 2017-05-15 |  | Ghanglekh | 2
2293 | Sindhuli | Bastipur | 6 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-19 | 2017-05-08 |  | Ghanglekh | 2
2294 | Sindhuli | Bastipur | 4 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-23 | 2017-06-13 |  | Ghanglekh | 2
2295 | Sindhuli | Bastipur | 5 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-23 | 2017-06-13 |  | Ghanglekh | 2
2296 | Sindhuli | Bastipur | 3 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-13 | 2017-08-02 |  | Ghanglekh | 2
2297 | Sindhuli | Bhadrakali | 2 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-01 | 2017-04-20 |  | Kamalamai | 2
2298 | Sindhuli | Bhadrakali | 4 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-10 | 2017-04-29 |  | Kamalamai | 2
2299 | Sindhuli | Bhadrakali | 8 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-05 | 2017-04-24 |  | Kamalamai | 2
2300 | Sindhuli | Bhadrakali | 5 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-02 | 2017-04-20 |  | Kamalamai | 2
2301 | Sindhuli | Bhadrakali | 1 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-02 | 2017-05-21 |  | Kamalamai | 2
2302 | Sindhuli | Bhadrakali | 8 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-12 | 2017-06-24 |  | Kamalamai | 2
2303 | Sindhuli | Bhadrakali | 3 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-10 | 2017-07-30 |  | Kamalamai | 2
2304 | Sindhuli | Bhadrakali | 3 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-12 | 2017-08-01 |  | Kamalamai | 2
2305 | Sindhuli | Bhadrakali | 6 | HELVETAS | BDCC | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-07-03 | 2017-07-10 |  | Kamalamai | 2
2306 | Sindhuli | Bhadrakali | 2 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-01 | 2017-04-20 |  | Kamalamai | 2
2307 | Sindhuli | Bhadrakali | 4 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-10 | 2017-04-29 |  | Kamalamai | 2
2308 | Sindhuli | Bhadrakali | 8 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-05 | 2017-04-24 |  | Kamalamai | 2
2309 | Sindhuli | Bhadrakali | 5 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-02 | 2017-04-20 |  | Kamalamai | 2
2310 | Sindhuli | Bhadrakali | 1 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-02 | 2017-05-21 |  | Kamalamai | 2
2311 | Sindhuli | Bhadrakali | 8 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-12 | 2017-06-24 |  | Kamalamai | 2
2312 | Sindhuli | Bhadrakali | 3 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-10 | 2017-07-30 |  | Kamalamai | 2
2313 | Sindhuli | Bhadrakali | 3 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-12 | 2017-08-01 |  | Kamalamai | 2
2314 | Sindhuli | Bhimeshwor | 1 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-08 | 2017-04-26 |  | Golanjor | 7
2315 | Sindhuli | Bhimeshwor | 4 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-05 | 2017-04-23 |  | Golanjor | 7
2316 | Sindhuli | Bhimeshwor | 9 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-07 | 2017-04-25 |  | Golanjor | 7
2317 | Sindhuli | Bhimeshwor | 8 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-04 | 2017-04-22 |  | Golanjor | 7
2318 | Sindhuli | Bhimeshwor | 7 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-04 | 2017-04-22 |  | Golanjor | 7
2319 | Sindhuli | Bhimeshwor | 5 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-09 | 2017-04-27 |  | Golanjor | 7
2320 | Sindhuli | Bhimeshwor |  | HELVETAS | RIMC | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Golanjor | 7
2321 | Sindhuli | Bhimeshwor | 1 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-08 | 2017-04-26 |  | Golanjor | 7
2322 | Sindhuli | Bhimeshwor | 4 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-05 | 2017-04-23 |  | Golanjor | 7
2323 | Sindhuli | Bhimeshwor | 9 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-07 | 2017-04-25 |  | Golanjor | 7
2324 | Sindhuli | Bhimeshwor | 8 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-04 | 2017-04-22 |  | Golanjor | 7
2325 | Sindhuli | Bhimeshwor | 7 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-04 | 2017-04-22 |  | Golanjor | 7
2326 | Sindhuli | Bhimeshwor | 5 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-09 | 2017-04-27 |  | Golanjor | 7
2327 | Sindhuli | BhuwaneshoriGwaltar |  | HELVETAS | UCEP-N | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Golanjor | 3
2328 | Sindhuli | BhuwaneshoriGwaltar | 2 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-22 | 2017-05-21 |  | Golanjor | 3
2329 | Sindhuli | BhuwaneshoriGwaltar | 9 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-22 | 2017-05-21 |  | Golanjor | 3
2330 | Sindhuli | BhuwaneshoriGwaltar | 5 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-20 | 2017-06-19 |  | Golanjor | 3
2331 | Sindhuli | BhuwaneshoriGwaltar | 1 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-22 | 2017-05-21 |  | Golanjor | 3
2332 | Sindhuli | BhuwaneshoriGwaltar | 4 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-27 | 2017-08-15 |  | Golanjor | 3
2333 | Sindhuli | BhuwaneshoriGwaltar | 6 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-08 | 2017-08-17 |  | Golanjor | 3
2334 | Sindhuli | BhuwaneshoriGwaltar | 2 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-22 | 2017-05-21 |  | Golanjor | 3
2335 | Sindhuli | BhuwaneshoriGwaltar | 9 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-22 | 2017-05-21 |  | Golanjor | 3
2336 | Sindhuli | BhuwaneshoriGwaltar | 5 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-19 |  | Golanjor | 3
2337 | Sindhuli | BhuwaneshoriGwaltar | 1 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-22 | 2017-05-21 |  | Golanjor | 3
2338 | Sindhuli | BhuwaneshoriGwaltar | 4 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-27 | 2017-08-15 |  | Golanjor | 3
2339 | Sindhuli | BhuwaneshoriGwaltar | 6 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-08 | 2017-08-17 |  | Golanjor | 3
2340 | Sindhuli | BitijorBagaiya |  | HELVETAS | UCEP-N | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Golanjor | 2
2341 | Sindhuli | BitijorBagaiya | 2 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-28 | 2017-05-27 |  | Golanjor | 2
2342 | Sindhuli | BitijorBagaiya | 4 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-03 | 2017-06-23 |  | Golanjor | 2
2343 | Sindhuli | BitijorBagaiya | 7 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-10 | 2017-05-30 |  | Golanjor | 2
2344 | Sindhuli | BitijorBagaiya | 5 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-23 | 2017-08-07 |  | Golanjor | 2
2345 | Sindhuli | BitijorBagaiya | 7 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-27 | 2017-08-15 |  | Golanjor | 2
2346 | Sindhuli | BitijorBagaiya | 8 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-12 | 2017-07-02 |  | Golanjor | 2
2347 | Sindhuli | BitijorBagaiya | All | CW |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0 |  |  |  | Golanjor | 2
2348 | Sindhuli | BitijorBagaiya | 2 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-28 | 2017-05-27 |  | Golanjor | 2
2349 | Sindhuli | BitijorBagaiya | 4 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-03 | 2017-06-23 |  | Golanjor | 2
2350 | Sindhuli | BitijorBagaiya | 7 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-10 | 2017-05-30 |  | Golanjor | 2
2351 | Sindhuli | BitijorBagaiya | 5 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-23 | 2017-08-07 |  | Golanjor | 2
2352 | Sindhuli | BitijorBagaiya | 7 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-27 | 2017-08-15 |  | Golanjor | 2
2353 | Sindhuli | BitijorBagaiya | 8 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-12 | 2017-07-02 |  | Golanjor | 2
2354 | Sindhuli | Dadiguranshe | 4 | HELVETAS | MSED | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-21 | 2017-06-27 |  | Kamalamai | 1
2355 | Sindhuli | Dadiguranshe | 7 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-05 | 2017-05-07 |  | Kamalamai | 1
2356 | Sindhuli | Dadiguranshe | 9 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-05 | 2017-05-07 |  | Kamalamai | 1
2357 | Sindhuli | Dadiguranshe | 5 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-22 | 2017-05-25 |  | Kamalamai | 1
2358 | Sindhuli | Dadiguranshe | 5 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-22 | 2017-05-25 |  | Kamalamai | 1
2359 | Sindhuli | Dadiguranshe | 8 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-03 | 2017-07-23 |  | Kamalamai | 1
2360 | Sindhuli | Dadiguranshe | 8 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-03 | 2017-07-23 |  | Kamalamai | 1
2361 | Sindhuli | Dadiguranshe | 8 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-15 | 2017-08-05 |  | Kamalamai | 1
2362 | Sindhuli | Dadiguranshe | 7 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-05 | 2017-05-07 |  | Kamalamai | 1
2363 | Sindhuli | Dadiguranshe | 9 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-05 | 2017-05-07 |  | Kamalamai | 1
2364 | Sindhuli | Dadiguranshe | 5 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-22 | 2017-05-25 |  | Kamalamai | 1
2365 | Sindhuli | Dadiguranshe | 5 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-22 | 2017-05-25 |  | Kamalamai | 1
2366 | Sindhuli | Dadiguranshe | 8 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-03 | 2017-07-23 |  | Kamalamai | 1
2367 | Sindhuli | Dadiguranshe | 8 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-03 | 2017-07-23 |  | Kamalamai | 1
2368 | Sindhuli | Dadiguranshe | 8 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-15 | 2017-08-05 |  | Kamalamai | 1
2369 | Sindhuli | Jalkanya | 9 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-30 | 2017-07-20 |  | Kamalamai | 3
2370 | Sindhuli | Jalkanya | 8 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-30 | 2017-07-20 |  | Kamalamai | 3
2371 | Sindhuli | Jalkanya | 8 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-30 | 2017-07-20 |  | Kamalamai | 3
2372 | Sindhuli | Jalkanya | 8 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-30 | 2017-07-20 |  | Kamalamai | 3
2373 | Sindhuli | Jalkanya | 4 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-30 | 2017-07-20 |  | Kamalamai | 3
2374 | Sindhuli | Jalkanya |  | HELVETAS | RIMC | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Kamalamai | 3
2375 | Sindhuli | Jalkanya | 9 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-30 | 2017-07-20 |  | Kamalamai | 3
2376 | Sindhuli | Jalkanya | 8 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-30 | 2017-07-20 |  | Kamalamai | 3
2377 | Sindhuli | Jalkanya | 8 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-30 | 2017-07-20 |  | Kamalamai | 3
2378 | Sindhuli | Jalkanya | 8 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-30 | 2017-07-20 |  | Kamalamai | 3
2379 | Sindhuli | Jalkanya | 4 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-30 | 2017-07-20 |  | Kamalamai | 3
2380 | Sindhuli | Kalpabrishykha | 3 | HELVETAS | MSED | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-07-07 | 2017-08-01 |  | Marin | 4
2381 | Sindhuli | Kalpabrishykha | 4 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-05 | 2017-05-07 |  | Marin | 4
2382 | Sindhuli | Kalpabrishykha | 6 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-04 | 2017-05-05 |  | Marin | 3
2383 | Sindhuli | Kalpabrishykha | 3 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-30 | 2017-05-30 |  | Marin | 4
2384 | Sindhuli | Kalpabrishykha | 6 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-15 | 2017-08-05 |  | Marin | 3
2385 | Sindhuli | Kalpabrishykha | 8 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-30 | 2017-07-20 |  | Marin | 3
2386 | Sindhuli | Kalpabrishykha | 4 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-05 | 2017-05-07 |  | Marin | 4
2387 | Sindhuli | Kalpabrishykha | 6 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-04 | 2017-05-05 |  | Marin | 3
2388 | Sindhuli | Kalpabrishykha | 3 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-30 | 2017-05-30 |  | Marin | 4
2389 | Sindhuli | Kalpabrishykha | 6 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-15 | 2017-08-05 |  | Marin | 3
2390 | Sindhuli | Kalpabrishykha | 8 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-30 | 2017-07-20 |  | Marin | 3
2391 | Sindhuli | Khangsang | 8 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-28 | 2107-04-18 |  | Phikkal | 4
2392 | Sindhuli | Khangsang | 4 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-23 | 2017-04-13 |  | Phikkal | 4
2393 | Sindhuli | Khangsang | 5 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-28 | 2017-04-18 |  | Phikkal | 4
2394 | Sindhuli | Khangsang | 3 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-23 | 2017-04-13 |  | Phikkal | 4
2395 | Sindhuli | Khangsang | 2 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-25 | 2017-04-15 |  | Phikkal | 4
2396 | Sindhuli | Khangsang | 1 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-03 | 2017-04-21 |  | Phikkal | 4
2397 | Sindhuli | Khangsang | 7 | HELVETAS | AFD | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-07-07 | 2017-07-13 |  | Phikkal | 4
2398 | Sindhuli | Khangsang | 8 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-02-28 | 2107-04-18 |  | Phikkal | 4
2399 | Sindhuli | Khangsang | 4 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-02-23 | 2017-04-13 |  | Phikkal | 4
2400 | Sindhuli | Khangsang | 5 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-02-28 | 2017-04-18 |  | Phikkal | 4
2401 | Sindhuli | Khangsang | 3 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-02-23 | 2017-04-13 |  | Phikkal | 4
2402 | Sindhuli | Khangsang | 2 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-02-25 | 2017-04-15 |  | Phikkal | 4
2403 | Sindhuli | Khangsang | 1 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-03 | 2017-04-21 |  | Phikkal | 4
2404 | Sindhuli | Kholagaun | 3 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-05 | 2017-05-24 |  | Phikkal | 3
2405 | Sindhuli | Kholagaun | 2 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-10 | 2017-05-31 |  | Phikkal | 3
2406 | Sindhuli | Kholagaun | 1 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-17 | 2017-06-06 |  | Phikkal | 3
2407 | Sindhuli | Kholagaun | 4 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-07 | 2017-05-26 |  | Phikkal | 3
2408 | Sindhuli | Kholagaun | 5 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-18 | 2017-06-07 |  | Phikkal | 3
2409 | Sindhuli | Kholagaun | 7 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-17 | 2017-06-06 |  | Phikkal | 3
2410 | Sindhuli | Kholagaun | 8 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-18 | 2017-06-07 |  | Phikkal | 3
2411 | Sindhuli | Kholagaun | 9 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-17 | 2017-06-06 |  | Phikkal | 3
2412 | Sindhuli | Kholagaun | 5 | HELVETAS | AFD | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-07-05 | 2017-07-11 |  | Phikkal | 3
2413 | Sindhuli | Kholagaun | 3 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-05 | 2017-05-24 |  | Phikkal | 3
2414 | Sindhuli | Kholagaun | 2 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-10 | 2017-05-31 |  | Phikkal | 3
2415 | Sindhuli | Kholagaun | 1 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-17 | 2017-06-06 |  | Phikkal | 3
2416 | Sindhuli | Kholagaun | 4 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-07 | 2017-05-26 |  | Phikkal | 3
2417 | Sindhuli | Kholagaun | 5 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-18 | 2017-06-07 |  | Phikkal | 3
2418 | Sindhuli | Kholagaun | 7 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-17 | 2017-06-06 |  | Phikkal | 3
2419 | Sindhuli | Kholagaun | 8 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-18 | 2017-06-07 |  | Phikkal | 3
2420 | Sindhuli | Kholagaun | 9 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-17 | 2017-06-06 |  | Phikkal | 3
2421 | Sindhuli | KusesworDumja | 7 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-26 | 2017-05-15 |  | Sunkoshi | 2
2422 | Sindhuli | KusesworDumja | 9 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-27 | 2017-05-17 |  | Sunkoshi | 1
2423 | Sindhuli | KusesworDumja | 6 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-11 | 2017-06-02 |  | Sunkoshi | 2
2424 | Sindhuli | KusesworDumja | 6 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-10 | 2017-06-01 |  | Sunkoshi | 2
2425 | Sindhuli | KusesworDumja | 9 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-04 | 2017-06-24 |  | Sunkoshi | 1
2426 | Sindhuli | KusesworDumja | 9 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-02 | 2017-07-22 |  | Sunkoshi | 1
2427 | Sindhuli | KusesworDumja | 9 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-10 | 2017-07-30 |  | Sunkoshi | 1
2428 | Sindhuli | KusesworDumja | 9 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-31 | 2017-07-22 |  | Sunkoshi | 1
2429 | Sindhuli | KusesworDumja | 10 | HELVETAS | BDCC | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-23 | 2017-06-30 |  | Sunkoshi | 1
2430 | Sindhuli | KusesworDumja | 6 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-10 | 2017-06-01 |  | Sunkoshi | 2
2431 | Sindhuli | KusesworDumja | 9 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-04 | 2017-06-24 |  | Sunkoshi | 1
2432 | Sindhuli | KusesworDumja | 9 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-02 | 2017-07-22 |  | Sunkoshi | 1
2433 | Sindhuli | KusesworDumja | 9 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-10 | 2017-07-30 |  | Sunkoshi | 1
2434 | Sindhuli | KusesworDumja | 9 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-31 | 2017-07-22 |  | Sunkoshi | 1
2435 | Sindhuli | KusesworDumja | 7 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-26 | 2017-05-15 |  | Sunkoshi | 2
2436 | Sindhuli | KusesworDumja | 9 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-27 | 2017-05-17 |  | Sunkoshi | 1
2437 | Sindhuli | KusesworDumja | 6 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-11 | 2017-06-02 |  | Sunkoshi | 2
2438 | Sindhuli | Kyaneshwor | 3 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-05 | 2017-06-05 |  | Hariharpurgadhi | 8
2439 | Sindhuli | Kyaneshwor | 5 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-30 | 2017-05-30 |  | Hariharpurgadhi | 8
2440 | Sindhuli | Kyaneshwor | 5 | HELVETAS | MSED | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-07-03 | 2017-07-09 |  | Hariharpurgadhi | 8
2441 | Sindhuli | Kyaneshwor | 3 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-05 | 2017-06-05 |  | Hariharpurgadhi | 8
2442 | Sindhuli | Kyaneshwor | 5 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-30 | 2017-05-30 |  | Hariharpurgadhi | 8
2443 | Sindhuli | Mahadevsthan | 7 | HELVETAS | MSED | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-07-07 | 2017-07-13 |  | Marin | 8
2444 | Sindhuli | Mahadevsthan | 8 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-15 | 2017-08-05 |  | Marin | 8
2445 | Sindhuli | Mahadevdada | 8 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-25 | 2017-04-15 |  | Phikkal | 1
2446 | Sindhuli | Mahadevdada | 2 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-25 | 2017-04-15 |  | Phikkal | 1
2447 | Sindhuli | Mahadevdada | 3 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-09 | 2017-04-27 |  | Phikkal | 1
2448 | Sindhuli | Mahadevdada | 9 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-15 | 2017-05-02 |  | Phikkal | 1
2449 | Sindhuli | Mahadevdada | 8 | HELVETAS | AFD | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-07-07 | 2017-07-13 |  | Phikkal | 1
2450 | Sindhuli | Mahadevdada | 8 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-02-25 | 2017-04-15 |  | Phikkal | 1
2451 | Sindhuli | Mahadevdada | 2 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-02-25 | 2017-04-15 |  | Phikkal | 1
2452 | Sindhuli | Mahadevdada | 3 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-09 | 2017-04-27 |  | Phikkal | 1
2453 | Sindhuli | Mahadevdada | 9 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-15 | 2017-05-02 |  | Phikkal | 1
2454 | Sindhuli | Mahadevsthan | 8 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-15 | 2017-08-05 |  | Marin | 8
2455 | Sindhuli | Mahadevsthan | 6 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-04 | 2017-05-05 |  | Marin | 8
2456 | Sindhuli | Mahadevsthan | 5 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-04 | 2017-05-05 |  | Marin | 8
2457 | Sindhuli | Mahadevsthan | 2 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-04 | 2017-05-05 |  | Marin | 5
2458 | Sindhuli | Mahadevsthan | 2 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-04 | 2017-05-05 |  | Marin | 5
2459 | Sindhuli | Mahadevsthan | 8 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-27 | 2017-05-30 |  | Marin | 8
2460 | Sindhuli | Mahadevsthan | 5 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-17 | 2017-06-19 |  | Marin | 8
2461 | Sindhuli | Mahadevsthan | 6 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-23 | 2017-06-25 |  | Marin | 8
2462 | Sindhuli | Mahadevsthan | 8 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-15 | 2017-08-05 |  | Marin | 8
2463 | Sindhuli | Mahadevsthan | 3 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-30 | 2017-07-20 |  | Marin | 5
2464 | Sindhuli | Mahadevsthan | 2 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-30 | 2017-07-20 |  | Marin | 5
2465 | Sindhuli | Mahadevsthan | 6 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-04 | 2017-05-05 |  | Marin | 8
2466 | Sindhuli | Mahadevsthan | 5 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-04 | 2017-05-05 |  | Marin | 8
2467 | Sindhuli | Mahadevsthan | 2 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-04 | 2017-05-05 |  | Marin | 5
2468 | Sindhuli | Mahadevsthan | 2 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-04 | 2017-05-05 |  | Marin | 5
2469 | Sindhuli | Mahadevsthan | 8 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-27 | 2017-05-30 |  | Marin | 8
2470 | Sindhuli | Mahadevsthan | 5 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-17 | 2017-06-19 |  | Marin | 8
2471 | Sindhuli | Mahadevsthan | 6 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-23 | 2017-06-25 |  | Marin | 8
2472 | Sindhuli | Mahadevsthan | 8 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-15 | 2017-08-05 |  | Marin | 8
2473 | Sindhuli | Mahadevsthan | 3 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-30 | 2017-07-20 |  | Marin | 5
2474 | Sindhuli | Mahadevsthan | 2 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-30 | 2017-07-20 |  | Marin | 5
2475 | Sindhuli | Mahendrajhayadi | 5 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-15 | 2017-08-05 |  | Hariharpurgadhi | 4
2476 | Sindhuli | Mahendrajhayadi | 2 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-21 | 2017-05-25 |  | Hariharpurgadhi | 4
2477 | Sindhuli | Mahendrajhayadi | 6 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-30 | 2017-07-20 |  | Hariharpurgadhi | 5
2478 | Sindhuli | Mahendrajhayadi | 7 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-30 | 2017-07-20 |  | Hariharpurgadhi | 5
2479 | Sindhuli | Mahendrajhayadi | 5 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-15 | 2017-08-05 |  | Hariharpurgadhi | 4
2480 | Sindhuli | Mahendrajhayadi | 3 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-21 | 2017-05-25 |  | Hariharpurgadhi | 4
2481 | Sindhuli | Mahendrajhayadi | 4 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-21 | 2017-05-25 |  | Hariharpurgadhi | 4
2482 | Sindhuli | Mahendrajhayadi | 3 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-21 | 2017-05-25 |  | Hariharpurgadhi | 4
2483 | Sindhuli | Mahendrajhayadi | 4 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-21 | 2017-05-25 |  | Hariharpurgadhi | 4
2484 | Sindhuli | Mahendrajhayadi | 2 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-21 | 2017-05-25 |  | Hariharpurgadhi | 4
2485 | Sindhuli | Mahendrajhayadi | 3 | HELVETAS | MSED | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-07-01 | 2017-07-07 |  | Hariharpurgadhi | 4
2486 | Sindhuli | Mahendrajhayadi | 6 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-30 | 2017-07-20 |  | Hariharpurgadhi | 5
2487 | Sindhuli | Mahendrajhayadi | 7 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-30 | 2017-07-20 |  | Hariharpurgadhi | 5
2488 | Sindhuli | Majhuwa | 3 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-21 | 2017-06-09 |  | Sunkoshi | 7
2489 | Sindhuli | Majhuwa | 2 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-26 | 2017-06-06 |  | Sunkoshi | 7
2490 | Sindhuli | Majhuwa | 9 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-29 | 2017-06-17 |  | Sunkoshi | 7
2491 | Sindhuli | Majhuwa | 7 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-29 | 2017-06-10 |  | Sunkoshi | 7
2492 | Sindhuli | Majhuwa | 5 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-29 | 2017-07-11 |  | Sunkoshi | 7
2493 | Sindhuli | Majhuwa | 8 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-30 | 2017-07-20 |  | Sunkoshi | 7
2494 | Sindhuli | Majhuwa |  | HELVETAS | RIMC | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Sunkoshi | 7
2495 | Sindhuli | Majhuwa | 3 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-21 | 2017-06-09 |  | Sunkoshi | 7
2496 | Sindhuli | Majhuwa | 2 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-26 | 2017-06-06 |  | Sunkoshi | 7
2497 | Sindhuli | Majhuwa | 9 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-29 | 2017-06-17 |  | Sunkoshi | 7
2498 | Sindhuli | Majhuwa | 7 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-29 | 2017-06-10 |  | Sunkoshi | 7
2499 | Sindhuli | Majhuwa | 5 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-29 | 2017-07-11 |  | Sunkoshi | 7
2500 | Sindhuli | Majhuwa | 8 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-30 | 2017-07-20 |  | Sunkoshi | 7
2501 | Sindhuli | Netrakali | 9 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-09 | 2017-05-29 |  | Ghanglekh | 4
2502 | Sindhuli | Netrakali | 1 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-09 | 2017-05-29 |  | Ghanglekh | 4
2503 | Sindhuli | Netrakali | 9 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-19 | 2017-06-08 |  | Ghanglekh | 4
2504 | Sindhuli | Netrakali | 3 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-19 | 2017-06-09 |  | Ghanglekh | 4
2505 | Sindhuli | Netrakali | 9 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-11 | 2017-07-31 |  | Ghanglekh | 4
2506 | Sindhuli | Netrakali | 1 | HELVETAS | BDCC | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-07-06 | 2017-07-11 |  | Ghanglekh | 4
2507 | Sindhuli | Netrakali | 9 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-09 | 2017-05-29 |  | Ghanglekh | 4
2508 | Sindhuli | Netrakali | 1 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-09 | 2017-05-29 |  | Ghanglekh | 4
2509 | Sindhuli | Netrakali | 9 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-19 | 2017-06-08 |  | Ghanglekh | 4
2510 | Sindhuli | Netrakali | 3 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-19 | 2017-06-09 |  | Ghanglekh | 4
2511 | Sindhuli | Netrakali | 9 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-11 | 2017-07-31 |  | Ghanglekh | 4
2512 | Sindhuli | Pipalmadi | 1 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-10 | 2017-05-12 |  | Hariharpurgadhi | 2
2513 | Sindhuli | Pipalmadi | 3 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-10 | 2017-05-12 |  | Hariharpurgadhi | 3
2514 | Sindhuli | Pipalmadi | 9 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-09 | 2017-06-09 |  | Hariharpurgadhi | 2
2515 | Sindhuli | Pipalmadi | 9 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-09 | 2017-06-09 |  | Hariharpurgadhi | 2
2516 | Sindhuli | Pipalmadi | 9 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-17 | 2017-06-19 |  | Hariharpurgadhi | 2
2517 | Sindhuli | Pipalmadi | 1 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-30 | 2017-07-20 |  | Hariharpurgadhi | 2
2518 | Sindhuli | Pipalmadi | 9 | HELVETAS | MSED | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-03 | 2017-07-23 |  | Hariharpurgadhi | 2
2519 | Sindhuli | Pipalmadi | 2 | HELVETAS | MSED | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-23 | 2017-06-30 |  | Hariharpurgadhi | 2
2520 | Sindhuli | Pipalmadi | 6 | HELVETAS | MSED | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-23 | 2017-06-30 |  | Hariharpurgadhi | 3
2521 | Sindhuli | Pipalmadi | 1 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-10 | 2017-05-12 |  | Hariharpurgadhi | 2
2522 | Sindhuli | Pipalmadi | 3 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-10 | 2017-05-12 |  | Hariharpurgadhi | 3
2523 | Sindhuli | Pipalmadi | 9 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-09 | 2017-06-09 |  | Hariharpurgadhi | 2
2524 | Sindhuli | Pipalmadi | 9 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-09 | 2017-06-09 |  | Hariharpurgadhi | 2
2525 | Sindhuli | Pipalmadi | 9 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-17 | 2017-06-19 |  | Hariharpurgadhi | 2
2526 | Sindhuli | Pipalmadi | 1 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-30 | 2017-07-20 |  | Hariharpurgadhi | 2
2527 | Sindhuli | Pipalmadi | 9 | HELVETAS | MSED | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-03 | 2017-07-23 |  | Hariharpurgadhi | 2
2528 | Sindhuli | PuranoJhangajholi | 3 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-19 | 2017-06-07 |  | Sunkoshi | 5
2529 | Sindhuli | PuranoJhangajholi | 8 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-08 | 2017-05-29 |  | Sunkoshi | 5
2530 | Sindhuli | PuranoJhangajholi | 8 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-08 | 2017-05-29 |  | Sunkoshi | 5
2531 | Sindhuli | PuranoJhangajholi | 6 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-19 | 2017-06-07 |  | Sunkoshi | 5
2532 | Sindhuli | PuranoJhangajholi |  | HELVETAS | RIMC | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Sunkoshi | 5
2533 | Sindhuli | PuranoJhangajholi | 6 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-28 | 2017-06-16 |  | Sunkoshi | 5
2534 | Sindhuli | PuranoJhangajholi | 8 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-08 | 2017-05-29 |  | Sunkoshi | 5
2535 | Sindhuli | PuranoJhangajholi | 8 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-08 | 2017-05-29 |  | Sunkoshi | 5
2536 | Sindhuli | PuranoJhangajholi | 6 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-19 | 2017-06-07 |  | Sunkoshi | 5
2537 | Sindhuli | PuranoJhangajholi | 3 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-19 | 2017-06-07 |  | Sunkoshi | 5
2538 | Sindhuli | PuranoJhangajholi | 6 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-28 | 2017-06-16 |  | Sunkoshi | 5
2539 | Sindhuli | Ranichuri | 8 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-20 |  | Kamalamai | 12
2540 | Sindhuli | Ranichuri | 7 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-19 | 2017-05-18 |  | Kamalamai | 12
2541 | Sindhuli | Ranichuri | 5 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-19 | 2017-05-18 |  | Kamalamai | 11
2542 | Sindhuli | Ranichuri | 3 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2017-07-07 | 2017-08-27 |  | Kamalamai | 11
2543 | Sindhuli | Ranichuri | 3 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-19 | 2017-05-18 |  | Kamalamai | 11
2544 | Sindhuli | Ranichuri | 5 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-17 | 2017-07-06 |  | Kamalamai | 11
2545 | Sindhuli | Ranichuri |  | HELVETAS | UCEP-N | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Kamalamai | 12
2546 | Sindhuli | Ranichuri | 8 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-20 | 2017-06-20 |  | Kamalamai | 12
2547 | Sindhuli | Ranichuri | 7 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-19 | 2017-05-18 |  | Kamalamai | 12
2548 | Sindhuli | Ranichuri | 5 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-19 | 2017-05-18 |  | Kamalamai | 11
2549 | Sindhuli | Ranichuri | 3 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Ongoing | 2 | 2 | 2017-07-07 | 2017-08-27 |  | Kamalamai | 11
2550 | Sindhuli | Ranichuri | 3 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-19 | 2017-05-18 |  | Kamalamai | 11
2551 | Sindhuli | Ranichuri | 5 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-17 | 2017-07-06 |  | Kamalamai | 11
2552 | Sindhuli | Ratanchura | 7 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-28 | 2017-06-16 |  | Golanjor | 5
2553 | Sindhuli | Ratanchura | 2 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-22 | 2017-05-10 |  | Golanjor | 5
2554 | Sindhuli | Ratanchura | 8 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-18 | 2017-03-06 |  | Golanjor | 5
2555 | Sindhuli | Ratanchura | 8 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-18 | 2017-03-06 |  | Golanjor | 5
2556 | Sindhuli | Ratanchura | 9 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-18 | 2017-03-06 |  | Golanjor | 5
2557 | Sindhuli | Ratanchura | 1 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-29 | 2017-05-17 |  | Golanjor | 5
2558 | Sindhuli | Ratanchura | 8 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-18 | 2017-05-06 |  | Golanjor | 5
2559 | Sindhuli | Ratanchura | 1 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-22 | 2017-05-10 |  | Golanjor | 5
2560 | Sindhuli | Ratanchura | 2 | HELVETAS | RIMC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-30 | 2017-07-23 |  | Golanjor | 5
2561 | Sindhuli | Ratanchura |  | HELVETAS | RIMC | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Golanjor | 5
2562 | Sindhuli | Ratanchura | 7 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-28 | 2017-06-16 |  | Golanjor | 5
2563 | Sindhuli | Ratanchura | 2 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-22 | 2017-05-10 |  | Golanjor | 5
2564 | Sindhuli | Ratanchura | 8 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-18 | 2017-03-06 |  | Golanjor | 5
2565 | Sindhuli | Ratanchura | 8 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-18 | 2017-03-06 |  | Golanjor | 5
2566 | Sindhuli | Ratanchura | 9 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-18 | 2017-03-06 |  | Golanjor | 5
2567 | Sindhuli | Ratanchura | 1 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-29 | 2017-05-17 |  | Golanjor | 5
2568 | Sindhuli | Ratanchura | 8 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-18 | 2017-05-06 |  | Golanjor | 5
2569 | Sindhuli | Ratanchura | 1 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-22 | 2017-05-10 |  | Golanjor | 5
2570 | Sindhuli | Ratanchura | 2 | HELVETAS | RIMC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-30 | 2017-07-23 |  | Golanjor | 5
2571 | Sindhuli | Ratnawati | 1 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-01 | 2017-06-20 |  | Phikkal | 6
2572 | Sindhuli | Ratnawati | 8 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-01 | 2017-06-20 |  | Phikkal | 6
2573 | Sindhuli | Ratnawati | 6 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-05-01 | 2017-06-20 |  | Phikkal | 6
2574 | Sindhuli | Ratnawati | 3 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-19 | 2017-08-03 |  | Phikkal | 6
2575 | Sindhuli | Ratnawati | 2 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-24 | 2017-08-08 |  | Phikkal | 6
2576 | Sindhuli | Ratnawati | 4 | HELVETAS | AFD | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-07-05 | 2017-07-11 |  | Phikkal | 6
2577 | Sindhuli | Ratnawati | 1 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-01 | 2017-06-20 |  | Phikkal | 6
2578 | Sindhuli | Ratnawati | 8 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-01 | 2017-06-20 |  | Phikkal | 6
2579 | Sindhuli | Ratnawati | 6 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-01 | 2017-06-20 |  | Phikkal | 6
2580 | Sindhuli | Ratnawati | 3 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-19 | 2017-08-03 |  | Phikkal | 6
2581 | Sindhuli | Ratnawati | 2 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-24 | 2017-08-08 |  | Phikkal | 6
2582 | Sindhuli | Santeswori(Rampur) | 5 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-05 | 2017-05-25 |  | Ghanglekh | 5
2583 | Sindhuli | Santeswori(Rampur) | 2 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-05 | 2017-05-25 |  | Ghanglekh | 5
2584 | Sindhuli | Santeswori(Rampur) | 7 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-21 | 2017-06-11 |  | Ghanglekh | 5
2585 | Sindhuli | Santeswori(Rampur) | 1 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-06-11 | 2017-07-31 |  | Ghanglekh | 5
2586 | Sindhuli | Santeswori(Rampur) | 7 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-21 | 2017-06-11 |  | Ghanglekh | 5
2587 | Sindhuli | Santeswori(Rampur) | 1 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-11 | 2017-07-31 |  | Ghanglekh | 5
2588 | Sindhuli | Santeswori(Rampur) | 2 | HELVETAS | BDCC | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-07-13 | 2017-07-19 |  | Ghanglekh | 5
2589 | Sindhuli | Santeswori(Rampur) | All | CW |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0 |  |  |  | Ghanglekh | 5
2590 | Sindhuli | Santeswori(Rampur) | 5 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-05 | 2017-05-25 |  | Ghanglekh | 5
2591 | Sindhuli | Santeswori(Rampur) | 2 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-05 | 2017-05-25 |  | Ghanglekh | 5
2592 | Sindhuli | Solpathana | 3 | HELVETAS | AFD | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-19 | 2017-06-25 |  | Phikkal | 5
2593 | Sindhuli | Solpathana | 9 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-25 | 2017-04-15 |  | Phikkal | 5
2594 | Sindhuli | Solpathana | 8 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-28 | 2017-04-18 |  | Phikkal | 5
2595 | Sindhuli | Solpathana | 2 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-25 | 2017-04-15 |  | Phikkal | 5
2596 | Sindhuli | Solpathana | 5 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-23 | 2017-04-13 |  | Phikkal | 5
2597 | Sindhuli | Solpathana | 4 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-09 | 2017-04-27 |  | Phikkal | 5
2598 | Sindhuli | Solpathana | 9 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-02-25 | 2017-04-15 |  | Phikkal | 5
2599 | Sindhuli | Solpathana | 8 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-02-28 | 2017-04-18 |  | Phikkal | 5
2600 | Sindhuli | Solpathana | 2 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-02-25 | 2017-04-15 |  | Phikkal | 5
2601 | Sindhuli | Solpathana | 5 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-02-23 | 2017-04-13 |  | Phikkal | 5
2602 | Sindhuli | Solpathana | 4 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-02-09 | 2017-04-27 |  | Phikkal | 5
2603 | Sindhuli | SunamPokhari | 1 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-02-23 | 2017-04-13 |  | Phikkal | 2
2604 | Sindhuli | SunamPokhari | 2 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-02-23 | 2017-04-13 |  | Phikkal | 2
2605 | Sindhuli | SunamPokhari | 3 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-02-23 | 2017-04-13 |  | Phikkal | 2
2606 | Sindhuli | SunamPokhari | 8 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-02-23 | 2017-04-13 |  | Phikkal | 2
2607 | Sindhuli | SunamPokhari | 6 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-03 | 2017-05-22 |  | Phikkal | 2
2608 | Sindhuli | SunamPokhari | 7 | HELVETAS | AFD | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-03 | 2017-05-22 |  | Phikkal | 2
2609 | Sindhuli | SunamPokhari | 2 | HELVETAS | AFD | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-07-05 | 2017-07-11 |  | Phikkal | 2
2610 | Sindhuli | SunamPokhari | 1 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-23 | 2017-04-13 |  | Phikkal | 2
2611 | Sindhuli | SunamPokhari | 2 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-23 | 2017-04-13 |  | Phikkal | 2
2612 | Sindhuli | SunamPokhari | 3 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-23 | 2017-04-13 |  | Phikkal | 2
2613 | Sindhuli | SunamPokhari | 8 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-23 | 2017-04-13 |  | Phikkal | 2
2614 | Sindhuli | SunamPokhari | 6 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-03 | 2017-05-22 |  | Phikkal | 2
2615 | Sindhuli | SunamPokhari | 7 | HELVETAS | AFD | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-03 | 2017-05-22 |  | Phikkal | 2
2616 | Sindhuli | Tamajor | 5 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-07 | 2017-05-27 |  | Ghanglekh | 3
2617 | Sindhuli | Tamajor | 9 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-07 | 2017-05-27 |  | Ghanglekh | 3
2618 | Sindhuli | Tamajor | 2 | HELVETAS | BDCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-11 | 2017-05-16 |  | Ghanglekh | 3
2619 | Sindhuli | Tamajor | 3 | HELVETAS | BDCC | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-25 | 2017-07-01 |  | Ghanglekh | 3
2620 | Sindhuli | Tamajor | 5 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-07 | 2017-05-27 |  | Ghanglekh | 3
2621 | Sindhuli | Tamajor | 9 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-07 | 2017-05-27 |  | Ghanglekh | 3
2622 | Sindhuli | Tamajor | 2 | HELVETAS | BDCC | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-11 | 2017-05-16 |  | Ghanglekh | 3
2623 | Sindhuli | Tinkanya | 8 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-17 | 2017-05-16 |  | Golanjor | 4
2624 | Sindhuli | Tinkanya | 7 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-10 | 2017-06-09 |  | Golanjor | 4
2625 | Sindhuli | Tinkanya | 5 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-18 | 2017-05-17 |  | Golanjor | 4
2626 | Sindhuli | Tinkanya | 2 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-17 | 2017-05-16 |  | Golanjor | 4
2627 | Sindhuli | Tinkanya | 1 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-17 | 2017-05-16 |  | Golanjor | 4
2628 | Sindhuli | Tinkanya | 6 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-18 | 2017-05-17 |  | Golanjor | 4
2629 | Sindhuli | Tinkanya |  | HELVETAS | UCEP-N | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Golanjor | 4
2630 | Sindhuli | Tinkanya | 8 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-17 | 2017-05-16 |  | Golanjor | 4
2631 | Sindhuli | Tinkanya | 7 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-10 | 2017-06-09 |  | Golanjor | 4
2632 | Sindhuli | Tinkanya | 5 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-18 | 2017-05-17 |  | Golanjor | 4
2633 | Sindhuli | Tinkanya | 2 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-17 | 2017-05-16 |  | Golanjor | 4
2634 | Sindhuli | Tinkanya | 1 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-17 | 2017-05-16 |  | Golanjor | 4
2635 | Sindhuli | Tinkanya | 6 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-18 | 2017-05-17 |  | Golanjor | 4
2636 | Sindhuli | Tosramkhola | 2 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-02 | 2017-06-01 |  | Tinpatan | 7
2637 | Sindhuli | Tosramkhola | 8 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-27 | 2017-05-26 |  | Tinpatan | 7
2638 | Sindhuli | Tosramkhola | 9 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-02 | 2017-06-01 |  | Tinpatan | 7
2639 | Sindhuli | Tosramkhola | 3 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-20 | 2017-06-19 |  | Tinpatan | 7
2640 | Sindhuli | Tosramkhola | 5 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-03-27 | 2017-05-26 |  | Tinpatan | 7
2641 | Sindhuli | Tosramkhola | 7 | HELVETAS | UCEP-N | DFID | Technical Assistance | Demonstration Construction | House | demo house has constructed during training | # of constructions | Yes | Completed | 2 | 2 | 2017-04-02 | 2017-06-01 |  | Tinpatan | 7
2642 | Sindhuli | Tosramkhola | 2 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-02 | 2017-06-01 |  | Tinpatan | 7
2643 | Sindhuli | Tosramkhola | 8 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-27 | 2017-05-26 |  | Tinpatan | 7
2644 | Sindhuli | Tosramkhola | 9 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-02 | 2017-06-01 |  | Tinpatan | 7
2645 | Sindhuli | Tosramkhola | 3 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-19 |  | Tinpatan | 7
2646 | Sindhuli | Tosramkhola | 5 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-27 | 2017-05-26 |  | Tinpatan | 7
2647 | Sindhuli | Tosramkhola | 7 | HELVETAS | UCEP-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-02 | 2017-06-01 |  | Tinpatan | 7
2648 | Sindhuli | Tosramkhola |  | HELVETAS | UCEP-N | DFID | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 10 | 10 | 2017-08-10 | 2017-08-17 |  | Tinpatan | 7
2649 | Sindhuli | PuranoJhangajholi | 5 | HELVETAS | RIMC | BC | Training | Retrofitting training | Skilled construction workers |  | # of trainees | Yes | Ongoing | 20 | 10 | 2017-12-28 | 2018-02-11 |  | Sunkoshi | 5
2650 | Sindhuli | Dudbhanjyang | 1 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 9 | 2017-03-22 | 2017-05-09 |  | Golanjor | 1
2651 | Sindhuli | Dudbhanjyang | 1 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-22 | 2017-05-09 |  | Golanjor | 1
2652 | Sindhuli | Dudbhanjyang | 1 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 7 | 20 | 2017-03-03 | 2017-03-11 |  | Golanjor | 1
2653 | Sindhuli | Dudbhanjyang | 2 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 3 | 2017-03-22 | 2017-05-09 |  | Golanjor | 1
2654 | Sindhuli | Dudbhanjyang | 2 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Golanjor | 1
2655 | Sindhuli | Dudbhanjyang | 2 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 7 | 7 |  |  |  | Golanjor | 1
2656 | Sindhuli | Dudbhanjyang | 3 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 9 |  |  |  | Golanjor | 1
2657 | Sindhuli | Dudbhanjyang | 3 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Golanjor | 1
2658 | Sindhuli | Dudbhanjyang | 3 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 7 | 7 | 2017-04-05 | 2017-04-14 |  | Golanjor | 1
2659 | Sindhuli | Dudbhanjyang | 4 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 9 |  |  |  | Golanjor | 1
2660 | Sindhuli | Dudbhanjyang | 4 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Golanjor | 1
2661 | Sindhuli | Dudbhanjyang | 4 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 6 | 8 | 2017-04-05 | 2017-08-19 |  | Golanjor | 1
2662 | Sindhuli | Dudbhanjyang | 5 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 1 | 2017-03-22 | 2017-05-09 |  | Golanjor | 1
2663 | Sindhuli | Dudbhanjyang | 5 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Golanjor | 1
2664 | Sindhuli | Dudbhanjyang | 5 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 7 | 2 | 2017-04-05 | 2017-04-14 |  | Golanjor | 1
2665 | Sindhuli | Dudbhanjyang | 6 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 5 | 2017-03-22 | 2017-05-09 |  | Golanjor | 1
2666 | Sindhuli | Dudbhanjyang | 6 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-22 | 2017-05-09 |  | Golanjor | 1
2667 | Sindhuli | Dudbhanjyang | 6 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Golanjor | 1
2668 | Sindhuli | Dudbhanjyang | 7 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 22 | 2017-03-22 | 2017-05-09 |  | Golanjor | 1
2669 | Sindhuli | Dudbhanjyang | 7 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 2 | 2017-03-22 | 2017-05-09 |  | Golanjor | 1
2670 | Sindhuli | Dudbhanjyang | 7 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 7 | 5 | 2017-04-05 | 2017-08-19 |  | Golanjor | 1
2671 | Sindhuli | Dudbhanjyang | 8 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 8 | 20 | 2017-06-24 | 2017-08-19 |  | Golanjor | 1
2672 | Sindhuli | Dudbhanjyang | 8 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 2 | 2017-06-24 | 2017-08-19 |  | Golanjor | 1
2673 | Sindhuli | Dudbhanjyang | 8 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 6 | 8 | 2017-08-11 | 2017-08-19 |  | Golanjor | 1
2674 | Sindhuli | Dudbhanjyang | 9 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 20 | 2017-06-24 | 2017-08-19 |  | Golanjor | 1
2675 | Sindhuli | Dudbhanjyang | 9 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 2 | 2017-06-24 | 2017-08-19 |  | Golanjor | 1
2676 | Sindhuli | Dudbhanjyang | 9 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 7 | 10 | 2017-08-11 | 2017-08-19 |  | Golanjor | 1
2677 | Sindhuli | JhangajholiRalmata | 1 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 16 | 2 | 2017-06-11 | 2017-08-30 |  | Sunkoshi | 3
2678 | Sindhuli | JhangajholiRalmata | 1 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Sunkoshi | 3
2679 | Sindhuli | JhangajholiRalmata | 1 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 9 | 9 |  |  |  | Sunkoshi | 3
2680 | Sindhuli | JhangajholiRalmata | 2 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 15 | 11 | 2017-06-11 | 2017-12-15 |  | Sunkoshi | 3
2681 | Sindhuli | JhangajholiRalmata | 2 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 |  |  |  | Sunkoshi | 3
2682 | Sindhuli | JhangajholiRalmata | 2 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 1 | 2017-03-04 | 2017-03-12 |  | Sunkoshi | 3
2683 | Sindhuli | JhangajholiRalmata | 3 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 16 | 46 | 2017-03-04 | 2017-12-15 |  | Sunkoshi | 3
2684 | Sindhuli | JhangajholiRalmata | 3 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 5 | 2017-03-04 | 2017-12-15 |  | Sunkoshi | 3
2685 | Sindhuli | JhangajholiRalmata | 3 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 9 | 8 | 2017-03-04 | 2017-09-17 |  | Sunkoshi | 3
2686 | Sindhuli | JhangajholiRalmata | 4 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 15 | 15 | 2017-06-11 | 2017-08-24 |  | Sunkoshi | 3
2687 | Sindhuli | JhangajholiRalmata | 4 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-06-11 | 2017-08-12 |  | Sunkoshi | 3
2688 | Sindhuli | JhangajholiRalmata | 4 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 9 | 6 | 2017-03-04 | 2017-09-17 |  | Sunkoshi | 3
2689 | Sindhuli | JhangajholiRalmata | 5 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 16 | 23 | 2017-06-11 | 2017-08-20 |  | Sunkoshi | 3
2690 | Sindhuli | JhangajholiRalmata | 5 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-06-11 | 2017-08-20 |  | Sunkoshi | 3
2691 | Sindhuli | JhangajholiRalmata | 5 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 9 | 16 | 2017-03-04 | 2017-09-17 |  | Sunkoshi | 3
2692 | Sindhuli | JhangajholiRalmata | 6 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 15 | 2 | 2017-06-11 | 2017-08-20 |  | Sunkoshi | 4
2693 | Sindhuli | JhangajholiRalmata | 6 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 1 | 2017-06-15 | 2017-08-20 |  | Sunkoshi | 4
2694 | Sindhuli | JhangajholiRalmata | 6 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 9 | 2 | 2017-03-04 | 2017-03-12 |  | Sunkoshi | 4
2695 | Sindhuli | JhangajholiRalmata | 7 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 16 | 21 | 2017-06-11 | 2017-08-20 |  | Sunkoshi | 4
2696 | Sindhuli | JhangajholiRalmata | 7 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 2 | 2017-06-11 | 2017-08-20 |  | Sunkoshi | 4
2697 | Sindhuli | JhangajholiRalmata | 7 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 9 | 19 | 2017-03-04 | 2017-09-17 |  | Sunkoshi | 4
2698 | Sindhuli | JhangajholiRalmata | 8 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 15 | 15 |  |  |  | Sunkoshi | 4
2699 | Sindhuli | JhangajholiRalmata | 8 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 |  |  |  | Sunkoshi | 4
2700 | Sindhuli | JhangajholiRalmata | 8 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 9 | 9 |  |  |  | Sunkoshi | 4
2701 | Sindhuli | JhangajholiRalmata | 9 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 16 | 20 | 2017-06-11 | 2017-08-20 |  | Sunkoshi | 4
2702 | Sindhuli | JhangajholiRalmata | 9 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-07-05 | 2017-08-27 |  | Sunkoshi | 4
2703 | Sindhuli | JhangajholiRalmata | 9 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 9 | 6 | 2017-03-04 | 2017-03-12 |  | Sunkoshi | 4
2704 | Sindhuli | Kamalami N.P. | 1 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 2 | 2017-09-04 | 2017-11-06 |  | Kamalamai | 4
2705 | Sindhuli | Kamalami N.P. | 1 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kamalamai | 4
2706 | Sindhuli | Kamalami N.P. | 1 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 4 | 2017-03-06 | 2017-11-14 |  | Kamalamai | 4
2707 | Sindhuli | Kamalami N.P. | 2 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Kamalamai | 4
2708 | Sindhuli | Kamalami N.P. | 2 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kamalamai | 4
2709 | Sindhuli | Kamalami N.P. | 2 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 16 | 2017-03-06 | 2017-11-14 |  | Kamalamai | 4
2710 | Sindhuli | Kamalami N.P. | 3 | SwissContact | PHPI | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 4 | 2017-07-17 | 2017-09-27 |  | Kamalamai | 8
2711 | Sindhuli | Kamalami N.P. | 3 | SwissContact | PHPI | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-08-01 | 2017-09-27 |  | Kamalamai | 8
2712 | Sindhuli | Kamalami N.P. | 3 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 3 | 2017-11-06 | 2017-11-14 |  | Kamalamai | 8
2713 | Sindhuli | Kamalami N.P. | 4 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 20 | 2017-06-13 | 2017-08-16 |  | Kamalamai | 5
2714 | Sindhuli | Kamalami N.P. | 4 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-06-13 | 2017-08-16 |  | Kamalamai | 5
2715 | Sindhuli | Kamalami N.P. | 4 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 43 | 2017-05-25 | 2017-11-14 |  | Kamalamai | 5
2716 | Sindhuli | Kamalami N.P. | 5 | SwissContact | PHPI | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 23 | 2017-06-13 | 2017-11-06 |  | Kamalamai | 4
2717 | Sindhuli | Kamalami N.P. | 5 | SwissContact | PHPI | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 3 | 2017-06-13 | 2017-05-04 |  | Kamalamai | 4
2718 | Sindhuli | Kamalami N.P. | 5 | SwissContact | PHPI | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 7 | 20 | 2017-05-23 | 2017-05-31 |  | Kamalamai | 4
2719 | Sindhuli | Kamalami N.P. | 6 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 13 | 2017-02-28 | 2017-11-06 |  | Kamalamai | 6
2720 | Sindhuli | Kamalami N.P. | 6 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 3 | 2017-02-28 | 2017-11-06 |  | Kamalamai | 6
2721 | Sindhuli | Kamalami N.P. | 6 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 6 | 2017-03-06 | 2017-11-14 |  | Kamalamai | 6
2722 | Sindhuli | Kamalami N.P. | 7 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 24 | 2017-02-28 | 2017-11-06 |  | Kamalamai | 7
2723 | Sindhuli | Kamalami N.P. | 7 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 9 | 2017-11-06 | 2017-11-14 |  | Kamalamai | 7
2724 | Sindhuli | Kamalami N.P. | 8 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 38 | 2017-06-06 | 2017-11-06 |  | Kamalamai | 7
2725 | Sindhuli | Kamalami N.P. | 8 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 2 | 2017-06-06 | 2017-08-12 |  | Kamalamai | 7
2726 | Sindhuli | Kamalami N.P. | 8 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 7 | 1 | 2017-11-06 | 2017-11-14 |  | Kamalamai | 7
2727 | Sindhuli | Kamalami N.P. | 9 | SwissContact | PHPI | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 5 | 2017-07-17 | 2017-11-06 |  | Kamalamai | 3
2728 | Sindhuli | Kamalami N.P. | 9 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kamalamai | 3
2729 | Sindhuli | Kamalami N.P. | 9 | SwissContact | PHPI | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 20 | 2017-03-07 | 2017-03-15 |  | Kamalamai | 3
2730 | Sindhuli | Kamalami N.P. | 10 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Kamalamai | 8
2731 | Sindhuli | Kamalami N.P. | 10 | SwissContact | PHPI | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-08-01 | 2017-09-27 |  | Kamalamai | 8
2732 | Sindhuli | Kamalami N.P. | 10 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 8 |  |  |  | Kamalamai | 8
2733 | Sindhuli | Kamalami N.P. | 11 | SwissContact | PHPI | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 7 | 2017-07-17 | 2017-09-12 |  | Kamalamai | 9
2734 | Sindhuli | Kamalami N.P. | 11 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 2 | 2017-07-17 | 2017-09-12 |  | Kamalamai | 9
2735 | Sindhuli | Kamalami N.P. | 11 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 18 | 2017-06-14 | 2017-06-22 |  | Kamalamai | 9
2736 | Sindhuli | Kamalami N.P. | 12 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 4 | 2017-07-17 | 2017-09-12 |  | Kamalamai | 9
2737 | Sindhuli | Kamalami N.P. | 12 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kamalamai | 9
2738 | Sindhuli | Kamalami N.P. | 12 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 7 | 2 | 2017-06-14 | 2017-06-22 |  | Kamalamai | 9
2739 | Sindhuli | Kamalami N.P. | 13 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-23 | 2017-05-11 |  | Kamalamai | 10
2740 | Sindhuli | Kamalami N.P. | 13 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kamalamai | 10
2741 | Sindhuli | Kamalami N.P. | 13 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 6 | 2017-03-07 | 2017-03-15 |  | Kamalamai | 10
2742 | Sindhuli | Kamalami N.P. | 14 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 1 | 2017-03-14 | 2017-05-01 |  | Kamalamai | 9
2743 | Sindhuli | Kamalami N.P. | 14 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kamalamai | 9
2744 | Sindhuli | Kamalami N.P. | 14 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 1 | 2017-03-07 | 2017-03-15 |  | Kamalamai | 9
2745 | Sindhuli | Kamalami N.P. | 15 | SwissContact | UCEP-N | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Kamalamai | 10
2746 | Sindhuli | Kamalami N.P. | 15 | SwissContact | UCEP-N | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kamalamai | 10
2747 | Sindhuli | Kamalami N.P. | 15 | SwissContact | UCEP-N | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 8 |  |  |  | Kamalamai | 10
2748 | Sindhuli | Kamalami N.P. | 16 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-14 | 2017-05-01 |  | Kamalamai | 10
2749 | Sindhuli | Kamalami N.P. | 16 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 2 | 2017-03-14 | 2017-05-01 |  | Kamalamai | 10
2750 | Sindhuli | Kamalami N.P. | 16 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 4 | 2017-03-07 | 2017-03-15 |  | Kamalamai | 10
2751 | Sindhuli | Kamalami N.P. | 17 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 12 | 2017-03-23 | 2017-05-11 |  | Kamalamai | 10
2752 | Sindhuli | Kamalami N.P. | 17 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 2 | 2017-03-23 | 2017-03-23 |  | Kamalamai | 10
2753 | Sindhuli | Kamalami N.P. | 17 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 7 | 8 | 2017-03-07 | 2017-03-15 |  | Kamalamai | 10
2754 | Sindhuli | Kamalami N.P. | 18 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 7 | 2017-03-14 | 2017-05-01 |  | Kamalamai | 10
2755 | Sindhuli | Kamalami N.P. | 18 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Kamalamai | 10
2756 | Sindhuli | Kamalami N.P. | 18 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 8 | 1 | 2017-03-07 | 2017-03-15 |  | Kamalamai | 10
2757 | Sindhuli | Kapilakot | 1 | SwissContact | PHPI | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 22 | 21 | 2017-02-26 | 2017-04-15 |  | Marin | 2
2758 | Sindhuli | Kapilakot | 1 | SwissContact | PHPI | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-26 | 2017-04-15 |  | Marin | 2
2759 | Sindhuli | Kapilakot | 1 | SwissContact | PHPI | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 13 | 20 | 2017-04-17 | 2017-04-25 |  | Marin | 2
2760 | Sindhuli | Kapilakot | 2 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 22 | 21 | 2017-02-23 | 2017-04-12 |  | Marin | 2
2761 | Sindhuli | Kapilakot | 2 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-23 | 2017-04-12 |  | Marin | 2
2762 | Sindhuli | Kapilakot | 2 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 14 | 20 | 2017-03-17 | 2017-03-25 |  | Marin | 2
2763 | Sindhuli | Kapilakot | 3 | SwissContact | PHPI | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 22 | 20 | 2017-02-26 | 2017-04-15 |  | Marin | 1
2764 | Sindhuli | Kapilakot | 3 | SwissContact | PHPI | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-26 | 2017-04-15 |  | Marin | 1
2765 | Sindhuli | Kapilakot | 3 | SwissContact | PHPI | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 14 | 20 | 2017-03-27 | 2017-04-04 |  | Marin | 1
2766 | Sindhuli | Kapilakot | 4 | SwissContact | PHPI | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 22 | 37 | 2017-02-28 | 2017-04-27 |  | Marin | 2
2767 | Sindhuli | Kapilakot | 4 | SwissContact | PHPI | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 4 | 2017-02-28 | 2017-04-27 |  | Marin | 2
2768 | Sindhuli | Kapilakot | 4 | SwissContact | PHPI | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 14 | 1 | 2017-07-12 | 2017-07-20 |  | Marin | 2
2769 | Sindhuli | Kapilakot | 5 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 23 | 21 | 2017-02-23 | 2017-04-12 |  | Marin | 1
2770 | Sindhuli | Kapilakot | 5 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-23 | 2017-04-12 |  | Marin | 1
2771 | Sindhuli | Kapilakot | 5 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 13 | 20 | 2017-02-23 | 2017-03-03 |  | Marin | 1
2772 | Sindhuli | Kapilakot | 6 | SwissContact | PHPI | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 23 | 16 | 2017-02-23 | 2017-04-12 |  | Marin | 6
2773 | Sindhuli | Kapilakot | 6 | SwissContact | PHPI | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 1 | 2017-02-23 | 2017-04-12 |  | Marin | 6
2774 | Sindhuli | Kapilakot | 6 | SwissContact | PHPI | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 13 | 21 | 2017-07-11 | 2017-07-19 |  | Marin | 6
2775 | Sindhuli | Kapilakot | 7 | SwissContact | PHPI | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 22 | 8 | 2017-02-23 | 2017-04-12 |  | Marin | 6
2776 | Sindhuli | Kapilakot | 7 | SwissContact | PHPI | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 1 | 2017-02-23 | 2017-04-12 |  | Marin | 6
2777 | Sindhuli | Kapilakot | 7 | SwissContact | PHPI | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 13 | 13 |  |  |  | Marin | 6
2778 | Sindhuli | Kapilakot | 8 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 22 | 30 | 2017-06-15 | 2017-09-12 |  | Marin | 6
2779 | Sindhuli | Kapilakot | 8 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 3 | 2 | 2017-06-15 | 2017-08-08 |  | Marin | 6
2780 | Sindhuli | Kapilakot | 8 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 13 | 12 | 2017-07-12 | 2017-07-20 |  | Marin | 6
2781 | Sindhuli | Kapilakot | 9 | SwissContact | AFD | SwS-SwissContact | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 22 | 26 | 2017-04-20 | 2017-06-20 |  | Marin | 6
2782 | Sindhuli | Kapilakot | 9 | SwissContact | AFD | SwS-SwissContact | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 3 | 4 | 2017-04-20 | 2017-06-20 |  | Marin | 6
2783 | Sindhuli | Kapilakot | 9 | SwissContact | AFD | SwS-SwissContact | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC 7 days curriculum plus 2 days life skills training(54 hrs) | # of trainees | Yes | Completed | 13 | 6 | 2017-07-12 | 2017-07-20 |  | Marin | 6
2784 | Sindhuli | Sitalpati | 2 | NRCS | NRCS | IFRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Planned | 30 | 30 | 2016-01-01 | 2018-12-31 |  | Sunkoshi | 6
2785 | Sindhuli | Sitalpati | 9 | NRCS | NRCS | IFRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Planned | 30 | 0 | 2016-01-01 | 2018-12-31 |  | Sunkoshi | 6
2786 | Sindhuli | Sitalpati | 1 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 16 | 16 | 2016-01-01 | 2018-12-31 |  | Sunkoshi | 6
2787 | Sindhuli | Sitalpati | 3 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 18 | 18 | 2016-01-01 | 2018-12-31 |  | Sunkoshi | 6
2788 | Sindhuli | Sitalpati | 4 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 22 | 22 | 2016-01-01 | 2018-12-31 |  | Sunkoshi | 6
2789 | Sindhuli | Sitalpati | 5 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 18 | 18 | 2016-01-01 | 2018-12-31 |  | Sunkoshi | 6
2790 | Sindhuli | Sitalpati | 6 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 16 | 16 | 2016-01-01 | 2018-12-31 |  | Sunkoshi | 6
2791 | Sindhuli | Sitalpati | 7 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 14 | 13 | 2016-01-01 | 2018-12-31 |  | Sunkoshi | 6
2792 | Sindhuli | Sitalpati | 8 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 19 | 19 | 2016-01-01 | 2018-12-31 |  | Sunkoshi | 6
2793 | Sindhuli | Sitalpati | 9 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 27 | 27 | 2016-01-01 | 2018-12-31 |  | Sunkoshi | 6
2794 | Sindhuli | Sitalpati | 1 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 47 | 44 | 2016-05-12 | 2016-06-26 |  | Sunkoshi | 6
2795 | Sindhuli | Sitalpati | 2 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 71 | 69 | 2017-06-22 | 2018-01-21 |  | Sunkoshi | 6
2796 | Sindhuli | Sitalpati | 3 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 70 | 68 | 2016-05-12 | 2016-06-26 |  | Sunkoshi | 6
2797 | Sindhuli | Sitalpati | 4 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 151 | 146 | 2016-05-12 | 2016-06-26 |  | Sunkoshi | 6
2798 | Sindhuli | Sitalpati | 5 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 138 | 134 | 2016-05-12 | 2016-06-26 |  | Sunkoshi | 6
2799 | Sindhuli | Sitalpati | 6 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 103 | 102 | 2016-05-12 | 2016-06-26 |  | Sunkoshi | 6
2800 | Sindhuli | Sitalpati | 7 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 74 | 74 | 2016-05-12 | 2016-06-26 |  | Sunkoshi | 6
2801 | Sindhuli | Sitalpati | 8 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 89 | 85 | 2016-05-12 | 2016-06-26 |  | Sunkoshi | 6
2802 | Sindhuli | Sitalpati | 9 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 137 | 134 | 2017-06-22 | 2018-01-21 |  | Sunkoshi | 6
2803 | Sindhuli | Sitalpati | 1 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 47 | 7 | 2016-09-01 | 2018-12-31 |  | Sunkoshi | 6
2804 | Sindhuli | Sitalpati | 2 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 71 | 8 | 2016-09-01 | 2018-12-31 |  | Sunkoshi | 6
2805 | Sindhuli | Sitalpati | 3 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 70 | 23 | 2016-09-01 | 2018-12-31 |  | Sunkoshi | 6
2806 | Sindhuli | Sitalpati | 4 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 151 | 18 | 2016-09-01 | 2018-12-31 |  | Sunkoshi | 6
2807 | Sindhuli | Sitalpati | 5 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 138 | 12 | 2016-09-01 | 2018-12-31 |  | Sunkoshi | 6
2808 | Sindhuli | Sitalpati | 6 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 103 | 14 | 2016-09-01 | 2018-12-31 |  | Sunkoshi | 6
2809 | Sindhuli | Sitalpati | 7 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 74 | 46 | 2016-09-01 | 2018-12-31 |  | Sunkoshi | 6
2810 | Sindhuli | Sitalpati | 8 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 89 | 25 | 2016-09-01 | 2018-12-31 |  | Sunkoshi | 6
2811 | Sindhuli | Sitalpati | 9 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 137 | 17 | 2016-05-12 | 2016-06-26 |  | Sunkoshi | 6
2812 | Sindhuli | Sitalpati | 1 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 47 | 1 | 2016-09-01 | 2018-12-31 |  | Sunkoshi | 6
2813 | Sindhuli | Sitalpati | 2 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 71 | 4 | 2016-09-01 | 2018-12-31 |  | Sunkoshi | 6
2814 | Sindhuli | Sitalpati | 3 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 70 | 5 | 2016-09-01 | 2018-12-31 |  | Sunkoshi | 6
2815 | Sindhuli | Sitalpati | 4 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 151 | 3 | 2016-09-01 | 2018-12-31 |  | Sunkoshi | 6
2816 | Sindhuli | Sitalpati | 5 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 138 | 8 | 2016-09-01 | 2018-12-31 |  | Sunkoshi | 6
2817 | Sindhuli | Sitalpati | 6 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 103 | 1 | 2016-09-01 | 2018-12-31 |  | Sunkoshi | 6
2818 | Sindhuli | Sitalpati | 7 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 74 | 12 | 2016-09-01 | 2018-12-31 |  | Sunkoshi | 6
2819 | Sindhuli | Sitalpati | 8 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 89 | 23 | 2016-09-01 | 2018-12-31 |  | Sunkoshi | 6
2820 | Sindhuli | Sitalpati | 9 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 137 | 19 | 2016-05-12 | 2016-06-03 |  | Sunkoshi | 6
2821 | Sindhuli | JhangajholiRalmata | 1 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-04-19 | Actual expenditure yet to be calculated | Sunkoshi | 3
2822 | Sindhuli | KusesworDumja | 3 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-04-19 | Actual expenditure yet to be calculated | Sunkoshi | 1
2823 | Sindhuli | Majhuwa | 4 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-04-19 | Actual expenditure yet to be calculated | Sunkoshi | 7
2824 | Sindhuli | PuranoJhangajholi | 4 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-04-19 | Actual expenditure yet to be calculated | Sunkoshi | 5
2825 | Sindhuli | Sitalpati | 9 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-09-01 | 2018-12-31 | Actual expenditure yet to be calculated | Sunkoshi | 6
2826 | Sindhuli | Sitalpati | 1 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 47 | 47 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Sunkoshi | 6
2827 | Sindhuli | Sitalpati | 2 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 71 | 71 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Sunkoshi | 6
2828 | Sindhuli | Sitalpati | 3 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 70 | 70 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Sunkoshi | 6
2829 | Sindhuli | Sitalpati | 4 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 151 | 151 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Sunkoshi | 6
2830 | Sindhuli | Sitalpati | 5 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 138 | 138 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Sunkoshi | 6
2831 | Sindhuli | Sitalpati | 6 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 103 | 103 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Sunkoshi | 6
2832 | Sindhuli | Sitalpati | 7 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 74 | 74 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Sunkoshi | 6
2833 | Sindhuli | Sitalpati | 8 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 89 | 89 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Sunkoshi | 6
2834 | Sindhuli | Sitalpati | 9 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 137 | 137 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Sunkoshi | 6
2835 | Bhaktapur | Nagarkot N.P. | 7 | DCA | FSCN | DCA | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Community orientation program on safe and resilient shelter construction | # of participants | Yes | Completed | 200 | 208 | 2016-07-17 | 2016-01-19 |  | Changunarayan | 8
2836 | Bhaktapur | Nagarkot N.P. | 7 | DCA | FSCN | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC curriculum mason training | # of trainees | Yes | Completed | 20 | 20 | 2016-11-21 | 2016-11-27 |  | Changunarayan | 8
2837 | Bhaktapur | Changunarayan N.P. | All | GON | GON | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 24 | 24 | 2015-07-20 | 2015-07-25 | Changunarayan N.P. | Changunarayan | 5
2838 | Bhaktapur | MadhyapurThimi N.P. | All | ISAP |  | PWJ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2015-12-24 | 2015-12-28 |  | Madhyapur Thimi | 6
2839 | Bhaktapur | Nagarkot N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 20 | 2016-12-15 | 2016-12-15 |  | Changunarayan | 9
2840 | Bhaktapur | Nagarkot N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 35 | 2016-12-26 | 2016-12-26 |  | Changunarayan | 7
2841 | Bhaktapur | Nagarkot N.P. | 11 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 46 | 2016-07-12 | 2016-07-12 |  | Changunarayan | 6
2842 | Bhaktapur | Nagarkot N.P. | 11 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 34 | 2016-07-13 | 2016-07-13 |  | Changunarayan | 6
2843 | Bhaktapur | Nagarkot N.P. | 11 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 72 | 2016-12-27 | 2016-12-27 |  | Changunarayan | 6
2844 | Bhaktapur | Nagarkot N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 43 | 2016-07-21 | 2016-07-21 |  | Changunarayan | 6
2845 | Bhaktapur | Nagarkot N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 36 | 2016-07-14 | 2016-07-14 |  | Changunarayan | 6
2846 | Bhaktapur | Nagarkot N.P. | 1 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Changunarayan | 9
2847 | Bhaktapur | Nagarkot N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Changunarayan | 9
2848 | Bhaktapur | Nagarkot N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Changunarayan | 9
2849 | Bhaktapur | Nagarkot N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Changunarayan | 8
2850 | Bhaktapur | Nagarkot N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Changunarayan | 8
2851 | Bhaktapur | Nagarkot N.P. | 6 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Changunarayan | 8
2852 | Bhaktapur | Nagarkot N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Changunarayan | 8
2853 | Bhaktapur | Nagarkot N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Changunarayan | 7
2854 | Bhaktapur | Nagarkot N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Changunarayan | 7
2855 | Bhaktapur | Nagarkot N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Changunarayan | 7
2856 | Bhaktapur | Nagarkot N.P. | 11 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Changunarayan | 6
2857 | Bhaktapur | Nagarkot N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Changunarayan | 6
2858 | Bhaktapur | Nagarkot N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Changunarayan | 6
2859 | Bhaktapur | Nagarkot N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Information center at municipality office | # of households supported | Yes | Ongoing | 200 | 0 | 2016-12-01 | 2017-03-31 |  | Changunarayan | 7
2860 | Bhaktapur | Nagarkot N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 4 | 2016-05-29 | 2016-06-04 |  | Changunarayan | 9
2861 | Bhaktapur | Nagarkot N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-29 | 2016-06-04 |  | Changunarayan | 8
2862 | Bhaktapur | Nagarkot N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-29 | 2016-06-04 |  | Changunarayan | 8
2863 | Bhaktapur | Nagarkot N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-29 | 2016-06-04 |  | Changunarayan | 8
2864 | Bhaktapur | Nagarkot N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-29 | 2016-06-04 |  | Changunarayan | 7
2865 | Bhaktapur | Nagarkot N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-29 | 2016-06-04 |  | Changunarayan | 7
2866 | Bhaktapur | Nagarkot N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 4 | 2016-05-29 | 2016-06-04 |  | Changunarayan | 7
2867 | Bhaktapur | Nagarkot N.P. | 11 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-29 | 2016-06-04 |  | Changunarayan | 6
2868 | Bhaktapur | Nagarkot N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-29 | 2016-06-04 |  | Changunarayan | 6
2869 | Bhaktapur | Nagarkot N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-29 | 2016-06-04 |  | Changunarayan | 6
2870 | Bhaktapur | Nagarkot N.P. | 1 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-07 | 2016-02-12 |  | Changunarayan | 9
2871 | Bhaktapur | Nagarkot N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 3 | 2016-02-07 | 2016-02-12 |  | Changunarayan | 9
2872 | Bhaktapur | Nagarkot N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | Changunarayan | 9
2873 | Bhaktapur | Nagarkot N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 3 | 2016-02-07 | 2016-02-12 |  | Changunarayan | 9
2874 | Bhaktapur | Nagarkot N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 2 | 2 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | Changunarayan | 8
2875 | Bhaktapur | Nagarkot N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-07 | 2016-02-12 |  | Changunarayan | 8
2876 | Bhaktapur | Nagarkot N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | Changunarayan | 8
2877 | Bhaktapur | Nagarkot N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 3 | 2016-02-07 | 2016-02-12 |  | Changunarayan | 8
2878 | Bhaktapur | Nagarkot N.P. | 6 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-07 | 2016-02-12 |  | Changunarayan | 8
2879 | Bhaktapur | Nagarkot N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 3 | 2016-02-07 | 2016-02-12 |  | Changunarayan | 8
2880 | Bhaktapur | Nagarkot N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | Changunarayan | 7
2881 | Bhaktapur | Nagarkot N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-07 | 2016-02-12 |  | Changunarayan | 7
2882 | Bhaktapur | Nagarkot N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-07 | 2016-02-12 |  | Changunarayan | 7
2883 | Bhaktapur | Nagarkot N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-07 | 2016-02-12 |  | Changunarayan | 7
2884 | Bhaktapur | Nagarkot N.P. | 11 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 2 | 2 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | Changunarayan | 6
2885 | Bhaktapur | Nagarkot N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 1 | 2 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | Changunarayan | 6
2886 | Bhaktapur | Changunarayan N.P. |  | OXFAM-GB |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Tathali, Chagunarayan | # of trainees | Yes | Completed | 22 | 22 |  |  |  | #N/A | #N/A
2887 | Bhaktapur | Changunarayan N.P. |  | OXFAM-GB |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Tathali, Bageshwori | # of trainees | Yes | Completed | 18 | 18 |  |  |  | #N/A | #N/A
2888 | Bhaktapur | Nagarkot N.P. | 13 | NRCS | NRCS | BRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 6
2889 | Bhaktapur | Suryabinayak N.P. | 6 | NRCS | NRCS | BRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Suryabinayak | 8
2890 | Bhaktapur | Anantalingeshwor N.P. | 5 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Suryabinayak | 3
2891 | Bhaktapur | Anantalingeshwor N.P. | 6 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Suryabinayak | 1
2892 | Bhaktapur | Anantalingeshwor N.P. | 8 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 1 | 2016-01-01 | 2018-12-31 |  | Suryabinayak | 1
2893 | Bhaktapur | Anantalingeshwor N.P. | 9 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Suryabinayak | 1
2894 | Bhaktapur | Anantalingeshwor N.P. | 10 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 14 | 14 | 2016-01-01 | 2018-12-31 |  | Suryabinayak | 4
2895 | Bhaktapur | Anantalingeshwor N.P. | 11 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 16 | 16 | 2016-01-01 | 2018-12-31 |  | Suryabinayak | 4
2896 | Bhaktapur | Anantalingeshwor N.P. | 12 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Suryabinayak | 4
2897 | Bhaktapur | Anantalingeshwor N.P. | 13 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 9 | 9 | 2016-01-01 | 2018-12-31 |  | Suryabinayak | 7
2898 | Bhaktapur | Anantalingeshwor N.P. | 14 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Suryabinayak | 7
2899 | Bhaktapur | Anantalingeshwor N.P. | 15 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Suryabinayak | 7
2900 | Bhaktapur | Bhaktapur N.P. | 15 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 30 | 30 | 2016-01-01 | 2018-12-31 |  | Bhaktapur | 2
2901 | Bhaktapur | Changunarayan N.P. | 1 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 29 | 29 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 5
2902 | Bhaktapur | Changunarayan N.P. | 2 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 5
2903 | Bhaktapur | Changunarayan N.P. | 3 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 5 | 5 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 5
2904 | Bhaktapur | Changunarayan N.P. | 4 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 4 | 4 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 5
2905 | Bhaktapur | Changunarayan N.P. | 5 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 3
2906 | Bhaktapur | Changunarayan N.P. | 6 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 11 | 11 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 3
2907 | Bhaktapur | Changunarayan N.P. | 7 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 15 | 15 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 3
2908 | Bhaktapur | Changunarayan N.P. | 8 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 5 | 5 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 4
2909 | Bhaktapur | Changunarayan N.P. | 10 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 4
2910 | Bhaktapur | Changunarayan N.P. | 9 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 4 | 4 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 4
2911 | Bhaktapur | Changunarayan N.P. | 11 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 5 | 5 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 4
2912 | Bhaktapur | Changunarayan N.P. | 12 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 2
2913 | Bhaktapur | Changunarayan N.P. | 13 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 2
2914 | Bhaktapur | Nagarkot N.P. | 1 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 1 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 9
2915 | Bhaktapur | Nagarkot N.P. | 2 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 4 | 4 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 9
2916 | Bhaktapur | Nagarkot N.P. | 3 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 4 | 4 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 9
2917 | Bhaktapur | Nagarkot N.P. | 4 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 1 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 8
2918 | Bhaktapur | Nagarkot N.P. | 5 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 8
2919 | Bhaktapur | Nagarkot N.P. | 6 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 11 | 11 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 8
2920 | Bhaktapur | Nagarkot N.P. | 7 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 8
2921 | Bhaktapur | Nagarkot N.P. | 8 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 8 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 7
2922 | Bhaktapur | Nagarkot N.P. | 9 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 7 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 7
2923 | Bhaktapur | Nagarkot N.P. | 10 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 12 | 12 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 7
2924 | Bhaktapur | Nagarkot N.P. | 11 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 4 | 5 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 6
2925 | Bhaktapur | Nagarkot N.P. | 12 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 4 | 2 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 6
2926 | Bhaktapur | Nagarkot N.P. | 13 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 3 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 6
2927 | Bhaktapur | Changunarayan N.P. | 4 | NRCS | NRCS | BRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 5
2928 | Bhaktapur | Changunarayan N.P. | 6 | NRCS | NRCS | BRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 1 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 3
2929 | Bhaktapur | Changunarayan N.P. | 9 | NRCS | NRCS | BRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 3 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 4
2930 | Bhaktapur | Anantalingeshwor N.P. | 10 | NRCS | NRCS | BRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 3 | 2016-01-01 | 2018-12-31 |  | Suryabinayak | 4
2931 | Bhaktapur | Anantalingeshwor N.P. | 13 | NRCS | NRCS | BRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 4 | 2016-01-01 | 2018-12-31 |  | Suryabinayak | 7
2932 | Bhaktapur | Nagarkot N.P. | 2 | NRCS | NRCS | BRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 3 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 9
2933 | Bhaktapur | Nagarkot N.P. | 5 | NRCS | NRCS | BRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 8
2934 | Bhaktapur | Nagarkot N.P. | 9 | NRCS | NRCS | BRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 7
2935 | Bhaktapur | Changunarayan N.P. | 17 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Changunarayan | 2
2936 | Bhaktapur | Suryabinayak N.P. | 6 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 8 | 2016-01-01 | 2018-12-31 |  | Suryabinayak | 8
2937 | Bhaktapur | Suryabinayak N.P. | 7 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 7 | 2016-01-01 | 2018-12-31 |  | Suryabinayak | 8
2938 | Bhaktapur | Suryabinayak N.P. | 8 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 12 | 8 | 2016-01-01 | 2018-12-31 |  | Suryabinayak | 8
2939 | Bhaktapur | Nagarkot N.P. |  | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Planned | 20 | 0 | 2016-01-01 | 2018-12-31 |  | #N/A | #N/A
2940 | Bhaktapur | Anantalingeshwor N.P. | 10 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 30 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Suryabinayak | 4
2941 | Bhaktapur | Anantalingeshwor N.P. | 13 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Suryabinayak | 7
2942 | Bhaktapur | Changunarayan N.P. | 1 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community training | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 5
2943 | Bhaktapur | Changunarayan N.P. | 2 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 5
2944 | Bhaktapur | Changunarayan N.P. | 3 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 5
2945 | Bhaktapur | Changunarayan N.P. | 4 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 5
2946 | Bhaktapur | Changunarayan N.P. | 6 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 3
2947 | Bhaktapur | Changunarayan N.P. | 9 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 4
2948 | Bhaktapur | Changunarayan N.P. | 10 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 4
2949 | Bhaktapur | Changunarayan N.P. | 11 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 4
2950 | Bhaktapur | Changunarayan N.P. | 17 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 2
2951 | Bhaktapur | Nagarkot N.P. | 1 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 9
2952 | Bhaktapur | Nagarkot N.P. | 2 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 9
2953 | Bhaktapur | Nagarkot N.P. | 3 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 9
2954 | Bhaktapur | Nagarkot N.P. | 5 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 8
2955 | Bhaktapur | Nagarkot N.P. | 7 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 8
2956 | Bhaktapur | Nagarkot N.P. | 9 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 7
2957 | Bhaktapur | Nagarkot N.P. | 10 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 7
2958 | Bhaktapur | Nagarkot N.P. | 11 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 6
2959 | Bhaktapur | Nagarkot N.P. | 12 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 6
2960 | Bhaktapur | Nagarkot N.P. | 13 | NRCS | NRCS | BRC | Technical Assistance | Household reconstruction orientation | 2-3 sessions | PASSA troll out at community | # of households | Yes | Completed | 50 | 50 | 2017-02-01 | 2017-04-01 | community PASSA rollout | Changunarayan | 6
2961 | Bhaktapur | Changunarayan N.P. | 3 | GON | DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  |  | Yes | Completed | 30 | 30 | 2018-02-17 | 2018-02-23 |  | Changunarayan | 5
2962 | Bhaktapur | Changunarayan N.P. | 3 | GON | DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  |  | Yes | Completed | 30 | 30 | 2018-02-06 | 2018-02-12 |  | Changunarayan | 5
#REF! | Kathmandu | Chandragiri N.P. | 13 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 66 | 58 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2964 | Kathmandu | Chandragiri N.P. | 14 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 49 | 38 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2965 | Kathmandu | Chandragiri N.P. | 13 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 66 | 0 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2966 | Kathmandu | Chandragiri N.P. | 14 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 49 | 0 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2967 | Kathmandu | Chandragiri N.P. | 13 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 66 | 0 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2968 | Kathmandu | Chandragiri N.P. | 14 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 49 | 0 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2969 | Kathmandu | Chandragiri N.P. | 13 | Lumanti | Lumanti | MSEREOR | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Planned | 15 | 0 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2970 | Kathmandu | Chandragiri N.P. | 14 | Lumanti | Lumanti | MSEREOR | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Planned | 15 | 0 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2971 | Kathmandu | Chandragiri N.P. | 14 | Lumanti | Lumanti | MSEREOR | Others | Others | (Please specify in Activity Detail) | Construction of 100 m road in Mahhenarayan, Machhegaun | # of trainees | Yes | Completed | 1 | 1 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2972 | Kathmandu | Chandragiri N.P. | 13 | Lumanti | Lumanti | MSEREOR | Others | Others | (Please specify in Activity Detail) | Land consolidation planning for Taukhel, Machhegaon | # of trainees | Yes | Completed | 1 | 1 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2973 | Kathmandu | Chandragiri N.P. | 13 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Ongoing | 120 | 180 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2974 | Kathmandu | Chandragiri N.P. | 14 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Ongoing | 120 | 86 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2975 | Kathmandu | Chandragiri N.P. | 13 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 66 | 66 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2976 | Kathmandu | Chandragiri N.P. | 14 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 49 | 49 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2977 | Kathmandu | Chandragiri N.P. | 13 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Information Center for reconstruction process | # of households supported | Yes | Ongoing | 115 | 115 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2978 | Kathmandu | Chandragiri N.P. | 13 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Household reconstruction orientation | 2-3 sessions |  | # of households | Yes | Ongoing | 66 | 66 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2979 | Kathmandu | Chandragiri N.P. | 14 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Household reconstruction orientation | 2-3 sessions |  | # of households | Yes | Ongoing | 49 | 49 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2980 | Kathmandu | Chandragiri N.P. | 13 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Water, Sanitation and Hygiene (Posters, Flipchart, documentaries and orientation ) | # of households | Yes | Ongoing | 66 | 45 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2981 | Kathmandu | Chandragiri N.P. | 14 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Water, Sanitation and Hygiene (Posters, Flipchart, documentaries and training) | # of households | Yes | Planned | 49 | 0 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2982 | Kathmandu | Chandragiri N.P. | 13 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC Curriculum | # of trainees | Yes | Ongoing | 24 | 0 | 2016-12-01 | 2018-02-28 |  | Chandragiri | 9
2983 | Kathmandu | Shankarapur N.P. | 1,2,14,15 | LWF |  | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Support to Construct Permanent Shelter | # of households | Yes | Completed | 100 | 100 |  |  |  | Shankharapur | 9
2984 | Kathmandu | Shankarapur N.P. | 1,2,14,15 | LWF |  | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Support to Construct Permanent Shelter | # of households | Yes | Completed | 100 | 100 |  |  |  | Shankharapur | 9
2985 | Kathmandu | Shankarapur N.P. | 1,2,14,15 | LWF |  | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  |  | Yes | Ongoing | 100 | 0 |  |  |  | Shankharapur | 9
2986 | Kathmandu | Shankarapur N.P. | 1,2,14,15 | LWF |  | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training to local residents | # of trainees | Yes | Completed | 30 | 30 |  |  |  | Shankharapur | 9
2987 | Kathmandu | Shankarapur N.P. | all | GoN | MoUD/DLPIU | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  |  | Yes | Completed | 37 | 37 | 2018-01-19 | 2018-01-25 |  | #N/A | #N/A
2988 | Kathmandu | Kageshwori Manahara N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 525 | 843 | 2015-10-01 | 2020-09-30 |  | Kageshwori Manohara | 1
2989 | Kathmandu | Kageshwori Manahara N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 525 | 212 | 2015-10-01 | 2020-09-30 |  | Kageshwori Manohara | 1
2990 | Kathmandu | Kageshwori Manahara N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 525 | 261 | 2015-10-01 | 2020-09-30 |  | Kageshwori Manohara | 2
2991 | Kathmandu | Kageshwori Manahara N.P. | 1 | NSET | BG | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 70 | 86 | 2015-10-01 | 2020-09-30 |  | Kageshwori Manohara | 1
2992 | Kathmandu | Kageshwori Manahara N.P. | 2 | NSET | BG | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 70 | 24 | 2015-10-01 | 2020-09-30 |  | Kageshwori Manohara | 1
2993 | Kathmandu | Kageshwori Manahara N.P. | 3 | NSET | BG | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 70 | 25 | 2015-10-01 | 2020-09-30 |  | Kageshwori Manohara | 2
2994 | Kathmandu | Kageshwori Manahara N.P. | 5 | NSET | BG | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 70 | 30 | 2015-10-01 | 2020-09-30 |  | Kageshwori Manohara | 4
2995 | Kathmandu | Kathmandu M.N.P. | 35 | NSET | NSET | USAID | Training | Other trainings | Local Authority Training |  | # of trainees | Yes | Completed | 2579 | 2579 | 2015-10-01 | 2020-09-30 |  | Kathmandu | 32
2996 | Kathmandu | Kathmandu M.N.P. | 11 | NSET | NSET | USAID | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Ongoing | 210 | 210 | 2015-10-01 | 2020-09-30 |  | Kathmandu | 11
2997 | Kathmandu | Kageshwori Manahara N.P. | 1,2,3 | NSET | BG | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  |  | Yes | Ongoing | 1878 | 301 | 2016-11-01 |  |  | #N/A | #N/A
2998 | Kathmandu | Chandragiri N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 43 | 2016-08-15 | 2016-08-15 |  | Chandragiri | 2
2999 | Kathmandu | Chandragiri N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 31 | 2016-12-15 | 2016-12-15 |  | Chandragiri | 5
3000 | Kathmandu | Chandragiri N.P. | 15 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 61 | 2016-10-20 | 2016-10-20 |  | Chandragiri | 10
3001 | Kathmandu | Chandragiri N.P. | 19 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 25 | 2016-11-24 | 2016-11-24 |  | Chandragiri | 13
3002 | Kathmandu | Chandragiri N.P. | 1 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 0 | 2016-12-20 | 2017-03-31 |  | Chandragiri | 1
3003 | Kathmandu | Chandragiri N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 0 | 2016-12-20 | 2017-03-31 |  | Chandragiri | 1
3004 | Kathmandu | Chandragiri N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 0 | 2016-12-20 | 2017-03-31 |  | Chandragiri | 2
3005 | Kathmandu | Chandragiri N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 0 | 2016-12-20 | 2017-03-31 |  | Chandragiri | 2
3006 | Kathmandu | Chandragiri N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 0 | 2016-12-20 | 2017-03-31 |  | Chandragiri | 3
3007 | Kathmandu | Chandragiri N.P. | 6 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 2 | 2016-12-20 | 2017-03-31 |  | Chandragiri | 4
3008 | Kathmandu | Chandragiri N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 2 | 2016-12-20 | 2017-03-31 |  | Chandragiri | 4
3009 | Kathmandu | Chandragiri N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 39 | 2016-12-20 | 2017-03-31 |  | Chandragiri | 5
3010 | Kathmandu | Chandragiri N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 17 | 2016-12-20 | 2017-03-31 |  | Chandragiri | 6
3011 | Kathmandu | Chandragiri N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 36 | 2016-12-20 | 2017-03-31 |  | Chandragiri | 7
3012 | Kathmandu | Chandragiri N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 0 | 2016-12-20 | 2017-03-31 |  | Chandragiri | 8
3013 | Kathmandu | Chandragiri N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 0 | 2016-12-20 | 2017-03-31 |  | Chandragiri | 9
3014 | Kathmandu | Chandragiri N.P. | 18 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Information center at municipality office | # of households supported | Yes | Ongoing | 200 | 0 | 2016-12-25 | 2017-03-31 |  | Chandragiri | 12
3015 | Kathmandu | Chandragiri N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-12-25 | 2016-12-31 |  | Chandragiri | 1
3016 | Kathmandu | Chandragiri N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-12-25 | 2016-12-31 |  | Chandragiri | 2
3017 | Kathmandu | Chandragiri N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 7 | 2016-12-25 | 2016-12-31 |  | Chandragiri | 2
3018 | Kathmandu | Chandragiri N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-12-25 | 2016-12-31 |  | Chandragiri | 3
3019 | Kathmandu | Chandragiri N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-12-25 | 2016-12-31 |  | Chandragiri | 4
3020 | Kathmandu | Chandragiri N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-12-25 | 2016-12-31 |  | Chandragiri | 6
3021 | Kathmandu | Chandragiri N.P. | 19 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-12-25 | 2016-12-31 |  | Chandragiri | 13
3022 | Kathmandu | Chandragiri N.P. | 20 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 3 | 2016-12-25 | 2016-12-31 |  | Chandragiri | 14
3023 | Kathmandu | Chandragiri N.P. | 22 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-12-25 | 2016-12-31 |  | Chandragiri | 15
3024 | Kathmandu | Chandragiri N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04 |  | Chandragiri | 2
3025 | Kathmandu | Chandragiri N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-09-08 |  | Chandragiri | 2
3026 | Kathmandu | Chandragiri N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 1 | 2016-02-28 | 2016-03-04 |  | Chandragiri | 2
3027 | Kathmandu | Chandragiri N.P. | 15 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04 |  | Chandragiri | 10
3028 | Kathmandu | Chandragiri N.P. | 16 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04 |  | Chandragiri | 11
3029 | Kathmandu | Chandragiri N.P. | 19 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 2 | 2 | 2016-08-25 | 2016-09-08 |  | Chandragiri | 13
3030 | Kathmandu | Chandragiri N.P. | 19 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04 |  | Chandragiri | 13
3031 | Kathmandu | Chandragiri N.P. | 21 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 1 | 2016-02-28 | 2016-03-04 |  | Chandragiri | 13
3032 | Kathmandu | Daxinkali N.P. | 1 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04 |  | Dakshinkali | 1
3033 | Kathmandu | Daxinkali N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04 |  | Dakshinkali | 5
3034 | Kathmandu | Daxinkali N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 1 | 1 | 2016-02-28 | 2016-03-04 |  | Dakshinkali | 6
3035 | Kathmandu | Daxinkali N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 1 | 1 | 2016-02-28 | 2016-03-04 |  | Dakshinkali | 6
3036 | Kathmandu | Daxinkali N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04 |  | Dakshinkali | 8
3037 | Kathmandu | Daxinkali N.P. | 14 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04 |  | Dakshinkali | 8
3038 | Kathmandu | Kirtipur N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 1 | 1 | 2016-02-28 | 2016-03-04 |  | Kirtipur | 10
3039 | Kathmandu | Kirtipur N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 1 | 1 | 2016-02-28 | 2016-03-04 |  | Kirtipur | 3
3040 | Kathmandu | Kirtipur N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04 |  | Kirtipur | 4
3041 | Kathmandu | Kirtipur N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04 |  | Kirtipur | 8
3042 | Kathmandu | Kirtipur N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 1 | 1 | 2016-02-28 | 2016-03-04 |  | Kirtipur | 8
3043 | Kathmandu | Kirtipur N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 1 | 1 | 2016-02-28 | 2016-03-04 |  | Kirtipur | 6
3044 | Kathmandu | Kirtipur N.P. | 15 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04 |  | Kirtipur | 6
3045 | Kathmandu | Nagarjun N.P. | 6 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 31 | 2016-10-15 | 2016-10-15 |  | Nagarjun | 5
3046 | Kathmandu | Nagarjun N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 69 | 2016-08-25 | 2016-09-25 |  | Nagarjun | 8
3047 | Kathmandu | Nagarjun N.P. | 14 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 29 | 2016-09-15 | 2016-09-15 |  | Nagarjun | 7
3048 | Kathmandu | Nagarjun N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 7 | 2016-12-20 | 2017-03-31 |  | Nagarjun | 2
3049 | Kathmandu | Nagarjun N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 19 | 2016-12-20 | 2017-03-31 |  | Nagarjun | 3
3050 | Kathmandu | Nagarjun N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 56 | 2016-12-20 | 2017-03-31 |  | Nagarjun | 6
3051 | Kathmandu | Nagarjun N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 22 | 2016-12-20 | 2017-03-31 |  | Nagarjun | 6
3052 | Kathmandu | Nagarjun N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 44 | 2016-12-20 | 2017-03-31 |  | Nagarjun | 7
3053 | Kathmandu | Nagarjun N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 26 | 2016-12-20 | 2017-03-31 |  | Nagarjun | 9
3054 | Kathmandu | Nagarjun N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 31 | 27 | 2016-12-20 | 2017-03-31 |  | Nagarjun | 10
3055 | Kathmandu | Nagarjun N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-25 | 2016-05-31 |  | Nagarjun | 3
3056 | Kathmandu | Nagarjun N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-25 | 2016-05-31 |  | Nagarjun | 4
3057 | Kathmandu | Nagarjun N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-25 | 2016-05-31 |  | Nagarjun | 5
3058 | Kathmandu | Nagarjun N.P. | 6 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-25 | 2016-05-31 |  | Nagarjun | 5
3059 | Kathmandu | Nagarjun N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-25 | 2016-05-31 |  | Nagarjun | 6
3060 | Kathmandu | Nagarjun N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-25 | 2016-05-31 |  | Nagarjun | 6
3061 | Kathmandu | Nagarjun N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-05-25 | 2016-05-31 |  | Nagarjun | 7
3062 | Kathmandu | Nagarjun N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-25 | 2016-05-31 |  | Nagarjun | 8
3063 | Kathmandu | Nagarjun N.P. | 11 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 3 | 2016-05-25 | 2016-05-31 |  | Nagarjun | 8
3064 | Kathmandu | Nagarjun N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-25 | 2016-05-31 |  | Nagarjun | 9
3065 | Kathmandu | Nagarjun N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-25 | 2016-05-31 |  | Nagarjun | 10
3066 | Kathmandu | Nagarjun N.P. | 14 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 3 | 2016-05-25 | 2016-05-31 |  | Nagarjun | 7
3067 | Kathmandu | Nagarjun N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | Nagarjun | 6
3068 | Kathmandu | Nagarjun N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04 |  | Nagarjun | 6
3069 | Kathmandu | Nagarjun N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | Nagarjun | 8
3070 | Kathmandu | Nagarjun N.P. | 11 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | Nagarjun | 8
3071 | Kathmandu | Nagarjun N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 3 | 3 | 2016-02-28 | 2016-03-04 |  | Nagarjun | 9
3072 | Kathmandu | Nagarjun N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 3 | 3 | 2016-02-28 | 2016-03-04 |  | Nagarjun | 10
3073 | Kathmandu | Nagarjun N.P. | 14 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-02-28 | 2016-03-04 |  | Nagarjun | 7
3074 | Kathmandu | Nagarjun N.P. | all | GoN | MoUD/DLPIU | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  |  | Yes | Completed | 32 | 32 | 2018-01-23 | 2018-01-29 |  | #N/A | #N/A
3075 | Kathmandu | Tarakeshwor N.P. | 1 | NRCS | NRCS | BRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 20 | 19 | 2016-01-01 | 2018-12-31 |  | Tarakeshwar | 1
3076 | Kathmandu | Tarakeshwor N.P. | 1 | NRCS | NRCS | BRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 20 | 0 | 2016-01-01 | 2018-12-31 |  | Tarakeshwar | 1
3077 | Kathmandu | Kathmandu M.N.P. | 17 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 55 | 55 | 2016-01-01 | 2018-12-31 |  | Kathmandu | 17
3078 | Kathmandu | Shankarapur N.P. | 8 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 7 | 2016-01-01 | 2018-12-31 |  | Shankharapur | 6
3079 | Kathmandu | Shankarapur N.P. | 9 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 4 | 3 | 2016-01-01 | 2018-12-31 |  | Shankharapur | 7
3080 | Kathmandu | Shankarapur N.P. | 10 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 4 | 3 | 2016-01-01 | 2018-12-31 |  | Shankharapur | 6
3081 | Kathmandu | Shankarapur N.P. | 11 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 4 | 5 | 2016-01-01 | 2018-12-31 |  | Shankharapur | 7
3082 | Kathmandu | Tarakeshwor N.P. | 1 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 15 | 31 | 2016-01-01 | 2018-12-31 |  | Tarakeshwar | 1
3083 | Kathmandu | Tarakeshwor N.P. | 2 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 15 | 10 | 2016-01-01 | 2018-12-31 |  | Tarakeshwar | 1
3084 | Kathmandu | Tarakeshwor N.P. | 3 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 15 | 18 | 2016-01-01 | 2018-12-31 |  | Tarakeshwar | 1
3085 | Kathmandu | Tarakeshwor N.P. | 7 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 15 | 5 | 2016-01-01 | 2018-12-31 |  | Tarakeshwar | 3
3086 | Kathmandu | Tarakeshwor N.P. | 8 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 15 | 46 | 2016-01-01 | 2018-12-31 |  | Tarakeshwar | 3
3087 | Kathmandu | Tarakeshwor N.P. | 13 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 15 | 32 | 2016-01-01 | 2018-12-31 |  | Tarakeshwar | 6
3088 | Kathmandu | Tarakeshwor N.P. | 14 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 14 | 9 | 2016-01-01 | 2018-12-31 |  | Tarakeshwar | 6
3089 | Kathmandu | Tarakeshwor N.P. | 15 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 15 | 23 | 2016-01-01 | 2018-12-31 |  | Tarakeshwar | 6
3090 | Kathmandu | Tarakeshwor N.P. | 9 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Ongoing | 10 | 7 | 2016-01-01 | 2018-12-31 |  | Tarakeshwar | 4
3091 | Kathmandu | Tarakeshwor N.P. | 10 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Ongoing | 10 | 4 | 2016-01-01 | 2018-12-31 |  | Tarakeshwar | 5
3092 | Kathmandu | Tarakeshwor N.P. | 11 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Ongoing | 10 | 19 | 2016-01-01 | 2018-12-31 |  | Tarakeshwar | 5
3093 | Kathmandu | Tarakeshwor N.P. | 1 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Ongoing | 10 | 0 | 2016-01-01 | 2018-12-31 |  | Tarakeshwar | 1
3094 | Kathmandu | Tarakeshwor N.P. | 2 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Ongoing | 10 | 0 | 2016-01-01 | 2018-12-31 |  | Tarakeshwar | 1
3095 | Kathmandu | Tarakeshwor N.P. | 3 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Ongoing | 10 | 0 | 2016-01-01 | 2018-12-31 |  | Tarakeshwar | 1
3096 | Kathmandu | Tarakeshwor N.P. | 7 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Ongoing | 10 | 0 | 2016-01-01 | 2018-12-31 |  | Tarakeshwar | 3
3097 | Kathmandu | Tarakeshwor N.P. | 8 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Ongoing | 20 | 0 | 2016-01-01 | 2018-12-31 |  | Tarakeshwar | 3
3098 | Kathmandu | Shankarapur N.P. |  | GoN | NRA-GMaLI | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  |  |  | Planned | 30 | 0 | 2018-06-14 | 2018-06-20 |  | #N/A | #N/A
#REF! | Lalitpur | Mahalaxmi N.P. | 19 | DCA | FSCN | DCA | Technical Assistance | Community reconstruction orientation | 1 session | Orientation on safe and resilient shelter construction | # of participants | Yes | Completed | 30 | 35 | 2016-07-13 | 2016-07-13 | Orientation by NRA Engineer | Mahalaxmi | 4
3100 | Lalitpur | Mahalaxmi N.P. | 1 | DCA | FSCN | DCA | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Community orientation program on safe and resilient shelter construction | # of participants | Yes | Completed | 150 | 180 | 2016-07-16 | 2016-07-17 |  | Mahalaxmi | 10
3101 | Lalitpur | Mahalaxmi N.P. | 1 | DCA | FSCN | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC curriculum mason training | # of trainees | Yes | Planned | 20 | 0 | 2016-12-30 | 2017-01-05 |  | Mahalaxmi | 10
3102 | Lalitpur | Mahalaxmi N.P. | 4 | DCA | FSCN | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC curriculum mason training | # of trainees | Yes | Completed | 20 | 23 | 2016-03-16 | 2016-03-20 | At that time the DUDBC curriculum was of 5 days | Mahalaxmi | 9
3103 | Lalitpur | Mahalaxmi N.P. |  | DCA | FSCN | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC curriculum mason training | # of trainees | Yes | Completed | 13 | 13 | 2017-01-25 | 2017-02-01 |  | Mahalaxmi | 9
3104 | Lalitpur | Mahalaxmi N.P. | 4 | DCA | FSCN | DCA | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT based 390 hours Mason Training | # of trainees | Yes | Completed | 18 | 18 | 2016-02-01 | 2016-04-02 |  | Mahalaxmi | 9
3105 | Lalitpur | Bajrabarahi N.P. | 2, 12, 13, 14, 15 | EWDE-DKH-N | Lumanti | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 65 houses under construction | # of households | Yes | Ongoing | 250 | 22 | 2016-10-15 | 2017-11-30 |  | Godawari | 5
3106 | Lalitpur | Bajrabarahi N.P. | 2, 12, 13, 14, 15 | EWDE-DKH-N | Lumanti | EWDE-DKH-N | Financial/Material/Labour Assistance | Material support on household WASH | HH water supply repair/rehabilitation |  | # of households | Yes | Ongoing | 6 | 3 | 2016-11-01 | 2017-08-31 |  | Godawari | 5
3107 | Lalitpur | Bajrabarahi N.P. | 2, 12, 13, 14, 15 | EWDE-DKH-N | Lumanti | EWDE-DKH-N | Financial/Material/Labour Assistance | Material support on household WASH | Household toilet construction | 5 latrines under construction | # of households | Yes | Ongoing | 250 | 9 | 2017-02-01 | 2017-11-30 |  | Godawari | 5
3108 | Lalitpur | Bajrabarahi N.P. | 2, 12, 13, 14, 15 | EWDE-DKH-N | Lumanti | EWDE-DKH-N | Others | Others | (Please specify in Activity Detail) | Capacity assessment, continuous capacity building and support; Capacity building of existing Saving & Credit groups | # of trainees | Yes | Ongoing | 6 | 0 | 2017-01-01 | 2017-10-31 |  | Godawari | 5
3109 | Lalitpur | Bajrabarahi N.P. | 2, 12, 13, 14, 15 | EWDE-DKH-N | Lumanti | EWDE-DKH-N | Others | Others | (Please specify in Activity Detail) | CBDRMPs finalised for Wards 1, 2, 3 and to be handed over to Municipality | # of trainees | Yes | Ongoing | 1 | 0 | 2016-11-01 | 2017-08-31 |  | Godawari | 5
3110 | Lalitpur | Bajrabarahi N.P. | 2, 12, 13, 14, 15 | EWDE-DKH-N | Lumanti | EWDE-DKH-N | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Ongoing | 300 | 132 | 2017-01-01 | 2017-09-30 |  | Godawari | 5
3111 | Lalitpur | Bajrabarahi N.P. | 2, 12, 13, 14, 15 | EWDE-DKH-N | Lumanti | EWDE-DKH-N | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 5 | 5 | 2016-11-01 | 2017-02-28 |  | Godawari | 5
3112 | Lalitpur | Bajrabarahi N.P. | 2, 12, 13, 14, 15 | EWDE-DKH-N | Lumanti | EWDE-DKH-N | Training | Other trainings | Other trainings (specify in Activity Detail) | First Aid | # of trainees | Yes | Completed | 48 | 50 | 2017-02-01 | 2017-02-28 |  | Godawari | 5
3113 | Lalitpur | Bajrabarahi N.P. | 2, 12, 13, 14, 15 | EWDE-DKH-N | Lumanti | EWDE-DKH-N | Training | Other trainings | Other trainings (specify in Activity Detail) | Search & Rescue | # of trainees | Yes | Ongoing | 48 | 44 | 2017-03-01 | 2017-07-31 |  | Godawari | 5
3114 | Lalitpur | Bajrabarahi N.P. | 2, 12, 13, 14, 15 | EWDE-DKH-N | Lumanti | EWDE-DKH-N | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Risk Management | # of trainees | Yes | Completed | 30 | 29 | 2017-01-01 | 2017-01-31 |  | Godawari | 5
3115 | Lalitpur | Bajrabarahi N.P. | 2, 12, 13, 14, 15 | EWDE-DKH-N | Lumanti | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 80 | 58 | 2016-09-15 | 2017-07-31 |  | Godawari | 5
3116 | Lalitpur | Bajrabarahi N.P. | 2, 12, 13, 14, 15 | EWDE-DKH-N | Lumanti | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 300 | 132 |  |  |  | Godawari | 5
3117 | Lalitpur | Bajrabarahi N.P. | 5 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 60 | 46 | 2016-12-01 | 2018-02-28 |  | Godawari | 12
3118 | Lalitpur | Bajrabarahi N.P. | 6 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 55 | 51 | 2016-12-01 | 2018-02-28 |  | Godawari | 12
3119 | Lalitpur | Bajrabarahi N.P. | 5 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 60 | 15 | 2016-12-01 | 2018-02-28 |  | Godawari | 12
3120 | Lalitpur | Bajrabarahi N.P. | 6 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 55 | 15 | 2016-12-01 | 2018-02-28 |  | Godawari | 12
3121 | Lalitpur | Bajrabarahi N.P. | 5 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 60 | 14 | 2016-12-01 | 2018-02-28 |  | Godawari | 12
3122 | Lalitpur | Bajrabarahi N.P. | 6 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 55 | 14 | 2016-12-01 | 2018-02-28 |  | Godawari | 12
3123 | Lalitpur | Bajrabarahi N.P. | 4 | Lumanti | Lumanti | MSEREOR | Others | Others | (Please specify in Activity Detail) | a)Retaining wall construction to prevent landslide at Pingal (b) Landscaping at Pingal Park (c) Road pavement of Funral route | # of trainees | Yes | Completed | 3 | 3 | 2016-08-01 | 2017-02-28 |  | Godawari | 12
3124 | Lalitpur | Bajrabarahi N.P. | 5 | Lumanti | Lumanti | MSEREOR | Others | Others | (Please specify in Activity Detail) | (a)Increasing the size of drainage pipe at Khacha, Kutujhol to speed up the flow of waste water and prevent clogging (b) Pavement of pathway in Buddha Park | # of trainees | Yes | Ongoing | 2 | 0 | 2016-08-01 | 2017-02-28 |  | Godawari | 12
3125 | Lalitpur | Bajrabarahi N.P. | 6 | Lumanti | Lumanti | MSEREOR | Others | Others | (Please specify in Activity Detail) | Drainage pipe maonagement from KweLahhi to Fongapukhu | # of trainees | Yes | Completed | 1 | 1 | 2016-08-01 | 2017-02-28 |  | Godawari | 12
3126 | Lalitpur | Bajrabarahi N.P. | 6 | Lumanti | Lumanti | MSEREOR | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Ongoing | 15 | 2 | 2016-12-01 | 2018-02-28 |  | Godawari | 12
3127 | Lalitpur | Bajrabarahi N.P. | 5 | Lumanti | Lumanti | MSEREOR | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Planned | 15 | 2 | 2016-12-01 | 2018-02-28 |  | Godawari | 12
3128 | Lalitpur | Bajrabarahi N.P. | 6 | Lumanti | Lumanti | MSEREOR | Others | Others | (Please specify in Activity Detail) | Construction of Fongashi Drainage | # of trainees | Yes | Completed | 1 | 3 | 2016-08-01 | 2017-02-28 |  | Godawari | 12
3129 | Lalitpur | Bajrabarahi N.P. | 5 | LUMANTI | LUMANTI | MSEREOR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Ongoing | 120 | 120 | 2016-12-01 | 2018-02-28 |  | Godawari | 12
3130 | Lalitpur | Bajrabarahi N.P. | 6 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Ongoing | 240 | 240 | 2016-12-01 | 2018-02-28 |  | Godawari | 12
3131 | Lalitpur | Bajrabarahi N.P. | 5 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 60 | 60 | 2016-12-01 | 2018-02-28 |  | Godawari | 12
3132 | Lalitpur | Bajrabarahi N.P. | 6 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 55 | 55 | 2016-12-01 | 2018-02-28 |  | Godawari | 12
3133 | Lalitpur | Bajrabarahi N.P. | 5 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Information Center for reconstruction process | # of households supported | Yes | Ongoing | 115 | 115 | 2016-12-01 | 2018-02-28 |  | Godawari | 12
3134 | Lalitpur | Bajrabarahi N.P. | 6 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Household reconstruction orientation | 2-3 sessions |  | # of households | Yes | Ongoing | 55 | 55 | 2016-12-01 | 2018-02-28 |  | Godawari | 12
3135 | Lalitpur | Bajrabarahi N.P. | 5 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Water, Sanitation and Hygiene (Posters, Flipchart, documentaries and orientation ) | # of households | Yes | Ongoing | 24 | 12 | 2016-12-01 | 2018-02-28 |  | Godawari | 12
3136 | Lalitpur | Bajrabarahi N.P. | 6 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | Water, Sanitation and Hygiene (Posters, Flipchart, documentaries ) | # of households | Yes | Ongoing | 2 | 0 | 2016-12-01 | 2018-02-28 |  | Godawari | 12
3137 | Lalitpur | Dalchoki | 1 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Project Completed from 31 July 2017 | # of households | Yes | Completed | 34 | 34 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3138 | Lalitpur | Dalchoki | 2 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Project Completed from 31 July 2017 | # of households | Yes | Completed | 15 | 15 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3139 | Lalitpur | Dalchoki | 3 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Project Completed from 31 July 2022 | # of households | Yes | Completed | 23 | 23 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3140 | Lalitpur | Dalchoki | 4 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Project Completed from 31 July 2027 | # of households | Yes | Completed | 23 | 23 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3141 | Lalitpur | Dalchoki | 5 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Project Completed from 31 July 2032 | # of households | Yes | Completed | 21 | 21 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3142 | Lalitpur | Dalchoki | 6 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Project Completed from 31 July 2037 | # of households | Yes | Completed | 19 | 19 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3143 | Lalitpur | Dalchoki | 7 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Project Completed from 31 July 2042 | # of households | Yes | Completed | 47 | 44 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3144 | Lalitpur | Dalchoki | 8 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Project Completed from 31 July 2047 | # of households | Yes | Completed | 34 | 34 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3145 | Lalitpur | Dalchoki | 9 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Project Completed from 31 July 2052 | # of households | Yes | Completed | 34 | 34 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3146 | Lalitpur | Dalchoki | 1 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Project Completed from 31 July 2018 | # of households | Yes | Completed | 34 | 34 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3147 | Lalitpur | Dalchoki | 2 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Project Completed from 31 July 2018 | # of households | Yes | Completed | 15 | 15 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3148 | Lalitpur | Dalchoki | 3 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Project Completed from 31 July 2023 | # of households | Yes | Completed | 23 | 23 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3149 | Lalitpur | Dalchoki | 4 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Project Completed from 31 July 2028 | # of households | Yes | Completed | 23 | 23 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3150 | Lalitpur | Dalchoki | 5 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Project Completed from 31 July 2033 | # of households | Yes | Completed | 21 | 21 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3151 | Lalitpur | Dalchoki | 6 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Project Completed from 31 July 2038 | # of households | Yes | Completed | 19 | 19 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3152 | Lalitpur | Dalchoki | 7 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Project Completed from 31 July 2043 | # of households | Yes | Completed | 47 | 44 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3153 | Lalitpur | Dalchoki | 8 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Project Completed from 31 July 2048 | # of households | Yes | Completed | 34 | 34 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3154 | Lalitpur | Dalchoki | 9 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Project Completed from 31 July 2053 | # of households | Yes | Completed | 34 | 34 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3155 | Lalitpur | Dalchoki | 1 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Project Completed from 31 July 2019 | # of households | Yes | Completed | 34 | 34 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3156 | Lalitpur | Dalchoki | 2 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Project Completed from 31 July 2019 | # of households | Yes | Completed | 15 | 15 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3157 | Lalitpur | Dalchoki | 3 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Project Completed from 31 July 2024 | # of households | Yes | Completed | 23 | 23 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3158 | Lalitpur | Dalchoki | 4 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Project Completed from 31 July 2029 | # of households | Yes | Completed | 23 | 23 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3159 | Lalitpur | Dalchoki | 5 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Project Completed from 31 July 2034 | # of households | Yes | Completed | 21 | 21 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3160 | Lalitpur | Dalchoki | 6 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Project Completed from 31 July 2039 | # of households | Yes | Completed | 19 | 19 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3161 | Lalitpur | Dalchoki | 7 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Project Completed from 31 July 2044 | # of households | Yes | Completed | 47 | 44 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3162 | Lalitpur | Dalchoki | 8 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Project Completed from 31 July 2049 | # of households | Yes | Completed | 34 | 34 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3163 | Lalitpur | Dalchoki | 9 | Lumanti | Lumanti | HUMEDICA | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Project Completed from 31 July 2054 | # of households | Yes | Completed | 34 | 32 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3164 | Lalitpur | Dalchoki | 1 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Project Completed from 31 July 2020 | # of participants | Yes | Completed | 34 | 34 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3165 | Lalitpur | Dalchoki | 2 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Project Completed from 31 July 2020 | # of participants | Yes | Completed | 15 | 15 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3166 | Lalitpur | Dalchoki | 3 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Project Completed from 31 July 2025 | # of participants | Yes | Completed | 23 | 23 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3167 | Lalitpur | Dalchoki | 4 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Project Completed from 31 July 2030 | # of participants | Yes | Completed | 23 | 23 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3168 | Lalitpur | Dalchoki | 5 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Project Completed from 31 July 2035 | # of participants | Yes | Completed | 21 | 21 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3169 | Lalitpur | Dalchoki | 6 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Project Completed from 31 July 2040 | # of participants | Yes | Completed | 19 | 19 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3170 | Lalitpur | Dalchoki | 7 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Project Completed from 31 July 2045 | # of participants | Yes | Completed | 47 | 47 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3171 | Lalitpur | Dalchoki | 8 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Project Completed from 31 July 2050 | # of participants | Yes | Completed | 34 | 34 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3172 | Lalitpur | Dalchoki | 9 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Project Completed from 31 July 2055 | # of participants | Yes | Completed | 34 | 34 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3173 | Lalitpur | Dalchoki | 1 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Door-to-door technical assistance | Continuous | Project Completed from 31 July 2021 | # of households | Yes | Completed | 34 | 34 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3174 | Lalitpur | Dalchoki | 2 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Door-to-door technical assistance | Continuous | Project Completed from 31 July 2021 | # of households | Yes | Completed | 15 | 15 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3175 | Lalitpur | Dalchoki | 3 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Door-to-door technical assistance | Continuous | Project Completed from 31 July 2026 | # of households | Yes | Completed | 23 | 23 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3176 | Lalitpur | Dalchoki | 4 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Door-to-door technical assistance | Continuous | Project Completed from 31 July 2031 | # of households | Yes | Completed | 23 | 23 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3177 | Lalitpur | Dalchoki | 5 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Door-to-door technical assistance | Continuous | Project Completed from 31 July 2036 | # of households | Yes | Completed | 21 | 21 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3178 | Lalitpur | Dalchoki | 6 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Door-to-door technical assistance | Continuous | Project Completed from 31 July 2041 | # of households | Yes | Completed | 19 | 19 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3179 | Lalitpur | Dalchoki | 7 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Door-to-door technical assistance | Continuous | Project Completed from 31 July 2046 | # of households | Yes | Completed | 47 | 47 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3180 | Lalitpur | Dalchoki | 8 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Door-to-door technical assistance | Continuous | Project Completed from 31 July 2051 | # of households | Yes | Completed | 34 | 34 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3181 | Lalitpur | Dalchoki | 9 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Door-to-door technical assistance | Continuous | Project Completed from 31 July 2056 | # of households | Yes | Completed | 34 | 34 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3182 | Lalitpur | Dalchoki | 1 | Lumanti | Lumanti | HUMEDICA | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Information Center for reconstruction process | # of households supported | Yes | Completed | 250 | 250 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3183 | Lalitpur | Dalchoki | 9 | Lumanti | Lumanti | HUMEDICA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC Curriculum 10 Days | # of trainees | Yes | Completed | 38 | 38 | 2016-02-01 | 2017-07-31 |  | Konjyosom | 3
3184 | Lalitpur | Mahalaxmi N.P. | 12 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 33 | 21 | 2016-12-01 | 2018-02-28 |  | Mahalaxmi | 6
3185 | Lalitpur | Mahalaxmi N.P. | 13 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 41 | 30 | 2016-12-01 | 2018-02-28 |  | Mahalaxmi | 6
3186 | Lalitpur | Mahalaxmi N.P. | 14 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 41 | 24 | 2016-12-01 | 2018-02-28 |  | Mahalaxmi | 6
3187 | Lalitpur | Mahalaxmi N.P. | 12 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 33 | 2 | 2016-12-01 | 2018-02-28 |  | Mahalaxmi | 6
3188 | Lalitpur | Mahalaxmi N.P. | 13 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 41 | 3 | 2016-12-01 | 2018-02-28 |  | Mahalaxmi | 6
3189 | Lalitpur | Mahalaxmi N.P. | 14 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 41 | 2 | 2016-12-01 | 2018-02-28 |  | Mahalaxmi | 6
3190 | Lalitpur | Mahalaxmi N.P. | 12 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 33 | 1 | 2016-12-01 | 2018-02-28 |  | Mahalaxmi | 6
3191 | Lalitpur | Mahalaxmi N.P. | 13 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 41 | 2 | 2016-12-01 | 2018-02-28 |  | Mahalaxmi | 6
3192 | Lalitpur | Mahalaxmi N.P. | 14 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 41 | 4 | 2016-12-01 | 2018-02-28 |  | Mahalaxmi | 6
3193 | Lalitpur | Mahalaxmi N.P. | 12 | Lumanti | Lumanti | MSEREOR | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Ongoing | 10 | 0 | 2016-12-01 | 2018-02-28 |  | Mahalaxmi | 6
3194 | Lalitpur | Mahalaxmi N.P. | 13 | Lumanti | Lumanti | MSEREOR | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Planned | 10 | 0 | 2017-03-01 | 2018-02-28 |  | Mahalaxmi | 6
3195 | Lalitpur | Mahalaxmi N.P. | 14 | Lumanti | Lumanti | MSEREOR | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Planned | 10 | 0 | 2017-03-01 | 2018-02-28 |  | Mahalaxmi | 6
3196 | Lalitpur | Mahalaxmi N.P. | 12 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 80 | 18 | 2017-07-15 | 2017-07-15 |  | Mahalaxmi | 6
3197 | Lalitpur | Mahalaxmi N.P. | 13 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 80 | 27 | 2017-08-04 | 2017-08-04 |  | Mahalaxmi | 6
3198 | Lalitpur | Mahalaxmi N.P. | 14 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Ongoing | 80 | 38 | 2017-08-12 | 2017-08-12 |  | Mahalaxmi | 6
3199 | Lalitpur | Mahalaxmi N.P. | 12 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 33 | 33 | 2016-12-01 | 2018-02-28 |  | Mahalaxmi | 6
3200 | Lalitpur | Mahalaxmi N.P. | 13 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 41 | 41 | 2016-12-01 | 2018-02-28 |  | Mahalaxmi | 6
3201 | Lalitpur | Mahalaxmi N.P. | 14 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 41 | 41 | 2016-12-01 | 2018-02-28 |  | Mahalaxmi | 6
3202 | Lalitpur | Mahalaxmi N.P. | 12 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Information Center for reconstruction process | # of households supported | Yes | Ongoing | 115 | 115 | 2016-12-01 | 2018-02-28 |  | Mahalaxmi | 6
3203 | Lalitpur | Mahalaxmi N.P. | 12 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Household reconstruction orientation | 2-3 sessions |  | # of households | Yes | Ongoing | 33 | 33 | 2016-12-01 | 2018-02-28 |  | Mahalaxmi | 6
3204 | Lalitpur | Mahalaxmi N.P. | 13 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Household reconstruction orientation | 2-3 sessions |  | # of households | Yes | Ongoing | 41 | 41 | 2016-12-01 | 2018-02-28 |  | Mahalaxmi | 6
3205 | Lalitpur | Mahalaxmi N.P. | 14 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Household reconstruction orientation | 2-3 sessions |  | # of households | Yes | Ongoing | 41 | 41 | 2016-12-01 | 2018-02-28 |  | Mahalaxmi | 6
3206 | Lalitpur | Mahalaxmi N.P. | 12 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Water, Sanitation and Hygiene (Posters, Flipchart, documentaries and orientation ) | # of households | Yes | Planned | 33 | 0 | 2017-03-01 | 2018-02-28 |  | Mahalaxmi | 6
3207 | Lalitpur | Mahalaxmi N.P. | 13 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Water, Sanitation and Hygiene (Posters, Flipchart, documentaries and orientation ) | # of households | Yes | Planned | 41 | 0 | 2017-03-01 | 2018-02-28 |  | Mahalaxmi | 6
3208 | Lalitpur | Mahalaxmi N.P. | 14 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Water, Sanitation and Hygiene (Posters, Flipchart, documentaries and orientation ) | # of households | Yes | Planned | 41 | 0 | 2017-03-01 | 2018-02-28 |  | Mahalaxmi | 6
3209 | Lalitpur | Asrang | 1 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Support housing grant to Construct Permanent Shelter | # of households | Yes | Completed | 2 | 2 | 2016-08-01 | 2017-03-30 |  | Bagmati | 6
3210 | Lalitpur | Asrang | 1 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 2 | 2 | 2016-08-01 | 2017-03-30 |  | Bagmati | 6
3211 | Lalitpur | Asrang | 1 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 2 | 2 | 2016-08-01 | 2017-03-30 |  | Bagmati | 6
3212 | Lalitpur | Asrang | 2 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 1 | 1 | 2016-08-01 | 2017-03-30 |  | Bagmati | 6
3213 | Lalitpur | Asrang | 2 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 1 | 1 | 2016-08-01 | 2017-03-30 |  | Bagmati | 6
3214 | Lalitpur | Asrang | 2 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 1 | 1 | 2016-08-01 | 2017-03-30 |  | Bagmati | 6
3215 | Lalitpur | Asrang | 3 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 14 | 14 | 2016-08-01 | 2017-03-30 |  | Bagmati | 6
3216 | Lalitpur | Asrang | 3 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 14 | 14 | 2016-08-01 | 2017-03-30 |  | Bagmati | 6
3217 | Lalitpur | Asrang | 3 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 14 | 14 | 2016-08-01 | 2017-03-30 |  | Bagmati | 6
3218 | Lalitpur | Asrang | 6 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 3 | 3 | 2016-08-01 | 2017-03-30 |  | Bagmati | 6
3219 | Lalitpur | Asrang | 6 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 3 | 3 | 2016-08-01 | 2017-03-30 |  | Bagmati | 6
3220 | Lalitpur | Asrang | 6 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 3 | 3 | 2016-08-01 | 2017-03-30 |  | Bagmati | 6
3221 | Lalitpur | Asrang | 7 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 11 | 11 | 2016-08-01 | 2017-03-30 |  | Bagmati | 6
3222 | Lalitpur | Asrang | 7 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 11 | 11 | 2016-08-01 | 2017-03-30 |  | Bagmati | 6
3223 | Lalitpur | Asrang | 7 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 11 | 11 | 2016-08-01 | 2017-03-30 |  | Bagmati | 6
3224 | Lalitpur | Asrang | 9 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 9 | 9 | 2016-08-01 | 2017-03-30 |  | Bagmati | 6
3225 | Lalitpur | Asrang | 9 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 9 | 9 | 2016-08-01 | 2017-03-30 |  | Bagmati | 6
3226 | Lalitpur | Asrang | 9 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 9 | 9 | 2016-08-01 | 2017-03-30 |  | Bagmati | 6
3227 | Lalitpur | Bhattedanda | 8 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 40 | 39 | 2016-08-01 | 2017-03-30 |  | Bagmati | 3
3228 | Lalitpur | Bhattedanda | 8 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 40 | 39 | 2016-08-01 | 2017-03-30 |  | Bagmati | 3
3229 | Lalitpur | Bhattedanda | 8 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 40 | 39 | 2016-08-01 | 2017-03-30 |  | Bagmati | 3
3230 | Lalitpur | Dhusel | 1 | LWF | Solve-N | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 67 | 67 | 2016-08-01 | 2017-03-30 |  | Bagmati | 1
3231 | Lalitpur | Dhusel | 1 | LWF | Solve-N | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 67 | 67 | 2016-08-01 | 2017-03-30 |  | Bagmati | 1
3232 | Lalitpur | Dhusel | 1 | LWF | Solve-N | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 67 | 67 | 2016-08-01 | 2017-03-30 |  | Bagmati | 1
3233 | Lalitpur | Dhusel | 8 | LWF | Solve-N | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 37 | 37 | 2016-08-01 | 2017-03-30 |  | Bagmati | 1
3234 | Lalitpur | Dhusel | 8 | LWF | Solve-N | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 37 | 37 | 2016-08-01 | 2017-03-30 |  | Bagmati | 1
3235 | Lalitpur | Dhusel | 8 | LWF | Solve-N | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 37 | 37 | 2016-08-01 | 2017-03-30 |  | Bagmati | 1
3236 | Lalitpur | Dhusel | 9 | LWF | Solve-N | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 16 | 16 | 2016-08-01 | 2017-03-30 |  | Bagmati | 1
3237 | Lalitpur | Dhusel | 9 | LWF | Solve-N | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 16 | 16 | 2016-08-01 | 2017-03-30 |  | Bagmati | 1
3238 | Lalitpur | Dhusel | 9 | LWF | Solve-N | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 16 | 16 | 2016-08-01 | 2017-03-30 |  | Bagmati | 1
3239 | Lalitpur | Gimdi | 2 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 3 | 3 | 2016-08-01 | 2017-03-30 |  | Bagmati | 7
3240 | Lalitpur | Gimdi | 2 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 3 | 3 | 2016-08-01 | 2017-03-30 |  | Bagmati | 7
3241 | Lalitpur | Gimdi | 2 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 3 | 3 | 2016-08-01 | 2017-03-30 |  | Bagmati | 7
3242 | Lalitpur | Gimdi | 4 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 17 | 17 | 2016-08-01 | 2017-03-30 |  | Bagmati | 7
3243 | Lalitpur | Gimdi | 4 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 17 | 17 | 2016-08-01 | 2017-03-30 |  | Bagmati | 7
3244 | Lalitpur | Gimdi | 4 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 17 | 17 | 2016-08-01 | 2017-03-30 |  | Bagmati | 7
3245 | Lalitpur | Gimdi | 5 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 20 | 19 | 2016-08-01 | 2017-03-30 |  | Bagmati | 7
3246 | Lalitpur | Gimdi | 5 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 20 | 19 | 2016-08-01 | 2017-03-30 |  | Bagmati | 7
3247 | Lalitpur | Gimdi | 5 | LWF | ICDO | ACT Alliance | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Support housing grant to Construct Permanent Shelter |  | Yes | Completed | 20 | 19 | 2016-08-01 | 2017-03-30 |  | Bagmati | 7
3248 | Lalitpur | Asrang | 1,2,3,6,7,9 | LWF | ICDO | ACT Alliance | Technical Assistance | Door-to-door technical assistance | Continuous |  |  | Yes | Completed | 40 | 40 | 2016-08-01 | 2017-03-30 |  | #N/A | #N/A
3249 | Lalitpur | Bhattedanda | 8 | LWF | ICDO | ACT Alliance | Technical Assistance | Door-to-door technical assistance | Continuous |  |  | Yes | Completed | 40 | 39 | 2016-08-01 | 2017-03-30 |  | Bagmati | 3
3250 | Lalitpur | Dhusel | 1,8,9 | LWF | Solve-N | ACT Alliance | Technical Assistance | Door-to-door technical assistance | Continuous |  |  | Yes | Completed | 120 | 120 | 2016-08-01 | 2017-03-30 |  | #N/A | #N/A
3251 | Lalitpur | Gimdi | 2,4,5 | LWF | ICDO | ACT Alliance | Technical Assistance | Door-to-door technical assistance | Continuous |  |  | Yes | Completed | 40 | 39 | 2016-08-01 | 2017-03-30 |  | #N/A | #N/A
3252 | Lalitpur | Asrang | All | LWF | ICDO | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training for existing masons | # of trainees | Yes | Completed | 30 | 30 | 2017-03-02 | 2017-03-08 |  | #N/A | #N/A
3253 | Lalitpur | Bhattedanda |  | LWF | ICDO | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training for existing masons | # of trainees | Yes | Completed | 30 | 30 | 2017-03-13 | 2017-03-19 |  | Bagmati | 3
3254 | Lalitpur | Dhusel |  | LWF | DEAN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training for existing masons | # of trainees | Yes | Completed | 30 | 31 | 2017-01-24 | 2017-01-30 |  | Bagmati | 1
3255 | Lalitpur | Gimdi |  | LWF | DEAN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) | Training for existing masons | # of trainees | Yes | Completed | 30 | 30 | 2017-02-06 | 2017-02-12 |  | Bagmati | 7
3256 | Lalitpur | Asrang | All | LWF | DEAN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 32 | 32 |  |  |  | #N/A | #N/A
3257 | Lalitpur | Gimdi | All | LWF | DEAN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 |  |  |  | #N/A | #N/A
3258 | Lalitpur | Ikudol | All | LWF | DEAN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 27 | 27 |  |  |  | #N/A | #N/A
3259 | Lalitpur | Pyutar | All | LWF | DEAN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 31 | 31 |  |  |  | #N/A | #N/A
3260 | Lalitpur | Devichour | All | LWF | DEAN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 28 | 28 |  |  |  | #N/A | #N/A
3261 | Lalitpur | Sankhu | All | LWF | DEAN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 27 | 27 |  |  |  | #N/A | #N/A
3262 | Lalitpur | Mahalaxmi N.P. | All | LWF | DEAN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 32 | 32 |  |  |  | #N/A | #N/A
3263 | Lalitpur | Dhusel | All | LWF | DEAN | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 |  |  |  | #N/A | #N/A
3264 | Lalitpur | Lalitpur U.M.N.P. | 25 | NSET | NSET | USAID | Training | Other trainings | Basic Engineers Training |  | # of trainees | Yes | Completed | 84 | 77 | 2015-10-01 | 2020-09-30 |  | Lalitpur | 24
3265 | Lalitpur | Lalitpur U.M.N.P. | 25 | NSET | NSET | USAID | Training | Other trainings | Other trainings (specify in Activity Detail) | Advance engineers training | # of trainees | Yes | Completed | 56 | 27 | 2015-10-01 | 2020-09-30 |  | Lalitpur | 24
3266 | Lalitpur | Lalitpur U.M.N.P. | 23 | NSET | NSET | USAID | Training | Other trainings | Other trainings (specify in Activity Detail) | Training for instuctors (TFI) | # of trainees | Yes | Completed | 112 | 83 | 2015-10-01 | 2020-09-30 |  | Lalitpur | 23
3267 | Lalitpur | Choughare | 1 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-12-22 | 2016-12-28 |  | Konjyosom | 1
3268 | Lalitpur | Choughare | 2 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 6 | 2016-12-22 | 2016-12-28 |  | Konjyosom | 1
3269 | Lalitpur | Choughare | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 4 | 2016-12-22 | 2016-12-28 |  | Konjyosom | 1
3270 | Lalitpur | Choughare | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 1 | 2016-12-22 | 2016-12-28 |  | Konjyosom | 1
3271 | Lalitpur | Choughare | 5 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 3 | 2016-12-22 | 2016-12-28 |  | Konjyosom | 1
3272 | Lalitpur | Choughare | 6 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-12-22 | 2016-12-28 |  | Konjyosom | 1
3273 | Lalitpur | Choughare | 7 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-12-22 | 2016-12-28 |  | Konjyosom | 1
3274 | Lalitpur | Choughare | 9 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 6 | 2016-12-22 | 2016-12-28 |  | Konjyosom | 1
3275 | Lalitpur | Godawari N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 9 | 9 | 2016-01-28 | 2016-02-02 |  | Godawari | 2
3276 | Lalitpur | Godawari N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 9 | 18 | 2016-01-28 | 2016-02-02 |  | Godawari | 2
3277 | Lalitpur | Mahalaxmi N.P. | 1 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 50 | 98 | 2016-06-15 | 2016-06-15 |  | Mahalaxmi | 10
3278 | Lalitpur | Mahalaxmi N.P. | 1 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 29 | 2016-12-08 | 2016-12-08 |  | Mahalaxmi | 10
3279 | Lalitpur | Mahalaxmi N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 30 | 20 | 2016-12-12 | 2016-12-12 |  | Mahalaxmi | 9
3280 | Lalitpur | Mahalaxmi N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 10 | 23 | 2016-08-12 | 2016-08-12 |  | Mahalaxmi | 8
3281 | Lalitpur | Mahalaxmi N.P. | 6 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 10 | 20 | 2016-08-12 | 2016-08-12 |  | Mahalaxmi | 8
3282 | Lalitpur | Mahalaxmi N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 10 | 20 | 2016-08-12 | 2016-08-12 |  | Mahalaxmi | 8
3283 | Lalitpur | Mahalaxmi N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 10 | 10 | 2016-08-12 | 2016-08-12 |  | Mahalaxmi | 8
3284 | Lalitpur | Mahalaxmi N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 15 | 18 | 2016-08-25 | 2016-08-25 |  | Mahalaxmi | 6
3285 | Lalitpur | Mahalaxmi N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 15 | 6 | 2016-08-25 | 2016-08-25 |  | Mahalaxmi | 6
3286 | Lalitpur | Mahalaxmi N.P. | 14 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Community reconstruction orientation | 1 session | 2-3 Hours session | # of participants | Yes | Completed | 15 | 6 | 2016-08-25 | 2016-08-25 |  | Mahalaxmi | 6
3287 | Lalitpur | Mahalaxmi N.P. | 1 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Mahalaxmi | 10
3288 | Lalitpur | Mahalaxmi N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Mahalaxmi | 9
3289 | Lalitpur | Mahalaxmi N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Mahalaxmi | 9
3290 | Lalitpur | Mahalaxmi N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Mahalaxmi | 9
3291 | Lalitpur | Mahalaxmi N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Mahalaxmi | 8
3292 | Lalitpur | Mahalaxmi N.P. | 6 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Mahalaxmi | 8
3293 | Lalitpur | Mahalaxmi N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Mahalaxmi | 8
3294 | Lalitpur | Mahalaxmi N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Mahalaxmi | 8
3295 | Lalitpur | Mahalaxmi N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Mahalaxmi | 5
3296 | Lalitpur | Mahalaxmi N.P. | 10 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Mahalaxmi | 5
3297 | Lalitpur | Mahalaxmi N.P. | 11 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Mahalaxmi | 7
3298 | Lalitpur | Mahalaxmi N.P. | 12 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Mahalaxmi | 6
3299 | Lalitpur | Mahalaxmi N.P. | 13 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Door-to-door technical assistance | Continuous | Mobilise a team of 5 for 5 days | # of households | Yes | Ongoing | 15 | 0 | 2017-01-23 | 2017-03-31 |  | Mahalaxmi | 6
3300 | Lalitpur | Mahalaxmi N.P. | 15 | OXFAM-GB | OXFAM-GB |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Information center at municipality office | # of households supported | Yes | Ongoing | 200 | 0 | 2016-11-25 | 2017-03-31 |  | Mahalaxmi | 4
3301 | Lalitpur | Mahalaxmi N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 7 | 2016-09-16 | 2016-09-22 |  | Mahalaxmi | 9
3302 | Lalitpur | Mahalaxmi N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 2 | 2016-09-16 | 2016-09-22 |  | Mahalaxmi | 9
3303 | Lalitpur | Mahalaxmi N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 1 | 2016-09-16 | 2016-09-22 |  | Mahalaxmi | 9
3304 | Lalitpur | Mahalaxmi N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 1 | 2016-09-16 | 2016-09-22 |  | Mahalaxmi | 8
3305 | Lalitpur | Mahalaxmi N.P. | 6 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 7 | 2016-09-16 | 2016-09-22 |  | Mahalaxmi | 8
3306 | Lalitpur | Mahalaxmi N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 2 | 2016-09-16 | 2016-09-22 |  | Mahalaxmi | 8
3307 | Lalitpur | Mahalaxmi N.P. | 1 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 2 | 1 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | Mahalaxmi | 10
3308 | Lalitpur | Mahalaxmi N.P. | 1 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 1 | 2016-01-28 | 2016-02-02 |  | Mahalaxmi | 10
3309 | Lalitpur | Mahalaxmi N.P. | 2 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-01-28 | 2016-02-02 |  | Mahalaxmi | 9
3310 | Lalitpur | Mahalaxmi N.P. | 3 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-01-28 | 2016-02-02 |  | Mahalaxmi | 9
3311 | Lalitpur | Mahalaxmi N.P. | 4 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-01-28 | 2016-02-02 |  | Mahalaxmi | 9
3312 | Lalitpur | Mahalaxmi N.P. | 5 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-01-28 | 2016-02-02 |  | Mahalaxmi | 8
3313 | Lalitpur | Mahalaxmi N.P. | 6 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-01-28 | 2016-02-02 |  | Mahalaxmi | 8
3314 | Lalitpur | Mahalaxmi N.P. | 7 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-01-28 | 2016-02-02 |  | Mahalaxmi | 8
3315 | Lalitpur | Mahalaxmi N.P. | 8 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-01-28 | 2016-02-02 |  | Mahalaxmi | 8
3316 | Lalitpur | Mahalaxmi N.P. | 9 | OXFAM-GB | OXFAM-GB |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | # of trainees | Yes | Completed | 2 | 2 | 2016-08-25 | 2016-09-08 | short term (15days), It has been tailored to meet the needs of low skilled labors to undertake 7 days masons training | Mahalaxmi | 5
3317 | Lalitpur | Choughare | 1 | OXFAM-GB |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Konjyosom | 1
3318 | Lalitpur | Choughare | 2 | OXFAM-GB |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Konjyosom | 1
3319 | Lalitpur | Choughare | 3 | OXFAM-GB |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Konjyosom | 1
3320 | Lalitpur | Choughare | 4 | OXFAM-GB |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Konjyosom | 1
3321 | Lalitpur | Choughare | 5 | OXFAM-GB |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Konjyosom | 1
3322 | Lalitpur | Choughare | 7 | OXFAM-GB |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Konjyosom | 1
3323 | Lalitpur | Choughare | 9 | OXFAM-GB |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 |  |  |  | Konjyosom | 1
3324 | Lalitpur | Thuladurlung | All | OXFAM-GB |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 |  |  |  | #N/A | #N/A
3325 | Lalitpur | Choughare | 1,2,3,4,5,7,9 | OXFAM-GB |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 |  |  |  | #N/A | #N/A
3326 | Lalitpur | Bajrabarahi N.P. | All | RICOD | MCC |  | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Planned | 40 | 0 |  |  |  | Godawari | 12
3327 | Lalitpur | Bhardev | All | RICOD | MCC |  | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Planned | 40 | 0 |  |  |  | Konjyosom | 5
3328 | Lalitpur | Bhardev | All | RICOD | MCC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 50 | 45 | 2017-03-03 | 2017-03-13 |  | Konjyosom | 5
3329 | Lalitpur | Choughare | All | RICOD | MCC |  | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Ongoing | 40 | 4 |  |  |  | Konjyosom | 1
3330 | Lalitpur | Dalchoki | All | RICOD | MCC |  | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Planned | 40 | 0 |  |  |  | Konjyosom | 3
3331 | Lalitpur | Nallu | All | RICOD | MCC |  | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Ongoing | 40 | 6 |  |  |  | Konjyosom | 4
3332 | Lalitpur | Bajrabarahi N.P. | 1 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 1 | 1 | 2015-09-01 | 2016-07-01 |  | Godawari | 13
3333 | Lalitpur | Bajrabarahi N.P. | 9 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 3 | 3 | 2015-09-01 | 2016-07-01 |  | Godawari | 11
3334 | Lalitpur | Bajrabarahi N.P. | 11 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 7 | 7 | 2015-09-01 | 2016-07-01 |  | Godawari | 10
3335 | Lalitpur | Bajrabarahi N.P. | 12 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 8 | 8 | 2015-09-01 | 2016-07-01 |  | Godawari | 10
3336 | Lalitpur | Bajrabarahi N.P. | 13 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 20 | 20 | 2015-09-01 | 2016-07-01 |  | Godawari | 10
3337 | Lalitpur | Bajrabarahi N.P. | 14 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 9 | 9 | 2015-09-01 | 2016-07-01 |  | Godawari | 5
3338 | Lalitpur | Bajrabarahi N.P. | 15 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 4 | 4 | 2015-09-01 | 2016-07-01 |  | Godawari | 5
3339 | Lalitpur | Bajrabarahi N.P. | 16 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 2 | 2 | 2015-09-01 | 2016-07-01 |  | Godawari | 6
3340 | Lalitpur | Bajrabarahi N.P. | 17 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 1 | 1 | 2015-09-01 | 2016-07-01 |  | Godawari | 6
3341 | Lalitpur | Bajrabarahi N.P. | 13 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 44 | 44 | 2016-01-01 | 2016-03-04 | Funding organisation name- GDAA(Govinda Development Aid Association ) | Godawari | 10
3342 | Lalitpur | Godawari N.P. | 9 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-05 | 2016-03-09 |  | Godawari | 4
3343 | Lalitpur | Karyabinayak N.P. | 14 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 5 | 5 | 2016-03-05 |  | Funding organisation name- GDAA(Govinda Development Aid Association ) | Godawari | 9
3344 | Lalitpur | Karyabinayak N.P. | 15 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 2 | 2 | 2016-03-05 |  | Funding organisation name- GDAA(Govinda Development Aid Association ) | Godawari | 9
3345 | Lalitpur | Karyabinayak N.P. | 14 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-01-01 | 2016-03-04 | Funding organisation name- GDAA(Govinda Development Aid Association ) | Godawari | 9
3346 | Lalitpur | Karyabinayak N.P. | 15 | SHANGRILA ORP | SHANGRILA ORP | GDAA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 24 | 24 | 2016-01-01 | 2016-03-04 | Funding organisation name- GDAA(Govinda Development Aid Association ) | Godawari | 9
3347 | Lalitpur | Lalitpur U.M.N.P. | All | UNDP | UNDP | UNDP | Others | Others | (Please specify in Activity Detail) | To develop and test a concrete building blocks out of the debris materials that could be used as major construction materials to make reconstruction affordable and faster. | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Lalitpur | 29
3348 | Lalitpur | Godawari N.P. | 4 | NRCS | NRCS | BRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees | Yes | Planned | 20 | 0 | 2016-01-01 | 2018-12-31 |  | Godawari | 2
3349 | Lalitpur | Godawari N.P. | 1 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 16 | 17 | 2016-01-01 | 2018-12-31 |  | Godawari | 1
3350 | Lalitpur | Godawari N.P. | 2 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 16 | 16 | 2016-01-01 | 2018-12-31 |  | Godawari | 1
3351 | Lalitpur | Godawari N.P. | 3 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 17 | 17 | 2016-01-01 | 2018-12-31 |  | Godawari | 2
3352 | Lalitpur | Godawari N.P. | 4 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 17 | 18 | 2016-01-01 | 2018-12-31 |  | Godawari | 2
3353 | Lalitpur | Karyabinayak N.P. | 10 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 13 | 15 | 2016-01-01 | 2018-12-31 |  | Lalitpur | 22
3354 | Lalitpur | Karyabinayak N.P. | 11 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 13 | 14 | 2016-01-01 | 2018-12-31 |  | Lalitpur | 22
3355 | Lalitpur | Karyabinayak N.P. | 12 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 12 | 14 | 2016-01-01 | 2018-12-31 |  | Lalitpur | 22
3356 | Lalitpur | Karyabinayak N.P. | 13 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 12 | 13 | 2016-01-01 | 2018-12-31 |  | Lalitpur | 22
3357 | Lalitpur | Lalitpur U.M.N.P. | 9 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 14 | 12 | 2016-01-01 | 2018-12-31 |  | Lalitpur | 9
3358 | Lalitpur | Lalitpur U.M.N.P. | 11 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 14 | 12 | 2016-01-01 | 2018-12-31 |  | Lalitpur | 12
3359 | Lalitpur | Lalitpur U.M.N.P. | 28 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 15 | 13 | 2016-01-01 | 2018-12-31 |  | Lalitpur | 28
3360 | Lalitpur | Lalitpur U.M.N.P. | 29 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 35 | 31 | 2016-01-01 | 2018-12-31 |  | Lalitpur | 29
3361 | Lalitpur | Mahalaxmi N.P. | 1 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 11 | 10 | 2016-01-01 | 2018-12-31 |  | Mahalaxmi | 10
3362 | Lalitpur | Mahalaxmi N.P. | 2 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 12 | 11 | 2016-01-01 | 2018-12-31 |  | Mahalaxmi | 9
3363 | Lalitpur | Mahalaxmi N.P. | 6 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 15 | 14 | 2016-01-01 | 2018-12-31 |  | Mahalaxmi | 8
3364 | Lalitpur | Mahalaxmi N.P. | 7 | NRCS | NRCS | BRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 14 | 14 | 2016-01-01 | 2018-12-31 |  | Mahalaxmi | 8
3365 | Lalitpur | Godawari N.P. | 6 | BATAS | BATAS Foundation | Oman Charitable organization, ACPL | Reconstruction through contractors | Construction | Private house | Construction of shelter with two rooms for the selected earthquake affected afimilies of Godawari-6, using Hollow block masonry | # of constructions | Yes | Completed | 100 | 100 | 2017-06-01 | 2018-01-15 |  | Godawari | 3
3366 | Lalitpur | Bukhel | 1 | GoN | GON - DUDBC | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-06-19 | 2017-06-25 |  | Mahankal | 1
3367 | Lalitpur | Chandanpur | 5 | GoN | GON - DUDBC | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-06-19 | 2017-06-25 |  | Mahankal | 5
3368 | Lalitpur | Gotikhel | 3 | GoN | GON - DUDBC | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2017-06-19 | 2017-06-25 |  | Mahankal | 3
3369 | Lalitpur | Kaleswor | 4 | GoN | GON - DUDBC | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-06-19 | 2017-06-25 |  | #N/A | #N/A
3370 | Lalitpur | Manikhel | 2 | GoN | GON - DUDBC | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-06-19 | 2017-06-25 |  | Mahankal | 2
3371 | Lalitpur | Thuladurlung | 6 | GoN | GON - DUDBC | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2017-06-19 | 2017-06-25 |  | Mahankal | 6
3372 | Dolakha | Alampu | 1 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27 |  | Bigu | 6
3373 | Dolakha | Alampu | 1 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 58 | 45 | 2016-05-01 | 2016-05-26 |  | Bigu | 6
3374 | Dolakha | Alampu | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 388 | 95 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3375 | Dolakha | Alampu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3376 | Dolakha | Alampu | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 48 | 7 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3377 | Dolakha | Alampu | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 48 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3378 | Dolakha | Alampu | 1 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-05-20 | 2016-05-25 |  | Bigu | 6
3379 | Dolakha | Alampu | 1 | IOM | CWIN-TUKI | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 58 | 45 | 2016-05-01 | 2016-05-26 |  | Bigu | 6
3380 | Dolakha | Alampu | 1 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27 |  | Bigu | 6
3381 | Dolakha | Alampu | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 8 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3382 | Dolakha | Alampu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3383 | Dolakha | Alampu | 2 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 6
3384 | Dolakha | Alampu | 2 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 118 | 109 | 2016-05-01 | 2016-05-26 |  | Bigu | 6
3385 | Dolakha | Alampu | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 388 | 130 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3386 | Dolakha | Alampu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3387 | Dolakha | Alampu | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 99 | 4 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3388 | Dolakha | Alampu | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 99 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3389 | Dolakha | Alampu | 2 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-05-20 | 2016-05-25 |  | Bigu | 6
3390 | Dolakha | Alampu | 2 | IOM | CWIN-TUKI | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 118 | 109 | 2016-05-01 | 2016-05-26 |  | Bigu | 6
3391 | Dolakha | Alampu | 2 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 6
3392 | Dolakha | Alampu | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 10 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3393 | Dolakha | Alampu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3394 | Dolakha | Alampu | 3 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 6
3395 | Dolakha | Alampu | 3 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 122 | 82 | 2016-05-01 | 2016-05-26 |  | Bigu | 6
3396 | Dolakha | Alampu | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 388 | 122 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3397 | Dolakha | Alampu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3398 | Dolakha | Alampu | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 55 | 4 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3399 | Dolakha | Alampu | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 55 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3400 | Dolakha | Alampu | 3 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-05-20 | 2016-05-25 |  | Bigu | 6
3401 | Dolakha | Alampu | 3 | IOM | CWIN-TUKI | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 122 | 82 | 2016-05-01 | 2016-05-26 |  | Bigu | 6
3402 | Dolakha | Alampu | 3 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 6
3403 | Dolakha | Alampu | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 12 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3404 | Dolakha | Alampu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3405 | Dolakha | Alampu | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 31 | 31 | 2017-07-02 | 2017-07-08 |  | Bigu | 6
3406 | Dolakha | Alampu | 4 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 6
3407 | Dolakha | Alampu | 4 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 43 | 48 | 2016-05-01 | 2016-05-26 |  | Bigu | 6
3408 | Dolakha | Alampu | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 388 | 126 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3409 | Dolakha | Alampu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3410 | Dolakha | Alampu | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 36 | 2 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3411 | Dolakha | Alampu | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 36 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3412 | Dolakha | Alampu | 4 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-05-20 | 2016-05-25 |  | Bigu | 6
3413 | Dolakha | Alampu | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 43 | 48 | 2016-05-01 | 2016-05-26 |  | Bigu | 6
3414 | Dolakha | Alampu | 4 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 6
3415 | Dolakha | Alampu | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 11 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3416 | Dolakha | Alampu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3417 | Dolakha | Alampu | 5 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 6
3418 | Dolakha | Alampu | 5 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 84 | 95 | 2016-05-01 | 2016-05-26 |  | Bigu | 6
3419 | Dolakha | Alampu | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 388 | 326 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3420 | Dolakha | Alampu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3421 | Dolakha | Alampu | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 69 | 11 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3422 | Dolakha | Alampu | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 69 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3423 | Dolakha | Alampu | 5 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 71 | 2016-05-20 | 2016-05-25 |  | Bigu | 6
3424 | Dolakha | Alampu | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 84 | 95 | 2016-05-01 | 2016-05-26 |  | Bigu | 6
3425 | Dolakha | Alampu | 5 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 6
3426 | Dolakha | Alampu | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 12 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3427 | Dolakha | Alampu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3428 | Dolakha | Alampu | 6 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 6
3429 | Dolakha | Alampu | 6 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 50 | 49 | 2016-05-01 | 2016-05-26 |  | Bigu | 6
3430 | Dolakha | Alampu | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 388 | 106 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3431 | Dolakha | Alampu | 6 | CA | HURADEC |  | Technical Assistance | Demonstration Construction | House | Construction of Demo house | # of constructions | Yes | Completed | 1 | 1 | 2017-02-15 | 2017-03-25 |  | Bigu | 6
3432 | Dolakha | Alampu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3433 | Dolakha | Alampu | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 42 | 12 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3434 | Dolakha | Alampu | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 42 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3435 | Dolakha | Alampu | 6 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-05-20 | 2016-05-25 |  | Bigu | 6
3436 | Dolakha | Alampu | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 50 | 49 | 2016-05-01 | 2016-05-26 |  | Bigu | 6
3437 | Dolakha | Alampu | 6 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 6
3438 | Dolakha | Alampu | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 17 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3439 | Dolakha | Alampu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3440 | Dolakha | Alampu | 7 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 6
3441 | Dolakha | Alampu | 7 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 45 | 46 | 2016-05-01 | 2016-05-26 |  | Bigu | 6
3442 | Dolakha | Alampu | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 388 | 74 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3443 | Dolakha | Alampu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3444 | Dolakha | Alampu | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 38 | 2 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3445 | Dolakha | Alampu | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 38 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3446 | Dolakha | Alampu | 7 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-05-20 | 2016-05-25 |  | Bigu | 6
3447 | Dolakha | Alampu | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 45 | 46 | 2016-05-01 | 2016-05-26 |  | Bigu | 6
3448 | Dolakha | Alampu | 7 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 6
3449 | Dolakha | Alampu | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 8 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3450 | Dolakha | Alampu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3451 | Dolakha | Alampu | 8 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 6
3452 | Dolakha | Alampu | 8 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 96 | 78 | 2016-05-01 | 2016-05-26 |  | Bigu | 6
3453 | Dolakha | Alampu | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 388 | 240 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3454 | Dolakha | Alampu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3455 | Dolakha | Alampu | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 81 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3456 | Dolakha | Alampu | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 81 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3457 | Dolakha | Alampu | 8 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-05-20 | 2016-05-25 |  | Bigu | 6
3458 | Dolakha | Alampu | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 96 | 78 | 2016-05-01 | 2016-05-26 |  | Bigu | 6
3459 | Dolakha | Alampu | 8 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 6
3460 | Dolakha | Alampu | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 12 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3461 | Dolakha | Alampu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3462 | Dolakha | Alampu | 9 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 6
3463 | Dolakha | Alampu | 9 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 66 | 65 | 2016-05-01 | 2016-05-26 |  | Bigu | 6
3464 | Dolakha | Alampu | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 388 | 126 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3465 | Dolakha | Alampu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3466 | Dolakha | Alampu | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 56 | 4 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3467 | Dolakha | Alampu | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 56 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3468 | Dolakha | Alampu | 9 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 68 | 68 | 2016-05-20 | 2016-05-25 |  | Bigu | 6
3469 | Dolakha | Alampu | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 66 | 65 | 2016-05-01 | 2016-05-26 |  | Bigu | 6
3470 | Dolakha | Alampu | 9 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 6
3471 | Dolakha | Alampu | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 10 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3472 | Dolakha | Alampu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 6
3473 | Dolakha | Alampu | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 58 |  |  |  | Bigu | 6
3474 | Dolakha | Babare | 1 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 2
3475 | Dolakha | Babare | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 311 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3476 | Dolakha | Babare | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3477 | Dolakha | Babare | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 118 | 19 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3478 | Dolakha | Babare | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 118 | 67 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3479 | Dolakha | Babare | 1 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 2
3480 | Dolakha | Babare | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 13 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3481 | Dolakha | Babare | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3482 | Dolakha | Babare | 2 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 2
3483 | Dolakha | Babare | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 264 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3484 | Dolakha | Babare | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3485 | Dolakha | Babare | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 163 | 30 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3486 | Dolakha | Babare | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 163 | 65 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3487 | Dolakha | Babare | 2 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 2
3488 | Dolakha | Babare | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 20 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3489 | Dolakha | Babare | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3490 | Dolakha | Babare | 3 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 2
3491 | Dolakha | Babare | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 218 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3492 | Dolakha | Babare | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3493 | Dolakha | Babare | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 114 | 20 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3494 | Dolakha | Babare | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 114 | 65 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3495 | Dolakha | Babare | 3 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 2
3496 | Dolakha | Babare | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 12 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3497 | Dolakha | Babare | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3498 | Dolakha | Babare | 4 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 2
3499 | Dolakha | Babare | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 293 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3500 | Dolakha | Babare | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3501 | Dolakha | Babare | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 161 | 20 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3502 | Dolakha | Babare | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 161 | 65 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3503 | Dolakha | Babare | 4 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 2
3504 | Dolakha | Babare | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 23 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3505 | Dolakha | Babare | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3506 | Dolakha | Babare | 5 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 2
3507 | Dolakha | Babare | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 72 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3508 | Dolakha | Babare | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3509 | Dolakha | Babare | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 86 | 14 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3510 | Dolakha | Babare | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 86 | 65 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3511 | Dolakha | Babare | 5 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 2
3512 | Dolakha | Babare | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 2 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3513 | Dolakha | Babare | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3514 | Dolakha | Babare | 6 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 2
3515 | Dolakha | Babare | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 86 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3516 | Dolakha | Babare | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3517 | Dolakha | Babare | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 95 | 7 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3518 | Dolakha | Babare | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 95 | 65 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3519 | Dolakha | Babare | 6 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 2
3520 | Dolakha | Babare | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 7 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3521 | Dolakha | Babare | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3522 | Dolakha | Babare | 7 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 2
3523 | Dolakha | Babare | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 113 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3524 | Dolakha | Babare | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3525 | Dolakha | Babare | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 100 | 4 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3526 | Dolakha | Babare | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 100 | 65 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3527 | Dolakha | Babare | 7 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 2
3528 | Dolakha | Babare | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 7 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3529 | Dolakha | Babare | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3530 | Dolakha | Babare | 8 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 2
3531 | Dolakha | Babare | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 86 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3532 | Dolakha | Babare | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3533 | Dolakha | Babare | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 73 | 1 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3534 | Dolakha | Babare | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 73 | 65 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3535 | Dolakha | Babare | 8 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 2
3536 | Dolakha | Babare | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 4 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3537 | Dolakha | Babare | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3538 | Dolakha | Babare | 9 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 8 | 8 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 2
3539 | Dolakha | Babare | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 134 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3540 | Dolakha | Babare | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3541 | Dolakha | Babare | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 135 | 10 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3542 | Dolakha | Babare | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 135 | 65 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3543 | Dolakha | Babare | 9 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 8 | 8 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 2
3544 | Dolakha | Babare | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 9 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3545 | Dolakha | Babare | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 2
3546 | Dolakha | Bhedapu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 4
3547 | Dolakha | Bhedapu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 4
3548 | Dolakha | Bhedapu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 4
3549 | Dolakha | Bhedapu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 4
3550 | Dolakha | Bhedapu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 4
3551 | Dolakha | Bhedapu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 4
3552 | Dolakha | Bhedapu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 4
3553 | Dolakha | Bhedapu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 4
3554 | Dolakha | Bhedapu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 4
3555 | Dolakha | Bhedapu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 4
3556 | Dolakha | Bhedapu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 4
3557 | Dolakha | Bhedapu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 4
3558 | Dolakha | Bhedapu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 4
3559 | Dolakha | Bhedapu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 4
3560 | Dolakha | Bhedapu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 4
3561 | Dolakha | Bhedapu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 4
3562 | Dolakha | Bhedapu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 4
3563 | Dolakha | Bhedapu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 4
3564 | Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 94 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 3
3565 | Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 3
3566 | Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 3
3567 | Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 544 | 63 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 3
3568 | Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 544 | 359 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 3
3569 | Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 25 | 67 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 3
3570 | Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 3
3571 | Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 3
3572 | Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 28 | 28 | 2017-07-11 | 2017-07-17 |  | Bhimeshwor | 3
3573 | Dolakha | Bhimeswor N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 200 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3574 | Dolakha | Bhimeswor N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3575 | Dolakha | Bhimeswor N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3576 | Dolakha | Bhimeswor N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 384 | 45 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3577 | Dolakha | Bhimeswor N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 384 | 359 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3578 | Dolakha | Bhimeswor N.P. | 2 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 200 | 87 | 2015-12-19 | 2016-09-30 |  | Bhimeshwor | 2
3579 | Dolakha | Bhimeswor N.P. | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 25 | 21 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3580 | Dolakha | Bhimeswor N.P. | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 25 | 25 | 2017-04-19 | 2017-04-25 |  | Bhimeshwor | 2
3581 | Dolakha | Bhimeswor N.P. | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3582 | Dolakha | Bhimeswor N.P. | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3583 | Dolakha | Bhimeswor N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 173 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3584 | Dolakha | Bhimeswor N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3585 | Dolakha | Bhimeswor N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3586 | Dolakha | Bhimeswor N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 250 | 31 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3587 | Dolakha | Bhimeswor N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 250 | 359 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3588 | Dolakha | Bhimeswor N.P. | 3 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 200 | 20 | 2015-12-19 | 2016-09-30 |  | Bhimeshwor | 2
3589 | Dolakha | Bhimeswor N.P. | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 25 | 8 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3590 | Dolakha | Bhimeswor N.P. | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3591 | Dolakha | Bhimeswor N.P. | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3592 | Dolakha | Bhimeswor N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 261 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3593 | Dolakha | Bhimeswor N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3594 | Dolakha | Bhimeswor N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3595 | Dolakha | Bhimeswor N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 389 | 27 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3596 | Dolakha | Bhimeswor N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 389 | 359 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3597 | Dolakha | Bhimeswor N.P. | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 25 | 44 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3598 | Dolakha | Bhimeswor N.P. | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3599 | Dolakha | Bhimeswor N.P. | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 2
3600 | Dolakha | Bhimeswor N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 46 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 4
3601 | Dolakha | Bhimeswor N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 4
3602 | Dolakha | Bhimeswor N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 4
3603 | Dolakha | Bhimeswor N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 190 | 11 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 4
3604 | Dolakha | Bhimeswor N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 190 | 359 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 4
3605 | Dolakha | Bhimeswor N.P. | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 25 | 7 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 4
3606 | Dolakha | Bhimeswor N.P. | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 4
3607 | Dolakha | Bhimeswor N.P. | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 4
3608 | Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 86 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3609 | Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3610 | Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3611 | Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 560 | 30 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3612 | Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 560 | 359 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3613 | Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 25 | 29 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3614 | Dolakha | Bhimeswor N.P. | 6 | IOM | REDR-I |  | Training | ToT | Social mobilizer (curriculum, specify in comment) |  | # of trainees | Yes | Completed | 18 | 18 | 2015-12-16 | 2015-12-21 |  | Bhimeshwor | 5
3615 | Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3616 | Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3617 | Dolakha | Bhimeswor N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 83 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 4
3618 | Dolakha | Bhimeswor N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 4
3619 | Dolakha | Bhimeswor N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 4
3620 | Dolakha | Bhimeswor N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 327 | 11 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 4
3621 | Dolakha | Bhimeswor N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 327 | 359 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 4
3622 | Dolakha | Bhimeswor N.P. | 7 | UNHABITAT |  |  | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 50 |  |  |  | Bhimeshwor | 4
3623 | Dolakha | Bhimeswor N.P. | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 25 | 4 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 4
3624 | Dolakha | Bhimeswor N.P. | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 4
3625 | Dolakha | Bhimeswor N.P. | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 4
3626 | Dolakha | Bhimeswor N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 159 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3627 | Dolakha | Bhimeswor N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3628 | Dolakha | Bhimeswor N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3629 | Dolakha | Bhimeswor N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 402 | 25 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3630 | Dolakha | Bhimeswor N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 402 | 359 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3631 | Dolakha | Bhimeswor N.P. | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 25 | 11 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3632 | Dolakha | Bhimeswor N.P. | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3633 | Dolakha | Bhimeswor N.P. | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3634 | Dolakha | Bhimeswor N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 64 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3635 | Dolakha | Bhimeswor N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3636 | Dolakha | Bhimeswor N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3637 | Dolakha | Bhimeswor N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 348 | 17 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3638 | Dolakha | Bhimeswor N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 348 | 359 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3639 | Dolakha | Bhimeswor N.P. | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 25 | 38 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3640 | Dolakha | Bhimeswor N.P. | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3641 | Dolakha | Bhimeswor N.P. | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 5
3642 | Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 148 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 6
3643 | Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 6
3644 | Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 476 | 52 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 6
3645 | Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 476 | 359 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 6
3646 | Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | Other trainings | Other trainings (specify in Activity Detail) | Social mobilizer (curriculum, specify in comment) | # of trainees | Yes | Ongoing | 32 | 95 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 6
3647 | Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | Other trainings | Other trainings (specify in Activity Detail) | Social mobilizer (curriculum, specify in comment) | # of trainees | Yes | Ongoing | 45 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 6
3648 | Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | Other trainings | Other trainings (specify in Activity Detail) | Training for Instructor | # of trainees | Yes | Ongoing | 45 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 6
3649 | Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | Retrofitting training | Engineers, sub-engineers |  | # of trainees | Yes | Ongoing | 32 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 6
3650 | Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 25 | 43 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 6
3651 | Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Ongoing | 544 | 354 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 6
3652 | Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 6
3653 | Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 24 | 24 | 2017-06-02 | 2017-06-08 |  | Bhimeshwor | 6
3654 | Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 29 | 29 | 2017-06-28 | 2017-07-02 |  | Bhimeshwor | 6
3655 | Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 26 | 26 | 2017-07-11 | 2017-07-17 |  | Bhimeshwor | 6
3656 | Dolakha | Bhimeswor N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 130 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 7
3657 | Dolakha | Bhimeswor N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 7
3658 | Dolakha | Bhimeswor N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 518 | 41 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 7
3659 | Dolakha | Bhimeswor N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 518 | 359 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 7
3660 | Dolakha | Bhimeswor N.P. | 11 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 25 | 13 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 7
3661 | Dolakha | Bhimeswor N.P. | 11 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 7
3662 | Dolakha | Bhimeswor N.P. | 12 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 174 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 7
3663 | Dolakha | Bhimeswor N.P. | 12 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 7
3664 | Dolakha | Bhimeswor N.P. | 12 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 345 | 16 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 7
3665 | Dolakha | Bhimeswor N.P. | 12 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 345 | 359 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 7
3666 | Dolakha | Bhimeswor N.P. | 12 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 25 | 41 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 7
3667 | Dolakha | Bhimeswor N.P. | 12 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 7
3668 | Dolakha | Bhimeswor N.P. | 13 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 608 | 20 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 7
3669 | Dolakha | Bhimeswor N.P. | 13 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 7
3670 | Dolakha | Bhimeswor N.P. | 13 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 414 | 14 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 7
3671 | Dolakha | Bhimeswor N.P. | 13 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 414 | 359 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 7
3672 | Dolakha | Bhimeswor N.P. | 13 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 25 | 16 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 7
3673 | Dolakha | Bhimeswor N.P. | 13 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 7
3674 | Dolakha | Bhimeswor N.P. | All | CA | SAMATA | CA | Technical Assistance | Communication and Outreach | PSA Radio broadcasting | Reconstruction situation updates grogram | # of episodes | Yes | Ongoing | 12 | 5 | 2017-06-10 |  |  | Bhimeshwor | 7
3675 | Dolakha | Bhimeswor N.P. | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 570 |  |  |  | Bhimeshwor | 7
3676 | Dolakha | Bhirkot | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 45 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3677 | Dolakha | Bhirkot | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3678 | Dolakha | Bhirkot | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 74 | 14 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3679 | Dolakha | Bhirkot | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 74 | 44 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3680 | Dolakha | Bhirkot | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 9 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3681 | Dolakha | Bhirkot | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3682 | Dolakha | Bhirkot | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 32 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3683 | Dolakha | Bhirkot | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3684 | Dolakha | Bhirkot | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 74 | 16 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3685 | Dolakha | Bhirkot | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 74 | 44 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3686 | Dolakha | Bhirkot | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 4 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3687 | Dolakha | Bhirkot | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3688 | Dolakha | Bhirkot | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 43 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3689 | Dolakha | Bhirkot | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3690 | Dolakha | Bhirkot | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 74 | 20 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3691 | Dolakha | Bhirkot | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 74 | 44 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3692 | Dolakha | Bhirkot | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 7 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3693 | Dolakha | Bhirkot | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3694 | Dolakha | Bhirkot | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 73 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3695 | Dolakha | Bhirkot | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3696 | Dolakha | Bhirkot | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 86 | 11 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3697 | Dolakha | Bhirkot | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 86 | 44 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3698 | Dolakha | Bhirkot | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 16 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3699 | Dolakha | Bhirkot | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3700 | Dolakha | Bhirkot | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 54 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3701 | Dolakha | Bhirkot | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3702 | Dolakha | Bhirkot | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 89 | 11 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3703 | Dolakha | Bhirkot | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 89 | 44 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3704 | Dolakha | Bhirkot | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 17 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3705 | Dolakha | Bhirkot | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3706 | Dolakha | Bhirkot | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 71 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3707 | Dolakha | Bhirkot | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3708 | Dolakha | Bhirkot | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 106 | 20 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3709 | Dolakha | Bhirkot | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 106 | 44 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3710 | Dolakha | Bhirkot | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 11 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3711 | Dolakha | Bhirkot | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3712 | Dolakha | Bhirkot | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 32 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3713 | Dolakha | Bhirkot | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3714 | Dolakha | Bhirkot | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 66 | 23 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3715 | Dolakha | Bhirkot | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 66 | 44 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3716 | Dolakha | Bhirkot | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 15 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3717 | Dolakha | Bhirkot | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3718 | Dolakha | Bhirkot | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 13 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3719 | Dolakha | Bhirkot | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3720 | Dolakha | Bhirkot | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 66 | 10 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3721 | Dolakha | Bhirkot | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 66 | 44 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3722 | Dolakha | Bhirkot | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3723 | Dolakha | Bhirkot | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3724 | Dolakha | Bhirkot | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 30 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3725 | Dolakha | Bhirkot | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3726 | Dolakha | Bhirkot | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 122 | 13 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3727 | Dolakha | Bhirkot | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 122 | 44 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3728 | Dolakha | Bhirkot | 9 | CW | RRN | DEC-II | Training | Short training | Masons (other curriculums, specify in Activity Detail) | Self (Prepared and endorsed from DUDBC) | # of trainees | Yes | Planned | 20 | 0 | 2017-01-01 |  |  | Tamakoshi | 1
3729 | Dolakha | Bhirkot | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3730 | Dolakha | Bhirkot | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 1
3731 | Dolakha | Bhirkot | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 42 |  |  |  | Tamakoshi | 1
3732 | Dolakha | Bhusaphedi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 2
3733 | Dolakha | Bhusaphedi | 1 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2016-09-27 | 2016-10-03 |  | Sailung | 2
3734 | Dolakha | Bhusaphedi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 2
3735 | Dolakha | Bhusaphedi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 2
3736 | Dolakha | Bhusaphedi | 2 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-09-27 | 2016-10-03 |  | Sailung | 2
3737 | Dolakha | Bhusaphedi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 2
3738 | Dolakha | Bhusaphedi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 2
3739 | Dolakha | Bhusaphedi | 3 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-09-27 | 2016-10-03 |  | Sailung | 2
3740 | Dolakha | Bhusaphedi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 2
3741 | Dolakha | Bhusaphedi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 2
3742 | Dolakha | Bhusaphedi | 4 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-09-27 | 2016-10-03 |  | Sailung | 2
3743 | Dolakha | Bhusaphedi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 2
3744 | Dolakha | Bhusaphedi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 2
3745 | Dolakha | Bhusaphedi | 5 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-09-27 | 2016-10-03 |  | Sailung | 2
3746 | Dolakha | Bhusaphedi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 2
3747 | Dolakha | Bhusaphedi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 2
3748 | Dolakha | Bhusaphedi | 6 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-09-27 | 2016-10-03 |  | Sailung | 2
3749 | Dolakha | Bhusaphedi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 2
3750 | Dolakha | Bhusaphedi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 2
3751 | Dolakha | Bhusaphedi | 7 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 11 | 11 | 2016-09-27 | 2016-10-03 |  | Sailung | 2
3752 | Dolakha | Bhusaphedi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 2
3753 | Dolakha | Bhusaphedi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 2
3754 | Dolakha | Bhusaphedi | 8 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-09-27 | 2016-10-03 |  | Sailung | 2
3755 | Dolakha | Bhusaphedi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 2
3756 | Dolakha | Bhusaphedi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 2
3757 | Dolakha | Bhusaphedi | 9 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-09-19 | 2016-09-25 |  | Sailung | 2
3758 | Dolakha | Bhusaphedi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 2
3759 | Dolakha | Bigu | 1 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 93 | 2016-04-11 | 2016-04-27 |  | Bigu | 7
3760 | Dolakha | Bigu | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 131 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3761 | Dolakha | Bigu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3762 | Dolakha | Bigu | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 132 | 16 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3763 | Dolakha | Bigu | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 132 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3764 | Dolakha | Bigu | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 93 | 2016-04-08 | 2016-04-29 |  | Bigu | 7
3765 | Dolakha | Bigu | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 7 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3766 | Dolakha | Bigu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3767 | Dolakha | Bigu | 2 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 45 | 2016-04-11 | 2016-04-27 |  | Bigu | 7
3768 | Dolakha | Bigu | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 127 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3769 | Dolakha | Bigu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3770 | Dolakha | Bigu | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 55 | 3 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3771 | Dolakha | Bigu | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 55 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3772 | Dolakha | Bigu | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 45 | 2016-04-08 | 2016-04-29 |  | Bigu | 7
3773 | Dolakha | Bigu | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 11 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3774 | Dolakha | Bigu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3775 | Dolakha | Bigu | 3 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 53 | 2016-04-11 | 2016-04-27 |  | Bigu | 7
3776 | Dolakha | Bigu | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 74 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3777 | Dolakha | Bigu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3778 | Dolakha | Bigu | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 82 | 10 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3779 | Dolakha | Bigu | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 82 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3780 | Dolakha | Bigu | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 53 | 2016-04-08 | 2016-04-29 |  | Bigu | 7
3781 | Dolakha | Bigu | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3782 | Dolakha | Bigu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3783 | Dolakha | Bigu | 4 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 48 | 2016-04-11 | 2016-04-27 |  | Bigu | 7
3784 | Dolakha | Bigu | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 72 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3785 | Dolakha | Bigu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3786 | Dolakha | Bigu | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 68 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3787 | Dolakha | Bigu | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 68 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3788 | Dolakha | Bigu | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 48 | 2016-04-08 | 2016-04-29 |  | Bigu | 7
3789 | Dolakha | Bigu | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 9 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3790 | Dolakha | Bigu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3791 | Dolakha | Bigu | 5 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 39 | 2016-04-11 | 2016-04-27 |  | Bigu | 7
3792 | Dolakha | Bigu | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 116 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3793 | Dolakha | Bigu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3794 | Dolakha | Bigu | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 44 | 3 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3795 | Dolakha | Bigu | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 44 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3796 | Dolakha | Bigu | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 39 | 2016-04-08 | 2016-04-29 |  | Bigu | 7
3797 | Dolakha | Bigu | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 8 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3798 | Dolakha | Bigu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3799 | Dolakha | Bigu | 6 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 40 | 2016-04-11 | 2016-04-27 |  | Bigu | 7
3800 | Dolakha | Bigu | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 134 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3801 | Dolakha | Bigu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3802 | Dolakha | Bigu | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 61 | 14 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3803 | Dolakha | Bigu | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 61 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3804 | Dolakha | Bigu | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 40 | 2016-04-08 | 2016-04-29 |  | Bigu | 7
3805 | Dolakha | Bigu | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3806 | Dolakha | Bigu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3807 | Dolakha | Bigu | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 32 | 32 | 2017-07-10 | 2017-07-16 |  | Bigu | 7
3808 | Dolakha | Bigu | 7 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 52 | 2016-04-11 | 2016-04-27 |  | Bigu | 7
3809 | Dolakha | Bigu | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 71 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3810 | Dolakha | Bigu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3811 | Dolakha | Bigu | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 82 | 11 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3812 | Dolakha | Bigu | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 82 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3813 | Dolakha | Bigu | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 52 | 2016-04-08 | 2016-04-29 |  | Bigu | 7
3814 | Dolakha | Bigu | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 1 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3815 | Dolakha | Bigu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3816 | Dolakha | Bigu | 8 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 62 | 2016-04-11 | 2016-04-27 |  | Bigu | 7
3817 | Dolakha | Bigu | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 124 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3818 | Dolakha | Bigu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3819 | Dolakha | Bigu | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 88 | 12 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3820 | Dolakha | Bigu | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 88 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3821 | Dolakha | Bigu | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 62 | 2016-04-08 | 2016-04-29 |  | Bigu | 7
3822 | Dolakha | Bigu | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3823 | Dolakha | Bigu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3824 | Dolakha | Bigu | 9 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 39 | 2016-04-11 | 2016-04-27 |  | Bigu | 7
3825 | Dolakha | Bigu | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 35 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3826 | Dolakha | Bigu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3827 | Dolakha | Bigu | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 52 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3828 | Dolakha | Bigu | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 52 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3829 | Dolakha | Bigu | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 39 | 2016-04-08 | 2016-04-29 |  | Bigu | 7
3830 | Dolakha | Bigu | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 10 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3831 | Dolakha | Bigu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 7
3832 | Dolakha | Bocha | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 8
3833 | Dolakha | Bocha | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 8
3834 | Dolakha | Bocha | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 8
3835 | Dolakha | Bocha | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 8
3836 | Dolakha | Bocha | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 8
3837 | Dolakha | Bocha | 3 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bhimeshwor | 8
3838 | Dolakha | Bocha | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 8
3839 | Dolakha | Bocha | 3 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0 |  |  |  | Bhimeshwor | 8
3840 | Dolakha | Bocha | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 8
3841 | Dolakha | Bocha | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 8
3842 | Dolakha | Bocha | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 8
3843 | Dolakha | Bocha | 5 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bhimeshwor | 8
3844 | Dolakha | Bocha | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 8
3845 | Dolakha | Bocha | 5 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0 |  |  |  | Bhimeshwor | 8
3846 | Dolakha | Bocha | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 8
3847 | Dolakha | Bocha | 6 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bhimeshwor | 8
3848 | Dolakha | Bocha | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 8
3849 | Dolakha | Bocha | 6 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0 |  |  |  | Bhimeshwor | 8
3850 | Dolakha | Bocha | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 8
3851 | Dolakha | Bocha | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 8
3852 | Dolakha | Bocha | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 8
3853 | Dolakha | Bocha | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 8
3854 | Dolakha | Bocha | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 8
3855 | Dolakha | Bocha | 9 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bhimeshwor | 8
3856 | Dolakha | Bocha | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 8
3857 | Dolakha | Bocha | 9 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 12 | 0 |  |  |  | Bhimeshwor | 8
3858 | Dolakha | Bocha | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 72 |  |  |  | Bhimeshwor | 8
3859 | Dolakha | Bulung | 1 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 80 | 80 | 2016-08-29 | 2017-08-21 |  | Bigu | 3
3860 | Dolakha | Bulung | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 3
3861 | Dolakha | Bulung | 1 | CARITAS-N | CARITAS-N | CARITAS-N | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2017-12-13 | 2017-12-19 |  | Bigu | 3
3862 | Dolakha | Bulung | 1 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 3
3863 | Dolakha | Bulung | 1 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15 |  | Bigu | 3
3864 | Dolakha | Bulung | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 3
3865 | Dolakha | Bulung | 2 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 74 | 74 | 2016-08-29 | 2017-08-21 |  | Bigu | 3
3866 | Dolakha | Bulung | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 3
3867 | Dolakha | Bulung | 2 | CARITAS-N | CARITAS-N | CARITAS-N | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2017-12-13 | 2017-12-19 |  | Bigu | 3
3868 | Dolakha | Bulung | 2 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 3
3869 | Dolakha | Bulung | 2 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15 |  | Bigu | 3
3870 | Dolakha | Bulung | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 3
3871 | Dolakha | Bulung | 3 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 84 | 84 | 2016-08-29 | 2017-08-21 |  | Bigu | 3
3872 | Dolakha | Bulung | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 3
3873 | Dolakha | Bulung | 3 | CARITAS-N | CARITAS-N | CARITAS-N | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2017-12-13 | 2017-12-19 |  | Bigu | 3
3874 | Dolakha | Bulung | 3 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15 |  | Bigu | 3
3875 | Dolakha | Bulung | 3 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15 |  | Bigu | 3
3876 | Dolakha | Bulung | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 3
3877 | Dolakha | Bulung | 4 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 85 | 85 | 2016-08-29 | 2017-08-21 |  | Bigu | 3
3878 | Dolakha | Bulung | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 3
3879 | Dolakha | Bulung | 4 | CARITAS-N | CARITAS-N | CARITAS-N | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2017-12-13 | 2017-12-19 |  | Bigu | 3
3880 | Dolakha | Bulung | 4 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 3
3881 | Dolakha | Bulung | 4 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15 |  | Bigu | 3
3882 | Dolakha | Bulung | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 3
3883 | Dolakha | Bulung | 5 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 90 | 90 | 2016-08-29 | 2017-08-21 |  | Bigu | 3
3884 | Dolakha | Bulung | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 3
3885 | Dolakha | Bulung | 5 | CARITAS-N | CARITAS-N | CARITAS-N | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2017-12-13 | 2017-12-19 |  | Bigu | 3
3886 | Dolakha | Bulung | 5 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15 |  | Bigu | 3
3887 | Dolakha | Bulung | 5 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15 |  | Bigu | 3
3888 | Dolakha | Bulung | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 3
3889 | Dolakha | Bulung | 6 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 68 | 68 | 2016-08-29 | 2017-08-21 |  | Bigu | 3
3890 | Dolakha | Bulung | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 3
3891 | Dolakha | Bulung | 6 | CARITAS-N | CARITAS-N | CARITAS-N | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2017-12-13 | 2017-12-19 |  | Bigu | 3
3892 | Dolakha | Bulung | 6 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 3
3893 | Dolakha | Bulung | 6 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15 |  | Bigu | 3
3894 | Dolakha | Bulung | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 3
3895 | Dolakha | Bulung | 7 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 98 | 98 | 2016-08-29 | 2017-08-21 |  | Bigu | 3
3896 | Dolakha | Bulung | 7 | CARITAS-N | CARITAS-N | CARITAS-N | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-09-08 |  |  | Bigu | 3
3897 | Dolakha | Bulung | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 3
3898 | Dolakha | Bulung | 7 | CARITAS-N | CARITAS-N | CARITAS-N | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-12-13 | 2017-12-19 |  | Bigu | 3
3899 | Dolakha | Bulung | 7 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 3
3900 | Dolakha | Bulung | 7 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15 |  | Bigu | 3
3901 | Dolakha | Bulung | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 3
3902 | Dolakha | Bulung | 8 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 78 | 78 | 2016-08-29 | 2017-08-21 |  | Bigu | 3
3903 | Dolakha | Bulung | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 3
3904 | Dolakha | Bulung | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 96 | 71 | 2016-06-15 | 2016-06-16 |  | Bigu | 3
3905 | Dolakha | Bulung | 8 | CARITAS-N | CARITAS-N | CARITAS-N | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2017-12-13 | 2017-12-19 |  | Bigu | 3
3906 | Dolakha | Bulung | 8 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 3
3907 | Dolakha | Bulung | 8 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15 |  | Bigu | 3
3908 | Dolakha | Bulung | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 3
3909 | Dolakha | Bulung | 9 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 56 | 56 | 2016-08-29 | 2017-08-21 |  | Bigu | 3
3910 | Dolakha | Bulung | 9 | CARITAS-N | CARITAS-N | CARITAS-N | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-09-08 |  |  | Bigu | 3
3911 | Dolakha | Bulung | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 3
3912 | Dolakha | Bulung | 9 | CARITAS-N | CARITAS-N | CARITAS-N | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-12-13 | 2017-12-19 |  | Bigu | 3
3913 | Dolakha | Bulung | 9 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 3
3914 | Dolakha | Bulung | 9 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 11 | 2015-12-14 | 2016-02-15 |  | Bigu | 3
3915 | Dolakha | Bulung | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 3
3916 | Dolakha | Chankhu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 6
3917 | Dolakha | Chankhu | 1 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 6
3918 | Dolakha | Chankhu | 1 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 4 | 4 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 6
3919 | Dolakha | Chankhu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 6
3920 | Dolakha | Chankhu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 6
3921 | Dolakha | Chankhu | 2 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 4 | 4 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 6
3922 | Dolakha | Chankhu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 6
3923 | Dolakha | Chankhu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 6
3924 | Dolakha | Chankhu | 3 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 4 | 4 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 6
3925 | Dolakha | Chankhu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 6
3926 | Dolakha | Chankhu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 6
3927 | Dolakha | Chankhu | 4 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 6
3928 | Dolakha | Chankhu | 4 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 6
3929 | Dolakha | Chankhu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 6
3930 | Dolakha | Chankhu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 6
3931 | Dolakha | Chankhu | 5 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 6
3932 | Dolakha | Chankhu | 5 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 6
3933 | Dolakha | Chankhu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 6
3934 | Dolakha | Chankhu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 6
3935 | Dolakha | Chankhu | 6 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 6
3936 | Dolakha | Chankhu | 6 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 6
3937 | Dolakha | Chankhu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 6
3938 | Dolakha | Chankhu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 6
3939 | Dolakha | Chankhu | 7 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 6
3940 | Dolakha | Chankhu | 7 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 6
3941 | Dolakha | Chankhu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 6
3942 | Dolakha | Chankhu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 6
3943 | Dolakha | Chankhu | 8 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 6
3944 | Dolakha | Chankhu | 8 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 6
3945 | Dolakha | Chankhu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 6
3946 | Dolakha | Chankhu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 6
3947 | Dolakha | Chankhu | 9 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 6
3948 | Dolakha | Chankhu | 9 | HELVETAS | CS |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 6
3949 | Dolakha | Chankhu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 6
3950 | Dolakha | Chhetrapa | 1 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 9 | 9 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 8
3951 | Dolakha | Chhetrapa | 1 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 9 | 9 | 2017-02-17 | 2017-02-17 |  | Baiteshwor | 8
3952 | Dolakha | Chhetrapa | 1 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Completed | 9 | 9 | 2017-03-21 | 2017-03-21 |  | Baiteshwor | 8
3953 | Dolakha | Chhetrapa | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 8
3954 | Dolakha | Chhetrapa | 1 | GON - PAF | REDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2017-05-11 | 2017-05-17 |  | Baiteshwor | 8
3955 | Dolakha | Chhetrapa | 1 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-04-19 | 2016-05-03 | 19-25 Apr First Session, 27 Apr-3 May Second Session | Baiteshwor | 8
3956 | Dolakha | Chhetrapa | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 8
3957 | Dolakha | Chhetrapa | 2 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 4 | 4 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 8
3958 | Dolakha | Chhetrapa | 2 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 4 | 4 | 2017-02-17 | 2017-02-17 |  | Baiteshwor | 8
3959 | Dolakha | Chhetrapa | 2 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Completed | 4 | 4 | 2017-03-21 | 2017-03-21 |  | Baiteshwor | 8
3960 | Dolakha | Chhetrapa | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 8
3961 | Dolakha | Chhetrapa | 2 | GON - PAF | REDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-05-11 | 2017-05-17 |  | Baiteshwor | 8
3962 | Dolakha | Chhetrapa | 2 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 8
3963 | Dolakha | Chhetrapa | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 8
3964 | Dolakha | Chhetrapa | 3 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 7 | 7 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 8
3965 | Dolakha | Chhetrapa | 3 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 7 | 7 | 2017-02-17 | 2017-02-17 |  | Baiteshwor | 8
3966 | Dolakha | Chhetrapa | 3 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Completed | 7 | 7 | 2017-03-21 | 2017-03-21 |  | Baiteshwor | 8
3967 | Dolakha | Chhetrapa | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 8
3968 | Dolakha | Chhetrapa | 3 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 8
3969 | Dolakha | Chhetrapa | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 8
3970 | Dolakha | Chhetrapa | 4 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 7 | 7 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 8
3971 | Dolakha | Chhetrapa | 4 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 7 | 7 | 2017-02-17 | 2017-02-17 |  | Baiteshwor | 8
3972 | Dolakha | Chhetrapa | 4 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Completed | 7 | 7 | 2017-03-21 | 2017-03-21 |  | Baiteshwor | 8
3973 | Dolakha | Chhetrapa | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 8
3974 | Dolakha | Chhetrapa | 4 | GON - PAF | REDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2017-05-11 | 2017-05-17 |  | Baiteshwor | 8
3975 | Dolakha | Chhetrapa | 4 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 7 | 7 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 8
3976 | Dolakha | Chhetrapa | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 8
3977 | Dolakha | Chhetrapa | 5 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 7 | 7 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 8
3978 | Dolakha | Chhetrapa | 5 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 7 | 7 | 2017-02-17 | 2017-02-17 |  | Baiteshwor | 8
3979 | Dolakha | Chhetrapa | 5 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 7 | 6 | 2017-03-21 | 2017-03-21 |  | Baiteshwor | 8
3980 | Dolakha | Chhetrapa | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 8
3981 | Dolakha | Chhetrapa | 5 | GON - PAF | REDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2017-05-11 | 2017-05-17 |  | Baiteshwor | 8
3982 | Dolakha | Chhetrapa | 5 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 8
3983 | Dolakha | Chhetrapa | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 8
3984 | Dolakha | Chhetrapa | 5 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 1 | 1 | 2016-12-01 |  |  | Baiteshwor | 8
3985 | Dolakha | Chhetrapa | 6 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 9 | 9 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 8
3986 | Dolakha | Chhetrapa | 6 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 9 | 9 | 2017-02-17 | 2017-02-17 |  | Baiteshwor | 8
3987 | Dolakha | Chhetrapa | 6 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 9 | 8 | 2017-03-21 | 2017-03-21 |  | Baiteshwor | 8
3988 | Dolakha | Chhetrapa | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 8
3989 | Dolakha | Chhetrapa | 6 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 8
3990 | Dolakha | Chhetrapa | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 8
3991 | Dolakha | Chhetrapa | 6 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 5 | 4 | 2016-12-01 |  |  | Baiteshwor | 8
3992 | Dolakha | Chhetrapa | 7 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 5 | 5 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 8
3993 | Dolakha | Chhetrapa | 7 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 5 | 5 | 2017-02-17 | 2017-02-17 |  | Baiteshwor | 8
3994 | Dolakha | Chhetrapa | 7 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 5 | 5 | 2017-03-21 | 2017-03-21 |  | Baiteshwor | 8
3995 | Dolakha | Chhetrapa | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 8
3996 | Dolakha | Chhetrapa | 7 | GON - PAF | REDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-05-11 | 2017-05-17 |  | Baiteshwor | 8
3997 | Dolakha | Chhetrapa | 7 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 8
3998 | Dolakha | Chhetrapa | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 8
3999 | Dolakha | Chhetrapa | 8 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 5 | 5 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 8
4000 | Dolakha | Chhetrapa | 8 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 5 | 5 | 2017-02-17 | 2017-02-17 |  | Baiteshwor | 8
4001 | Dolakha | Chhetrapa | 8 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 5 | 5 | 2017-03-21 | 2017-03-21 |  | Baiteshwor | 8
4002 | Dolakha | Chhetrapa | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 8
4003 | Dolakha | Chhetrapa | 8 | GON - PAF | REDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2017-05-11 | 2017-05-17 |  | Baiteshwor | 8
4004 | Dolakha | Chhetrapa | 8 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 8 | 8 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 8
4005 | Dolakha | Chhetrapa | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 8
4006 | Dolakha | Chhetrapa | 9 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 7 | 7 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 8
4007 | Dolakha | Chhetrapa | 9 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 7 | 7 | 2017-02-17 | 2017-02-17 |  | Baiteshwor | 8
4008 | Dolakha | Chhetrapa | 9 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 7 | 7 | 2017-03-21 | 2017-03-21 |  | Baiteshwor | 8
4009 | Dolakha | Chhetrapa | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 8
4010 | Dolakha | Chhetrapa | 9 | GON - PAF | REDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-05-11 | 2017-05-17 |  | Baiteshwor | 8
4011 | Dolakha | Chhetrapa | 9 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 8
4012 | Dolakha | Chhetrapa | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 8
4013 | Dolakha | Chhetrapa | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 132 |  |  |  | Baiteshwor | 8
4014 | Dolakha | Chilankha | 1 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27 |  | Bigu | 5
4015 | Dolakha | Chilankha | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 162 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4016 | Dolakha | Chilankha | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4017 | Dolakha | Chilankha | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 113 | 18 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4018 | Dolakha | Chilankha | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 113 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4019 | Dolakha | Chilankha | 1 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27 |  | Bigu | 5
4020 | Dolakha | Chilankha | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 18 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4021 | Dolakha | Chilankha | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4022 | Dolakha | Chilankha | 2 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Bigu | 5
4023 | Dolakha | Chilankha | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 139 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4024 | Dolakha | Chilankha | 2 | CA | HURADEC |  | Technical Assistance | Demonstration Construction | House | Construction of Demo house | # of constructions | Yes | Completed | 2 | 2 | 2017-02-15 | 2017-05-30 |  | Bigu | 5
4025 | Dolakha | Chilankha | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4026 | Dolakha | Chilankha | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 76 | 17 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4027 | Dolakha | Chilankha | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 76 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4028 | Dolakha | Chilankha | 2 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Bigu | 5
4029 | Dolakha | Chilankha | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4030 | Dolakha | Chilankha | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4031 | Dolakha | Chilankha | 3 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Bigu | 5
4032 | Dolakha | Chilankha | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 117 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4033 | Dolakha | Chilankha | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4034 | Dolakha | Chilankha | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 76 | 15 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4035 | Dolakha | Chilankha | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 76 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4036 | Dolakha | Chilankha | 3 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Bigu | 5
4037 | Dolakha | Chilankha | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 12 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4038 | Dolakha | Chilankha | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4039 | Dolakha | Chilankha | 4 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27 |  | Bigu | 5
4040 | Dolakha | Chilankha | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 253 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4041 | Dolakha | Chilankha | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4042 | Dolakha | Chilankha | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 112 | 27 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4043 | Dolakha | Chilankha | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 112 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4044 | Dolakha | Chilankha | 4 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27 |  | Bigu | 5
4045 | Dolakha | Chilankha | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 8 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4046 | Dolakha | Chilankha | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4047 | Dolakha | Chilankha | 5 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Bigu | 5
4048 | Dolakha | Chilankha | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 124 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4049 | Dolakha | Chilankha | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4050 | Dolakha | Chilankha | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 66 | 5 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4051 | Dolakha | Chilankha | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 66 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4052 | Dolakha | Chilankha | 5 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Bigu | 5
4053 | Dolakha | Chilankha | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 13 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4054 | Dolakha | Chilankha | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4055 | Dolakha | Chilankha | 6 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27 |  | Bigu | 5
4056 | Dolakha | Chilankha | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 194 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4057 | Dolakha | Chilankha | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4058 | Dolakha | Chilankha | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 112 | 8 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4059 | Dolakha | Chilankha | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 112 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4060 | Dolakha | Chilankha | 6 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27 |  | Bigu | 5
4061 | Dolakha | Chilankha | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 19 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4062 | Dolakha | Chilankha | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4063 | Dolakha | Chilankha | 7 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Bigu | 5
4064 | Dolakha | Chilankha | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 91 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4065 | Dolakha | Chilankha | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4066 | Dolakha | Chilankha | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 72 | 5 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4067 | Dolakha | Chilankha | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 72 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4068 | Dolakha | Chilankha | 7 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Bigu | 5
4069 | Dolakha | Chilankha | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 4 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4070 | Dolakha | Chilankha | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4071 | Dolakha | Chilankha | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 35 | 35 | 2017-07-20 | 2017-07-26 |  | Bigu | 5
4072 | Dolakha | Chilankha | 8 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Bigu | 5
4073 | Dolakha | Chilankha | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 99 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4074 | Dolakha | Chilankha | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4075 | Dolakha | Chilankha | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 80 | 8 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4076 | Dolakha | Chilankha | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 80 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4077 | Dolakha | Chilankha | 8 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Bigu | 5
4078 | Dolakha | Chilankha | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 8 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4079 | Dolakha | Chilankha | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4080 | Dolakha | Chilankha | 9 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Bigu | 5
4081 | Dolakha | Chilankha | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 103 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4082 | Dolakha | Chilankha | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4083 | Dolakha | Chilankha | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 86 | 10 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4084 | Dolakha | Chilankha | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 86 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4085 | Dolakha | Chilankha | 9 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Bigu | 5
4086 | Dolakha | Chilankha | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 8 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4087 | Dolakha | Chilankha | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 5
4088 | Dolakha | Chyama | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 80 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4089 | Dolakha | Chyama | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4090 | Dolakha | Chyama | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 84 | 14 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4091 | Dolakha | Chyama | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 84 | 61 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4092 | Dolakha | Chyama | 1 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 6
4093 | Dolakha | Chyama | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 3 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4094 | Dolakha | Chyama | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4095 | Dolakha | Chyama | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 80 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4096 | Dolakha | Chyama | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4097 | Dolakha | Chyama | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 106 | 22 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4098 | Dolakha | Chyama | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 106 | 61 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4099 | Dolakha | Chyama | 2 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 6
4100 | Dolakha | Chyama | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 5 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4101 | Dolakha | Chyama | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4102 | Dolakha | Chyama | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 129 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4103 | Dolakha | Chyama | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4104 | Dolakha | Chyama | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 106 | 20 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4105 | Dolakha | Chyama | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 106 | 61 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4106 | Dolakha | Chyama | 3 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 6
4107 | Dolakha | Chyama | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4108 | Dolakha | Chyama | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4109 | Dolakha | Chyama | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 168 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4110 | Dolakha | Chyama | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4111 | Dolakha | Chyama | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 91 | 20 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4112 | Dolakha | Chyama | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 91 | 61 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4113 | Dolakha | Chyama | 4 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 6
4114 | Dolakha | Chyama | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 1 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4115 | Dolakha | Chyama | 4 | MC | REDC | MC | Training | ToT | Skilled masons |  | # of trainees | Yes | Completed | 28 | 26 | 2016-09-18 | 2016-09-24 |  | Tamakoshi | 6
4116 | Dolakha | Chyama | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4117 | Dolakha | Chyama | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 62 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4118 | Dolakha | Chyama | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4119 | Dolakha | Chyama | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 78 | 14 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4120 | Dolakha | Chyama | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 78 | 61 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4121 | Dolakha | Chyama | 5 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 6
4122 | Dolakha | Chyama | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 3 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4123 | Dolakha | Chyama | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4124 | Dolakha | Chyama | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 77 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4125 | Dolakha | Chyama | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4126 | Dolakha | Chyama | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 75 | 8 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4127 | Dolakha | Chyama | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 75 | 61 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4128 | Dolakha | Chyama | 6 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 6
4129 | Dolakha | Chyama | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 1 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4130 | Dolakha | Chyama | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4131 | Dolakha | Chyama | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 67 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4132 | Dolakha | Chyama | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4133 | Dolakha | Chyama | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 114 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4134 | Dolakha | Chyama | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 114 | 61 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4135 | Dolakha | Chyama | 7 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 6
4136 | Dolakha | Chyama | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 1 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4137 | Dolakha | Chyama | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4138 | Dolakha | Chyama | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 132 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4139 | Dolakha | Chyama | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4140 | Dolakha | Chyama | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 77 | 16 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4141 | Dolakha | Chyama | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 77 | 61 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4142 | Dolakha | Chyama | 8 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 6
4143 | Dolakha | Chyama | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 4 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4144 | Dolakha | Chyama | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4145 | Dolakha | Chyama | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 188 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4146 | Dolakha | Chyama | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4147 | Dolakha | Chyama | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 69 | 13 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4148 | Dolakha | Chyama | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 69 | 61 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4149 | Dolakha | Chyama | 9 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 6
4150 | Dolakha | Chyama | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4151 | Dolakha | Chyama | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 6
4152 | Dolakha | Dandakharka | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 6
4153 | Dolakha | Dandakharka | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 6
4154 | Dolakha | Dandakharka | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 5
4155 | Dolakha | Dandakharka | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 5
4156 | Dolakha | Dandakharka | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 5
4157 | Dolakha | Dandakharka | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 5
4158 | Dolakha | Dandakharka | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 5
4159 | Dolakha | Dandakharka | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 5
4160 | Dolakha | Dandakharka | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 5
4161 | Dolakha | Dandakharka | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 5
4162 | Dolakha | Dandakharka | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 5
4163 | Dolakha | Dandakharka | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 5
4164 | Dolakha | Dandakharka | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 6
4165 | Dolakha | Dandakharka | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 6
4166 | Dolakha | Dandakharka | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 5
4167 | Dolakha | Dandakharka | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 5
4168 | Dolakha | Dandakharka | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 6
4169 | Dolakha | Dandakharka | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 6
4170 | Dolakha | Dudhpokhari | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 1
4171 | Dolakha | Dudhpokhari | 1 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-16 | 2016-10-22 |  | Sailung | 1
4172 | Dolakha | Dudhpokhari | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 1
4173 | Dolakha | Dudhpokhari | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 1
4174 | Dolakha | Dudhpokhari | 2 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-16 | 2016-10-22 |  | Sailung | 1
4175 | Dolakha | Dudhpokhari | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 1
4176 | Dolakha | Dudhpokhari | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 1
4177 | Dolakha | Dudhpokhari | 3 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-16 | 2016-10-22 |  | Sailung | 1
4178 | Dolakha | Dudhpokhari | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 1
4179 | Dolakha | Dudhpokhari | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 1
4180 | Dolakha | Dudhpokhari | 4 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-16 | 2016-10-22 |  | Sailung | 1
4181 | Dolakha | Dudhpokhari | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 1
4182 | Dolakha | Dudhpokhari | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 1
4183 | Dolakha | Dudhpokhari | 5 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-16 | 2016-10-22 |  | Sailung | 1
4184 | Dolakha | Dudhpokhari | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 1
4185 | Dolakha | Dudhpokhari | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 1
4186 | Dolakha | Dudhpokhari | 6 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-16 | 2016-10-22 |  | Sailung | 1
4187 | Dolakha | Dudhpokhari | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 1
4188 | Dolakha | Dudhpokhari | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 1
4189 | Dolakha | Dudhpokhari | 7 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-16 | 2016-10-22 |  | Sailung | 1
4190 | Dolakha | Dudhpokhari | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 1
4191 | Dolakha | Dudhpokhari | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 1
4192 | Dolakha | Dudhpokhari | 8 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-16 | 2016-10-22 |  | Sailung | 1
4193 | Dolakha | Dudhpokhari | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 1
4194 | Dolakha | Dudhpokhari | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 1
4195 | Dolakha | Dudhpokhari | 9 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-16 | 2016-10-22 |  | Sailung | 1
4196 | Dolakha | Dudhpokhari | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 1
4197 | Dolakha | Fasku | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 7
4198 | Dolakha | Fasku | 1 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-23 | 2016-10-29 |  | Sailung | 7
4199 | Dolakha | Fasku | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 7
4200 | Dolakha | Fasku | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 7
4201 | Dolakha | Fasku | 2 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Sailung | 7
4202 | Dolakha | Fasku | 2 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-23 | 2016-10-29 |  | Sailung | 7
4203 | Dolakha | Fasku | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 7
4204 | Dolakha | Fasku | 2 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0 |  |  |  | Sailung | 7
4205 | Dolakha | Fasku | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 7
4206 | Dolakha | Fasku | 3 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Sailung | 7
4207 | Dolakha | Fasku | 3 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-23 | 2016-10-29 |  | Sailung | 7
4208 | Dolakha | Fasku | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 7
4209 | Dolakha | Fasku | 3 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0 |  |  |  | Sailung | 7
4210 | Dolakha | Fasku | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 7
4211 | Dolakha | Fasku | 4 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-23 | 2016-10-29 |  | Sailung | 7
4212 | Dolakha | Fasku | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 7
4213 | Dolakha | Fasku | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 7
4214 | Dolakha | Fasku | 5 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Sailung | 7
4215 | Dolakha | Fasku | 5 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-23 | 2016-10-29 |  | Sailung | 7
4216 | Dolakha | Fasku | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 7
4217 | Dolakha | Fasku | 5 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0 |  |  |  | Sailung | 7
4218 | Dolakha | Fasku | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 6
4219 | Dolakha | Fasku | 6 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-23 | 2016-10-29 |  | Sailung | 6
4220 | Dolakha | Fasku | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 6
4221 | Dolakha | Fasku | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 6
4222 | Dolakha | Fasku | 7 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-23 | 2016-10-29 |  | Sailung | 6
4223 | Dolakha | Fasku | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 6
4224 | Dolakha | Fasku | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 6
4225 | Dolakha | Fasku | 8 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Sailung | 6
4226 | Dolakha | Fasku | 8 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-23 | 2016-10-29 |  | Sailung | 6
4227 | Dolakha | Fasku | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 6
4228 | Dolakha | Fasku | 8 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 12 | 0 |  |  |  | Sailung | 6
4229 | Dolakha | Fasku | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 6
4230 | Dolakha | Fasku | 9 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-05 | 2016-11-11 |  | Sailung | 6
4231 | Dolakha | Fasku | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 6
4232 | Dolakha | Fasku | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 49 |  |  |  | Sailung | 7
4233 | Dolakha | Gairimudi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 1
4234 | Dolakha | Gairimudi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 1
4235 | Dolakha | Gairimudi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 1
4236 | Dolakha | Gairimudi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 1
4237 | Dolakha | Gairimudi | 2 | AA | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2016-11-27 | 2016-12-03 |  | Baiteshwor | 1
4238 | Dolakha | Gairimudi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 1
4239 | Dolakha | Gairimudi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 1
4240 | Dolakha | Gairimudi | 3 | AA | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-11-27 | 2016-12-03 |  | Baiteshwor | 1
4241 | Dolakha | Gairimudi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 1
4242 | Dolakha | Gairimudi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 1
4243 | Dolakha | Gairimudi | 4 | AA | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 18 | 18 | 2016-11-27 | 2016-12-03 |  | Baiteshwor | 1
4244 | Dolakha | Gairimudi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 1
4245 | Dolakha | Gairimudi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 1
4246 | Dolakha | Gairimudi | 5 | AA | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2016-11-27 | 2016-12-03 |  | Baiteshwor | 1
4247 | Dolakha | Gairimudi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 2
4248 | Dolakha | Gairimudi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 2
4249 | Dolakha | Gairimudi | 6 | AA | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-11-27 | 2016-12-03 |  | Baiteshwor | 2
4250 | Dolakha | Gairimudi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 2
4251 | Dolakha | Gairimudi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 2
4252 | Dolakha | Gairimudi | 7 | AA | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2016-11-27 | 2016-12-03 |  | Baiteshwor | 2
4253 | Dolakha | Gairimudi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 2
4254 | Dolakha | Gairimudi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 2
4255 | Dolakha | Gairimudi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 2
4256 | Dolakha | Gairimudi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 2
4257 | Dolakha | GauriSankar | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 9
4258 | Dolakha | GauriSankar | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 9
4259 | Dolakha | GauriSankar | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 9
4260 | Dolakha | Gaurisankar | 2 | HELVETAS | KITE |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 5 | 5 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 9
4261 | Dolakha | GauriSankar | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 9
4262 | Dolakha | GauriSankar | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 9
4263 | Dolakha | Gaurisankar | 3 | HELVETAS | KITE |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 5 | 5 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 9
4264 | Dolakha | GauriSankar | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 9
4265 | Dolakha | GauriSankar | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 9
4266 | Dolakha | Gaurisankar | 4 | HELVETAS | KITE |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 9
4267 | Dolakha | Gaurisankar | 4 | HELVETAS | KITE |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 5 | 5 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 9
4268 | Dolakha | GauriSankar | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 9
4269 | Dolakha | GauriSankar | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 9
4270 | Dolakha | Gaurisankar | 5 | HELVETAS | KITE |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 9
4271 | Dolakha | Gaurisankar | 5 | HELVETAS | KITE |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 5 | 5 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 9
4272 | Dolakha | GauriSankar | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 9
4273 | Dolakha | GauriSankar | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 9
4274 | Dolakha | Gaurisankar | 6 | HELVETAS | KITE |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 9
4275 | Dolakha | Gaurisankar | 6 | HELVETAS | KITE |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 5 | 5 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 9
4276 | Dolakha | GauriSankar | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 9
4277 | Dolakha | GauriSankar | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 9
4278 | Dolakha | Gaurisankar | 7 | HELVETAS | KITE |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 5 | 5 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 9
4279 | Dolakha | GauriSankar | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 9
4280 | Dolakha | GauriSankar | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 9
4281 | Dolakha | Gaurisankar | 8 | HELVETAS | KITE |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 9
4282 | Dolakha | Gaurisankar | 8 | HELVETAS | KITE |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 5 | 5 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 9
4283 | Dolakha | GauriSankar | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 9
4284 | Dolakha | GauriSankar | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 9
4285 | Dolakha | Gaurisankar | 9 | HELVETAS | KITE |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 9
4286 | Dolakha | Gaurisankar | 9 | HELVETAS | KITE |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 5 | 5 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 9
4287 | Dolakha | GauriSankar | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 9
4288 | Dolakha | GhangSukathokar | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 2
4289 | Dolakha | GhangSukathokar | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 2
4290 | Dolakha | GhangSukathokar | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 2
4291 | Dolakha | GhangSukathokar | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 2
4292 | Dolakha | GhangSukathokar | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 2
4293 | Dolakha | GhangSukathokar | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 2
4294 | Dolakha | GhangSukathokar | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 2
4295 | Dolakha | GhangSukathokar | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 2
4296 | Dolakha | GhangSukathokar | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 3
4297 | Dolakha | GhangSukathokar | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 3
4298 | Dolakha | GhangSukathokar | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 3
4299 | Dolakha | GhangSukathokar | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 3
4300 | Dolakha | GhangSukathokar | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 3
4301 | Dolakha | GhangSukathokar | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 3
4302 | Dolakha | GhangSukathokar | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 3
4303 | Dolakha | GhangSukathokar | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 3
4304 | Dolakha | GhangSukathokar | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 3
4305 | Dolakha | GhangSukathokar | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 3
4306 | Dolakha | Hawa | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 7
4307 | Dolakha | Hawa | 1 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 7
4308 | Dolakha | Hawa | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 7
4309 | Dolakha | Hawa | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 7
4310 | Dolakha | Hawa | 2 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 7
4311 | Dolakha | Hawa | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 7
4312 | Dolakha | Hawa | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 7
4313 | Dolakha | Hawa | 3 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 7
4314 | Dolakha | Hawa | 3 | MC | REDC | MC | Training | ToT | Skilled masons |  | # of trainees | Yes | Completed | 28 | 28 | 2016-09-18 | 2016-09-24 |  | Tamakoshi | 7
4315 | Dolakha | Hawa | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 7
4316 | Dolakha | Hawa | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 7
4317 | Dolakha | Hawa | 4 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 7
4318 | Dolakha | Hawa | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 7
4319 | Dolakha | Hawa | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 7
4320 | Dolakha | Hawa | 5 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 7
4321 | Dolakha | Hawa | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 7
4322 | Dolakha | Hawa | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 7
4323 | Dolakha | Hawa | 6 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 7
4324 | Dolakha | Hawa | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 7
4325 | Dolakha | Hawa | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 7
4326 | Dolakha | Hawa | 7 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 7
4327 | Dolakha | Hawa | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 7
4328 | Dolakha | Hawa | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 7
4329 | Dolakha | Hawa | 8 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 7
4330 | Dolakha | Hawa | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 7
4331 | Dolakha | Hawa | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 7
4332 | Dolakha | Hawa | 9 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 7
4333 | Dolakha | Hawa | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 7
4334 | Dolakha | Japhe | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 175 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4335 | Dolakha | Japhe | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4336 | Dolakha | Japhe | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 235 | 15 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4337 | Dolakha | Japhe | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 235 | 63 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4338 | Dolakha | Japhe | 1 | GON - PAF | REDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2017-05-11 | 2017-05-17 |  | Tamakoshi | 3
4339 | Dolakha | Japhe | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 9 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4340 | Dolakha | Japhe | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4341 | Dolakha | Japhe | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 151 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4342 | Dolakha | Japhe | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4343 | Dolakha | Japhe | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 113 | 28 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4344 | Dolakha | Japhe | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 113 | 63 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4345 | Dolakha | Japhe | 2 | GON - PAF | REDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-05-11 | 2017-05-17 |  | Tamakoshi | 3
4346 | Dolakha | Japhe | 2 | CW | RRN | DEC-II | Training | Short training | Masons (other curriculums, specify in Activity Detail) | Self (Prepared and endorsed from DUDBC) | # of trainees | Yes | Planned | 10 | 0 | 2017-01-01 |  |  | Tamakoshi | 3
4347 | Dolakha | Japhe | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 10 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4348 | Dolakha | Japhe | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4349 | Dolakha | Japhe | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 107 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4350 | Dolakha | Japhe | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4351 | Dolakha | Japhe | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 119 | 2 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4352 | Dolakha | Japhe | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 119 | 63 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4353 | Dolakha | Japhe | 3 | GON - PAF | REDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2017-05-11 | 2017-05-17 |  | Tamakoshi | 3
4354 | Dolakha | Japhe | 3 | CW | RRN | DEC-II | Training | Short training | Masons (other curriculums, specify in Activity Detail) | Self (Prepared and endorsed from DUDBC) | # of trainees | Yes | Planned | 10 | 0 | 2017-01-01 |  |  | Tamakoshi | 3
4355 | Dolakha | Japhe | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4356 | Dolakha | Japhe | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4357 | Dolakha | Japhe | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 171 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4358 | Dolakha | Japhe | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4359 | Dolakha | Japhe | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 116 | 15 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4360 | Dolakha | Japhe | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 116 | 111 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4361 | Dolakha | Japhe | 4 | GON - PAF | REDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2017-05-11 | 2017-05-17 |  | Tamakoshi | 3
4362 | Dolakha | Japhe | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 8 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4363 | Dolakha | Japhe | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4364 | Dolakha | Japhe | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 89 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4365 | Dolakha | Japhe | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4366 | Dolakha | Japhe | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 161 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4367 | Dolakha | Japhe | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 161 | 63 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4368 | Dolakha | Japhe | 5 | GON - PAF | REDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-05-11 | 2017-05-17 |  | Tamakoshi | 3
4369 | Dolakha | Japhe | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 10 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4370 | Dolakha | Japhe | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4371 | Dolakha | Japhe | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 88 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4372 | Dolakha | Japhe | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4373 | Dolakha | Japhe | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 94 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4374 | Dolakha | Japhe | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 94 | 63 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4375 | Dolakha | Japhe | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 7 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4376 | Dolakha | Japhe | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4377 | Dolakha | Japhe | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 150 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4378 | Dolakha | Japhe | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4379 | Dolakha | Japhe | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 100 | 11 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4380 | Dolakha | Japhe | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 100 | 63 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4381 | Dolakha | Japhe | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4382 | Dolakha | Japhe | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4383 | Dolakha | Japhe | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 212 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4384 | Dolakha | Japhe | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4385 | Dolakha | Japhe | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 64 | 11 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4386 | Dolakha | Japhe | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 64 | 63 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4387 | Dolakha | Japhe | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 15 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4388 | Dolakha | Japhe | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4389 | Dolakha | Japhe | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 322 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4390 | Dolakha | Japhe | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4391 | Dolakha | Japhe | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 101 | 13 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4392 | Dolakha | Japhe | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 101 | 63 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4393 | Dolakha | Japhe | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 11 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4394 | Dolakha | Japhe | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 3
4395 | Dolakha | Japhe | ALL | UNHABITAT |  |  | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 50 |  |  |  | Tamakoshi | 3
4396 | Dolakha | Japhe | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 174 |  |  |  | Tamakoshi | 3
4397 | Dolakha | Jhule | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 93 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4398 | Dolakha | Jhule | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4399 | Dolakha | Jhule | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 57 | 9 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4400 | Dolakha | Jhule | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 57 | 71 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4401 | Dolakha | Jhule | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4402 | Dolakha | Jhule | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4403 | Dolakha | Jhule | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 48 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4404 | Dolakha | Jhule | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4405 | Dolakha | Jhule | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 37 | 5 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4406 | Dolakha | Jhule | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 37 | 71 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4407 | Dolakha | Jhule | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 7 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4408 | Dolakha | Jhule | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4409 | Dolakha | Jhule | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 96 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4410 | Dolakha | Jhule | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4411 | Dolakha | Jhule | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 44 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4412 | Dolakha | Jhule | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 44 | 71 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4413 | Dolakha | Jhule | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 10 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4414 | Dolakha | Jhule | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 4 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4415 | Dolakha | Jhule | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 118 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4416 | Dolakha | Jhule | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4417 | Dolakha | Jhule | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 50 | 4 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4418 | Dolakha | Jhule | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 50 | 71 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4419 | Dolakha | Jhule | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 12 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4420 | Dolakha | Jhule | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4421 | Dolakha | Jhule | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 121 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4422 | Dolakha | Jhule | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4423 | Dolakha | Jhule | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 49 | 21 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4424 | Dolakha | Jhule | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 49 | 71 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4425 | Dolakha | Jhule | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 7 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4426 | Dolakha | Jhule | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4427 | Dolakha | Jhule | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 90 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4428 | Dolakha | Jhule | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4429 | Dolakha | Jhule | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 36 | 12 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4430 | Dolakha | Jhule | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 36 | 71 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4431 | Dolakha | Jhule | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 4 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4432 | Dolakha | Jhule | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4433 | Dolakha | Jhule | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 58 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4434 | Dolakha | Jhule | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4435 | Dolakha | Jhule | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 93 | 2 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4436 | Dolakha | Jhule | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 93 | 71 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4437 | Dolakha | Jhule | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 5 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4438 | Dolakha | Jhule | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4439 | Dolakha | Jhule | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 131 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4440 | Dolakha | Jhule | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4441 | Dolakha | Jhule | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 42 | 5 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4442 | Dolakha | Jhule | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 42 | 71 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4443 | Dolakha | Jhule | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 10 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4444 | Dolakha | Jhule | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4445 | Dolakha | Jhule | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 148 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4446 | Dolakha | Jhule | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4447 | Dolakha | Jhule | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 53 | 11 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4448 | Dolakha | Jhule | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 53 | 71 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4449 | Dolakha | Jhule | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 9 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4450 | Dolakha | Jhule | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 2
4451 | Dolakha | Jhyaku | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 4
4452 | Dolakha | Jhyaku | 1 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 12 | 12 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 4
4453 | Dolakha | Jhyaku | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 4
4454 | Dolakha | Jhyaku | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 4
4455 | Dolakha | Jhyaku | 2 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 4
4456 | Dolakha | Jhyaku | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 4
4457 | Dolakha | Jhyaku | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 4
4458 | Dolakha | Jhyaku | 3 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 4
4459 | Dolakha | Jhyaku | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 4
4460 | Dolakha | Jhyaku | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 4
4461 | Dolakha | Jhyaku | 4 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 4
4462 | Dolakha | Jhyaku | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 4
4463 | Dolakha | Jhyaku | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 3
4464 | Dolakha | Jhyaku | 5 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 3
4465 | Dolakha | Jhyaku | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 3
4466 | Dolakha | Jhyaku | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 3
4467 | Dolakha | Jhyaku | 6 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 3
4468 | Dolakha | Jhyaku | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 3
4469 | Dolakha | Jhyaku | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 3
4470 | Dolakha | Jhyaku | 7 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 3
4471 | Dolakha | Jhyaku | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 3
4472 | Dolakha | Jhyaku | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 3
4473 | Dolakha | Jhyaku | 8 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 3
4474 | Dolakha | Jhyaku | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 3
4475 | Dolakha | Jhyaku | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 3
4476 | Dolakha | Jhyaku | 9 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 13 | 13 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 3
4477 | Dolakha | Jhyaku | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 3
4478 | Dolakha | Jiri N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 2
4479 | Dolakha | Jiri N.P. | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 2
4480 | Dolakha | Jiri N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 3
4481 | Dolakha | Jiri N.P. | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 3
4482 | Dolakha | Jiri N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 3
4483 | Dolakha | Jiri N.P. | 3 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-05-28 | 2017-06-03 |  | Jiri | 3
4484 | Dolakha | Jiri N.P. | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 3
4485 | Dolakha | Jiri N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 4
4486 | Dolakha | Jiri N.P. | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 4
4487 | Dolakha | Jiri N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 5
4488 | Dolakha | Jiri N.P. | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 5
4489 | Dolakha | Jiri N.P. | 6 | LWF | HURADEC | LWF | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Ongoing | 50 | 30 | 2017-04-29 | 2017-04-29 |  | Jiri | 6
4490 | Dolakha | Jiri N.P. | 6 | LWF | HURADEC | LWF | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Ongoing | 50 | 18 | 2017-05-03 | 2017-05-03 |  | Jiri | 6
4491 | Dolakha | Jiri N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 6
4492 | Dolakha | Jiri N.P. | 6 | LWF | HURADEC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 30 | 30 | 2017-02-24 | 2017-03-02 |  | Jiri | 6
4493 | Dolakha | Jiri N.P. | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 6
4494 | Dolakha | Jiri N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 7
4495 | Dolakha | Jiri N.P. | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 7
4496 | Dolakha | Jiri N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 8
4497 | Dolakha | Jiri N.P. | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 8
4498 | Dolakha | Jiri N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 8
4499 | Dolakha | Jiri N.P. | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 8
4500 | Dolakha | Jiri N.P. | All | BC |  | BC | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 0 | 0 |  |  | Note that the implementing party will be Jiri Technical School | Jiri | 9
4501 | Dolakha | Jiri N.P. | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 196 |  |  |  | Jiri | 9
4502 | Dolakha | Jugu | 1 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 14 | 14 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 1
4503 | Dolakha | Jugu | 1 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 14 | 14 | 2017-03-02 | 2017-03-02 |  | Gaurishankar | 1
4504 | Dolakha | Jugu | 1 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 14 | 11 | 2017-03-21 | 2017-03-21 |  | Gaurishankar | 1
4505 | Dolakha | Jugu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 1
4506 | Dolakha | Jugu | 1 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 15 | 15 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 1
4507 | Dolakha | Jugu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 1
4508 | Dolakha | Jugu | 1 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 1 | 1 | 2016-12-01 |  |  | Gaurishankar | 1
4509 | Dolakha | Jugu | 2 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 11 | 11 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 2
4510 | Dolakha | Jugu | 2 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 11 | 11 | 2017-03-02 | 2017-03-02 |  | Gaurishankar | 2
4511 | Dolakha | Jugu | 2 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 11 | 8 | 2017-03-21 | 2017-03-21 |  | Gaurishankar | 2
4512 | Dolakha | Jugu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 2
4513 | Dolakha | Jugu | 2 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 7 | 7 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 2
4514 | Dolakha | Jugu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 2
4515 | Dolakha | Jugu | 2 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-12-01 |  |  | Gaurishankar | 2
4516 | Dolakha | Jugu | 3 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 12 | 12 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 2
4517 | Dolakha | Jugu | 3 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 12 | 12 | 2017-03-02 | 2017-03-02 |  | Gaurishankar | 2
4518 | Dolakha | Jugu | 3 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 12 | 7 | 2017-03-21 | 2017-03-21 |  | Gaurishankar | 2
4519 | Dolakha | Jugu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 2
4520 | Dolakha | Jugu | 3 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 8 | 8 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 2
4521 | Dolakha | Jugu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 2
4522 | Dolakha | Jugu | 3 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 3 | 1 | 2016-12-01 |  |  | Gaurishankar | 2
4523 | Dolakha | Jugu | 4 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 9 | 9 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 2
4524 | Dolakha | Jugu | 4 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 9 | 7 | 2017-03-02 | 2017-03-02 |  | Gaurishankar | 2
4525 | Dolakha | Jugu | 4 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 9 | 9 | 2017-03-21 | 2017-03-21 |  | Gaurishankar | 2
4526 | Dolakha | Jugu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 2
4527 | Dolakha | Jugu | 4 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 2
4528 | Dolakha | Jugu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 2
4529 | Dolakha | Jugu | 4 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 1 | 1 | 2016-12-01 |  |  | Gaurishankar | 2
4530 | Dolakha | Jugu | 5 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 9 | 9 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 2
4531 | Dolakha | Jugu | 5 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 9 | 5 | 2017-03-02 | 2017-03-02 |  | Gaurishankar | 2
4532 | Dolakha | Jugu | 5 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 9 | 7 | 2017-03-21 | 2017-03-21 |  | Gaurishankar | 2
4533 | Dolakha | Jugu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 2
4534 | Dolakha | Jugu | 5 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 2
4535 | Dolakha | Jugu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 2
4536 | Dolakha | Jugu | 6 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 12 | 12 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 2
4537 | Dolakha | Jugu | 6 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 12 | 10 | 2017-03-02 | 2017-03-02 |  | Gaurishankar | 2
4538 | Dolakha | Jugu | 6 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 12 | 9 | 2017-03-21 | 2017-03-21 |  | Gaurishankar | 2
4539 | Dolakha | Jugu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 2
4540 | Dolakha | Jugu | 6 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 9 | 9 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 2
4541 | Dolakha | Jugu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 2
4542 | Dolakha | Jugu | 6 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 1 | 1 | 2016-12-01 |  |  | Gaurishankar | 2
4543 | Dolakha | Jugu | 7 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 10 | 10 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 1
4544 | Dolakha | Jugu | 7 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 10 | 9 | 2017-03-02 | 2017-03-02 |  | Gaurishankar | 1
4545 | Dolakha | Jugu | 7 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 10 | 8 | 2017-03-21 | 2017-03-21 |  | Gaurishankar | 1
4546 | Dolakha | Jugu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 1
4547 | Dolakha | Jugu | 7 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 1
4548 | Dolakha | Jugu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 1
4549 | Dolakha | Jugu | 7 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 3 | 3 | 2016-12-01 |  |  | Gaurishankar | 1
4550 | Dolakha | Jugu | 8 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 11 | 11 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 1
4551 | Dolakha | Jugu | 8 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 11 | 11 | 2017-03-02 | 2017-03-02 |  | Gaurishankar | 1
4552 | Dolakha | Jugu | 8 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 11 | 10 | 2017-03-21 | 2017-03-21 |  | Gaurishankar | 1
4553 | Dolakha | Jugu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 1
4554 | Dolakha | Jugu | 8 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 9 | 9 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 1
4555 | Dolakha | Jugu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 1
4556 | Dolakha | Jugu | 8 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 4 | 4 | 2016-12-01 |  |  | Gaurishankar | 1
4557 | Dolakha | Jugu | 9 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 12 | 12 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 1
4558 | Dolakha | Jugu | 9 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 12 | 11 | 2017-03-02 | 2017-03-02 |  | Gaurishankar | 1
4559 | Dolakha | Jugu | 9 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 12 | 10 | 2017-03-21 | 2017-03-21 |  | Gaurishankar | 1
4560 | Dolakha | Jugu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 1
4561 | Dolakha | Jugu | 9 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 9 | 9 | 2015-07-20 | 2015-07-24 |  | Gaurishankar | 1
4562 | Dolakha | Jugu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 1
4563 | Dolakha | Jugu | 9 | SCI | RDTA |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-12-01 |  |  | Gaurishankar | 1
4564 | Dolakha | Kabhre | 1 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 30 | 30 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 5
4565 | Dolakha | Kabhre | 1 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 30 | 28 | 2017-03-23 | 2017-03-23 |  | Baiteshwor | 5
4566 | Dolakha | Kabhre | 1 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Completed | 30 | 17 | 2017-03-23 | 2017-03-23 |  | Baiteshwor | 5
4567 | Dolakha | Kabhre | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 5
4568 | Dolakha | Kabhre | 1 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 9 | 9 | 2016-04-19 | 2016-05-03 | 19-25 Apr First Session, 27 Apr-3 May Second Session | Baiteshwor | 5
4569 | Dolakha | Kabhre | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 5
4570 | Dolakha | Kabhre | 2 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 20 | 20 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 5
4571 | Dolakha | Kabhre | 2 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 20 | 18 | 2017-03-23 | 2017-03-23 |  | Baiteshwor | 5
4572 | Dolakha | Kabhre | 2 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Completed | 20 | 11 | 2017-03-23 | 2017-03-23 |  | Baiteshwor | 5
4573 | Dolakha | Kabhre | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 5
4574 | Dolakha | Kabhre | 2 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 14 | 14 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 5
4575 | Dolakha | Kabhre | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 5
4576 | Dolakha | Kabhre | 3 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 20 | 20 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 5
4577 | Dolakha | Kabhre | 3 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 20 | 15 | 2017-03-23 | 2017-03-23 |  | Baiteshwor | 5
4578 | Dolakha | Kabhre | 3 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Completed | 20 | 13 | 2017-03-23 | 2017-03-23 |  | Baiteshwor | 5
4579 | Dolakha | Kabhre | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 5
4580 | Dolakha | Kabhre | 3 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 5
4581 | Dolakha | Kabhre | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 5
4582 | Dolakha | Kabhre | 3 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 3 | 3 | 2017-01-07 | 2017-02-15 |  | Baiteshwor | 5
4583 | Dolakha | Kabhre | 4 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 20 | 20 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 4
4584 | Dolakha | Kabhre | 4 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 20 | 18 | 2017-03-23 | 2017-03-23 |  | Baiteshwor | 4
4585 | Dolakha | Kabhre | 4 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Completed | 20 | 10 | 2017-03-23 | 2017-03-23 |  | Baiteshwor | 4
4586 | Dolakha | Kabhre | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 4
4587 | Dolakha | Kabhre | 4 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 4
4588 | Dolakha | Kabhre | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 4
4589 | Dolakha | Kabhre | 4 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 4 | 4 | 2017-01-07 | 2017-02-15 |  | Baiteshwor | 4
4590 | Dolakha | Kabhre | 4 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 10 | 10 | 2017-05-07 | 2017-06-14 |  | Baiteshwor | 4
4591 | Dolakha | Kabhre | 5 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 20 | 20 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 4
4592 | Dolakha | Kabhre | 5 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 20 | 18 | 2017-03-23 | 2017-03-23 |  | Baiteshwor | 4
4593 | Dolakha | Kabhre | 5 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Completed | 20 | 8 | 2017-03-23 | 2017-03-23 |  | Baiteshwor | 4
4594 | Dolakha | Kabhre | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 4
4595 | Dolakha | Kabhre | 5 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 4
4596 | Dolakha | Kabhre | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 4
4597 | Dolakha | Kabhre | 5 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2017-01-07 | 2017-02-15 |  | Baiteshwor | 4
4598 | Dolakha | Kabhre | 5 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-05-07 | 2017-06-14 |  | Baiteshwor | 4
4599 | Dolakha | Kabhre | 6 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 20 | 20 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 4
4600 | Dolakha | Kabhre | 6 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 20 | 18 | 2017-03-23 | 2017-03-23 |  | Baiteshwor | 4
4601 | Dolakha | Kabhre | 6 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Completed | 20 | 6 | 2017-03-23 | 2017-03-23 |  | Baiteshwor | 4
4602 | Dolakha | Kabhre | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 4
4603 | Dolakha | Kabhre | 6 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 15 | 15 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 4
4604 | Dolakha | Kabhre | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 4
4605 | Dolakha | Kabhre | 6 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 5 | 5 | 2017-01-07 | 2017-02-15 |  | Baiteshwor | 4
4606 | Dolakha | Kabhre | 6 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 7 | 7 | 2017-05-07 | 2017-06-14 |  | Baiteshwor | 4
4607 | Dolakha | Kabhre | 7 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 20 | 20 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 4
4608 | Dolakha | Kabhre | 7 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 20 | 15 | 2017-03-23 | 2017-03-23 |  | Baiteshwor | 4
4609 | Dolakha | Kabhre | 7 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Completed | 20 | 5 | 2017-03-23 | 2017-03-23 |  | Baiteshwor | 4
4610 | Dolakha | Kabhre | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 4
4611 | Dolakha | Kabhre | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 4
4612 | Dolakha | Kabhre | 7 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2017-01-07 | 2017-02-15 |  | Baiteshwor | 4
4613 | Dolakha | Kabhre | 7 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2017-05-07 | 2017-06-14 |  | Baiteshwor | 4
4614 | Dolakha | Kabhre | 8 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 20 | 20 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 5
4615 | Dolakha | Kabhre | 8 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 20 | 16 | 2017-03-23 | 2017-03-23 |  | Baiteshwor | 5
4616 | Dolakha | Kabhre | 8 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Completed | 20 | 4 | 2017-03-23 | 2017-03-23 |  | Baiteshwor | 5
4617 | Dolakha | Kabhre | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 5
4618 | Dolakha | Kabhre | 8 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 5
4619 | Dolakha | Kabhre | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 5
4620 | Dolakha | Kabhre | 8 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2017-05-07 | 2017-06-14 |  | Baiteshwor | 5
4621 | Dolakha | Kabhre | 9 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 20 | 20 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 5
4622 | Dolakha | Kabhre | 9 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Completed | 20 | 15 | 2017-03-23 | 2017-03-23 |  | Baiteshwor | 5
4623 | Dolakha | Kabhre | 9 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Completed | 20 | 5 | 2017-03-23 | 2017-03-23 |  | Baiteshwor | 5
4624 | Dolakha | Kabhre | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 5
4625 | Dolakha | Kabhre | 9 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2016-04-19 | 2016-05-03 |  | Baiteshwor | 5
4626 | Dolakha | Kabhre | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 5
4627 | Dolakha | Kabhre | 9 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 240 Hrs Training affiliated to CTEVT | # of trainees | Yes | Completed | 5 | 5 | 2017-01-07 | 2017-02-15 |  | Baiteshwor | 5
4628 | Dolakha | Kabhre | 9 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-05-07 | 2017-06-14 |  | Baiteshwor | 5
4629 | Dolakha | Kabhre | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 93 |  |  |  | Baiteshwor | 5
4630 | Dolakha | Kalingchok | 1 | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 90 | 87 | 2015-12-19 | 2016-09-30 |  | Kalinchok | 1
4631 | Dolakha | Kalingchok | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 1
4632 | Dolakha | Kalingchok | 1 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 90 | 87 | 2015-12-19 | 2016-09-30 |  | Kalinchok | 1
4633 | Dolakha | Kalingchok | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 1
4634 | Dolakha | Kalingchok | 2 | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 80 | 79 | 2015-12-19 | 2016-09-30 |  | Kalinchok | 1
4635 | Dolakha | Kalingchok | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 1
4636 | Dolakha | Kalingchok | 2 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 80 | 79 | 2015-12-19 | 2016-09-30 |  | Kalinchok | 1
4637 | Dolakha | Kalingchok | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 1
4638 | Dolakha | Kalingchok | 3 | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 110 | 105 | 2015-12-19 | 2016-09-30 |  | Kalinchok | 1
4639 | Dolakha | Kalingchok | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 1
4640 | Dolakha | Kalingchok | 3 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 110 | 105 | 2015-12-19 | 2016-09-30 |  | Kalinchok | 1
4641 | Dolakha | Kalingchok | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 1
4642 | Dolakha | Kalingchok | 4 | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 100 | 95 | 2015-12-19 | 2016-09-30 |  | Kalinchok | 1
4643 | Dolakha | Kalingchok | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 1
4644 | Dolakha | Kalingchok | 4 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 100 | 95 | 2015-12-19 | 2016-09-30 |  | Kalinchok | 1
4645 | Dolakha | Kalingchok | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 1
4646 | Dolakha | Kalingchok | 5 | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 85 | 82 | 2015-12-19 | 2016-09-30 |  | Kalinchok | 1
4647 | Dolakha | Kalingchok | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 1
4648 | Dolakha | Kalingchok | 5 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 85 | 82 | 2015-12-19 | 2016-09-30 |  | Kalinchok | 1
4649 | Dolakha | Kalingchok | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 1
4650 | Dolakha | Kalingchok | 6 | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 55 | 53 | 2015-12-19 | 2016-09-30 |  | Kalinchok | 1
4651 | Dolakha | Kalingchok | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 1
4652 | Dolakha | Kalingchok | 6 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 55 | 53 | 2015-12-19 | 2016-09-30 |  | Kalinchok | 1
4653 | Dolakha | Kalingchok | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 1
4654 | Dolakha | Kalingchok | 7 | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 75 | 73 | 2015-12-19 | 2016-09-30 |  | Kalinchok | 1
4655 | Dolakha | Kalingchok | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 1
4656 | Dolakha | Kalingchok | 7 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 75 | 73 | 2015-12-19 | 2016-09-30 |  | Kalinchok | 1
4657 | Dolakha | Kalingchok | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 1
4658 | Dolakha | Kalingchok | 8 | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 40 | 36 | 2015-12-19 | 2016-09-30 |  | Kalinchok | 1
4659 | Dolakha | Kalingchok | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 1
4660 | Dolakha | Kalingchok | 8 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 40 | 36 | 2015-12-19 | 2016-09-30 |  | Kalinchok | 1
4661 | Dolakha | Kalingchok | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 1
4662 | Dolakha | Kalingchok | 9 | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 45 | 43 | 2015-12-19 | 2016-09-30 |  | Kalinchok | 1
4663 | Dolakha | Kalingchok | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 1
4664 | Dolakha | Kalingchok | 9 | IOM | IOM |  | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 45 | 43 | 2015-12-19 | 2016-09-30 |  | Kalinchok | 1
4665 | Dolakha | Kalingchok | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 1
4666 | Dolakha | Kalingchok | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 25 |  |  |  | Kalinchok | 1
4667 | Dolakha | Katakuti | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 215 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4668 | Dolakha | Katakuti | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4669 | Dolakha | Katakuti | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 70 | 7 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4670 | Dolakha | Katakuti | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 70 | 51 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4671 | Dolakha | Katakuti | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 20 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4672 | Dolakha | Katakuti | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4673 | Dolakha | Katakuti | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 140 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4674 | Dolakha | Katakuti | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4675 | Dolakha | Katakuti | 2 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Sailung | 3
4676 | Dolakha | Katakuti | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 110 | 7 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4677 | Dolakha | Katakuti | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 110 | 51 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4678 | Dolakha | Katakuti | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 13 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4679 | Dolakha | Katakuti | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4680 | Dolakha | Katakuti | 2 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0 |  |  |  | Sailung | 3
4681 | Dolakha | Katakuti | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 28 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4682 | Dolakha | Katakuti | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4683 | Dolakha | Katakuti | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 172 | 6 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4684 | Dolakha | Katakuti | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 172 | 51 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4685 | Dolakha | Katakuti | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 7 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4686 | Dolakha | Katakuti | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4687 | Dolakha | Katakuti | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 30 | 30 | 2017-06-02 | 2017-06-08 |  | Sailung | 5
4688 | Dolakha | Katakuti | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 47 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4689 | Dolakha | Katakuti | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4690 | Dolakha | Katakuti | 4 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Sailung | 5
4691 | Dolakha | Katakuti | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 242 | 6 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4692 | Dolakha | Katakuti | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 242 | 51 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4693 | Dolakha | Katakuti | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 5 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4694 | Dolakha | Katakuti | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4695 | Dolakha | Katakuti | 4 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0 |  |  |  | Sailung | 5
4696 | Dolakha | Katakuti | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 14 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4697 | Dolakha | Katakuti | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4698 | Dolakha | Katakuti | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 208 | 8 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4699 | Dolakha | Katakuti | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 208 | 51 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4700 | Dolakha | Katakuti | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 4 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4701 | Dolakha | Katakuti | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4702 | Dolakha | Katakuti | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 160 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4703 | Dolakha | Katakuti | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4704 | Dolakha | Katakuti | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 265 | 6 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4705 | Dolakha | Katakuti | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 265 | 51 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4706 | Dolakha | Katakuti | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 5 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4707 | Dolakha | Katakuti | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4708 | Dolakha | Katakuti | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 175 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4709 | Dolakha | Katakuti | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4710 | Dolakha | Katakuti | 7 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Sailung | 5
4711 | Dolakha | Katakuti | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 120 | 8 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4712 | Dolakha | Katakuti | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 120 | 51 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4713 | Dolakha | Katakuti | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 10 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4714 | Dolakha | Katakuti | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 5
4715 | Dolakha | Katakuti | 7 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0 |  |  |  | Sailung | 5
4716 | Dolakha | Katakuti | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 131 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4717 | Dolakha | Katakuti | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4718 | Dolakha | Katakuti | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 115 | 4 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4719 | Dolakha | Katakuti | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 115 | 51 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4720 | Dolakha | Katakuti | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 13 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4721 | Dolakha | Katakuti | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4722 | Dolakha | Katakuti | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 8 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4723 | Dolakha | Katakuti | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4724 | Dolakha | Katakuti | 9 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Sailung | 3
4725 | Dolakha | Katakuti | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 80 | 4 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4726 | Dolakha | Katakuti | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 80 | 59 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4727 | Dolakha | Katakuti | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 6 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4728 | Dolakha | Katakuti | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
4729 | Dolakha | Katakuti | 9 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 12 | 0 |  |  |  | Sailung | 3
4730 | Dolakha | Katakuti | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 128 |  |  |  | Sailung | 5
4731 | Dolakha | Khare | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 8
4732 | Dolakha | Khare | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 8
4733 | Dolakha | Khare | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 8
4734 | Dolakha | Khare | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 8
4735 | Dolakha | Khare | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 8
4736 | Dolakha | Khare | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 8
4737 | Dolakha | Khare | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 8
4738 | Dolakha | Khare | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 8
4739 | Dolakha | Khare | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 8
4740 | Dolakha | Khare | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 8
4741 | Dolakha | Khare | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 8
4742 | Dolakha | Khare | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 8
4743 | Dolakha | Khare | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 8
4744 | Dolakha | Khare | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 8
4745 | Dolakha | Khare | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 8
4746 | Dolakha | Khare | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 8
4747 | Dolakha | Khare | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 8
4748 | Dolakha | Khare | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 8
4749 | Dolakha | Khare | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 50 |  |  |  | Gaurishankar | 8
4750 | Dolakha | Khopachagu | 1 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27 |  | Bigu | 8
4751 | Dolakha | Khopachagu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 8
4752 | Dolakha | Khopachagu | 1 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 90 | 90 | 2016-07-28 | 2016-07-30 |  | Bigu | 8
4753 | Dolakha | Khopachagu | 1 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27 |  | Bigu | 8
4754 | Dolakha | Khopachagu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 8
4755 | Dolakha | Khopachagu | 2 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Bigu | 8
4756 | Dolakha | Khopachagu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 8
4757 | Dolakha | Khopachagu | 2 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 37 | 37 | 2016-07-28 | 2016-07-30 |  | Bigu | 8
4758 | Dolakha | Khopachagu | 2 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Bigu | 8
4759 | Dolakha | Khopachagu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 8
4760 | Dolakha | Khopachagu | 3 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 8
4761 | Dolakha | Khopachagu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 8
4762 | Dolakha | Khopachagu | 3 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 12 | 12 | 2016-07-28 | 2016-07-30 |  | Bigu | 8
4763 | Dolakha | Khopachagu | 3 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 8
4764 | Dolakha | Khopachagu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 8
4765 | Dolakha | Khopachagu | 4 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Bigu | 8
4766 | Dolakha | Khopachagu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 8
4767 | Dolakha | Khopachagu | 4 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 24 | 24 | 2016-07-28 | 2016-07-30 |  | Bigu | 8
4768 | Dolakha | Khopachagu | 4 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Bigu | 8
4769 | Dolakha | Khopachagu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 8
4770 | Dolakha | Khopachagu | 5 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27 |  | Bigu | 8
4771 | Dolakha | Khopachagu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 8
4772 | Dolakha | Khopachagu | 5 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 16 | 16 | 2016-07-28 | 2016-07-30 |  | Bigu | 8
4773 | Dolakha | Khopachagu | 5 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27 |  | Bigu | 8
4774 | Dolakha | Khopachagu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 8
4775 | Dolakha | Khopachagu | 6 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 8
4776 | Dolakha | Khopachagu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 8
4777 | Dolakha | Khopachagu | 6 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 25 | 25 | 2016-07-28 | 2016-07-30 |  | Bigu | 8
4778 | Dolakha | Khopachagu | 6 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 8
4779 | Dolakha | Khopachagu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 8
4780 | Dolakha | Khopachagu | 7 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27 |  | Bigu | 8
4781 | Dolakha | Khopachagu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 8
4782 | Dolakha | Khopachagu | 7 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 20 | 20 | 2016-07-28 | 2016-07-30 |  | Bigu | 8
4783 | Dolakha | Khopachagu | 7 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27 |  | Bigu | 8
4784 | Dolakha | Khopachagu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 8
4785 | Dolakha | Khopachagu | 8 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 8
4786 | Dolakha | Khopachagu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 8
4787 | Dolakha | Khopachagu | 8 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 21 | 21 | 2016-07-28 | 2016-07-30 |  | Bigu | 8
4788 | Dolakha | Khopachagu | 8 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 29 | 29 | 2017-04-21 | 2017-04-27 |  | Bigu | 8
4789 | Dolakha | Khopachagu | 8 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 8
4790 | Dolakha | Khopachagu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 8
4791 | Dolakha | Khopachagu | 9 | CA | HURADEC | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 8
4792 | Dolakha | Khopachagu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 8
4793 | Dolakha | Khopachagu | 9 | CA | HURADEC | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 25 | 25 | 2016-07-28 | 2016-07-30 |  | Bigu | 8
4794 | Dolakha | Khopachagu | 9 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Bigu | 8
4795 | Dolakha | Khopachagu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 8
4796 | Dolakha | Laduk | 1 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 109 | 92 | 2016-03-01 | 2016-03-25 |  | Bigu | 4
4797 | Dolakha | Laduk | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 31 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4798 | Dolakha | Laduk | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4799 | Dolakha | Laduk | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 65 | 2 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4800 | Dolakha | Laduk | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 65 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4801 | Dolakha | Laduk | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 109 | 92 | 2016-03-09 | 2016-03-09 |  | Bigu | 4
4802 | Dolakha | Laduk | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 17 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4803 | Dolakha | Laduk | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 8 | 8 | 2017-04-06 | 2017-04-12 |  | Bigu | 4
4804 | Dolakha | Laduk | 1 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 4
4805 | Dolakha | Laduk | 1 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 15 | 15 | 2015-12-14 | 2016-02-15 |  | Bigu | 4
4806 | Dolakha | Laduk | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4807 | Dolakha | Laduk | 2 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 86 | 62 | 2016-03-01 | 2016-03-25 |  | Bigu | 4
4808 | Dolakha | Laduk | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 58 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4809 | Dolakha | Laduk | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4810 | Dolakha | Laduk | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 55 | 3 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4811 | Dolakha | Laduk | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 55 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4812 | Dolakha | Laduk | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 86 | 63 | 2016-03-04 | 2016-03-04 |  | Bigu | 4
4813 | Dolakha | Laduk | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 17 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4814 | Dolakha | Laduk | 2 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 4
4815 | Dolakha | Laduk | 2 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 15 | 15 | 2015-12-14 | 2016-02-15 |  | Bigu | 4
4816 | Dolakha | Laduk | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4817 | Dolakha | Laduk | 3 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 89 | 65 | 2016-03-01 | 2016-03-25 |  | Bigu | 4
4818 | Dolakha | Laduk | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 82 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4819 | Dolakha | Laduk | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4820 | Dolakha | Laduk | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 75 | 4 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4821 | Dolakha | Laduk | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 75 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4822 | Dolakha | Laduk | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 89 | 64 | 2016-03-10 | 2016-03-10 |  | Bigu | 4
4823 | Dolakha | Laduk | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 17 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4824 | Dolakha | Laduk | 3 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15 |  | Bigu | 4
4825 | Dolakha | Laduk | 3 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 15 | 15 | 2015-12-14 | 2016-02-15 |  | Bigu | 4
4826 | Dolakha | Laduk | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4827 | Dolakha | Laduk | 4 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 109 | 81 | 2016-03-01 | 2016-03-25 |  | Bigu | 4
4828 | Dolakha | Laduk | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 161 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4829 | Dolakha | Laduk | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4830 | Dolakha | Laduk | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 60 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4831 | Dolakha | Laduk | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 60 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4832 | Dolakha | Laduk | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 109 | 81 | 2016-03-11 | 2016-03-11 |  | Bigu | 4
4833 | Dolakha | Laduk | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 17 | 2 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4834 | Dolakha | Laduk | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2017-04-06 | 2017-04-12 |  | Bigu | 4
4835 | Dolakha | Laduk | 4 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 4
4836 | Dolakha | Laduk | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4837 | Dolakha | Laduk | 5 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 161 | 128 | 2016-03-01 | 2016-03-25 |  | Bigu | 4
4838 | Dolakha | Laduk | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 203 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4839 | Dolakha | Laduk | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4840 | Dolakha | Laduk | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 50 | 7 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4841 | Dolakha | Laduk | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 50 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4842 | Dolakha | Laduk | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 101 | 130 | 2016-03-03 | 2016-03-03 |  | Bigu | 4
4843 | Dolakha | Laduk | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 17 | 1 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4844 | Dolakha | Laduk | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2017-04-06 | 2017-04-12 |  | Bigu | 4
4845 | Dolakha | Laduk | 5 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 4
4846 | Dolakha | Laduk | 5 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 15 | 14 | 2015-12-14 | 2016-02-15 |  | Bigu | 4
4847 | Dolakha | Laduk | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4848 | Dolakha | Laduk | 6 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 107 | 79 | 2016-03-01 | 2016-03-25 |  | Bigu | 4
4849 | Dolakha | Laduk | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 101 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4850 | Dolakha | Laduk | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4851 | Dolakha | Laduk | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 39 | 2 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4852 | Dolakha | Laduk | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 39 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4853 | Dolakha | Laduk | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 107 | 79 | 2016-03-02 | 2016-03-02 |  | Bigu | 4
4854 | Dolakha | Laduk | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 17 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4855 | Dolakha | Laduk | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2017-04-06 | 2017-04-12 |  | Bigu | 4
4856 | Dolakha | Laduk | 6 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15 |  | Bigu | 4
4857 | Dolakha | Laduk | 6 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 15 | 15 | 2015-12-14 | 2016-02-15 |  | Bigu | 4
4858 | Dolakha | Laduk | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4859 | Dolakha | Laduk | 7 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 215 | 174 | 2016-03-01 | 2016-03-25 |  | Bigu | 4
4860 | Dolakha | Laduk | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 335 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4861 | Dolakha | Laduk | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4862 | Dolakha | Laduk | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 57 | 17 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4863 | Dolakha | Laduk | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 57 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4864 | Dolakha | Laduk | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 215 | 175 | 2016-03-01 | 2016-03-01 |  | Bigu | 4
4865 | Dolakha | Laduk | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 17 | 13 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4866 | Dolakha | Laduk | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2017-04-06 | 2017-04-12 |  | Bigu | 4
4867 | Dolakha | Laduk | 7 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 4
4868 | Dolakha | Laduk | 7 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 15 | 15 | 2015-12-14 | 2016-02-15 |  | Bigu | 4
4869 | Dolakha | Laduk | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4870 | Dolakha | Laduk | 8 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 245 | 160 | 2016-03-01 | 2016-03-25 |  | Bigu | 4
4871 | Dolakha | Laduk | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 241 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4872 | Dolakha | Laduk | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4873 | Dolakha | Laduk | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 77 | 5 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4874 | Dolakha | Laduk | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 77 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4875 | Dolakha | Laduk | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 245 | 159 | 2016-03-14 | 2016-03-15 |  | Bigu | 4
4876 | Dolakha | Laduk | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 17 | 16 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4877 | Dolakha | Laduk | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2017-04-06 | 2017-04-12 |  | Bigu | 4
4878 | Dolakha | Laduk | 8 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 4
4879 | Dolakha | Laduk | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4880 | Dolakha | Laduk | 9 | IOM | IOM | ECHO-JAP-NOR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 115 | 95 | 2016-03-01 | 2016-03-25 |  | Bigu | 4
4881 | Dolakha | Laduk | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 142 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4882 | Dolakha | Laduk | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4883 | Dolakha | Laduk | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 48 | 6 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4884 | Dolakha | Laduk | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 48 | 65 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4885 | Dolakha | Laduk | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 115 | 95 | 2016-03-08 | 2016-03-08 |  | Bigu | 4
4886 | Dolakha | Laduk | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 20 | 5 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4887 | Dolakha | Laduk | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2017-04-06 | 2017-04-12 |  | Bigu | 4
4888 | Dolakha | Laduk | 9 | HELVETAS | CS |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 4
4889 | Dolakha | Laduk | 9 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 15 | 15 | 2015-12-14 | 2016-02-15 |  | Bigu | 4
4890 | Dolakha | Laduk | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 4
4891 | Dolakha | Laduk | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 45 |  |  |  | Bigu | 4
4892 | Dolakha | LakuriDada | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 9
4893 | Dolakha | LakuriDada | 1 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bhimeshwor | 9
4894 | Dolakha | LakuriDada | 1 | SOS | SOS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 Days Mason Training | # of trainees | Yes | Completed | 5 | 5 | 2016-12-11 | 2016-12-21 |  | Bhimeshwor | 9
4895 | Dolakha | LakuriDada | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 9
4896 | Dolakha | LakuriDada | 1 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0 |  |  |  | Bhimeshwor | 9
4897 | Dolakha | LakuriDada | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 9
4898 | Dolakha | LakuriDada | 2 | SOS | SOS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 Days Mason Training | # of trainees | Yes | Completed | 5 | 5 | 2016-12-11 | 2016-12-21 |  | Bhimeshwor | 9
4899 | Dolakha | LakuriDada | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 9
4900 | Dolakha | LakuriDada | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 9
4901 | Dolakha | LakuriDada | 3 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bhimeshwor | 9
4902 | Dolakha | LakuriDada | 3 | SOS | SOS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 Days Mason Training | # of trainees | Yes | Completed | 5 | 5 | 2016-12-11 | 2016-12-21 |  | Bhimeshwor | 9
4903 | Dolakha | LakuriDada | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 9
4904 | Dolakha | LakuriDada | 3 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0 |  |  |  | Bhimeshwor | 9
4905 | Dolakha | LakuriDada | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 9
4906 | Dolakha | LakuriDada | 4 | SOS | SOS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 Days Mason Training | # of trainees | Yes | Completed | 5 | 5 | 2016-12-11 | 2016-12-21 |  | Bhimeshwor | 9
4907 | Dolakha | LakuriDada | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 9
4908 | Dolakha | LakuriDada | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 9
4909 | Dolakha | LakuriDada | 5 | SOS | SOS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 Days Mason Training | # of trainees | Yes | Completed | 5 | 5 | 2016-12-11 | 2016-12-21 |  | Bhimeshwor | 9
4910 | Dolakha | LakuriDada | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 9
4911 | Dolakha | LakuriDada | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 9
4912 | Dolakha | LakuriDada | 6 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bhimeshwor | 9
4913 | Dolakha | LakuriDada | 6 | SOS | SOS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 Days Mason Training | # of trainees | Yes | Completed | 5 | 5 | 2016-12-11 | 2016-12-21 |  | Bhimeshwor | 9
4914 | Dolakha | LakuriDada | 6 | Brot | RRN | Brot | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 19 | 19 | 2017-11-27 | 2017-12-03 |  | Bhimeshwor | 9
4915 | Dolakha | LakuriDada | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 9
4916 | Dolakha | LakuriDada | 6 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0 |  |  |  | Bhimeshwor | 9
4917 | Dolakha | LakuriDada | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 9
4918 | Dolakha | LakuriDada | 7 | SOS | SOS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 Days Mason Training | # of trainees | Yes | Completed | 5 | 5 | 2016-12-11 | 2016-12-21 |  | Bhimeshwor | 9
4919 | Dolakha | LakuriDada | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 9
4920 | Dolakha | LakuriDada | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 9
4921 | Dolakha | LakuriDada | 8 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bhimeshwor | 9
4922 | Dolakha | LakuriDada | 8 | SOS | SOS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 Days Mason Training | # of trainees | Yes | Completed | 5 | 3 | 2016-12-11 | 2016-12-21 |  | Bhimeshwor | 9
4923 | Dolakha | LakuriDada | 8 | Brot | RRN | Brot | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 38 | 38 | 2017-11-06 | 2017-11-12 |  | Bhimeshwor | 9
4924 | Dolakha | LakuriDada | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 9
4925 | Dolakha | LakuriDada | 8 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 12 | 0 |  |  |  | Bhimeshwor | 9
4926 | Dolakha | LakuriDada | 9 | SOS | SOS |  | Reconstruction through contractors | Construction | Private house | Constructing houses for households | # of constructions | Yes | Ongoing | 108 | 95 | 2017-03-17 |  |  | Bhimeshwor | 9
4927 | Dolakha | LakuriDada | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 9
4928 | Dolakha | LakuriDada | 9 | SOS | SOS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 Days Mason Training | # of trainees | Yes | Completed | 5 | 2 | 2016-12-11 | 2016-12-21 |  | Bhimeshwor | 9
4929 | Dolakha | LakuriDada | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 9
4930 | Dolakha | LakuriDada | ALL | UNHABITAT |  |  | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 37 |  |  |  | Bhimeshwor | 9
4931 | Dolakha | LakuriDada | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 176 |  |  |  | Bhimeshwor | 9
4932 | Dolakha | Lamabagar | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 1
4933 | Dolakha | Lamabagar | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 1
4934 | Dolakha | Lamabagar | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 1
4935 | Dolakha | Lamabagar | 2 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 7 | 2015-12-14 | 2016-02-15 |  | Bigu | 1
4936 | Dolakha | Lamabagar | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 1
4937 | Dolakha | Lamabagar | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 1
4938 | Dolakha | Lamabagar | 3 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 8 | 2015-12-14 | 2016-02-15 |  | Bigu | 1
4939 | Dolakha | Lamabagar | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 1
4940 | Dolakha | Lamabagar | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 1
4941 | Dolakha | Lamabagar | 4 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 4 | 4 | 2015-12-14 | 2016-02-15 |  | Bigu | 1
4942 | Dolakha | Lamabagar | 4 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 8 | 2015-12-14 | 2016-02-15 |  | Bigu | 1
4943 | Dolakha | Lamabagar | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 1
4944 | Dolakha | Lamabagar | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 1
4945 | Dolakha | Lamabagar | 5 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 4 | 4 | 2015-12-14 | 2016-02-15 |  | Bigu | 1
4946 | Dolakha | Lamabagar | 5 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 8 | 2015-12-14 | 2016-02-15 |  | Bigu | 1
4947 | Dolakha | Lamabagar | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 1
4948 | Dolakha | Lamabagar | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 1
4949 | Dolakha | Lamabagar | 6 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 4 | 4 | 2015-12-14 | 2016-02-15 |  | Bigu | 1
4950 | Dolakha | Lamabagar | 6 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 7 | 2015-12-14 | 2016-02-15 |  | Bigu | 1
4951 | Dolakha | Lamabagar | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 1
4952 | Dolakha | Lamabagar | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 1
4953 | Dolakha | Lamabagar | 7 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 8 | 2015-12-14 | 2016-02-15 |  | Bigu | 1
4954 | Dolakha | Lamabagar | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 1
4955 | Dolakha | Lamabagar | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 1
4956 | Dolakha | Lamabagar | 8 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 4 | 4 | 2015-12-14 | 2016-02-15 |  | Bigu | 1
4957 | Dolakha | Lamabagar | 8 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 7 | 2015-12-14 | 2016-02-15 |  | Bigu | 1
4958 | Dolakha | Lamabagar | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 1
4959 | Dolakha | Lamabagar | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 1
4960 | Dolakha | Lamabagar | 9 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 4 | 4 | 2015-12-14 | 2016-02-15 |  | Bigu | 1
4961 | Dolakha | Lamabagar | 9 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 7 | 2015-12-14 | 2016-02-15 |  | Bigu | 1
4962 | Dolakha | Lamabagar | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 1
4963 | Dolakha | Lamidada | 1 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 4
4964 | Dolakha | Lamidada | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 34 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4965 | Dolakha | Lamidada | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4966 | Dolakha | Lamidada | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 85 | 16 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4967 | Dolakha | Lamidada | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 85 | 65 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4968 | Dolakha | Lamidada | 1 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 4
4969 | Dolakha | Lamidada | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 3 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4970 | Dolakha | Lamidada | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4971 | Dolakha | Lamidada | 2 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 4
4972 | Dolakha | Lamidada | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 89 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4973 | Dolakha | Lamidada | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4974 | Dolakha | Lamidada | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 73 | 15 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4975 | Dolakha | Lamidada | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 73 | 65 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4976 | Dolakha | Lamidada | 2 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 4
4977 | Dolakha | Lamidada | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 17 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4978 | Dolakha | Lamidada | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4979 | Dolakha | Lamidada | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 165 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4980 | Dolakha | Lamidada | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4981 | Dolakha | Lamidada | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 61 | 27 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4982 | Dolakha | Lamidada | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 61 | 65 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4983 | Dolakha | Lamidada | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 4 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4984 | Dolakha | Lamidada | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4985 | Dolakha | Lamidada | 4 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 4
4986 | Dolakha | Lamidada | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 196 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4987 | Dolakha | Lamidada | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4988 | Dolakha | Lamidada | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 198 | 26 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4989 | Dolakha | Lamidada | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 198 | 65 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4990 | Dolakha | Lamidada | 4 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 4
4991 | Dolakha | Lamidada | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 8 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4992 | Dolakha | Lamidada | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4993 | Dolakha | Lamidada | 5 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 4
4994 | Dolakha | Lamidada | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 317 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4995 | Dolakha | Lamidada | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4996 | Dolakha | Lamidada | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 124 | 34 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4997 | Dolakha | Lamidada | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 124 | 65 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
4998 | Dolakha | Lamidada | 5 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 4
4999 | Dolakha | Lamidada | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 9 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
5000 | Dolakha | Lamidada | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 4
5001 | Dolakha | Lamidada | 6 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 3
5002 | Dolakha | Lamidada | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 234 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5003 | Dolakha | Lamidada | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5004 | Dolakha | Lamidada | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 162 | 10 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5005 | Dolakha | Lamidada | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 162 | 65 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5006 | Dolakha | Lamidada | 6 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 3
5007 | Dolakha | Lamidada | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 3 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5008 | Dolakha | Lamidada | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5009 | Dolakha | Lamidada | 7 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 3
5010 | Dolakha | Lamidada | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 151 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5011 | Dolakha | Lamidada | 7 | CA | CEEPAARD | CA | Technical Assistance | Demonstration Construction | House | Single room demo house built with mud, stone and timber | # of constructions | Yes | Planned | 1 | 0 | 2016-12-01 |  |  | Kalinchok | 3
5012 | Dolakha | Lamidada | 7 | CA | CEEPAARD |  | Technical Assistance | Demonstration Construction | House | Construction of Demo house | # of constructions | Yes | Completed | 1 | 1 | 2016-10-31 | 2017-02-15 |  | Kalinchok | 3
5013 | Dolakha | Lamidada | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5014 | Dolakha | Lamidada | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 138 | 21 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5015 | Dolakha | Lamidada | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 138 | 65 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5016 | Dolakha | Lamidada | 7 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 3
5017 | Dolakha | Lamidada | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 3 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5018 | Dolakha | Lamidada | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5019 | Dolakha | Lamidada | 8 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 3
5020 | Dolakha | Lamidada | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 156 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5021 | Dolakha | Lamidada | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5022 | Dolakha | Lamidada | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 215 | 13 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5023 | Dolakha | Lamidada | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 215 | 65 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5024 | Dolakha | Lamidada | 8 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 3
5025 | Dolakha | Lamidada | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 8 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5026 | Dolakha | Lamidada | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5027 | Dolakha | Lamidada | 9 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 3
5028 | Dolakha | Lamidada | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 196 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5029 | Dolakha | Lamidada | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5030 | Dolakha | Lamidada | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 187 | 28 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5031 | Dolakha | Lamidada | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 187 | 65 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5032 | Dolakha | Lamidada | 9 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 3
5033 | Dolakha | Lamidada | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 3 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5034 | Dolakha | Lamidada | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 3
5035 | Dolakha | Lamidada | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 54 |  |  |  | Kalinchok | 4
5036 | Dolakha | Lapilang | 1 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 5
5037 | Dolakha | Lapilang | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 5
5038 | Dolakha | Lapilang | 1 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 5
5039 | Dolakha | Lapilang | 1 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 2 | 2 | 2017-02-22 | 2017-03-27 |  | Kalinchok | 5
5040 | Dolakha | Lapilang | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 5
5041 | Dolakha | Lapilang | 2 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 5
5042 | Dolakha | Lapilang | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 5
5043 | Dolakha | Lapilang | 2 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 5
5044 | Dolakha | Lapilang | 2 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 2 | 2 | 2017-02-22 | 2017-03-27 |  | Kalinchok | 5
5045 | Dolakha | Lapilang | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 5
5046 | Dolakha | Lapilang | 3 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 5
5047 | Dolakha | Lapilang | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 5
5048 | Dolakha | Lapilang | 3 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 5
5049 | Dolakha | Lapilang | 3 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 2 | 2 | 2017-02-22 | 2017-03-27 |  | Kalinchok | 5
5050 | Dolakha | Lapilang | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 5
5051 | Dolakha | Lapilang | 4 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 5
5052 | Dolakha | Lapilang | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 5
5053 | Dolakha | Lapilang | 4 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 5
5054 | Dolakha | Lapilang | 4 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 2 | 2 | 2017-02-22 | 2017-03-27 |  | Kalinchok | 5
5055 | Dolakha | Lapilang | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 5
5056 | Dolakha | Lapilang | 5 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 6
5057 | Dolakha | Lapilang | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 6
5058 | Dolakha | Lapilang | 5 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 6
5059 | Dolakha | Lapilang | 5 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 2 | 2 | 2017-02-22 | 2017-03-27 |  | Kalinchok | 6
5060 | Dolakha | Lapilang | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 6
5061 | Dolakha | Lapilang | 6 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 6
5062 | Dolakha | Lapilang | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 6
5063 | Dolakha | Lapilang | 6 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 6
5064 | Dolakha | Lapilang | 6 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 2 | 2 | 2017-02-22 | 2017-03-27 |  | Kalinchok | 6
5065 | Dolakha | Lapilang | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 6
5066 | Dolakha | Lapilang | 7 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 6
5067 | Dolakha | Lapilang | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 6
5068 | Dolakha | Lapilang | 7 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 6
5069 | Dolakha | Lapilang | 7 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 1 | 1 | 2017-02-22 | 2017-03-27 |  | Kalinchok | 6
5070 | Dolakha | Lapilang | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 6
5071 | Dolakha | Lapilang | 8 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 6
5072 | Dolakha | Lapilang | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 6
5073 | Dolakha | Lapilang | 8 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 6
5074 | Dolakha | Lapilang | 8 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 1 | 1 | 2017-02-22 | 2017-03-27 |  | Kalinchok | 6
5075 | Dolakha | Lapilang | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 6
5076 | Dolakha | Lapilang | 9 | CA | CEEPAARD | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Set of toolkit of cost NPR 300 | # of kits | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 6
5077 | Dolakha | Lapilang | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 6
5078 | Dolakha | Lapilang | 9 | CA | CEEPAARD | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2016-10-21 | 2016-10-27 |  | Kalinchok | 6
5079 | Dolakha | Lapilang | 9 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 1 | 1 | 2017-02-22 | 2017-03-27 |  | Kalinchok | 6
5080 | Dolakha | Lapilang | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 6
5081 | Dolakha | Lapilang | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 52 |  |  |  | Kalinchok | 6
5082 | Dolakha | Magapauwa | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 336 | 295 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
5083 | Dolakha | Magapauwa | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
5084 | Dolakha | Magapauwa | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 88 | 18 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
5085 | Dolakha | Magapauwa | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 88 | 69 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
5086 | Dolakha | Magapauwa | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 5 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
5087 | Dolakha | Magapauwa | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Sailung | 3
5088 | Dolakha | Magapauwa | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 336 | 193 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5089 | Dolakha | Magapauwa | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5090 | Dolakha | Magapauwa | 2 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Sailung | 4
5091 | Dolakha | Magapauwa | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 103 | 18 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5092 | Dolakha | Magapauwa | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 103 | 61 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5093 | Dolakha | Magapauwa | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 15 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5094 | Dolakha | Magapauwa | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5095 | Dolakha | Magapauwa | 2 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0 |  |  |  | Sailung | 4
5096 | Dolakha | Magapauwa | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 336 | 81 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5097 | Dolakha | Magapauwa | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5098 | Dolakha | Magapauwa | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 161 | 10 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5099 | Dolakha | Magapauwa | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 161 | 61 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5100 | Dolakha | Magapauwa | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 8 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5101 | Dolakha | Magapauwa | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5102 | Dolakha | Magapauwa | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 336 | 96 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5103 | Dolakha | Magapauwa | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5104 | Dolakha | Magapauwa | 4 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Sailung | 4
5105 | Dolakha | Magapauwa | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 151 | 17 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5106 | Dolakha | Magapauwa | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 151 | 61 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5107 | Dolakha | Magapauwa | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 4 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5108 | Dolakha | Magapauwa | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5109 | Dolakha | Magapauwa | 4 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0 |  |  |  | Sailung | 4
5110 | Dolakha | Magapauwa | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 336 | 69 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5111 | Dolakha | Magapauwa | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5112 | Dolakha | Magapauwa | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 260 | 24 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5113 | Dolakha | Magapauwa | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 260 | 61 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5114 | Dolakha | Magapauwa | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 6 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5115 | Dolakha | Magapauwa | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5116 | Dolakha | Magapauwa | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 336 | 45 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5117 | Dolakha | Magapauwa | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5118 | Dolakha | Magapauwa | 6 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Sailung | 4
5119 | Dolakha | Magapauwa | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 171 | 8 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5120 | Dolakha | Magapauwa | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 171 | 61 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5121 | Dolakha | Magapauwa | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 7 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5122 | Dolakha | Magapauwa | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5123 | Dolakha | Magapauwa | 6 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 11 | 0 |  |  |  | Sailung | 4
5124 | Dolakha | Magapauwa | 7 | CARITAS-L | Pourakhi |  | Technical Assistance | Community reconstruction orientation | 1 session | First Orientation | # of participants | Yes | Completed | 37 | 37 | 2017-01-14 | 2017-01-14 |  | Sailung | 4
5125 | Dolakha | Magapauwa | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 336 | 59 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5126 | Dolakha | Magapauwa | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5127 | Dolakha | Magapauwa | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 133 | 22 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5128 | Dolakha | Magapauwa | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 133 | 61 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5129 | Dolakha | Magapauwa | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 12 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5130 | Dolakha | Magapauwa | 7 | CARITAS-L | Pourakhi |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 7 | 7 | 2016-11-16 | 2016-12-16 |  | Sailung | 4
5131 | Dolakha | Magapauwa | 7 | CARITAS-L | Pourakhi |  | Training | Vocational training | Carpenter (CTEVT) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 4 | 4 | 2016-11-16 | 2016-12-16 |  | Sailung | 4
5132 | Dolakha | Magapauwa | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5133 | Dolakha | Magapauwa | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 27 | 27 | 2017-06-27 | 2017-07-01 |  | Sailung | 4
5134 | Dolakha | Magapauwa | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 336 | 66 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5135 | Dolakha | Magapauwa | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5136 | Dolakha | Magapauwa | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 97 | 10 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5137 | Dolakha | Magapauwa | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 97 | 61 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5138 | Dolakha | Magapauwa | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 8 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5139 | Dolakha | Magapauwa | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5140 | Dolakha | Magapauwa | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 336 | 32 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5141 | Dolakha | Magapauwa | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5142 | Dolakha | Magapauwa | 9 | UNDP | UNDP | ECHO | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Sailung | 4
5143 | Dolakha | Magapauwa | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 106 | 11 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5144 | Dolakha | Magapauwa | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 106 | 68 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5145 | Dolakha | Magapauwa | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 6 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5146 | Dolakha | Magapauwa | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 4
5147 | Dolakha | Magapauwa | 9 | UNDP | UNDP | ECHO | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days Training CTEVT | # of trainees | Yes | Planned | 12 | 0 |  |  |  | Sailung | 4
5148 | Dolakha | Magapauwa | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 46 |  |  |  | Sailung | 4
5149 | Dolakha | Malu | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 193 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5150 | Dolakha | Malu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5151 | Dolakha | Malu | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 157 | 21 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5152 | Dolakha | Malu | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 157 | 41 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5153 | Dolakha | Malu | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 8 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5154 | Dolakha | Malu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5155 | Dolakha | Malu | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 105 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5156 | Dolakha | Malu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5157 | Dolakha | Malu | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 147 | 9 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5158 | Dolakha | Malu | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 147 | 41 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5159 | Dolakha | Malu | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 7 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5160 | Dolakha | Malu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5161 | Dolakha | Malu | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 138 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5162 | Dolakha | Malu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5163 | Dolakha | Malu | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 223 | 12 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5164 | Dolakha | Malu | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 223 | 41 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5165 | Dolakha | Malu | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 5 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5166 | Dolakha | Malu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5167 | Dolakha | Malu | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 106 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5168 | Dolakha | Malu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5169 | Dolakha | Malu | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 160 | 7 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5170 | Dolakha | Malu | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 160 | 41 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5171 | Dolakha | Malu | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 8 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5172 | Dolakha | Malu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5173 | Dolakha | Malu | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 246 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5174 | Dolakha | Malu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5175 | Dolakha | Malu | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 225 | 7 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5176 | Dolakha | Malu | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 225 | 41 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5177 | Dolakha | Malu | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 4 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5178 | Dolakha | Malu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5179 | Dolakha | Malu | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 79 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5180 | Dolakha | Malu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5181 | Dolakha | Malu | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 107 | 12 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5182 | Dolakha | Malu | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 107 | 41 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5183 | Dolakha | Malu | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 10 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5184 | Dolakha | Malu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5185 | Dolakha | Malu | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 77 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5186 | Dolakha | Malu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5187 | Dolakha | Malu | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 115 | 13 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5188 | Dolakha | Malu | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 115 | 41 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5189 | Dolakha | Malu | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 2 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5190 | Dolakha | Malu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5191 | Dolakha | Malu | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 118 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5192 | Dolakha | Malu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5193 | Dolakha | Malu | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 155 | 1 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5194 | Dolakha | Malu | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 155 | 41 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5195 | Dolakha | Malu | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 6 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5196 | Dolakha | Malu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5197 | Dolakha | Malu | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 420 | 137 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5198 | Dolakha | Malu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5199 | Dolakha | Malu | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 124 | 5 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5200 | Dolakha | Malu | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 124 | 41 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5201 | Dolakha | Malu | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 10 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5202 | Dolakha | Malu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 4
5203 | Dolakha | Malu | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 47 |  |  |  | Tamakoshi | 4
5204 | Dolakha | Marbu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 7
5205 | Dolakha | Marbu | 1 | HELVETAS | KITE |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5206 | Dolakha | Marbu | 1 | HELVETAS | KITE |  | Training | Vocational training | Electrician (CTEVT) | 50 Days training for fresh Electricians | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5207 | Dolakha | Marbu | 1 | HELVETAS | KITE |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 8 | 8 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5208 | Dolakha | Marbu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 7
5209 | Dolakha | Marbu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 7
5210 | Dolakha | Marbu | 2 | HELVETAS | KITE |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5211 | Dolakha | Marbu | 2 | HELVETAS | KITE |  | Training | Vocational training | Electrician (CTEVT) | 50 Days training for fresh Electricians | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5212 | Dolakha | Marbu | 2 | HELVETAS | KITE |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 8 | 7 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5213 | Dolakha | Marbu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 7
5214 | Dolakha | Marbu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 7
5215 | Dolakha | Marbu | 3 | HELVETAS | KITE |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5216 | Dolakha | Marbu | 3 | HELVETAS | KITE |  | Training | Vocational training | Electrician (CTEVT) | 50 Days training for fresh Electricians | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5217 | Dolakha | Marbu | 3 | HELVETAS | KITE |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 7 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5218 | Dolakha | Marbu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 7
5219 | Dolakha | Marbu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 7
5220 | Dolakha | Marbu | 4 | HELVETAS | KITE |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5221 | Dolakha | Marbu | 4 | HELVETAS | KITE |  | Training | Vocational training | Electrician (CTEVT) | 50 Days training for fresh Electricians | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5222 | Dolakha | Marbu | 4 | HELVETAS | KITE |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 8 | 8 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5223 | Dolakha | Marbu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 7
5224 | Dolakha | Marbu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 7
5225 | Dolakha | Marbu | 5 | HELVETAS | KITE |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 3 | 2 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5226 | Dolakha | Marbu | 5 | HELVETAS | KITE |  | Training | Vocational training | Electrician (CTEVT) | 50 Days training for fresh Electricians | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5227 | Dolakha | Marbu | 5 | HELVETAS | KITE |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 8 | 7 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5228 | Dolakha | Marbu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 7
5229 | Dolakha | Marbu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 7
5230 | Dolakha | Marbu | 6 | HELVETAS | KITE |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5231 | Dolakha | Marbu | 6 | HELVETAS | KITE |  | Training | Vocational training | Electrician (CTEVT) | 50 Days training for fresh Electricians | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5232 | Dolakha | Marbu | 6 | HELVETAS | KITE |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 8 | 7 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5233 | Dolakha | Marbu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 7
5234 | Dolakha | Marbu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 7
5235 | Dolakha | Marbu | 7 | HELVETAS | KITE |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5236 | Dolakha | Marbu | 7 | HELVETAS | KITE |  | Training | Vocational training | Electrician (CTEVT) | 50 Days training for fresh Electricians | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5237 | Dolakha | Marbu | 7 | HELVETAS | KITE |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 7 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5238 | Dolakha | Marbu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 7
5239 | Dolakha | Marbu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 7
5240 | Dolakha | Marbu | 8 | HELVETAS | KITE |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5241 | Dolakha | Marbu | 8 | HELVETAS | KITE |  | Training | Vocational training | Electrician (CTEVT) | 50 Days training for fresh Electricians | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5242 | Dolakha | Marbu | 8 | HELVETAS | KITE |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 8 | 7 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5243 | Dolakha | Marbu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 7
5244 | Dolakha | Marbu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 7
5245 | Dolakha | Marbu | 9 | HELVETAS | KITE |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5246 | Dolakha | Marbu | 9 | HELVETAS | KITE |  | Training | Vocational training | Electrician (CTEVT) | 50 Days training for fresh Electricians | # of trainees | Yes | Completed | 1 | 1 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5247 | Dolakha | Marbu | 9 | HELVETAS | KITE |  | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 7 | 7 | 2015-12-14 | 2016-02-15 |  | Gaurishankar | 7
5248 | Dolakha | Marbu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 7
5249 | Dolakha | Melung | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 7
5250 | Dolakha | Melung | 1 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Melung | 7
5251 | Dolakha | Melung | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 7
5252 | Dolakha | Melung | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 7
5253 | Dolakha | Melung | 2 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Melung | 7
5254 | Dolakha | Melung | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 7
5255 | Dolakha | Melung | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 7
5256 | Dolakha | Melung | 3 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Melung | 7
5257 | Dolakha | Melung | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 7
5258 | Dolakha | Melung | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 7
5259 | Dolakha | Melung | 4 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-04-30 | 2017-05-06 |  | Melung | 7
5260 | Dolakha | Melung | 4 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Melung | 7
5261 | Dolakha | Melung | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 7
5262 | Dolakha | Melung | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 7
5263 | Dolakha | Melung | 5 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-30 | 2017-05-06 |  | Melung | 7
5264 | Dolakha | Melung | 5 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Melung | 7
5265 | Dolakha | Melung | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 7
5266 | Dolakha | Melung | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 6
5267 | Dolakha | Melung | 6 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2017-04-30 | 2017-05-06 |  | Melung | 6
5268 | Dolakha | Melung | 6 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Melung | 6
5269 | Dolakha | Melung | 6 | MC | REDC | MC | Training | ToT | Skilled masons |  | # of trainees | Yes | Completed | 28 | 28 | 2016-09-25 | 2016-10-01 |  | Melung | 6
5270 | Dolakha | Melung | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 6
5271 | Dolakha | Melung | 6 | CW | ECARDS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 12 | 11 | 2016-11-19 | 2016-11-25 |  | Melung | 6
5272 | Dolakha | Melung | 6 | AA | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 17 | 17 | 2016-11-18 | 2016-11-24 |  | Melung | 6
5273 | Dolakha | Melung | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 7
5274 | Dolakha | Melung | 7 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2017-04-30 | 2017-05-06 |  | Melung | 7
5275 | Dolakha | Melung | 7 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Melung | 7
5276 | Dolakha | Melung | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 7
5277 | Dolakha | Melung | 7 | CW | ECARDS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 12 | 12 | 2016-11-19 | 2016-11-25 |  | Melung | 7
5278 | Dolakha | Melung | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 6
5279 | Dolakha | Melung | 8 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Melung | 6
5280 | Dolakha | Melung | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 6
5281 | Dolakha | Melung | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 6
5282 | Dolakha | Melung | 9 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Melung | 6
5283 | Dolakha | Melung | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 6
5284 | Dolakha | Mirge | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 2
5285 | Dolakha | Mirge | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 2
5286 | Dolakha | Mirge | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 3
5287 | Dolakha | Mirge | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 3
5288 | Dolakha | Mirge | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 3
5289 | Dolakha | Mirge | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 3
5290 | Dolakha | Mirge | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 3
5291 | Dolakha | Mirge | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 3
5292 | Dolakha | Mirge | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 3
5293 | Dolakha | Mirge | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 3
5294 | Dolakha | Mirge | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 3
5295 | Dolakha | Mirge | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 3
5296 | Dolakha | Mirge | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 3
5297 | Dolakha | Mirge | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 3
5298 | Dolakha | Mirge | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 3
5299 | Dolakha | Mirge | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 3
5300 | Dolakha | Mirge | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 3
5301 | Dolakha | Mirge | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 3
5302 | Dolakha | Mirge | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 22 |  |  |  | Baiteshwor | 3
5303 | Dolakha | Namdu | 1 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 24 | 24 | 2016-05-04 | 2016-05-26 |  | Baiteshwor | 6
5304 | Dolakha | Namdu | 1 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Ongoing | 24 | 21 | 2017-02-03 | 2017-02-03 |  | Baiteshwor | 6
5305 | Dolakha | Namdu | 1 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 24 | 11 | 2017-03-21 | 2017-03-21 |  | Baiteshwor | 6
5306 | Dolakha | Namdu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 6
5307 | Dolakha | Namdu | 1 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 10 | 10 | 2016-05-04 | 2016-05-26 | 4-10 May First Session, 12-18 May Second Session, 20-26 Third Session | Baiteshwor | 6
5308 | Dolakha | Namdu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 6
5309 | Dolakha | Namdu | 1 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 9 | 9 | 2017-05-07 | 2017-06-14 |  | Baiteshwor | 6
5310 | Dolakha | Namdu | 2 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 24 | 24 | 2016-05-04 | 2016-05-26 |  | Baiteshwor | 6
5311 | Dolakha | Namdu | 2 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Ongoing | 24 | 20 | 2017-02-03 | 2017-02-03 |  | Baiteshwor | 6
5312 | Dolakha | Namdu | 2 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 24 | 14 | 2017-03-21 | 2017-03-21 |  | Baiteshwor | 6
5313 | Dolakha | Namdu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 6
5314 | Dolakha | Namdu | 2 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2016-05-04 | 2016-05-26 |  | Baiteshwor | 6
5315 | Dolakha | Namdu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 6
5316 | Dolakha | Namdu | 2 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2017-05-07 | 2017-06-14 |  | Baiteshwor | 6
5317 | Dolakha | Namdu | 3 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 28 | 28 | 2016-05-04 | 2016-05-26 |  | Baiteshwor | 6
5318 | Dolakha | Namdu | 3 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Ongoing | 28 | 21 | 2017-02-03 | 2017-02-03 |  | Baiteshwor | 6
5319 | Dolakha | Namdu | 3 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 28 | 5 | 2017-03-21 | 2017-03-21 |  | Baiteshwor | 6
5320 | Dolakha | Namdu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 6
5321 | Dolakha | Namdu | 3 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 10 | 10 | 2016-05-04 | 2016-05-26 |  | Baiteshwor | 6
5322 | Dolakha | Namdu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 6
5323 | Dolakha | Namdu | 3 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2017-05-07 | 2017-06-14 |  | Baiteshwor | 6
5324 | Dolakha | Namdu | 4 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 22 | 22 | 2016-05-04 | 2016-05-26 |  | Baiteshwor | 6
5325 | Dolakha | Namdu | 4 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Ongoing | 22 | 15 | 2017-02-03 | 2017-02-03 |  | Baiteshwor | 6
5326 | Dolakha | Namdu | 4 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 22 | 7 | 2017-03-21 | 2017-03-21 |  | Baiteshwor | 6
5327 | Dolakha | Namdu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 6
5328 | Dolakha | Namdu | 4 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 11 | 11 | 2016-05-04 | 2016-05-26 |  | Baiteshwor | 6
5329 | Dolakha | Namdu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 6
5330 | Dolakha | Namdu | 4 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2017-05-07 | 2017-06-14 |  | Baiteshwor | 6
5331 | Dolakha | Namdu | 5 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 22 | 22 | 2016-05-04 | 2016-05-26 |  | Baiteshwor | 7
5332 | Dolakha | Namdu | 5 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Ongoing | 22 | 13 | 2017-02-03 | 2017-02-03 |  | Baiteshwor | 7
5333 | Dolakha | Namdu | 5 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 22 | 12 | 2017-03-21 | 2017-03-21 |  | Baiteshwor | 7
5334 | Dolakha | Namdu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 7
5335 | Dolakha | Namdu | 5 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 14 | 14 | 2016-05-04 | 2016-05-26 |  | Baiteshwor | 7
5336 | Dolakha | Namdu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 7
5337 | Dolakha | Namdu | 5 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-05-07 | 2017-06-14 |  | Baiteshwor | 7
5338 | Dolakha | Namdu | 6 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 24 | 24 | 2016-05-04 | 2016-05-26 |  | Baiteshwor | 7
5339 | Dolakha | Namdu | 6 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Ongoing | 24 | 20 | 2017-02-03 | 2017-02-03 |  | Baiteshwor | 7
5340 | Dolakha | Namdu | 6 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 24 | 13 | 2017-03-21 | 2017-03-21 |  | Baiteshwor | 7
5341 | Dolakha | Namdu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 7
5342 | Dolakha | Namdu | 6 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 8 | 8 | 2016-05-04 | 2016-05-26 |  | Baiteshwor | 7
5343 | Dolakha | Namdu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 7
5344 | Dolakha | Namdu | 6 | SEEDS | REDC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 50 | 0 | 2017-11-01 |  |  | Baiteshwor | 7
5345 | Dolakha | Namdu | 7 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 22 | 22 | 2016-05-04 | 2016-05-26 |  | Baiteshwor | 6
5346 | Dolakha | Namdu | 7 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Ongoing | 22 | 21 | 2017-02-03 | 2017-02-03 |  | Baiteshwor | 6
5347 | Dolakha | Namdu | 7 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 22 | 4 | 2017-03-21 | 2017-03-21 |  | Baiteshwor | 6
5348 | Dolakha | Namdu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 6
5349 | Dolakha | Namdu | 7 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 10 | 10 | 2016-05-04 | 2016-05-26 |  | Baiteshwor | 6
5350 | Dolakha | Namdu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 6
5351 | Dolakha | Namdu | 7 | SCI | RDTA |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2017-05-07 | 2017-06-14 |  | Baiteshwor | 6
5352 | Dolakha | Namdu | 7 | SEEDS | REDC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 50 | 0 | 2017-11-01 |  |  | Baiteshwor | 6
5353 | Dolakha | Namdu | 8 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 12 | 12 | 2016-05-04 | 2016-05-26 |  | Baiteshwor | 7
5354 | Dolakha | Namdu | 8 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Ongoing | 12 | 11 | 2017-02-03 | 2017-02-03 |  | Baiteshwor | 7
5355 | Dolakha | Namdu | 8 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 12 | 8 | 2017-03-21 | 2017-03-21 |  | Baiteshwor | 7
5356 | Dolakha | Namdu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 7
5357 | Dolakha | Namdu | 8 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 14 | 14 | 2016-05-04 | 2016-05-26 |  | Baiteshwor | 7
5358 | Dolakha | Namdu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 7
5359 | Dolakha | Namdu | 9 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Completed | 22 | 22 | 2016-05-04 | 2016-05-26 |  | Baiteshwor | 7
5360 | Dolakha | Namdu | 9 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Ongoing | 22 | 19 | 2017-02-03 | 2017-02-03 |  | Baiteshwor | 7
5361 | Dolakha | Namdu | 9 | SCI | RDTA |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 22 | 13 | 2017-03-21 | 2017-03-21 |  | Baiteshwor | 7
5362 | Dolakha | Namdu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 7
5363 | Dolakha | Namdu | 9 | SCI | RDTA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 10 | 10 | 2016-05-04 | 2016-05-26 |  | Baiteshwor | 7
5364 | Dolakha | Namdu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Baiteshwor | 7
5365 | Dolakha | Namdu | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 138 |  |  |  | Baiteshwor | 6
5366 | Dolakha | Orang | 1 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 70 | 70 | 2016-08-29 | 2017-08-21 |  | Bigu | 2
5367 | Dolakha | Orang | 1 | CARITAS-N | CARITAS-N | CARITAS-N | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-09-08 |  |  | Bigu | 2
5368 | Dolakha | Orang | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 2
5369 | Dolakha | Orang | 1 | CARITAS-N | CARITAS-N | CARITAS-N | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-12-13 | 2017-12-19 |  | Bigu | 2
5370 | Dolakha | Orang | 1 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 2
5371 | Dolakha | Orang | 1 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15 |  | Bigu | 2
5372 | Dolakha | Orang | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 2
5373 | Dolakha | Orang | 2 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 52 | 52 | 2016-08-29 | 2017-08-21 |  | Bigu | 2
5374 | Dolakha | Orang | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 2
5375 | Dolakha | Orang | 2 | CARITAS-N | CARITAS-N | CARITAS-N | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-12-13 | 2017-12-19 |  | Bigu | 2
5376 | Dolakha | Orang | 2 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 2
5377 | Dolakha | Orang | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 2
5378 | Dolakha | Orang | 3 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 50 | 50 | 2016-08-29 | 2017-08-21 |  | Bigu | 2
5379 | Dolakha | Orang | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 2
5380 | Dolakha | Orang | 3 | CARITAS-N | CARITAS-N | CARITAS-N | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 7 | 7 | 2017-12-13 | 2017-12-19 |  | Bigu | 2
5381 | Dolakha | Orang | 3 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 2
5382 | Dolakha | Orang | 3 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15 |  | Bigu | 2
5383 | Dolakha | Orang | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 2
5384 | Dolakha | Orang | 4 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 60 | 60 | 2016-08-29 | 2017-08-21 |  | Bigu | 2
5385 | Dolakha | Orang | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 2
5386 | Dolakha | Orang | 4 | CARITAS-N | CARITAS-N | CARITAS-N | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 7 | 7 | 2017-12-13 | 2017-12-19 |  | Bigu | 2
5387 | Dolakha | Orang | 4 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 2
5388 | Dolakha | Orang | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 2
5389 | Dolakha | Orang | 5 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 75 | 75 | 2016-08-29 | 2017-08-21 |  | Bigu | 2
5390 | Dolakha | Orang | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 2
5391 | Dolakha | Orang | 5 | CARITAS-N | CARITAS-N | CARITAS-N | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-12-13 | 2017-12-19 |  | Bigu | 2
5392 | Dolakha | Orang | 5 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 2
5393 | Dolakha | Orang | 5 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15 |  | Bigu | 2
5394 | Dolakha | Orang | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 2
5395 | Dolakha | Orang | 6 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 48 | 48 | 2016-08-29 | 2017-08-21 |  | Bigu | 2
5396 | Dolakha | Orang | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 2
5397 | Dolakha | Orang | 6 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 2
5398 | Dolakha | Orang | 6 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15 |  | Bigu | 2
5399 | Dolakha | Orang | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 2
5400 | Dolakha | Orang | 7 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 86 | 86 | 2016-08-29 | 2017-08-21 |  | Bigu | 2
5401 | Dolakha | Orang | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 2
5402 | Dolakha | Orang | 7 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 2 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 2
5403 | Dolakha | Orang | 7 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15 |  | Bigu | 2
5404 | Dolakha | Orang | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 2
5405 | Dolakha | Orang | 8 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 65 | 65 | 2016-08-29 | 2017-08-21 |  | Bigu | 2
5406 | Dolakha | Orang | 8 | CARITAS-N | CARITAS-N | CARITAS-N | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-09-08 |  |  | Bigu | 2
5407 | Dolakha | Orang | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 2
5408 | Dolakha | Orang | 8 | CARITAS-N | CARITAS-N | CARITAS-N | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2017-12-13 | 2017-12-19 |  | Bigu | 2
5409 | Dolakha | Orang | 8 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 3 | 2 | 2015-12-14 | 2016-02-15 |  | Bigu | 2
5410 | Dolakha | Orang | 8 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 10 | 2015-12-14 | 2016-02-15 |  | Bigu | 2
5411 | Dolakha | Orang | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 2
5412 | Dolakha | Orang | 9 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 55 | 55 | 2016-08-29 | 2017-08-21 |  | Bigu | 2
5413 | Dolakha | Orang | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 2
5414 | Dolakha | Orang | 9 | CARITAS-N | CARITAS-N | CARITAS-N | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2017-12-13 | 2017-12-19 |  | Bigu | 2
5415 | Dolakha | Orang | 9 | HELVETAS | AFD |  | Training | Vocational training | Carpenter (CTEVT) | 50 Days Carpentry Training to fresh carpenters | # of trainees | Yes | Completed | 3 | 3 | 2015-12-14 | 2016-02-15 |  | Bigu | 2
5416 | Dolakha | Orang | 9 | HELVETAS | AFD | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 Days Masonary Training to fresh masons | # of trainees | Yes | Completed | 10 | 9 | 2015-12-14 | 2016-02-15 |  | Bigu | 2
5417 | Dolakha | Orang | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bigu | 2
5418 | Dolakha | Pawati | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 1
5419 | Dolakha | Pawati | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 1
5420 | Dolakha | Pawati | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 1
5421 | Dolakha | Pawati | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 1
5422 | Dolakha | Pawati | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 1
5423 | Dolakha | Pawati | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 1
5424 | Dolakha | Pawati | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 1
5425 | Dolakha | Pawati | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 1
5426 | Dolakha | Pawati | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 1
5427 | Dolakha | Pawati | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 1
5428 | Dolakha | Pawati | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 1
5429 | Dolakha | Pawati | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 1
5430 | Dolakha | Pawati | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 1
5431 | Dolakha | Pawati | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 1
5432 | Dolakha | Pawati | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 1
5433 | Dolakha | Pawati | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 1
5434 | Dolakha | Pawati | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 1
5435 | Dolakha | Pawati | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Melung | 1
5436 | Dolakha | Pawati | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 83 |  |  |  | Melung | 1
5437 | Dolakha | Pawati | All | BC | PLAN | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 30 | 0 |  |  |  | Melung | 1
5438 | Dolakha | Sahare | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 5
5439 | Dolakha | Sahare | 1 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 5
5440 | Dolakha | Sahare | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 5
5441 | Dolakha | Sahare | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 5
5442 | Dolakha | Sahare | 2 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 5
5443 | Dolakha | Sahare | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 5
5444 | Dolakha | Sahare | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 5
5445 | Dolakha | Sahare | 3 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 5
5446 | Dolakha | Sahare | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 5
5447 | Dolakha | Sahare | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 5
5448 | Dolakha | Sahare | 4 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 5
5449 | Dolakha | Sahare | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 5
5450 | Dolakha | Sahare | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 5
5451 | Dolakha | Sahare | 5 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 5
5452 | Dolakha | Sahare | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 5
5453 | Dolakha | Sahare | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 5
5454 | Dolakha | Sahare | 6 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 5
5455 | Dolakha | Sahare | 6 | MC | REDC | MC | Training | ToT | Skilled masons |  | # of trainees | Yes | Completed | 28 | 32 | 2016-09-25 | 2016-10-01 |  | Tamakoshi | 5
5456 | Dolakha | Sahare | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 5
5457 | Dolakha | Sahare | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 5
5458 | Dolakha | Sahare | 7 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 5
5459 | Dolakha | Sahare | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 5
5460 | Dolakha | Sahare | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 5
5461 | Dolakha | Sahare | 8 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 5
5462 | Dolakha | Sahare | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 5
5463 | Dolakha | Sahare | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 5
5464 | Dolakha | Sahare | 9 | MC | REDC | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Tamakoshi | 5
5465 | Dolakha | Sahare | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Tamakoshi | 5
5466 | Dolakha | Sahare | ALL | UNHABITAT |  |  | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 12 |  |  |  | Tamakoshi | 5
5467 | Dolakha | Sailungeswor | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 8
5468 | Dolakha | Sailungeswor | 1 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-12 | 2016-11-18 |  | Sailung | 8
5469 | Dolakha | Sailungeswor | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 8
5470 | Dolakha | Sailungeswor | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 8
5471 | Dolakha | Sailungeswor | 2 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-12 | 2016-11-18 |  | Sailung | 8
5472 | Dolakha | Sailungeswor | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 8
5473 | Dolakha | Sailungeswor | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 8
5474 | Dolakha | Sailungeswor | 3 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-12 | 2016-11-18 |  | Sailung | 8
5475 | Dolakha | Sailungeswor | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 8
5476 | Dolakha | Sailungeswor | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 8
5477 | Dolakha | Sailungeswor | 4 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-12 | 2016-11-18 |  | Sailung | 8
5478 | Dolakha | Sailungeswor | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 8
5479 | Dolakha | Sailungeswor | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 8
5480 | Dolakha | Sailungeswor | 5 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-12 | 2016-11-18 |  | Sailung | 8
5481 | Dolakha | Sailungeswor | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 8
5482 | Dolakha | Sailungeswor | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 8
5483 | Dolakha | Sailungeswor | 6 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-12 | 2016-11-18 |  | Sailung | 8
5484 | Dolakha | Sailungeswor | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 8
5485 | Dolakha | Sailungeswor | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 8
5486 | Dolakha | Sailungeswor | 7 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-12 | 2016-11-18 |  | Sailung | 8
5487 | Dolakha | Sailungeswor | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 8
5488 | Dolakha | Sailungeswor | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 8
5489 | Dolakha | Sailungeswor | 8 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-12 | 2016-11-18 |  | Sailung | 8
5490 | Dolakha | Sailungeswor | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 8
5491 | Dolakha | Sailungeswor | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 8
5492 | Dolakha | Sailungeswor | 9 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2016-11-12 | 2016-11-18 |  | Sailung | 8
5493 | Dolakha | Sailungeswor | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Sailung | 8
5494 | Dolakha | Sailungeswor | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 73 |  |  |  | Sailung | 8
5495 | Dolakha | Sundrawati | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 9
5496 | Dolakha | Sundrawati | 1 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 2 | 2 | 2017-02-01 | 2017-04-04 |  | Kalinchok | 9
5497 | Dolakha | Sundrawati | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 9
5498 | Dolakha | Sundrawati | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 9
5499 | Dolakha | Sundrawati | 2 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 2 | 2 | 2017-02-01 | 2017-04-04 |  | Kalinchok | 9
5500 | Dolakha | Sundrawati | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 9
5501 | Dolakha | Sundrawati | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 9
5502 | Dolakha | Sundrawati | 3 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 2 | 2 | 2017-02-01 | 2017-04-04 |  | Kalinchok | 9
5503 | Dolakha | Sundrawati | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 9
5504 | Dolakha | Sundrawati | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 9
5505 | Dolakha | Sundrawati | 4 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 2 | 2 | 2017-02-01 | 2017-04-04 |  | Kalinchok | 9
5506 | Dolakha | Sundrawati | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 9
5507 | Dolakha | Sundrawati | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 9
5508 | Dolakha | Sundrawati | 5 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 2 | 2 | 2017-02-01 | 2017-04-04 |  | Kalinchok | 9
5509 | Dolakha | Sundrawati | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 9
5510 | Dolakha | Sundrawati | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 9
5511 | Dolakha | Sundrawati | 6 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 2 | 2 | 2017-02-01 | 2017-04-04 |  | Kalinchok | 9
5512 | Dolakha | Sundrawati | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 9
5513 | Dolakha | Sundrawati | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 9
5514 | Dolakha | Sundrawati | 7 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 1 | 1 | 2017-02-01 | 2017-04-04 |  | Kalinchok | 9
5515 | Dolakha | Sundrawati | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 9
5516 | Dolakha | Sundrawati | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 9
5517 | Dolakha | Sundrawati | 8 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 1 | 1 | 2017-02-01 | 2017-04-04 |  | Kalinchok | 9
5518 | Dolakha | Sundrawati | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 9
5519 | Dolakha | Sundrawati | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 9
5520 | Dolakha | Sundrawati | 9 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 1 | 1 | 2017-02-01 | 2017-04-04 |  | Kalinchok | 9
5521 | Dolakha | Sundrawati | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 9
5522 | Dolakha | Sundrawati | ALL | UNHABITAT |  |  | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 24 |  |  |  | Kalinchok | 9
5523 | Dolakha | Sundrawati | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 41 |  |  |  | Kalinchok | 9
5524 | Dolakha | Sunkhani | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 8
5525 | Dolakha | Sunkhani | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 8
5526 | Dolakha | Sunkhani | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 8
5527 | Dolakha | Sunkhani | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 8
5528 | Dolakha | Sunkhani | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 8
5529 | Dolakha | Sunkhani | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 8
5530 | Dolakha | Sunkhani | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 7
5531 | Dolakha | Sunkhani | 4 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2015-08-27 | 2015-09-08 |  | Kalinchok | 7
5532 | Dolakha | Sunkhani | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 7
5533 | Dolakha | Sunkhani | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 7
5534 | Dolakha | Sunkhani | 5 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2015-08-27 | 2015-09-08 |  | Kalinchok | 7
5535 | Dolakha | Sunkhani | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 7
5536 | Dolakha | Sunkhani | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 8
5537 | Dolakha | Sunkhani | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 8
5538 | Dolakha | Sunkhani | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 8
5539 | Dolakha | Sunkhani | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 8
5540 | Dolakha | Sunkhani | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 7
5541 | Dolakha | Sunkhani | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 7
5542 | Dolakha | Sunkhani | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 7
5543 | Dolakha | Sunkhani | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Kalinchok | 7
5544 | Dolakha | Sunkhani | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 45 |  |  |  | Kalinchok | 8
5545 | Dolakha | Suri | 1 | LWF | HURADEC | LWF | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Ongoing | 64 | 64 | 2017-03-30 | 2017-03-30 |  | Gaurishankar | 5
5546 | Dolakha | Suri | 1 | LWF | HURADEC | LWF | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Ongoing | 64 | 55 | 2017-06-08 | 2017-06-08 |  | Gaurishankar | 5
5547 | Dolakha | Suri | 1 | LWF | HURADEC | LWF | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 64 | 30 | 2017-06-08 | 2017-06-08 |  | Gaurishankar | 5
5548 | Dolakha | Suri | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 5
5549 | Dolakha | Suri | 1 | LWF | HURADEC |  | Technical Assistance | Community reconstruction orientation | 1 session | 3 sessions per VDC on 10 key messages | # of participants | Yes | Ongoing | 135 | 67 | 2017-01-23 |  |  | Gaurishankar | 5
5550 | Dolakha | Suri | 1 | LWF | HURADEC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 19 | 19 | 2016-11-29 | 2016-12-05 |  | Gaurishankar | 5
5551 | Dolakha | Suri | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 5
5552 | Dolakha | Suri | 2 | LWF | HURADEC | LWF | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Fifty Thousand of first installment | # of households | Yes | Ongoing | 77 | 77 | 2017-03-30 | 2017-03-30 |  | Gaurishankar | 5
5553 | Dolakha | Suri | 2 | LWF | HURADEC | LWF | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | One hundred and Fifty Thousand of Second Installment | # of households | Yes | Ongoing | 77 | 34 | 2017-06-08 | 2017-06-08 |  | Gaurishankar | 5
5554 | Dolakha | Suri | 2 | LWF | HURADEC | LWF | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Seventy Five Thousand of Third Installment | # of households | Yes | Ongoing | 77 | 38 | 2017-06-08 | 2017-06-08 |  | Gaurishankar | 5
5555 | Dolakha | Suri | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 5
5556 | Dolakha | Suri | 2 | LWF | HURADEC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 11 | 11 | 2017-11-29 | 2017-12-05 |  | Gaurishankar | 5
5557 | Dolakha | Suri | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 5
5558 | Dolakha | Suri | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 5
5559 | Dolakha | Suri | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 5
5560 | Dolakha | Suri | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 5
5561 | Dolakha | Suri | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 5
5562 | Dolakha | Suri | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 5
5563 | Dolakha | Suri | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 5
5564 | Dolakha | Suri | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 5
5565 | Dolakha | Suri | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 5
5566 | Dolakha | Suri | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 5
5567 | Dolakha | Suri | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 5
5568 | Dolakha | Suri | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 5
5569 | Dolakha | Suri | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 5
5570 | Dolakha | Suri | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 5
5571 | Dolakha | Suri | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Gaurishankar | 5
5572 | Dolakha | SusmaChhemawati | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 1
5573 | Dolakha | SusmaChhemawati | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session | Explaining 10 key messages for households with short demo on constructing EQ resistance house for 3-4 Hr sessions | # of households | Yes | Completed | 84 | 36 | 2016-06-13 | 2016-06-13 |  | Bhimeshwor | 1
5574 | Dolakha | SusmaChhemawati | 1 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 2 | 2 | 2017-02-12 | 2017-03-17 |  | Bhimeshwor | 1
5575 | Dolakha | SusmaChhemawati | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 1
5576 | Dolakha | SusmaChhemawati | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 1
5577 | Dolakha | SusmaChhemawati | 2 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 2 | 2 | 2017-02-12 | 2017-03-17 |  | Bhimeshwor | 1
5578 | Dolakha | SusmaChhemawati | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 1
5579 | Dolakha | SusmaChhemawati | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 1
5580 | Dolakha | SusmaChhemawati | 3 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 2 | 2 | 2017-02-12 | 2017-03-17 |  | Bhimeshwor | 1
5581 | Dolakha | SusmaChhemawati | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 1
5582 | Dolakha | SusmaChhemawati | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 1
5583 | Dolakha | SusmaChhemawati | 4 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 2 | 2 | 2017-02-12 | 2017-03-17 |  | Bhimeshwor | 1
5584 | Dolakha | SusmaChhemawati | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 1
5585 | Dolakha | SusmaChhemawati | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 1
5586 | Dolakha | SusmaChhemawati | 5 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 2 | 2 | 2017-02-12 | 2017-03-17 |  | Bhimeshwor | 1
5587 | Dolakha | SusmaChhemawati | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 1
5588 | Dolakha | SusmaChhemawati | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 1
5589 | Dolakha | SusmaChhemawati | 6 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 2 | 1 | 2017-02-12 | 2017-03-17 |  | Bhimeshwor | 1
5590 | Dolakha | SusmaChhemawati | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 1
5591 | Dolakha | SusmaChhemawati | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 1
5592 | Dolakha | SusmaChhemawati | 7 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 1 | 1 | 2017-02-12 | 2017-03-17 |  | Bhimeshwor | 1
5593 | Dolakha | SusmaChhemawati | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 1
5594 | Dolakha | SusmaChhemawati | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 1
5595 | Dolakha | SusmaChhemawati | 8 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 1 | 1 | 2017-02-12 | 2017-03-17 |  | Bhimeshwor | 1
5596 | Dolakha | SusmaChhemawati | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 1
5597 | Dolakha | SusmaChhemawati | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 1
5598 | Dolakha | SusmaChhemawati | 9 | GAN | CEEPAARD |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 30 Days Training for New Masons | # of trainees | Yes | Completed | 1 | 1 | 2017-02-12 | 2017-03-17 |  | Bhimeshwor | 1
5599 | Dolakha | SusmaChhemawati | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Bhimeshwor | 1
5600 | Dolakha | SusmaChhemawati | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 96 |  |  |  | Bhimeshwor | 1
5601 | Dolakha | Syama | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 1
5602 | Dolakha | Syama | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 1
5603 | Dolakha | Syama | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 1
5604 | Dolakha | Syama | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 1
5605 | Dolakha | Syama | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 1
5606 | Dolakha | Syama | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 1
5607 | Dolakha | Syama | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 1
5608 | Dolakha | Syama | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 1
5609 | Dolakha | Syama | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 1
5610 | Dolakha | Syama | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 1
5611 | Dolakha | Syama | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 1
5612 | Dolakha | Syama | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 1
5613 | Dolakha | Syama | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 2
5614 | Dolakha | Syama | 7 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-05-28 | 2017-06-03 |  | Jiri | 2
5615 | Dolakha | Syama | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 2
5616 | Dolakha | Syama | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 2
5617 | Dolakha | Syama | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 2
5618 | Dolakha | Syama | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 2
5619 | Dolakha | Syama | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2015-10-01 | 2020-09-30 |  | Jiri | 2
5620 | Dolakha | Babare | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 32 | 32 | 2017-08-06 | 2017-08-12 |  | Kalinchok | 2
5621 | Dolakha | Lamidada | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 30 | 30 | 2017-08-09 | 2017-08-15 |  | Kalinchok | 4
5622 | Dolakha | Bhirkot | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 32 | 32 | 2017-08-15 | 2017-08-21 |  | Tamakoshi | 1
5623 | Dolakha | Malu | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 32 | 32 | 2017-08-17 |  |  | Tamakoshi | 4
5624 | Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 35 | 35 | 2017-08-22 | 2017-08-28 |  | Bhimeshwor | 6
5625 | Dolakha | Laduk | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 5 | 5 | 2017-08-25 | 2017-08-31 |  | Bigu | 4
5626 | Dolakha | Japhe | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 30 | 0 | 2017-08-26 |  |  | Tamakoshi | 3
5627 | Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-04-23 | 2017-06-03 |  | Bhimeshwor | 3
5628 | Dolakha | Chyama | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-04-23 | 2017-06-03 |  | Tamakoshi | 6
5629 | Dolakha | Bhimeswor N.P. | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-05-23 | 2017-07-31 |  | Bhimeshwor | 4
5630 | Dolakha | GhangSukathokar | 1 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-07-06 | 2017-07-12 |  | Melung | 2
5631 | Dolakha | GhangSukathokar | 2 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-07-06 | 2017-07-12 |  | Melung | 2
5632 | Dolakha | GhangSukathokar | 3 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-07-06 | 2017-07-12 |  | Melung | 2
5633 | Dolakha | GhangSukathokar | 4 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-07-06 | 2017-07-12 |  | Melung | 2
5634 | Dolakha | GhangSukathokar | 5 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-07-06 | 2017-07-12 |  | Melung | 3
5635 | Dolakha | Bhedapu | 1 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-07-06 | 2017-07-12 |  | Melung | 4
5636 | Dolakha | GhangSukathokar | 7 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-07-06 | 2017-07-12 |  | Melung | 3
5637 | Dolakha | GhangSukathokar | 8 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-07-06 | 2017-07-12 |  | Melung | 3
5638 | Dolakha | GhangSukathokar | 9 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-07-06 | 2017-07-12 |  | Melung | 3
5639 | Dolakha | Bhedapu | 5 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-07-06 | 2017-07-12 |  | Melung | 4
5640 | Dolakha | Jiri N.P. | 2 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-07-06 | 2017-07-12 |  | Jiri | 3
5641 | Dolakha | Jiri N.P. | 3 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2017-07-06 | 2017-07-12 |  | Jiri | 3
5642 | Dolakha | Jiri N.P. | 4 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-07-06 | 2017-07-12 |  | Jiri | 4
5643 | Dolakha | Jiri N.P. | 5 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-07-06 | 2017-07-12 |  | Jiri | 5
5644 | Dolakha | Jiri N.P. | 6 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2017-07-06 | 2017-07-12 |  | Jiri | 6
5645 | Dolakha | Jiri N.P. | 7 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-07-06 | 2017-07-12 |  | Jiri | 7
5646 | Dolakha | Jiri N.P. | 8 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-07-06 | 2017-07-12 |  | Jiri | 8
5647 | Dolakha | Syama | 3 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-07-06 | 2017-07-12 |  | Jiri | 1
5648 | Dolakha | Melung | 4 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-06-25 | 2017-07-01 |  | Melung | 7
5649 | Dolakha | Melung | 5 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 24 | 24 | 2017-06-25 | 2017-07-01 |  | Melung | 7
5650 | Dolakha | Melung | 6 | GON - DUDBC | GON - DLPIU | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-06-25 | 2017-07-01 |  | Melung | 6
5651 | Dolakha | Alampu | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 22 | 22 | 2017-09-11 | 2017-09-11 |  | Bigu | 6
5652 | Dolakha | Alampu | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 25 | 25 | 2017-09-12 | 2017-09-12 |  | Bigu | 6
5653 | Dolakha | Alampu | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 26 | 26 | 2017-09-12 | 2017-09-12 |  | Bigu | 6
5654 | Dolakha | Alampu | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 41 | 41 | 2017-09-13 | 2017-09-13 |  | Bigu | 6
5655 | Dolakha | Babare | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 31 | 31 | 2017-09-01 | 2017-09-01 |  | Kalinchok | 2
5656 | Dolakha | Babare | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 23 | 23 | 2017-09-11 | 2017-09-11 |  | Kalinchok | 2
5657 | Dolakha | Babare | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 42 | 42 | 2017-09-11 | 2017-09-11 |  | Kalinchok | 2
5658 | Dolakha | Babare | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 23 | 23 | 2017-09-11 | 2017-09-11 |  | Kalinchok | 2
5659 | Dolakha | Babare | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 25 | 25 | 2017-09-12 | 2017-09-12 |  | Kalinchok | 2
5660 | Dolakha | Babare | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 23 | 23 | 2017-09-14 | 2017-09-14 |  | Kalinchok | 2
5661 | Dolakha | Bhirkot | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 | 2017-09-11 | 2017-09-11 |  | Tamakoshi | 1
5662 | Dolakha | Bhirkot | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 9 | 9 | 2017-09-15 | 2017-09-15 |  | Tamakoshi | 1
5663 | Dolakha | Bhirkot | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 15 | 15 | 2017-09-19 | 2017-09-19 |  | Tamakoshi | 1
5664 | Dolakha | Bhirkot | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 15 | 15 | 2017-09-19 | 2017-09-19 |  | Tamakoshi | 1
5665 | Dolakha | Bhimeswor N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 8 | 8 | 2017-09-01 | 2017-09-01 |  | Bhimeshwor | 2
5666 | Dolakha | Bhimeswor N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 15 | 15 | 2017-09-11 | 2017-09-11 |  | Bhimeshwor | 2
5667 | Dolakha | Bhimeswor N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 17 | 17 | 2017-09-12 | 2017-09-12 |  | Bhimeshwor | 2
5668 | Dolakha | Bhimeswor N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 11 | 11 | 2017-09-12 | 2017-09-12 |  | Bhimeshwor | 7
5669 | Dolakha | Bhimeswor N.P. | 13 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 | 2017-09-13 | 2017-09-13 |  | Bhimeshwor | 7
5670 | Dolakha | Bhimeswor N.P. | 13 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 17 | 17 | 2017-09-14 | 2017-09-14 |  | Bhimeshwor | 7
5671 | Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 16 | 16 | 2017-09-15 | 2017-09-15 |  | Bhimeshwor | 3
5672 | Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 16 | 16 | 2017-09-15 | 2017-09-15 |  | Bhimeshwor | 3
5673 | Dolakha | Bhimeswor N.P. | 12 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 13 | 13 | 2017-09-16 | 2017-09-16 |  | Bhimeshwor | 7
5674 | Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 17 | 17 | 2017-09-17 | 2017-09-17 |  | Bhimeshwor | 5
5675 | Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 16 | 16 | 2017-09-17 | 2017-09-17 |  | Bhimeshwor | 5
5676 | Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 8 | 8 | 2017-09-17 | 2017-09-17 |  | Bhimeshwor | 3
5677 | Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 23 | 23 | 2017-09-17 | 2017-09-17 |  | Bhimeshwor | 3
5678 | Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 23 | 23 | 2017-09-18 | 2017-09-18 |  | Bhimeshwor | 5
5679 | Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 15 | 15 | 2017-09-18 | 2017-09-18 |  | Bhimeshwor | 5
5680 | Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 21 | 21 | 2017-09-18 | 2017-09-18 |  | Bhimeshwor | 5
5681 | Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 11 | 11 | 2017-09-18 | 2017-09-18 |  | Bhimeshwor | 5
5682 | Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 17 | 17 | 2017-09-18 | 2017-09-18 |  | Bhimeshwor | 5
5683 | Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 19 | 19 | 2017-09-18 | 2017-09-18 |  | Bhimeshwor | 3
5684 | Dolakha | Bhimeswor N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 | 2017-09-18 | 2017-09-18 |  | Bhimeshwor | 3
5685 | Dolakha | Bigu | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 17 | 17 | 2017-09-03 | 2017-09-03 |  | Bigu | 7
5686 | Dolakha | Bigu | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 27 | 27 | 2017-09-04 | 2017-09-04 |  | Bigu | 7
5687 | Dolakha | Bigu | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2017-09-08 | 2017-09-08 |  | Bigu | 7
5688 | Dolakha | Bigu | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 17 | 17 | 2017-09-12 | 2017-09-12 |  | Bigu | 7
5689 | Dolakha | Bigu | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 13 | 13 | 2017-09-13 | 2017-09-13 |  | Bigu | 7
5690 | Dolakha | Bigu | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 41 | 41 | 2017-09-13 | 2017-09-13 |  | Bigu | 7
5691 | Dolakha | Chilankha | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 11 | 11 | 2017-09-04 | 2017-09-04 |  | Bigu | 5
5692 | Dolakha | Chilankha | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 14 | 14 | 2017-09-05 | 2017-09-05 |  | Bigu | 5
5693 | Dolakha | Chilankha | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 25 | 25 | 2017-09-06 | 2017-09-06 |  | Bigu | 5
5694 | Dolakha | Chilankha | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 21 | 21 | 2017-09-06 | 2017-09-06 |  | Bigu | 5
5695 | Dolakha | Chilankha | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2017-09-07 | 2017-09-07 |  | Bigu | 5
5696 | Dolakha | Chilankha | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 | 2017-09-10 | 2017-09-10 |  | Bigu | 5
5697 | Dolakha | Chilankha | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 14 | 14 | 2017-09-10 | 2017-09-10 |  | Bigu | 5
5698 | Dolakha | Chilankha | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 15 | 15 | 2017-09-11 | 2017-09-11 |  | Bigu | 5
5699 | Dolakha | Chilankha | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 | 2017-09-12 | 2017-09-12 |  | Bigu | 5
5700 | Dolakha | Chyama | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 13 | 13 | 2017-09-15 | 2017-09-15 |  | Tamakoshi | 6
5701 | Dolakha | Chyama | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 | 2017-09-15 | 2017-09-15 |  | Tamakoshi | 6
5702 | Dolakha | Japhe | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 15 | 15 | 2017-09-15 | 2017-09-15 |  | Tamakoshi | 3
5703 | Dolakha | Japhe | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 11 | 11 | 2017-09-16 | 2017-09-16 |  | Tamakoshi | 3
5704 | Dolakha | Jhule | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 | 2017-09-04 | 2017-09-04 |  | Tamakoshi | 2
5705 | Dolakha | Jhule | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 13 | 13 | 2017-09-06 | 2017-09-06 |  | Tamakoshi | 2
5706 | Dolakha | Jhule | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 9 | 9 | 2017-09-10 | 2017-09-10 |  | Tamakoshi | 2
5707 | Dolakha | Jhule | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 | 2017-09-12 | 2017-09-12 |  | Tamakoshi | 2
5708 | Dolakha | Jhule | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 | 2017-09-15 | 2017-09-15 |  | Tamakoshi | 2
5709 | Dolakha | Jhule | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 8 | 8 | 2017-09-15 | 2017-09-15 |  | Tamakoshi | 2
5710 | Dolakha | Jhule | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 8 | 8 | 2017-09-15 | 2017-09-15 |  | Tamakoshi | 2
5711 | Dolakha | Jhule | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 13 | 13 | 2017-09-19 | 2017-09-19 |  | Tamakoshi | 2
5712 | Dolakha | Jhule | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 | 2017-09-19 | 2017-09-19 |  | Tamakoshi | 2
5713 | Dolakha | Jhule | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 14 | 14 | 2017-09-19 | 2017-09-19 |  | Tamakoshi | 2
5714 | Dolakha | Jhule | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 | 2017-09-20 | 2017-09-20 |  | Tamakoshi | 2
5715 | Dolakha | Jhule | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 16 | 16 | 2017-09-20 | 2017-09-20 |  | Tamakoshi | 2
5716 | Dolakha | Jhule | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 9 | 9 | 2017-09-20 | 2017-09-20 |  | Tamakoshi | 2
5717 | Dolakha | Katakuti | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 22 | 22 | 2017-09-06 | 2017-09-06 |  | Sailung | 5
5718 | Dolakha | Katakuti | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 23 | 23 | 2017-09-06 | 2017-09-06 |  | Sailung | 5
5719 | Dolakha | Katakuti | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 16 | 16 | 2017-09-06 | 2017-09-06 |  | Sailung | 5
5720 | Dolakha | Katakuti | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 14 | 14 | 2017-09-06 | 2017-09-06 |  | Sailung | 5
5721 | Dolakha | Katakuti | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 | 2017-09-07 | 2017-09-07 |  | Sailung | 5
5722 | Dolakha | Lamidada | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 16 | 16 | 2017-09-01 | 2017-09-01 |  | Kalinchok | 4
5723 | Dolakha | Lamidada | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 22 | 22 | 2017-09-01 | 2017-09-01 |  | Kalinchok | 4
5724 | Dolakha | Lamidada | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 32 | 32 | 2017-09-05 | 2017-09-05 |  | Kalinchok | 3
5725 | Dolakha | Lamidada | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 26 | 26 | 2017-09-05 | 2017-09-05 |  | Kalinchok | 3
5726 | Dolakha | Lamidada | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 32 | 32 | 2017-09-05 | 2017-09-05 |  | Kalinchok | 3
5727 | Dolakha | Lamidada | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 23 | 23 | 2017-09-05 | 2017-09-05 |  | Kalinchok | 3
5728 | Dolakha | Magapauwa | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 11 | 11 | 2017-09-05 | 2017-09-05 |  | Sailung | 4
5729 | Dolakha | Magapauwa | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 11 | 11 | 2017-09-06 | 2017-09-06 |  | Sailung | 4
5730 | Dolakha | Magapauwa | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 | 2017-09-06 | 2017-09-06 |  | Sailung | 4
5731 | Dolakha | Magapauwa | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 11 | 11 | 2017-09-18 | 2017-09-18 |  | Sailung | 4
5732 | Dolakha | Malu | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 9 | 9 | 2017-09-10 | 2017-09-10 |  | Tamakoshi | 4
5733 | Dolakha | Malu | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 38 | 38 | 2017-09-15 | 2017-09-15 |  | Tamakoshi | 4
5734 | Dolakha | Malu | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 13 | 13 | 2017-09-19 | 2017-09-19 |  | Tamakoshi | 4
5735 | Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | Short training | Social mobilizer |  | # of trainees | Yes | Completed | 30 | 30 | 2017-09-04 | 2017-09-08 |  | Bhimeshwor | 6
5736 | Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | Short training | Social mobilizer |  | # of trainees | Yes | Completed | 28 | 28 | 2017-09-11 | 2017-09-15 |  | Bhimeshwor | 6
5737 | Dolakha | Bulung | 1 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 80 | 55 | 2017-08-21 | 2017-08-21 |  | Bigu | 3
5738 | Dolakha | Bulung | 2 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 74 | 70 | 2017-08-21 | 2017-08-21 |  | Bigu | 3
5739 | Dolakha | Bulung | 3 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 84 | 35 | 2017-08-21 | 2017-08-21 |  | Bigu | 3
5740 | Dolakha | Bulung | 4 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 85 | 72 | 2017-08-21 | 2017-08-21 |  | Bigu | 3
5741 | Dolakha | Bulung | 5 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 90 | 70 | 2017-08-21 | 2017-08-21 |  | Bigu | 3
5742 | Dolakha | Bulung | 6 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 68 | 48 | 2017-08-21 | 2017-08-21 |  | Bigu | 3
5743 | Dolakha | Bulung | 7 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 98 | 60 | 2017-08-21 | 2017-08-21 |  | Bigu | 3
5744 | Dolakha | Bulung | 8 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 78 | 54 | 2017-08-21 | 2017-08-21 |  | Bigu | 3
5745 | Dolakha | Bulung | 9 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 56 | 38 | 2017-08-21 | 2017-08-21 |  | Bigu | 3
5746 | Dolakha | Orang | 1 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 70 | 70 | 2017-08-21 | 2017-08-21 |  | Bigu | 2
5747 | Dolakha | Orang | 2 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 52 | 31 | 2017-08-21 | 2017-08-21 |  | Bigu | 2
5748 | Dolakha | Orang | 3 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 50 | 50 | 2017-08-21 | 2017-08-21 |  | Bigu | 2
5749 | Dolakha | Orang | 4 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 60 | 48 | 2017-08-21 | 2017-08-21 |  | Bigu | 2
5750 | Dolakha | Orang | 5 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 75 | 42 | 2017-08-21 | 2017-08-21 |  | Bigu | 2
5751 | Dolakha | Orang | 6 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 48 | 38 | 2017-08-21 | 2017-08-21 |  | Bigu | 2
5752 | Dolakha | Orang | 7 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 86 | 86 | 2017-08-21 | 2017-08-21 |  | Bigu | 2
5753 | Dolakha | Orang | 8 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 65 | 65 | 2017-08-21 | 2017-08-21 |  | Bigu | 2
5754 | Dolakha | Orang | 9 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 55 | 36 | 2017-08-21 | 2017-08-21 |  | Bigu | 2
5755 | Dolakha | Mirge | 2 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-11-01 | 2017-11-07 |  | Baiteshwor | 3
5756 | Dolakha | Mirge | 3 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-11-01 | 2017-11-07 |  | Baiteshwor | 3
5757 | Dolakha | Mirge | 4 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-11-01 | 2017-11-07 |  | Baiteshwor | 3
5758 | Dolakha | Mirge | 5 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-11-01 | 2017-11-07 |  | Baiteshwor | 3
5759 | Dolakha | Mirge | 6 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-11-01 | 2017-11-07 |  | Baiteshwor | 3
5760 | Dolakha | Mirge | 7 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-11-01 | 2017-11-07 |  | Baiteshwor | 3
5761 | Dolakha | Mirge | 8 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-11-01 | 2017-11-07 |  | Baiteshwor | 3
5762 | Dolakha | Mirge | 9 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-11-01 | 2017-11-07 |  | Baiteshwor | 3
5763 | Dolakha | Jiri N.P. | 4 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-11-01 | 2017-11-07 |  | Jiri | 4
5764 | Dolakha | Jiri N.P. | 1 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-11-01 | 2017-11-07 |  | Jiri | 2
5765 | Dolakha | Jiri N.P. | 1 | CA | HURADEC | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-11-01 | 2017-11-07 |  | Jiri | 2
5766 | Dolakha | Laduk | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 4 | 4 | 2017-08-25 | 2017-08-31 |  | Bigu | 4
5767 | Dolakha | Laduk | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-08-25 | 2017-08-31 |  | Bigu | 4
5768 | Dolakha | Laduk | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 8 | 8 | 2017-08-25 | 2017-08-31 |  | Bigu | 4
5769 | Dolakha | Laduk | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 10 | 10 | 2017-08-25 | 2017-08-31 |  | Bigu | 4
5770 | Dolakha | Laduk | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-08-25 | 2017-08-31 |  | Bigu | 4
5771 | Dolakha | Laduk | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 3 | 3 | 2017-08-25 | 2017-08-31 |  | Bigu | 4
5772 | Dolakha | Jhule | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2017-08-25 | 2017-08-31 |  | Tamakoshi | 2
5773 | Dolakha | Jhule | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-08-25 | 2017-08-31 |  | Tamakoshi | 2
5774 | Dolakha | Japhe | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-08-25 | 2017-08-31 |  | Tamakoshi | 3
5775 | Dolakha | Japhe | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2017-08-25 | 2017-08-31 |  | Tamakoshi | 3
5776 | Dolakha | Japhe | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-08-25 | 2017-08-31 |  | Tamakoshi | 3
5777 | Dolakha | Japhe | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2017-08-25 | 2017-08-31 |  | Tamakoshi | 3
5778 | Dolakha | Japhe | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 1 | 1 | 2017-08-25 | 2017-08-31 |  | Tamakoshi | 3
5779 | Dolakha | Japhe | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2017-08-25 | 2017-08-31 |  | Tamakoshi | 3
5780 | Dolakha | Japhe | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 2 | 2 | 2017-08-25 | 2017-08-31 |  | Tamakoshi | 3
5781 | Dolakha | Japhe | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 6 | 6 | 2017-08-25 | 2017-08-31 |  | Tamakoshi | 3
5782 | Dolakha | Orang | 1 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 70 | 46 | 2017-11-18 |  |  | Bigu | 2
5783 | Dolakha | Orang | 2 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 52 | 37 | 2017-11-18 |  |  | Bigu | 2
5784 | Dolakha | Orang | 3 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 50 | 36 | 2017-11-18 |  |  | Bigu | 2
5785 | Dolakha | Orang | 4 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 60 | 42 | 2017-11-18 |  |  | Bigu | 2
5786 | Dolakha | Orang | 5 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 75 | 46 | 2017-11-18 |  |  | Bigu | 2
5787 | Dolakha | Orang | 6 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 48 | 33 | 2017-11-18 |  |  | Bigu | 2
5788 | Dolakha | Orang | 7 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 86 | 51 | 2017-11-18 |  |  | Bigu | 2
5789 | Dolakha | Orang | 8 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 65 | 45 | 2017-11-18 |  |  | Bigu | 2
5790 | Dolakha | Orang | 9 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 55 | 40 | 2017-11-18 |  |  | Bigu | 2
5791 | Dolakha | Bulung | 1 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 80 | 30 | 2017-11-21 |  |  | Bigu | 3
5792 | Dolakha | Bulung | 2 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 74 | 43 | 2017-11-21 |  |  | Bigu | 3
5793 | Dolakha | Bulung | 3 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 84 | 32 | 2017-11-21 |  |  | Bigu | 3
5794 | Dolakha | Bulung | 4 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 85 | 45 | 2017-11-21 |  |  | Bigu | 3
5795 | Dolakha | Bulung | 5 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 90 | 44 | 2017-11-21 |  |  | Bigu | 3
5796 | Dolakha | Bulung | 6 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 68 | 33 | 2017-11-21 |  |  | Bigu | 3
5797 | Dolakha | Bulung | 7 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 98 | 35 | 2017-11-21 |  |  | Bigu | 3
5798 | Dolakha | Bulung | 8 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 78 | 42 | 2017-11-21 |  |  | Bigu | 3
5799 | Dolakha | Bulung | 9 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 56 | 35 | 2017-11-21 |  |  | Bigu | 3
5800 | Dolakha | Lapilang | 1 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 9 | 2016-01-01 | 2018-12-31 |  | Kalinchok | 5
5801 | Dolakha | Lapilang | 2 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 9 | 2016-01-01 | 2018-12-31 |  | Kalinchok | 5
5802 | Dolakha | Lapilang | 3 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kalinchok | 5
5803 | Dolakha | Lapilang | 4 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kalinchok | 5
5804 | Dolakha | Lapilang | 5 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kalinchok | 6
5805 | Dolakha | Lapilang | 6 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kalinchok | 6
5806 | Dolakha | Lapilang | 7 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kalinchok | 6
5807 | Dolakha | Lapilang | 8 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 15 | 15 | 2016-01-01 | 2018-12-31 |  | Kalinchok | 6
5808 | Dolakha | Lapilang | 9 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 14 | 13 | 2016-01-01 | 2018-12-31 |  | Kalinchok | 6
5809 | Dolakha | SusmaChhemawati | 1 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 7 | 2016-01-01 | 2018-12-31 |  | Bhimeshwor | 1
5810 | Dolakha | SusmaChhemawati | 2 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 6 | 2016-01-01 | 2018-12-31 |  | Bhimeshwor | 1
5811 | Dolakha | SusmaChhemawati | 3 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Bhimeshwor | 1
5812 | Dolakha | SusmaChhemawati | 4 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Bhimeshwor | 1
5813 | Dolakha | SusmaChhemawati | 5 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Bhimeshwor | 1
5814 | Dolakha | SusmaChhemawati | 6 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Bhimeshwor | 1
5815 | Dolakha | SusmaChhemawati | 7 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Bhimeshwor | 1
5816 | Dolakha | SusmaChhemawati | 8 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Bhimeshwor | 1
5817 | Dolakha | SusmaChhemawati | 9 | NRCS | NRCS | SRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 15 | 15 | 2016-01-01 | 2018-12-31 |  | Bhimeshwor | 1
5818 | Dolakha | Babare | 2 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-11-01 | 2016-01-27 | Actual expenditure yet to be calculated | Kalinchok | 2
5819 | Dolakha | Bhimeswor N.P. | 2 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-01-27 | 2016-04-16 | Actual expenditure yet to be calculated | Bhimeshwor | 2
5820 | Dolakha | Chyama | 4 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-11-07 | 2016-02-02 | Actual expenditure yet to be calculated | Tamakoshi | 6
5821 | Dolakha | Hawa | 3 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-11-06 | 2016-02-02 | Actual expenditure yet to be calculated | Tamakoshi | 7
5822 | Dolakha | Lamidada | 8 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-11-03 | 2016-01-30 | Actual expenditure yet to be calculated | Kalinchok | 3
5823 | Dolakha | Lapilang | 4 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-07-19 | 2016-07-25 | Actual expenditure yet to be calculated | Kalinchok | 5
5824 | Dolakha | Melung | 6 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-11-13 | 2016-02-10 | Actual expenditure yet to be calculated | Melung | 6
5825 | Dolakha | Sahare | 6 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-11-08 | 2016-02-05 | Actual expenditure yet to be calculated | Tamakoshi | 5
5826 | Dolakha | Sundrawati | 3 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-11-10 | 2016-02-12 | Actual expenditure yet to be calculated | Kalinchok | 9
5827 | Dolakha | Sunkhani | 5 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-11-04 | 2016-02-04 | Actual expenditure yet to be calculated | Kalinchok | 7
5828 | Dolakha | SusmaChhemawati | 9 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-11-09 | 2016-11-15 | Actual expenditure yet to be calculated | Bhimeshwor | 1
5829 | Dolakha | Dandakharka | 1 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 90 | 90 | 2018-01-02 | 2018-02-08 |  | Melung | 6
5830 | Dolakha | Bhedapu | 1 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frameRural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 76 | 76 | 2017-12-24 | 2017-12-30 |  | Melung | 4
5831 | Dolakha | GhangSukathokar | 1 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frameRural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 60 | 60 | 2017-12-24 | 2017-12-30 |  | Melung | 2
5832 | Dolakha | GhangSukathokar | 2 | PLAN | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frameRural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 60 | 60 | 2017-12-24 | 2017-12-30 |  | Melung | 2
5833 | Dolakha | Khopachagu | 1 | NRA | NRA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frameRural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 30 | 29 | 2018-12-28 | 2018-01-03 |  | Bigu | 8
5834 | Dolakha | Sailungeswor | 1 | NRA | NRA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frameRural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 30 | 30 | 2018-01-17 | 2018-01-23 |  | Sailung | 8
5835 | Dolakha | Chyama | 1 | MC | REDC | MC | Training | Vocational training | New masons (50 days OJT CTEVT) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Tamakoshi | 6
5836 | Dolakha | Chyama | 2 | MC | REDC | MC | Training | Vocational training | New masons (50 days OJT CTEVT) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Tamakoshi | 6
5837 | Dolakha | Hawa | 1 | MC | REDC | MC | Training | Vocational training | New masons (50 days OJT CTEVT) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Tamakoshi | 7
5838 | Dolakha | Hawa | 2 | MC | REDC | MC | Training | Vocational training | New masons (50 days OJT CTEVT) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Tamakoshi | 7
5839 | Dolakha | Sahare | 1 | MC | REDC | MC | Training | Vocational training | New masons (50 days OJT CTEVT) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Tamakoshi | 5
5840 | Dolakha | Jhyaku | 1 | GON - DUDBC | GON - DLPIU | GON - DUDBC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Ongoing | 0 | 0 |  |  |  | Gaurishankar | 4
5841 | Dolakha | Kabhre | 1 | GON - DUDBC | GON - DLPIU | GON - DUDBC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 27 | 27 |  |  |  | Baiteshwor | 5
5842 | Dolakha | Sundrawati | 1 | GON - DUDBC | GON - DLPIU | GON - DUDBC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 36 | 36 |  |  |  | Kalinchok | 9
5843 | Dolakha | Khare | 1 | GON - DUDBC | GON - DLPIU | GON - DUDBC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 23 | 23 |  |  |  | Gaurishankar | 8
5844 | Dolakha | Pawati | 1 | GON | Cottage and Small Industry Office |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 25 | 25 |  |  |  | Melung | 1
5845 | Dolakha | Bhedapu | 2 | GON | Cottage and Small Industry Office |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 25 | 25 |  |  |  | Melung | 4
5846 | Dolakha | Suri | 5 | GON | Cottage and Small Industry Office |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 25 | 25 |  |  |  | Gaurishankar | 5
5847 | Dolakha | Jiri N.P. | 4 | GON | Cottage and Small Industry Office |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 25 | 25 |  |  |  | Jiri | 4
5848 | Dolakha | Jiri N.P. | 5 | GON | Cottage and Small Industry Office |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 25 | 25 |  |  |  | Jiri | 5
5849 | Dolakha | Jiri N.P. | 6 | GON | Cottage and Small Industry Office |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 25 | 25 |  |  |  | Jiri | 6
5850 | Dolakha | Bhusaphedi | 2 | GON | Cottage and Small Industry Office |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 25 | 24 |  |  |  | Sailung | 2
5851 | Dolakha | Bhimeswor N.P. | 6 | GON | Cottage and Small Industry Office |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 25 | 25 |  |  |  | Bhimeshwor | 5
5852 | Dolakha | Bhimeswor N.P. | 3 | GON | Cottage and Small Industry Office |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 25 | 25 |  |  |  | Bhimeshwor | 2
5853 | Dolakha | Bigu | 7 | GON | Cottage and Small Industry Office |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 25 | 25 |  |  |  | Bigu | 7
5854 | Dolakha | Chhetrapa | 8 | GON | Cottage and Small Industry Office |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 25 | 29 |  |  |  | Baiteshwor | 8
5855 | Dolakha | Kalingchok | 1 | GON | Cottage and Small Industry Office |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 25 | 27 |  |  |  | Kalinchok | 1
5856 | Dolakha | Bhimeswor N.P. | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | urban masonary training with brick and cement | # of trainees | Yes | Completed | 60 | 59 | 2018-03-15 | 2018-03-21 |  | Bhimeshwor | 5
5857 | Dolakha | Alampu | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 60 | 60 | 2018-03-21 | 2018-03-27 |  | Bigu | 6
5858 | Dolakha | Bhimeswor N.P. | 10 | NSET | NSET | USAID | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 32 | 32 | 2018-05-17 | 2018-05-21 |  | Bhimeshwor | 6
5859 | Dolakha | Babare | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Completed | 27 | 27 | 2018-05-28 | 2018-06-03 |  | Kalinchok | 2
5860 | Dolakha | Alampu | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 25 | 0 | 2018-06-05 | 2018-06-11 |  | Bigu | 6
5861 | Dolakha | Bigu | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 25 | 0 | 2018-06-05 | 2018-06-11 |  | Bigu | 7
5862 | Dolakha | Bhirkot | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Rural Masonary Training with stone and mud model frame | # of trainees | Yes | Planned | 25 | 0 | 2018-06-05 | 2018-06-11 |  | Tamakoshi | 1
5863 | Gorkha | Palumtar N.P. | 11 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Completed | 30 | 30 |  |  |  | Palungtar | 3
5864 | Gorkha | Palumtar N.P. | 12 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Completed | 30 | 30 |  |  |  | Palungtar | 2
5865 | Gorkha | Palumtar N.P. | 13 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Completed | 30 | 30 |  |  |  | Palungtar | 2
5866 | Gorkha | Palumtar N.P. | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Completed | 30 | 30 |  |  |  | Palungtar | 6
5867 | Gorkha | Palumtar N.P. | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Completed | 30 | 30 |  |  |  | Palungtar | 7
5868 | Gorkha | Palumtar N.P. | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Completed | 30 | 30 |  |  |  | Palungtar | 7
5869 | Gorkha | Palumtar N.P. | 11 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 3 | 3 |  |  |  | Palungtar | 3
5870 | Gorkha | Palumtar N.P. | 12 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 3 | 3 |  |  |  | Palungtar | 2
5871 | Gorkha | Palumtar N.P. | 13 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 3 | 3 |  |  |  | Palungtar | 2
5872 | Gorkha | Palumtar N.P. | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 3 | 3 |  |  |  | Palungtar | 6
5873 | Gorkha | Palumtar N.P. | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 3 | 3 |  |  |  | Palungtar | 7
5874 | Gorkha | Palumtar N.P. | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 3 | 3 |  |  |  | Palungtar | 7
5875 | Gorkha | Asrang | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Completed | 10 | 10 |  |  |  | Bhimsen | 6
5876 | Gorkha | Asrang | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Completed | 10 | 10 |  |  |  | Bhimsen | 6
5877 | Gorkha | Asrang | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Completed | 10 | 10 |  |  |  | Bhimsen | 6
5878 | Gorkha | Asrang | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Bhimsen | 6
5879 | Gorkha | Asrang | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Completed | 10 | 10 |  |  |  | Bhimsen | 6
5880 | Gorkha | Asrang | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Completed | 10 | 10 |  |  |  | Bhimsen | 6
5881 | Gorkha | Asrang | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Completed | 10 | 10 |  |  |  | Bhimsen | 6
5882 | Gorkha | Asrang | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Completed | 10 | 10 |  |  |  | Bhimsen | 6
5883 | Gorkha | Asrang | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 0 |  |  |  | Bhimsen | 6
5884 | Gorkha | Baguwa | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Bhimsen | 5
5885 | Gorkha | Baguwa | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Bhimsen | 5
5886 | Gorkha | Baguwa | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Bhimsen | 5
5887 | Gorkha | Baguwa | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Bhimsen | 5
5888 | Gorkha | Baguwa | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Bhimsen | 5
5889 | Gorkha | Baguwa | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Bhimsen | 5
5890 | Gorkha | Baguwa | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Bhimsen | 5
5891 | Gorkha | Baguwa | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Bhimsen | 5
5892 | Gorkha | Baguwa | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Bhimsen | 5
5893 | Gorkha | Bhumlichok | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Gandaki | 6
5894 | Gorkha | Bhumlichok | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Gandaki | 6
5895 | Gorkha | Bhumlichok | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Gandaki | 6
5896 | Gorkha | Bhumlichok | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Gandaki | 6
5897 | Gorkha | Bhumlichok | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Gandaki | 6
5898 | Gorkha | Bhumlichok | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Gandaki | 6
5899 | Gorkha | Bhumlichok | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Gandaki | 6
5900 | Gorkha | Bhumlichok | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Gandaki | 6
5901 | Gorkha | Bhumlichok | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Gandaki | 6
5902 | Gorkha | Borlang | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Bhimsen | 7
5903 | Gorkha | Borlang | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Bhimsen | 8
5904 | Gorkha | Borlang | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Bhimsen | 8
5905 | Gorkha | Borlang | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Bhimsen | 7
5906 | Gorkha | Borlang | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Bhimsen | 8
5907 | Gorkha | Borlang | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Bhimsen | 8
5908 | Gorkha | Borlang | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Bhimsen | 8
5909 | Gorkha | Borlang | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Bhimsen | 7
5910 | Gorkha | Borlang | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Bhimsen | 7
5911 | Gorkha | Chhoprak | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Siranchok | 5
5912 | Gorkha | Chhoprak | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 5
5913 | Gorkha | Chhoprak | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 5
5914 | Gorkha | Chhoprak | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 5
5915 | Gorkha | Chhoprak | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 5
5916 | Gorkha | Chhoprak | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 5
5917 | Gorkha | Chhoprak | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 4
5918 | Gorkha | Chhoprak | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 4
5919 | Gorkha | Chhoprak | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 4
5920 | Gorkha | Chumchet | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 6
5921 | Gorkha | Chumchet | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 6
5922 | Gorkha | Chumchet | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 6
5923 | Gorkha | Chumchet | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 6
5924 | Gorkha | Chumchet | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 6
5925 | Gorkha | Chumchet | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 6
5926 | Gorkha | Chumchet | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 6
5927 | Gorkha | Chumchet | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 6
5928 | Gorkha | Chumchet | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 6
5929 | Gorkha | Darbhung | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Gandaki | 5
5930 | Gorkha | Darbhung | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Gandaki | 5
5931 | Gorkha | Darbhung | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Gandaki | 5
5932 | Gorkha | Darbhung | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Gandaki | 5
5933 | Gorkha | Darbhung | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Gandaki | 5
5934 | Gorkha | Darbhung | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Gandaki | 5
5935 | Gorkha | Darbhung | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Gandaki | 5
5936 | Gorkha | Darbhung | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Gandaki | 5
5937 | Gorkha | Darbhung | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Gandaki | 5
5938 | Gorkha | Dhawa | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Bhimsen | 4
5939 | Gorkha | Dhawa | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Bhimsen | 4
5940 | Gorkha | Dhawa | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Bhimsen | 4
5941 | Gorkha | Dhawa | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Bhimsen | 4
5942 | Gorkha | Dhawa | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Bhimsen | 4
5943 | Gorkha | Dhawa | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Bhimsen | 4
5944 | Gorkha | Dhawa | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Bhimsen | 4
5945 | Gorkha | Dhawa | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Bhimsen | 4
5946 | Gorkha | Dhawa | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Bhimsen | 4
5947 | Gorkha | Jaubari | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 8
5948 | Gorkha | Jaubari | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 8
5949 | Gorkha | Jaubari | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 8
5950 | Gorkha | Jaubari | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 8
5951 | Gorkha | Jaubari | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 8
5952 | Gorkha | Jaubari | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 8
5953 | Gorkha | Jaubari | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 8
5954 | Gorkha | Jaubari | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 8
5955 | Gorkha | Jaubari | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Siranchok | 8
5956 | Gorkha | Kerabari | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 1
5957 | Gorkha | Kerabari | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 1
5958 | Gorkha | Kerabari | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 1
5959 | Gorkha | Kerabari | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 1
5960 | Gorkha | Kerabari | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 1
5961 | Gorkha | Kerabari | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 1
5962 | Gorkha | Kerabari | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 1
5963 | Gorkha | Kerabari | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 1
5964 | Gorkha | Kerabari | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 1
5965 | Gorkha | Kerauja | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 2
5966 | Gorkha | Kerauja | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 2
5967 | Gorkha | Kerauja | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 2
5968 | Gorkha | Kerauja | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 2
5969 | Gorkha | Kerauja | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 2
5970 | Gorkha | Kerauja | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 2
5971 | Gorkha | Kerauja | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 1
5972 | Gorkha | Kerauja | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 1
5973 | Gorkha | Kerauja | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 1
5974 | Gorkha | Laprak | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 4
5975 | Gorkha | Laprak | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 4
5976 | Gorkha | Laprak | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 4
5977 | Gorkha | Laprak | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 4
5978 | Gorkha | Laprak | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 4
5979 | Gorkha | Laprak | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 4
5980 | Gorkha | Laprak | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 4
5981 | Gorkha | Laprak | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 4
5982 | Gorkha | Laprak | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 4
5983 | Gorkha | Muchhok | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Ajirkot | 5
5984 | Gorkha | Muchhok | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Ajirkot | 5
5985 | Gorkha | Muchhok | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Ajirkot | 5
5986 | Gorkha | Muchhok | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Ajirkot | 5
5987 | Gorkha | Muchhok | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Ajirkot | 5
5988 | Gorkha | Muchhok | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Ajirkot | 5
5989 | Gorkha | Muchhok | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Ajirkot | 5
5990 | Gorkha | Muchhok | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Ajirkot | 5
5991 | Gorkha | Muchhok | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Ajirkot | 5
5992 | Gorkha | Namjung | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Sahid Lakhan | 9
5993 | Gorkha | Namjung | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Sahid Lakhan | 9
5994 | Gorkha | Namjung | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Sahid Lakhan | 9
5995 | Gorkha | Namjung | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Sahid Lakhan | 9
5996 | Gorkha | Namjung | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Sahid Lakhan | 9
5997 | Gorkha | Namjung | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Sahid Lakhan | 9
5998 | Gorkha | Namjung | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Sahid Lakhan | 9
5999 | Gorkha | Namjung | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Sahid Lakhan | 9
6000 | Gorkha | Namjung | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Sahid Lakhan | 9
6001 | Gorkha | Shreenathkot | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 7
6002 | Gorkha | Shreenathkot | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 7
6003 | Gorkha | Shreenathkot | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 7
6004 | Gorkha | Shreenathkot | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 7
6005 | Gorkha | Shreenathkot | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 7
6006 | Gorkha | Shreenathkot | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 7
6007 | Gorkha | Shreenathkot | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 7
6008 | Gorkha | Shreenathkot | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 7
6009 | Gorkha | Shreenathkot | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Siranchok | 7
6010 | Gorkha | Simjung | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Ajirkot | 4
6011 | Gorkha | Simjung | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Ajirkot | 4
6012 | Gorkha | Simjung | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Ajirkot | 4
6013 | Gorkha | Simjung | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Ajirkot | 4
6014 | Gorkha | Simjung | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Ajirkot | 4
6015 | Gorkha | Simjung | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Ajirkot | 4
6016 | Gorkha | Simjung | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Ajirkot | 4
6017 | Gorkha | Simjung | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Ajirkot | 4
6018 | Gorkha | Simjung | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Ajirkot | 4
6019 | Gorkha | Sirdibas | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 3
6020 | Gorkha | Sirdibas | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 3
6021 | Gorkha | Sirdibas | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 3
6022 | Gorkha | Sirdibas | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 3
6023 | Gorkha | Sirdibas | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 3
6024 | Gorkha | Sirdibas | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 3
6025 | Gorkha | Sirdibas | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 3
6026 | Gorkha | Sirdibas | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 3
6027 | Gorkha | Sirdibas | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 3
6028 | Gorkha | Uhya | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 3
6029 | Gorkha | Uhya | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 3
6030 | Gorkha | Uhya | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 3
6031 | Gorkha | Uhya | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 3
6032 | Gorkha | Uhya | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 3
6033 | Gorkha | Uhya | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 3
6034 | Gorkha | Uhya | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 3
6035 | Gorkha | Uhya | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 3
6036 | Gorkha | Uhya | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Dharche | 3
6037 | Gorkha | hansapur | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Ajirkot | 3
6038 | Gorkha | hansapur | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Ajirkot | 3
6039 | Gorkha | hansapur | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Ajirkot | 3
6040 | Gorkha | hansapur | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Ajirkot | 3
6041 | Gorkha | hansapur | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Ajirkot | 3
6042 | Gorkha | hansapur | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Ajirkot | 3
6043 | Gorkha | hansapur | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Ajirkot | 3
6044 | Gorkha | hansapur | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Ajirkot | 3
6045 | Gorkha | hansapur | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Ajirkot | 3
6046 | Gorkha | bhirkot | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Palungtar | 10
6047 | Gorkha | bhirkot | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Palungtar | 10
6048 | Gorkha | bhirkot | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Palungtar | 10
6049 | Gorkha | bhirkot | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Palungtar | 10
6050 | Gorkha | bhirkot | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Palungtar | 9
6051 | Gorkha | bhirkot | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Palungtar | 10
6052 | Gorkha | bhirkot | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Palungtar | 10
6053 | Gorkha | bhirkot | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Palungtar | 9
6054 | Gorkha | bhirkot | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Ongoing | 10 | 10 |  |  |  | Palungtar | 10
6055 | Gorkha | chhaikampar | 1 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 7
6056 | Gorkha | chhaikampar | 2 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 7
6057 | Gorkha | chhaikampar | 3 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 7
6058 | Gorkha | chhaikampar | 4 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 7
6059 | Gorkha | chhaikampar | 5 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 7
6060 | Gorkha | chhaikampar | 6 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 7
6061 | Gorkha | chhaikampar | 7 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 7
6062 | Gorkha | chhaikampar | 8 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 7
6063 | Gorkha | chhaikampar | 9 | GON - DLPIU | TCN | WB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training based on CTEVT level 1 | # of trainees |  | Planned | 10 | 0 |  |  |  | Chum Nubri | 7
6064 | Gorkha | Asrang | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 6
6065 | Gorkha | Asrang | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 6
6066 | Gorkha | Asrang | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 6
6067 | Gorkha | Asrang | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Bhimsen | 6
6068 | Gorkha | Asrang | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 6
6069 | Gorkha | Asrang | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 6
6070 | Gorkha | Asrang | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 6
6071 | Gorkha | Asrang | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 6
6072 | Gorkha | Asrang | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Bhimsen | 6
6073 | Gorkha | Baguwa | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Bhimsen | 5
6074 | Gorkha | Baguwa | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 5
6075 | Gorkha | Baguwa | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 5
6076 | Gorkha | Baguwa | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Bhimsen | 5
6077 | Gorkha | Baguwa | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Bhimsen | 5
6078 | Gorkha | Baguwa | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 5
6079 | Gorkha | Baguwa | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 5
6080 | Gorkha | Baguwa | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 5
6081 | Gorkha | Baguwa | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 5
6082 | Gorkha | Bhumlichok | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 6
6083 | Gorkha | Bhumlichok | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 6
6084 | Gorkha | Bhumlichok | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 6
6085 | Gorkha | Bhumlichok | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 6
6086 | Gorkha | Bhumlichok | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 6
6087 | Gorkha | Bhumlichok | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 6
6088 | Gorkha | Bhumlichok | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 6
6089 | Gorkha | Bhumlichok | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 6
6090 | Gorkha | Bhumlichok | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 6
6091 | Gorkha | Borlang | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Bhimsen | 7
6092 | Gorkha | Borlang | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Bhimsen | 8
6093 | Gorkha | Borlang | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 8
6094 | Gorkha | Borlang | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 7
6095 | Gorkha | Borlang | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 8
6096 | Gorkha | Borlang | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 8
6097 | Gorkha | Borlang | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Bhimsen | 8
6098 | Gorkha | Borlang | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 7
6099 | Gorkha | Borlang | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 7
6100 | Gorkha | Chhoprak | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 5
6101 | Gorkha | Chhoprak | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 5
6102 | Gorkha | Chhoprak | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 5
6103 | Gorkha | Chhoprak | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 5
6104 | Gorkha | Chhoprak | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 5
6105 | Gorkha | Chhoprak | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 5
6106 | Gorkha | Chhoprak | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 4
6107 | Gorkha | Chhoprak | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 4
6108 | Gorkha | Chhoprak | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 4
6109 | Gorkha | Chumchet | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 6
6110 | Gorkha | Chumchet | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 6
6111 | Gorkha | Chumchet | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 6
6112 | Gorkha | Chumchet | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 6
6113 | Gorkha | Chumchet | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 6
6114 | Gorkha | Chumchet | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 6
6115 | Gorkha | Chumchet | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 6
6116 | Gorkha | Chumchet | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 6
6117 | Gorkha | Chumchet | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 6
6118 | Gorkha | Darbhung | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 5
6119 | Gorkha | Darbhung | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 5
6120 | Gorkha | Darbhung | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 5
6121 | Gorkha | Darbhung | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 5
6122 | Gorkha | Darbhung | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 5
6123 | Gorkha | Darbhung | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 5
6124 | Gorkha | Darbhung | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 5
6125 | Gorkha | Darbhung | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 5
6126 | Gorkha | Darbhung | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 5
6127 | Gorkha | Dhawa | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 4
6128 | Gorkha | Dhawa | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 4
6129 | Gorkha | Dhawa | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 4
6130 | Gorkha | Dhawa | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Bhimsen | 4
6131 | Gorkha | Dhawa | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Bhimsen | 4
6132 | Gorkha | Dhawa | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Bhimsen | 4
6133 | Gorkha | Dhawa | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Bhimsen | 4
6134 | Gorkha | Dhawa | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Bhimsen | 4
6135 | Gorkha | Dhawa | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Bhimsen | 4
6136 | Gorkha | Jaubari | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 8
6137 | Gorkha | Jaubari | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 8
6138 | Gorkha | Jaubari | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 8
6139 | Gorkha | Jaubari | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 8
6140 | Gorkha | Jaubari | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 8
6141 | Gorkha | Jaubari | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 8
6142 | Gorkha | Jaubari | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 8
6143 | Gorkha | Jaubari | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 8
6144 | Gorkha | Jaubari | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 8
6145 | Gorkha | Kerabari | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 1
6146 | Gorkha | Kerabari | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 1
6147 | Gorkha | Kerabari | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 1
6148 | Gorkha | Kerabari | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 1
6149 | Gorkha | Kerabari | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 1
6150 | Gorkha | Kerabari | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 1
6151 | Gorkha | Kerabari | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 1
6152 | Gorkha | Kerabari | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 1
6153 | Gorkha | Kerabari | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 1
6154 | Gorkha | Kerauja | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 2
6155 | Gorkha | Kerauja | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 2
6156 | Gorkha | Kerauja | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 2
6157 | Gorkha | Kerauja | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 2
6158 | Gorkha | Kerauja | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 2
6159 | Gorkha | Kerauja | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 2
6160 | Gorkha | Kerauja | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 1
6161 | Gorkha | Kerauja | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 1
6162 | Gorkha | Kerauja | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 1
6163 | Gorkha | Laprak | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 4
6164 | Gorkha | Laprak | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 4
6165 | Gorkha | Laprak | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 4
6166 | Gorkha | Laprak | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 4
6167 | Gorkha | Laprak | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 4
6168 | Gorkha | Laprak | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 4
6169 | Gorkha | Laprak | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 4
6170 | Gorkha | Laprak | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 4
6171 | Gorkha | Laprak | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 4
6172 | Gorkha | Muchhok | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Ajirkot | 5
6173 | Gorkha | Muchhok | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Ajirkot | 5
6174 | Gorkha | Muchhok | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Ajirkot | 5
6175 | Gorkha | Muchhok | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Ajirkot | 5
6176 | Gorkha | Muchhok | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Ajirkot | 5
6177 | Gorkha | Muchhok | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Ajirkot | 5
6178 | Gorkha | Muchhok | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Ajirkot | 5
6179 | Gorkha | Muchhok | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Ajirkot | 5
6180 | Gorkha | Muchhok | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Ajirkot | 5
6181 | Gorkha | Namjung | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Sahid Lakhan | 9
6182 | Gorkha | Namjung | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Sahid Lakhan | 9
6183 | Gorkha | Namjung | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Sahid Lakhan | 9
6184 | Gorkha | Namjung | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Sahid Lakhan | 9
6185 | Gorkha | Namjung | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Sahid Lakhan | 9
6186 | Gorkha | Namjung | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Sahid Lakhan | 9
6187 | Gorkha | Namjung | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Sahid Lakhan | 9
6188 | Gorkha | Namjung | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Sahid Lakhan | 9
6189 | Gorkha | Namjung | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 9
6190 | Gorkha | Shreenathkot | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 7
6191 | Gorkha | Shreenathkot | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 7
6192 | Gorkha | Shreenathkot | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 7
6193 | Gorkha | Shreenathkot | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 7
6194 | Gorkha | Shreenathkot | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 7
6195 | Gorkha | Shreenathkot | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 7
6196 | Gorkha | Shreenathkot | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 7
6197 | Gorkha | Shreenathkot | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 7
6198 | Gorkha | Shreenathkot | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Siranchok | 7
6199 | Gorkha | Simjung | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 4
6200 | Gorkha | Simjung | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 4
6201 | Gorkha | Simjung | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 4
6202 | Gorkha | Simjung | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 4
6203 | Gorkha | Simjung | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 4
6204 | Gorkha | Simjung | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 4
6205 | Gorkha | Simjung | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 4
6206 | Gorkha | Simjung | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 4
6207 | Gorkha | Simjung | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 4
6208 | Gorkha | Sirdibas | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 3
6209 | Gorkha | Sirdibas | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 3
6210 | Gorkha | Sirdibas | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 3
6211 | Gorkha | Sirdibas | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 3
6212 | Gorkha | Sirdibas | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 3
6213 | Gorkha | Sirdibas | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 3
6214 | Gorkha | Sirdibas | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 3
6215 | Gorkha | Sirdibas | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 3
6216 | Gorkha | Sirdibas | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 3
6217 | Gorkha | Uhya | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 3
6218 | Gorkha | Uhya | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 3
6219 | Gorkha | Uhya | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 3
6220 | Gorkha | Uhya | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 3
6221 | Gorkha | Uhya | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 3
6222 | Gorkha | Uhya | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 3
6223 | Gorkha | Uhya | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 3
6224 | Gorkha | Uhya | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 3
6225 | Gorkha | Uhya | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 3
6226 | Gorkha | hansapur | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Ajirkot | 3
6227 | Gorkha | hansapur | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Ajirkot | 3
6228 | Gorkha | hansapur | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Ajirkot | 3
6229 | Gorkha | hansapur | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Ajirkot | 3
6230 | Gorkha | hansapur | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Ajirkot | 3
6231 | Gorkha | hansapur | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Ajirkot | 3
6232 | Gorkha | hansapur | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Ajirkot | 3
6233 | Gorkha | hansapur | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Ajirkot | 3
6234 | Gorkha | hansapur | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Ajirkot | 3
6235 | Gorkha | bhirkot | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Palungtar | 10
6236 | Gorkha | bhirkot | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Palungtar | 10
6237 | Gorkha | bhirkot | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Palungtar | 10
6238 | Gorkha | bhirkot | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Palungtar | 10
6239 | Gorkha | bhirkot | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 9
6240 | Gorkha | bhirkot | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Palungtar | 10
6241 | Gorkha | bhirkot | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Palungtar | 10
6242 | Gorkha | bhirkot | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Palungtar | 9
6243 | Gorkha | bhirkot | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Ongoing | 1 | 1 |  |  |  | Palungtar | 10
6244 | Gorkha | chhaikampar | 1 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 7
6245 | Gorkha | chhaikampar | 2 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 7
6246 | Gorkha | chhaikampar | 3 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 7
6247 | Gorkha | chhaikampar | 4 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 7
6248 | Gorkha | chhaikampar | 5 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 7
6249 | Gorkha | chhaikampar | 6 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 7
6250 | Gorkha | chhaikampar | 7 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 7
6251 | Gorkha | chhaikampar | 8 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 7
6252 | Gorkha | chhaikampar | 9 | GON - DLPIU | TCN | WB | Technical Assistance | Demonstration Construction | House | house construction of the most vulnerable HH during the Vocational training. | # of constructions |  | Planned | 1 | 0 |  |  |  | Chum Nubri | 7
6253 | Gorkha | AaruArbang | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-05 | 2017-06-20 |  | Aarughat | 6
6254 | Gorkha | AaruArbang | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 72 | 27 | 2017-05-21 |  |  | Aarughat | 6
6255 | Gorkha | AaruArbang | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 15 | 2017-03-17 |  |  | Aarughat | 6
6256 | Gorkha | AaruArbang | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 72 | 0 |  |  |  | Aarughat | 6
6257 | Gorkha | AaruArbang | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 72 | 0 |  |  |  | Aarughat | 6
6258 | Gorkha | AaruArbang | 1 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-06-06 | Baram Gaun CBRC | Aarughat | 6
6259 | Gorkha | AaruArbang | 1 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0 | 2016-09-01 | 2017-03-31 |  | Aarughat | 6
6260 | Gorkha | AaruArbang | 1 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-05 | 2017-06-13 |  | Aarughat | 6
6261 | Gorkha | AaruArbang | 1 | HELVETAS | Kantipur | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 50 | 50 | 2015-12-01 | 2016-01-30 |  | Aarughat | 6
6262 | Gorkha | AaruArbang | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-06 | 2017-06-20 |  | Aarughat | 6
6263 | Gorkha | AaruArbang | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 126 | 56 | 2017-05-21 |  |  | Aarughat | 6
6264 | Gorkha | AaruArbang | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 10 | 2017-03-17 |  |  | Aarughat | 6
6265 | Gorkha | AaruArbang | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 126 | 0 |  |  |  | Aarughat | 6
6266 | Gorkha | AaruArbang | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 126 | 0 |  |  |  | Aarughat | 6
6267 | Gorkha | AaruArbang | 2 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-06-22 | Alaiche CBRC | Aarughat | 6
6268 | Gorkha | AaruArbang | 2 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0 | 2016-09-01 | 2017-03-31 |  | Aarughat | 6
6269 | Gorkha | AaruArbang | 2 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-06 | 2017-06-12 |  | Aarughat | 6
6270 | Gorkha | AaruArbang | 2 | HELVETAS | Kantipur | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 50 | 50 | 2016-08-15 | 2016-10-03 |  | Aarughat | 6
6271 | Gorkha | AaruArbang | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-12 | 2017-06-20 |  | Aarughat | 6
6272 | Gorkha | AaruArbang | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 49 | 18 | 2017-05-21 |  |  | Aarughat | 6
6273 | Gorkha | AaruArbang | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 15 |  |  |  | Aarughat | 6
6274 | Gorkha | AaruArbang | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 49 | 0 |  |  |  | Aarughat | 6
6275 | Gorkha | AaruArbang | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 49 | 0 |  |  |  | Aarughat | 6
6276 | Gorkha | AaruArbang | 3 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-06-18 | Simle Kalleri CBRC | Aarughat | 6
6277 | Gorkha | AaruArbang | 3 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0 | 2016-09-01 | 2017-03-31 |  | Aarughat | 6
6278 | Gorkha | AaruArbang | 3 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-12 | 2017-06-18 |  | Aarughat | 6
6279 | Gorkha | AaruArbang | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-12 | 2017-06-20 |  | Aarughat | 6
6280 | Gorkha | AaruArbang | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 113 | 24 | 2017-05-21 |  |  | Aarughat | 6
6281 | Gorkha | AaruArbang | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 24 | 2017-03-17 |  |  | Aarughat | 6
6282 | Gorkha | AaruArbang | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 113 | 0 |  |  |  | Aarughat | 6
6283 | Gorkha | AaruArbang | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 113 | 0 |  |  |  | Aarughat | 6
6284 | Gorkha | AaruArbang | 4 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-06-18 | Kaleri CBRC | Aarughat | 6
6285 | Gorkha | AaruArbang | 4 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0 | 2016-09-01 | 2017-03-31 |  | Aarughat | 6
6286 | Gorkha | AaruArbang | 4 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-12 | 2017-06-18 |  | Aarughat | 6
6287 | Gorkha | AaruArbang | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Aarughat | 5
6288 | Gorkha | AaruArbang | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 174 | 75 | 2017-05-21 |  |  | Aarughat | 5
6289 | Gorkha | AaruArbang | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 20 | 2017-03-17 |  |  | Aarughat | 5
6290 | Gorkha | AaruArbang | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 174 | 0 |  |  |  | Aarughat | 5
6291 | Gorkha | AaruArbang | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 174 | 0 |  |  |  | Aarughat | 5
6292 | Gorkha | AaruArbang | 5 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-06-21 | Jyalbung CBRC | Aarughat | 5
6293 | Gorkha | AaruArbang | 5 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 20 | 0 | 2016-09-01 | 2017-03-31 |  | Aarughat | 5
6294 | Gorkha | AaruArbang | 5 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Aarughat | 5
6295 | Gorkha | AaruArbang | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-03 | 2017-06-20 |  | Aarughat | 6
6296 | Gorkha | AaruArbang | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 152 | 68 | 2017-05-21 |  |  | Aarughat | 6
6297 | Gorkha | AaruArbang | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 20 | 2017-03-17 |  |  | Aarughat | 6
6298 | Gorkha | AaruArbang | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 152 | 0 |  |  |  | Aarughat | 6
6299 | Gorkha | AaruArbang | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 152 | 0 |  |  |  | Aarughat | 6
6300 | Gorkha | AaruArbang | 6 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-06-19 | Aprik CBRC | Aarughat | 6
6301 | Gorkha | AaruArbang | 6 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 19 | 2017-01-04 | 2017-01-10 |  | Aarughat | 6
6302 | Gorkha | AaruArbang | 6 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-03 | 2017-06-09 |  | Aarughat | 6
6303 | Gorkha | AaruArbang | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Aarughat | 5
6304 | Gorkha | AaruArbang | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 101 | 34 | 2017-05-21 |  |  | Aarughat | 5
6305 | Gorkha | AaruArbang | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 10 | 2017-03-17 |  |  | Aarughat | 5
6306 | Gorkha | AaruArbang | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 101 | 0 |  |  |  | Aarughat | 5
6307 | Gorkha | AaruArbang | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 101 | 0 |  |  |  | Aarughat | 5
6308 | Gorkha | AaruArbang | 7 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-19 | Devithan Thulo Pakhure CBRC | Aarughat | 5
6309 | Gorkha | AaruArbang | 7 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 21 | 2016-12-03 | 2016-12-09 |  | Aarughat | 5
6310 | Gorkha | AaruArbang | 7 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Aarughat | 5
6311 | Gorkha | AaruArbang | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-02-27 | 2017-06-20 |  | Aarughat | 5
6312 | Gorkha | AaruArbang | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 164 | 61 | 2017-05-21 |  |  | Aarughat | 5
6313 | Gorkha | AaruArbang | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 13 | 2017-03-17 |  |  | Aarughat | 5
6314 | Gorkha | AaruArbang | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 164 | 0 |  |  |  | Aarughat | 5
6315 | Gorkha | AaruArbang | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 164 | 0 |  |  |  | Aarughat | 5
6316 | Gorkha | AaruArbang | 8 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-20 | Devithan sano Pakhure CBRC | Aarughat | 5
6317 | Gorkha | AaruArbang | 8 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-26 | Oyak CBRC | Aarughat | 5
6318 | Gorkha | AaruArbang | 8 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-02-03 | 2017-02-09 |  | Aarughat | 5
6319 | Gorkha | AaruArbang | 8 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Completed | 10 | 10 | 2017-03-05 | 2017-05-01 |  | Aarughat | 5
6320 | Gorkha | AaruArbang | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Aarughat | 5
6321 | Gorkha | AaruArbang | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 139 | 30 | 2017-05-21 |  |  | Aarughat | 5
6322 | Gorkha | AaruArbang | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 14 |  |  |  | Aarughat | 5
6323 | Gorkha | AaruArbang | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 139 | 0 |  |  |  | Aarughat | 5
6324 | Gorkha | AaruArbang | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 139 | 0 |  |  |  | Aarughat | 5
6325 | Gorkha | AaruArbang | 9 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-26 | Shanti Bazar CBRC | Aarughat | 5
6326 | Gorkha | AaruArbang | 9 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-09-01 | 2017-03-31 |  | Aarughat | 5
6327 | Gorkha | AaruArbang | 9 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Aarughat | 5
6328 | Gorkha | AaruArbang | All | HELVETAS | Kantipur | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-06-13 | 2016-10-03 |  | Aarughat | 6
6329 | Gorkha | AaruArbang | All | HELVETAS | Kantipur | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-13 | 2016-09-18 |  | Aarughat | 6
6330 | Gorkha | AaruChanuate | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Aarughat | 9
6331 | Gorkha | AaruChanuate | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 181 | 12 | 2017-05-21 |  |  | Aarughat | 9
6332 | Gorkha | AaruChanuate | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 1 |  |  |  | Aarughat | 9
6333 | Gorkha | AaruChanuate | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 181 | 0 |  |  |  | Aarughat | 9
6334 | Gorkha | AaruChanuate | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 181 | 0 |  |  |  | Aarughat | 9
6335 | Gorkha | AaruChanuate | 1 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-06-03 | Mathillo Bazar CBRC | Aarughat | 9
6336 | Gorkha | AaruChanuate | 1 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 7 | 3 | 2016-12-08 | 2016-12-14 |  | Aarughat | 9
6337 | Gorkha | AaruChanuate | 1 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Aarughat | 9
6338 | Gorkha | AaruChanuate | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Aarughat | 9
6339 | Gorkha | AaruChanuate | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 21 | 11 | 2017-05-21 |  |  | Aarughat | 9
6340 | Gorkha | AaruChanuate | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 4 |  |  |  | Aarughat | 9
6341 | Gorkha | AaruChanuate | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 21 | 0 |  |  |  | Aarughat | 9
6342 | Gorkha | AaruChanuate | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 21 | 0 |  |  |  | Aarughat | 9
6343 | Gorkha | AaruChanuate | 2 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-31 | Tallo Bazar CBRC | Aarughat | 9
6344 | Gorkha | AaruChanuate | 2 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 10 | 0 | 2016-09-01 | 2017-03-31 |  | Aarughat | 9
6345 | Gorkha | AaruChanuate | 2 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Aarughat | 9
6346 | Gorkha | AaruChanuate | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Aarughat | 9
6347 | Gorkha | AaruChanuate | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 178 | 70 | 2017-05-21 |  |  | Aarughat | 9
6348 | Gorkha | AaruChanuate | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 17 | 2017-03-17 |  |  | Aarughat | 9
6349 | Gorkha | AaruChanuate | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 178 | 0 |  |  |  | Aarughat | 9
6350 | Gorkha | AaruChanuate | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 178 | 0 |  |  |  | Aarughat | 9
6351 | Gorkha | AaruChanuate | 3 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-06-01 | Arutar CBRC | Aarughat | 9
6352 | Gorkha | AaruChanuate | 3 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-12-08 | 2016-12-14 |  | Aarughat | 9
6353 | Gorkha | AaruChanuate | 3 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Aarughat | 9
6354 | Gorkha | AaruChanuate | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-02-24 | 2017-06-20 |  | Aarughat | 10
6355 | Gorkha | AaruChanuate | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 108 | 49 | 2017-05-21 |  |  | Aarughat | 10
6356 | Gorkha | AaruChanuate | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 28 | 2017-03-17 |  |  | Aarughat | 10
6357 | Gorkha | AaruChanuate | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 108 | 0 |  |  |  | Aarughat | 10
6358 | Gorkha | AaruChanuate | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 108 | 0 |  |  |  | Aarughat | 10
6359 | Gorkha | AaruChanuate | 4 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-30 | Sitala mangaltar CBRC | Aarughat | 10
6360 | Gorkha | AaruChanuate | 4 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-30 | Jalkanya Chanaute CBRC | Aarughat | 10
6361 | Gorkha | AaruChanuate | 4 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-12-08 | 2016-12-14 |  | Aarughat | 10
6362 | Gorkha | AaruChanuate | 4 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-25 | 2017-04-20 |  | Aarughat | 10
6363 | Gorkha | AaruChanuate | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Aarughat | 10
6364 | Gorkha | AaruChanuate | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 73 | 16 | 2017-05-21 |  |  | Aarughat | 10
6365 | Gorkha | AaruChanuate | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 15 | 2017-03-17 |  |  | Aarughat | 10
6366 | Gorkha | AaruChanuate | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 73 | 0 |  |  |  | Aarughat | 10
6367 | Gorkha | AaruChanuate | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 73 | 0 |  |  |  | Aarughat | 10
6368 | Gorkha | AaruChanuate | 5 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-29 | Shiva Shakit CBRC | Aarughat | 10
6369 | Gorkha | AaruChanuate | 5 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-28 | 2017-02-03 |  | Aarughat | 10
6370 | Gorkha | AaruChanuate | 5 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Aarughat | 10
6371 | Gorkha | AaruChanuate | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-18 | 2017-06-20 |  | Aarughat | 10
6372 | Gorkha | AaruChanuate | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 34 | 25 | 2017-05-21 |  |  | Aarughat | 10
6373 | Gorkha | AaruChanuate | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 13 | 2017-03-17 |  |  | Aarughat | 10
6374 | Gorkha | AaruChanuate | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 34 | 0 |  |  |  | Aarughat | 10
6375 | Gorkha | AaruChanuate | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 34 | 0 |  |  |  | Aarughat | 10
6376 | Gorkha | AaruChanuate | 6 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-28 | Khatri Swanra CBRC | Aarughat | 10
6377 | Gorkha | AaruChanuate | 6 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 18 | 18 | 2016-12-24 | 2016-12-30 |  | Aarughat | 10
6378 | Gorkha | AaruChanuate | 6 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-18 | 2017-06-25 |  | Aarughat | 10
6379 | Gorkha | AaruChanuate | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-30 | 2017-06-20 |  | Aarughat | 10
6380 | Gorkha | AaruChanuate | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 67 | 36 | 2017-05-21 |  |  | Aarughat | 10
6381 | Gorkha | AaruChanuate | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 6 | 2017-03-17 |  |  | Aarughat | 10
6382 | Gorkha | AaruChanuate | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 67 | 0 |  |  |  | Aarughat | 10
6383 | Gorkha | AaruChanuate | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 67 | 0 |  |  |  | Aarughat | 10
6384 | Gorkha | AaruChanuate | 7 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-24 | Pallo Danda CBRC | Aarughat | 10
6385 | Gorkha | AaruChanuate | 7 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 7 | 3 | 2016-09-01 | 2017-03-31 |  | Aarughat | 10
6386 | Gorkha | AaruChanuate | 7 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-30 | 2017-06-25 |  | Aarughat | 10
6387 | Gorkha | AaruChanuate | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-17 | 2017-06-20 |  | Aarughat | 10
6388 | Gorkha | AaruChanuate | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 50 | 29 | 2017-05-21 |  |  | Aarughat | 10
6389 | Gorkha | AaruChanuate | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 10 | 2017-03-17 |  |  | Aarughat | 10
6390 | Gorkha | AaruChanuate | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 50 | 0 |  |  |  | Aarughat | 10
6391 | Gorkha | AaruChanuate | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 50 | 0 |  |  |  | Aarughat | 10
6392 | Gorkha | AaruChanuate | 8 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-26 | Dada Gaun Deurali CBRC | Aarughat | 10
6393 | Gorkha | AaruChanuate | 8 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 3 | 2016-12-24 | 2016-12-30 |  | Aarughat | 10
6394 | Gorkha | AaruChanuate | 8 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-17 | 2017-06-25 |  | Aarughat | 10
6395 | Gorkha | AaruChanuate | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-30 | 2017-06-20 |  | Aarughat | 10
6396 | Gorkha | AaruChanuate | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 55 | 24 | 2017-05-21 |  |  | Aarughat | 10
6397 | Gorkha | AaruChanuate | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 10 |  |  |  | Aarughat | 10
6398 | Gorkha | AaruChanuate | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 55 | 0 |  |  |  | Aarughat | 10
6399 | Gorkha | AaruChanuate | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 55 | 0 |  |  |  | Aarughat | 10
6400 | Gorkha | AaruChanuate | 9 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-27 | Siddakali CBRC | Aarughat | 10
6401 | Gorkha | AaruChanuate | 9 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 18 | 18 | 2016-12-24 | 2016-12-30 |  | Aarughat | 10
6402 | Gorkha | AaruChanuate | 9 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-30 | 2017-06-25 |  | Aarughat | 10
6403 | Gorkha | AaruChanuate |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 91 |  |  |  | Aarughat | 10
6404 | Gorkha | Aarupokhari | 1 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Aarughat | 7
6405 | Gorkha | Aarupokhari | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 226 | 25 | 2017-05-21 |  |  | Aarughat | 7
6406 | Gorkha | Aarupokhari | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 13 | 2017-03-17 |  |  | Aarughat | 7
6407 | Gorkha | Aarupokhari | 1 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 226 | 0 |  |  |  | Aarughat | 7
6408 | Gorkha | Aarupokhari | 1 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 226 | 0 |  |  |  | Aarughat | 7
6409 | Gorkha | Aarupokhari | 1 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-16 | Arubotea CBRC | Aarughat | 7
6410 | Gorkha | Aarupokhari | 1 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-17 | Satdobato CBRC | Aarughat | 7
6411 | Gorkha | Aarupokhari | 1 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-12-10 | 2016-12-16 |  | Aarughat | 7
6412 | Gorkha | Aarupokhari | 1 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Aarughat | 7
6413 | Gorkha | Aarupokhari | 2 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-07 | 2017-06-20 |  | Aarughat | 7
6414 | Gorkha | Aarupokhari | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 121 | 11 | 2017-05-21 |  |  | Aarughat | 7
6415 | Gorkha | Aarupokhari | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 9 | 2017-03-17 |  |  | Aarughat | 7
6416 | Gorkha | Aarupokhari | 2 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 121 | 0 |  |  |  | Aarughat | 7
6417 | Gorkha | Aarupokhari | 2 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 121 | 0 |  |  |  | Aarughat | 7
6418 | Gorkha | Aarupokhari | 2 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-17 | Shree Pravakari CBRC | Aarughat | 7
6419 | Gorkha | Aarupokhari | 2 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-12-10 | 2016-12-16 |  | Aarughat | 7
6420 | Gorkha | Aarupokhari | 2 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-07 | 2017-06-25 |  | Aarughat | 7
6421 | Gorkha | Aarupokhari | 3 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-20 | 2017-06-20 |  | Aarughat | 8
6422 | Gorkha | Aarupokhari | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 82 | 14 | 2017-05-21 |  |  | Aarughat | 8
6423 | Gorkha | Aarupokhari | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 5 | 2017-03-17 |  |  | Aarughat | 8
6424 | Gorkha | Aarupokhari | 3 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 82 | 0 |  |  |  | Aarughat | 8
6425 | Gorkha | Aarupokhari | 3 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 82 | 0 |  |  |  | Aarughat | 8
6426 | Gorkha | Aarupokhari | 3 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-19 | Nawanirmit CBRC | Aarughat | 8
6427 | Gorkha | Aarupokhari | 3 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 19 | 19 | 2016-12-14 | 2016-12-20 |  | Aarughat | 8
6428 | Gorkha | Aarupokhari | 3 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-20 | 2017-06-25 |  | Aarughat | 8
6429 | Gorkha | Aarupokhari | 4 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-24 | 2017-06-20 |  | Aarughat | 8
6430 | Gorkha | Aarupokhari | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 123 | 38 | 2017-05-21 |  |  | Aarughat | 8
6431 | Gorkha | Aarupokhari | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 12 | 2017-03-17 |  |  | Aarughat | 8
6432 | Gorkha | Aarupokhari | 4 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 123 | 0 |  |  |  | Aarughat | 8
6433 | Gorkha | Aarupokhari | 4 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 123 | 0 |  |  |  | Aarughat | 8
6434 | Gorkha | Aarupokhari | 4 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-18 | Pokhari Chock CBRC | Aarughat | 8
6435 | Gorkha | Aarupokhari | 4 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-12-10 | 2016-12-16 |  | Aarughat | 8
6436 | Gorkha | Aarupokhari | 4 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Completed | 10 | 10 | 2017-03-24 | 2017-06-25 |  | Aarughat | 8
6437 | Gorkha | Aarupokhari | 5 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-27 | 2017-06-20 |  | Aarughat | 7
6438 | Gorkha | Aarupokhari | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 89 | 12 | 2017-03-21 |  |  | Aarughat | 7
6439 | Gorkha | Aarupokhari | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 9 | 2017-03-17 |  |  | Aarughat | 7
6440 | Gorkha | Aarupokhari | 5 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 89 | 0 |  |  |  | Aarughat | 7
6441 | Gorkha | Aarupokhari | 5 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 89 | 0 |  |  |  | Aarughat | 7
6442 | Gorkha | Aarupokhari | 5 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-15 | Pragatisil CBRC | Aarughat | 7
6443 | Gorkha | Aarupokhari | 5 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-12-10 | 2016-12-16 |  | Aarughat | 7
6444 | Gorkha | Aarupokhari | 5 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-27 | 2017-06-25 |  | Aarughat | 7
6445 | Gorkha | Aarupokhari | 6 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-20 | 2017-06-20 |  | Aarughat | 8
6446 | Gorkha | Aarupokhari | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 85 | 11 | 2017-05-21 |  |  | Aarughat | 8
6447 | Gorkha | Aarupokhari | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 5 | 2017-03-17 |  |  | Aarughat | 8
6448 | Gorkha | Aarupokhari | 6 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 85 | 0 |  |  |  | Aarughat | 8
6449 | Gorkha | Aarupokhari | 6 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 85 | 0 |  |  |  | Aarughat | 8
6450 | Gorkha | Aarupokhari | 6 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-16 | Saugat CBRC | Aarughat | 8
6451 | Gorkha | Aarupokhari | 6 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-12-14 | 2016-12-20 |  | Aarughat | 8
6452 | Gorkha | Aarupokhari | 6 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Completed | 10 | 10 | 2017-03-20 | 2017-05-01 |  | Aarughat | 8
6453 | Gorkha | Aarupokhari | 7 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-11 | 2017-06-20 |  | Aarughat | 8
6454 | Gorkha | Aarupokhari | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 100 | 10 | 2017-05-21 |  |  | Aarughat | 8
6455 | Gorkha | Aarupokhari | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 4 | 2017-03-17 |  |  | Aarughat | 8
6456 | Gorkha | Aarupokhari | 7 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 100 | 0 |  |  |  | Aarughat | 8
6457 | Gorkha | Aarupokhari | 7 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 100 | 0 |  |  |  | Aarughat | 8
6458 | Gorkha | Aarupokhari | 7 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-23 | Namuna CBRC | Aarughat | 8
6459 | Gorkha | Aarupokhari | 7 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-12-03 | 2016-12-09 |  | Aarughat | 8
6460 | Gorkha | Aarupokhari | 7 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-11 | 2017-06-25 |  | Aarughat | 8
6461 | Gorkha | Aarupokhari | 8 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-22 | 2017-06-20 |  | Aarughat | 8
6462 | Gorkha | Aarupokhari | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 148 | 18 | 2017-05-21 |  |  | Aarughat | 8
6463 | Gorkha | Aarupokhari | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 10 | 2017-03-17 |  |  | Aarughat | 8
6464 | Gorkha | Aarupokhari | 8 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 148 | 0 |  |  |  | Aarughat | 8
6465 | Gorkha | Aarupokhari | 8 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 148 | 0 |  |  |  | Aarughat | 8
6466 | Gorkha | Aarupokhari | 8 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-22 | Janachetana CBRC | Aarughat | 8
6467 | Gorkha | Aarupokhari | 8 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-26 | Prativa CBRC | Aarughat | 8
6468 | Gorkha | Aarupokhari | 8 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-12-03 | 2016-12-09 |  | Aarughat | 8
6469 | Gorkha | Aarupokhari | 8 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-22 | 2017-06-25 |  | Aarughat | 8
6470 | Gorkha | Aarupokhari | 9 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-16 | 2017-06-20 |  | Aarughat | 7
6471 | Gorkha | Aarupokhari | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 182 | 17 | 2017-05-21 |  |  | Aarughat | 7
6472 | Gorkha | Aarupokhari | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 19 | 2017-03-17 |  |  | Aarughat | 7
6473 | Gorkha | Aarupokhari | 9 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 182 | 0 |  |  |  | Aarughat | 7
6474 | Gorkha | Aarupokhari | 9 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions | BBS Messaging to the HHs in the Community | # of households | Yes | Planned | 182 | 0 |  |  |  | Aarughat | 7
6475 | Gorkha | Aarupokhari | 9 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-19 | Nawanirmit CBRC | Aarughat | 7
6476 | Gorkha | Aarupokhari | 9 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 17 | 2017-02-12 | 2017-02-18 |  | Aarughat | 7
6477 | Gorkha | Aarupokhari | 9 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-16 | 2017-06-25 |  | Aarughat | 7
6478 | Gorkha | Aarupokhari | All | CRS | SDSC |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 6 | 6 | 2017-03-17 |  |  | Aarughat | 8
6479 | Gorkha | Aarupokhari | All | HELVETAS | PANCHA KANYA | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-06-02 | 2016-08-06 |  | Aarughat | 8
6480 | Gorkha | Aarupokhari | All | HELVETAS | PANCHA KANYA | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 120 | 120 | 2016-06-02 | 2016-08-06 |  | Aarughat | 8
6481 | Gorkha | Asrang | 1 | CA | PANCHA KANYA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 6
6482 | Gorkha | Asrang | 1 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 6
6483 | Gorkha | Asrang | 1 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-01 | 2016-05-15 |  | Bhimsen | 6
6484 | Gorkha | Asrang | 2 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 6
6485 | Gorkha | Asrang | 2 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 6
6486 | Gorkha | Asrang | 2 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-01 | 2016-05-15 |  | Bhimsen | 6
6487 | Gorkha | Asrang | 3 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 6
6488 | Gorkha | Asrang | 3 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 6
6489 | Gorkha | Asrang | 3 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-01 | 2016-05-15 |  | Bhimsen | 6
6490 | Gorkha | Asrang | 4 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 6
6491 | Gorkha | Asrang | 4 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 6
6492 | Gorkha | Asrang | 4 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-01 | 2016-05-15 |  | Bhimsen | 6
6493 | Gorkha | Asrang | 5 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 6
6494 | Gorkha | Asrang | 5 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 6
6495 | Gorkha | Asrang | 5 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-01 | 2016-05-15 |  | Bhimsen | 6
6496 | Gorkha | Asrang | 6 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 7 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 6
6497 | Gorkha | Asrang | 6 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 6
6498 | Gorkha | Asrang | 6 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-01 | 2016-05-15 |  | Bhimsen | 6
6499 | Gorkha | Asrang | 7 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 6
6500 | Gorkha | Asrang | 7 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 6
6501 | Gorkha | Asrang | 7 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-01 | 2016-05-15 |  | Bhimsen | 6
6502 | Gorkha | Asrang | 8 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 11 | 11 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 6
6503 | Gorkha | Asrang | 8 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 6
6504 | Gorkha | Asrang | 8 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-01 | 2016-05-15 |  | Bhimsen | 6
6505 | Gorkha | Asrang | 9 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 6
6506 | Gorkha | Asrang | 9 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 6
6507 | Gorkha | Asrang | 9 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-01 | 2016-05-15 |  | Bhimsen | 6
6508 | Gorkha | Asrang | All | GON - PAF | SDSC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0 |  |  |  | Bhimsen | 6
6509 | Gorkha | Asrang |  | CA | GORETO GORKHA | CA | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Completed | 2 | 2 |  |  |  | Bhimsen | 6
6510 | Gorkha | Asrang |  | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households |  | Completed | 60 | 60 |  |  |  | Bhimsen | 6
6511 | Gorkha | Asrang |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 52 |  |  |  | Bhimsen | 6
6512 | Gorkha | Asrang |  | PA | GORETO GORKHA | PA-UK | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 10 | 10 | 2016-02-07 | 2016-02-11 |  | Bhimsen | 6
6513 | Gorkha | Asrang | All | PA | GORETO GORKHA | PA-UK | Training | Vocational training | Plumber (CTEVT) |  | # of trainees | Yes | Completed | 8 | 8 | 2015-12-13 | 2016-01-13 |  | Bhimsen | 6
6514 | Gorkha | Baguwa | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Ward no. 1 Purna Nirman Samudaik Samiti | Bhimsen | 5
6515 | Gorkha | Baguwa | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-11 | 2016-06-17 |  | Bhimsen | 5
6516 | Gorkha | Baguwa | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Dudh Kanya Devi Purna Nirman Samudaik Samiti | Bhimsen | 5
6517 | Gorkha | Baguwa | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-11 | 2016-06-17 |  | Bhimsen | 5
6518 | Gorkha | Baguwa | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Shiva Purna Nirman Samudaik Samiti | Bhimsen | 5
6519 | Gorkha | Baguwa | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-11 | 2016-06-17 |  | Bhimsen | 5
6520 | Gorkha | Baguwa | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Eakikrit Milan Basti Purna Nirman Samudaik Samiti | Bhimsen | 5
6521 | Gorkha | Baguwa | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-11 | 2016-06-17 |  | Bhimsen | 5
6522 | Gorkha | Baguwa | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-11 | 2016-06-17 |  | Bhimsen | 5
6523 | Gorkha | Baguwa | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Machha Pokhari Purna Nirman Samudaik Samiti | Bhimsen | 5
6524 | Gorkha | Baguwa | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-11 | 2016-06-17 |  | Bhimsen | 5
6525 | Gorkha | Baguwa | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-21 | Chandi Purna Nirman Samudaik Samiti | Bhimsen | 5
6526 | Gorkha | Baguwa | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-11 | 2016-06-17 |  | Bhimsen | 5
6527 | Gorkha | Baguwa | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Shiva Mandir Purna Nirman Samudaik Samiti | Bhimsen | 5
6528 | Gorkha | Baguwa | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-11 | 2016-06-17 |  | Bhimsen | 5
6529 | Gorkha | Baguwa | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Nawa Jagaran Purna Nirman Samudaik Samiti | Bhimsen | 5
6530 | Gorkha | Baguwa | All | JICA |  |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 653 | 653 | 2017-05-03 |  |  | Bhimsen | 5
6531 | Gorkha | Baguwa | All | DCA | ECO-N | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 31 | 31 | 2016-03-07 | 2016-03-11 |  | Bhimsen | 5
6532 | Gorkha | Baguwa |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 75 |  |  |  | Bhimsen | 5
6533 | Gorkha | Bakrang | All | OXFAM-GB |  |  | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 856 | 856 |  |  |  | Sahid Lakhan | 1
6534 | Gorkha | Bakrang |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 268 |  |  |  | Sahid Lakhan | 1
6535 | Gorkha | Bhirkot |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 484 |  |  |  | Palungtar | 10
6536 | Gorkha | Bhumlichok | 5 | ACN | ACN | INFUK-GZB-Others | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-08-20 | 2016-08-27 | We are planning to give this training for skill manpower | Gandaki | 6
6537 | Gorkha | Bhumlichok | All | DCA | ECO-N | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 17 | 2016-01-25 | 2016-01-29 |  | Gandaki | 6
6538 | Gorkha | Bhumlichok | All | GON - PAF | GORETO GORKHA | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0 |  |  |  | Gandaki | 6
6539 | Gorkha | Bihi | 1 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Chum Nubri | 5
6540 | Gorkha | Bihi | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 17 | 0 |  |  |  | Chum Nubri | 5
6541 | Gorkha | Bihi | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 5
6542 | Gorkha | Bihi | 1 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 17 | 0 |  |  |  | Chum Nubri | 5
6543 | Gorkha | Bihi | 1 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 17 | 0 |  |  |  | Chum Nubri | 5
6544 | Gorkha | Bihi | 1 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-01-01 | 2017-01-07 |  | Chum Nubri | 5
6545 | Gorkha | Bihi | 1 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 5
6546 | Gorkha | Bihi | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 30 | 0 |  |  |  | Chum Nubri | 5
6547 | Gorkha | Bihi | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 5
6548 | Gorkha | Bihi | 2 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 30 | 0 |  |  |  | Chum Nubri | 5
6549 | Gorkha | Bihi | 2 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 30 | 0 |  |  |  | Chum Nubri | 5
6550 | Gorkha | Bihi | 2 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-01-01 | 2017-01-07 |  | Chum Nubri | 5
6551 | Gorkha | Bihi | 2 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 5
6552 | Gorkha | Bihi | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 32 | 0 |  |  |  | Chum Nubri | 5
6553 | Gorkha | Bihi | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 5
6554 | Gorkha | Bihi | 3 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 32 | 0 |  |  |  | Chum Nubri | 5
6555 | Gorkha | Bihi | 3 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 32 | 0 |  |  |  | Chum Nubri | 5
6556 | Gorkha | Bihi | 3 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-01-01 | 2017-01-07 |  | Chum Nubri | 5
6557 | Gorkha | Bihi | 3 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 5
6558 | Gorkha | Bihi | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 5
6559 | Gorkha | Bihi | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 5
6560 | Gorkha | Bihi | 4 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 5
6561 | Gorkha | Bihi | 4 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 5
6562 | Gorkha | Bihi | 4 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-01-01 | 2017-01-07 |  | Chum Nubri | 5
6563 | Gorkha | Bihi | 4 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 5
6564 | Gorkha | Bihi | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 5
6565 | Gorkha | Bihi | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 5
6566 | Gorkha | Bihi | 5 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 5
6567 | Gorkha | Bihi | 5 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 5
6568 | Gorkha | Bihi | 5 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 | 2016-09-01 | 2017-03-31 |  | Chum Nubri | 5
6569 | Gorkha | Bihi | 5 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 5
6570 | Gorkha | Bihi | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 16 | 0 |  |  |  | Chum Nubri | 5
6571 | Gorkha | Bihi | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 5
6572 | Gorkha | Bihi | 6 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 16 | 0 |  |  |  | Chum Nubri | 5
6573 | Gorkha | Bihi | 6 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 16 | 0 |  |  |  | Chum Nubri | 5
6574 | Gorkha | Bihi | 6 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-01-01 | 2017-01-07 |  | Chum Nubri | 5
6575 | Gorkha | Bihi | 6 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 5
6576 | Gorkha | Bihi | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 26 | 0 |  |  |  | Chum Nubri | 5
6577 | Gorkha | Bihi | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 5
6578 | Gorkha | Bihi | 7 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 26 | 0 |  |  |  | Chum Nubri | 5
6579 | Gorkha | Bihi | 7 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 26 | 0 |  |  |  | Chum Nubri | 5
6580 | Gorkha | Bihi | 7 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-01-01 | 2017-01-07 |  | Chum Nubri | 5
6581 | Gorkha | Bihi | 7 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 5
6582 | Gorkha | Bihi | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 40 | 0 |  |  |  | Chum Nubri | 5
6583 | Gorkha | Bihi | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 5
6584 | Gorkha | Bihi | 8 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 40 | 0 |  |  |  | Chum Nubri | 5
6585 | Gorkha | Bihi | 8 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 40 | 0 |  |  |  | Chum Nubri | 5
6586 | Gorkha | Bihi | 8 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-07-09 |  | Chum Nubri | 5
6587 | Gorkha | Bihi | 8 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-01-01 | 2017-01-07 |  | Chum Nubri | 5
6588 | Gorkha | Bihi | 8 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 5
6589 | Gorkha | Bihi | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 37 | 0 |  |  |  | Chum Nubri | 5
6590 | Gorkha | Bihi | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 0 |  |  |  | Chum Nubri | 5
6591 | Gorkha | Bihi | 9 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 37 | 0 |  |  |  | Chum Nubri | 5
6592 | Gorkha | Bihi | 9 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 37 | 0 |  |  |  | Chum Nubri | 5
6593 | Gorkha | Bihi | 9 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-07-10 |  | Chum Nubri | 5
6594 | Gorkha | Bihi | 9 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-01-01 | 2017-01-07 |  | Chum Nubri | 5
6595 | Gorkha | Bihi | 9 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 5
6596 | Gorkha | Bihi | 1,2,3 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-06-06 |  | Chum Nubri | 5
6597 | Gorkha | Bihi | 5,6,7 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-07-05 |  | Chum Nubri | 5
6598 | Gorkha | Borlang | 1 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 7
6599 | Gorkha | Borlang | 1 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 7
6600 | Gorkha | Borlang | 2 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 8
6601 | Gorkha | Borlang | 2 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 8
6602 | Gorkha | Borlang | 3 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 5 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 8
6603 | Gorkha | Borlang | 3 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 8
6604 | Gorkha | Borlang | 4 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 7
6605 | Gorkha | Borlang | 4 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 7
6606 | Gorkha | Borlang | 5 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 8
6607 | Gorkha | Borlang | 5 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 8
6608 | Gorkha | Borlang | 6 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 7 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 8
6609 | Gorkha | Borlang | 6 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 8
6610 | Gorkha | Borlang | 7 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 9 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 8
6611 | Gorkha | Borlang | 7 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 8
6612 | Gorkha | Borlang | 8 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 7
6613 | Gorkha | Borlang | 8 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 7
6614 | Gorkha | Borlang | 9 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 10 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 7
6615 | Gorkha | Borlang | 9 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-09-27 | 2016-10-04 |  | Bhimsen | 7
6616 | Gorkha | Borlang |  | CA | GORETO GORKHA | CA | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Completed | 2 | 2 |  |  |  | Bhimsen | 8
6617 | Gorkha | Borlang |  | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 60 | 60 |  |  |  | Bhimsen | 8
6618 | Gorkha | Borlang |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 89 |  |  |  | Bhimsen | 8
6619 | Gorkha | Borlang |  | PA | GORETO GORKHA | PA-UK | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 14 | 14 | 2016-02-07 | 2016-02-11 |  | Bhimsen | 8
6620 | Gorkha | Borlang | all | PA | GORETO GORKHA | PA-UK | Training | Vocational training | Plumber (CTEVT) |  | # of trainees | Yes | Completed | 15 | 15 | 2015-12-13 | 2016-01-13 |  | Bhimsen | 8
6621 | Gorkha | Bunkot | 1 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-26 | 2017-06-20 |  | Sahid Lakhan | 7
6622 | Gorkha | Bunkot | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 262 | 22 | 2017-05-21 |  |  | Sahid Lakhan | 7
6623 | Gorkha | Bunkot | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 18 | 2017-03-17 |  |  | Sahid Lakhan | 7
6624 | Gorkha | Bunkot | 1 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 262 | 0 |  |  |  | Sahid Lakhan | 7
6625 | Gorkha | Bunkot | 1 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 262 | 0 |  |  |  | Sahid Lakhan | 7
6626 | Gorkha | Bunkot | 1 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-01-19 | Nimjung CBRC | Sahid Lakhan | 7
6627 | Gorkha | Bunkot | 1 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-01-17 | Susare Gaun CBRC | Sahid Lakhan | 7
6628 | Gorkha | Bunkot | 1 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-01-18 | Kot Gaun CBRC | Sahid Lakhan | 7
6629 | Gorkha | Bunkot | 1 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-05-09 | 2016-05-13 |  | Sahid Lakhan | 7
6630 | Gorkha | Bunkot | 1 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Completed | 10 | 10 | 2017-03-26 | 2017-05-01 |  | Sahid Lakhan | 7
6631 | Gorkha | Bunkot | 1 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-02-08 | 2016-03-15 | 30 days vocational training | Sahid Lakhan | 7
6632 | Gorkha | Bunkot | 2 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 7
6633 | Gorkha | Bunkot | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 203 | 36 | 2017-05-21 |  |  | Sahid Lakhan | 7
6634 | Gorkha | Bunkot | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 16 | 2017-03-17 |  |  | Sahid Lakhan | 7
6635 | Gorkha | Bunkot | 2 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 203 | 0 |  |  |  | Sahid Lakhan | 7
6636 | Gorkha | Bunkot | 2 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 203 | 0 |  |  |  | Sahid Lakhan | 7
6637 | Gorkha | Bunkot | 2 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-01-21 | Chilaune Chautara CBRC | Sahid Lakhan | 7
6638 | Gorkha | Bunkot | 2 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-09 | 2016-05-13 |  | Sahid Lakhan | 7
6639 | Gorkha | Bunkot | 2 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Sahid Lakhan | 7
6640 | Gorkha | Bunkot | 2 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-02-08 | 2016-03-15 | 30 days vocational training | Sahid Lakhan | 7
6641 | Gorkha | Bunkot | 3 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-06-20 | 2017-10-01 |  | Sahid Lakhan | 7
6642 | Gorkha | Bunkot | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 311 | 56 | 2017-05-21 |  |  | Sahid Lakhan | 7
6643 | Gorkha | Bunkot | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 6 | 2017-03-17 |  |  | Sahid Lakhan | 7
6644 | Gorkha | Bunkot | 3 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 311 | 0 |  |  |  | Sahid Lakhan | 7
6645 | Gorkha | Bunkot | 3 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 311 | 127 | 2016-02-17 | 2016-02-28 |  | Sahid Lakhan | 7
6646 | Gorkha | Bunkot | 3 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Turtue Dhara CBRC | Sahid Lakhan | 7
6647 | Gorkha | Bunkot | 3 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2015-11-24 | 2015-11-28 |  | Sahid Lakhan | 7
6648 | Gorkha | Bunkot | 3 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Sahid Lakhan | 7
6649 | Gorkha | Bunkot | 3 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-02-08 | 2016-03-15 | 30 days vocational training | Sahid Lakhan | 7
6650 | Gorkha | Bunkot | 4 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-06-20 | 2017-10-01 |  | Sahid Lakhan | 7
6651 | Gorkha | Bunkot | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 249 | 37 | 2017-05-21 |  |  | Sahid Lakhan | 7
6652 | Gorkha | Bunkot | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 20 | 2017-03-17 |  |  | Sahid Lakhan | 7
6653 | Gorkha | Bunkot | 4 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 249 | 0 |  |  |  | Sahid Lakhan | 7
6654 | Gorkha | Bunkot | 4 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 249 | 213 | 2016-02-01 | 2016-02-14 |  | Sahid Lakhan | 7
6655 | Gorkha | Bunkot | 4 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Thani mai CBRC | Sahid Lakhan | 7
6656 | Gorkha | Bunkot | 4 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 16 | 16 | 2015-11-24 | 2015-11-28 |  | Sahid Lakhan | 7
6657 | Gorkha | Bunkot | 4 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Sahid Lakhan | 7
6658 | Gorkha | Bunkot | 4 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-11-12 | 2015-12-16 | 30 days vocational training | Sahid Lakhan | 7
6659 | Gorkha | Bunkot | 5 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-21 | 2017-05-23 |  | Sahid Lakhan | 8
6660 | Gorkha | Bunkot | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 184 | 31 | 2017-05-21 |  |  | Sahid Lakhan | 8
6661 | Gorkha | Bunkot | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 6 |  |  |  | Sahid Lakhan | 8
6662 | Gorkha | Bunkot | 5 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 184 | 0 |  |  |  | Sahid Lakhan | 8
6663 | Gorkha | Bunkot | 5 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 184 | 0 |  |  |  | Sahid Lakhan | 8
6664 | Gorkha | Bunkot | 5 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-01-08 | Hatiya CBRC | Sahid Lakhan | 8
6665 | Gorkha | Bunkot | 5 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-03-14 | 2016-03-18 |  | Sahid Lakhan | 8
6666 | Gorkha | Bunkot | 5 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Completed | 10 | 10 | 2017-03-21 |  |  | Sahid Lakhan | 8
6667 | Gorkha | Bunkot | 5 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 11 | 11 | 2015-11-12 | 2015-12-16 | 30 days vocational training | Sahid Lakhan | 8
6668 | Gorkha | Bunkot | 6 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 8
6669 | Gorkha | Bunkot | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 164 | 15 | 2017-05-21 |  |  | Sahid Lakhan | 8
6670 | Gorkha | Bunkot | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 5 | 2017-03-17 |  |  | Sahid Lakhan | 8
6671 | Gorkha | Bunkot | 6 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 164 | 0 |  |  |  | Sahid Lakhan | 8
6672 | Gorkha | Bunkot | 6 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 164 | 0 |  |  |  | Sahid Lakhan | 8
6673 | Gorkha | Bunkot | 6 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-01-06 | Chhapthok CBRC | Sahid Lakhan | 8
6674 | Gorkha | Bunkot | 6 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-03-14 | 2016-03-18 |  | Sahid Lakhan | 8
6675 | Gorkha | Bunkot | 6 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Sahid Lakhan | 8
6676 | Gorkha | Bunkot | 6 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 11 | 11 | 2015-11-12 | 2015-12-16 | 30 days vocational training | Sahid Lakhan | 8
6677 | Gorkha | Bunkot | 7 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 |  |  |  | Sahid Lakhan | 8
6678 | Gorkha | Bunkot | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 79 | 10 | 2017-05-21 |  |  | Sahid Lakhan | 8
6679 | Gorkha | Bunkot | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 2 | 2017-03-17 |  |  | Sahid Lakhan | 8
6680 | Gorkha | Bunkot | 7 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 79 | 0 |  |  |  | Sahid Lakhan | 8
6681 | Gorkha | Bunkot | 7 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 79 | 0 |  |  |  | Sahid Lakhan | 8
6682 | Gorkha | Bunkot | 7 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2015-12-18 | Shavi Shakti CBRC | Sahid Lakhan | 8
6683 | Gorkha | Bunkot | 7 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-02-08 | 2016-02-12 |  | Sahid Lakhan | 8
6684 | Gorkha | Bunkot | 7 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Ongoing | 10 | 10 | 2017-07-15 | 2017-09-15 |  | Sahid Lakhan | 8
6685 | Gorkha | Bunkot | 7 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-28 | 2016-05-03 | 30 days vocational training | Sahid Lakhan | 8
6686 | Gorkha | Bunkot | 8 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 8
6687 | Gorkha | Bunkot | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 158 | 10 | 2017-05-21 |  |  | Sahid Lakhan | 8
6688 | Gorkha | Bunkot | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 1 |  |  |  | Sahid Lakhan | 8
6689 | Gorkha | Bunkot | 8 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 158 | 0 |  |  |  | Sahid Lakhan | 8
6690 | Gorkha | Bunkot | 8 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 158 | 0 |  |  |  | Sahid Lakhan | 8
6691 | Gorkha | Bunkot | 8 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Sahid Lakhan | 8
6692 | Gorkha | Bunkot | 8 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-02-08 | 2016-02-12 |  | Sahid Lakhan | 8
6693 | Gorkha | Bunkot | 8 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Sahid Lakhan | 8
6694 | Gorkha | Bunkot | 8 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-03-28 | 2016-05-03 | 30 days vocational training | Sahid Lakhan | 8
6695 | Gorkha | Bunkot | 9 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 8
6696 | Gorkha | Bunkot | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 183 | 27 | 2017-05-21 |  |  | Sahid Lakhan | 8
6697 | Gorkha | Bunkot | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 13 | 2017-03-17 |  |  | Sahid Lakhan | 8
6698 | Gorkha | Bunkot | 9 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 183 | 0 |  |  |  | Sahid Lakhan | 8
6699 | Gorkha | Bunkot | 9 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 183 | 0 |  |  |  | Sahid Lakhan | 8
6700 | Gorkha | Bunkot | 9 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-04 | Mailung CBRC | Sahid Lakhan | 8
6701 | Gorkha | Bunkot | 9 | JICA | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 8
6702 | Gorkha | Bunkot | 9 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-02-08 | 2016-02-12 |  | Sahid Lakhan | 8
6703 | Gorkha | Bunkot | 9 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Sahid Lakhan | 8
6704 | Gorkha | Bunkot | 9 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-03-28 | 2016-05-03 | 30 days vocational training | Sahid Lakhan | 8
6705 | Gorkha | Bunkot | 5,8,9 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-01-04 | Jaydul Faat CBRC | Sahid Lakhan | 8
6706 | Gorkha | Bunkot | ALL | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 1 |  |  |  | Sahid Lakhan | 8
6707 | Gorkha | Bunkot | All | CRS | SDSC |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 18 | 18 | 2017-03-17 |  |  | Sahid Lakhan | 8
6708 | Gorkha | Bunkot | All | UNWOMEN | WHR |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 18 | 18 | 2017-05-07 | 2017-06-28 |  | Sahid Lakhan | 8
6709 | Gorkha | Ghairung | All | OXFAM-GB |  |  | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 744 | 800 |  |  |  | Sahid Lakhan | 6
6710 | Gorkha | Ghyachok | All | OXFAM-GB |  |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Completed | 414 | 454 |  |  |  | Ajirkot | 1
6711 | Gorkha | Kharibot | All | OXFAM-GB |  |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Completed | 534 | 480 |  |  |  | Ajirkot | 2
6712 | Gorkha | Manakamana | All | OXFAM-GB |  |  | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 755 | 755 |  |  |  | Sahid Lakhan | 3
6713 | Gorkha | Namjung | All | OXFAM-GB |  |  | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 800 | 800 |  |  |  | Sahid Lakhan | 9
6714 | Gorkha | Saurpani | All | OXFAM-GB | GORETO GORKHA |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 81 | 81 |  |  | CGI 2B | Sulikot | 4
6715 | Gorkha | Taklung | All | OXFAM-GB | TMUC |  | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 783 | 783 |  |  |  | Sahid Lakhan | 5
6716 | Gorkha | Chhaikampar | 6 | PIN | PIN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-07-15 | 2015-10-06 |  | Chum Nubri | 7
6717 | Gorkha | Chhaikampar | All | OXFAM-GB |  |  | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 267 | 251 |  |  |  | Chum Nubri | 7
6718 | Gorkha | Chhaikampar | 1 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 100 |  |  |  | Chum Nubri | 7
6719 | Gorkha | Chhaikampar | 2 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 100 |  |  |  | Chum Nubri | 7
6720 | Gorkha | Chhaikampar | 3 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 100 |  |  |  | Chum Nubri | 7
6721 | Gorkha | Chhaikampar | 4 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 100 |  |  |  | Chum Nubri | 7
6722 | Gorkha | Chhaikampar | 5 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 100 |  |  |  | Chum Nubri | 7
6723 | Gorkha | Chhoprak | 1 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 9 | 9 |  |  |  | Siranchok | 5
6724 | Gorkha | Chhoprak | 1 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 9 | 7 |  |  |  | Siranchok | 5
6725 | Gorkha | Chhoprak | 1 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 9 | 3 |  |  |  | Siranchok | 5
6726 | Gorkha | Chhoprak | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 109 | 109 | 2016-06-09 | 2016-08-12 |  | Siranchok | 5
6727 | Gorkha | Chhoprak | 1 | INF-N | GCS | INF International | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 9 | 9 |  |  |  | Siranchok | 5
6728 | Gorkha | Chhoprak | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 45 | 45 |  |  |  | Siranchok | 5
6729 | Gorkha | Chhoprak | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-02 | 2016-07-18 |  | Siranchok | 5
6730 | Gorkha | Chhoprak | 2 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 1 | 1 |  |  |  | Siranchok | 5
6731 | Gorkha | Chhoprak | 2 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Completed | 1 | 1 |  |  |  | Siranchok | 5
6732 | Gorkha | Chhoprak | 2 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 1 | 1 |  |  |  | Siranchok | 5
6733 | Gorkha | Chhoprak | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2016-06-09 | 2016-06-09 |  | Siranchok | 5
6734 | Gorkha | Chhoprak | 2 | INF-N | GCS | INF International | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 1 | 1 |  |  |  | Siranchok | 5
6735 | Gorkha | Chhoprak | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 64 | 64 |  |  |  | Siranchok | 5
6736 | Gorkha | Chhoprak | 3 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 6 | 6 |  |  |  | Siranchok | 5
6737 | Gorkha | Chhoprak | 3 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Completed | 6 | 6 |  |  |  | Siranchok | 5
6738 | Gorkha | Chhoprak | 3 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 6 | 3 |  |  |  | Siranchok | 5
6739 | Gorkha | Chhoprak | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 6 | 6 | 2016-06-09 | 2016-06-09 |  | Siranchok | 5
6740 | Gorkha | Chhoprak | 3 | INF-N | GCS | INF International | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 6 | 6 |  |  |  | Siranchok | 5
6741 | Gorkha | Chhoprak | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 46 | 46 |  |  |  | Siranchok | 5
6742 | Gorkha | Chhoprak | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-02 | 2016-07-18 |  | Siranchok | 5
6743 | Gorkha | Chhoprak | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 2 | 2 | 2016-06-09 | 2016-06-09 |  | Siranchok | 5
6744 | Gorkha | Chhoprak | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 177 | 177 |  |  |  | Siranchok | 5
6745 | Gorkha | Chhoprak | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-02 | 2016-07-18 |  | Siranchok | 5
6746 | Gorkha | Chhoprak | 5 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 11 | 11 |  |  |  | Siranchok | 5
6747 | Gorkha | Chhoprak | 5 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 9 | 8 |  |  |  | Siranchok | 5
6748 | Gorkha | Chhoprak | 5 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 11 | 5 |  |  |  | Siranchok | 5
6749 | Gorkha | Chhoprak | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 15 | 15 | 2016-06-09 | 2016-06-09 |  | Siranchok | 5
6750 | Gorkha | Chhoprak | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 |  |  |  | Siranchok | 5
6751 | Gorkha | Chhoprak | 5 | INF-N | GCS | INF International | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 9 | 9 |  |  |  | Siranchok | 5
6752 | Gorkha | Chhoprak | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 94 | 94 |  |  |  | Siranchok | 5
6753 | Gorkha | Chhoprak | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-02 | 2016-07-18 |  | Siranchok | 5
6754 | Gorkha | Chhoprak | 6 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 18 | 18 |  |  |  | Siranchok | 5
6755 | Gorkha | Chhoprak | 6 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 20 | 19 |  |  |  | Siranchok | 5
6756 | Gorkha | Chhoprak | 6 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 20 | 7 |  |  |  | Siranchok | 5
6757 | Gorkha | Bakrang | 6 | ROTARY | CDRA | ROTARY | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | School Building Construction | # of households |  | Completed | 1 | 1 |  |  |  | Sahid Lakhan | 1
6758 | Gorkha | Chhoprak | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 17 | 17 | 2016-06-09 | 2016-06-09 |  | Siranchok | 5
6759 | Gorkha | Chhoprak | 6 | INF-N | GCS | INF International | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 20 |  |  |  | Siranchok | 5
6760 | Gorkha | Chhoprak | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 59 | 59 |  |  |  | Siranchok | 5
6761 | Gorkha | Chhoprak | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-02 | 2016-07-18 |  | Siranchok | 5
6762 | Gorkha | Chhoprak | 7 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 8 | 8 |  |  |  | Siranchok | 4
6763 | Gorkha | Chhoprak | 7 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Completed | 8 | 8 |  |  |  | Siranchok | 4
6764 | Gorkha | Chhoprak | 7 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 8 | 5 |  |  |  | Siranchok | 4
6765 | Gorkha | Chhoprak | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 15 | 15 | 2016-06-09 | 2016-06-09 |  | Siranchok | 4
6766 | Gorkha | Chhoprak | 7 | INF-N | GCS | INF International | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 8 | 8 |  |  |  | Siranchok | 4
6767 | Gorkha | Chhoprak | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 263 | 263 |  |  |  | Siranchok | 4
6768 | Gorkha | Chhoprak | 7 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 19 | 19 | 2016-06-02 | 2016-07-18 |  | Siranchok | 4
6769 | Gorkha | Chhoprak | 8 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 5 | 5 |  |  |  | Siranchok | 4
6770 | Gorkha | Chhoprak | 8 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Planned | 5 | 0 |  |  |  | Siranchok | 4
6771 | Gorkha | Chhoprak | 8 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 5 | 0 |  |  |  | Siranchok | 4
6772 | Gorkha | Chhoprak | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 15 | 15 | 2016-06-09 | 2016-06-09 |  | Siranchok | 4
6773 | Gorkha | Chhoprak | 8 | INF-N | GCS | INF International | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Planned | 5 | 0 |  |  |  | Siranchok | 4
6774 | Gorkha | Chhoprak | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 288 | 288 |  |  |  | Siranchok | 4
6775 | Gorkha | Chhoprak | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-02 | 2016-06-08 |  | Siranchok | 4
6776 | Gorkha | Chhoprak | 9 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 17 | 17 |  |  |  | Siranchok | 4
6777 | Gorkha | Chhoprak | 9 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Completed | 17 | 17 |  |  |  | Siranchok | 4
6778 | Gorkha | Chhoprak | 9 | INF-N | GCS | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 17 | 8 |  |  |  | Siranchok | 4
6779 | Gorkha | Chhoprak | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 10 | 10 | 2016-06-09 | 2016-06-09 |  | Siranchok | 4
6780 | Gorkha | Chhoprak | 9 | INF-N | GCS | INF International | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 17 | 17 |  |  |  | Siranchok | 4
6781 | Gorkha | Chhoprak | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 238 | 238 |  |  |  | Siranchok | 4
6782 | Gorkha | Chhoprak | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-02 | 2016-07-18 |  | Siranchok | 4
6783 | Gorkha | Chhoprak | All | CARE-N | UNIFICATION-N |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Siranchok | 5
6784 | Gorkha | Chhoprak |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Completed | 1 | 1 |  |  | Flagged as 1 to show the area has plans | Siranchok | 5
6785 | Gorkha | Chhoprak |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 52 |  |  |  | Siranchok | 5
6786 | Gorkha | Chhaikampar | 6 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 100 |  |  |  | Chum Nubri | 7
6787 | Gorkha | Chumchet | All | SP | UVN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 29 | 29 | 2017-01-22 | 2017-01-28 |  | Chum Nubri | 6
6788 | Gorkha | Chumchet | ALL | SP | UVN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 32 | 32 | 2017-02-17 | 2017-02-23 |  | Chum Nubri | 6
6789 | Gorkha | Chumchet |  | SP | UVN |  | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Model House construction | # of households |  | Completed | 1 | 1 |  |  | Hand over to vulnerabl benificiaries ( total Cost 8 Lakhs Per House Expect transportation) | Chum Nubri | 6
6790 | Gorkha | Darbhung | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 36 | 2016-06-23 | 2016-06-23 |  | Gandaki | 5
6791 | Gorkha | Darbhung | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 44 | 2016-06-24 | 2016-06-24 |  | Gandaki | 5
6792 | Gorkha | Darbhung | 3 | ACN | ACN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-07-07 | 2017-07-15 |  | Gandaki | 5
6793 | Gorkha | Darbhung | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 89 | 2016-07-19 | 2016-07-20 |  | Gandaki | 5
6794 | Gorkha | Darbhung | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 150 | 111 | 2016-06-23 | 2016-07-01 |  | Gandaki | 5
6795 | Gorkha | Darbhung | 7 | ACN | ACN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2017-07-07 | 2017-07-15 |  | Gandaki | 5
6796 | Gorkha | Darbhung | 8 | ACN | ACN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2017-07-07 | 2017-07-15 |  | Gandaki | 5
6797 | Gorkha | Darbhung | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 28 | 2016-07-14 | 2016-07-14 |  | Gandaki | 5
6798 | Gorkha | Darbhung | 9 | ACN | ACN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2017-07-07 | 2017-07-15 |  | Gandaki | 5
6799 | Gorkha | Darbhung | 2 and 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 48 | 2016-07-01 | 2016-07-01 |  | Gandaki | 5
6800 | Gorkha | Darbhung | 2,4, 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 41 | 2016-07-13 | 2016-07-13 |  | Gandaki | 5
6801 | Gorkha | Darbhung | 3 and 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 57 | 2016-07-07 | 2016-07-08 |  | Gandaki | 5
6802 | Gorkha | Darbhung | 3,4 and 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 66 | 2016-07-14 | 2016-07-14 |  | Gandaki | 5
6803 | Gorkha | Darbhung | 5 and 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 27 | 2016-07-15 | 2016-07-15 |  | Gandaki | 5
6804 | Gorkha | Darbhung | 5 and 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 9 | 2016-07-22 | 2016-07-22 |  | Gandaki | 5
6805 | Gorkha | Darbhung | 6,7 and 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 35 | 2016-07-21 | 2016-07-21 |  | Gandaki | 5
6806 | Gorkha | Darbhung | 7 and 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 37 | 2016-07-13 | 2016-07-13 |  | Gandaki | 5
6807 | Gorkha | Darbhung | 7 and 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 14 | 2016-07-15 | 2016-07-15 |  | Gandaki | 5
6808 | Gorkha | Darbhung | 8 and 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 42 | 2016-07-14 | 2016-07-14 |  | Gandaki | 5
6809 | Gorkha | Darbhung | All | ACN | ACN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 28 | 28 | 2017-07-07 | 2017-07-15 |  | Gandaki | 5
6810 | Gorkha | Darbhung | All | GON - PAF | GORETO GORKHA | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-14 | 2017-06-20 |  | Gandaki | 5
6811 | Gorkha | Darbhung | All | ACN | ACN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 28 |  |  |  | Gandaki | 5
6812 | Gorkha | Deurali | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 40 | 2016-08-25 | 2016-08-25 |  | Gorkha | 14
6813 | Gorkha | Deurali | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 77 | 2016-08-24 | 2016-08-25 |  | Gorkha | 14
6814 | Gorkha | Deurali | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  | Organized in Pandrung; People from Deurali participated | Gorkha | 14
6815 | Gorkha | Deurali | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 150 | 125 | 2016-08-11 | 2016-09-07 |  | Gorkha | 14
6816 | Gorkha | Deurali | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 210 | 180 | 2016-08-11 | 2016-09-01 |  | Gorkha | 14
6817 | Gorkha | Deurali | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 250 | 197 | 2016-08-23 | 2016-09-02 |  | Gorkha | 13
6818 | Gorkha | Deurali | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 |  |  | Organized in Pandrung; People from Deurali participated | Gorkha | 13
6819 | Gorkha | Deurali | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 93 | 2016-08-04 | 2016-08-05 |  | Gorkha | 13
6820 | Gorkha | Deurali | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  | Organized in Pandrung; People from Deurali participated | Gorkha | 13
6821 | Gorkha | Deurali | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 150 | 144 | 2016-08-10 | 2016-09-02 |  | Gorkha | 13
6822 | Gorkha | Deurali | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 93 | 2016-08-16 | 2016-08-17 |  | Gorkha | 13
6823 | Gorkha | Deurali | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 112 | 2016-08-12 | 2016-08-26 |  | Gorkha | 14
6824 | Gorkha | Deurali | 9 | GON - DLPIU | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 60 | 70 | 2017-06-28 | 2017-07-04 |  | Gorkha | 14
6825 | Gorkha | Deurali | All | ACN | ACN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 55 | 55 | 2017-07-01 |  |  | Gorkha | 14
6826 | Gorkha | Deurali |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 46 | 46 |  |  | Extracted from JICA Pandrung Database | Gorkha | 14
6827 | Gorkha | Deurali |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 325 |  |  |  | Gorkha | 14
6828 | Gorkha | Dhawa | All | DCA | ECO-N | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 29 | 29 | 2016-03-04 | 2016-03-08 |  | Bhimsen | 4
6829 | Gorkha | Dhawa | All | GON - PAF | SDSC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 50 | 0 |  |  |  | Bhimsen | 4
6830 | Gorkha | Dhawa |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 132 |  |  |  | Bhimsen | 4
6831 | Gorkha | Dhuwakot | 9 | GON - DLPIU | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 35 | 2017-07-04 | 2017-07-11 |  | Palungtar | 9
6832 | Gorkha | Dhuwakot |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 400 |  |  |  | Palungtar | 9
6833 | Gorkha | Dhuwakot |  | ACN | ACN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 24 |  |  |  | Palungtar | 9
6834 | Gorkha | Fujel | 1 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 | 2017-03-20 | 2017-03-27 |  | Gandaki | 4
6835 | Gorkha | Fujel | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 400 | 345 | 2016-05-18 | 2016-05-31 |  | Gandaki | 4
6836 | Gorkha | Fujel | 1 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2017-03-20 | 2017-03-27 |  | Gandaki | 4
6837 | Gorkha | Fujel | 2 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 9 | 9 | 2017-03-20 | 2017-03-27 |  | Gandaki | 4
6838 | Gorkha | Fujel | 2 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2017-03-20 | 2017-03-27 |  | Gandaki | 4
6839 | Gorkha | Fujel | 3 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 | 2017-03-20 | 2017-03-27 |  | Gandaki | 4
6840 | Gorkha | Fujel | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 42 | 2016-05-25 | 2016-05-25 |  | Gandaki | 4
6841 | Gorkha | Fujel | 3 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2017-03-20 | 2017-03-27 |  | Gandaki | 4
6842 | Gorkha | Fujel | 4 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 7 | 7 | 2017-03-20 | 2017-03-27 |  | Gandaki | 3
6843 | Gorkha | Fujel | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 44 | 2016-05-11 | 2016-05-11 |  | Gandaki | 3
6844 | Gorkha | Fujel | 4 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2017-03-20 | 2017-03-27 |  | Gandaki | 3
6845 | Gorkha | Fujel | 5 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 9 | 9 | 2017-03-20 | 2017-03-27 |  | Gandaki | 3
6846 | Gorkha | Fujel | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 150 | 126 | 2016-05-10 | 2016-05-17 |  | Gandaki | 3
6847 | Gorkha | Fujel | 5 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2017-03-20 | 2017-03-27 |  | Gandaki | 3
6848 | Gorkha | Fujel | 6 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 | 2017-03-20 | 2017-03-27 |  | Gandaki | 3
6849 | Gorkha | Fujel | 6 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2017-03-20 | 2017-03-27 |  | Gandaki | 3
6850 | Gorkha | Fujel | 7 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 9 | 9 | 2017-03-20 | 2017-03-27 |  | Gandaki | 3
6851 | Gorkha | Fujel | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 83 | 2016-05-04 | 2016-05-04 |  | Gandaki | 3
6852 | Gorkha | Fujel | 7 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2017-03-20 | 2017-03-27 |  | Gandaki | 3
6853 | Gorkha | Fujel | 8 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 7 | 7 | 2017-03-20 | 2017-03-27 |  | Gandaki | 3
6854 | Gorkha | Fujel | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 91 | 2016-05-10 | 2016-05-11 |  | Gandaki | 3
6855 | Gorkha | Fujel | 8 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2017-03-20 | 2017-03-27 |  | Gandaki | 3
6856 | Gorkha | Fujel | 9 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 10 | 2017-03-20 | 2017-03-27 |  | Gandaki | 4
6857 | Gorkha | Fujel | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 88 | 2016-05-04 | 2016-05-05 |  | Gandaki | 4
6858 | Gorkha | Fujel | 9 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-20 | 2017-03-27 |  | Gandaki | 4
6859 | Gorkha | Fujel | 2 and 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 200 | 187 | 2016-05-26 | 2016-05-31 |  | Gandaki | 4
6860 | Gorkha | Fujel | 4 and 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 68 | 2016-05-12 | 2016-05-19 |  | Gandaki | 3
6861 | Gorkha | Fujel | 4,5 and 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 40 | 2016-05-18 | 2016-05-18 |  | Gandaki | 3
6862 | Gorkha | Fujel | 4,6 and 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 40 | 2016-05-13 | 2016-05-13 |  | Gandaki | 3
6863 | Gorkha | Fujel | 4,7 and 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 38 | 2016-05-12 | 2016-05-12 |  | Gandaki | 3
6864 | Gorkha | Fujel | 5,6 and 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 45 | 2015-05-06 | 2015-05-06 |  | Gandaki | 3
6865 | Gorkha | Fujel | 8 and 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 43 | 2016-05-06 | 2016-05-06 |  | Gandaki | 4
6866 | Gorkha | Fujel | All | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 968 | 968 | 2016-05-24 | 2016-06-23 |  | Gandaki | 4
6867 | Gorkha | Fujel |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 148 |  |  |  | Gandaki | 4
6868 | Gorkha | Gakhu | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 34 | 34 | 2016-08-12 | 2016-08-12 |  | Siranchok | 6
6869 | Gorkha | Gakhu | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 114 | 114 |  |  |  | Siranchok | 6
6870 | Gorkha | Gakhu | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-05 | 2016-08-05 |  | Siranchok | 6
6871 | Gorkha | Gakhu | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 56 | 56 | 2016-07-26 | 2016-07-26 |  | Siranchok | 6
6872 | Gorkha | Gakhu | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 114 | 114 |  |  |  | Siranchok | 6
6873 | Gorkha | Gakhu | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-05 | 2016-08-05 |  | Siranchok | 6
6874 | Gorkha | Gakhu | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 24 | 24 | 2016-07-23 | 2016-07-23 |  | Siranchok | 6
6875 | Gorkha | Gakhu | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 30 | 30 |  |  |  | Siranchok | 6
6876 | Gorkha | Gakhu | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-05 | 2016-08-05 |  | Siranchok | 6
6877 | Gorkha | Gakhu | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 62 | 62 | 2016-07-25 | 2016-07-25 |  | Siranchok | 6
6878 | Gorkha | Gakhu | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 268 | 268 |  |  |  | Siranchok | 6
6879 | Gorkha | Gakhu | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-05 | 2016-08-05 |  | Siranchok | 6
6880 | Gorkha | Gakhu | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 146 | 146 | 2016-08-12 | 2016-08-12 |  | Siranchok | 6
6881 | Gorkha | Gakhu | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 |  |  |  | Siranchok | 6
6882 | Gorkha | Gakhu | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 216 | 216 |  |  |  | Siranchok | 6
6883 | Gorkha | Gakhu | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-05 | 2016-08-05 |  | Siranchok | 6
6884 | Gorkha | Gakhu | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 94 | 94 | 2016-08-11 | 2016-08-11 |  | Siranchok | 6
6885 | Gorkha | Gakhu | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 131 | 131 |  |  |  | Siranchok | 6
6886 | Gorkha | Gakhu | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-05 | 2016-08-05 |  | Siranchok | 6
6887 | Gorkha | Gakhu | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 192 | 192 | 2016-08-10 | 2016-08-10 |  | Siranchok | 6
6888 | Gorkha | Gakhu | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 484 | 484 |  |  |  | Siranchok | 6
6889 | Gorkha | Gakhu | 7 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-05 | 2016-08-05 |  | Siranchok | 6
6890 | Gorkha | Gakhu | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 40 | 40 | 2016-08-07 | 2016-08-07 |  | Siranchok | 6
6891 | Gorkha | Gakhu | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 209 | 209 |  |  |  | Siranchok | 6
6892 | Gorkha | Gakhu | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-05 | 2016-08-05 |  | Siranchok | 6
6893 | Gorkha | Gakhu | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 57 | 57 | 2016-08-07 | 2016-08-07 |  | Siranchok | 6
6894 | Gorkha | Gakhu | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 98 | 98 |  |  |  | Siranchok | 6
6895 | Gorkha | Gakhu | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-05 | 2016-08-05 |  | Siranchok | 6
6896 | Gorkha | Gakhu | All | CARE-N | UNIFICATION-N |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Siranchok | 6
6897 | Gorkha | Gakhu |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Completed | 1 | 1 |  |  | Flagged as 1 to show the area has plans | Siranchok | 6
6898 | Gorkha | Gakhu |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 97 |  |  |  | Siranchok | 6
6899 | Gorkha | Chhaikampar | 7 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 100 |  |  |  | Chum Nubri | 7
6900 | Gorkha | Ghairung | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 140 | 148 | 2016-01-24 | 2016-04-19 |  | Sahid Lakhan | 6
6901 | Gorkha | Chhaikampar | 8 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 100 |  |  |  | Chum Nubri | 7
6902 | Gorkha | Ghairung | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 58 | 2016-02-19 | 2016-02-19 |  | Sahid Lakhan | 6
6903 | Gorkha | Chhaikampar | 9 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 100 | 100 |  |  |  | Chum Nubri | 7
6904 | Gorkha | Ghairung | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 130 | 136 | 2016-02-18 | 2016-04-13 |  | Sahid Lakhan | 6
6905 | Gorkha | Chhaikampar | 9 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Chum Nubri | 7
6906 | Gorkha | Chhaikampar | All | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 269 | 269 |  |  |  | Chum Nubri | 7
6907 | Gorkha | Ghairung | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 61 | 2016-02-25 | 2016-02-25 |  | Sahid Lakhan | 6
6908 | Gorkha | Chhaikampar | All | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 15 | 15 |  |  |  | Chum Nubri | 7
6909 | Gorkha | Ghairung | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 130 | 164 | 2016-02-10 | 2016-04-28 |  | Sahid Lakhan | 6
6910 | Gorkha | Chumchet | All | OXFAM-GB |  |  | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 243 | 243 |  |  |  | Chum Nubri | 6
6911 | Gorkha | Ghairung | 1 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sahid Lakhan | 6
6912 | Gorkha | Ghairung | 2 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sahid Lakhan | 6
6913 | Gorkha | Ghairung | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 42 | 2016-02-12 | 2016-02-12 |  | Sahid Lakhan | 6
6914 | Gorkha | Ghairung | 3 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 228 | 228 |  |  |  | Sahid Lakhan | 6
6915 | Gorkha | Ghairung | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 90 | 110 | 2015-12-19 | 2016-04-07 |  | Sahid Lakhan | 6
6916 | Gorkha | Ghairung | 4 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Sahid Lakhan | 6
6917 | Gorkha | Ghairung | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 45 | 2016-02-11 | 2016-02-11 |  | Sahid Lakhan | 6
6918 | Gorkha | Ghairung | 4 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 224 | 224 |  |  |  | Sahid Lakhan | 6
6919 | Gorkha | Ghairung | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 84 | 2016-02-26 | 2016-04-27 |  | Sahid Lakhan | 6
6920 | Gorkha | Ghairung | 5 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sahid Lakhan | 6
6921 | Gorkha | Ghairung | 1 and 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 40 | 40 | 2016-04-20 | 2016-04-20 |  | Sahid Lakhan | 6
6922 | Gorkha | Ghairung | 2 and 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 47 | 2016-04-21 | 2016-04-21 |  | Sahid Lakhan | 6
6923 | Gorkha | Ghairung | 5, 2, 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 40 | 43 | 2016-04-08 | 2016-04-08 |  | Sahid Lakhan | 6
6924 | Gorkha | Ghairung | 6 and 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 70 | 69 | 2016-04-22 | 2016-04-26 |  | Sahid Lakhan | 6
6925 | Gorkha | Ghairung | All | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 986 | 986 | 2016-03-05 | 2016-05-15 |  | Sahid Lakhan | 6
6926 | Gorkha | Ghairung | 5 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Sahid Lakhan | 6
6927 | Gorkha | Ghairung | 6 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Sahid Lakhan | 6
6928 | Gorkha | Ghairung | All | UNWOMEN | WHR |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2017-05-07 | 2017-06-28 |  | Sahid Lakhan | 6
6929 | Gorkha | Ghairung | All | GON - PAF | LLCSC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0 |  |  |  | Sahid Lakhan | 6
6930 | Gorkha | Ghairung | 6 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sahid Lakhan | 6
6931 | Gorkha | Ghairung |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 115 |  |  |  | Sahid Lakhan | 6
6932 | Gorkha | Ghairung | 7 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 157 |  |  |  | Sahid Lakhan | 6
6933 | Gorkha | Ghairung | 8 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sahid Lakhan | 6
6934 | Gorkha | Ghairung | 9 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sahid Lakhan | 6
6935 | Gorkha | Ghairung | All | OXFAM-GB | TMUC |  | Others | Others | (Please specify in Activity Detail) | Model Panel Construction (no. of constructions) | # of trainees | Yes | Completed | 3 | 3 |  |  | EQ Resilient Technique incorporated Pollutry farms | Sahid Lakhan | 6
6936 | Gorkha | Ghairung | All | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 1053 | 1053 |  |  | Information Center | Sahid Lakhan | 6
6937 | Gorkha | Ghairung | All | OXFAM-GB | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 60 | 60 |  |  |  | Sahid Lakhan | 6
6938 | Gorkha | Ghairung | 1 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 6 |  |  |  | Sahid Lakhan | 6
6939 | Gorkha | Ghairung | 2 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 6 |  |  |  | Sahid Lakhan | 6
6940 | Gorkha | Ghairung | 3 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 8 |  |  |  | Sahid Lakhan | 6
6941 | Gorkha | Ghairung | 4 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 7 |  |  |  | Sahid Lakhan | 6
6942 | Gorkha | Ghyachok | 1 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity. | Ajirkot | 1
6943 | Gorkha | Ghyachok | 2 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity. | Ajirkot | 1
6944 | Gorkha | Ghyachok | 3 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity. | Ajirkot | 1
6945 | Gorkha | Ghyachok | 4 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity. | Ajirkot | 1
6946 | Gorkha | Ghyachok | 5 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity. | Ajirkot | 1
6947 | Gorkha | Ghyachok | 6 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity. | Ajirkot | 1
6948 | Gorkha | Ghyachok | 9 | CW | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-01-12 | 2017-01-18 | First batch of skilled mason training is already completed but looking for another activity. | Ajirkot | 1
6949 | Gorkha | Ghyachok | All | ACN | ACN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-07-01 |  |  | Ajirkot | 1
6950 | Gorkha | Ghyachok | All | GON - PAF | LDF | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 20 | 0 |  |  |  | Ajirkot | 1
6951 | Gorkha | Ghyalchok | 2 | HELVETAS | Kantipur | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-12-01 | 2016-10-01 |  | Gandaki | 8
6952 | Gorkha | Ghyalchok | 9 | HELVETAS | Kantipur | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01 |  | Gandaki | 8
6953 | Gorkha | Ghyalchok | 9 | HELVETAS | Kantipur | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01 |  | Gandaki | 8
6954 | Gorkha | Ghyalchok | All | DCA | ECO-N | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 48 | 48 | 2016-01-25 | 2016-01-29 |  | Gandaki | 8
6955 | Gorkha | Gorakha N.P. | 15 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 30 | 12 | 2017-03-17 |  |  | Gorkha | 3
6956 | Gorkha | Gorakha N.P. | 1 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Gorkha | 6
6957 | Gorkha | Gorakha N.P. | 1 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 261 | 76 | 2017-05-21 |  |  | Gorkha | 6
6958 | Gorkha | Gorakha N.P. | 1 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 30 | 42 | 2017-03-17 |  |  | Gorkha | 6
6959 | Gorkha | Gorakha N.P. | 1 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 261 | 0 |  |  |  | Gorkha | 6
6960 | Gorkha | Gorakha N.P. | 1 | CRS | CARITAS-N | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Gorkha | 6
6961 | Gorkha | Gorakha N.P. | 1 | CRS | CARITAS-N | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 462 | 0 |  |  |  | Gorkha | 6
6962 | Gorkha | Gorakha N.P. | 1 | GON | GON |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Gorkha | 6
6963 | Gorkha | Gorakha N.P. | 1 | CARE-N | CARE-N | ADH | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 26 | 26 | 2016-05-15 | 2016-05-21 |  | Gorkha | 6
6964 | Gorkha | Gorakha N.P. | 1 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-09-01 | 2017-03-31 |  | Gorkha | 6
6965 | Gorkha | Gorakha N.P. | 1 | CRS | CARITAS-N | CARITAS-A | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0 |  |  |  | Gorkha | 6
6966 | Gorkha | Gorakha N.P. | 2 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Gorkha | 7
6967 | Gorkha | Gorakha N.P. | 2 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 175 | 69 | 2017-05-21 |  |  | Gorkha | 7
6968 | Gorkha | Gorakha N.P. | 2 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 30 | 98 | 2017-03-17 |  |  | Gorkha | 7
6969 | Gorkha | Gorakha N.P. | 2 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 175 | 0 |  |  |  | Gorkha | 7
6970 | Gorkha | Gorakha N.P. | 2 | CRS | CARITAS-N | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Gorkha | 7
6971 | Gorkha | Gorakha N.P. | 2 | CRS | CARITAS-N | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 369 | 0 |  |  |  | Gorkha | 7
6972 | Gorkha | Gorakha N.P. | 2 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 22 | 22 | 2016-09-01 | 2017-03-31 |  | Gorkha | 7
6973 | Gorkha | Gorakha N.P. | 2 | CRS | CARITAS-N | CARITAS-A | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0 |  |  |  | Gorkha | 7
6974 | Gorkha | Gorakha N.P. | 3 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Gorkha | 6
6975 | Gorkha | Gorakha N.P. | 3 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 157 | 59 | 2017-05-21 |  |  | Gorkha | 6
6976 | Gorkha | Gorakha N.P. | 3 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 30 | 31 | 2017-03-17 |  |  | Gorkha | 6
6977 | Gorkha | Gorakha N.P. | 3 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 157 | 0 |  |  |  | Gorkha | 6
6978 | Gorkha | Gorakha N.P. | 3 | CRS | CARITAS-N | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Gorkha | 6
6979 | Gorkha | Gorakha N.P. | 3 | CRS | CARITAS-N | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 574 | 0 |  |  |  | Gorkha | 6
6980 | Gorkha | Gorakha N.P. | 3 | GON | GON |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Gorkha | 6
6981 | Gorkha | Gorakha N.P. | 3 | UNDP | UNDP | UNDP | Technical Assistance | Demonstration Construction | House | Compressed stabilized earthen block technology house with 1 room | # of constructions | Yes | Completed | 1 | 1 | 2015-12-05 | 2016-12-01 |  | Gorkha | 6
6982 | Gorkha | Gorakha N.P. | 3 | UNDP | UNDP | UNDP | Technical Assistance | Demonstration Construction | House | GI wire containment technology house with 1 room | # of constructions | Yes | Completed | 1 | 1 | 2015-12-05 | 2016-12-01 |  | Gorkha | 6
6983 | Gorkha | Gorakha N.P. | 3 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 40 | 0 | 2016-09-01 | 2017-03-31 |  | Gorkha | 6
6984 | Gorkha | Gorakha N.P. | 3 | CRS | CARITAS-N | CARITAS-A | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0 |  |  |  | Gorkha | 6
6985 | Gorkha | Gorakha N.P. | 4 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-07-01 | 2017-10-10 |  | Gorkha | 5
6986 | Gorkha | Gorakha N.P. | 15 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-07-01 | 2017-10-10 |  | Gorkha | 3
6987 | Gorkha | Gorakha N.P. | 4 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 612 | 176 | 2017-05-21 |  |  | Gorkha | 5
6988 | Gorkha | Gorakha N.P. | 4 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 30 | 102 | 2017-03-17 |  |  | Gorkha | 5
6989 | Gorkha | Gorakha N.P. | 4 | CRS | CARITAS-N | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Gorkha | 5
6990 | Gorkha | Gorakha N.P. | 4 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 261 | 0 |  |  |  | Gorkha | 5
6991 | Gorkha | Gorakha N.P. | 4 | CRS | CARITAS-N | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 521 | 0 |  |  |  | Gorkha | 5
6992 | Gorkha | Gorakha N.P. | 4 | GON | GON |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Gorkha | 5
6993 | Gorkha | Gorakha N.P. | 4 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 73 | 73 | 2017-03-07 | 2017-03-14 |  | Gorkha | 5
6994 | Gorkha | Gorakha N.P. | 4 | CRS | CARITAS-N | CARITAS-A | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 18 | 18 | 2016-05-09 | 2016-06-14 |  | Gorkha | 5
6995 | Gorkha | Gorakha N.P. | 4 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 20 | 0 | 2017-07-01 | 2017-10-10 |  | Gorkha | 5
6996 | Gorkha | Gorakha N.P. | 5 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gorkha | 7
6997 | Gorkha | Gorakha N.P. | 5 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 340 | 165 | 2017-05-21 |  |  | Gorkha | 7
6998 | Gorkha | Gorakha N.P. | 5 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 30 | 85 | 2017-03-17 |  |  | Gorkha | 7
6999 | Gorkha | Gorakha N.P. | 5 | CRS | CARITAS-N | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 340 | 0 |  |  |  | Gorkha | 7
7000 | Gorkha | Gorakha N.P. | 5 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 175 | 0 |  |  |  | Gorkha | 7
7001 | Gorkha | Gorakha N.P. | 5 | CRS | CARITAS-N | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 338 | 0 |  |  |  | Gorkha | 7
7002 | Gorkha | Gorakha N.P. | 5 | GON | GON |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Gorkha | 7
7003 | Gorkha | Gorakha N.P. | 5 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 50 | 50 | 2016-09-01 | 2017-03-31 |  | Gorkha | 7
7004 | Gorkha | Gorakha N.P. | 5 | CRS | CARITAS-N | CARITAS-A | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 20 | 20 | 2017-07-01 | 2017-10-10 |  | Gorkha | 7
7005 | Gorkha | Gorakha N.P. | 6 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Gorkha | 8
7006 | Gorkha | Gorakha N.P. | 6 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 253 | 157 | 2017-05-21 |  |  | Gorkha | 8
7007 | Gorkha | Gorakha N.P. | 6 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 30 | 85 | 2017-03-17 |  |  | Gorkha | 8
7008 | Gorkha | Gorakha N.P. | 6 | CRS | CARITAS-N | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 253 | 0 |  |  |  | Gorkha | 8
7009 | Gorkha | Gorakha N.P. | 6 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 157 | 0 |  |  |  | Gorkha | 8
7010 | Gorkha | Gorakha N.P. | 6 | CRS | CARITAS-N | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 606 | 0 |  |  |  | Gorkha | 8
7011 | Gorkha | Gorakha N.P. | 6 | GON | GON |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Gorkha | 8
7012 | Gorkha | Gorakha N.P. | 6 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 38 | 20 | 2017-02-10 | 2017-02-16 |  | Gorkha | 8
7013 | Gorkha | Gorakha N.P. | 6 | CRS | CARITAS-N | CARITAS-A | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0 |  |  |  | Gorkha | 8
7014 | Gorkha | Gorakha N.P. | 7 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-05-08 | 2017-06-20 |  | Gorkha | 8
7015 | Gorkha | Gorakha N.P. | 7 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 338 | 141 | 2017-05-21 |  |  | Gorkha | 8
7016 | Gorkha | Gorakha N.P. | 7 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 30 | 43 | 2017-03-17 |  |  | Gorkha | 8
7017 | Gorkha | Gorakha N.P. | 7 | CRS | CARITAS-N | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 338 | 0 |  |  |  | Gorkha | 8
7018 | Gorkha | Gorakha N.P. | 7 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 612 | 0 |  |  |  | Gorkha | 8
7019 | Gorkha | Gorakha N.P. | 7 | CRS | CARITAS-N | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 460 | 0 |  |  |  | Gorkha | 8
7020 | Gorkha | Gorakha N.P. | 7 | GON | GON |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Gorkha | 8
7021 | Gorkha | Gorakha N.P. | 7 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 23 | 23 | 2017-02-10 | 2017-02-16 |  | Gorkha | 8
7022 | Gorkha | Gorakha N.P. | 7 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 18 | 18 | 2016-05-09 | 2016-06-16 |  | Gorkha | 8
7023 | Gorkha | Gorakha N.P. | 7 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-08 | 2017-06-25 |  | Gorkha | 8
7024 | Gorkha | Gorakha N.P. | 8 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-07-01 | 2017-10-10 |  | Gorkha | 9
7025 | Gorkha | Gorakha N.P. | 8 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 606 | 130 | 2017-05-21 |  |  | Gorkha | 9
7026 | Gorkha | Gorakha N.P. | 8 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 30 | 71 |  |  |  | Gorkha | 9
7027 | Gorkha | Gorakha N.P. | 8 | CRS | CARITAS-N | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 606 | 0 |  |  |  | Gorkha | 9
7028 | Gorkha | Gorakha N.P. | 8 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 340 | 0 |  |  |  | Gorkha | 9
7029 | Gorkha | Gorakha N.P. | 8 | CRS | CARITAS-N | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 484 | 0 |  |  |  | Gorkha | 9
7030 | Gorkha | Gorakha N.P. | 8 | GON | GON |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Gorkha | 9
7031 | Gorkha | Gorakha N.P. | 8 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 116 | 116 | 2017-02-20 | 2017-02-26 |  | Gorkha | 9
7032 | Gorkha | Gorakha N.P. | 8 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 20 | 0 | 2017-07-01 | 2017-10-10 |  | Gorkha | 9
7033 | Gorkha | Gorakha N.P. | 9 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-07-01 | 2017-10-10 |  | Gorkha | 10
7034 | Gorkha | Gorakha N.P. | 9 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 660 | 109 | 2017-05-21 |  |  | Gorkha | 10
7035 | Gorkha | Gorakha N.P. | 9 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 30 | 36 |  |  |  | Gorkha | 10
7036 | Gorkha | Gorakha N.P. | 9 | CRS | CARITAS-N | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 660 | 0 |  |  |  | Gorkha | 10
7037 | Gorkha | Gorakha N.P. | 9 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 253 | 0 |  |  |  | Gorkha | 10
7038 | Gorkha | Gorakha N.P. | 9 | CRS | CARITAS-N | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 328 | 0 |  |  |  | Gorkha | 10
7039 | Gorkha | Gorakha N.P. | 9 | GON | GON |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Birenchok CBRC | Gorkha | 10
7040 | Gorkha | Gorakha N.P. | 9 | GON | GON |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Chhepetar CBRC | Gorkha | 10
7041 | Gorkha | Gorakha N.P. | 9 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 46 | 46 | 2017-02-21 | 2017-02-27 |  | Gorkha | 10
7042 | Gorkha | Gorakha N.P. | 9 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 20 | 0 | 2017-07-01 | 2017-10-10 |  | Gorkha | 10
7043 | Gorkha | Gorakha N.P. | 10 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 |  |  |  | Gorkha | 11
7044 | Gorkha | Gorakha N.P. | 10 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 484 | 160 | 2017-05-21 |  |  | Gorkha | 11
7045 | Gorkha | Gorakha N.P. | 10 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 30 | 68 | 2017-03-17 |  |  | Gorkha | 11
7046 | Gorkha | Gorakha N.P. | 10 | ACN | ACN | CEDAR | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees | Yes | Completed | 15 | 13 | 2016-04-06 | 2016-04-13 | This training we focused for our own technical staff. | Gorkha | 11
7047 | Gorkha | Gorakha N.P. | 10 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 43 | 43 | 2016-09-01 | 2017-03-31 |  | Gorkha | 11
7048 | Gorkha | Gorakha N.P. | 10 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0 |  |  |  | Gorkha | 11
7049 | Gorkha | Gorakha N.P. | 11 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-07-01 | 2017-10-10 |  | Gorkha | 12
7050 | Gorkha | Gorakha N.P. | 11 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 328 | 152 | 2017-05-21 |  |  | Gorkha | 12
7051 | Gorkha | Gorakha N.P. | 11 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 30 | 21 |  |  |  | Gorkha | 12
7052 | Gorkha | Gorakha N.P. | 11 | GON | GON |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Gorkha | 12
7053 | Gorkha | Gorakha N.P. | 11 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 35 | 2016-09-01 | 2017-03-31 |  | Gorkha | 12
7054 | Gorkha | Gorakha N.P. | 11 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 20 | 0 | 2017-07-01 | 2017-10-10 |  | Gorkha | 12
7055 | Gorkha | Gorakha N.P. | 12 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-07-01 | 2017-10-10 |  | Gorkha | 4
7056 | Gorkha | Gorakha N.P. | 12 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 462 | 190 | 2017-05-21 |  |  | Gorkha | 4
7057 | Gorkha | Gorakha N.P. | 12 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 30 | 27 | 2017-03-17 |  |  | Gorkha | 4
7058 | Gorkha | Gorakha N.P. | 12 | GON | GON |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Gorkha | 4
7059 | Gorkha | Gorakha N.P. | 12 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 38 | 38 | 2017-03-01 | 2017-03-09 |  | Gorkha | 4
7060 | Gorkha | Gorakha N.P. | 12 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 18 | 2016-05-09 | 2016-06-16 |  | Gorkha | 4
7061 | Gorkha | Gorakha N.P. | 12 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 20 | 0 | 2017-07-01 | 2017-10-10 |  | Gorkha | 4
7062 | Gorkha | Gorakha N.P. | 13 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Gorkha | 4
7063 | Gorkha | Gorakha N.P. | 13 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 369 | 113 | 2017-05-21 |  |  | Gorkha | 4
7064 | Gorkha | Gorakha N.P. | 13 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 30 | 11 | 2017-03-17 |  |  | Gorkha | 4
7065 | Gorkha | Gorakha N.P. | 13 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 30 | 0 |  |  |  | Gorkha | 4
7066 | Gorkha | Gorakha N.P. | 13 | GON | GON |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Gorkha | 4
7067 | Gorkha | Gorakha N.P. | 13 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 43 | 43 | 2017-03-01 | 2017-03-09 |  | Gorkha | 4
7068 | Gorkha | Gorakha N.P. | 13 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0 |  |  |  | Gorkha | 4
7069 | Gorkha | Gorakha N.P. | 14 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 |  |  |  | Gorkha | 3
7070 | Gorkha | Gorakha N.P. | 14 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 574 | 158 | 2017-05-21 |  |  | Gorkha | 3
7071 | Gorkha | Gorakha N.P. | 14 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 30 | 14 | 2017-03-17 |  |  | Gorkha | 3
7072 | Gorkha | Gorakha N.P. | 14 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 30 | 0 |  |  |  | Gorkha | 3
7073 | Gorkha | Gorakha N.P. | 14 | GON | GON |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Gorkha | 3
7074 | Gorkha | Gorakha N.P. | 14 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 42 | 42 | 2017-03-03 | 2017-03-11 |  | Gorkha | 3
7075 | Gorkha | Gorakha N.P. | 14 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0 |  |  |  | Gorkha | 3
7076 | Gorkha | Gorakha N.P. | 14 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 45 | 45 | 2016-06-24 | 2016-06-30 |  | Gorkha | 3
7077 | Gorkha | Gorakha N.P. | 15 | CRS | CARITAS-N | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 521 | 137 | 2017-05-21 |  |  | Gorkha | 3
7078 | Gorkha | Gorakha N.P. | 15 | CRS | CARITAS-N | CARITAS-A | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 30 | 0 |  |  |  | Gorkha | 3
7079 | Gorkha | Gorakha N.P. | 15 | GON | GON |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Gorkha | 3
7080 | Gorkha | Gorakha N.P. | 15 | CRS | CARITAS-N | CARITAS-A | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 44 | 44 | 2017-03-03 | 2017-03-11 |  | Gorkha | 3
7081 | Gorkha | Gorakha N.P. | 15 | CRS | CARITAS-N | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 20 | 0 |  |  |  | Gorkha | 3
7082 | Gorkha | Gorakha N.P. | 15 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 45 | 45 | 2016-06-24 | 2016-06-30 |  | Gorkha | 3
7083 | Gorkha | Gorakha N.P. | All | CRS | CARITAS-N |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 272 | 281 | 2017-03-17 |  |  | Gorkha | 12
7084 | Gorkha | Gorakha N.P. |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 578 |  |  |  | Gorkha | 12
7085 | Gorkha | Gorakha N.P. |  | JICA |  |  | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 189 | 189 | 2016-07-28 | 2016-09-06 |  | Gorkha | 12
7086 | Gorkha | Gumda | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 37 | 37 | 2016-07-09 | 2016-07-09 |  | Dharche | 5
7087 | Gorkha | Gumda | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 74 | 74 |  |  |  | Dharche | 5
7088 | Gorkha | Gumda | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 36 | 36 | 2016-06-04 | 2016-07-10 |  | Dharche | 5
7089 | Gorkha | Gumda | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 87 | 87 |  |  |  | Dharche | 5
7090 | Gorkha | Gumda | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-28 | 2016-06-03 |  | Dharche | 5
7091 | Gorkha | Gumda | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 37 | 37 | 2016-06-04 | 2016-07-11 |  | Dharche | 5
7092 | Gorkha | Gumda | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 37 | 37 |  |  |  | Dharche | 5
7093 | Gorkha | Gumda | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-28 | 2016-06-03 |  | Dharche | 5
7094 | Gorkha | Gumda | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 59 | 59 | 2016-06-04 | 2016-07-15 |  | Dharche | 5
7095 | Gorkha | Gumda | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 68 | 68 |  |  |  | Dharche | 5
7096 | Gorkha | Gumda | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-28 | 2016-06-03 |  | Dharche | 5
7097 | Gorkha | Gumda | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 75 | 75 | 2016-06-04 | 2016-07-15 |  | Dharche | 5
7098 | Gorkha | Gumda | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 196 | 196 |  |  |  | Dharche | 5
7099 | Gorkha | Gumda | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-28 | 2016-06-03 |  | Dharche | 5
7100 | Gorkha | Gumda | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 85 | 85 | 2016-06-04 | 2016-06-04 |  | Dharche | 5
7101 | Gorkha | Gumda | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 |  |  |  | Dharche | 5
7102 | Gorkha | Gumda | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 291 | 291 |  |  |  | Dharche | 5
7103 | Gorkha | Gumda | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-28 | 2016-06-03 |  | Dharche | 5
7104 | Gorkha | Gumda | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 70 | 70 | 2016-06-04 | 2016-07-18 |  | Dharche | 5
7105 | Gorkha | Gumda | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 214 | 214 |  |  |  | Dharche | 5
7106 | Gorkha | Gumda | 7 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-28 | 2016-06-03 |  | Dharche | 5
7107 | Gorkha | Gumda | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 62 | 62 | 2016-06-04 | 2016-07-17 |  | Dharche | 5
7108 | Gorkha | Gumda | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 175 | 175 |  |  |  | Dharche | 5
7109 | Gorkha | Gumda | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-28 | 2016-06-03 |  | Dharche | 5
7110 | Gorkha | Gumda | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 61 | 61 | 2016-06-04 | 2016-07-13 |  | Dharche | 5
7111 | Gorkha | Gumda | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 155 | 155 |  |  |  | Dharche | 5
7112 | Gorkha | Gumda | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-28 | 2016-06-03 |  | Dharche | 5
7113 | Gorkha | Gumda | All | CARE-N | UNIFICATION-N |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Dharche | 5
7114 | Gorkha | Gumda | All | GON - PAF | HADC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0 |  |  |  | Dharche | 5
7115 | Gorkha | Gumda |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Completed | 1 | 1 |  |  | Flagged as 1 to show the area has plans | Dharche | 5
7116 | Gorkha | Hansapur | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Muktichetra CBRC | Ajirkot | 3
7117 | Gorkha | Hansapur | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Ajirkot | 3
7118 | Gorkha | Hansapur | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Hansapur-2, Saraswoti CBRC | Ajirkot | 3
7119 | Gorkha | Hansapur | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Ajirkot | 3
7120 | Gorkha | Hansapur | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Lapsibot CBRC | Ajirkot | 3
7121 | Gorkha | Hansapur | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Ajirkot | 3
7122 | Gorkha | Hansapur | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Kafaldanda CBRC | Ajirkot | 3
7123 | Gorkha | Hansapur | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Ajirkot | 3
7124 | Gorkha | Hansapur | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Janakalyan CBRC | Ajirkot | 3
7125 | Gorkha | Hansapur | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Ajirkot | 3
7126 | Gorkha | Hansapur | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Khalanga CBRC | Ajirkot | 3
7127 | Gorkha | Hansapur | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Ajirkot | 3
7128 | Gorkha | Hansapur | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Sitaldanda CBRC | Ajirkot | 3
7129 | Gorkha | Hansapur | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Ajirkot | 3
7130 | Gorkha | Hansapur | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Budhisinghtar CBRC | Ajirkot | 3
7131 | Gorkha | Hansapur | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Ajirkot | 3
7132 | Gorkha | Hansapur | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Dhadinggara CBRC | Ajirkot | 3
7133 | Gorkha | Hansapur | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Sungure CBRC | Ajirkot | 3
7134 | Gorkha | Hansapur | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Ajirkot | 3
7135 | Gorkha | Hansapur | All | JICA |  |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 944 | 1079 | 2017-05-03 |  |  | Ajirkot | 3
7136 | Gorkha | Hansapur |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 65 |  |  |  | Ajirkot | 3
7137 | Gorkha | Hansapur |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 236 |  |  |  | Ajirkot | 3
7138 | Gorkha | Harmhi | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 42 | 42 | 2016-08-31 | 2016-09-07 |  | Siranchok | 3
7139 | Gorkha | Harmhi | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 16 | 16 |  |  |  | Siranchok | 3
7140 | Gorkha | Harmhi | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-07-31 | 2016-08-06 |  | Siranchok | 3
7141 | Gorkha | Harmhi | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 66 | 66 | 2016-09-01 | 2016-09-01 |  | Siranchok | 3
7142 | Gorkha | Harmhi | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 43 | 43 |  |  |  | Siranchok | 3
7143 | Gorkha | Harmhi | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-07-31 | 2016-08-06 |  | Siranchok | 3
7144 | Gorkha | Harmhi | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 40 | 40 | 2016-08-30 | 2016-08-30 |  | Siranchok | 3
7145 | Gorkha | Harmhi | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 119 | 119 |  |  |  | Siranchok | 3
7146 | Gorkha | Harmhi | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-07-31 | 2016-08-13 |  | Siranchok | 3
7147 | Gorkha | Harmhi | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 50 | 50 | 2016-09-02 | 2016-09-02 |  | Siranchok | 3
7148 | Gorkha | Harmhi | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 30 | 30 |  |  |  | Siranchok | 3
7149 | Gorkha | Harmhi | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-07-31 | 2016-08-06 |  | Siranchok | 3
7150 | Gorkha | Harmhi | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 49 | 49 | 2016-09-07 | 2016-09-07 |  | Siranchok | 3
7151 | Gorkha | Harmhi | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 49 | 49 |  |  |  | Siranchok | 3
7152 | Gorkha | Harmhi | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-07-31 | 2016-08-06 |  | Siranchok | 3
7153 | Gorkha | Harmhi | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 50 | 50 | 2016-08-29 | 2016-08-29 |  | Siranchok | 3
7154 | Gorkha | Harmhi | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 107 | 107 |  |  |  | Siranchok | 3
7155 | Gorkha | Harmhi | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-08-07 | 2016-08-13 |  | Siranchok | 3
7156 | Gorkha | Harmhi | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 43 | 43 | 2016-09-03 | 2016-09-03 |  | Siranchok | 3
7157 | Gorkha | Harmhi | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 42 | 42 |  |  |  | Siranchok | 3
7158 | Gorkha | Harmhi | 7 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-08-07 | 2016-08-13 |  | Siranchok | 3
7159 | Gorkha | Harmhi | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 90 | 90 | 2016-08-28 | 2016-08-28 |  | Siranchok | 3
7160 | Gorkha | Harmhi | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 |  |  |  | Siranchok | 3
7161 | Gorkha | Harmhi | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 266 | 266 |  |  |  | Siranchok | 3
7162 | Gorkha | Harmhi | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-07-31 | 2016-08-13 |  | Siranchok | 3
7163 | Gorkha | Harmhi | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 160 | 160 | 2016-07-27 | 2016-07-27 |  | Siranchok | 3
7164 | Gorkha | Harmhi | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 180 | 180 |  |  |  | Siranchok | 3
7165 | Gorkha | Harmhi | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-07-31 | 2016-08-13 |  | Siranchok | 3
7166 | Gorkha | Harmhi | All | CARE-N | UNIFICATION-N |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Siranchok | 3
7167 | Gorkha | Harmhi |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Completed | 1 | 1 |  |  | Flagged as 1 to show the area has plans | Siranchok | 3
7168 | Gorkha | Harmhi |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 94 |  |  |  | Siranchok | 3
7169 | Gorkha | Jaubari | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | Laliguras CBRC | Siranchok | 8
7170 | Gorkha | Jaubari | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Siranchok | 8
7171 | Gorkha | Jaubari | 1 | LWR | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-08 | 2016-05-12 |  | Siranchok | 8
7172 | Gorkha | Jaubari | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-12 | Janajagaran CBRC | Siranchok | 8
7173 | Gorkha | Jaubari | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Siranchok | 8
7174 | Gorkha | Jaubari | 2 | LWR | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-08 | 2016-05-12 |  | Siranchok | 8
7175 | Gorkha | Jaubari | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-11 | Shreesatya CBRC | Siranchok | 8
7176 | Gorkha | Jaubari | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Siranchok | 8
7177 | Gorkha | Jaubari | 3 | LWR | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-08 | 2016-05-12 |  | Siranchok | 8
7178 | Gorkha | Jaubari | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Langdi CBRC | Siranchok | 8
7179 | Gorkha | Jaubari | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Balkanya CBRC | Siranchok | 8
7180 | Gorkha | Jaubari | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Siranchok | 8
7181 | Gorkha | Jaubari | 4 | LWR | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-02 | 2016-05-06 |  | Siranchok | 8
7182 | Gorkha | Jaubari | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Gaikure CBRC | Siranchok | 8
7183 | Gorkha | Jaubari | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Siranchok | 8
7184 | Gorkha | Jaubari | 5 | LWR | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-05-02 | 2016-05-06 |  | Siranchok | 8
7185 | Gorkha | Jaubari | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-12 | Sundarbazar CBRC | Siranchok | 8
7186 | Gorkha | Jaubari | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Siranchok | 8
7187 | Gorkha | Jaubari | 6 | LWR | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-04-27 | 2016-05-01 |  | Siranchok | 8
7188 | Gorkha | Jaubari | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-12 | Paropakar CBRC | Siranchok | 8
7189 | Gorkha | Jaubari | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Siranchok | 8
7190 | Gorkha | Jaubari | 7 | LWR | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-04-27 | 2016-05-01 |  | Siranchok | 8
7191 | Gorkha | Jaubari | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | Amar CBRC | Siranchok | 8
7192 | Gorkha | Jaubari | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Siranchok | 8
7193 | Gorkha | Jaubari | 8 | LWR | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-04-27 | 2016-05-01 |  | Siranchok | 8
7194 | Gorkha | Jaubari | 9 | LWR | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000 was provided as first tranche | # of households | Yes | Completed | 100 | 100 |  |  | Rs 50000 first tranche of Government subsidy was supported by Save | Siranchok | 8
7195 | Gorkha | Jaubari | 9 | LWR | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 150000 is provided as second tranche | # of households | Yes | Ongoing | 100 | 96 |  |  |  | Siranchok | 8
7196 | Gorkha | Jaubari | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | Janajagaran CBRC | Siranchok | 8
7197 | Gorkha | Jaubari | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | Finamtar CBRC | Siranchok | 8
7198 | Gorkha | Jaubari | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Siranchok | 8
7199 | Gorkha | Jaubari | 9 | LWR | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-04-27 | 2016-05-01 |  | Siranchok | 8
7200 | Gorkha | Jaubari | All | JICA |  |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 686 | 843 | 2017-05-03 |  |  | Siranchok | 8
7201 | Gorkha | Jaubari |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 78 |  |  |  | Siranchok | 8
7202 | Gorkha | Kashigaun | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 62 | 62 | 2016-07-15 | 2016-08-11 |  | Dharche | 6
7203 | Gorkha | Kashigaun | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 22 | 22 |  |  |  | Dharche | 6
7204 | Gorkha | Kashigaun | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-08 | 2016-07-14 |  | Dharche | 6
7205 | Gorkha | Kashigaun | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 54 | 54 | 2016-07-15 | 2016-08-12 |  | Dharche | 6
7206 | Gorkha | Kashigaun | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 45 | 45 |  |  |  | Dharche | 6
7207 | Gorkha | Kashigaun | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-08 | 2016-07-14 |  | Dharche | 6
7208 | Gorkha | Kashigaun | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 40 | 40 | 2016-07-15 | 2016-08-08 |  | Dharche | 6
7209 | Gorkha | Kashigaun | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 42 | 42 |  |  |  | Dharche | 6
7210 | Gorkha | Kashigaun | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-08 | 2016-07-14 |  | Dharche | 6
7211 | Gorkha | Kashigaun | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 35 | 35 | 2016-07-15 | 2016-08-09 |  | Dharche | 6
7212 | Gorkha | Kashigaun | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 39 | 39 |  |  |  | Dharche | 6
7213 | Gorkha | Kashigaun | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-07-08 | 2016-07-14 |  | Dharche | 6
7214 | Gorkha | Kashigaun | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 58 | 58 | 2016-07-15 | 2016-08-06 |  | Dharche | 6
7215 | Gorkha | Kashigaun | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 42 | 42 |  |  |  | Dharche | 6
7216 | Gorkha | Kashigaun | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-07-08 | 2016-07-14 |  | Dharche | 6
7217 | Gorkha | Kashigaun | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 32 | 32 | 2016-07-15 | 2016-08-07 |  | Dharche | 6
7218 | Gorkha | Kashigaun | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 42 | 42 |  |  |  | Dharche | 6
7219 | Gorkha | Kashigaun | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-07-08 | 2016-07-14 |  | Dharche | 6
7220 | Gorkha | Kashigaun | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 41 | 41 | 2016-07-15 | 2016-08-10 |  | Dharche | 6
7221 | Gorkha | Kashigaun | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 |  |  |  | Dharche | 6
7222 | Gorkha | Kashigaun | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 51 | 51 |  |  |  | Dharche | 6
7223 | Gorkha | Kashigaun | 7 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-08 | 2016-07-14 |  | Dharche | 6
7224 | Gorkha | Kashigaun | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 58 | 58 | 2016-07-15 | 2016-08-04 |  | Dharche | 6
7225 | Gorkha | Kashigaun | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 17 | 17 |  |  |  | Dharche | 6
7226 | Gorkha | Kashigaun | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-08 | 2016-07-14 |  | Dharche | 6
7227 | Gorkha | Kashigaun | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 52 | 52 | 2016-07-15 | 2016-08-05 |  | Dharche | 6
7228 | Gorkha | Kashigaun | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 55 | 55 |  |  |  | Dharche | 6
7229 | Gorkha | Kashigaun | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-07-08 | 2016-07-14 |  | Dharche | 6
7230 | Gorkha | Kashigaun | All | CARE-N | UNIFICATION-N |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Dharche | 6
7231 | Gorkha | Kashigaun | All | GON - PAF | SSICDC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 50 | 0 |  |  |  | Dharche | 6
7232 | Gorkha | Kashigaun |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Completed | 1 | 1 |  |  | Flagged as 1 to show the area has plans | Dharche | 6
7233 | Gorkha | Kerabari | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Mandali CBRC | Siranchok | 1
7234 | Gorkha | Kerabari | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Siranchok | 1
7235 | Gorkha | Kerabari | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Jai Santoshi Mata CBRC | Siranchok | 1
7236 | Gorkha | Kerabari | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Siranchok | 1
7237 | Gorkha | Kerabari | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Himchuli CBRC | Siranchok | 1
7238 | Gorkha | Kerabari | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Annapurna CBRC | Siranchok | 1
7239 | Gorkha | Kerabari | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Siranchok | 1
7240 | Gorkha | Kerabari | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Shiva Shakti CBRC | Siranchok | 1
7241 | Gorkha | Kerabari | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 |  |  |  | Siranchok | 1
7242 | Gorkha | Kerabari | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Deurali CBRC | Siranchok | 1
7243 | Gorkha | Kerabari | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Siranchok | 1
7244 | Gorkha | Kerabari | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Gyampeshori CBRC | Siranchok | 1
7245 | Gorkha | Kerabari | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Siranchok | 1
7246 | Gorkha | Kerabari | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Kerabari-8 CBRC | Siranchok | 1
7247 | Gorkha | Kerabari | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Siranchok | 1
7248 | Gorkha | Kerabari | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 |  |  |  | Siranchok | 1
7249 | Gorkha | Kerabari | All | JICA |  |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 302 | 445 | 2017-05-03 |  |  | Siranchok | 1
7250 | Gorkha | kerabari | All | GON - PAF | LDF | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 20 | 0 |  |  |  | Siranchok | 1
7251 | Gorkha | Kerabari |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 80 |  |  |  | Siranchok | 1
7252 | Gorkha | Kerauja | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 65 | 65 | 2016-09-08 | 2016-09-08 |  | Dharche | 2
7253 | Gorkha | Ghairung | 5 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Sahid Lakhan | 6
7254 | Gorkha | Kerauja | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 162 | 162 |  |  |  | Dharche | 2
7255 | Gorkha | Kerauja | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-07-22 | 2016-07-28 |  | Dharche | 2
7256 | Gorkha | Kerauja | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 43 | 43 | 2016-09-09 | 2016-09-09 |  | Dharche | 2
7257 | Gorkha | Ghairung | 6 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 6 |  |  |  | Sahid Lakhan | 6
7258 | Gorkha | Kerauja | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 32 | 32 |  |  |  | Dharche | 2
7259 | Gorkha | Kerauja | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-07-22 | 2016-07-28 |  | Dharche | 2
7260 | Gorkha | Kerauja | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 21 | 21 | 2016-09-12 | 2016-09-12 |  | Dharche | 2
7261 | Gorkha | Ghairung | 7 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 5 |  |  |  | Sahid Lakhan | 6
7262 | Gorkha | Kerauja | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 5 | 5 |  |  |  | Dharche | 2
7263 | Gorkha | Kerauja | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 46 | 46 | 2016-09-09 | 2016-09-09 |  | Dharche | 2
7264 | Gorkha | Kerauja | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 |  |  |  | Dharche | 2
7265 | Gorkha | Ghairung | 8 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 5 |  |  |  | Sahid Lakhan | 6
7266 | Gorkha | Kerauja | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 44 | 44 |  |  |  | Dharche | 2
7267 | Gorkha | Kerauja | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-07-22 | 2016-07-28 |  | Dharche | 2
7268 | Gorkha | Kerauja | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 23 | 23 | 2016-09-16 | 2016-09-16 |  | Dharche | 2
7269 | Gorkha | Ghairung | 9 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 7 |  |  |  | Sahid Lakhan | 6
7270 | Gorkha | Kerauja | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 70 | 70 |  |  |  | Dharche | 2
7271 | Gorkha | Kerauja | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 35 | 35 | 2016-09-17 | 2016-09-17 |  | Dharche | 2
7272 | Gorkha | Kerauja | 1 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 81 | 81 |  |  |  | Dharche | 2
7273 | Gorkha | Kerauja | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 99 | 99 |  |  |  | Dharche | 2
7274 | Gorkha | Kerauja | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-07-22 | 2016-07-28 |  | Dharche | 2
7275 | Gorkha | Kerauja | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 59 | 59 | 2016-09-15 | 2016-09-15 |  | Dharche | 1
7276 | Gorkha | Kerauja | 2 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 105 | 105 |  |  |  | Dharche | 2
7277 | Gorkha | Kerauja | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 69 | 69 | 2016-09-14 | 2016-09-14 |  | Dharche | 1
7278 | Gorkha | Kerauja | 3 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 56 | 56 |  |  |  | Dharche | 2
7279 | Gorkha | Kerauja | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 18 | 18 | 2016-09-13 | 2016-09-13 |  | Dharche | 1
7280 | Gorkha | Kerauja | 4 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 58 | 58 |  |  |  | Dharche | 2
7281 | Gorkha | Kerauja | 5 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 96 | 96 |  |  |  | Dharche | 2
7282 | Gorkha | Kerauja | All | PIN | UNIFICATION-N | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 476 | 469 | 2016-06-26 | 2016-06-29 | 30 beneficiares were not present during distribution | Dharche | 2
7283 | Gorkha | Kerauja | All | CARE-N | UNIFICATION-N |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Dharche | 2
7284 | Gorkha | Kerauja | 6 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 73 | 73 |  |  |  | Dharche | 2
7285 | Gorkha | Kerauja | All | PIN | UNIFICATION-N | ECHO | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 384 | 358 | 2016-09-01 | 2016-11-01 |  | Dharche | 2
7286 | Gorkha | Kerauja |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Completed | 1 | 1 |  |  | Flagged as 1 to show the area has plans | Dharche | 2
7287 | Gorkha | Kerauja | 7 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 61 | 61 |  |  |  | Dharche | 1
7288 | Gorkha | Kharibot | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 40 | 42 | 2016-03-10 | 2016-03-10 |  | Ajirkot | 2
7289 | Gorkha | Kharibot | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 49 | 2016-03-03 | 2016-03-03 |  | Ajirkot | 2
7290 | Gorkha | Kharibot | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 78 | 2016-03-16 | 2016-03-17 |  | Ajirkot | 2
7291 | Gorkha | Kharibot | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 41 | 2016-03-18 | 2016-03-18 |  | Ajirkot | 2
7292 | Gorkha | Kharibot | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 40 | 44 | 2016-03-11 | 2016-03-11 |  | Ajirkot | 2
7293 | Gorkha | Kharibot | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 46 | 2016-03-20 | 2016-03-20 |  | Ajirkot | 2
7294 | Gorkha | Kharibot | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 42 | 2016-01-01 | 2016-01-01 |  | Ajirkot | 2
7295 | Gorkha | Kharibot | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 43 | 2016-03-30 | 2016-03-30 |  | Ajirkot | 2
7296 | Gorkha | Kharibot | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 42 | 2016-03-31 | 2016-03-31 |  | Ajirkot | 2
7297 | Gorkha | Kharibot | 1 &2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 33 | 2015-03-04 | 2016-03-04 |  | Ajirkot | 2
7298 | Gorkha | Kharibot | 1 to 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 30 | 30 | 2016-04-02 | 2016-04-02 |  | Ajirkot | 2
7299 | Gorkha | Kharibot | 4 & 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 45 | 2016-03-19 | 2016-03-21 |  | Ajirkot | 2
7300 | Gorkha | Kharibot | All | IOM | IOM |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 553 | 533 | 2016-04-07 | 2016-04-26 |  | Ajirkot | 2
7301 | Gorkha | Kharibot | All | ACN | ACN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-07-01 |  |  | Ajirkot | 2
7302 | Gorkha | Kharibot | All | GON - PAF | LDF | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 20 | 0 |  |  |  | Ajirkot | 2
7303 | Gorkha | Kharibot |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 81 |  |  |  | Ajirkot | 2
7304 | Gorkha | Khoplang | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 54 | 54 | 2016-06-25 | 2016-08-11 |  | Palungtar | 2
7305 | Gorkha | Khoplang | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 178 | 178 |  |  |  | Palungtar | 2
7306 | Gorkha | Khoplang | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-18 | 2016-06-24 |  | Palungtar | 2
7307 | Gorkha | Khoplang | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 139 | 139 | 2016-06-25 | 2016-08-10 |  | Palungtar | 2
7308 | Gorkha | Khoplang | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 320 | 320 |  |  |  | Palungtar | 2
7309 | Gorkha | Khoplang | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-18 | 2016-06-24 |  | Palungtar | 2
7310 | Gorkha | Khoplang | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 61 | 61 | 2016-06-25 | 2016-08-09 |  | Palungtar | 2
7311 | Gorkha | Khoplang | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 13 | 13 |  |  |  | Palungtar | 2
7312 | Gorkha | Khoplang | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-18 | 2016-06-24 |  | Palungtar | 2
7313 | Gorkha | Khoplang | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 292 | 292 | 2016-06-25 | 2016-08-12 |  | Palungtar | 1
7314 | Gorkha | Khoplang | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 186 | 186 |  |  |  | Palungtar | 1
7315 | Gorkha | Khoplang | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-18 | 2016-06-24 |  | Palungtar | 1
7316 | Gorkha | Khoplang | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 15 | 15 | 2016-06-25 | 2016-08-13 |  | Palungtar | 1
7317 | Gorkha | Khoplang | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 28 | 28 |  |  |  | Palungtar | 1
7318 | Gorkha | Khoplang | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 28 | 28 | 2016-07-30 | 2016-08-05 |  | Palungtar | 1
7319 | Gorkha | Khoplang | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 122 | 122 | 2016-06-25 | 2016-08-08 |  | Palungtar | 1
7320 | Gorkha | Khoplang | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 136 | 136 |  |  |  | Palungtar | 1
7321 | Gorkha | Khoplang | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-18 | 2016-06-24 |  | Palungtar | 1
7322 | Gorkha | Khoplang | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 66 | 66 | 2016-06-25 | 2016-08-13 |  | Palungtar | 1
7323 | Gorkha | Khoplang | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 |  |  |  | Palungtar | 1
7324 | Gorkha | Khoplang | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 57 | 57 |  |  |  | Palungtar | 1
7325 | Gorkha | Khoplang | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 84 | 84 | 2016-07-29 | 2016-07-29 |  | Palungtar | 1
7326 | Gorkha | Khoplang | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 167 | 167 |  |  |  | Palungtar | 1
7327 | Gorkha | Khoplang | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-18 | 2016-06-24 |  | Palungtar | 1
7328 | Gorkha | Khoplang | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 109 | 109 | 2016-07-28 | 2016-08-11 |  | Palungtar | 1
7329 | Gorkha | Khoplang | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 208 | 208 |  |  |  | Palungtar | 1
7330 | Gorkha | Khoplang | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-18 | 2016-06-24 |  | Palungtar | 1
7331 | Gorkha | Khoplang | All | CARE-N | UNIFICATION-N |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Palungtar | 2
7332 | Gorkha | Khoplang |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Completed | 1 | 1 |  |  | Flagged as 1 to show the area has plans | Palungtar | 2
7333 | Gorkha | Khoplang |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 100 |  |  |  | Palungtar | 2
7334 | Gorkha | Laprak | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 64 | 64 | 2016-07-08 | 2016-07-10 |  | Dharche | 4
7335 | Gorkha | Laprak | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 15 | 15 |  |  |  | Dharche | 4
7336 | Gorkha | Laprak | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-10 | 2016-06-16 |  | Dharche | 4
7337 | Gorkha | Laprak | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 103 | 103 | 2016-07-09 | 2016-07-10 |  | Dharche | 4
7338 | Gorkha | Laprak | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 83 | 83 |  |  |  | Dharche | 4
7339 | Gorkha | Laprak | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-10 | 2016-06-16 |  | Dharche | 4
7340 | Gorkha | Laprak | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 61 | 61 | 2016-07-10 | 2016-07-10 |  | Dharche | 4
7341 | Gorkha | Laprak | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 21 | 21 |  |  |  | Dharche | 4
7342 | Gorkha | Laprak | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-10 | 2016-06-16 |  | Dharche | 4
7343 | Gorkha | Laprak | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 66 | 66 | 2016-07-10 | 2016-07-12 |  | Dharche | 4
7344 | Gorkha | Laprak | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 44 | 44 |  |  |  | Dharche | 4
7345 | Gorkha | Laprak | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 56 | 56 | 2016-07-10 | 2016-07-13 |  | Dharche | 4
7346 | Gorkha | Laprak | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 34 | 34 |  |  |  | Dharche | 4
7347 | Gorkha | Laprak | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-10 | 2016-06-16 |  | Dharche | 4
7348 | Gorkha | Laprak | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 73 | 73 | 2016-07-10 | 2016-07-14 |  | Dharche | 4
7349 | Gorkha | Laprak | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 |  |  |  | Dharche | 4
7350 | Gorkha | Laprak | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 41 | 41 |  |  |  | Dharche | 4
7351 | Gorkha | Laprak | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-10 | 2016-06-16 |  | Dharche | 4
7352 | Gorkha | Laprak | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 51 | 51 | 2016-07-10 | 2016-07-20 |  | Dharche | 4
7353 | Gorkha | Laprak | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 20 |  |  |  | Dharche | 4
7354 | Gorkha | Laprak | 7 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-10 | 2016-06-16 |  | Dharche | 4
7355 | Gorkha | Laprak | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 65 | 65 | 2016-07-10 | 2016-07-17 |  | Dharche | 4
7356 | Gorkha | Laprak | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 31 | 31 |  |  |  | Dharche | 4
7357 | Gorkha | Laprak | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-10 | 2016-06-16 |  | Dharche | 4
7358 | Gorkha | Laprak | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 68 | 68 | 2016-07-10 | 2016-07-18 |  | Dharche | 4
7359 | Gorkha | Laprak | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 9 | 9 |  |  |  | Dharche | 4
7360 | Gorkha | Laprak | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-10 | 2016-06-16 |  | Dharche | 4
7361 | Gorkha | Laprak | All | PIN | UNIFICATION-N | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 640 | 627 | 2016-10-25 | 2016-10-28 |  | Dharche | 4
7362 | Gorkha | Laprak | All | CARE-N | UNIFICATION-N |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Dharche | 4
7363 | Gorkha | Laprak | All | PIN | UNIFICATION-N | ECHO | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 397 | 397 | 2016-09-01 | 2016-11-01 |  | Dharche | 4
7364 | Gorkha | Laprak | All | GON - PAF | HADC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0 |  |  |  | Dharche | 4
7365 | Gorkha | Laprak |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Completed | 1 | 1 |  |  | Flagged as 1 to show the area has plans | Dharche | 4
7366 | Gorkha | Lapu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-10 | 2017-06-15 |  | Dharche | 7
7367 | Gorkha | Lapu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 113 | 46 | 2017-05-21 |  |  | Dharche | 7
7368 | Gorkha | Lapu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 5 | 2017-03-17 |  |  | Dharche | 7
7369 | Gorkha | Lapu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 113 | 0 |  |  |  | Dharche | 7
7370 | Gorkha | Lapu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 113 | 0 |  |  |  | Dharche | 7
7371 | Gorkha | Lapu | 1 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-30 | Liding CBRC | Dharche | 7
7372 | Gorkha | Lapu | 1 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-30 | Thandi Gaun CBRC | Dharche | 7
7373 | Gorkha | Lapu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-10 | 2017-06-15 |  | Dharche | 7
7374 | Gorkha | Lapu | 1 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 26 | 26 | 2017-01-04 | 2017-02-09 |  | Dharche | 7
7375 | Gorkha | Lapu | 1 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-10 | 2017-06-16 |  | Dharche | 7
7376 | Gorkha | Lapu | 1 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2015-04-15 | 2017-06-21 |  | Dharche | 7
7377 | Gorkha | Lapu | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 17 | 4 | 2017-05-21 |  |  | Dharche | 7
7378 | Gorkha | Lapu | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 4 |  |  |  | Dharche | 7
7379 | Gorkha | Lapu | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 17 | 0 |  |  |  | Dharche | 7
7380 | Gorkha | Lapu | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 17 | 0 |  |  |  | Dharche | 7
7381 | Gorkha | Lapu | 2 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-27 | Putau CBRC | Dharche | 7
7382 | Gorkha | Lapu | 2 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-11-30 | 2016-12-06 |  | Dharche | 7
7383 | Gorkha | Lapu | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dharche | 7
7384 | Gorkha | Lapu | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 86 | 9 | 2017-05-21 |  |  | Dharche | 7
7385 | Gorkha | Lapu | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 4 | 2017-03-17 |  |  | Dharche | 7
7386 | Gorkha | Lapu | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 86 | 0 |  |  |  | Dharche | 7
7387 | Gorkha | Lapu | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 86 | 0 |  |  |  | Dharche | 7
7388 | Gorkha | Lapu | 3 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-29 | Damphu Danda CBRC | Dharche | 7
7389 | Gorkha | Lapu | 3 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 24 | 24 | 2017-01-04 | 2017-01-10 |  | Dharche | 7
7390 | Gorkha | Lapu | 3 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Dharche | 7
7391 | Gorkha | Lapu | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-07-01 | 2017-10-10 |  | Dharche | 7
7392 | Gorkha | Lapu | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 50 | 20 | 2017-05-21 |  |  | Dharche | 7
7393 | Gorkha | Lapu | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 14 | 2017-03-17 |  |  | Dharche | 7
7394 | Gorkha | Lapu | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 50 | 0 |  |  |  | Dharche | 7
7395 | Gorkha | Lapu | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 50 | 0 |  |  |  | Dharche | 7
7396 | Gorkha | Lapu | 4 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-29 | Milijuli CBRC | Dharche | 7
7397 | Gorkha | Lapu | 4 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2017-01-04 | 2017-01-10 |  | Dharche | 7
7398 | Gorkha | Lapu | 4 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-18 | 2017-07-28 |  | Dharche | 7
7399 | Gorkha | Lapu | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-02-26 | 2017-06-20 |  | Dharche | 7
7400 | Gorkha | Lapu | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 34 | 18 | 2017-03-21 |  |  | Dharche | 7
7401 | Gorkha | Lapu | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 15 | 2017-03-17 |  |  | Dharche | 7
7402 | Gorkha | Lapu | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 34 | 0 |  |  |  | Dharche | 7
7403 | Gorkha | Lapu | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 34 | 0 |  |  |  | Dharche | 7
7404 | Gorkha | Lapu | 5 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-27 | Siran Ganu CBRC | Dharche | 7
7405 | Gorkha | Lapu | 5 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-11-30 | 2016-12-06 |  | Dharche | 7
7406 | Gorkha | Lapu | 5 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-18 | 2017-07-26 |  | Dharche | 7
7407 | Gorkha | Lapu | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-07 | 2017-06-20 |  | Dharche | 7
7408 | Gorkha | Lapu | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 82 | 73 | 2017-05-21 |  |  | Dharche | 7
7409 | Gorkha | Lapu | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 16 | 2017-03-17 |  |  | Dharche | 7
7410 | Gorkha | Lapu | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 82 | 0 |  |  |  | Dharche | 7
7411 | Gorkha | Lapu | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 82 | 0 |  |  |  | Dharche | 7
7412 | Gorkha | Lapu | 6 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-07-18 | Khani Gaun CBRC | Dharche | 7
7413 | Gorkha | Lapu | 6 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-11-30 | 2016-12-06 |  | Dharche | 7
7414 | Gorkha | Lapu | 6 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-07 | 2017-06-28 |  | Dharche | 7
7415 | Gorkha | Lapu | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dharche | 7
7416 | Gorkha | Lapu | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 57 | 10 | 2017-05-21 |  |  | Dharche | 7
7417 | Gorkha | Lapu | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 6 | 2017-03-17 |  |  | Dharche | 7
7418 | Gorkha | Lapu | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 57 | 0 |  |  |  | Dharche | 7
7419 | Gorkha | Lapu | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 57 | 0 |  |  |  | Dharche | 7
7420 | Gorkha | Lapu | 7 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-07-31 | Puchhar Gaun CBRC | Dharche | 7
7421 | Gorkha | Lapu | 7 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-11-30 | 2016-12-06 |  | Dharche | 7
7422 | Gorkha | Lapu | 7 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Dharche | 7
7423 | Gorkha | Lapu | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dharche | 7
7424 | Gorkha | Lapu | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 58 | 15 | 2017-05-21 |  |  | Dharche | 7
7425 | Gorkha | Lapu | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 1 | 2017-03-17 |  |  | Dharche | 7
7426 | Gorkha | Lapu | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 58 | 0 |  |  |  | Dharche | 7
7427 | Gorkha | Lapu | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 58 | 0 |  |  |  | Dharche | 7
7428 | Gorkha | Lapu | 8 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-26 | MajhGaun CBRC | Dharche | 7
7429 | Gorkha | Lapu | 8 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-11-30 | 2016-12-06 |  | Dharche | 7
7430 | Gorkha | Lapu | 8 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Dharche | 7
7431 | Gorkha | Lapu | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dharche | 7
7432 | Gorkha | Lapu | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 25 | 8 | 2017-05-21 |  |  | Dharche | 7
7433 | Gorkha | Lapu | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 7 | 2017-03-17 |  |  | Dharche | 7
7434 | Gorkha | Lapu | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 25 | 0 |  |  |  | Dharche | 7
7435 | Gorkha | Lapu | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 25 | 0 |  |  |  | Dharche | 7
7436 | Gorkha | Lapu | 9 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-26 | Harsang CBRC | Dharche | 7
7437 | Gorkha | Lapu | 9 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-11-30 | 2016-12-06 |  | Dharche | 7
7438 | Gorkha | Lapu | 9 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Dharche | 7
7439 | Gorkha | Lho | 1 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Chum Nubri | 2
7440 | Gorkha | Lho | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 35 | 0 |  |  |  | Chum Nubri | 2
7441 | Gorkha | Lho | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 2
7442 | Gorkha | Lho | 1 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 35 | 0 |  |  |  | Chum Nubri | 2
7443 | Gorkha | Lho | 1 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 35 | 0 |  |  |  | Chum Nubri | 2
7444 | Gorkha | Lho | 1 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-12-24 | 2017-01-04 |  | Chum Nubri | 2
7445 | Gorkha | Lho | 1 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 2
7446 | Gorkha | Lho | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 50 | 0 |  |  |  | Chum Nubri | 2
7447 | Gorkha | Lho | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 2
7448 | Gorkha | Lho | 2 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 50 | 0 |  |  |  | Chum Nubri | 2
7449 | Gorkha | Lho | 2 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 50 | 0 |  |  |  | Chum Nubri | 2
7450 | Gorkha | Lho | 2 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 2 | 2 | 2016-12-24 | 2017-01-04 |  | Chum Nubri | 2
7451 | Gorkha | Lho | 2 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 2
7452 | Gorkha | Lho | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 43 | 0 |  |  |  | Chum Nubri | 2
7453 | Gorkha | Lho | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 2
7454 | Gorkha | Lho | 3 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 43 | 0 |  |  |  | Chum Nubri | 2
7455 | Gorkha | Lho | 3 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 43 | 0 |  |  |  | Chum Nubri | 2
7456 | Gorkha | Lho | 3 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 4 | 4 | 2016-12-24 | 2017-01-04 |  | Chum Nubri | 2
7457 | Gorkha | Lho | 3 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 2
7458 | Gorkha | Lho | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 55 | 0 |  |  |  | Chum Nubri | 2
7459 | Gorkha | Lho | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 2
7460 | Gorkha | Lho | 4 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 55 | 0 |  |  |  | Chum Nubri | 2
7461 | Gorkha | Lho | 4 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 55 | 0 |  |  |  | Chum Nubri | 2
7462 | Gorkha | Lho | 4 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 | 2016-09-01 | 2017-03-31 |  | Chum Nubri | 2
7463 | Gorkha | Lho | 4 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 2
7464 | Gorkha | Lho | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 30 | 0 |  |  |  | Chum Nubri | 2
7465 | Gorkha | Lho | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 2
7466 | Gorkha | Lho | 5 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 30 | 0 |  |  |  | Chum Nubri | 2
7467 | Gorkha | Lho | 5 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 30 | 0 |  |  |  | Chum Nubri | 2
7468 | Gorkha | Lho | 5 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 3 | 2016-12-24 | 2017-01-04 |  | Chum Nubri | 2
7469 | Gorkha | Lho | 5 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 2
7470 | Gorkha | Lho | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 44 | 0 |  |  |  | Chum Nubri | 2
7471 | Gorkha | Lho | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 2
7472 | Gorkha | Lho | 6 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 44 | 0 |  |  |  | Chum Nubri | 2
7473 | Gorkha | Lho | 6 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 44 | 0 |  |  |  | Chum Nubri | 2
7474 | Gorkha | Lho | 6 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 2 | 2 | 2016-12-24 | 2017-01-04 |  | Chum Nubri | 2
7475 | Gorkha | Lho | 6 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 2
7476 | Gorkha | Lho | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 23 | 0 |  |  |  | Chum Nubri | 2
7477 | Gorkha | Lho | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 2
7478 | Gorkha | Lho | 7 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 23 | 0 |  |  |  | Chum Nubri | 2
7479 | Gorkha | Lho | 7 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 23 | 0 |  |  |  | Chum Nubri | 2
7480 | Gorkha | Lho | 7 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 | 2016-09-01 | 2017-03-31 |  | Chum Nubri | 2
7481 | Gorkha | Lho | 7 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 2
7482 | Gorkha | Lho | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 30 | 0 |  |  |  | Chum Nubri | 2
7483 | Gorkha | Lho | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 2
7484 | Gorkha | Lho | 8 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 30 | 0 |  |  |  | Chum Nubri | 2
7485 | Gorkha | Lho | 8 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 30 | 0 |  |  |  | Chum Nubri | 2
7486 | Gorkha | Lho | 8 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 | 2016-09-01 | 2017-03-31 |  | Chum Nubri | 2
7487 | Gorkha | Lho | 8 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 2
7488 | Gorkha | Lho | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 36 | 0 |  |  |  | Chum Nubri | 2
7489 | Gorkha | Lho | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 2
7490 | Gorkha | Lho | 9 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 36 | 0 |  |  |  | Chum Nubri | 2
7491 | Gorkha | Lho | 9 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 36 | 0 |  |  |  | Chum Nubri | 2
7492 | Gorkha | Lho | 9 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 3 | 3 | 2016-12-24 | 2017-01-04 |  | Chum Nubri | 2
7493 | Gorkha | Lho | 9 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 2
7494 | Gorkha | Lho | 1,2 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-06-17 |  | Chum Nubri | 2
7495 | Gorkha | Lho | 3,4 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-06-15 |  | Chum Nubri | 2
7496 | Gorkha | Lho | 5,6,7,8,9 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-31 |  | Chum Nubri | 2
7497 | Gorkha | Makaising | All | DCA | ECO-N | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 28 | 28 | 2016-02-15 | 2016-02-19 |  | Gandaki | 1
7498 | Gorkha | Makaising | All | GON - PAF | GORETO GORKHA | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0 |  |  |  | Gandaki | 1
7499 | Gorkha | Kerauja | 8 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 75 | 75 |  |  |  | Dharche | 1
7500 | Gorkha | Manbu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-30 | 2017-06-20 |  | Aarughat | 2
7501 | Gorkha | Manbu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 70 | 21 | 2017-05-21 |  |  | Aarughat | 2
7502 | Gorkha | Manbu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 11 | 2017-03-17 |  |  | Aarughat | 2
7503 | Gorkha | Manbu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 70 | 0 |  |  |  | Aarughat | 2
7504 | Gorkha | Manbu | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 70 | 0 |  |  |  | Aarughat | 2
7505 | Gorkha | Manbu | 1 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-28 | Thotneri CBRC | Aarughat | 2
7506 | Gorkha | Manbu | 1 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-01-01 | 2017-01-07 |  | Aarughat | 2
7507 | Gorkha | Manbu | 1 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-30 | 2017-06-25 |  | Aarughat | 2
7508 | Gorkha | Manbu | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-24 | 2017-06-20 |  | Aarughat | 2
7509 | Gorkha | Manbu | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 152 | 23 | 2017-05-21 |  |  | Aarughat | 2
7510 | Gorkha | Manbu | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 8 | 2017-03-17 |  |  | Aarughat | 2
7511 | Gorkha | Manbu | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 152 | 0 |  |  |  | Aarughat | 2
7512 | Gorkha | Manbu | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 152 | 0 |  |  |  | Aarughat | 2
7513 | Gorkha | Manbu | 2 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-30 | Dhalchok BRC | Aarughat | 2
7514 | Gorkha | Manbu | 2 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-01-01 | 2017-01-07 |  | Aarughat | 2
7515 | Gorkha | Manbu | 2 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-24 | 2017-06-25 |  | Aarughat | 2
7516 | Gorkha | Manbu | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-30 | 2017-06-20 |  | Aarughat | 2
7517 | Gorkha | Manbu | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 264 | 28 | 2017-05-21 |  |  | Aarughat | 2
7518 | Gorkha | Manbu | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 20 | 2017-03-17 |  |  | Aarughat | 2
7519 | Gorkha | Manbu | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 264 | 0 |  |  |  | Aarughat | 2
7520 | Gorkha | Manbu | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 264 | 0 |  |  |  | Aarughat | 2
7521 | Gorkha | Manbu | 3 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-27 | Patlekhark CBRC | Aarughat | 2
7522 | Gorkha | Manbu | 3 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-27 | Manbu Basi CBRC | Aarughat | 2
7523 | Gorkha | Manbu | 3 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-27 | Manbu Gaun CBRC | Aarughat | 2
7524 | Gorkha | Manbu | 3 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-01-01 | 2017-01-07 |  | Aarughat | 2
7525 | Gorkha | Manbu | 3 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-30 | 2017-06-25 |  | Aarughat | 2
7526 | Gorkha | Manbu | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-18 | 2017-06-20 |  | Aarughat | 2
7527 | Gorkha | Manbu | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 185 | 20 | 2017-05-21 |  |  | Aarughat | 2
7528 | Gorkha | Manbu | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 21 | 2017-03-17 |  |  | Aarughat | 2
7529 | Gorkha | Manbu | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 185 | 0 |  |  |  | Aarughat | 2
7530 | Gorkha | Manbu | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 185 | 0 |  |  |  | Aarughat | 2
7531 | Gorkha | Manbu | 4 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-29 | Katunjie Gaun CBRC | Aarughat | 2
7532 | Gorkha | Manbu | 4 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 5 | 2017-01-01 | 2017-01-07 |  | Aarughat | 2
7533 | Gorkha | Manbu | 4 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-18 | 2017-06-25 |  | Aarughat | 2
7534 | Gorkha | Manbu | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-23 | 2017-06-20 |  | Aarughat | 1
7535 | Gorkha | Manbu | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 224 | 27 | 2017-05-21 |  |  | Aarughat | 1
7536 | Gorkha | Manbu | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 25 | 2017-03-17 |  |  | Aarughat | 1
7537 | Gorkha | Manbu | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 224 | 0 |  |  |  | Aarughat | 1
7538 | Gorkha | Manbu | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 224 | 0 |  |  |  | Aarughat | 1
7539 | Gorkha | Manbu | 5 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-22 | Siran Gaun CBRC | Aarughat | 1
7540 | Gorkha | Manbu | 5 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 5 | 2017-01-16 | 2017-01-22 |  | Aarughat | 1
7541 | Gorkha | Manbu | 5 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-23 | 2017-06-25 |  | Aarughat | 1
7542 | Gorkha | Manbu | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-02-27 | 2017-06-20 |  | Aarughat | 1
7543 | Gorkha | Manbu | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 305 | 8 | 2017-05-21 |  |  | Aarughat | 1
7544 | Gorkha | Manbu | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 15 | 2017-03-17 |  |  | Aarughat | 1
7545 | Gorkha | Manbu | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 305 | 0 |  |  |  | Aarughat | 1
7546 | Gorkha | Manbu | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 305 | 0 |  |  |  | Aarughat | 1
7547 | Gorkha | Manbu | 6 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-24 | Majh Gaun CBRC | Aarughat | 1
7548 | Gorkha | Manbu | 6 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-24 | Syamchet CBRC | Aarughat | 1
7549 | Gorkha | Manbu | 6 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 18 | 18 | 2017-01-16 | 2017-01-22 |  | Aarughat | 1
7550 | Gorkha | Manbu | 6 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-27 | 2017-06-25 |  | Aarughat | 1
7551 | Gorkha | Manbu | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-18 | 2017-06-20 |  | Aarughat | 1
7552 | Gorkha | Manbu | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 228 | 13 | 2017-05-21 |  |  | Aarughat | 1
7553 | Gorkha | Manbu | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 20 | 2017-03-17 |  |  | Aarughat | 1
7554 | Gorkha | Manbu | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 228 | 0 |  |  |  | Aarughat | 1
7555 | Gorkha | Manbu | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 228 | 0 |  |  |  | Aarughat | 1
7556 | Gorkha | Manbu | 7 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-23 | Sapchet CBRC | Aarughat | 1
7557 | Gorkha | Manbu | 7 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-23 | Dauchet CBRC | Aarughat | 1
7558 | Gorkha | Manbu | 7 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-12-10 | 2016-12-16 |  | Aarughat | 1
7559 | Gorkha | Manbu | 7 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-18 | 2017-06-25 |  | Aarughat | 1
7560 | Gorkha | Manbu | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-09 | 2017-06-20 |  | Aarughat | 1
7561 | Gorkha | Manbu | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 216 | 14 | 2017-05-21 |  |  | Aarughat | 1
7562 | Gorkha | Manbu | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 32 | 2017-03-17 |  |  | Aarughat | 1
7563 | Gorkha | Manbu | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 216 | 0 |  |  |  | Aarughat | 1
7564 | Gorkha | Manbu | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 216 | 0 |  |  |  | Aarughat | 1
7565 | Gorkha | Manbu | 8 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-26 | Dhunchet CBRC | Aarughat | 1
7566 | Gorkha | Manbu | 8 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 2016-12-10 | 2016-12-16 |  | Aarughat | 1
7567 | Gorkha | Manbu | 8 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-09 | 2017-06-25 |  | Aarughat | 1
7568 | Gorkha | Manbu | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Aarughat | 1
7569 | Gorkha | Manbu | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 203 | 23 | 2017-05-21 |  |  | Aarughat | 1
7570 | Gorkha | Manbu | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 13 | 2017-03-17 |  |  | Aarughat | 1
7571 | Gorkha | Manbu | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 203 | 0 |  |  |  | Aarughat | 1
7572 | Gorkha | Manbu | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 203 | 0 |  |  |  | Aarughat | 1
7573 | Gorkha | Manbu | 9 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-25 | Dhorat CBRC | Aarughat | 1
7574 | Gorkha | Manbu | 9 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-12-10 | 2016-12-16 |  | Aarughat | 1
7575 | Gorkha | Manbu | 9 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-09 | 2017-06-25 |  | Aarughat | 1
7576 | Gorkha | Tandrang | 7 | NDS | NDS | MEDICO-I | Training | Short training | Carpenter | Carpenter Traiing done at Chitawon District | # of trainees | Yes | Completed | 120 | 3 | 2016-07-01 | 2017-04-01 |  | Bhimsen | 2
7577 | Gorkha | Masel | 1 | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 75000 is provided as third tranche | # of households | Yes | Completed | 35 | 35 |  |  |  | Bhimsen | 1
7578 | Gorkha | Masel | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-21 | Ward no. 1 Purna Nirman Samudaik Samiti | Bhimsen | 1
7579 | Gorkha | Masel | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Bhimsen | 1
7580 | Gorkha | Masel | 1 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-01 | 2016-02-29 |  | Bhimsen | 1
7581 | Gorkha | Masel | 1 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 17 | 2016-04-06 | 2016-04-12 |  | Bhimsen | 1
7582 | Gorkha | Masel | 2 | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 17 | 17 |  |  |  | Bhimsen | 1
7583 | Gorkha | Masel | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Ward no. 2 Purna Nirman Samudaik Samiti | Bhimsen | 1
7584 | Gorkha | Masel | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimsen | 1
7585 | Gorkha | Masel | 2 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-01 | 2016-02-29 |  | Bhimsen | 1
7586 | Gorkha | Masel | 2 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-04-06 | 2016-04-12 |  | Bhimsen | 1
7587 | Gorkha | Masel | 3 | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 23 | 23 |  |  |  | Bhimsen | 1
7588 | Gorkha | Masel | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Ujyalo Purna Nirman Samudaik Samiti | Bhimsen | 1
7589 | Gorkha | Masel | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Bhimsen | 1
7590 | Gorkha | Masel | 3 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-01 | 2016-02-29 |  | Bhimsen | 1
7591 | Gorkha | Masel | 3 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-04-06 | 2016-07-26 |  | Bhimsen | 1
7592 | Gorkha | Masel | 4 | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 16 | 16 |  |  |  | Bhimsen | 1
7593 | Gorkha | Masel | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Ward no. 4 Purna Nirman Samudaik Samiti | Bhimsen | 1
7594 | Gorkha | Masel | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Bhimsen | 1
7595 | Gorkha | Masel | 4 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-01 | 2016-02-29 |  | Bhimsen | 1
7596 | Gorkha | Masel | 4 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-04-06 | 2016-04-12 |  | Bhimsen | 1
7597 | Gorkha | Masel | 5 | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 75000 is provided as third tranche | # of households | Yes | Completed | 14 | 14 |  |  |  | Bhimsen | 1
7598 | Gorkha | Masel | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-22 | Shree Krishna Purna Nirman Samudaik Samiti | Bhimsen | 1
7599 | Gorkha | Masel | 5 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-01 | 2016-02-29 |  | Bhimsen | 1
7600 | Gorkha | Masel | 5 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-04-01 | 2016-04-07 |  | Bhimsen | 1
7601 | Gorkha | Masel | 6 | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 18 | 18 |  |  |  | Bhimsen | 1
7602 | Gorkha | Masel | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Khagi Thok Purna Nirman Samudaik Samiti | Bhimsen | 1
7603 | Gorkha | Masel | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Bhimsen | 1
7604 | Gorkha | Masel | 6 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-01 | 2016-02-29 |  | Bhimsen | 1
7605 | Gorkha | Masel | 6 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-04-01 | 2016-04-07 |  | Bhimsen | 1
7606 | Gorkha | Masel | 7 | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 75000 is provided as third tranche | # of households | Yes | Completed | 14 | 10 |  |  |  | Bhimsen | 1
7607 | Gorkha | Masel | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Brindawati Purna Nirman Samudaik Samiti | Bhimsen | 1
7608 | Gorkha | Masel | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Bhimsen | 1
7609 | Gorkha | Masel | 7 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-01 | 2016-02-29 |  | Bhimsen | 1
7610 | Gorkha | Masel | 7 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-04-01 | 2016-04-07 |  | Bhimsen | 1
7611 | Gorkha | Masel | 8 | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 13 | 6 |  |  |  | Bhimsen | 1
7612 | Gorkha | Masel | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Devi Sthan Purna Nirman Samudaik Samiti | Bhimsen | 1
7613 | Gorkha | Masel | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimsen | 1
7614 | Gorkha | Masel | 8 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-01 | 2016-02-29 |  | Bhimsen | 1
7615 | Gorkha | Masel | 8 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-04-01 | 2016-04-07 |  | Bhimsen | 1
7616 | Gorkha | Masel | 9 | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 36 | 36 |  |  |  | Bhimsen | 1
7617 | Gorkha | Masel | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-28 | Mandali Purna Nirman Samudaik Samiti | Bhimsen | 1
7618 | Gorkha | Masel | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 |  |  |  | Bhimsen | 1
7619 | Gorkha | Masel | 9 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-01 | 2016-02-29 |  | Bhimsen | 1
7620 | Gorkha | Masel | 9 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-04-01 | 2016-04-07 |  | Bhimsen | 1
7621 | Gorkha | Masel | All | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000 was provided as first tranche | # of households | Yes | Completed | 200 | 200 |  |  | Rs 50000 first tranche of Government subsidy was supported by Save | Bhimsen | 1
7622 | Gorkha | Masel | All | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 150000 is provided as second tranche | # of households | Yes | Completed | 200 | 195 |  |  |  | Bhimsen | 1
7623 | Gorkha | Masel | All | JICA |  |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 1097 | 1460 | 2017-05-03 |  |  | Bhimsen | 1
7624 | Gorkha | Masel | All | GON - PAF | SDSC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0 |  |  |  | Bhimsen | 1
7625 | Gorkha | Masel | All | SCI | SSICDC | SCI | Training | Other trainings | Other trainings (specify in Activity Detail) | CSEB Training( Block Making Training) | # of trainees | Yes | Completed | 10 | 10 | 2017-03-01 | 2017-03-10 |  | Bhimsen | 1
7626 | Gorkha | Masel | All | SCI | SSICDC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-01-04 | 2017-02-12 |  | Bhimsen | 1
7627 | Gorkha | Masel |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 78 |  |  |  | Bhimsen | 1
7628 | Gorkha | Masel |  | NYF | NYF |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-02-01 | 2016-02-29 |  | Bhimsen | 1
7629 | Gorkha | Masel |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 63 |  |  |  | Bhimsen | 1
7630 | Gorkha | Muchhok | 1 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 6 | 6 |  |  |  | Ajirkot | 5
7631 | Gorkha | Muchhok | 1 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 6 | 1 |  |  |  | Ajirkot | 5
7632 | Gorkha | Muchhok | 1 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 6 | 0 |  |  |  | Ajirkot | 5
7633 | Gorkha | Muchhok | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 189 | 189 | 2016-06-08 | 2016-09-01 |  | Ajirkot | 5
7634 | Gorkha | Muchhok | 1 | INF-N | PDF | INF International | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Planned | 6 | 0 |  |  |  | Ajirkot | 5
7635 | Gorkha | Muchhok | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | Muchhok-1 CBRC | Ajirkot | 5
7636 | Gorkha | Muchhok | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Vryangdada CBRC | Ajirkot | 5
7637 | Gorkha | Muchhok | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Manighaun CBRC | Ajirkot | 5
7638 | Gorkha | Muchhok | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 236 | 236 |  |  |  | Ajirkot | 5
7639 | Gorkha | Muchhok | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-01 | 2016-07-21 |  | Ajirkot | 5
7640 | Gorkha | Muchhok | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Ajirkot | 5
7641 | Gorkha | Muchhok | 2 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 2 | 2 |  |  |  | Ajirkot | 5
7642 | Gorkha | Muchhok | 2 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Planned | 2 | 0 |  |  |  | Ajirkot | 5
7643 | Gorkha | Muchhok | 2 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 2 | 0 |  |  |  | Ajirkot | 5
7644 | Gorkha | Muchhok | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 78 | 78 | 2016-08-12 | 2016-08-12 |  | Ajirkot | 5
7645 | Gorkha | Muchhok | 2 | INF-N | PDF | INF International | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Planned | 2 | 0 |  |  |  | Ajirkot | 5
7646 | Gorkha | Muchhok | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Dhiska CBRC | Ajirkot | 5
7647 | Gorkha | Muchhok | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 91 | 91 |  |  |  | Ajirkot | 5
7648 | Gorkha | Muchhok | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-01 | 2016-07-21 |  | Ajirkot | 5
7649 | Gorkha | Muchhok | 3 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 3 | 3 |  |  |  | Ajirkot | 5
7650 | Gorkha | Muchhok | 3 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Planned | 3 | 0 |  |  |  | Ajirkot | 5
7651 | Gorkha | Muchhok | 3 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 3 | 0 |  |  |  | Ajirkot | 5
7652 | Gorkha | Muchhok | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 54 | 54 | 2016-08-05 | 2016-08-05 |  | Ajirkot | 5
7653 | Gorkha | Muchhok | 3 | INF-N | PDF | INF International | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Planned | 3 | 0 |  |  |  | Ajirkot | 5
7654 | Gorkha | Muchhok | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Muchhok-3, Muchhoktar CBRC | Ajirkot | 5
7655 | Gorkha | Muchhok | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Muchhok-3 CBRC | Ajirkot | 5
7656 | Gorkha | Muchhok | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 59 | 59 |  |  |  | Ajirkot | 5
7657 | Gorkha | Muchhok | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-07-15 | 2016-07-21 |  | Ajirkot | 5
7658 | Gorkha | Muchhok | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 62 | 62 | 2016-08-11 | 2016-08-11 |  | Ajirkot | 5
7659 | Gorkha | Muchhok | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Muchhok-4 CBRC | Ajirkot | 5
7660 | Gorkha | Muchhok | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 64 | 64 |  |  |  | Ajirkot | 5
7661 | Gorkha | Muchhok | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-01 | 2016-06-07 |  | Ajirkot | 5
7662 | Gorkha | Muchhok | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Ajirkot | 5
7663 | Gorkha | Muchhok | 5 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 6 | 6 |  |  |  | Ajirkot | 5
7664 | Gorkha | Muchhok | 5 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 6 | 2 |  |  |  | Ajirkot | 5
7665 | Gorkha | Muchhok | 5 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 6 | 0 |  |  |  | Ajirkot | 5
7666 | Gorkha | Muchhok | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 91 | 91 | 2016-08-31 | 2016-08-31 |  | Ajirkot | 5
7667 | Gorkha | Muchhok | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 |  |  |  | Ajirkot | 5
7668 | Gorkha | Muchhok | 5 | INF-N | PDF | INF International | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Planned | 6 | 0 |  |  |  | Ajirkot | 5
7669 | Gorkha | Muchhok | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Muchhok-5 CBRC | Ajirkot | 5
7670 | Gorkha | Muchhok | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 149 | 149 |  |  |  | Ajirkot | 5
7671 | Gorkha | Muchhok | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-01 | 2016-07-21 |  | Ajirkot | 5
7672 | Gorkha | Muchhok | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Ajirkot | 5
7673 | Gorkha | Muchhok | 6 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 7 | 7 |  |  |  | Ajirkot | 5
7674 | Gorkha | Muchhok | 6 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 7 | 2 |  |  |  | Ajirkot | 5
7675 | Gorkha | Muchhok | 6 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 7 | 0 |  |  |  | Ajirkot | 5
7676 | Gorkha | Muchhok | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 105 | 105 | 2016-09-03 | 2016-09-03 |  | Ajirkot | 5
7677 | Gorkha | Muchhok | 6 | INF-N | PDF | INF International | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Planned | 7 | 0 |  |  |  | Ajirkot | 5
7678 | Gorkha | Muchhok | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Muchhok-6 CBRC | Ajirkot | 5
7679 | Gorkha | Muchhok | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 186 | 186 |  |  |  | Ajirkot | 5
7680 | Gorkha | Muchhok | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-01 | 2016-07-21 |  | Ajirkot | 5
7681 | Gorkha | Muchhok | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Ajirkot | 5
7682 | Gorkha | Muchhok | 7 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 1 | 1 |  |  |  | Ajirkot | 5
7683 | Gorkha | Muchhok | 7 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Planned | 1 | 0 |  |  |  | Ajirkot | 5
7684 | Gorkha | Muchhok | 7 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 1 | 0 |  |  |  | Ajirkot | 5
7685 | Gorkha | Muchhok | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 56 | 56 | 2016-08-04 | 2016-08-04 |  | Ajirkot | 5
7686 | Gorkha | Muchhok | 7 | INF-N | PDF | INF International | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Planned | 1 | 0 |  |  |  | Ajirkot | 5
7687 | Gorkha | Muchhok | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 62 | 62 |  |  |  | Ajirkot | 5
7688 | Gorkha | Muchhok | 7 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-01 | 2016-07-21 |  | Ajirkot | 5
7689 | Gorkha | Muchhok | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Ajirkot | 5
7690 | Gorkha | Muchhok | 8 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 1 | 1 |  |  |  | Ajirkot | 5
7691 | Gorkha | Muchhok | 8 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Planned | 1 | 0 |  |  |  | Ajirkot | 5
7692 | Gorkha | Muchhok | 8 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 1 | 0 |  |  |  | Ajirkot | 5
7693 | Gorkha | Muchhok | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 47 | 47 | 2016-08-01 | 2016-08-01 |  | Ajirkot | 5
7694 | Gorkha | Muchhok | 8 | INF-N | PDF | INF International | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Planned | 1 | 0 |  |  |  | Ajirkot | 5
7695 | Gorkha | Muchhok | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Muchhok-8 CBRC | Ajirkot | 5
7696 | Gorkha | Muchhok | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 40 | 40 |  |  |  | Ajirkot | 5
7697 | Gorkha | Muchhok | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-01 | 2016-07-21 |  | Ajirkot | 5
7698 | Gorkha | Muchhok | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 |  |  |  | Ajirkot | 5
7699 | Gorkha | Muchhok | 9 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 1 | 1 |  |  |  | Ajirkot | 5
7700 | Gorkha | Muchhok | 9 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Planned | 1 | 0 |  |  |  | Ajirkot | 5
7701 | Gorkha | Muchhok | 9 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 1 | 0 |  |  |  | Ajirkot | 5
7702 | Gorkha | Muchhok | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 104 | 104 | 2016-07-31 | 2016-07-31 |  | Ajirkot | 5
7703 | Gorkha | Muchhok | 9 | INF-N | PDF | INF International | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Planned | 1 | 0 |  |  |  | Ajirkot | 5
7704 | Gorkha | Muchhok | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Agridanda CBRC | Ajirkot | 5
7705 | Gorkha | Muchhok | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Dharapani CBRC | Ajirkot | 5
7706 | Gorkha | Muchhok | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 151 | 151 |  |  |  | Ajirkot | 5
7707 | Gorkha | Muchhok | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-01 | 2016-07-21 |  | Ajirkot | 5
7708 | Gorkha | Muchhok | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Ajirkot | 5
7709 | Gorkha | Muchhok | All | CARE-N | UNIFICATION-N |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Ajirkot | 5
7710 | Gorkha | Muchhok | All | JICA |  |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 983 | 661 | 2017-05-03 |  |  | Ajirkot | 5
7711 | Gorkha | Muchhok | All | GON - PAF | LDF | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 20 | 0 |  |  |  | Ajirkot | 5
7712 | Gorkha | Muchhok |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Completed | 1 | 1 |  |  | Flagged as 1 to show the area has plans | Ajirkot | 5
7713 | Gorkha | Muchhok |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 78 |  |  |  | Ajirkot | 5
7714 | Gorkha | Muchhok |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 31 |  |  |  | Ajirkot | 5
7715 | Gorkha | Kerauja | 9 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 65 | 65 |  |  |  | Dharche | 1
7716 | Gorkha | Namjung | 1 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 5 | 2016-09-27 | 2016-10-04 |  | Sahid Lakhan | 9
7717 | Gorkha | Namjung | 1 | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 75 | 72 | 2016-09-23 | 2016-09-29 |  | Sahid Lakhan | 9
7718 | Gorkha | Namjung | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 73 | 2016-08-27 | 2016-08-27 |  | Sahid Lakhan | 9
7719 | Gorkha | Namjung | 1 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-27 | 2016-10-04 |  | Sahid Lakhan | 9
7720 | Gorkha | Namjung | 2 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 9 | 2016-09-27 | 2016-10-04 |  | Sahid Lakhan | 9
7721 | Gorkha | Namjung | 2 | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 75 | 72 | 2016-09-23 | 2016-09-29 |  | Sahid Lakhan | 9
7722 | Gorkha | Namjung | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 100 | 2016-08-23 | 2016-08-23 |  | Sahid Lakhan | 9
7723 | Gorkha | Namjung | 2 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-09-27 | 2016-10-04 |  | Sahid Lakhan | 9
7724 | Gorkha | Namjung | 3 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 6 | 2016-09-27 | 2016-10-04 |  | Sahid Lakhan | 9
7725 | Gorkha | Namjung | 3 | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 75 | 72 | 2016-09-23 | 2016-09-29 |  | Sahid Lakhan | 9
7726 | Gorkha | Namjung | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 65 | 2016-08-24 | 2016-08-24 |  | Sahid Lakhan | 9
7727 | Gorkha | Namjung | 3 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-09-27 | 2016-10-04 |  | Sahid Lakhan | 9
7728 | Gorkha | Namjung | 4 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 5 | 2016-09-27 | 2016-10-04 |  | Sahid Lakhan | 9
7729 | Gorkha | Namjung | 4 | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 75 | 72 | 2016-09-23 | 2016-09-29 |  | Sahid Lakhan | 9
7730 | Gorkha | Namjung | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 37 | 2016-08-10 | 2016-08-10 |  | Sahid Lakhan | 9
7731 | Gorkha | Namjung | 4 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-27 | 2016-10-04 |  | Sahid Lakhan | 9
7732 | Gorkha | Namjung | 5 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 10 | 2016-09-27 | 2016-10-04 |  | Sahid Lakhan | 9
7733 | Gorkha | Namjung | 5 | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 75 | 74 | 2016-09-23 | 2016-09-29 |  | Sahid Lakhan | 9
7734 | Gorkha | Namjung | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 150 | 116 | 2016-08-11 | 2016-08-13 |  | Sahid Lakhan | 9
7735 | Gorkha | Namjung | 5 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-09-27 | 2016-10-04 |  | Sahid Lakhan | 9
7736 | Gorkha | Namjung | 6 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 9 | 2016-09-27 | 2016-10-04 |  | Sahid Lakhan | 9
7737 | Gorkha | Namjung | 6 | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 75 | 72 | 2016-09-23 | 2016-09-29 |  | Sahid Lakhan | 9
7738 | Gorkha | Namjung | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 66 | 2016-08-14 | 2016-08-14 |  | Sahid Lakhan | 9
7739 | Gorkha | Namjung | 6 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-09-27 | 2016-10-04 |  | Sahid Lakhan | 9
7740 | Gorkha | Namjung | 7 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04 |  | Sahid Lakhan | 9
7741 | Gorkha | Namjung | 7 | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 75 | 72 | 2016-09-23 | 2016-09-29 |  | Sahid Lakhan | 9
7742 | Gorkha | Namjung | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 48 | 2016-08-25 | 2016-08-25 |  | Sahid Lakhan | 9
7743 | Gorkha | Namjung | 7 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-09-27 | 2016-10-04 |  | Sahid Lakhan | 9
7744 | Gorkha | Namjung | 8 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 8 | 2016-09-27 | 2016-10-04 |  | Sahid Lakhan | 9
7745 | Gorkha | Namjung | 8 | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 75 | 72 | 2016-09-23 | 2016-09-29 |  | Sahid Lakhan | 9
7746 | Gorkha | Namjung | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 86 | 2016-08-26 | 2016-08-26 |  | Sahid Lakhan | 9
7747 | Gorkha | Namjung | 8 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-09-27 | 2016-10-04 |  | Sahid Lakhan | 9
7748 | Gorkha | Namjung | 9 | CA | GORETO GORKHA | CA | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 10 | 7 | 2016-09-27 | 2016-10-04 |  | Sahid Lakhan | 9
7749 | Gorkha | Namjung | 9 | CA | GORETO GORKHA | CA | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 75 | 72 | 2016-09-23 | 2016-09-29 |  | Sahid Lakhan | 9
7750 | Gorkha | Namjung | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 50 | 2016-08-13 | 2016-08-13 |  | Sahid Lakhan | 9
7751 | Gorkha | Namjung | 9 | CA | GORETO GORKHA | CA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-09-27 | 2016-10-04 |  | Sahid Lakhan | 9
7752 | Gorkha | Namjung |  | CA | GORETO GORKHA | CA | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Completed | 2 | 2 |  |  |  | Sahid Lakhan | 9
7753 | Gorkha | Namjung |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 340 |  |  |  | Sahid Lakhan | 9
7754 | Gorkha | Palumtar N.P. | 7 | INF-N | INF- B | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 2 | 2 |  |  |  | Palungtar | 3
7755 | Gorkha | Palumtar N.P. | 7 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Planned | 2 | 0 |  |  |  | Palungtar | 3
7756 | Gorkha | Palumtar N.P. | 7 | INF-N | PDF | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 2 | 0 |  |  |  | Palungtar | 3
7757 | Gorkha | Palumtar N.P. | 7 | INF-N | PDF | INF International | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Planned | 2 | 0 |  |  |  | Palungtar | 3
7758 | Gorkha | Palumtar N.P. | 9 | INF-N | INF- B | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 1 | 1 |  |  |  | Palungtar | 4
7759 | Gorkha | Palumtar N.P. | 9 | INF-N | INF- B | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Planned | 1 | 0 |  |  |  | Palungtar | 4
7760 | Gorkha | Palumtar N.P. | 9 | INF-N | INF- B | INF International | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 1 | 0 |  |  |  | Palungtar | 4
7761 | Gorkha | Palumtar N.P. | 9 | INF-N | INF- B | INF International | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Planned | 1 | 0 |  |  |  | Palungtar | 4
7762 | Gorkha | Palumtar N.P. | 1,2,3 | ACN | ACN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 55 | 55 | 2017-07-01 |  |  | Palungtar | 7
7763 | Gorkha | Palumtar N.P. | 11,12,13 | ACN | ACN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 30 | 2017-07-19 |  |  | Palungtar | 2
7764 | Gorkha | Palumtar N.P. | 11,12,13 | ACN | ACN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 |  |  |  | Palungtar | 2
7765 | Gorkha | Palumtar N.P. | 2,3 | GON - PAF | LLCSC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 50 | 0 |  |  |  | Palungtar | 7
7766 | Gorkha | Palumtar N.P. | 4,5,6 | ACN | ACN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-07-01 |  |  | Palungtar | 6
7767 | Gorkha | Palumtar N.P. | 7,8,9,10 | ACN | ACN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 24 | 2017-07-01 |  |  | Palungtar | 4
7768 | Gorkha | Palumtar N.P. |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 552 |  |  |  | Palungtar | 7
7769 | Gorkha | Panchkhuwadeurali | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-04 | Simalkheti Purna Nirman Samudaik Samiti | Sulikot | 7
7770 | Gorkha | Panchkhuwadeurali | 1 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-04-17 | 2016-04-23 |  | Sulikot | 7
7771 | Gorkha | Panchkhuwadeurali | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-05 | Mandali Chautara Purna Nirman Samudaik Samiti | Sulikot | 7
7772 | Gorkha | Panchkhuwadeurali | 2 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-07-28 | 2016-05-02 |  | Sulikot | 7
7773 | Gorkha | Panchkhuwadeurali | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-06 | Bhawani Purna Nirman Samudaik Samiti | Sulikot | 7
7774 | Gorkha | Panchkhuwadeurali | 3 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-04-17 | 2016-04-23 |  | Sulikot | 7
7775 | Gorkha | Panchkhuwadeurali | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-09 | Dharapani Purna Nirman Samudaik Samiti | Sulikot | 7
7776 | Gorkha | Panchkhuwadeurali | 4 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-07-28 | 2016-05-02 |  | Sulikot | 7
7777 | Gorkha | Panchkhuwadeurali | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-07 | Lakuridhara Purna Nirman Samudaik Samiti | Sulikot | 7
7778 | Gorkha | Panchkhuwadeurali | 5 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-04-17 | 2016-04-23 |  | Sulikot | 7
7779 | Gorkha | Panchkhuwadeurali | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-08 | Aamle Purna Nirman Samudaik Samiti | Sulikot | 7
7780 | Gorkha | Panchkhuwadeurali | 6 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-07-28 | 2016-05-02 |  | Sulikot | 7
7781 | Gorkha | Panchkhuwadeurali | 7 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-07-26 | 2016-05-02 |  | Sulikot | 7
7782 | Gorkha | Panchkhuwadeurali | 8 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 |  |  |  | Sulikot | 7
7783 | Gorkha | Panchkhuwadeurali | 9 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 |  |  |  | Sulikot | 7
7784 | Gorkha | Panchkhuwadeurali | All | JICA |  |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 547 | 730 | 2017-05-03 |  |  | Sulikot | 7
7785 | Gorkha | Panchkhuwadeurali | All | HELVETAS | PANCHA KANYA | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-06-02 | 2016-08-06 |  | Sulikot | 7
7786 | Gorkha | Panchkhuwadeurali | All | HELVETAS | PANCHA KANYA | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 130 | 130 | 2016-06-02 | 2016-10-01 |  | Sulikot | 7
7787 | Gorkha | Panchkhuwadeurali |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 |  |  |  | Sulikot | 7
7788 | Gorkha | Panchkhuwadeurali |  | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 60 | 0 |  |  |  | Sulikot | 7
7789 | Gorkha | Pandrung | 1 | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 100000 is provided as third tranche | # of households | Yes | Completed | 42 | 42 |  |  |  | Sulikot | 8
7790 | Gorkha | Pandrung | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Gau Sudhar Purna Nirman Samudaik Samiti | Sulikot | 8
7791 | Gorkha | Pandrung | 1 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-08 | 2016-02-22 |  | Sulikot | 8
7792 | Gorkha | Pandrung | 1 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-04-17 | 2016-04-23 |  | Sulikot | 8
7793 | Gorkha | Pandrung | 2 | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 100000 is provided as third tranche | # of households | Yes | Completed | 24 | 24 |  |  |  | Sulikot | 8
7794 | Gorkha | Pandrung | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Bramha Charini Purna Nirman Samudaik Samiti | Sulikot | 8
7795 | Gorkha | Pandrung | 2 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-08 | 2016-02-22 |  | Sulikot | 8
7796 | Gorkha | Pandrung | 2 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-17 | 2016-04-23 |  | Sulikot | 8
7797 | Gorkha | Pandrung | 3 | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 100000 is provided as third tranche | # of households | Yes | Completed | 38 | 38 |  |  |  | Sulikot | 8
7798 | Gorkha | Pandrung | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Bhawani Purna Nirman Samudaik Samiti | Sulikot | 8
7799 | Gorkha | Pandrung | 3 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-08 | 2016-02-22 |  | Sulikot | 8
7800 | Gorkha | Pandrung | 3 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-04-17 | 2016-04-23 |  | Sulikot | 8
7801 | Gorkha | Pandrung | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Thulo Pandrung Purna Nirman Samudaik Samiti | Sulikot | 8
7802 | Gorkha | Pandrung | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Sulikot | 8
7803 | Gorkha | Pandrung | 4 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-08 | 2016-02-22 |  | Sulikot | 8
7804 | Gorkha | Pandrung | 4 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-04-17 | 2016-04-23 |  | Sulikot | 8
7805 | Gorkha | Pandrung | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Thali Bari Purna Nirman Samudaik Samiti | Sulikot | 8
7806 | Gorkha | Pandrung | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 |  |  |  | Sulikot | 8
7807 | Gorkha | Pandrung | 5 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-08 | 2016-02-22 |  | Sulikot | 8
7808 | Gorkha | Pandrung | 5 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-04-17 | 2016-04-23 |  | Sulikot | 8
7809 | Gorkha | Pandrung | 6 | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 100000 is provided as third tranche | # of households | Yes | Completed | 33 | 33 |  |  |  | Sulikot | 8
7810 | Gorkha | Pandrung | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-28 | Lama Gau Purna Nirman Samudaik Samiti | Sulikot | 8
7811 | Gorkha | Pandrung | 6 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-08 | 2016-02-22 |  | Sulikot | 8
7812 | Gorkha | Pandrung | 6 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-04-26 | 2016-05-02 |  | Sulikot | 8
7813 | Gorkha | Pandrung | 7 | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 100000 is provided as third tranche | # of households | Yes | Completed | 46 | 46 |  |  |  | Sulikot | 8
7814 | Gorkha | Pandrung | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-28 | Mandali Purna Nirman Samudaik Samiti | Sulikot | 8
7815 | Gorkha | Pandrung | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Sulikot | 8
7816 | Gorkha | Pandrung | 7 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-08 | 2016-02-22 |  | Sulikot | 8
7817 | Gorkha | Pandrung | 7 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-04-26 | 2016-05-02 |  | Sulikot | 8
7818 | Gorkha | Pandrung | 8 | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Two Beneficiaries received Rs 75000 and other Eight Beneficiaries received Rs.100000 provided as third tranche | # of households | Yes | Completed | 26 | 26 |  |  |  | Sulikot | 8
7819 | Gorkha | Pandrung | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | Jana Jagriti Purna Nirman Samudaik Samiti | Sulikot | 8
7820 | Gorkha | Pandrung | 8 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-08 | 2016-02-22 |  | Sulikot | 8
7821 | Gorkha | Pandrung | 8 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-04-26 | 2016-05-02 |  | Sulikot | 8
7822 | Gorkha | Pandrung | 9 | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 100000 is provided as third tranche | # of households | Yes | Completed | 41 | 41 |  |  |  | Sulikot | 8
7823 | Gorkha | Pandrung | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Kalika Purna Nirman Samudaik Samiti | Sulikot | 8
7824 | Gorkha | Pandrung | 9 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-08 | 2016-02-22 |  | Sulikot | 8
7825 | Gorkha | Pandrung | 9 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-04-26 | 2016-05-02 |  | Sulikot | 8
7826 | Gorkha | Pandrung | All | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 150000 is provided as second tranche | # of households | Yes | Completed | 195 | 241 |  |  |  | Sulikot | 8
7827 | Gorkha | Pandrung | All | SCI | SSICDC |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000 was provided as first tranche | # of households | Yes | Completed | 120 | 120 |  |  | Rs 50000 first tranche of Government subsidy was supported by Save | Sulikot | 8
7828 | Gorkha | Pandrung | All | JICA |  |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 632 | 548 | 2017-05-03 |  |  | Sulikot | 8
7829 | Gorkha | Pandrung | All | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 70 | 70 | 2016-12-01 | 2016-10-01 |  | Sulikot | 8
7830 | Gorkha | Pandrung | All | SCI | SSICDC | SCI | Training | Other trainings | Other trainings (specify in Activity Detail) | CSEB Training( Block Making Training) | # of trainees | Yes | Completed | 10 | 10 | 2017-03-01 | 2017-03-10 |  | Sulikot | 8
7831 | Gorkha | Pandrung | All | SCI | SSICDC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-02-18 | 2017-03-29 |  | Sulikot | 8
7832 | Gorkha | Pandrung |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 43 |  |  |  | Sulikot | 8
7833 | Gorkha | Pandrung |  | NYF | NYF |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-02-08 | 2016-02-22 |  | Sulikot | 8
7834 | Gorkha | Prok | 1 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Chum Nubri | 4
7835 | Gorkha | Prok | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 34 | 0 |  |  |  | Chum Nubri | 4
7836 | Gorkha | Prok | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 4
7837 | Gorkha | Prok | 1 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 34 | 0 |  |  |  | Chum Nubri | 4
7838 | Gorkha | Prok | 1 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 34 | 0 |  |  |  | Chum Nubri | 4
7839 | Gorkha | Prok | 1 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 | 2016-09-01 | 2017-03-31 |  | Chum Nubri | 4
7840 | Gorkha | Prok | 1 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 4
7841 | Gorkha | Prok | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 26 | 0 |  |  |  | Chum Nubri | 4
7842 | Gorkha | Prok | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 4
7843 | Gorkha | Prok | 2 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 26 | 0 |  |  |  | Chum Nubri | 4
7844 | Gorkha | Prok | 2 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 26 | 0 |  |  |  | Chum Nubri | 4
7845 | Gorkha | Prok | 2 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 18 | 18 | 2016-12-25 | 2016-12-31 |  | Chum Nubri | 4
7846 | Gorkha | Prok | 2 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 4
7847 | Gorkha | Prok | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 27 | 0 |  |  |  | Chum Nubri | 4
7848 | Gorkha | Prok | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 4
7849 | Gorkha | Prok | 3 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 27 | 0 |  |  |  | Chum Nubri | 4
7850 | Gorkha | Prok | 3 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 27 | 0 |  |  |  | Chum Nubri | 4
7851 | Gorkha | Prok | 3 | PIN | PIN |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-09-04 | 2016-01-01 |  | Chum Nubri | 4
7852 | Gorkha | Prok | 3 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 | 2016-09-01 | 2017-03-31 |  | Chum Nubri | 4
7853 | Gorkha | Prok | 3 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 4
7854 | Gorkha | Prok | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 23 | 0 |  |  |  | Chum Nubri | 4
7855 | Gorkha | Prok | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 4
7856 | Gorkha | Prok | 4 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 23 | 0 |  |  |  | Chum Nubri | 4
7857 | Gorkha | Prok | 4 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 23 | 0 |  |  |  | Chum Nubri | 4
7858 | Gorkha | Prok | 4 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-12-25 | 2016-12-31 |  | Chum Nubri | 4
7859 | Gorkha | Prok | 4 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 4
7860 | Gorkha | Prok | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 28 | 0 |  |  |  | Chum Nubri | 4
7861 | Gorkha | Prok | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 4
7862 | Gorkha | Prok | 5 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 28 | 0 |  |  |  | Chum Nubri | 4
7863 | Gorkha | Prok | 5 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 28 | 0 |  |  |  | Chum Nubri | 4
7864 | Gorkha | Prok | 5 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 | 2016-09-01 | 2017-03-31 |  | Chum Nubri | 4
7865 | Gorkha | Prok | 5 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 4
7866 | Gorkha | Prok | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 40 | 0 |  |  |  | Chum Nubri | 4
7867 | Gorkha | Prok | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 4
7868 | Gorkha | Prok | 6 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 40 | 0 |  |  |  | Chum Nubri | 4
7869 | Gorkha | Prok | 6 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 40 | 0 |  |  |  | Chum Nubri | 4
7870 | Gorkha | Prok | 6 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-12-25 | 2016-12-31 |  | Chum Nubri | 4
7871 | Gorkha | Prok | 6 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 4
7872 | Gorkha | Prok | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 25 | 0 |  |  |  | Chum Nubri | 4
7873 | Gorkha | Prok | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 4
7874 | Gorkha | Prok | 7 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 25 | 0 |  |  |  | Chum Nubri | 4
7875 | Gorkha | Prok | 7 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 25 | 0 |  |  |  | Chum Nubri | 4
7876 | Gorkha | Prok | 7 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 | 2016-09-01 | 2017-03-31 |  | Chum Nubri | 4
7877 | Gorkha | Prok | 7 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 4
7878 | Gorkha | Prok | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 19 | 0 |  |  |  | Chum Nubri | 4
7879 | Gorkha | Prok | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 4
7880 | Gorkha | Prok | 8 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 19 | 0 |  |  |  | Chum Nubri | 4
7881 | Gorkha | Prok | 8 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 19 | 0 |  |  |  | Chum Nubri | 4
7882 | Gorkha | Prok | 8 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 | 2016-09-01 | 2017-03-31 |  | Chum Nubri | 4
7883 | Gorkha | Prok | 8 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 4
7884 | Gorkha | Prok | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 4
7885 | Gorkha | Prok | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 4
7886 | Gorkha | Prok | 9 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 4
7887 | Gorkha | Prok | 9 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 4
7888 | Gorkha | Prok | 9 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 | 2016-09-01 | 2017-03-31 |  | Chum Nubri | 4
7889 | Gorkha | Prok | 9 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 4
7890 | Gorkha | Prok | 1,2,3 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-06-06 |  | Chum Nubri | 4
7891 | Gorkha | Prok | 4,5 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Chum Nubri | 4
7892 | Gorkha | Prok | 6,7 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-06-06 |  | Chum Nubri | 4
7893 | Gorkha | Prok | 8.,9 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-06-04 |  | Chum Nubri | 4
7894 | Gorkha | Samagaun | 1 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Chum Nubri | 1
7895 | Gorkha | Samagaun | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 28 | 0 |  |  |  | Chum Nubri | 1
7896 | Gorkha | Samagaun | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 1
7897 | Gorkha | Samagaun | 1 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 28 | 0 |  |  |  | Chum Nubri | 1
7898 | Gorkha | Samagaun | 1 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 28 | 0 |  |  |  | Chum Nubri | 1
7899 | Gorkha | Samagaun | 1 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-12-21 | 2016-12-28 |  | Chum Nubri | 1
7900 | Gorkha | Samagaun | 1 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 1
7901 | Gorkha | Samagaun | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 1
7902 | Gorkha | Samagaun | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 1
7903 | Gorkha | Samagaun | 2 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 1
7904 | Gorkha | Samagaun | 2 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 1
7905 | Gorkha | Samagaun | 2 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 | 2016-09-01 | 2017-03-31 |  | Chum Nubri | 1
7906 | Gorkha | Samagaun | 2 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 1
7907 | Gorkha | Samagaun | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 36 | 0 |  |  |  | Chum Nubri | 1
7908 | Gorkha | Samagaun | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 1
7909 | Gorkha | Samagaun | 3 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 36 | 0 |  |  |  | Chum Nubri | 1
7910 | Gorkha | Samagaun | 3 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 36 | 0 |  |  |  | Chum Nubri | 1
7911 | Gorkha | Samagaun | 3 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-12-21 | 2016-12-28 |  | Chum Nubri | 1
7912 | Gorkha | Samagaun | 3 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 1
7913 | Gorkha | Samagaun | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 30 | 0 |  |  |  | Chum Nubri | 1
7914 | Gorkha | Samagaun | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 1
7915 | Gorkha | Samagaun | 4 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 30 | 0 |  |  |  | Chum Nubri | 1
7916 | Gorkha | Samagaun | 4 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 30 | 0 |  |  |  | Chum Nubri | 1
7917 | Gorkha | Samagaun | 4 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-12-21 | 2016-12-28 |  | Chum Nubri | 1
7918 | Gorkha | Samagaun | 4 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 1
7919 | Gorkha | Samagaun | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 26 | 0 |  |  |  | Chum Nubri | 1
7920 | Gorkha | Samagaun | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 1
7921 | Gorkha | Samagaun | 5 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 26 | 0 |  |  |  | Chum Nubri | 1
7922 | Gorkha | Samagaun | 5 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 26 | 0 |  |  |  | Chum Nubri | 1
7923 | Gorkha | Samagaun | 5 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-12-21 | 2016-12-28 |  | Chum Nubri | 1
7924 | Gorkha | Samagaun | 5 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 1
7925 | Gorkha | Samagaun | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 40 | 0 |  |  |  | Chum Nubri | 1
7926 | Gorkha | Samagaun | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 1
7927 | Gorkha | Samagaun | 6 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 40 | 0 |  |  |  | Chum Nubri | 1
7928 | Gorkha | Samagaun | 6 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 40 | 0 |  |  |  | Chum Nubri | 1
7929 | Gorkha | Samagaun | 6 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 | 2016-09-01 | 2017-03-31 |  | Chum Nubri | 1
7930 | Gorkha | Samagaun | 6 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 1
7931 | Gorkha | Samagaun | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 12 | 0 |  |  |  | Chum Nubri | 1
7932 | Gorkha | Samagaun | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 1
7933 | Gorkha | Samagaun | 7 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 12 | 0 |  |  |  | Chum Nubri | 1
7934 | Gorkha | Samagaun | 7 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 12 | 0 |  |  |  | Chum Nubri | 1
7935 | Gorkha | Samagaun | 7 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-12-21 | 2016-12-28 |  | Chum Nubri | 1
7936 | Gorkha | Samagaun | 7 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 1
7937 | Gorkha | Samagaun | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 17 | 0 |  |  |  | Chum Nubri | 1
7938 | Gorkha | Samagaun | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 1
7939 | Gorkha | Samagaun | 8 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 17 | 0 |  |  |  | Chum Nubri | 1
7940 | Gorkha | Samagaun | 8 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 17 | 0 |  |  |  | Chum Nubri | 1
7941 | Gorkha | Samagaun | 8 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-12-21 | 2016-12-28 |  | Chum Nubri | 1
7942 | Gorkha | Samagaun | 8 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 1
7943 | Gorkha | Samagaun | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Planned | 11 | 0 |  |  |  | Chum Nubri | 1
7944 | Gorkha | Samagaun | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Planned | 20 | 0 |  |  |  | Chum Nubri | 1
7945 | Gorkha | Samagaun | 9 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 11 | 0 |  |  |  | Chum Nubri | 1
7946 | Gorkha | Samagaun | 9 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 11 | 0 |  |  |  | Chum Nubri | 1
7947 | Gorkha | Samagaun | 9 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-12-21 | 2016-12-28 |  | Chum Nubri | 1
7948 | Gorkha | Samagaun | 9 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Chum Nubri | 1
7949 | Gorkha | Samagaun | 1,2,3 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-06-06 | Samagoun CBRC | Chum Nubri | 1
7950 | Gorkha | Samagaun | 4,5 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-07-05 | Manasalu CBRC | Chum Nubri | 1
7951 | Gorkha | Samagaun | 7,8,9 | CRS | SDSC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-26 | Samdo Border CBRC | Chum Nubri | 1
7952 | Gorkha | Samagaun |  | CA | CA | IOM | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Completed | 220 | 220 | 2015-12-24 | 2015-12-28 |  | Chum Nubri | 1
7953 | Gorkha | Saurpani | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Bhuwanighunchok CBRC | Sulikot | 4
7954 | Gorkha | Kerauja | All | OXFAM-GB | GORETO GORKHA |  | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 465 | 465 | 2015-12-25 | 2016-01-15 | CGI (2B PHH) | Dharche | 2
7955 | Gorkha | Kerauja | All | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 844 | 844 |  |  |  | Dharche | 2
7956 | Gorkha | Saurpani | 1 | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01 |  | Sulikot | 4
7957 | Gorkha | Saurpani | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Sulikot | 4
7958 | Gorkha | Saurpani | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Manakamana CBRC | Sulikot | 4
7959 | Gorkha | Saurpani | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-23 | Thani CBRC | Sulikot | 4
7960 | Gorkha | Saurpani | 1 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sulikot | 4
7961 | Gorkha | Saurpani | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Sulikot | 4
7962 | Gorkha | Saurpani | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Devithan CBRC | Sulikot | 4
7963 | Gorkha | Saurpani | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Devithan CBRC | Sulikot | 4
7964 | Gorkha | Saurpani | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Bhagbhairab CBRC | Sulikot | 4
7965 | Gorkha | Saurpani | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Gyaji CBRC | Sulikot | 4
7966 | Gorkha | Saurpani | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Pokhari CBRC | Sulikot | 4
7967 | Gorkha | Saurpani | 1 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Sulikot | 4
7968 | Gorkha | Saurpani | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Thanthani CBRC | Sulikot | 4
7969 | Gorkha | Saurpani | 2 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sulikot | 4
7970 | Gorkha | Saurpani | 3 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sulikot | 4
7971 | Gorkha | Saurpani | 4 | HELVETAS | Janahit | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees |  | Completed | 10 | 10 |  |  |  | Sulikot | 4
7972 | Gorkha | Saurpani | 4 | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 | 2015-12-01 | 2016-01-30 |  | Sulikot | 4
7973 | Gorkha | Saurpani | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Sulikot | 4
7974 | Gorkha | Saurpani | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Chunedada CBRC | Sulikot | 4
7975 | Gorkha | Saurpani | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Srijana CBRC | Sulikot | 4
7976 | Gorkha | Saurpani | 4 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sulikot | 4
7977 | Gorkha | Saurpani | 4 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Sulikot | 4
7978 | Gorkha | Saurpani | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Sulikot | 4
7979 | Gorkha | Saurpani | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Rakshakdevi CBRC | Sulikot | 4
7980 | Gorkha | Saurpani | 5 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sulikot | 4
7981 | Gorkha | Saurpani | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 |  |  |  | Sulikot | 4
7982 | Gorkha | Saurpani | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Tukrang CBRC | Sulikot | 4
7983 | Gorkha | Saurpani | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Kewara CBRC | Sulikot | 4
7984 | Gorkha | Saurpani | 5 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Sulikot | 4
7985 | Gorkha | Saurpani | 6 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sulikot | 4
7986 | Gorkha | Saurpani | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Sulikot | 4
7987 | Gorkha | Saurpani | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Bhukampa Pratirodhi CBRC | Sulikot | 4
7988 | Gorkha | Saurpani | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Nawa Jagrit CBRC | Sulikot | 4
7989 | Gorkha | Saurpani | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Gurung Samaj CBRC | Sulikot | 4
7990 | Gorkha | Saurpani | 7 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 247 | 247 |  |  |  | Sulikot | 4
7991 | Gorkha | Saurpani | 7 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Sulikot | 4
7992 | Gorkha | Saurpani | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 |  |  |  | Sulikot | 4
7993 | Gorkha | Saurpani | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Tamu Samaj CBRC | Sulikot | 4
7994 | Gorkha | Saurpani | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Simbu Samaj CBRC | Sulikot | 4
7995 | Gorkha | Saurpani | 8 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sulikot | 4
7996 | Gorkha | Saurpani | 8 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Sulikot | 4
7997 | Gorkha | Saurpani | All | JICA |  |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 1556 | 387 | 2017-05-03 |  |  | Sulikot | 4
7998 | Gorkha | Saurpani | 9 | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 353 | 353 |  |  |  | Sulikot | 4
7999 | Gorkha | Saurpani | All | GON - PAF | UNIFICATION-N | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0 |  |  |  | Sulikot | 4
8000 | Gorkha | Saurpani | All | HELVETAS | Janahit | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-06-12 | 2016-08-17 |  | Sulikot | 4
8001 | Gorkha | Saurpani | All | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-12-01 | 2016-10-01 |  | Sulikot | 4
8002 | Gorkha | Saurpani | All | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 80 | 80 | 2016-06-12 | 2016-08-17 |  | Sulikot | 4
8003 | Gorkha | Saurpani | All | OXFAM-GB | GORETO GORKHA |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 1535 | 1535 |  |  |  | Sulikot | 4
8004 | Gorkha | Saurpani |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 65 |  |  |  | Sulikot | 4
8005 | Gorkha | Saurpani | All | OXFAM-GB | GORETO GORKHA |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 60 | 59 |  |  |  | Sulikot | 4
8006 | Gorkha | Saurpani | 1 | OXFAM-GB | GORETO GORKHA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 6 |  |  |  | Sulikot | 4
8007 | Gorkha | Saurpani | 2 | OXFAM-GB | GORETO GORKHA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 8 |  |  |  | Sulikot | 4
8008 | Gorkha | Saurpani | 3 | OXFAM-GB | GORETO GORKHA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 8 |  |  |  | Sulikot | 4
8009 | Gorkha | Saurpani | 4 | OXFAM-GB | GORETO GORKHA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 6 |  |  |  | Sulikot | 4
8010 | Gorkha | Saurpani | 5 | OXFAM-GB | GORETO GORKHA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 6 |  |  |  | Sulikot | 4
8011 | Gorkha | Saurpani | 6 | OXFAM-GB | GORETO GORKHA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 6 |  |  |  | Sulikot | 4
8012 | Gorkha | Saurpani | 7 | OXFAM-GB | GORETO GORKHA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 3 |  |  |  | Sulikot | 4
8013 | Gorkha | Saurpani | 8 | OXFAM-GB | GORETO GORKHA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 9 |  |  |  | Sulikot | 4
8014 | Gorkha | Shreenathkot | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Sankamai CBRC | Siranchok | 7
8015 | Gorkha | Shreenathkot | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Siranchok | 7
8016 | Gorkha | Shreenathkot | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Srijanshil CBRC | Siranchok | 7
8017 | Gorkha | Shreenathkot | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Laganshil CBRC | Siranchok | 7
8018 | Gorkha | Shreenathkot | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Siranchok | 7
8019 | Gorkha | Shreenathkot | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Ghatmai CBRC | Siranchok | 7
8020 | Gorkha | Shreenathkot | 3 | ACN | ACN | INFUK-GZB-Others | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-08-15 | 2016-08-22 | We are planning to give this training for skill manpower | Siranchok | 7
8021 | Gorkha | Shreenathkot | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 |  |  |  | Siranchok | 7
8022 | Gorkha | Shreenathkot | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Gurung Samaj CBRC | Siranchok | 7
8023 | Gorkha | Shreenathkot | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Dhakalsamaj CBRC | Siranchok | 7
8024 | Gorkha | Shreenathkot | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Siranchok | 7
8025 | Gorkha | Shreenathkot | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Pipal Chautara CBRC | Siranchok | 7
8026 | Gorkha | Shreenathkot | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Siranchok | 7
8027 | Gorkha | Shreenathkot | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Shreenath Mandali CBRC | Siranchok | 7
8028 | Gorkha | Shreenathkot | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Siranchok | 7
8029 | Gorkha | Shreenathkot | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Banmala CBRC | Siranchok | 7
8030 | Gorkha | Shreenathkot | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Laliguras CBRC | Siranchok | 7
8031 | Gorkha | Shreenathkot | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Siranchok | 7
8032 | Gorkha | Shreenathkot | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Birele jhayl CBRC | Siranchok | 7
8033 | Gorkha | Shreenathkot | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Siamley Devisthan CBRC | Siranchok | 7
8034 | Gorkha | Shreenathkot | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Siranchok | 7
8035 | Gorkha | Shreenathkot | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Thanimandali CBRC | Siranchok | 7
8036 | Gorkha | Shreenathkot | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Janagaran CBRC | Siranchok | 7
8037 | Gorkha | Shreenathkot | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | Dharmawati CBRC | Siranchok | 7
8038 | Gorkha | Shreenathkot | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Siranchok | 7
8039 | Gorkha | Shreenathkot | All | JICA |  |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 714 | 840 | 2017-05-03 |  |  | Siranchok | 7
8040 | Gorkha | Shreenathkot |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 67 |  |  |  | Siranchok | 7
8041 | Gorkha | Simjung | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Tamuthum CBRC | Ajirkot | 4
8042 | Gorkha | Saurpani | 9 | OXFAM-GB | GORETO GORKHA |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 8 |  |  |  | Sulikot | 4
8043 | Gorkha | Simjung | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Ajirkot | 4
8044 | Gorkha | Simjung | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Kalika CBRC | Ajirkot | 4
8045 | Gorkha | Simjung | 1 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Ajirkot | 4
8046 | Gorkha | Simjung | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | Annapurna CBRC | Ajirkot | 4
8047 | Gorkha | Simjung | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | Devithan CBRC | Ajirkot | 4
8048 | Gorkha | Simjung | 2 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Ajirkot | 4
8049 | Gorkha | Simjung | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Ajirkot | 4
8050 | Gorkha | Simjung | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Inarpani CBRC | Ajirkot | 4
8051 | Gorkha | Simjung | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Sivalaya CBRC | Ajirkot | 4
8052 | Gorkha | Simjung | 3 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Ajirkot | 4
8053 | Gorkha | Simjung | 4 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 218 | 218 |  |  |  | Ajirkot | 4
8054 | Gorkha | Simjung | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Ajirkot | 4
8055 | Gorkha | Simjung | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Dadagaun CBRC | Ajirkot | 4
8056 | Gorkha | Simjung | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Newar tole CBRC | Ajirkot | 4
8057 | Gorkha | simjung | 4 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Ajirkot | 4
8058 | Gorkha | Simjung | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 |  |  |  | Ajirkot | 4
8059 | Gorkha | Simjung | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Bharke CBRC | Ajirkot | 4
8060 | Gorkha | Simjung | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Taguse CBRC | Ajirkot | 4
8061 | Gorkha | Simjung | 5 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Ajirkot | 4
8062 | Gorkha | Simjung | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Goganpani CBRC | Ajirkot | 4
8063 | Gorkha | Simjung | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Taple CBRC | Ajirkot | 4
8064 | Gorkha | Simjung | 6 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Ajirkot | 4
8065 | Gorkha | Simjung | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Dhodeni CBRC | Ajirkot | 4
8066 | Gorkha | Simjung | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Pokhardada CBRC | Ajirkot | 4
8067 | Gorkha | Simjung | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Pokharatar CBRC | Ajirkot | 4
8068 | Gorkha | Simjung | 7 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Ajirkot | 4
8069 | Gorkha | Simjung | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Ajirkot | 4
8070 | Gorkha | Simjung | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Baluwa CBRC | Ajirkot | 4
8071 | Gorkha | Simjung | 8 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Ajirkot | 4
8072 | Gorkha | Simjung | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Ajirkot | 4
8073 | Gorkha | Simjung | All | JICA |  |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 897 | 838 | 2017-05-03 |  |  | Ajirkot | 4
8074 | Gorkha | Simjung | 9 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Ajirkot | 4
8075 | Gorkha | Simjung | All | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 915 | 915 |  |  | Information Center | Ajirkot | 4
8076 | Gorkha | Simjung |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 68 |  |  |  | Ajirkot | 4
8077 | Gorkha | Simjung | All | OXFAM-GB | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 29 |  |  |  | Ajirkot | 4
8078 | Gorkha | simjung | 1 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 6 |  |  |  | Ajirkot | 4
8079 | Gorkha | simjung | 2 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 5 |  |  |  | Ajirkot | 4
8080 | Gorkha | simjung | 3 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 3 |  |  |  | Ajirkot | 4
8081 | Gorkha | simjung | 7 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 1 |  |  |  | Ajirkot | 4
8082 | Gorkha | simjung | 8 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 13 | 13 |  |  |  | Ajirkot | 4
8083 | Gorkha | simjung | 9 | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 1 |  |  |  | Ajirkot | 4
8084 | Gorkha | Sirdibas | All | SP | UVN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2016-08-29 | 2016-09-04 |  | Chum Nubri | 3
8085 | Gorkha | Sirdibas | All | SP | UVN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2016-09-18 | 2016-09-24 |  | Chum Nubri | 3
8086 | Gorkha | Sirdibas | ALL | SP | UVN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 22 | 22 | 2016-11-20 | 2016-11-26 |  | Chum Nubri | 3
8087 | Gorkha | Sirdibas | All | SP | UVN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 21 | 21 | 2016-12-01 | 2016-12-07 |  | Chum Nubri | 3
8088 | Gorkha | Sirdibas | All | SP | UVN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 38 | 38 | 2017-01-22 | 2017-01-28 |  | Chum Nubri | 3
8089 | Gorkha | Sirdibas | All | SP | UVN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 23 | 23 | 2017-02-23 | 2017-03-01 |  | Chum Nubri | 3
8090 | Gorkha | Sirdibas |  | SP | UVN |  | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households |  | Ongoing | 50 | 10 |  |  |  | Chum Nubri | 3
8091 | Gorkha | Sirdibas |  | SP | UVN |  | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Model House Construction | # of households |  | Completed | 1 | 3 |  | 2017-03-01 |  | Chum Nubri | 3
8092 | Gorkha | Swara | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Rupa kot Swara Purna Nirman Samudaik Samiti | Sulikot | 3
8093 | Gorkha | Swara | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Sulikot | 3
8094 | Gorkha | Swara | 1 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-05-12 | 2016-05-18 |  | Sulikot | 3
8095 | Gorkha | Swara | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Sita Gufa Bagdul Purna Nirman Samudaik Samiti | Sulikot | 3
8096 | Gorkha | Swara | 2 | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01 |  | Sulikot | 3
8097 | Gorkha | Swara | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Sulikot | 3
8098 | Gorkha | Swara | 2 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 |  |  |  | Sulikot | 3
8099 | Gorkha | Swara | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Sulikot Rato Matey Purna Nirman Samudaik Samiti | Sulikot | 3
8100 | Gorkha | Swara | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Sulikot | 3
8101 | Gorkha | Swara | 3 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-19 | 2016-05-25 |  | Sulikot | 3
8102 | Gorkha | Swara | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Bageshwori Purna Nirman Samudaik Samiti | Sulikot | 3
8103 | Gorkha | Swara | 4 | HELVETAS | Janahit | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01 |  | Sulikot | 3
8104 | Gorkha | Swara | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Sulikot | 3
8105 | Gorkha | Swara | 4 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-05-12 | 2016-05-18 |  | Sulikot | 3
8106 | Gorkha | Swara | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-15 | Shimvu Purna Nirman Samudaik Samiti | Sulikot | 3
8107 | Gorkha | Swara | 5 | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01 |  | Sulikot | 3
8108 | Gorkha | Swara | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Sulikot | 3
8109 | Gorkha | Swara | 5 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-05-19 | 2016-05-25 |  | Sulikot | 3
8110 | Gorkha | Swara | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-08 | Majh Gau Chitrey Purna Nirman Samudaik Samiti | Sulikot | 3
8111 | Gorkha | Swara | 6 | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Sulikot | 3
8112 | Gorkha | Swara | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Sulikot | 3
8113 | Gorkha | Swara | 6 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-05-19 | 2016-05-25 |  | Sulikot | 3
8114 | Gorkha | Swara | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Himali Samajh Purna Nirman Samudaik Samiti | Sulikot | 3
8115 | Gorkha | Swara | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Sulikot | 3
8116 | Gorkha | Swara | 7 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-12 | 2016-05-18 |  | Sulikot | 3
8117 | Gorkha | Swara | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-04 | Manakamana Purna Nirman Samudaik Samiti | Sulikot | 3
8118 | Gorkha | Swara | 8 | HELVETAS | Janahit | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01 |  | Sulikot | 3
8119 | Gorkha | Swara | 8 | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 40 | 40 | 2016-12-01 | 2016-10-01 |  | Sulikot | 3
8120 | Gorkha | Swara | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Sulikot | 3
8121 | Gorkha | Swara | 8 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-05-12 | 2016-05-18 |  | Sulikot | 3
8122 | Gorkha | Swara | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-04 | Saat Kanya Devi Purna Nirman Samudaik Samiti | Sulikot | 3
8123 | Gorkha | Swara | 9 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-12 | 2016-05-18 |  | Sulikot | 3
8124 | Gorkha | Swara | All | JICA |  |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 908 | 606 | 2017-05-03 |  |  | Sulikot | 3
8125 | Gorkha | Swara | All | GON - PAF | UNIFICATION-N | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0 |  |  |  | Sulikot | 3
8126 | Gorkha | Swara | All | HELVETAS | Janahit | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-06-06 | 2016-08-04 |  | Sulikot | 3
8127 | Gorkha | Swara | All | HELVETAS | Janahit | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 10 | 2016-06-06 | 2016-08-04 |  | Sulikot | 3
8128 | Gorkha | Swara |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 80 |  |  |  | Sulikot | 3
8129 | Gorkha | Sirdibas | All | OXFAM-GB |  |  | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 625 | 625 |  |  |  | Chum Nubri | 3
8130 | Gorkha | Taklung | 1 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 90 | 2016-08-17 | 2016-08-18 |  | Sahid Lakhan | 4
8131 | Gorkha | Taklung | 1 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sahid Lakhan | 4
8132 | Gorkha | Taklung | 2 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 63 | 2016-08-04 | 2016-08-05 |  | Sahid Lakhan | 4
8133 | Gorkha | Taklung | 2 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sahid Lakhan | 4
8134 | Gorkha | Taklung | 2 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Sahid Lakhan | 4
8135 | Gorkha | Taklung | 3 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 300 | 293 | 2016-08-17 | 2016-08-23 |  | Sahid Lakhan | 4
8136 | Gorkha | Taklung | 3 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 205 | 205 |  |  |  | Sahid Lakhan | 4
8137 | Gorkha | Taklung | 3 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Sahid Lakhan | 4
8138 | Gorkha | Taklung | 4 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 67 | 2016-08-10 | 2016-08-10 |  | Sahid Lakhan | 4
8139 | Gorkha | Taklung | 4 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sahid Lakhan | 4
8140 | Gorkha | Taklung | 5 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 150 | 122 | 2016-08-11 | 2016-08-12 |  | Sahid Lakhan | 5
8141 | Gorkha | Taklung | 5 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 245 | 245 |  |  |  | Sahid Lakhan | 5
8142 | Gorkha | Taklung | 6 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 150 | 115 | 2016-08-16 | 2016-08-17 |  | Sahid Lakhan | 5
8143 | Gorkha | Taklung | 6 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sahid Lakhan | 5
8144 | Gorkha | Taklung | 7 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 50 | 61 | 2016-08-26 | 2016-08-26 |  | Sahid Lakhan | 5
8145 | Gorkha | Taklung | 7 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sahid Lakhan | 5
8146 | Gorkha | Taklung | 7 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Sahid Lakhan | 5
8147 | Gorkha | Taklung | 8 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 100 | 77 | 2016-08-25 | 2016-08-25 |  | Sahid Lakhan | 5
8148 | Gorkha | Taklung | 8 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 200 | 200 |  |  |  | Sahid Lakhan | 5
8149 | Gorkha | Taklung | 8 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Sahid Lakhan | 5
8150 | Gorkha | Taklung | 9 | IOM | IOM | ECHO-JAP-NOR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 150 | 150 | 2016-08-31 | 2016-09-01 |  | Sahid Lakhan | 5
8151 | Gorkha | Taklung | 9 | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 235 | 235 |  |  |  | Sahid Lakhan | 5
8152 | Gorkha | Taklung | All | OXFAM-GB | TMUC |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 1241 | 1241 |  |  |  | Sahid Lakhan | 5
8153 | Gorkha | Taklung | All | GON - PAF | LLCSC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0 |  |  |  | Sahid Lakhan | 5
8154 | Gorkha | Taklung | All | OXFAM-GB | TMUC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-02-02 |  |  | Sahid Lakhan | 5
8155 | Gorkha | Taklung |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 171 |  |  |  | Sahid Lakhan | 5
8156 | Gorkha | Taklung | All | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 60 | 60 |  |  |  | Sahid Lakhan | 5
8157 | Gorkha | Takukot | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-28 | Ward no. 1 Purna Nirman Samudaik Samiti | Sulikot | 6
8158 | Gorkha | Takukot | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Sulikot | 6
8159 | Gorkha | Takukot | 1 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 19 | 19 | 2016-04-28 | 2016-06-21 |  | Sulikot | 6
8160 | Gorkha | Takukot | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Bhale Dhunga Purna Nirman Samudaik Samiti | Sulikot | 6
8161 | Gorkha | Takukot | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Sulikot | 6
8162 | Gorkha | Takukot | 2 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-04-28 | 2016-05-04 |  | Sulikot | 6
8163 | Gorkha | Takukot | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Ward no. 3 Purna Nirman Samudaik Samiti | Sulikot | 6
8164 | Gorkha | Takukot | 3 | HELVETAS | Sathi | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees |  | Completed | 10 | 10 |  |  |  | Sulikot | 6
8165 | Gorkha | Takukot | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Sulikot | 6
8166 | Gorkha | Takukot | 3 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-04-28 | 2016-05-04 |  | Sulikot | 6
8167 | Gorkha | Takukot | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Ward no. 4 Purna Nirman Samudaik Samiti | Sulikot | 6
8168 | Gorkha | Takukot | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Sulikot | 6
8169 | Gorkha | Takukot | 4 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-28 | 2016-05-04 |  | Sulikot | 6
8170 | Gorkha | Takukot | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-13 | Ward no. 5 Purna Nirman Samudaik Samiti | Sulikot | 6
8171 | Gorkha | Takukot | 5 | HELVETAS | Sathi | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01 |  | Sulikot | 6
8172 | Gorkha | Takukot | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Sulikot | 6
8173 | Gorkha | Takukot | 5 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-04-28 | 2016-05-04 |  | Sulikot | 6
8174 | Gorkha | Takukot | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-29 | Bahakot Purna Nirman Samudaik Samiti | Sulikot | 6
8175 | Gorkha | Takukot | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Sulikot | 6
8176 | Gorkha | Takukot | 6 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-04-28 | 2016-05-04 |  | Sulikot | 6
8177 | Gorkha | Takukot | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Bhohoriya Purna Nirman Samudaik Samiti | Sulikot | 6
8178 | Gorkha | Takukot | 7 | HELVETAS | Sathi | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01 |  | Sulikot | 6
8179 | Gorkha | Takukot | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Sulikot | 6
8180 | Gorkha | Takukot | 7 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-05-03 | 2016-06-21 |  | Sulikot | 6
8181 | Gorkha | Takukot | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-31 | Ward no. 8 Purna Nirman Samudaik Samiti | Sulikot | 6
8182 | Gorkha | Takukot | 8 | HELVETAS | Sathi | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-01 | 2016-10-01 |  | Sulikot | 6
8183 | Gorkha | Takukot | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Sulikot | 6
8184 | Gorkha | Takukot | 8 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 44 | 44 | 2016-05-03 | 2016-06-21 |  | Sulikot | 6
8185 | Gorkha | Takukot | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-01 | Ward no. 9 Purna Nirman Samudaik Samiti | Sulikot | 6
8186 | Gorkha | Takukot | 9 | HELVETAS | Sathi | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2015-12-01 | 2016-10-01 |  | Sulikot | 6
8187 | Gorkha | Takukot | 9 | HELVETAS | Sathi | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 40 | 10 | 2016-12-01 | 2016-10-01 |  | Sulikot | 6
8188 | Gorkha | Takukot | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Sulikot | 6
8189 | Gorkha | Takukot | 9 | SCI | SSICDC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 23 | 23 | 2016-05-03 | 2016-06-21 |  | Sulikot | 6
8190 | Gorkha | Takukot | All | JICA |  |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 818 | 912 | 2017-05-03 |  |  | Sulikot | 6
8191 | Gorkha | Takukot |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 80 |  |  |  | Sulikot | 6
8192 | Gorkha | Takumajhalakuribot | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-06 | Ward no. 1 Purna Nirman Samudaik Samiti | Sulikot | 5
8193 | Gorkha | Takumajhalakuribot | 1 | OXFAM-GB | TMUC |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 76 | 76 |  |  |  | Sulikot | 5
8194 | Gorkha | Takumajhalakuribot | 1 | OXFAM-GB | TMUC |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Sulikot | 5
8195 | Gorkha | Takumajhalakuribot | 1 | OXFAM-GB | TMUC |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Sulikot | 5
8196 | Gorkha | Takumajhalakuribot | 1 | HELVETAS | Sathi | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2015-12-01 | 2016-10-01 |  | Sulikot | 5
8197 | Gorkha | Takumajhalakuribot | 1 | HELVETAS | Sathi | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees |  | Completed | 10 | 10 |  |  |  | Sulikot | 5
8198 | Gorkha | Takumajhalakuribot | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Sulikot | 5
8199 | Gorkha | Takumajhalakuribot | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Ward no. 2 Purna Nirman Samudaik Samiti | Sulikot | 5
8200 | Gorkha | Takumajhalakuribot | 2 | OXFAM-GB | TMUC |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 76 | 76 |  |  |  | Sulikot | 5
8201 | Gorkha | Takumajhalakuribot | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Sulikot | 5
8202 | Gorkha | Takumajhalakuribot | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-03 | Siran Lakuribot Purna Nirman Samudaik Samiti | Sulikot | 5
8203 | Gorkha | Takumajhalakuribot | 3 | OXFAM-GB | TMUC |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 70 |  |  |  | Sulikot | 5
8204 | Gorkha | Takumajhalakuribot | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Sulikot | 5
8205 | Gorkha | Takumajhalakuribot | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-14 | Ward no. 4 Purna Nirman Samudaik Samiti | Sulikot | 5
8206 | Gorkha | Takumajhalakuribot | 4 | OXFAM-GB | TMUC |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 70 | 70 |  |  |  | Sulikot | 5
8207 | Gorkha | Takumajhalakuribot | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Sulikot | 5
8208 | Gorkha | Takumajhalakuribot | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-09 | Thale Purna Nirman Samudaik Samiti | Sulikot | 5
8209 | Gorkha | Takumajhalakuribot | 5 | OXFAM-GB | TMUC |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 92 | 92 |  |  |  | Sulikot | 5
8210 | Gorkha | Takumajhalakuribot | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Sulikot | 5
8211 | Gorkha | Takumajhalakuribot | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-07 | Jal Kanya Purna Nirman Samudaik Samiti | Sulikot | 5
8212 | Gorkha | Takumajhalakuribot | 6 | OXFAM-GB | TMUC |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 81 | 81 |  |  |  | Sulikot | 5
8213 | Gorkha | Takumajhalakuribot | 6 | HELVETAS | Sathi | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Sulikot | 5
8214 | Gorkha | Takumajhalakuribot | 6 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Sulikot | 5
8215 | Gorkha | Takumajhalakuribot | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-02 | Ward no. 7 Purna Nirman Samudaik Samiti | Sulikot | 5
8216 | Gorkha | Takumajhalakuribot | 7 | OXFAM-GB | TMUC |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 80 | 80 |  |  |  | Sulikot | 5
8217 | Gorkha | Takumajhalakuribot | 7 | HELVETAS | Sathi | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Sulikot | 5
8218 | Gorkha | Takumajhalakuribot | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Sulikot | 5
8219 | Gorkha | Takumajhalakuribot | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-30 | Ward no. 8 Purna Nirman Samudaik Samiti | Sulikot | 5
8220 | Gorkha | Takumajhalakuribot | 8 | OXFAM-GB | TMUC |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 72 | 72 |  |  |  | Sulikot | 5
8221 | Gorkha | Takumajhalakuribot | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Sulikot | 5
8222 | Gorkha | Takumajhalakuribot | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-02-10 | Ward no. 9 Purna Nirman Samudaik Samiti | Sulikot | 5
8223 | Gorkha | Takumajhalakuribot | 9 | OXFAM-GB | TMUC |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 89 | 89 |  |  |  | Sulikot | 5
8224 | Gorkha | Takumajhalakuribot | 9 | HELVETAS | Sathi | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 10 | 2015-12-01 | 2016-01-01 |  | Sulikot | 5
8225 | Gorkha | Takumajhalakuribot | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Sulikot | 5
8226 | Gorkha | Takumajhalakuribot | All | JICA |  |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 630 | 799 | 2017-05-03 |  |  | Sulikot | 5
8227 | Gorkha | Takumajhalakuribot | All | OXFAM-GB | TMUC |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 638 | 638 |  |  | Info Center | Sulikot | 5
8228 | Gorkha | Takumajhalakuribot | All | HELVETAS | Sathi | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2015-12-01 | 2016-01-01 |  | Sulikot | 5
8229 | Gorkha | Takumajhalakuribot | All | HELVETAS | Sathi | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2015-12-01 | 2016-01-01 |  | Sulikot | 5
8230 | Gorkha | Takumajhalakuribot | All | OXFAM-GB | TMUC |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 |  |  |  | Sulikot | 5
8231 | Gorkha | Takumajhalakuribot |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Ongoing | 160 | 78 |  |  |  | Sulikot | 5
8232 | Gorkha | Takumajhalakuribot | 1 | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 3 |  |  |  | Sulikot | 5
8233 | Gorkha | Takumajhalakuribot | 2 | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 2 |  |  |  | Sulikot | 5
8234 | Gorkha | Takumajhalakuribot | 3 | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 2 |  |  |  | Sulikot | 5
8235 | Gorkha | Takumajhalakuribot | 4 | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 3 |  |  |  | Sulikot | 5
8236 | Gorkha | Takumajhalakuribot | 5 | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 3 |  |  |  | Sulikot | 5
8237 | Gorkha | Takumajhalakuribot | 6 | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 3 |  |  |  | Sulikot | 5
8238 | Gorkha | Takumajhalakuribot | 7 | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 4 |  |  |  | Sulikot | 5
8239 | Gorkha | Takumajhalakuribot | 8 | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 4 |  |  |  | Sulikot | 5
8240 | Gorkha | Takumajhalakuribot | 9 | OXFAM-GB | TMUC |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 5 |  |  |  | Sulikot | 5
8241 | Gorkha | Tandrang | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bhimsen | 3
8242 | Gorkha | Tandrang | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 173 | 72 | 2017-05-21 |  |  | Bhimsen | 3
8243 | Gorkha | Tandrang | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 7 | 2017-03-17 |  |  | Bhimsen | 3
8244 | Gorkha | Tandrang | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 173 | 0 |  |  |  | Bhimsen | 3
8245 | Gorkha | Tandrang | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 173 | 0 |  |  |  | Bhimsen | 3
8246 | Gorkha | Tandrang | 1 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-28 | Danda Basi CBRC | Bhimsen | 3
8247 | Gorkha | Tandrang | 1 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-11-29 | 2017-02-07 |  | Bhimsen | 3
8248 | Gorkha | Tandrang | 1 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Bhimsen | 3
8249 | Gorkha | Tandrang | 1 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-08 | 2016-03-19 |  | Bhimsen | 3
8250 | Gorkha | Tandrang | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-27 | 2017-06-20 |  | Bhimsen | 3
8251 | Gorkha | Tandrang | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 174 | 39 | 2017-05-21 |  |  | Bhimsen | 3
8252 | Gorkha | Tandrang | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 12 | 2017-03-17 |  |  | Bhimsen | 3
8253 | Gorkha | Tandrang | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 174 | 0 |  |  |  | Bhimsen | 3
8254 | Gorkha | Tandrang | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 174 | 0 |  |  |  | Bhimsen | 3
8255 | Gorkha | Tandrang | 2 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-23 | Nange Dada CBRC | Bhimsen | 3
8256 | Gorkha | Tandrang | 2 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 17 | 2016-12-31 | 2017-01-06 |  | Bhimsen | 3
8257 | Gorkha | Tandrang | 2 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-27 | 2017-06-28 |  | Bhimsen | 3
8258 | Gorkha | Tandrang | 2 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-08 | 2016-03-19 |  | Bhimsen | 3
8259 | Gorkha | Tandrang | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-23 | 2017-06-20 |  | Bhimsen | 3
8260 | Gorkha | Tandrang | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 51 | 11 | 2017-05-21 |  |  | Bhimsen | 3
8261 | Gorkha | Tandrang | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 14 | 2017-03-17 |  |  | Bhimsen | 3
8262 | Gorkha | Tandrang | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 51 | 0 |  |  |  | Bhimsen | 3
8263 | Gorkha | Tandrang | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 51 | 0 |  |  |  | Bhimsen | 3
8264 | Gorkha | Tandrang | 3 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-24 | Lali Guras CBRC | Bhimsen | 3
8265 | Gorkha | Tandrang | 3 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 1 | 2016-12-31 | 2017-01-06 |  | Bhimsen | 3
8266 | Gorkha | Tandrang | 3 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-23 | 2017-06-28 |  | Bhimsen | 3
8267 | Gorkha | Tandrang | 3 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-08 | 2016-03-19 |  | Bhimsen | 3
8268 | Gorkha | Tandrang | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-10 | 2017-06-20 |  | Bhimsen | 3
8269 | Gorkha | Tandrang | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 74 | 12 | 2017-05-21 |  |  | Bhimsen | 3
8270 | Gorkha | Tandrang | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 15 | 2017-03-17 |  |  | Bhimsen | 3
8271 | Gorkha | Tandrang | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 74 | 0 |  |  |  | Bhimsen | 3
8272 | Gorkha | Tandrang | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 74 | 0 |  |  |  | Bhimsen | 3
8273 | Gorkha | Tandrang | 4 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-24 | Jagaran CBRC | Bhimsen | 3
8274 | Gorkha | Tandrang | 4 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 1 | 2016-12-31 | 2017-01-06 |  | Bhimsen | 3
8275 | Gorkha | Tandrang | 4 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-10 | 2017-06-28 |  | Bhimsen | 3
8276 | Gorkha | Tandrang | 4 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-08 | 2016-03-19 |  | Bhimsen | 3
8277 | Gorkha | Tandrang | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-05-03 | 2017-06-20 |  | Bhimsen | 2
8278 | Gorkha | Tandrang | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 58 | 14 | 2017-05-21 |  |  | Bhimsen | 2
8279 | Gorkha | Tandrang | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 8 | 2017-03-17 |  |  | Bhimsen | 2
8280 | Gorkha | Tandrang | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 58 | 0 |  |  |  | Bhimsen | 2
8281 | Gorkha | Tandrang | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 58 | 0 |  |  |  | Bhimsen | 2
8282 | Gorkha | Tandrang | 5 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-26 | Gurdhauli CBRC | Bhimsen | 2
8283 | Gorkha | Tandrang | 5 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-11-29 | 2016-12-05 |  | Bhimsen | 2
8284 | Gorkha | Tandrang | 5 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-03 | 2017-06-28 |  | Bhimsen | 2
8285 | Gorkha | Tandrang | 5 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-08 | 2016-03-19 |  | Bhimsen | 2
8286 | Gorkha | Tandrang | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-28 | 2017-06-20 |  | Bhimsen | 2
8287 | Gorkha | Tandrang | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 102 | 54 | 2017-05-21 |  |  | Bhimsen | 2
8288 | Gorkha | Tandrang | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 12 | 2017-03-17 |  |  | Bhimsen | 2
8289 | Gorkha | Tandrang | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 102 | 0 |  |  |  | Bhimsen | 2
8290 | Gorkha | Tandrang | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 102 | 0 |  |  |  | Bhimsen | 2
8291 | Gorkha | Tandrang | 6 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-26 | Okhle CBRC | Bhimsen | 2
8292 | Gorkha | Tandrang | 6 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-11-29 | 2016-12-05 |  | Bhimsen | 2
8293 | Gorkha | Tandrang | 6 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-28 | 2017-06-28 |  | Bhimsen | 2
8294 | Gorkha | Tandrang | 6 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-08 | 2016-03-19 |  | Bhimsen | 2
8295 | Gorkha | Tandrang | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-20 | 2017-06-20 |  | Bhimsen | 2
8296 | Gorkha | Tandrang | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 136 | 26 | 2017-05-21 |  |  | Bhimsen | 2
8297 | Gorkha | Tandrang | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 10 | 2017-03-17 |  |  | Bhimsen | 2
8298 | Gorkha | Tandrang | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 136 | 0 |  |  |  | Bhimsen | 2
8299 | Gorkha | Tandrang | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 136 | 0 |  |  |  | Bhimsen | 2
8300 | Gorkha | Tandrang | 7 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-27 | Darme CBRC | Bhimsen | 2
8301 | Gorkha | Tandrang | 7 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-11-29 | 2016-12-05 |  | Bhimsen | 2
8302 | Gorkha | Tandrang | 7 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-28 |  | Bhimsen | 2
8303 | Gorkha | Tandrang | 7 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-08 | 2016-03-19 |  | Bhimsen | 2
8304 | Gorkha | Tandrang | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bhimsen | 2
8305 | Gorkha | Tandrang | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 91 | 12 | 2017-05-21 |  |  | Bhimsen | 2
8306 | Gorkha | Tandrang | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 5 | 2017-03-17 |  |  | Bhimsen | 2
8307 | Gorkha | Tandrang | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 91 | 0 |  |  |  | Bhimsen | 2
8308 | Gorkha | Tandrang | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 91 | 0 |  |  |  | Bhimsen | 2
8309 | Gorkha | Tandrang | 8 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-27 | Pauwa CBRC | Bhimsen | 2
8310 | Gorkha | Tandrang | 8 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 1 | 2016-11-29 | 2016-12-05 |  | Bhimsen | 2
8311 | Gorkha | Tandrang | 8 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Bhimsen | 2
8312 | Gorkha | Tandrang | 8 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-08 | 2016-03-19 |  | Bhimsen | 2
8313 | Gorkha | Tandrang | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-29 | 2017-06-20 |  | Bhimsen | 2
8314 | Gorkha | Tandrang | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 134 | 21 | 2017-05-21 |  |  | Bhimsen | 2
8315 | Gorkha | Tandrang | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 10 | 2017-03-17 |  |  | Bhimsen | 2
8316 | Gorkha | Tandrang | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 134 | 0 |  |  |  | Bhimsen | 2
8317 | Gorkha | Tandrang | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 134 | 0 |  |  |  | Bhimsen | 2
8318 | Gorkha | Tandrang | 9 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-27 | Pokhari dada CBRC | Bhimsen | 2
8319 | Gorkha | Tandrang | 9 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 13 | 0 | 2016-09-01 | 2017-03-31 |  | Bhimsen | 2
8320 | Gorkha | Tandrang | 9 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-29 | 2017-06-28 |  | Bhimsen | 2
8321 | Gorkha | Tandrang | 9 | NYF | NYF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-08 | 2016-03-19 |  | Bhimsen | 2
8322 | Gorkha | Tandrang | All | CRS | SSICDC |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 1 | 1 | 2017-03-17 |  |  | Bhimsen | 3
8323 | Gorkha | Tandrang |  | NYF | NYF |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-08 | 2016-03-19 |  | Bhimsen | 3
8324 | Gorkha | Tandrang |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 364 |  |  |  | Bhimsen | 3
8325 | Gorkha | Tanglichok | All | UNWOMEN | WHR |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 19 | 19 | 2017-05-07 | 2017-06-07 |  | Gandaki | 2
8326 | Gorkha | Tanglichok | All | DCA | ECO-N | DCA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 62 | 62 | 2016-02-20 | 2016-02-24 |  | Gandaki | 2
8327 | Gorkha | Tanglichok | All | GON - PAF | GORETO GORKHA | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0 |  |  |  | Gandaki | 2
8328 | Gorkha | Taple | 1 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-19 | 2017-06-20 |  | Gorkha | 2
8329 | Gorkha | Taple | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 165 | 50 | 2017-05-21 |  |  | Gorkha | 2
8330 | Gorkha | Taple | 1 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 27 | 2017-03-17 |  |  | Gorkha | 2
8331 | Gorkha | Taple | 1 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 165 | 0 |  |  |  | Gorkha | 2
8332 | Gorkha | Taple | 1 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 165 | 0 |  |  |  | Gorkha | 2
8333 | Gorkha | Taple | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-06 | Bagh Bhairav Purna Nirman Samudaik Samiti | Gorkha | 2
8334 | Gorkha | Taple | 1 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-03-28 | 2016-04-01 |  | Gorkha | 2
8335 | Gorkha | Taple | 1 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Completed | 10 | 10 | 2017-03-19 | 2017-06-22 |  | Gorkha | 2
8336 | Gorkha | Taple | 1 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 7 | 2016-02-08 | 2016-03-14 | 30 days vocational training | Gorkha | 2
8337 | Gorkha | Taple | 2 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-19 | 2017-06-20 |  | Gorkha | 2
8338 | Gorkha | Taple | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 121 | 35 | 2017-05-21 |  |  | Gorkha | 2
8339 | Gorkha | Taple | 2 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 7 | 2017-03-17 |  |  | Gorkha | 2
8340 | Gorkha | Taple | 2 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 121 | 0 |  |  |  | Gorkha | 2
8341 | Gorkha | Taple | 2 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 121 | 0 |  |  |  | Gorkha | 2
8342 | Gorkha | Taple | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-07 | Shree Krishna Purna Nirman Samudaik Samiti | Gorkha | 2
8343 | Gorkha | Taple | 2 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-03-28 | 2016-04-01 |  | Gorkha | 2
8344 | Gorkha | Taple | 2 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Completed | 10 | 10 | 2017-03-19 | 2017-06-22 |  | Gorkha | 2
8345 | Gorkha | Taple | 2 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 5 | 2016-02-08 | 2016-03-14 | 30 days vocational training | Gorkha | 2
8346 | Gorkha | Taple | 3 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-19 | 2017-06-20 |  | Gorkha | 2
8347 | Gorkha | Taple | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 169 | 41 | 2017-05-21 |  |  | Gorkha | 2
8348 | Gorkha | Taple | 3 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 22 | 2017-03-17 |  |  | Gorkha | 2
8349 | Gorkha | Taple | 3 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 169 | 0 |  |  |  | Gorkha | 2
8350 | Gorkha | Taple | 3 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 169 | 0 |  |  |  | Gorkha | 2
8351 | Gorkha | Taple | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-08 | Gauir Shankar Purna Nirman Samudaik Samiti | Gorkha | 2
8352 | Gorkha | Taple | 3 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-04-25 | 2016-04-29 |  | Gorkha | 2
8353 | Gorkha | Taple | 3 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Completed | 10 | 10 | 2017-03-19 | 2017-06-22 |  | Gorkha | 2
8354 | Gorkha | Taple | 3 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 7 | 2016-02-08 | 2016-03-14 | 30 days vocational training | Gorkha | 2
8355 | Gorkha | Taple | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 1 |  |  | Organized in Pandrung; People from Taple participated | Gorkha | 2
8356 | Gorkha | Taple | 4 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Gorkha | 2
8357 | Gorkha | Taple | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 145 | 16 | 2017-05-21 |  |  | Gorkha | 2
8358 | Gorkha | Taple | 4 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 6 | 2017-03-17 |  |  | Gorkha | 2
8359 | Gorkha | Taple | 4 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 145 | 0 |  |  |  | Gorkha | 2
8360 | Gorkha | Taple | 4 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 145 | 0 |  |  |  | Gorkha | 2
8361 | Gorkha | Taple | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-09 | Aahaley Bhanjyan Purna Nirman Samudaik Samiti | Gorkha | 2
8362 | Gorkha | Taple | 4 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-04-25 | 2016-04-29 |  | Gorkha | 2
8363 | Gorkha | Taple | 4 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Gorkha | 2
8364 | Gorkha | Taple | 4 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 9 | 9 | 2015-07-10 | 2015-08-08 | 30 days vocational training | Gorkha | 2
8365 | Gorkha | Taple | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 |  |  | Organized in Pandrung; People from Taple participated | Gorkha | 2
8366 | Gorkha | Taple | 5 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Gorkha | 2
8367 | Gorkha | Taple | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 174 | 37 | 2017-05-21 |  |  | Gorkha | 2
8368 | Gorkha | Taple | 5 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 37 | 2017-03-17 |  |  | Gorkha | 2
8369 | Gorkha | Taple | 5 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 174 | 0 |  |  |  | Gorkha | 2
8370 | Gorkha | Taple | 5 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 174 | 0 |  |  |  | Gorkha | 2
8371 | Gorkha | Taple | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Manaslu Gau Purna Nirman Samiti | Gorkha | 2
8372 | Gorkha | Taple | 5 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-02-29 | 2016-03-04 |  | Gorkha | 2
8373 | Gorkha | Taple | 5 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Gorkha | 2
8374 | Gorkha | Taple | 5 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 7 | 2016-03-28 | 2016-05-01 | 30 days vocational training | Gorkha | 2
8375 | Gorkha | Taple | 6 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-03-19 | 2017-06-20 |  | Gorkha | 1
8376 | Gorkha | Taple | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 225 | 3 | 2017-05-21 |  |  | Gorkha | 1
8377 | Gorkha | Taple | 6 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 19 | 2017-03-17 |  |  | Gorkha | 1
8378 | Gorkha | Taple | 6 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 225 | 0 |  |  |  | Gorkha | 1
8379 | Gorkha | Taple | 6 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 225 | 0 |  |  |  | Gorkha | 1
8380 | Gorkha | Taple | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Mahadev Basti Gau Purna Nirman Samiti | Gorkha | 1
8381 | Gorkha | Taple | 6 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-02-29 | 2016-03-04 |  | Gorkha | 1
8382 | Gorkha | Taple | 6 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Completed | 10 | 10 | 2017-03-19 | 2017-06-22 |  | Gorkha | 1
8383 | Gorkha | Taple | 6 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 7 | 2016-03-28 | 2016-05-01 | 30 days vocational training | Gorkha | 1
8384 | Gorkha | Taple | 7 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-05-20 | 2017-06-20 |  | Gorkha | 1
8385 | Gorkha | Taple | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 135 | 26 | 2017-05-21 |  |  | Gorkha | 1
8386 | Gorkha | Taple | 7 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 10 | 2017-03-17 |  |  | Gorkha | 1
8387 | Gorkha | Taple | 7 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 135 | 0 |  |  |  | Gorkha | 1
8388 | Gorkha | Taple | 7 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 135 | 0 |  |  |  | Gorkha | 1
8389 | Gorkha | Taple | 7 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-04 | Shiva Aakala Purna Nirman Samudaik Samiti | Gorkha | 1
8390 | Gorkha | Taple | 7 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-02-29 | 2016-03-04 |  | Gorkha | 1
8391 | Gorkha | Taple | 7 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Gorkha | 1
8392 | Gorkha | Taple | 7 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 7 | 2016-03-28 | 2016-05-01 | 30 days vocational training | Gorkha | 1
8393 | Gorkha | Taple | 8 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-02-16 | 2017-06-20 |  | Gorkha | 1
8394 | Gorkha | Taple | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 138 | 37 | 2017-05-21 |  |  | Gorkha | 1
8395 | Gorkha | Taple | 8 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 13 | 2017-03-17 |  |  | Gorkha | 1
8396 | Gorkha | Taple | 8 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 138 | 0 |  |  |  | Gorkha | 1
8397 | Gorkha | Taple | 8 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 138 | 36 | 2016-02-19 | 2016-02-19 |  | Gorkha | 1
8398 | Gorkha | Taple | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-05 | Taplekot Purna Nirman Samudaik Samiti | Gorkha | 1
8399 | Gorkha | Taple | 8 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-01-25 | 2016-01-29 |  | Gorkha | 1
8400 | Gorkha | Taple | 8 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Completed | 10 | 10 | 2017-01-12 | 2017-03-12 |  | Gorkha | 1
8401 | Gorkha | Taple | 8 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 8 | 2016-03-28 | 2016-03-03 | 30 days vocational training | Gorkha | 1
8402 | Gorkha | Taple | 9 | CRS | SDSC | CRS | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Gorkha | 1
8403 | Gorkha | Taple | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 151 | 40 | 2017-05-21 |  |  | Gorkha | 1
8404 | Gorkha | Taple | 9 | CRS | SDSC | CRS | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 10 | 2017-03-17 |  |  | Gorkha | 1
8405 | Gorkha | Taple | 9 | CRS | SDSC | CRS | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 151 | 0 |  |  |  | Gorkha | 1
8406 | Gorkha | Taple | 9 | CRS | SDSC | CRS | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 151 | 98 | 2016-02-19 | 2016-02-21 |  | Gorkha | 1
8407 | Gorkha | Taple | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-03-03 | Shiva Parbati Purna Nirman Samudaik Samiti | Gorkha | 1
8408 | Gorkha | Taple | 9 | CRS | SDSC | CRS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-01-25 | 2016-01-29 |  | Gorkha | 1
8409 | Gorkha | Taple | 9 | CRS | SDSC | CRS | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason training | # of trainees | Yes | Planned | 10 | 0 |  |  |  | Gorkha | 1
8410 | Gorkha | Taple | 9 | CRS | SDSC | CRS | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-03-28 | 2016-03-03 | 30 days vocational training | Gorkha | 1
8411 | Gorkha | Taple | 4,8,9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  | Sirdibas Gau Purna Nirman Samiti | Gorkha | 1
8412 | Gorkha | Taple | All | JICA |  |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 1228 | 1146 | 2017-05-03 |  |  | Gorkha | 2
8413 | Gorkha | Taple | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 85 |  |  |  | Gorkha | 2
8414 | Gorkha | Taple | All | CRS | SDSC |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 26 | 27 | 2017-03-17 |  |  | Gorkha | 2
8415 | Gorkha | Taple |  | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 |  |  |  | Gorkha | 2
8416 | Gorkha | Thalajung |  | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 51 |  |  |  | Siranchok | 2
8417 | Gorkha | Thumi | 2 | SAHAS | SAHAS |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 50000 was provided as first tranche | # of households | Yes | Ongoing | 49 | 15 |  |  | Rs 50000 first tranche of Government subsidy was supported by Save | Aarughat | 4
8418 | Gorkha | Thumi | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-12 | 2017-06-20 |  | Aarughat | 4
8419 | Gorkha | Thumi | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 83 | 42 | 2017-05-21 |  |  | Aarughat | 4
8420 | Gorkha | Thumi | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 10 | 2017-03-17 |  |  | Aarughat | 4
8421 | Gorkha | Thumi | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 83 | 0 |  |  |  | Aarughat | 4
8422 | Gorkha | Thumi | 1 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 83 | 0 |  |  |  | Aarughat | 4
8423 | Gorkha | Thumi | 1 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-30 | Maseb CBRC | Aarughat | 4
8424 | Gorkha | Thumi | 1 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-12-11 | 2016-12-17 |  | Aarughat | 4
8425 | Gorkha | Thumi | 1 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-12 | 2017-06-20 |  | Aarughat | 4
8426 | Gorkha | Thumi | 2 | SAHAS | SAHAS |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000 was provided as first tranche | # of households | Yes | Completed | 59 | 59 |  |  | Rs 50000 first tranche of Government subsidy was supported by Save | Aarughat | 4
8427 | Gorkha | Thumi | 2 | SAHAS | SAHAS |  | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 150000 is provided as second tranche | # of households | Yes | Completed | 59 | 59 |  |  |  | Aarughat | 4
8428 | Gorkha | Thumi | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-21 | 2017-06-20 |  | Aarughat | 4
8429 | Gorkha | Thumi | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 94 | 19 | 2017-05-21 |  |  | Aarughat | 4
8430 | Gorkha | Thumi | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 12 | 2017-03-17 |  |  | Aarughat | 4
8431 | Gorkha | Thumi | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 94 | 0 |  |  |  | Aarughat | 4
8432 | Gorkha | Thumi | 2 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 94 | 0 |  |  |  | Aarughat | 4
8433 | Gorkha | Thumi | 2 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-31 | Jamune CBRC | Aarughat | 4
8434 | Gorkha | Thumi | 2 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-12-11 | 2016-12-17 |  | Aarughat | 4
8435 | Gorkha | Thumi | 2 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-21 | 2017-06-20 |  | Aarughat | 4
8436 | Gorkha | Thumi | 2 | SAHAS | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-18 | 2016-06-25 | mason training done with partner with CARE-N dhadhing. | Aarughat | 4
8437 | Gorkha | Thumi | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-28 | 2017-06-20 |  | Aarughat | 4
8438 | Gorkha | Thumi | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 131 | 52 | 2017-05-21 |  |  | Aarughat | 4
8439 | Gorkha | Thumi | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 18 | 2017-03-17 |  |  | Aarughat | 4
8440 | Gorkha | Thumi | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 131 | 0 |  |  |  | Aarughat | 4
8441 | Gorkha | Thumi | 3 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 131 | 0 |  |  |  | Aarughat | 4
8442 | Gorkha | Thumi | 3 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-29 | Chandi Thumi CBRC | Aarughat | 4
8443 | Gorkha | Thumi | 3 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-12-11 | 2016-12-17 |  | Aarughat | 4
8444 | Gorkha | Thumi | 3 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-28 | 2017-06-20 |  | Aarughat | 4
8445 | Gorkha | Thumi | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-01 | 2017-06-20 |  | Aarughat | 3
8446 | Gorkha | Thumi | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 95 | 34 | 2017-05-21 |  |  | Aarughat | 3
8447 | Gorkha | Thumi | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 15 | 2017-03-17 |  |  | Aarughat | 3
8448 | Gorkha | Thumi | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 95 | 0 |  |  |  | Aarughat | 3
8449 | Gorkha | Thumi | 4 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 95 | 0 |  |  |  | Aarughat | 3
8450 | Gorkha | Thumi | 4 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-06-05 | Sundar Swanra CBRC | Aarughat | 3
8451 | Gorkha | Thumi | 4 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-01 | 2017-02-07 |  | Aarughat | 3
8452 | Gorkha | Thumi | 4 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-01 | 2017-06-20 |  | Aarughat | 3
8453 | Gorkha | Thumi | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-01-09 | 2017-06-20 |  | Aarughat | 4
8454 | Gorkha | Thumi | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 241 | 54 | 2017-05-21 |  |  | Aarughat | 4
8455 | Gorkha | Thumi | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 28 | 2017-03-17 |  |  | Aarughat | 4
8456 | Gorkha | Thumi | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 241 | 0 |  |  |  | Aarughat | 4
8457 | Gorkha | Thumi | 5 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 241 | 0 |  |  |  | Aarughat | 4
8458 | Gorkha | Thumi | 5 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-28 | Arkhet CBRC | Aarughat | 4
8459 | Gorkha | Thumi | 5 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-28 | Dhodeni CBRC | Aarughat | 4
8460 | Gorkha | Thumi | 5 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-12-27 | 2017-01-02 |  | Aarughat | 4
8461 | Gorkha | Thumi | 5 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-11 | 2017-03-11 |  | Aarughat | 4
8462 | Gorkha | Thumi | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-05 | 2017-06-20 |  | Aarughat | 3
8463 | Gorkha | Thumi | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 206 | 63 | 2017-05-21 |  |  | Aarughat | 3
8464 | Gorkha | Thumi | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 19 | 2017-03-17 |  |  | Aarughat | 3
8465 | Gorkha | Thumi | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 206 | 0 |  |  |  | Aarughat | 3
8466 | Gorkha | Thumi | 6 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 206 | 0 |  |  |  | Aarughat | 3
8467 | Gorkha | Thumi | 6 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-27 | Jinu Bhalak CBRC | Aarughat | 3
8468 | Gorkha | Thumi | 6 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-27 | Soti Kyaurpani CBRC | Aarughat | 3
8469 | Gorkha | Thumi | 6 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-12-27 | 2017-01-02 |  | Aarughat | 3
8470 | Gorkha | Thumi | 6 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-05 | 2017-06-20 |  | Aarughat | 3
8471 | Gorkha | Thumi | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Aarughat | 3
8472 | Gorkha | Thumi | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 115 | 61 | 2017-05-21 |  |  | Aarughat | 3
8473 | Gorkha | Thumi | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 5 | 2017-03-17 |  |  | Aarughat | 3
8474 | Gorkha | Thumi | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 115 | 0 |  |  |  | Aarughat | 3
8475 | Gorkha | Thumi | 7 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 115 | 0 |  |  |  | Aarughat | 3
8476 | Gorkha | Thumi | 7 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-24 | Syamrang CBRC | Aarughat | 3
8477 | Gorkha | Thumi | 7 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-12-27 | 2017-01-02 |  | Aarughat | 3
8478 | Gorkha | Thumi | 7 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Aarughat | 3
8479 | Gorkha | Thumi | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-02 | 2017-06-20 |  | Aarughat | 3
8480 | Gorkha | Thumi | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 112 | 27 | 2017-05-21 |  |  | Aarughat | 3
8481 | Gorkha | Thumi | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 4 | 2017-05-21 |  |  | Aarughat | 3
8482 | Gorkha | Thumi | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 112 | 0 |  |  |  | Aarughat | 3
8483 | Gorkha | Thumi | 8 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 112 | 0 |  |  |  | Aarughat | 3
8484 | Gorkha | Thumi | 8 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-24 | Deurali Banel CBRC | Aarughat | 3
8485 | Gorkha | Thumi | 8 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-25 | Nebot pokhari CBRC | Aarughat | 3
8486 | Gorkha | Thumi | 8 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-02-01 | 2017-02-07 |  | Aarughat | 3
8487 | Gorkha | Thumi | 8 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-02 | 2017-06-20 |  | Aarughat | 3
8488 | Gorkha | Thumi | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-03 | 2017-06-20 |  | Aarughat | 4
8489 | Gorkha | Thumi | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 118 | 40 | 2017-05-21 |  |  | Aarughat | 4
8490 | Gorkha | Thumi | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 20 | 27 | 2017-03-17 |  |  | Aarughat | 4
8491 | Gorkha | Thumi | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 118 | 0 |  |  |  | Aarughat | 4
8492 | Gorkha | Thumi | 9 | CRS | SSICDC | CAFOD | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 118 | 0 |  |  |  | Aarughat | 4
8493 | Gorkha | Thumi | 9 | CRS | SSICDC |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2016-05-26 | Bato Maghachi CBRC | Aarughat | 4
8494 | Gorkha | Thumi | 9 | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-02-01 | 2017-02-07 |  | Aarughat | 4
8495 | Gorkha | Thumi | 9 | CRS | SSICDC | CAFOD | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-03 | 2017-06-20 |  | Aarughat | 4
8496 | Gorkha | Thumi | All | UNDP | UNDP | UNDP | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 100 | 91 |  |  |  | Aarughat | 4
8497 | Gorkha | Uhya | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 69 | 69 | 2016-06-15 | 2016-09-14 |  | Dharche | 3
8498 | Gorkha | Uhya | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 94 | 94 |  |  |  | Dharche | 3
8499 | Gorkha | Uhya | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-08 | 2016-06-14 |  | Dharche | 3
8500 | Gorkha | Uhya | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 91 | 91 | 2016-06-15 | 2016-07-31 |  | Dharche | 3
8501 | Gorkha | Uhya | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 131 | 131 |  |  |  | Dharche | 3
8502 | Gorkha | Uhya | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 95 | 95 | 2016-06-15 | 2016-07-31 |  | Dharche | 3
8503 | Gorkha | Uhya | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 188 | 188 |  |  |  | Dharche | 3
8504 | Gorkha | Uhya | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-08 | 2016-06-14 |  | Dharche | 3
8505 | Gorkha | Uhya | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 20 | 20 | 2016-06-15 | 2016-09-06 |  | Dharche | 3
8506 | Gorkha | Uhya | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 |  |  |  | Dharche | 3
8507 | Gorkha | Uhya | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 88 | 88 |  |  |  | Dharche | 3
8508 | Gorkha | Uhya | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 61 | 61 | 2016-06-15 | 2016-09-07 |  | Dharche | 3
8509 | Gorkha | Uhya | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 48 | 48 |  |  |  | Dharche | 3
8510 | Gorkha | Uhya | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-08 | 2016-06-14 |  | Dharche | 3
8511 | Gorkha | Uhya | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 18 | 18 | 2016-09-09 | 2016-09-09 |  | Dharche | 3
8512 | Gorkha | Uhya | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 74 | 74 |  |  |  | Dharche | 3
8513 | Gorkha | Uhya | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-08 | 2016-06-14 |  | Dharche | 3
8514 | Gorkha | Uhya | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 40 | 40 | 2016-09-09 | 2016-09-09 |  | Dharche | 3
8515 | Gorkha | Uhya | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 134 | 134 |  |  |  | Dharche | 3
8516 | Gorkha | Uhya | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 28 | 28 | 2016-09-11 | 2016-09-11 |  | Dharche | 3
8517 | Gorkha | Uhya | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 69 | 69 |  |  |  | Dharche | 3
8518 | Gorkha | Uhya | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-08 | 2016-06-14 |  | Dharche | 3
8519 | Gorkha | Uhya | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 40 | 40 | 2016-09-13 | 2016-09-13 |  | Dharche | 3
8520 | Gorkha | Uhya | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 19 | 19 | 2016-06-08 | 2016-06-14 |  | Dharche | 3
8521 | Gorkha | Uhya | All | CARE-N | UNIFICATION-N |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Dharche | 3
8522 | Gorkha | Uhya | All | GON - PAF | HADC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Planned | 25 | 0 |  |  |  | Dharche | 3
8523 | Gorkha | Uhya |  | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported |  | Completed | 1 | 1 |  |  | Flagged as 1 to show the area has plans | Dharche | 3
8524 | Gorkha | Warpak | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 70 | 70 | 2016-06-25 | 2016-07-21 |  | Sulikot | 2
8525 | Gorkha | Warpak | 1 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-27 | Barpak-1, Pokhare CBRC | Sulikot | 2
8526 | Gorkha | Warpak | 1 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 413 | 413 |  |  |  | Sulikot | 2
8527 | Gorkha | Warpak | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-18 | 2016-06-24 |  | Sulikot | 2
8528 | Gorkha | Warpak | 1 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-03-19 | 2017-03-25 |  | Sulikot | 2
8529 | Gorkha | Warpak | 1 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Sulikot | 2
8530 | Gorkha | Warpak | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 117 | 117 | 2016-07-22 | 2016-07-27 |  | Sulikot | 2
8531 | Gorkha | Warpak | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Barpak-2, Rangrung CBRC | Sulikot | 2
8532 | Gorkha | Warpak | 2 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-26 | Barpak-2, Mandrey CBRC | Sulikot | 2
8533 | Gorkha | Warpak | 2 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 158 | 158 |  |  |  | Sulikot | 2
8534 | Gorkha | Warpak | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-18 | 2016-06-24 |  | Sulikot | 2
8535 | Gorkha | Warpak | 2 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-03-19 | 2017-03-25 |  | Sulikot | 2
8536 | Gorkha | Warpak | 2 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Sulikot | 2
8537 | Gorkha | Warpak | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 51 | 51 | 2016-07-23 | 2016-07-23 |  | Sulikot | 2
8538 | Gorkha | Warpak | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Barpak-3, Allghau CBRC | Sulikot | 2
8539 | Gorkha | Warpak | 3 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-25 | Barpak-3, Thamsuk CBRC | Sulikot | 2
8540 | Gorkha | Warpak | 3 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 117 | 117 |  |  |  | Sulikot | 2
8541 | Gorkha | Warpak | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-18 | 2016-06-24 |  | Sulikot | 2
8542 | Gorkha | Warpak | 3 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-03-19 | 2017-03-25 |  | Sulikot | 2
8543 | Gorkha | Warpak | 3 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Sulikot | 2
8544 | Gorkha | Warpak | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 85 | 85 | 2016-06-25 | 2016-07-28 |  | Sulikot | 1
8545 | Gorkha | Warpak | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Barpak-4 Sorda CBRC | Sulikot | 1
8546 | Gorkha | Warpak | 4 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-18 | Barpak-4 CBRC | Sulikot | 1
8547 | Gorkha | Warpak | 4 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 336 | 336 |  |  |  | Sulikot | 1
8548 | Gorkha | Warpak | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-18 | 2016-06-24 |  | Sulikot | 1
8549 | Gorkha | Warpak | 4 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-03-19 | 2017-03-25 |  | Sulikot | 1
8550 | Gorkha | Warpak | 4 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 |  |  |  | Sulikot | 1
8551 | Gorkha | Warpak | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 14 | 14 | 2016-06-25 | 2016-07-24 |  | Sulikot | 1
8552 | Gorkha | Warpak | 5 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Barpak 5 CBRC | Sulikot | 1
8553 | Gorkha | Warpak | 5 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 39 | 39 |  |  |  | Sulikot | 1
8554 | Gorkha | Warpak | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-18 | 2016-06-24 |  | Sulikot | 1
8555 | Gorkha | Warpak | 5 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-03-19 | 2017-03-25 |  | Sulikot | 1
8556 | Gorkha | Warpak | 5 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Sulikot | 1
8557 | Gorkha | Warpak | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 44 | 44 | 2016-06-25 | 2016-07-24 |  | Sulikot | 2
8558 | Gorkha | Warpak | 6 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-24 | Barpak 6 CBRC | Sulikot | 2
8559 | Gorkha | Warpak | 6 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 101 | 101 |  |  |  | Sulikot | 2
8560 | Gorkha | Warpak | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-18 | 2016-06-24 |  | Sulikot | 2
8561 | Gorkha | Warpak | 6 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-03-19 | 2017-03-25 |  | Sulikot | 2
8562 | Gorkha | Warpak | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 101 | 101 | 2016-06-25 | 2016-07-26 |  | Sulikot | 2
8563 | Gorkha | Warpak | 7 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 165 | 165 |  |  |  | Sulikot | 2
8564 | Gorkha | Warpak | 7 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-18 | 2016-06-24 |  | Sulikot | 2
8565 | Gorkha | Warpak | 7 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-03-19 | 2017-03-25 |  | Sulikot | 2
8566 | Gorkha | Warpak | 7 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 |  |  |  | Sulikot | 2
8567 | Gorkha | Warpak | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 7 | 7 | 2016-06-25 | 2016-06-25 |  | Sulikot | 2
8568 | Gorkha | Warpak | 8 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-20 | Barpak 8 CBRC | Sulikot | 2
8569 | Gorkha | Warpak | 8 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 225 | 225 |  |  |  | Sulikot | 2
8570 | Gorkha | Warpak | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-18 | 2016-06-24 |  | Sulikot | 2
8571 | Gorkha | Warpak | 8 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2017-03-19 | 2017-03-25 |  | Sulikot | 2
8572 | Gorkha | Warpak | 8 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Sulikot | 2
8573 | Gorkha | Warpak | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 52 | 52 | 2016-06-25 | 2016-07-25 |  | Sulikot | 2
8574 | Gorkha | Warpak | 9 | JICA |  |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  | 2017-01-19 | Barpak 9 CBRC | Sulikot | 2
8575 | Gorkha | Warpak | 9 | CARE-N | UNIFICATION-N | ADH | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 90 | 90 |  |  |  | Sulikot | 2
8576 | Gorkha | Warpak | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-18 | 2016-06-24 |  | Sulikot | 2
8577 | Gorkha | Warpak | 9 | CARE-N | UNIFICATION-N | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-03-19 | 2017-03-25 |  | Sulikot | 2
8578 | Gorkha | Warpak | 9 | JICA | Ertech |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Sulikot | 2
8579 | Gorkha | Warpak | All | PIN | UNIFICATION-N | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 108 | 108 | 2016-10-25 | 2016-10-26 |  | Sulikot | 2
8580 | Gorkha | Warpak | All | CARE-N | UNIFICATION-N |  | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 |  |  |  | Sulikot | 2
8581 | Gorkha | Warpak | All | JICA |  |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical support will be provide to the household who are building their house. | # of households | Yes | Ongoing | 1294 | 640 | 2017-05-03 |  |  | Sulikot | 2
8582 | Gorkha | Warpak | All | JICA | TPIS-ERP |  | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1380 | 0 |  |  |  | Sulikot | 2
8583 | Gorkha | Warpak | All | JICA | TPIS-ERP |  | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Planned | 160 | 0 |  |  |  | Sulikot | 2
8584 | Gorkha | Warpak | All | PIN | UNIFICATION-N | ECHO | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Completed | 407 | 407 | 2016-09-01 | 2016-11-01 |  | Sulikot | 2
8585 | Gorkha | Ghyachok | ALL | OXFAM-GB | UNIFICATION-N |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Completed | 30 | 30 |  |  |  | Ajirkot | 1
8586 | Gorkha | Ghyachok | ALL | OXFAM-GB | UNIFICATION-N |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Completed | 3 | 3 |  |  |  | Ajirkot | 1
8587 | Gorkha | Ghyachok | All | OXFAM-GB | UNIFICATION-N |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees |  | Completed | 30 | 26 |  |  |  | Ajirkot | 1
8588 | Gorkha | Dhawa | All | OXFAM-GB |  |  | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 1046 | 146 |  |  |  | Bhimsen | 4
8589 | Gorkha | Borlang | All | OXFAM-GB |  |  | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 1383 | 1383 |  |  |  | Bhimsen | 8
8590 | Gorkha | Asrang | All | OXFAM-GB |  |  | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 942 | 942 |  |  |  | Bhimsen | 6
8591 | Gorkha | Thalajung | All | OXFAM-GB |  |  | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 772 | 772 |  |  |  | Siranchok | 2
8592 | Gorkha | Thumi | All | CRS | SSICDC |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 2 | 2 | 2017-03-17 |  |  | Aarughat | 4
8593 | Gorkha | AaruChanuate | All | CRS | SSICDC |  | Technical Assistance | Door-to-door technical assistance | Continuous | Technical assistance will be provided to the mason | # of households | Yes | Ongoing | 47 | 47 | 2017-03-17 |  |  | Aarughat | 10
8594 | Gorkha | ghairung | All | OXFAM-GB |  |  | Training | Retrofitting training | Skilled construction workers |  | # of trainees |  | Completed | 10 | 10 |  |  |  | Sahid Lakhan | 6
8595 | Gorkha | Takumajhalakuribot | All | OXFAM-GB |  |  | Training | Retrofitting training | Skilled construction workers |  | # of trainees |  | Completed | 10 | 10 |  |  |  | Sulikot | 5
8596 | Gorkha | saurpani | All | OXFAM-GB |  |  | Training | Retrofitting training | Skilled construction workers |  | # of trainees |  | Completed | 10 | 10 |  |  |  | Sulikot | 4
8597 | Gorkha | Ghyalchok | ALL | NRA | Swostik |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | BBS mason training | # of trainees | Yes | Completed | 29 | 29 | 2017-11-07 | 2017-11-13 |  | Gandaki | 8
8598 | Gorkha | Kharibot | ALL | NRA | Swostik |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | BBS mason training | # of trainees | Yes | Completed | 27 | 27 | 2017-11-10 | 2017-11-16 |  | Ajirkot | 2
8599 | Gorkha | Namjung | ALl | NRA | Swostik |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | BBS mason training | # of trainees | Yes | Completed | 30 | 30 | 2017-11-03 | 2017-11-09 |  | Sahid Lakhan | 9
8600 | Gorkha | Swara | ALl | NRA | Swostik |  | Training | Short training | Masons (7 days DUDBC, rural or urban) | BBS mason training | # of trainees | Yes | Completed | 23 | 23 | 2018-01-03 | 2018-01-09 |  | Sulikot | 3
8601 | Gorkha | Thumi | All | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 35 | 2017-02-01 | 2017-02-07 |  | Aarughat | 4
8602 | Gorkha | Manbu | All | CRS | SSICDC | CAFOD | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 40 | 40 | 2017-02-01 | 2017-02-07 |  | Aarughat | 2
8603 | Gorkha | Palumtar N.P. | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 6
8604 | Gorkha | Palumtar N.P. | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 7
8605 | Gorkha | Palumtar N.P. | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 7
8606 | Gorkha | Palumtar N.P. | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 6
8607 | Gorkha | Palumtar N.P. | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 6
8608 | Gorkha | Palumtar N.P. | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 4
8609 | Gorkha | Palumtar N.P. | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 3
8610 | Gorkha | Palumtar N.P. | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 4
8611 | Gorkha | Palumtar N.P. | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 4
8612 | Gorkha | Palumtar N.P. | 10 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 5
8613 | Gorkha | Palumtar N.P. | 11 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 3
8614 | Gorkha | Palumtar N.P. | 12 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 2
8615 | Gorkha | Palumtar N.P. | 13 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 2
8616 | Gorkha | Bhumlichok | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 6
8617 | Gorkha | Bhumlichok | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 6
8618 | Gorkha | Bhumlichok | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 6
8619 | Gorkha | Bhumlichok | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 6
8620 | Gorkha | Bhumlichok | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 6
8621 | Gorkha | Bhumlichok | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 6
8622 | Gorkha | Bhumlichok | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 6
8623 | Gorkha | Bhumlichok | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 6
8624 | Gorkha | Bhumlichok | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 6
8625 | Gorkha | Chhoprak | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 5
8626 | Gorkha | Chhoprak | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 5
8627 | Gorkha | Chhoprak | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 5
8628 | Gorkha | Chhoprak | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 5
8629 | Gorkha | Chhoprak | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 5
8630 | Gorkha | Chhoprak | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 5
8631 | Gorkha | Chhoprak | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 4
8632 | Gorkha | Chhoprak | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 4
8633 | Gorkha | Chhoprak | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 4
8634 | Gorkha | Deurali | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 14
8635 | Gorkha | Deurali | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 14
8636 | Gorkha | Deurali | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 14
8637 | Gorkha | Deurali | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 14
8638 | Gorkha | Deurali | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 13
8639 | Gorkha | Deurali | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 13
8640 | Gorkha | Deurali | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 13
8641 | Gorkha | Deurali | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 13
8642 | Gorkha | Deurali | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 14
8643 | Gorkha | Dhuwakot | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 8
8644 | Gorkha | Dhuwakot | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 8
8645 | Gorkha | Dhuwakot | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 8
8646 | Gorkha | Dhuwakot | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 8
8647 | Gorkha | Dhuwakot | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 8
8648 | Gorkha | Dhuwakot | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 8
8649 | Gorkha | Dhuwakot | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 9
8650 | Gorkha | Dhuwakot | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 9
8651 | Gorkha | Dhuwakot | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 9
8652 | Gorkha | Gakhu | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 6
8653 | Gorkha | Gakhu | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 6
8654 | Gorkha | Gakhu | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 6
8655 | Gorkha | Gakhu | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 6
8656 | Gorkha | Gakhu | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 6
8657 | Gorkha | Gakhu | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 6
8658 | Gorkha | Gakhu | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 6
8659 | Gorkha | Gakhu | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 6
8660 | Gorkha | Gakhu | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 6
8661 | Gorkha | Ghairung | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 6
8662 | Gorkha | Ghairung | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 6
8663 | Gorkha | Ghairung | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 6
8664 | Gorkha | Ghairung | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 6
8665 | Gorkha | Ghairung | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 6
8666 | Gorkha | Ghairung | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 6
8667 | Gorkha | Ghairung | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 6
8668 | Gorkha | Ghairung | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 6
8669 | Gorkha | Ghairung | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 6
8670 | Gorkha | Ghyachok | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Ajirkot | 1
8671 | Gorkha | Ghyachok | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Ajirkot | 1
8672 | Gorkha | Ghyachok | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Ajirkot | 1
8673 | Gorkha | Ghyachok | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Ajirkot | 1
8674 | Gorkha | Ghyachok | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Ajirkot | 1
8675 | Gorkha | Ghyachok | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Ajirkot | 1
8676 | Gorkha | Ghyachok | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Ajirkot | 1
8677 | Gorkha | Ghyachok | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Ajirkot | 1
8678 | Gorkha | Ghyachok | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Ajirkot | 1
8679 | Gorkha | Gorakha N.P. | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 6
8680 | Gorkha | Gorakha N.P. | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 7
8681 | Gorkha | Gorakha N.P. | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 6
8682 | Gorkha | Gorakha N.P. | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 5
8683 | Gorkha | Gorakha N.P. | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 7
8684 | Gorkha | Gorakha N.P. | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 8
8685 | Gorkha | Gorakha N.P. | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 8
8686 | Gorkha | Gorakha N.P. | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 9
8687 | Gorkha | Gorakha N.P. | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 10
8688 | Gorkha | Gorakha N.P. | 10 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 11
8689 | Gorkha | Gorakha N.P. | 11 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 12
8690 | Gorkha | Gorakha N.P. | 12 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 4
8691 | Gorkha | Gorakha N.P. | 13 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 4
8692 | Gorkha | Gorakha N.P. | 14 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 3
8693 | Gorkha | Gorakha N.P. | 15 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gorkha | 3
8694 | Gorkha | Gumda | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 5
8695 | Gorkha | Gumda | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 5
8696 | Gorkha | Gumda | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 5
8697 | Gorkha | Gumda | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 5
8698 | Gorkha | Gumda | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 5
8699 | Gorkha | Gumda | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 5
8700 | Gorkha | Gumda | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 5
8701 | Gorkha | Gumda | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 5
8702 | Gorkha | Gumda | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 5
8703 | Gorkha | Harmhi | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 3
8704 | Gorkha | Harmhi | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 3
8705 | Gorkha | Harmhi | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 3
8706 | Gorkha | Harmhi | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 3
8707 | Gorkha | Harmhi | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 3
8708 | Gorkha | Harmhi | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 3
8709 | Gorkha | Harmhi | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 3
8710 | Gorkha | Harmhi | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 3
8711 | Gorkha | Harmhi | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 3
8712 | Gorkha | Kashigaun | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 6
8713 | Gorkha | Kashigaun | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 6
8714 | Gorkha | Kashigaun | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 6
8715 | Gorkha | Kashigaun | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 6
8716 | Gorkha | Kashigaun | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 6
8717 | Gorkha | Kashigaun | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 6
8718 | Gorkha | Kashigaun | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 6
8719 | Gorkha | Kashigaun | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 6
8720 | Gorkha | Kashigaun | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 6
8721 | Gorkha | Kharibot | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Ajirkot | 2
8722 | Gorkha | Kharibot | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Ajirkot | 2
8723 | Gorkha | Kharibot | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Ajirkot | 2
8724 | Gorkha | Kharibot | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Ajirkot | 2
8725 | Gorkha | Kharibot | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Ajirkot | 2
8726 | Gorkha | Kharibot | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Ajirkot | 2
8727 | Gorkha | Kharibot | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Ajirkot | 2
8728 | Gorkha | Kharibot | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Ajirkot | 2
8729 | Gorkha | Kharibot | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Ajirkot | 2
8730 | Gorkha | Khoplang | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 2
8731 | Gorkha | Khoplang | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 2
8732 | Gorkha | Khoplang | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 2
8733 | Gorkha | Khoplang | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 1
8734 | Gorkha | Khoplang | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 1
8735 | Gorkha | Khoplang | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 1
8736 | Gorkha | Khoplang | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 1
8737 | Gorkha | Khoplang | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 1
8738 | Gorkha | Khoplang | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 1
8739 | Gorkha | Lapu | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 7
8740 | Gorkha | Lapu | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 7
8741 | Gorkha | Lapu | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 7
8742 | Gorkha | Lapu | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 7
8743 | Gorkha | Lapu | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 7
8744 | Gorkha | Lapu | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 7
8745 | Gorkha | Lapu | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 7
8746 | Gorkha | Lapu | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 7
8747 | Gorkha | Lapu | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Dharche | 7
8748 | Gorkha | Makaising | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 1
8749 | Gorkha | Makaising | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 1
8750 | Gorkha | Makaising | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 1
8751 | Gorkha | Makaising | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 1
8752 | Gorkha | Makaising | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 1
8753 | Gorkha | Makaising | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 1
8754 | Gorkha | Makaising | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 1
8755 | Gorkha | Makaising | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 1
8756 | Gorkha | Makaising | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 1
8757 | Gorkha | Manakamana | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 2
8758 | Gorkha | Manakamana | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 2
8759 | Gorkha | Manakamana | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 3
8760 | Gorkha | Manakamana | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 2
8761 | Gorkha | Manakamana | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 2
8762 | Gorkha | Manakamana | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 3
8763 | Gorkha | Manakamana | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 3
8764 | Gorkha | Manakamana | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 3
8765 | Gorkha | Manakamana | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 3
8766 | Gorkha | Manbu | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Aarughat | 2
8767 | Gorkha | Manbu | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Aarughat | 2
8768 | Gorkha | Manbu | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Aarughat | 2
8769 | Gorkha | Manbu | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Aarughat | 2
8770 | Gorkha | Manbu | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Aarughat | 1
8771 | Gorkha | Manbu | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Aarughat | 1
8772 | Gorkha | Manbu | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Aarughat | 1
8773 | Gorkha | Manbu | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Aarughat | 1
8774 | Gorkha | Manbu | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Aarughat | 1
8775 | Gorkha | Bhirkot | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 10
8776 | Gorkha | Bhirkot | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 10
8777 | Gorkha | Bhirkot | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 10
8778 | Gorkha | Bhirkot | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 10
8779 | Gorkha | Bhirkot | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 9
8780 | Gorkha | Bhirkot | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 10
8781 | Gorkha | Bhirkot | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 10
8782 | Gorkha | Bhirkot | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 9
8783 | Gorkha | Bhirkot | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Palungtar | 10
8784 | Gorkha | Taklung | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 4
8785 | Gorkha | Taklung | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 4
8786 | Gorkha | Taklung | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 4
8787 | Gorkha | Taklung | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 4
8788 | Gorkha | Taklung | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 5
8789 | Gorkha | Taklung | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 5
8790 | Gorkha | Taklung | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 5
8791 | Gorkha | Taklung | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 5
8792 | Gorkha | Taklung | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Sahid Lakhan | 5
8793 | Gorkha | Tanglichok | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 2
8794 | Gorkha | Tanglichok | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 2
8795 | Gorkha | Tanglichok | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 2
8796 | Gorkha | Tanglichok | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 2
8797 | Gorkha | Tanglichok | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 2
8798 | Gorkha | Tanglichok | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 2
8799 | Gorkha | Tanglichok | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 2
8800 | Gorkha | Tanglichok | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 2
8801 | Gorkha | Tanglichok | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Gandaki | 2
8802 | Gorkha | Thalajung | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 2
8803 | Gorkha | Thalajung | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 2
8804 | Gorkha | Thalajung | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 2
8805 | Gorkha | Thalajung | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 2
8806 | Gorkha | Thalajung | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 2
8807 | Gorkha | Thalajung | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 2
8808 | Gorkha | Thalajung | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 2
8809 | Gorkha | Thalajung | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 2
8810 | Gorkha | Thalajung | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees |  | Planned | 6 | 0 |  |  |  | Siranchok | 2
8811 | Gorkha | Palumtar N.P. | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 6
8812 | Gorkha | Palumtar N.P. | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 7
8813 | Gorkha | Palumtar N.P. | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 7
8814 | Gorkha | Palumtar N.P. | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 6
8815 | Gorkha | Palumtar N.P. | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 6
8816 | Gorkha | Palumtar N.P. | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 4
8817 | Gorkha | Palumtar N.P. | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 3
8818 | Gorkha | Palumtar N.P. | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 4
8819 | Gorkha | Palumtar N.P. | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 4
8820 | Gorkha | Palumtar N.P. | 10 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 5
8821 | Gorkha | Palumtar N.P. | 11 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 3
8822 | Gorkha | Palumtar N.P. | 12 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 2
8823 | Gorkha | Palumtar N.P. | 13 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 2
8824 | Gorkha | Bhumlichok | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 6
8825 | Gorkha | Bhumlichok | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 6
8826 | Gorkha | Bhumlichok | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 6
8827 | Gorkha | Bhumlichok | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 6
8828 | Gorkha | Bhumlichok | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 6
8829 | Gorkha | Bhumlichok | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 6
8830 | Gorkha | Bhumlichok | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 6
8831 | Gorkha | Bhumlichok | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 6
8832 | Gorkha | Bhumlichok | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 6
8833 | Gorkha | Chhoprak | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 5
8834 | Gorkha | Chhoprak | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 5
8835 | Gorkha | Chhoprak | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 5
8836 | Gorkha | Chhoprak | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 5
8837 | Gorkha | Chhoprak | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 5
8838 | Gorkha | Chhoprak | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 5
8839 | Gorkha | Chhoprak | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 4
8840 | Gorkha | Chhoprak | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 4
8841 | Gorkha | Chhoprak | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 4
8842 | Gorkha | Deurali | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 14
8843 | Gorkha | Deurali | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 14
8844 | Gorkha | Deurali | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 14
8845 | Gorkha | Deurali | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 14
8846 | Gorkha | Deurali | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 13
8847 | Gorkha | Deurali | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 13
8848 | Gorkha | Deurali | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 13
8849 | Gorkha | Deurali | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 13
8850 | Gorkha | Deurali | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 14
8851 | Gorkha | Dhuwakot | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 8
8852 | Gorkha | Dhuwakot | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 8
8853 | Gorkha | Dhuwakot | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 8
8854 | Gorkha | Dhuwakot | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 8
8855 | Gorkha | Dhuwakot | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 8
8856 | Gorkha | Dhuwakot | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 8
8857 | Gorkha | Dhuwakot | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 9
8858 | Gorkha | Dhuwakot | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 9
8859 | Gorkha | Dhuwakot | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 9
8860 | Gorkha | Gakhu | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 6
8861 | Gorkha | Gakhu | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 6
8862 | Gorkha | Gakhu | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 6
8863 | Gorkha | Gakhu | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 6
8864 | Gorkha | Gakhu | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 6
8865 | Gorkha | Gakhu | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 6
8866 | Gorkha | Gakhu | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 6
8867 | Gorkha | Gakhu | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 6
8868 | Gorkha | Gakhu | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 6
8869 | Gorkha | Ghairung | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 6
8870 | Gorkha | Ghairung | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 6
8871 | Gorkha | Ghairung | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 6
8872 | Gorkha | Ghairung | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 6
8873 | Gorkha | Ghairung | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 6
8874 | Gorkha | Ghairung | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 6
8875 | Gorkha | Ghairung | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 6
8876 | Gorkha | Ghairung | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 6
8877 | Gorkha | Ghairung | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 6
8878 | Gorkha | Ghyachok | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 1
8879 | Gorkha | Ghyachok | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 1
8880 | Gorkha | Ghyachok | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 1
8881 | Gorkha | Ghyachok | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 1
8882 | Gorkha | Ghyachok | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 1
8883 | Gorkha | Ghyachok | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 1
8884 | Gorkha | Ghyachok | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 1
8885 | Gorkha | Ghyachok | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 1
8886 | Gorkha | Ghyachok | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 1
8887 | Gorkha | Gorakha N.P. | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 6
8888 | Gorkha | Gorakha N.P. | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 7
8889 | Gorkha | Gorakha N.P. | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 6
8890 | Gorkha | Gorakha N.P. | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 5
8891 | Gorkha | Gorakha N.P. | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 7
8892 | Gorkha | Gorakha N.P. | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 8
8893 | Gorkha | Gorakha N.P. | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 8
8894 | Gorkha | Gorakha N.P. | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 9
8895 | Gorkha | Gorakha N.P. | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 10
8896 | Gorkha | Gorakha N.P. | 10 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 11
8897 | Gorkha | Gorakha N.P. | 11 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 12
8898 | Gorkha | Gorakha N.P. | 12 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 4
8899 | Gorkha | Gorakha N.P. | 13 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 4
8900 | Gorkha | Gorakha N.P. | 14 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 3
8901 | Gorkha | Gorakha N.P. | 15 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gorkha | 3
8902 | Gorkha | Gumda | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 5
8903 | Gorkha | Gumda | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 5
8904 | Gorkha | Gumda | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 5
8905 | Gorkha | Gumda | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 5
8906 | Gorkha | Gumda | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 5
8907 | Gorkha | Gumda | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 5
8908 | Gorkha | Gumda | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 5
8909 | Gorkha | Gumda | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 5
8910 | Gorkha | Gumda | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 5
8911 | Gorkha | Harmhi | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 3
8912 | Gorkha | Harmhi | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 3
8913 | Gorkha | Harmhi | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 3
8914 | Gorkha | Harmhi | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 3
8915 | Gorkha | Harmhi | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 3
8916 | Gorkha | Harmhi | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 3
8917 | Gorkha | Harmhi | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 3
8918 | Gorkha | Harmhi | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 3
8919 | Gorkha | Harmhi | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 3
8920 | Gorkha | Kashigaun | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 6
8921 | Gorkha | Kashigaun | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 6
8922 | Gorkha | Kashigaun | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 6
8923 | Gorkha | Kashigaun | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 6
8924 | Gorkha | Kashigaun | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 6
8925 | Gorkha | Kashigaun | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 6
8926 | Gorkha | Kashigaun | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 6
8927 | Gorkha | Kashigaun | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 6
8928 | Gorkha | Kashigaun | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 6
8929 | Gorkha | Kharibot | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 2
8930 | Gorkha | Kharibot | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 2
8931 | Gorkha | Kharibot | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 2
8932 | Gorkha | Kharibot | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 2
8933 | Gorkha | Kharibot | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 2
8934 | Gorkha | Kharibot | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 2
8935 | Gorkha | Kharibot | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 2
8936 | Gorkha | Kharibot | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 2
8937 | Gorkha | Kharibot | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Ajirkot | 2
8938 | Gorkha | Khoplang | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 2
8939 | Gorkha | Khoplang | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 2
8940 | Gorkha | Khoplang | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 2
8941 | Gorkha | Khoplang | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 1
8942 | Gorkha | Khoplang | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 1
8943 | Gorkha | Khoplang | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 1
8944 | Gorkha | Khoplang | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 1
8945 | Gorkha | Khoplang | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 1
8946 | Gorkha | Khoplang | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 1
8947 | Gorkha | Lapu | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 7
8948 | Gorkha | Lapu | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 7
8949 | Gorkha | Lapu | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 7
8950 | Gorkha | Lapu | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 7
8951 | Gorkha | Lapu | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 7
8952 | Gorkha | Lapu | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 7
8953 | Gorkha | Lapu | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 7
8954 | Gorkha | Lapu | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 7
8955 | Gorkha | Lapu | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Dharche | 7
8956 | Gorkha | Makaising | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 1
8957 | Gorkha | Makaising | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 1
8958 | Gorkha | Makaising | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 1
8959 | Gorkha | Makaising | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 1
8960 | Gorkha | Makaising | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 1
8961 | Gorkha | Makaising | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 1
8962 | Gorkha | Makaising | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 1
8963 | Gorkha | Makaising | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 1
8964 | Gorkha | Makaising | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 1
8965 | Gorkha | Manakamana | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 2
8966 | Gorkha | Manakamana | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 2
8967 | Gorkha | Manakamana | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 3
8968 | Gorkha | Manakamana | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 2
8969 | Gorkha | Manakamana | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 2
8970 | Gorkha | Manakamana | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 3
8971 | Gorkha | Manakamana | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 3
8972 | Gorkha | Manakamana | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 3
8973 | Gorkha | Manakamana | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 3
8974 | Gorkha | Manbu | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Aarughat | 2
8975 | Gorkha | Manbu | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Aarughat | 2
8976 | Gorkha | Manbu | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Aarughat | 2
8977 | Gorkha | Manbu | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Aarughat | 2
8978 | Gorkha | Manbu | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Aarughat | 1
8979 | Gorkha | Manbu | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Aarughat | 1
8980 | Gorkha | Manbu | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Aarughat | 1
8981 | Gorkha | Manbu | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Aarughat | 1
8982 | Gorkha | Manbu | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Aarughat | 1
8983 | Gorkha | Bhirkot | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 10
8984 | Gorkha | Bhirkot | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 10
8985 | Gorkha | Bhirkot | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 10
8986 | Gorkha | Bhirkot | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 10
8987 | Gorkha | Bhirkot | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 9
8988 | Gorkha | Bhirkot | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 10
8989 | Gorkha | Bhirkot | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 10
8990 | Gorkha | Bhirkot | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 9
8991 | Gorkha | Bhirkot | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Palungtar | 10
8992 | Gorkha | Taklung | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 4
8993 | Gorkha | Taklung | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 4
8994 | Gorkha | Taklung | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 4
8995 | Gorkha | Taklung | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 4
8996 | Gorkha | Taklung | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 5
8997 | Gorkha | Taklung | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 5
8998 | Gorkha | Taklung | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 5
8999 | Gorkha | Taklung | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 5
9000 | Gorkha | Taklung | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Sahid Lakhan | 5
9001 | Gorkha | Tanglichok | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 2
9002 | Gorkha | Tanglichok | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 2
9003 | Gorkha | Tanglichok | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 2
9004 | Gorkha | Tanglichok | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 2
9005 | Gorkha | Tanglichok | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 2
9006 | Gorkha | Tanglichok | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 2
9007 | Gorkha | Tanglichok | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 2
9008 | Gorkha | Tanglichok | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 2
9009 | Gorkha | Tanglichok | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Gandaki | 2
9010 | Gorkha | Thalajung | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 2
9011 | Gorkha | Thalajung | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 2
9012 | Gorkha | Thalajung | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 2
9013 | Gorkha | Thalajung | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 2
9014 | Gorkha | Thalajung | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 2
9015 | Gorkha | Thalajung | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 2
9016 | Gorkha | Thalajung | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 2
9017 | Gorkha | Thalajung | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 2
9018 | Gorkha | Thalajung | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions |  | Planned | 1 | 0 |  |  |  | Siranchok | 2
9019 | Gorkha | Bakrang | 1 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 20 | 10 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 1
9020 | Gorkha | Bakrang | 2 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 1
9021 | Gorkha | Bakrang | 3 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 1
9022 | Gorkha | Bakrang | 4 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 1
9023 | Gorkha | Bakrang | 5 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 1
9024 | Gorkha | Bakrang | 6 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 1
9025 | Gorkha | Bakrang | 7 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 1
9026 | Gorkha | Bakrang | 8 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 1
9027 | Gorkha | Bakrang | 9 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 1
9028 | Gorkha | Bhirkot | 1 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 20 | 10 | 2016-01-01 | 2018-12-31 |  | Palungtar | 10
9029 | Gorkha | Bhirkot | 2 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Palungtar | 10
9030 | Gorkha | Bhirkot | 3 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Palungtar | 10
9031 | Gorkha | Bhirkot | 4 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Palungtar | 10
9032 | Gorkha | Bhirkot | 5 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Palungtar | 9
9033 | Gorkha | Bhirkot | 6 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Palungtar | 10
9034 | Gorkha | Bhirkot | 7 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Palungtar | 10
9035 | Gorkha | Bhirkot | 8 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Palungtar | 9
9036 | Gorkha | Bhirkot | 9 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Palungtar | 10
9037 | Gorkha | Harmhi | 1 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9038 | Gorkha | Harmhi | 2 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9039 | Gorkha | Harmhi | 3 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9040 | Gorkha | Harmhi | 4 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 20 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9041 | Gorkha | Harmhi | 5 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9042 | Gorkha | Harmhi | 6 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9043 | Gorkha | Harmhi | 7 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9044 | Gorkha | Harmhi | 8 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9045 | Gorkha | Harmhi | 9 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9046 | Gorkha | Manakamana | 1 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 2
9047 | Gorkha | Manakamana | 2 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 2
9048 | Gorkha | Manakamana | 3 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 3
9049 | Gorkha | Manakamana | 4 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 2
9050 | Gorkha | Manakamana | 5 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 2
9051 | Gorkha | Manakamana | 6 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 3
9052 | Gorkha | Manakamana | 7 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 3
9053 | Gorkha | Manakamana | 8 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 3
9054 | Gorkha | Manakamana | 9 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 3
9055 | Gorkha | Shreenathkot | 1 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9056 | Gorkha | Shreenathkot | 2 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9057 | Gorkha | Shreenathkot | 3 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9058 | Gorkha | Shreenathkot | 4 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9059 | Gorkha | Shreenathkot | 5 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9060 | Gorkha | Shreenathkot | 6 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9061 | Gorkha | Shreenathkot | 7 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9062 | Gorkha | Shreenathkot | 8 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9063 | Gorkha | Shreenathkot | 9 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9064 | Gorkha | Thalajung | 1 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9065 | Gorkha | Thalajung | 2 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9066 | Gorkha | Thalajung | 3 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9067 | Gorkha | Thalajung | 4 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9068 | Gorkha | Thalajung | 5 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9069 | Gorkha | Thalajung | 6 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9070 | Gorkha | Thalajung | 7 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9071 | Gorkha | Thalajung | 8 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9072 | Gorkha | Thalajung | 9 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9073 | Gorkha | Warpak | 1 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Sulikot | 2
9074 | Gorkha | Warpak | 2 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Sulikot | 2
9075 | Gorkha | Warpak | 3 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Sulikot | 2
9076 | Gorkha | Warpak | 4 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Sulikot | 1
9077 | Gorkha | Warpak | 5 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Sulikot | 1
9078 | Gorkha | Warpak | 6 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Sulikot | 2
9079 | Gorkha | Warpak | 7 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Sulikot | 2
9080 | Gorkha | Warpak | 8 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Sulikot | 2
9081 | Gorkha | Warpak | 9 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Sulikot | 2
9082 | Gorkha | Warpak | 1 | NRCS | NRCS | BRC FL | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Sulikot | 2
9083 | Gorkha | Warpak | 2 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Sulikot | 2
9084 | Gorkha | Warpak | 3 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Sulikot | 2
9085 | Gorkha | Warpak | 4 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Sulikot | 1
9086 | Gorkha | Warpak | 5 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Sulikot | 1
9087 | Gorkha | Warpak | 6 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Sulikot | 2
9088 | Gorkha | Warpak | 7 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Sulikot | 2
9089 | Gorkha | Warpak | 8 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Sulikot | 2
9090 | Gorkha | Warpak | 9 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Sulikot | 2
9091 | Gorkha | Jaubari | 1 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Siranchok | 8
9092 | Gorkha | Jaubari | 2 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Siranchok | 8
9093 | Gorkha | Jaubari | 3 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Siranchok | 8
9094 | Gorkha | Jaubari | 4 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Siranchok | 8
9095 | Gorkha | Jaubari | 5 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Siranchok | 8
9096 | Gorkha | Jaubari | 6 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Siranchok | 8
9097 | Gorkha | Jaubari | 7 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Siranchok | 8
9098 | Gorkha | Jaubari | 8 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Siranchok | 8
9099 | Gorkha | Jaubari | 9 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Siranchok | 8
9100 | Gorkha | Shreenathkot | 1 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9101 | Gorkha | Shreenathkot | 2 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9102 | Gorkha | Shreenathkot | 3 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9103 | Gorkha | Shreenathkot | 4 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9104 | Gorkha | Shreenathkot | 5 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9105 | Gorkha | Shreenathkot | 6 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9106 | Gorkha | Shreenathkot | 7 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9107 | Gorkha | Shreenathkot | 8 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9108 | Gorkha | Shreenathkot | 9 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9109 | Gorkha | Thalajung | 1 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9110 | Gorkha | Thalajung | 2 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9111 | Gorkha | Thalajung | 3 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9112 | Gorkha | Thalajung | 4 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9113 | Gorkha | Thalajung | 5 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9114 | Gorkha | Thalajung | 6 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9115 | Gorkha | Thalajung | 7 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9116 | Gorkha | Thalajung | 8 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9117 | Gorkha | Thalajung | 9 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9118 | Gorkha | Gakhu | 1 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 6
9119 | Gorkha | Gakhu | 2 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 6
9120 | Gorkha | Gakhu | 3 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 6
9121 | Gorkha | Gakhu | 4 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 6
9122 | Gorkha | Gakhu | 5 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 6
9123 | Gorkha | Gakhu | 6 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 6
9124 | Gorkha | Gakhu | 7 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 6
9125 | Gorkha | Gakhu | 8 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 6
9126 | Gorkha | Gakhu | 9 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 6
9127 | Gorkha | Harmhi | 1 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9128 | Gorkha | Harmhi | 2 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9129 | Gorkha | Harmhi | 3 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9130 | Gorkha | Harmhi | 4 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9131 | Gorkha | Harmhi | 5 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9132 | Gorkha | Harmhi | 6 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9133 | Gorkha | Harmhi | 7 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9134 | Gorkha | Harmhi | 8 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9135 | Gorkha | Harmhi | 9 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9136 | Gorkha | Bhirkot | 1 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Palungtar | 10
9137 | Gorkha | Bhirkot | 2 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Palungtar | 10
9138 | Gorkha | Bhirkot | 3 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Palungtar | 10
9139 | Gorkha | Bhirkot | 4 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Palungtar | 10
9140 | Gorkha | Bhirkot | 5 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Palungtar | 9
9141 | Gorkha | Bhirkot | 6 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Palungtar | 10
9142 | Gorkha | Bhirkot | 7 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Palungtar | 10
9143 | Gorkha | Bhirkot | 8 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Palungtar | 9
9144 | Gorkha | Bhirkot | 9 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Palungtar | 10
9145 | Gorkha | Manakamana | 1 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 2
9146 | Gorkha | Manakamana | 2 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 2
9147 | Gorkha | Manakamana | 3 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 3
9148 | Gorkha | Manakamana | 4 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 2
9149 | Gorkha | Manakamana | 5 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 2
9150 | Gorkha | Manakamana | 6 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 3
9151 | Gorkha | Manakamana | 7 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 3
9152 | Gorkha | Manakamana | 8 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 3
9153 | Gorkha | Manakamana | 9 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Ongoing | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 3
9154 | Gorkha | Bakrang | 5 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 1
9155 | Gorkha | Bhirkot | 5 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-01-01 | 2018-12-31 |  | Palungtar | 9
9156 | Gorkha | Gakhu | 2 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 6
9157 | Gorkha | Harmhi | 3 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9158 | Gorkha | Jaubari | 9 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 8
9159 | Gorkha | Shreenathkot | 2 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9160 | Gorkha | Thalajung | 6 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9161 | Gorkha | Warpak | 1 | NRCS | NRCS | BRC FL | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees | Yes | Ongoing | 2 | 2 |  |  |  | Sulikot | 2
9162 | Gorkha | Manakamana | 5 | NRCS | NRCS | BRC FL | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 2
9163 | Gorkha | Bakrang | 5 | NRCS | NRCS | BRC FL | Reconstruction through contractors | Construction | Private house | Reconstruction of House | # of constructions | Yes | Ongoing | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 1
9164 | Gorkha | Bhirkot | 5 | NRCS | NRCS | BRC FL | Reconstruction through contractors | Construction | Private house | Reconstruction of House | # of constructions | Yes | Ongoing | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Palungtar | 9
9165 | Gorkha | Gakhu | 2 | NRCS | NRCS | BRC FL | Reconstruction through contractors | Construction | Private house | Reconstruction of House | # of constructions | Yes | Ongoing | 1 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 6
9166 | Gorkha | Harmhi | 3 | NRCS | NRCS | BRC FL | Reconstruction through contractors | Construction | Private house | Reconstruction of House | # of constructions | Yes | Ongoing | 1 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 3
9167 | Gorkha | Jaubari | 9 | NRCS | NRCS | BRC FL | Reconstruction through contractors | Construction | Private house | Reconstruction of House | # of constructions | Yes | Ongoing | 1 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 8
9168 | Gorkha | Shreenathkot | 2 | NRCS | NRCS | BRC FL | Reconstruction through contractors | Construction | Private house | Reconstruction of House | # of constructions | Yes | Ongoing | 1 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 7
9169 | Gorkha | Thalajung | 6 | NRCS | NRCS | BRC FL | Reconstruction through contractors | Construction | Private house | Reconstruction of House | # of constructions | Yes | Ongoing | 1 | 0 | 2016-01-01 | 2018-12-31 |  | Siranchok | 2
9170 | Gorkha | Manakamana | 5 | NRCS | NRCS | BRC FL | Reconstruction through contractors | Construction | Private house | Reconstruction of House | # of constructions | Yes | Ongoing | 1 | 0 | 2016-01-01 | 2018-12-31 |  | Sahid Lakhan | 2
9171 | Kavrepalanchok | Balting | 1 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT Curriculum | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 10
9172 | Kavrepalanchok | Balting | 2 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT Curriculum | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 10
9173 | Kavrepalanchok | Balting | 3 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT Curriculum | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 10
9174 | Kavrepalanchok | Balting | 4 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT Curriculum | # of trainees | Yes | Ongoing | 10 | 10 |  |  | To be verified | Roshi | 10
9175 | Kavrepalanchok | Balting | 5 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT Curriculum | # of trainees | Yes | Planned | 0 | 0 |  |  | To be verified | Roshi | 10
9176 | Kavrepalanchok | Balting | 6 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT Curriculum | # of trainees | Yes | Completed | 10 | 10 | 2017-05-05 | 2017-07-15 | To be verified | Roshi | 10
9177 | Kavrepalanchok | Balting | 7 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT Curriculum | # of trainees | Yes | Completed | 10 | 10 | 2017-04-16 | 2017-06-14 | To be verified | Roshi | 10
9178 | Kavrepalanchok | Balting | 8 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT Curriculum | # of trainees | Yes | Ongoing | 0 | 0 |  |  | To be verified | Roshi | 10
9179 | Kavrepalanchok | Balting | 9 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT Curriculum | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Roshi | 10
9180 | Kavrepalanchok | BaluwapatiDeupur | 1 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT Curriculum | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Mandandeupur | 1
9181 | Kavrepalanchok | BaluwapatiDeupur | 2 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT Curriculum | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Mandandeupur | 2
9182 | Kavrepalanchok | BaluwapatiDeupur | 3 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT Curriculum | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mandandeupur | 1
9183 | Kavrepalanchok | BaluwapatiDeupur | 4 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-14 | 2017-05-08 | Verified | Mandandeupur | 2
9184 | Kavrepalanchok | BaluwapatiDeupur | 5 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  | Verified | Mandandeupur | 1
9185 | Kavrepalanchok | BaluwapatiDeupur | 6 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 |  |  | Verified | Mandandeupur | 1
9186 | Kavrepalanchok | BaluwapatiDeupur | 7 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-05 | 2017-03-29 | Verified | Mandandeupur | 2
9187 | Kavrepalanchok | BaluwapatiDeupur | 8 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2017-03-23 | 2017-05-13 | Verified | Mandandeupur | 2
9188 | Kavrepalanchok | BaluwapatiDeupur | 9 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-13 | 2016-02-18 | Total 36 masons were trained in this (13-18 Feb 2016) training, in which 11 masons from other district | Mandandeupur | 2
9189 | Kavrepalanchok | BaluwapatiDeupur | 9 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-05 | 2017-04-29 | Verified | Mandandeupur | 2
9190 | Kavrepalanchok | BanakhuChor | 1 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 6
9191 | Kavrepalanchok | BanakhuChor | 2 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 6
9192 | Kavrepalanchok | BanakhuChor | 3 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 6
9193 | Kavrepalanchok | BanakhuChor | 4 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-03-01 | 2017-05-01 | Verified | Mahabharat | 6
9194 | Kavrepalanchok | BanakhuChor | 5 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-03-01 | 2017-05-01 | Verified | Mahabharat | 6
9195 | Kavrepalanchok | BanakhuChor | 6 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 6
9196 | Kavrepalanchok | BanakhuChor | 7 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  | Verified | Mahabharat | 7
9197 | Kavrepalanchok | BanakhuChor | 8 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  | Verified | Mahabharat | 7
9198 | Kavrepalanchok | BanakhuChor | 9 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 7
9199 | Kavrepalanchok | Banepa N.P. | 3 | CL | CL | VG | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT Short training | # of trainees | Yes | Completed | 18 | 18 | 2016-08-15 | 2016-10-12 | Was funded as part of Corporate CSR activity - Centum didn't report to any local authorities | Banepa | 9
9200 | Kavrepalanchok | Banepa N.P. | 6 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-13 | 2016-02-18 |  | Banepa | 8
9201 | Kavrepalanchok | Banepa N.P. | 9 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-13 | 2016-02-18 |  | Banepa | 7
9202 | Kavrepalanchok | Banepa N.P. | 10 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-13 | 2016-02-18 |  | Banepa | 7
9203 | Kavrepalanchok | BekhsimleDhartigaun | 1 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-23 | 2017-06-05 | To be verified | Bhumlu | 3
9204 | Kavrepalanchok | BekhsimleDhartigaun | 2 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 3
9205 | Kavrepalanchok | BekhsimleDhartigaun | 3 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 3
9206 | Kavrepalanchok | BekhsimleDhartigaun | 4 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-19 | 2017-06-08 | To be verified | Bhumlu | 3
9207 | Kavrepalanchok | BekhsimleDhartigaun | 5 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 3
9208 | Kavrepalanchok | BekhsimleDhartigaun | 6 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 3
9209 | Kavrepalanchok | BekhsimleDhartigaun | 7 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  | To be verified | Bhumlu | 3
9210 | Kavrepalanchok | BekhsimleDhartigaun | 8 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2017-04-04 | 2017-06-15 |  | Bhumlu | 3
9211 | Kavrepalanchok | BekhsimleDhartigaun | 9 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Bhumlu | 3
9212 | Kavrepalanchok | Bhimkhori | 1 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-04 | 2017-05-01 |  | Roshi | 11
9213 | Kavrepalanchok | Bhimkhori | 2 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 11
9214 | Kavrepalanchok | Bhimkhori | 3 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-30 | 2017-06-30 |  | Roshi | 11
9215 | Kavrepalanchok | Bhimkhori | 4 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-10 | 2017-04-06 |  | Roshi | 11
9216 | Kavrepalanchok | Bhimkhori | 5 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 11
9217 | Kavrepalanchok | Bhimkhori | 6 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-18 | 2017-05-10 |  | Roshi | 11
9218 | Kavrepalanchok | Bhimkhori | 7 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 12
9219 | Kavrepalanchok | Bhimkhori | 8 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-10 | 2017-05-09 |  | Roshi | 12
9220 | Kavrepalanchok | Bhimkhori | 9 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-16 | 2017-06-17 |  | Roshi | 12
9221 | Kavrepalanchok | Bhumlutar | 1 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 1 | 1 | 2015-11-02 | 2015-11-06 | MToT training, Implementing Partner:- Nangshal Association | Bhumlu | 8
9222 | Kavrepalanchok | Bhumlutar | 1 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 8
9223 | Kavrepalanchok | Bhumlutar | 2 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 2 | 2 | 2015-11-02 | 2015-11-06 |  | Bhumlu | 8
9224 | Kavrepalanchok | Bhumlutar | 2 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 8
9225 | Kavrepalanchok | Bhumlutar | 3 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2015-11-02 | 2015-11-06 |  | Bhumlu | 8
9226 | Kavrepalanchok | Bhumlutar | 3 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 8
9227 | Kavrepalanchok | Bhumlutar | 4 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06 |  | Bhumlu | 8
9228 | Kavrepalanchok | Bhumlutar | 4 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 8
9229 | Kavrepalanchok | Bhumlutar | 5 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 11 | 11 | 2015-11-02 | 2015-11-06 |  | Bhumlu | 8
9230 | Kavrepalanchok | Bhumlutar | 5 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 8
9231 | Kavrepalanchok | Bhumlutar | 6 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-03-30 | 2017-05-17 | Verified | Bhumlu | 8
9232 | Kavrepalanchok | Bhumlutar | 7 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06 |  | Bhumlu | 8
9233 | Kavrepalanchok | Bhumlutar | 7 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 8
9234 | Kavrepalanchok | Bhumlutar | 8 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 | 2015-11-02 | 2015-11-06 |  | Bhumlu | 8
9235 | Kavrepalanchok | Bhumlutar | 8 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2017-03-23 | 2017-05-17 | Verified | Bhumlu | 8
9236 | Kavrepalanchok | Bhumlutar | 9 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Bhumlu | 8
9237 | kavrepalanchok | Birtadeurali | 7 | NYF | NYF | NYF-US | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 25 | 20 | 2016-04-14 | 2016-04-20 | The tools distributed in the community for common use to Social leader and Chairperson of Bachheshwor Primary School in Birta Deurali VDC. | Chaurideurali | 8
9238 | Kavrepalanchok | Birtadeurali | 7 | NYF | NYF | NYF-US | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-04-15 | 2016-05-15 | Lead Engineer | Chaurideurali | 8
9239 | Kavrepalanchok | Birtadeurali | 7 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 26 | 20 | 2016-04-14 | 2016-04-20 | Reconstruction Manager | Chaurideurali | 8
9240 | Kavrepalanchok | BoldeFediche | 5 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-03-28 | 2016-04-03 |  | Temal | 4
9241 | Kavrepalanchok | BoldeFediche | 6 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-28 | 2016-04-03 |  | Temal | 4
9242 | Kavrepalanchok | BoldeFediche | 7 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-28 | 2016-04-03 |  | Temal | 4
9243 | Kavrepalanchok | BoldeFediche | 8 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-03-28 | 2016-04-03 |  | Temal | 4
9244 | Kavrepalanchok | BoldeFediche | 9 | NYF | NYF | NYF-US | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 25 | 24 | 2016-05-20 | 2016-05-20 | The tools distributed in the community for common use to Bolde Vikash Samaj in Bolde Fediche VDC kavre | Temal | 4
9245 | Kavrepalanchok | BoldeFediche | 9 | NYF | NYF | NYF-US | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-28 | 2016-05-05 |  | Temal | 4
9246 | Kavrepalanchok | BoldeFediche | 9 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-28 | 2016-04-03 |  | Temal | 4
9247 | Kavrepalanchok | Budhakhani | 1 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-01 | 2017-05-01 | Verified | Mahabharat | 5
9248 | Kavrepalanchok | Budhakhani | 2 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 4
9249 | Kavrepalanchok | Budhakhani | 3 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 4
9250 | Kavrepalanchok | Budhakhani | 4 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-01 | 2017-05-01 | Verified | Mahabharat | 4
9251 | Kavrepalanchok | Budhakhani | 5 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Mahabharat | 4
9252 | Kavrepalanchok | Budhakhani | 6 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Mahabharat | 4
9253 | Kavrepalanchok | Budhakhani | 7 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-10 | 2016-08-16 |  | Mahabharat | 5
9254 | Kavrepalanchok | Budhakhani | 7 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 5
9255 | Kavrepalanchok | Budhakhani | 8 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2017-03-10 | 2017-05-10 |  | Mahabharat | 5
9256 | Kavrepalanchok | Budhakhani | 9 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  | one Completed one ongoing verified. | Mahabharat | 5
9257 | Kavrepalanchok | ChalalGaneshsthan | 1 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-09-12 | 2016-09-18 |  | Bethanchowk | 4
9258 | Kavrepalanchok | ChalalGaneshsthan | 1 | BC | ARSOW-N | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-07 | 2016-05-13 |  | Bethanchowk | 4
9259 | Kavrepalanchok | ChalalGaneshsthan | 2 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-09-12 | 2016-09-18 |  | Bethanchowk | 4
9260 | Kavrepalanchok | ChalalGaneshsthan | 3 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-12 | 2016-09-18 |  | Bethanchowk | 4
9261 | Kavrepalanchok | ChalalGaneshsthan | 4 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-09-12 | 2016-09-18 |  | Bethanchowk | 4
9262 | Kavrepalanchok | ChalalGaneshsthan | 5 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-12 | 2016-09-18 |  | Bethanchowk | 4
9263 | Kavrepalanchok | ChalalGaneshsthan | 6 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-12 | 2016-09-18 |  | Bethanchowk | 4
9264 | Kavrepalanchok | ChalalGaneshsthan | 7 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-09-12 | 2016-09-18 |  | Bethanchowk | 4
9265 | Kavrepalanchok | ChalalGaneshsthan | 8 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-12 | 2016-09-18 |  | Bethanchowk | 4
9266 | Kavrepalanchok | ChalalGaneshsthan | 9 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-12 | 2016-09-18 |  | Bethanchowk | 4
9267 | Kavrepalanchok | Choubas | 2 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-03-08 | 2017-04-28 | Verified | Bhumlu | 4
9268 | Kavrepalanchok | Choubas | 3 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2017-03-15 | 2017-05-09 | Verified | Bhumlu | 4
9269 | Kavrepalanchok | Choubas | 4 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 20 | 20 |  |  |  | Bhumlu | 4
9270 | Kavrepalanchok | Choubas | 5 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-09 | 2017-06-01 | Verified | Bhumlu | 4
9271 | Kavrepalanchok | Choubas | 6 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 4
9272 | Kavrepalanchok | Choubas | 7 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 4
9273 | Kavrepalanchok | Choubas | 8 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 4
9274 | Kavrepalanchok | Choubas | 9 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 4
9275 | Kavrepalanchok | Chyamrangbesi | 1 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-09-21 | 2016-09-27 |  | Bethanchowk | 1
9276 | Kavrepalanchok | Chyamrangbesi | 1 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bethanchowk | 1
9277 | Kavrepalanchok | Chyamrangbesi | 2 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-09-21 | 2016-09-27 |  | Bethanchowk | 1
9278 | Kavrepalanchok | Chyamrangbesi | 2 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Bethanchowk | 1
9279 | Kavrepalanchok | Chyamrangbesi | 3 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-09-21 | 2016-09-27 |  | Bethanchowk | 1
9280 | Kavrepalanchok | Chyamrangbesi | 3 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bethanchowk | 1
9281 | Kavrepalanchok | Chyamrangbesi | 4 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-09-21 | 2016-09-27 |  | Bethanchowk | 1
9282 | Kavrepalanchok | Chyamrangbesi | 4 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bethanchowk | 1
9283 | Kavrepalanchok | Chyamrangbesi | 5 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-09-21 | 2016-09-27 |  | Bethanchowk | 1
9284 | Kavrepalanchok | Chyamrangbesi | 5 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  | Verified | Bethanchowk | 1
9285 | Kavrepalanchok | Chyamrangbesi | 6 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-21 | 2016-09-27 |  | Bethanchowk | 1
9286 | Kavrepalanchok | Chyamrangbesi | 6 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Bethanchowk | 1
9287 | Kavrepalanchok | Chyamrangbesi | 7 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-21 | 2016-09-27 |  | Bethanchowk | 1
9288 | Kavrepalanchok | Chyamrangbesi | 7 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bethanchowk | 1
9289 | Kavrepalanchok | Chyamrangbesi | 8 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-21 | 2016-09-27 |  | Bethanchowk | 1
9290 | Kavrepalanchok | Chyamrangbesi | 8 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bethanchowk | 1
9291 | Kavrepalanchok | Chyamrangbesi | 9 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-21 | 2016-09-27 |  | Bethanchowk | 1
9292 | Kavrepalanchok | Chyamrangbesi | 9 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bethanchowk | 1
9293 | Kavrepalanchok | ChyasingKharka | 1 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-09-14 | 2016-09-20 |  | Bethanchowk | 5
9294 | Kavrepalanchok | ChyasingKharka | 2 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-14 | 2016-09-20 |  | Bethanchowk | 5
9295 | Kavrepalanchok | ChyasingKharka | 3 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-14 | 2016-09-20 |  | Bethanchowk | 5
9296 | Kavrepalanchok | ChyasingKharka | 4 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-14 | 2016-09-20 |  | Bethanchowk | 5
9297 | Kavrepalanchok | ChyasingKharka | 5 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20 |  | Bethanchowk | 5
9298 | Kavrepalanchok | ChyasingKharka | 6 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20 |  | Bethanchowk | 5
9299 | Kavrepalanchok | ChyasingKharka | 7 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-14 | 2016-09-20 |  | Bethanchowk | 5
9300 | Kavrepalanchok | Dandagaun | 1 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Khanikhola | 4
9301 | Kavrepalanchok | Dandagaun | 2 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Khanikhola | 3
9302 | Kavrepalanchok | Dandagaun | 3 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 20 | 20 |  |  | Verified | Khanikhola | 4
9303 | Kavrepalanchok | Dandagaun | 4 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Khanikhola | 3
9304 | Kavrepalanchok | Dandagaun | 5 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 30 | 30 |  |  | Verified | Khanikhola | 3
9305 | Kavrepalanchok | Dandagaun | 6 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Khanikhola | 3
9306 | Kavrepalanchok | Dandagaun | 7 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Khanikhola | 3
9307 | Kavrepalanchok | Dandagaun | 8 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 30 | 30 |  |  | Verified | Khanikhola | 4
9308 | Kavrepalanchok | Dandagaun | 9 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 30 | 30 |  |  | Verified | Khanikhola | 4
9309 | Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 25 | 25 | 2016-09-07 | 2016-09-13 | Previous Methinkot vdc - Our plan is to conduct 8 mason training and 25 mason in each training | Namobuddha | 1
9310 | Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | NCRS | NCRS | SP | Reconstruction through contractors | Construction | Private house | Model house smc 1.1 | # of constructions | Yes | Completed | 1 | 1 | 2016-10-20 | 2016-12-31 |  | Namobuddha | 1
9311 | Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | NCRS | NCRS | SP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-08-17 | 2016-12-31 | Previous Methinkot vdc - 1 model houses per 3 mason training | Namobuddha | 1
9312 | Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 29 | 29 | 2016-09-07 | 2016-09-13 | Previous Methinkot vdc - Our plan is to conduct 8 mason training and 25 mason in each training | Namobuddha | 1
9313 | Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok | Namobuddha | 1
9314 | Kavrepalanchok | Dapcha Kashikhand N.P. | 2 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 31 | 31 | 2016-09-21 | 2016-09-27 |  | Namobuddha | 2
9315 | Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-15 | 2016-06-21 |  | Namobuddha | 1
9316 | Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-07-07 | 2016-07-13 |  | Namobuddha | 1
9317 | Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-08-10 | 2016-08-16 |  | Namobuddha | 1
9318 | Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31 |  | Namobuddha | 1
9319 | Kavrepalanchok | Dapcha Kashikhand N.P. | 2 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 33 | 33 | 2016-09-21 | 2016-09-27 |  | Namobuddha | 2
9320 | Kavrepalanchok | Dapcha Kashikhand N.P. | 3 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-02-14 | 2017-02-21 |  | Namobuddha | 2
9321 | Kavrepalanchok | Dapcha Kashikhand N.P. | 2 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok | Namobuddha | 2
9322 | Kavrepalanchok | Dapcha Kashikhand N.P. | 4 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 2 | 2 | 2016-10-19 | 2016-10-25 |  | Namobuddha | 3
9323 | Kavrepalanchok | Dapcha Kashikhand N.P. | 2 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-15 | 2016-06-21 |  | Namobuddha | 2
9324 | Kavrepalanchok | Dapcha Kashikhand N.P. | 2 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-07 | 2016-07-13 |  | Namobuddha | 2
9325 | Kavrepalanchok | Dapcha Kashikhand N.P. | 2 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-08-10 | 2016-08-16 |  | Namobuddha | 2
9326 | Kavrepalanchok | Dapcha Kashikhand N.P. | 2 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31 |  | Namobuddha | 2
9327 | Kavrepalanchok | Dapcha Kashikhand N.P. | 4 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 42 | 42 | 2016-11-02 |  |  | Namobuddha | 3
9328 | Kavrepalanchok | Dapcha Kashikhand N.P. | 3 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-13 | 2016-02-18 |  | Namobuddha | 2
9329 | Kavrepalanchok | Dapcha Kashikhand N.P. | 3 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok | Namobuddha | 2
9330 | Kavrepalanchok | Dapcha Kashikhand N.P. | 4 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-10-19 | 2016-10-25 |  | Namobuddha | 3
9331 | Kavrepalanchok | Dapcha Kashikhand N.P. | 3 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-15 | 2016-06-21 |  | Namobuddha | 2
9332 | Kavrepalanchok | Dapcha Kashikhand N.P. | 3 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-07-07 | 2016-07-13 |  | Namobuddha | 2
9333 | Kavrepalanchok | Dapcha Kashikhand N.P. | 3 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-08-10 | 2016-08-16 |  | Namobuddha | 2
9334 | Kavrepalanchok | Dapcha Kashikhand N.P. | 3 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31 |  | Namobuddha | 2
9335 | Kavrepalanchok | Dapcha Kashikhand N.P. | 5 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 13 | 13 | 2016-10-19 | 2016-10-25 |  | Namobuddha | 3
9336 | Kavrepalanchok | Dapcha Kashikhand N.P. | 5 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-10-19 | 2016-10-25 |  | Namobuddha | 3
9337 | Kavrepalanchok | Dapcha Kashikhand N.P. | 4 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok | Namobuddha | 3
9338 | Kavrepalanchok | Dapcha Kashikhand N.P. | 6 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 4 | 4 | 2016-10-19 | 2016-10-25 |  | Namobuddha | 4
9339 | Kavrepalanchok | Dapcha Kashikhand N.P. | 6 | NCRS | NCRS | SP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-08-17 | 2016-12-31 |  | Namobuddha | 4
9340 | Kavrepalanchok | Dapcha Kashikhand N.P. | 4 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-15 | 2016-06-21 |  | Namobuddha | 3
9341 | Kavrepalanchok | Dapcha Kashikhand N.P. | 4 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-07-07 | 2016-07-13 |  | Namobuddha | 3
9342 | Kavrepalanchok | Dapcha Kashikhand N.P. | 4 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-08-10 | 2016-08-16 |  | Namobuddha | 3
9343 | Kavrepalanchok | Dapcha Kashikhand N.P. | 4 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-08-25 | 2016-08-31 |  | Namobuddha | 3
9344 | Kavrepalanchok | Dapcha Kashikhand N.P. | 6 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-10-19 | 2016-10-25 |  | Namobuddha | 4
9345 | Kavrepalanchok | Dapcha Kashikhand N.P. | 7 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 16 | 16 | 2016-10-19 | 2016-10-25 |  | Namobuddha | 6
9346 | Kavrepalanchok | Dapcha Kashikhand N.P. | 5 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok | Namobuddha | 3
9347 | Kavrepalanchok | Dapcha Kashikhand N.P. | 7 | NCRS | NCRS | SP | Reconstruction through contractors | Construction | Private house | Model house smc 1.1 | # of constructions | Yes | Completed | 1 | 1 | 2016-10-20 | 2016-12-31 |  | Namobuddha | 6
9348 | Kavrepalanchok | Dapcha Kashikhand N.P. | 5 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-15 | 2016-06-21 |  | Namobuddha | 3
9349 | Kavrepalanchok | Dapcha Kashikhand N.P. | 5 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-07-07 | 2016-07-13 |  | Namobuddha | 3
9350 | Kavrepalanchok | Dapcha Kashikhand N.P. | 5 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31 |  | Namobuddha | 3
9351 | Kavrepalanchok | Dapcha Kashikhand N.P. | 7 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 23 | 23 | 2016-10-19 | 2016-10-25 |  | Namobuddha | 6
9352 | Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 1 | 1 | 2016-10-19 | 2016-10-25 |  | Namobuddha | 7
9353 | Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | NCRS | NCRS | SP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 | 2016-08-17 | 2016-12-31 |  | Namobuddha | 7
9354 | Kavrepalanchok | Dapcha Kashikhand N.P. | 6 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-13 | 2016-02-18 |  | Namobuddha | 4
9355 | Kavrepalanchok | Dapcha Kashikhand N.P. | 6 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok | Namobuddha | 4
9356 | Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-10-19 | 2016-10-25 |  | Namobuddha | 7
9357 | Kavrepalanchok | Dapcha Kashikhand N.P. | 6 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-07-07 | 2016-07-13 |  | Namobuddha | 4
9358 | Kavrepalanchok | Dapcha Kashikhand N.P. | 6 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-08-10 | 2016-08-16 |  | Namobuddha | 4
9359 | Kavrepalanchok | Dapcha Kashikhand N.P. | 6 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-08-25 | 2016-08-31 |  | Namobuddha | 4
9360 | Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 57 | 57 | 2016-11-15 | 2016-11-21 |  | Namobuddha | 7
9361 | Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | NCRS | NCRS | SP | Reconstruction through contractors | Construction | Private house | Model house smc 1.1 | # of constructions | Yes | Ongoing | 1 | 1 | 2016-02-07 |  |  | Namobuddha | 7
9362 | Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 42 | 42 | 2016-12-07 |  |  | Namobuddha | 7
9363 | Kavrepalanchok | Dapcha Kashikhand N.P. | 7 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-13 | 2016-02-18 |  | Namobuddha | 6
9364 | Kavrepalanchok | Dapcha Kashikhand N.P. | 7 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok | Namobuddha | 6
9365 | Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 69 | 69 | 2016-11-15 | 2016-11-21 |  | Namobuddha | 7
9366 | Kavrepalanchok | Dapcha Kashikhand N.P. | 7 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-07-07 | 2016-07-13 |  | Namobuddha | 6
9367 | Kavrepalanchok | Dapcha Kashikhand N.P. | 7 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-10 | 2016-08-16 |  | Namobuddha | 6
9368 | Kavrepalanchok | Dapcha Kashikhand N.P. | 7 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-08-25 | 2016-08-31 |  | Namobuddha | 6
9369 | Kavrepalanchok | Dapcha Kashikhand N.P. | 1,2 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 36 | 36 | 2016-07-13 |  | Ward wise data is not received | Namobuddha | 1
9370 | Kavrepalanchok | Dapcha Kashikhand N.P. | 5,6 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 47 | 47 | 2016-08-17 |  | Ward wise data is not received | Namobuddha | 4
9371 | Kavrepalanchok | Dapcha Kashikhand N.P. | 7,6 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 35 | 35 | 2016-09-14 |  | Ward wise data is not received | Namobuddha | 8
9372 | Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-13 | 2016-02-18 |  | Namobuddha | 7
9373 | Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok | Namobuddha | 7
9374 | Kavrepalanchok | Dapcha Kashikhand N.P. | 8,3 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 35 | 35 | 2016-08-10 |  | Ward wise data is not received | Namobuddha | 7
9375 | Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-15 | 2016-06-21 |  | Namobuddha | 7
9376 | Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-07-07 | 2016-07-13 |  | Namobuddha | 7
9377 | Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-08-10 | 2016-08-16 |  | Namobuddha | 7
9378 | Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-08-25 | 2016-08-31 |  | Namobuddha | 7
9379 | Kavrepalanchok | Dapcha Kashikhand N.P. |  | NCRS | NCRS | SP | Others | Others | (Please specify in Activity Detail) | Previous Methainkot vdc - 1 training for water user committie | # of trainees | Yes | Planned | 1 | 0 | 2016-05-01 | 2016-12-31 |  | Namobuddha | 10
9380 | Kavrepalanchok | Dapcha Kashikhand N.P. |  | NCRS | NCRS | SP | Others | Others | (Please specify in Activity Detail) | Prrvious Methainkot vdc- 1 sign bord with Built Back Safer ( 10 Key Messaged) in each 9 wards | # of trainees | Yes | Planned | 8 | 0 | 2016-05-01 | 2016-12-31 |  | Namobuddha | 10
9381 | Kavrepalanchok | Dapcha Kashikhand N.P. |  | NCRS | NCRS | SP | Technical Assistance | Household drinking water schemes | Household drinking water schemes |  | # of households | Yes | Planned | 1 | 0 | 2016-05-01 | 2016-12-31 | Detail data yet to come (Previous Methinkot vdc - Rehabilitation of community water supply system - 1 community water supply system in Methinkot VDC) | Namobuddha | 10
9382 | Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok | Namobuddha | 7
9383 | Kavrepalanchok | Dapcha Kashikhand N.P. |  | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 51 | 0 | 2016-11-15 | 2016-11-21 |  | Namobuddha | 10
9384 | Kavrepalanchok | RyaleBhir | 1 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 35 | 35 | 2016-08-29 |  |  | Panauti | 1
9385 | Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-15 | 2016-06-21 |  | Namobuddha | 7
9386 | Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-07-07 | 2016-07-13 |  | Namobuddha | 7
9387 | Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-10 | 2016-08-16 |  | Namobuddha | 7
9388 | Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31 |  | Namobuddha | 7
9389 | Kavrepalanchok | Dapcha Kashikhand N.P. | 10 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok | Namobuddha | 10
9390 | Kavrepalanchok | Dapcha Kashikhand N.P. | 10 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-07-07 | 2016-07-13 |  | Namobuddha | 10
9391 | Kavrepalanchok | Dapcha Kashikhand N.P. | 10 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-10 | 2016-08-16 |  | Namobuddha | 10
9392 | Kavrepalanchok | Dapcha Kashikhand N.P. | 11 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok | Namobuddha | 10
9393 | Kavrepalanchok | Dapcha Kashikhand N.P. | 12 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok | Namobuddha | 9
9394 | Kavrepalanchok | Dapcha Kashikhand N.P. | 12 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-07-07 | 2016-07-13 |  | Namobuddha | 9
9395 | Kavrepalanchok | Dapcha Kashikhand N.P. | 13 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok | Namobuddha | 9
9396 | Kavrepalanchok | Dapcha Kashikhand N.P. | 13 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31 |  | Namobuddha | 9
9397 | Kavrepalanchok | Dapcha Kashikhand N.P. | 14 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok | Namobuddha | 8
9398 | Kavrepalanchok | Dapcha Kashikhand N.P. | 14 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-15 | 2016-06-21 |  | Namobuddha | 8
9399 | Kavrepalanchok | Dapcha Kashikhand N.P. | 14 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31 |  | Namobuddha | 8
9400 | Kavrepalanchok | Dapcha Kashikhand N.P. | 15 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-10 | 2016-03-16 | By DUDBC Kavrepalanchok | Namobuddha | 8
9401 | Kavrepalanchok | RyaleBhir | 2 | NCRS | NCRS | SP | Reconstruction through contractors | Construction | Private house | Model house smc 1.1 | # of constructions | Yes | Ongoing | 1 | 1 | 2016-02-07 |  |  | Panauti | 1
9402 | Kavrepalanchok | RyaleBhir | 2 | NCRS | NCRS | SP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2016-08-17 | 2016-12-31 |  | Panauti | 1
9403 | Kavrepalanchok | RyaleBhir | 3 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 17 | 17 | 2016-12-06 | 2016-12-12 | Ryale vdc - Our plan is to conduct 8 mason training and 25 mason in each training | Panauti | 1
9404 | Kavrepalanchok | RyaleBhir | 3 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 17 | 2016-12-06 | 2016-12-12 | Ryale vdc - Our plan is to conduct 8 mason training and 25 mason in each training | Panauti | 1
9405 | Kavrepalanchok | RyaleBhir | 4 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 63 | 63 | 2016-11-08 | 2016-11-14 |  | Panauti | 1
9406 | Kavrepalanchok | RyaleBhir | 4 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 38 | 38 | 2016-10-19 |  |  | Panauti | 1
9407 | Kavrepalanchok | RyaleBhir | 4 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 63 | 63 | 2016-11-08 | 2016-11-14 |  | Panauti | 1
9408 | Kavrepalanchok | RyaleBhir | 5 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 31 | 31 | 2016-10-22 | 2016-10-28 |  | Panauti | 1
9409 | Kavrepalanchok | Devitar | 1 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-07 | 2017-06-02 | Verified | Dhulikhel | 1
9410 | Kavrepalanchok | Devitar | 2 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-08 | 2017-05-13 | Verified | Dhulikhel | 1
9411 | Kavrepalanchok | Devitar | 3 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Dhulikhel | 1
9412 | Kavrepalanchok | Devitar | 4 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-07 | 2017-06-02 | Verified | Banepa | 3
9413 | Kavrepalanchok | Devitar | 5 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Banepa | 3
9414 | Kavrepalanchok | Devitar | 6 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-11 | 2017-05-12 | Verified | Dhulikhel | 1
9415 | Kavrepalanchok | Devitar | 7 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-21 | 2017-04-15 | Verified | Dhulikhel | 1
9416 | Kavrepalanchok | Devitar | 8 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Dhulikhel | 1
9417 | Kavrepalanchok | Devitar | 9 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Dhulikhel | 1
9418 | Kavrepalanchok | Dhunkharka | 1 | BC | ARSOW-N | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-07 | 2016-05-13 |  | Bethanchowk | 3
9419 | Kavrepalanchok | Dhunkharka | 2 | BC | ARSOW-N | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 341 | 341 | 2016-03-23 | 2016-03-24 |  | Bethanchowk | 3
9420 | Kavrepalanchok | Dhunkharka | 4 | BC | ARSOW-N | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 204 | 204 | 2016-03-26 | 2016-03-26 |  | Bethanchowk | 3
9421 | Kavrepalanchok | Dhunkharka | 4 | BC | ARSOW-N | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-07 | 2016-05-13 |  | Bethanchowk | 3
9422 | Kavrepalanchok | Dhunkharka | 6 | BC | ARSOW-N | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 142 | 142 | 2016-03-25 | 2016-03-25 |  | Bethanchowk | 2
9423 | Kavrepalanchok | Dhunkharka | 6 | BC | ARSOW-N | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-07 | 2016-05-13 |  | Bethanchowk | 2
9424 | Kavrepalanchok | Dhunkharka | 7 | BC | ARSOW-N | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 111 | 111 | 2016-03-24 | 2016-03-24 |  | Bethanchowk | 2
9425 | Kavrepalanchok | Dhunkharka | 7 | BC | ARSOW-N | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-07 | 2016-05-13 |  | Bethanchowk | 2
9426 | Kavrepalanchok | Dhunkharka | 8 | BC | ARSOW-N | BC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-05-24 | 2016-08-12 | Community building | Bethanchowk | 2
9427 | Kavrepalanchok | Dhunkharka | 8 | BC | ARSOW-N | BC | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 |  |  | 3 Technical resource center | Bethanchowk | 2
9428 | Kavrepalanchok | Dhunkharka | 8 | BC | ARSOW-N | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 326 | 326 | 2016-03-25 | 2016-03-25 |  | Bethanchowk | 2
9429 | Kavrepalanchok | Dhunkharka | 8 | BC | ARSOW-N | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-07 | 2016-05-13 |  | Bethanchowk | 2
9430 | Kavrepalanchok | Dhunkharka | 9 | BC | ARSOW-N | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 180 | 180 | 2016-03-26 | 2016-03-26 |  | Bethanchowk | 2
9431 | Kavrepalanchok | Dhunkharka | 9 | BC | ARSOW-N | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-07 | 2016-05-13 |  | Bethanchowk | 2
9432 | Kavrepalanchok | Dhunkharka |  | BC | ARSOW-N | BC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 | 2017-03-01 |  | Ward not fixed yet (planned for March 2017) | Bethanchowk | 3
9433 | Kavrepalanchok | Falatebhumlu | 1 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 7
9434 | Kavrepalanchok | Falatebhumlu | 2 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  | Verified | Bhumlu | 7
9435 | Kavrepalanchok | Falatebhumlu | 3 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 7
9436 | Kavrepalanchok | Falatebhumlu | 4 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 7
9437 | Kavrepalanchok | Falatebhumlu | 5 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  | Verified | Bhumlu | 7
9438 | Kavrepalanchok | Falatebhumlu | 6 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 7
9439 | Kavrepalanchok | Falatebhumlu | 7 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 7
9440 | Kavrepalanchok | Falatebhumlu | 8 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  | Verified | Bhumlu | 7
9441 | Kavrepalanchok | Falatebhumlu | 9 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  | Verified | Bhumlu | 7
9442 | Kavrepalanchok | Falemetar | 1 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Khanikhola | 2
9443 | Kavrepalanchok | Falemetar | 2 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Khanikhola | 2
9444 | Kavrepalanchok | Falemetar | 3 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Khanikhola | 2
9445 | Kavrepalanchok | Falemetar | 4 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Khanikhola | 1
9446 | Kavrepalanchok | Falemetar | 5 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Khanikhola | 1
9447 | Kavrepalanchok | Falemetar | 6 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Khanikhola | 1
9448 | Kavrepalanchok | Falemetar | 7 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Khanikhola | 2
9449 | Kavrepalanchok | Falemetar | 8 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Khanikhola | 2
9450 | Kavrepalanchok | Falemetar | 9 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Khanikhola | 1
9451 | Kavrepalanchok | Foksingtar | 1 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 3
9452 | Kavrepalanchok | Foksingtar | 2 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 3
9453 | Kavrepalanchok | Foksingtar | 3 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 3
9454 | Kavrepalanchok | Foksingtar | 4 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 3
9455 | Kavrepalanchok | Foksingtar | 5 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 3
9456 | Kavrepalanchok | Foksingtar | 6 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 3
9457 | Kavrepalanchok | Foksingtar | 7 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 3
9458 | Kavrepalanchok | Foksingtar | 8 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 3
9459 | Kavrepalanchok | Foksingtar | 9 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 3
9460 | Kavrepalanchok | GairiBisounaDeupur | 1 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mandandeupur | 6
9461 | Kavrepalanchok | GairiBisounaDeupur | 2 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-02-26 | 2017-06-17 | Verified | Mandandeupur | 5
9462 | Kavrepalanchok | GairiBisounaDeupur | 3 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mandandeupur | 6
9463 | Kavrepalanchok | GairiBisounaDeupur | 4 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-06 | 2017-05-08 | Verified | Mandandeupur | 6
9464 | Kavrepalanchok | GairiBisounaDeupur | 5 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 29 | 29 | 2015-10-03 | 2015-10-07 | MToT training, Implementing Partner:- Nangshal Association | Mandandeupur | 6
9465 | Kavrepalanchok | GairiBisounaDeupur | 5 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mandandeupur | 6
9466 | Kavrepalanchok | GairiBisounaDeupur | 6 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-19 | 2017-05-09 | Verified | Mandandeupur | 5
9467 | Kavrepalanchok | GairiBisounaDeupur | 7 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-02-27 | 2017-05-17 | Verified | Mandandeupur | 5
9468 | Kavrepalanchok | GairiBisounaDeupur | 8 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mandandeupur | 5
9469 | Kavrepalanchok | GairiBisounaDeupur | 9 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-16 | 2017-06-10 |  | Mandandeupur | 5
9470 | Kavrepalanchok | Ghartichhap | 1 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-03 | 2017-05-31 | Verified | Mahabharat | 8
9471 | Kavrepalanchok | Ghartichhap | 2 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-24 | 2017-06-18 | Verified | Mahabharat | 8
9472 | Kavrepalanchok | Ghartichhap | 3 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-03 | 2017-06-01 | Verified | Mahabharat | 8
9473 | Kavrepalanchok | Ghartichhap | 4 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 8
9474 | Kavrepalanchok | Ghartichhap | 5 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 8
9475 | Kavrepalanchok | Ghartichhap | 6 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 8
9476 | Kavrepalanchok | Ghartichhap | 7 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-05 | 2017-06-03 | Verified | Mahabharat | 8
9477 | Kavrepalanchok | Ghartichhap | 8 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Mahabharat | 8
9478 | Kavrepalanchok | Ghartichhap | 9 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 8
9479 | Kavrepalanchok | Gokule | 1 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-24 | 2017-06-21 |  | Mahabharat | 1
9480 | Kavrepalanchok | Gokule | 2 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  | Verified | Mahabharat | 1
9481 | Kavrepalanchok | Gokule | 3 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-11 | 2017-06-08 | Verified | Mahabharat | 1
9482 | Kavrepalanchok | Gokule | 4 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-10 | 2016-08-16 |  | Mahabharat | 2
9483 | Kavrepalanchok | Gokule | 4 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-16 | 2017-06-13 | Verified | Mahabharat | 2
9484 | Kavrepalanchok | Gokule | 5 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 2
9485 | Kavrepalanchok | Gokule | 6 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-23 | 2017-06-20 | Verified | Mahabharat | 2
9486 | Kavrepalanchok | Gokule | 7 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Mahabharat | 2
9487 | Kavrepalanchok | Gokule | 8 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-11 | 2017-06-08 | Verified | Mahabharat | 1
9488 | Kavrepalanchok | Gokule | 9 | HELVETAS | Alliance-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-19 | 2017-06-16 | Verified | Mahabharat | 2
9489 | Kavrepalanchok | KatunjeBesi | 6 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-10 | 2016-08-16 |  | Roshi | 7
9490 | Kavrepalanchok | Kharpachok | 1 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 8
9491 | Kavrepalanchok | Kharpachok | 2 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  | Verified | Roshi | 8
9492 | Kavrepalanchok | Kharpachok | 3 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 8
9493 | Kavrepalanchok | Kharpachok | 4 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 8
9494 | Kavrepalanchok | Kharpachok | 5 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Roshi | 8
9495 | Kavrepalanchok | Kharpachok | 6 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 8
9496 | Kavrepalanchok | Kharpachok | 7 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 30 | 30 |  |  | Verified | Roshi | 8
9497 | Kavrepalanchok | Kharpachok | 8 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 40 | 40 |  |  | Verified | Roshi | 8
9498 | Kavrepalanchok | Kharpachok | 9 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 8
9499 | Kavrepalanchok | Koshidekha | 1 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Completed | 7 | 7 | 2015-05-01 | 2016-07-30 |  | Panchkhal | 12
9500 | Kavrepalanchok | Koshidekha | 1 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-28 | 2017-06-24 |  | Panchkhal | 12
9501 | Kavrepalanchok | Koshidekha | 2 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Completed | 20 | 20 | 2015-05-01 | 2016-07-30 |  | Panchkhal | 13
9502 | Kavrepalanchok | Koshidekha | 2 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-14 | 2017-06-01 |  | Panchkhal | 13
9503 | Kavrepalanchok | Koshidekha | 3 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Completed | 8 | 8 | 2015-05-01 | 2016-07-30 |  | Panchkhal | 13
9504 | Kavrepalanchok | Koshidekha | 3 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Panchkhal | 13
9505 | Kavrepalanchok | Koshidekha | 4 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Completed | 15 | 15 | 2015-05-01 | 2016-07-30 |  | Panchkhal | 13
9506 | Kavrepalanchok | Koshidekha | 4 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-03 | 2017-06-01 |  | Panchkhal | 13
9507 | Kavrepalanchok | Koshidekha | 5 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Completed | 7 | 7 | 2015-05-01 | 2016-07-30 |  | Panchkhal | 13
9508 | Kavrepalanchok | Koshidekha | 5 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Panchkhal | 13
9509 | Kavrepalanchok | Koshidekha | 6 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Completed | 46 | 46 | 2015-05-01 | 2016-07-30 |  | Panchkhal | 13
9510 | Kavrepalanchok | Koshidekha | 6 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | Material support on household WASH | HH Rain Water Harvesting | Tank and Hygiene Kits | # of households | Yes | Completed | 41 | 41 | 2016-08-01 | 2018-07-30 |  | Panchkhal | 13
9511 | Kavrepalanchok | Koshidekha | 6 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Panchkhal | 13
9512 | Kavrepalanchok | Koshidekha | 7 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Completed | 9 | 9 | 2015-05-01 | 2016-07-30 |  | Panchkhal | 13
9513 | Kavrepalanchok | Koshidekha | 7 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-13 | 2017-06-09 |  | Panchkhal | 13
9514 | Kavrepalanchok | Koshidekha | 8 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Completed | 35 | 35 | 2015-05-01 | 2016-07-30 |  | Panchkhal | 13
9515 | Kavrepalanchok | Koshidekha | 8 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Panchkhal | 13
9516 | Kavrepalanchok | Koshidekha | 9 | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Completed | 23 | 23 | 2015-05-01 | 2016-07-30 |  | Panchkhal | 13
9517 | Kavrepalanchok | Koshidekha | 9 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Panchkhal | 13
9518 | Kavrepalanchok | Koshidekha |  | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Cement Blocks | # of households | Yes | Planned | 200 | 0 | 2016-08-01 | 2017-07-30 | Ward will be fixed after beneficiary selection | Panchkhal | 13
9519 | Kavrepalanchok | Koshidekha |  | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | Material support on household WASH | HH Rain Water Harvesting | Tank and Hygiene Kits | # of households | Yes | Planned | 55 | 0 | 2016-08-01 | 2018-07-30 | Ward will be fixed after beneficiary selection | Panchkhal | 13
9520 | Kavrepalanchok | Koshidekha |  | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | Material support on household WASH | Household toilet construction | 35 Eco Toilet Construction | # of households | Yes | Planned | 35 | 0 | 2016-08-01 | 2018-07-30 | Ward will be fixed after beneficiary selection | Panchkhal | 13
9521 | Kavrepalanchok | Koshidekha |  | NAVJYOTI | NC | TDH-GER-CARITAS-ITA | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | 2 Plastic ponds, water source protection and supply system construction | # of constructions | Yes | Planned | 4 | 0 | 2016-08-01 | 2018-07-30 | Ward not fixed yet | Panchkhal | 13
9522 | Kavrepalanchok | KuruwasChapakhori | 1 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-06-12 | 2017-06-18 |  | Temal | 7
9523 | Kavrepalanchok | KuruwasChapakhori | 3 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-06-12 | 2017-06-18 |  | Temal | 7
9524 | Kavrepalanchok | KuruwasChapakhori | 4 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2017-06-12 | 2017-06-18 |  | Temal | 7
9525 | Kavrepalanchok | KuruwasChapakhori | 5 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-06-12 | 2017-06-18 |  | Temal | 7
9526 | Kavrepalanchok | KuruwasChapakhori | 7 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-06-12 | 2017-06-18 |  | Temal | 7
9527 | Kavrepalanchok | KuruwasChapakhori | 8 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-06-12 | 2017-06-18 |  | Temal | 7
9528 | Kavrepalanchok | Kushadevi | 1 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Panauti | 3
9529 | Kavrepalanchok | Kushadevi | 2 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-02-19 | 2017-04-22 | Verified | Panauti | 3
9530 | Kavrepalanchok | Kushadevi | 3 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Panauti | 3
9531 | Kavrepalanchok | Kushadevi | 4 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Panauti | 2
9532 | Kavrepalanchok | Kushadevi | 5 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-06 | 2017-05-06 |  | Panauti | 2
9533 | Kavrepalanchok | Kushadevi | 6 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-02 | 2017-05-27 |  | Panauti | 2
9534 | Kavrepalanchok | Kushadevi | 7 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Panauti | 2
9535 | Kavrepalanchok | Kushadevi | 8 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-01 | 2017-05-01 |  | Panauti | 2
9536 | Kavrepalanchok | Kushadevi | 9 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-13 | 2016-02-18 |  | Panauti | 3
9537 | Kavrepalanchok | Kushadevi | 9 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-02-19 | 2017-04-22 |  | Panauti | 3
9538 | Kavrepalanchok | MahadevsthanMandan | 1 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06 | MToT training, Implementing Partner:- Nangshal Association | Mandandeupur | 7
9539 | Kavrepalanchok | MahadevsthanMandan | 2 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06 |  | Mandandeupur | 7
9540 | Kavrepalanchok | MahadevsthanMandan | 3 | ROTARY | CC | ROTARY-BHU | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Planned | 28 | 0 | 2017-01-01 |  | Creative Cooperative in local implementing partner | Mandandeupur | 8
9541 | Kavrepalanchok | MahadevsthanMandan | 3 | ROTARY | CDRA | ROTARY-BHU | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 69 | 69 | 2015-12-27 | 2018-12-30 |  | Mandandeupur | 8
9542 | Kavrepalanchok | MahadevsthanMandan | 3 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06 |  | Mandandeupur | 8
9543 | Kavrepalanchok | MahadevsthanMandan | 3 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Carpenter | DUDBC | # of trainees | Yes | Completed | 3 | 3 | 2016-02-13 | 2016-02-18 | Total 25 carpenter were trained in this (13-18 Feb 2016) training, in which 15 from other districts | Mandandeupur | 8
9544 | Kavrepalanchok | MahadevsthanMandan | 3 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-02-13 | 2016-02-18 |  | Mandandeupur | 8
9545 | Kavrepalanchok | MahadevsthanMandan | 4 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06 |  | Mandandeupur | 8
9546 | Kavrepalanchok | MahadevsthanMandan | 5 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06 |  | Mandandeupur | 8
9547 | Kavrepalanchok | MahadevsthanMandan | 6 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06 |  | Mandandeupur | 8
9548 | Kavrepalanchok | MahadevsthanMandan | 6 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Carpenter | DUDBC | # of trainees | Yes | Completed | 3 | 3 | 2016-02-13 | 2016-02-18 |  | Mandandeupur | 8
9549 | Kavrepalanchok | MahadevsthanMandan | 7 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06 |  | Mandandeupur | 6
9550 | Kavrepalanchok | MahadevsthanMandan | 7 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Carpenter | DUDBC | # of trainees | Yes | Completed | 1 | 1 | 2016-02-13 | 2016-02-18 |  | Mandandeupur | 6
9551 | Kavrepalanchok | MahadevsthanMandan | 8 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06 |  | Mandandeupur | 6
9552 | Kavrepalanchok | MahadevsthanMandan | 9 | ADRA | NA | ADRA | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days DUDBC curriculum | # of trainees | Yes | Completed | 3 | 3 | 2015-11-02 | 2015-11-06 |  | Mandandeupur | 6
9553 | Kavrepalanchok | Mahadevtar | 2 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2015-11-29 | 2015-12-03 |  | Roshi | 4
9554 | Kavrepalanchok | Mahadevtar | 3 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-11-29 | 2015-12-03 |  | Roshi | 4
9555 | Kavrepalanchok | Mahadevtar | 4 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-11-29 | 2015-12-03 |  | Roshi | 4
9556 | Kavrepalanchok | Mahadevtar | 6 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-11-29 | 2015-12-03 |  | Roshi | 4
9557 | Kavrepalanchok | Mahadevtar | 7 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-11-29 | 2015-12-03 |  | Roshi | 4
9558 | Kavrepalanchok | Mahadevtar | 8 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-11-29 | 2015-12-03 |  | Roshi | 4
9559 | Kavrepalanchok | Mahadevtar | 9 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-11-29 | 2015-12-03 |  | Roshi | 4
9560 | Kavrepalanchok | MahankalChaur | 1 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-22 | 2016-09-28 |  | Bethanchowk | 6
9561 | Kavrepalanchok | MahankalChaur | 2 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-22 | 2016-09-28 |  | Bethanchowk | 6
9562 | Kavrepalanchok | MahankalChaur | 3 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-22 | 2016-09-28 |  | Bethanchowk | 6
9563 | Kavrepalanchok | MahankalChaur | 4 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-22 | 2016-09-28 |  | Bethanchowk | 6
9564 | Kavrepalanchok | MahankalChaur | 5 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-22 | 2016-09-28 |  | Bethanchowk | 6
9565 | Kavrepalanchok | MahankalChaur | 6 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-22 | 2016-09-28 |  | Bethanchowk | 6
9566 | Kavrepalanchok | MahankalChaur | 7 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-09-22 | 2016-09-28 |  | Bethanchowk | 6
9567 | Kavrepalanchok | MahankalChaur | 8 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-22 | 2016-09-28 |  | Bethanchowk | 6
9568 | Kavrepalanchok | MahankalChaur | 9 | ARSOW-N | ARSOW-N | MC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-09-22 | 2016-09-28 |  | Bethanchowk | 6
9569 | Kavrepalanchok | Mangaltar | 1 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 9
9570 | Kavrepalanchok | Mangaltar | 2 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-16 | 2017-04-17 | Verified | Roshi | 9
9571 | Kavrepalanchok | Mangaltar | 3 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-14 | 2017-04-13 | Verified | Roshi | 9
9572 | Kavrepalanchok | Mangaltar | 4 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 9
9573 | Kavrepalanchok | Mangaltar | 5 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31 |  | Roshi | 9
9574 | Kavrepalanchok | Mangaltar | 5 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2017-04-25 | 2017-06-30 | Verified | Roshi | 9
9575 | Kavrepalanchok | Mangaltar | 6 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 9
9576 | Kavrepalanchok | Mangaltar | 7 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Roshi | 9
9577 | Kavrepalanchok | Mangaltar | 8 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-12 | 2017-04-10 | Verified | Roshi | 9
9578 | Kavrepalanchok | Mangaltar | 9 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 9
9579 | Kavrepalanchok | Milche | 1 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-04 | 2017-06-03 | Verified | Khanikhola | 7
9580 | Kavrepalanchok | Milche | 1 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-06-12 | 2017-06-18 |  | Khanikhola | 7
9581 | Kavrepalanchok | Milche | 2 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-11 | 2017-06-17 | Verified | Khanikhola | 7
9582 | Kavrepalanchok | Milche | 2 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-06-12 | 2017-06-18 |  | Khanikhola | 7
9583 | Kavrepalanchok | Milche | 3 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-30 | Verified | Khanikhola | 7
9584 | Kavrepalanchok | Milche | 3 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-06-12 | 2017-06-18 |  | Khanikhola | 7
9585 | Kavrepalanchok | Milche | 4 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-06 | 2017-06-14 | To be verified | Khanikhola | 7
9586 | Kavrepalanchok | Milche | 4 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-06-12 | 2017-06-18 |  | Khanikhola | 7
9587 | Kavrepalanchok | Milche | 5 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2017-04-13 | 2017-06-21 | Verified | Khanikhola | 7
9588 | Kavrepalanchok | Milche | 6 | BC | ARSOW-N | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-07 | 2016-05-13 |  | Khanikhola | 7
9589 | Kavrepalanchok | Milche | 6 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2017-04-20 | 2017-06-20 | Verified | Khanikhola | 7
9590 | Kavrepalanchok | Milche | 7 | BC | ARSOW-N | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-07 | 2016-05-13 |  | Khanikhola | 7
9591 | Kavrepalanchok | Milche | 7 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  | To be verified | Khanikhola | 7
9592 | Kavrepalanchok | Milche | 7 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-06-12 | 2017-06-18 |  | Khanikhola | 7
9593 | Kavrepalanchok | Milche | 8 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  | To be verified | Khanikhola | 7
9594 | Kavrepalanchok | Milche | 8 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-06-12 | 2017-06-18 |  | Khanikhola | 7
9595 | Kavrepalanchok | Milche | 9 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  | Verified | Khanikhola | 7
9596 | Kavrepalanchok | Milche | 9 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-06-12 | 2017-06-18 |  | Khanikhola | 7
9597 | Kavrepalanchok | Nala(Ugrachandi) | 9 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Carpenter | DUDBC | # of trainees | Yes | Completed | 2 | 2 | 2016-02-13 | 2016-02-18 |  | Banepa | 3
9598 | Kavrepalanchok | Panauti N.P. | 9 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Carpenter | DUDBC | # of trainees | Yes | Completed | 1 | 1 | 2016-02-13 | 2016-02-18 |  | Panauti | 8
9599 | Kavrepalanchok | Panauti N.P. | 11 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-13 | 2016-02-18 |  | Panauti | 6
9600 | Kavrepalanchok | Panchkhal N.P. | 1 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-25 | 2016-02-29 | Location Detail: Tamaghat | Panchkhal | 5
9601 | Kavrepalanchok | Panchkhal N.P. | 1 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-28 | 2016-04-03 | Location Detail: Tinpiple | Panchkhal | 5
9602 | Kavrepalanchok | Panchkhal N.P. | 2 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-28 | 2016-04-03 |  | Panchkhal | 3
9603 | Kavrepalanchok | Panchkhal N.P. | 3 | UNDP | CTEVT | UNDP | Technical Assistance | Demonstration Construction | House | Brick masonry with cement mortar technology house with 1 room | # of constructions | Yes | Completed | 1 | 1 | 2016-11-10 | 2016-12-31 |  | Panchkhal | 4
9604 | Kavrepalanchok | Panchkhal N.P. | 3 | UNDP | CTEVT | UNDP | Technical Assistance | Demonstration Construction | House | GI wire containment technology house with 1 room | # of constructions | Yes | Ongoing | 1 | 0 | 2016-11-20 | 2017-01-31 |  | Panchkhal | 4
9605 | Kavrepalanchok | Panchkhal N.P. | 3 | CL | CL | VG | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT Short training | # of trainees | Yes | Completed | 20 | 20 | 2016-08-15 | 2016-10-12 | Was funded as part of Corporate CSR activity - Centum didn't report to any local authorities | Panchkhal | 4
9606 | Kavrepalanchok | Panchkhal N.P. | 3 | CL | VG | VG | Training | Short training | Plumber | CTEVT Short training | # of trainees | Yes | Completed | 20 | 20 | 2016-08-18 | 2016-10-12 | Was funded as part of Corporate CSR activity - Centum didn't report to any local authorities | Panchkhal | 4
9607 | Kavrepalanchok | Panchkhal N.P. | 3 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-25 | 2016-02-29 |  | Panchkhal | 4
9608 | Kavrepalanchok | Panchkhal N.P. | 4 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-25 | 2016-02-29 |  | Panchkhal | 6
9609 | Kavrepalanchok | Panchkhal N.P. | 4 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-28 | 2016-04-03 |  | Panchkhal | 6
9610 | Kavrepalanchok | Panchkhal N.P. | 5 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-21 | 2015-12-25 | Location Detail: Anaikot | Panchkhal | 6
9611 | Kavrepalanchok | Panchkhal N.P. | 5 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-03-28 | 2016-04-03 |  | Panchkhal | 6
9612 | Kavrepalanchok | Panchkhal N.P. | 7 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-25 | 2016-02-29 |  | Panchkhal | 8
9613 | Kavrepalanchok | Panchkhal N.P. | 7 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-28 | 2016-04-03 |  | Panchkhal | 8
9614 | Kavrepalanchok | Panchkhal N.P. | 8 | PIPALTAR | PSD-N | HFH | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Ongoing | 86 | 44 | 2016-04-01 | 2017-03-01 | This project is in planning stage. It will be finalized at the end of March | Panchkhal | 8
9615 | Kavrepalanchok | Panchkhal N.P. | 8 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-02-25 | 2016-02-29 |  | Panchkhal | 8
9616 | Kavrepalanchok | Panchkhal N.P. | 8 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-28 | 2016-04-03 |  | Panchkhal | 8
9617 | Kavrepalanchok | Panchkhal N.P. | 9 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-25 | 2016-02-29 |  | Panchkhal | 12
9618 | Kavrepalanchok | Panchkhal N.P. | 9 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-28 | 2016-04-03 |  | Panchkhal | 12
9619 | Kavrepalanchok | Panchkhal N.P. | 10 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-02-25 | 2016-02-29 |  | Panchkhal | 12
9620 | Kavrepalanchok | Panchkhal N.P. | 10 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-28 | 2016-04-03 |  | Panchkhal | 12
9621 | Kavrepalanchok | Panchkhal N.P. | 11 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-02-25 | 2016-02-29 |  | Panchkhal | 10
9622 | Kavrepalanchok | Panchkhal N.P. | 11 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-03-28 | 2016-04-03 |  | Panchkhal | 10
9623 | Kavrepalanchok | Panchkhal N.P. | 13 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-21 | 2015-12-25 |  | Panchkhal | 1
9624 | Kavrepalanchok | Panchkhal N.P. | 14 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2015-12-21 | 2015-12-25 |  | Panchkhal | 2
9625 | Kavrepalanchok | Panchkhal N.P. | 15 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2015-12-21 | 2015-12-25 |  | Panchkhal | 2
9626 | Kavrepalanchok | Panchkhal N.P. | 15 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-25 | 2016-02-29 |  | Panchkhal | 2
9627 | Kavrepalanchok | Panchkhal N.P. | 15 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-28 | 2016-04-03 |  | Panchkhal | 2
9628 | Kavrepalanchok | Panchkhal N.P. | 16 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 27 | 27 | 2016-01-12 | 2016-01-16 | Location Detail: Anaikot | Panchkhal | 9
9629 | Kavrepalanchok | Panchkhal N.P. | 16 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-25 | 2016-02-29 |  | Panchkhal | 9
9630 | Kavrepalanchok | Panchkhal N.P. | 17 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-21 | 2015-12-25 |  | Panchkhal | 9
9631 | Kavrepalanchok | Panchkhal N.P. |  | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT,Batch 2 | # of trainees | Yes | Completed | 30 | 30 | 2016-11-14 | 2016-09-18 |  | Panchkhal | 6
9632 | Kavrepalanchok | Panchkhal N.P. |  | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT,Batch 1 | # of trainees | Yes | Completed | 30 | 30 | 2016-09-25 | 2016-09-29 |  | Panchkhal | 6
9633 | Kavrepalanchok | Panchkhal N.P. |  | UNDP | CTEVT | GOJ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 5 Days training,CTEVT,Batch 3 | # of trainees | Yes | Completed | 30 | 30 | 2016-11-21 | 2016-11-25 |  | Panchkhal | 6
9634 | Kavrepalanchok | RaviOpi | 1 | CDRA | CDRA | GCF Global-U | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-05-14 | 2016-05-20 |  | Dhulikhel | 2
9635 | Kavrepalanchok | RaviOpi | 1 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-09 | 2017-05-07 | Verified | Dhulikhel | 2
9636 | Kavrepalanchok | RaviOpi | 2 | CDRA | CDRA | GCF Global-U | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-14 | 2016-05-20 |  | Dhulikhel | 2
9637 | Kavrepalanchok | RaviOpi | 2 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Dhulikhel | 2
9638 | Kavrepalanchok | RaviOpi | 3 | CDRA | CDRA | GCF Global-U | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-14 | 2016-05-20 |  | Dhulikhel | 2
9639 | Kavrepalanchok | RaviOpi | 3 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Dhulikhel | 2
9640 | Kavrepalanchok | RaviOpi | 4 | CDRA | CDRA | GCF Global-U | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-14 | 2016-05-20 |  | Dhulikhel | 2
9641 | Kavrepalanchok | RaviOpi | 4 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-08 | 2017-05-04 | Verified | Dhulikhel | 2
9642 | Kavrepalanchok | RaviOpi | 5 | CDRA | CDRA | GCF Global-U | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-14 | 2016-05-20 |  | Dhulikhel | 2
9643 | Kavrepalanchok | RaviOpi | 5 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-26 | 2017-06-21 | Verified | Dhulikhel | 2
9644 | Kavrepalanchok | RaviOpi | 6 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Banepa | 5
9645 | Kavrepalanchok | RaviOpi | 7 | CDRA | CDRA | GCF Global-U | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-14 | 2016-05-20 |  | Banepa | 5
9646 | Kavrepalanchok | RaviOpi | 7 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Banepa | 5
9647 | Kavrepalanchok | RaviOpi | 8 | CDRA | CDRA | GCF Global-U | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-14 | 2016-05-20 |  | Banepa | 5
9648 | Kavrepalanchok | RaviOpi | 8 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Banepa | 5
9649 | Kavrepalanchok | RaviOpi | 9 | CDRA | CDRA | GCF Global-U | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-14 | 2016-05-20 |  | Banepa | 5
9650 | Kavrepalanchok | RaviOpi | 9 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-13 | 2016-02-18 |  | Banepa | 5
9651 | Kavrepalanchok | RaviOpi | 9 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-08 | 2017-05-04 | Verified | Banepa | 5
9652 | Kavrepalanchok | RyaleBhir | 5 | NCRS | NCRS | SP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-08-17 | 2016-12-31 | Ryale vdc - 1 model houses per 3 mason training | Panauti | 1
9653 | Kavrepalanchok | RyaleBhir | 1 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Panauti | 1
9654 | Kavrepalanchok | RyaleBhir | 5 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 41 | 41 | 2016-11-16 |  |  | Panauti | 1
9655 | Kavrepalanchok | RyaleBhir | 5 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 31 | 31 | 2016-10-22 | 2016-10-28 |  | Panauti | 1
9656 | Kavrepalanchok | RyaleBhir | 6 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 13 | 13 | 2016-10-22 | 2016-12-12 |  | Panauti | 1
9657 | Kavrepalanchok | RyaleBhir | 2 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Panauti | 1
9658 | Kavrepalanchok | RyaleBhir | 6 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-10-22 | 2016-12-12 |  | Panauti | 1
9659 | Kavrepalanchok | RyaleBhir | 7 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 1 | 1 | 2016-10-22 | 2016-10-28 |  | Panauti | 1
9660 | Kavrepalanchok | RyaleBhir | 7 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-10-22 | 2016-10-28 |  | Panauti | 1
9661 | Kavrepalanchok | RyaleBhir | 3 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Panauti | 1
9662 | Kavrepalanchok | RyaleBhir | 8 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-10-28 |  | Panauti | 1
9663 | Kavrepalanchok | RyaleBhir | 8 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-10-22 | 2016-10-28 |  | Panauti | 1
9664 | Kavrepalanchok | RyaleBhir | 9 | NCRS | NCRS | SP | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 1 | 1 | 2016-10-22 | 2016-10-28 |  | Panauti | 1
9665 | Kavrepalanchok | RyaleBhir | 9 | NCRS | NCRS | SP | Reconstruction through contractors | Construction | Private house | Model house smc 1.1 | # of constructions | Yes | Ongoing | 1 | 1 | 2016-02-07 |  |  | Panauti | 1
9666 | Kavrepalanchok | RyaleBhir | 4 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-03-07 | 2017-05-08 | Verified | Panauti | 1
9667 | Kavrepalanchok | RyaleBhir | 9 | NCRS | NCRS | SP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2016-08-17 | 2016-12-31 |  | Panauti | 1
9668 | Kavrepalanchok | RyaleBhir | 9 | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-10-22 | 2016-10-28 |  | Panauti | 1
9669 | Kavrepalanchok | RyaleBhir | 2,7,8 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 30 | 30 | 2016-09-27 |  | Ward wise data is not received | Panauti | 1
9670 | Kavrepalanchok | RyaleBhir | 6,3 | NCRS | NCRS | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Preparedness | # of trainees | Yes | Completed | 35 | 35 | 2016-09-06 |  | Ward wise data is not received | Panauti | 1
9671 | Kavrepalanchok | RyaleBhir |  | NCRS | NCRS | SP | Others | Others | (Please specify in Activity Detail) | Prrvious Methainkot vdc- 1 sign bord with Built Back Safer ( 10 Key Messaged) in each 9 wards | # of trainees | Yes | Ongoing | 8 | 8 | 2016-05-01 | 2016-12-31 |  | Panauti | 1
9672 | Kavrepalanchok | RyaleBhir |  | NCRS | NCRS | SP | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 67 | 67 | 2016-10-22 | 2016-10-28 |  | Panauti | 1
9673 | Kavrepalanchok | RyaleBhir | 5 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Panauti | 1
9674 | Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Completed | 49 | 49 | 2017-03-17 | 2017-06-06 |  | Namobuddha | 1
9675 | Kavrepalanchok | Dapcha Kashikhand N.P. | 2 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 30 | 28 | 2017-04-25 |  |  | Namobuddha | 2
9676 | Kavrepalanchok | Dapcha Kashikhand N.P. | 3 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Completed | 5 | 5 | 2016-06-05 | 2017-04-28 |  | Namobuddha | 2
9677 | Kavrepalanchok | RyaleBhir | 6 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Panauti | 1
9678 | Kavrepalanchok | Dapcha Kashikhand N.P. | 4 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 25 | 23 | 2016-06-05 |  |  | Namobuddha | 3
9679 | Kavrepalanchok | Dapcha Kashikhand N.P. | 5 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 29 | 26 | 2016-06-05 |  |  | Namobuddha | 3
9680 | Kavrepalanchok | Dapcha Kashikhand N.P. | 6 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 17 | 17 | 2016-06-05 |  |  | Namobuddha | 4
9681 | Kavrepalanchok | RyaleBhir | 7 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Panauti | 1
9682 | Kavrepalanchok | Dapcha Kashikhand N.P. | 7 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 10 | 8 | 2016-06-05 |  |  | Namobuddha | 6
9683 | Kavrepalanchok | Dapcha Kashikhand N.P. | 8 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 53 | 50 | 2016-06-05 |  |  | Namobuddha | 7
9684 | Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Ongoing | 35 | 34 | 2016-06-05 | 2016-12-31 |  | Namobuddha | 7
9685 | Kavrepalanchok | RyaleBhir | 8 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-01 | 2017-04-21 | Verified | Panauti | 1
9686 | Kavrepalanchok | RyaleBhir | 1 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Completed | 5 | 5 | 2016-06-05 | 2017-02-27 |  | Panauti | 1
9687 | Kavrepalanchok | RyaleBhir | 2 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Completed | 8 | 8 | 2016-06-05 | 2017-02-27 |  | Panauti | 1
9688 | Kavrepalanchok | RyaleBhir | 3 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Completed | 16 | 16 | 2016-06-05 | 2017-03-07 |  | Panauti | 1
9689 | Kavrepalanchok | RyaleBhir | 4 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Completed | 15 | 15 | 2016-06-05 | 2017-04-28 |  | Panauti | 1
9690 | Kavrepalanchok | RyaleBhir | 5 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Completed | 26 | 26 | 2016-06-05 | 2017-05-26 |  | Panauti | 1
9691 | Kavrepalanchok | RyaleBhir | 9 | HELVETAS | PTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Panauti | 1
9692 | Kavrepalanchok | RyaleBhir | 6 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Completed | 52 | 52 | 2016-06-05 | 2017-03-01 |  | Panauti | 1
9693 | Kavrepalanchok | RyaleBhir | 7 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Completed | 10 | 10 | 2016-06-05 | 2017-03-09 |  | Panauti | 1
9694 | Kavrepalanchok | RyaleBhir | 8 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Completed | 3 | 3 | 2016-06-05 | 2017-03-31 |  | Panauti | 1
9695 | Kavrepalanchok | RyaleBhir | 9 | SP | SP | SP | Reconstruction through contractors | Construction | Private house | Earth Bag Homes | # of constructions | Yes | Completed | 12 | 12 | 2016-06-05 | 2017-05-03 |  | Panauti | 1
9696 | Kavrepalanchok | Saldhara | 1 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Khanikhola | 6
9697 | Kavrepalanchok | Saldhara | 2 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Khanikhola | 6
9698 | Kavrepalanchok | Saldhara | 3 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Khanikhola | 6
9699 | Kavrepalanchok | Saldhara | 4 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  | Verified | Khanikhola | 6
9700 | Kavrepalanchok | Saldhara | 5 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  | Verified | Khanikhola | 6
9701 | Kavrepalanchok | Saldhara | 6 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Khanikhola | 6
9702 | Kavrepalanchok | Saldhara | 7 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Khanikhola | 6
9703 | Kavrepalanchok | Saldhara | 8 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  | Verified | Khanikhola | 6
9704 | Kavrepalanchok | Saldhara | 9 | HELVETAS | ANS | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Khanikhola | 6
9705 | Kavrepalanchok | SalleBhumlu | 1 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 5
9706 | Kavrepalanchok | SalleBhumlu | 2 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 5
9707 | Kavrepalanchok | SalleBhumlu | 3 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 5
9708 | Kavrepalanchok | SalleBhumlu | 4 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 5
9709 | Kavrepalanchok | SalleBhumlu | 5 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-09 | 2017-05-01 | Verified | Bhumlu | 5
9710 | Kavrepalanchok | SalleBhumlu | 6 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 5
9711 | Kavrepalanchok | SalleBhumlu | 7 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 5
9712 | Kavrepalanchok | SalleBhumlu | 8 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-08 | 2017-04-29 | Verified | Bhumlu | 5
9713 | Kavrepalanchok | SalleBhumlu | 9 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 5
9714 | Kavrepalanchok | Salmechakala(Taldhu) | 1 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Khanikhola | 5
9715 | Kavrepalanchok | Salmechakala(Taldhu) | 2 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Khanikhola | 5
9716 | Kavrepalanchok | Salmechakala(Taldhu) | 3 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Khanikhola | 5
9717 | Kavrepalanchok | Salmechakala(Taldhu) | 4 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Khanikhola | 5
9718 | Kavrepalanchok | Salmechakala(Taldhu) | 5 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Khanikhola | 5
9719 | Kavrepalanchok | Salmechakala(Taldhu) | 6 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Khanikhola | 5
9720 | Kavrepalanchok | Salmechakala(Taldhu) | 7 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Khanikhola | 5
9721 | Kavrepalanchok | Salmechakala(Taldhu) | 8 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Khanikhola | 5
9722 | Kavrepalanchok | Salmechakala(Taldhu) | 9 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Khanikhola | 5
9723 | Kavrepalanchok | Sanowangthali | 9 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 35 | 0 | 2016-05-14 | 2016-05-20 |  | Chaurideurali | 1
9724 | Kavrepalanchok | Saping | 1 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-19 | 2017-06-09 |  | Bhumlu | 1
9725 | Kavrepalanchok | Saping | 2 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-14 | 2017-06-04 |  | Bhumlu | 1
9726 | Kavrepalanchok | Saping | 3 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 1
9727 | Kavrepalanchok | Saping | 4 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 1
9728 | Kavrepalanchok | Saping | 5 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-31 | 2017-06-07 |  | Bhumlu | 1
9729 | Kavrepalanchok | Saping | 6 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 1
9730 | Kavrepalanchok | Saping | 7 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-04 | 2017-05-26 |  | Bhumlu | 1
9731 | Kavrepalanchok | Saping | 8 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 30 | 30 |  |  |  | Bhumlu | 1
9732 | Kavrepalanchok | Saping | 9 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 1
9733 | Kavrepalanchok | Saramthali | 1 | NYF | NYF | NYF-US | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 11 | 11 | 2016-05-20 | 2016-05-20 | The tools distributed in the community for common use to Social leader and Chairperson of Bhume Secondary School in Shramthali VDC. | Temal | 3
9734 | Kavrepalanchok | Saramthali | 1 | NYF | NYF | NYF-US | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-04-10 | 2016-05-15 |  | Temal | 3
9735 | Kavrepalanchok | Saramthali | 1 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-07 | 2016-04-13 |  | Temal | 3
9736 | Kavrepalanchok | Saramthali | 5 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-07 | 2016-04-13 |  | Temal | 3
9737 | Kavrepalanchok | Saramthali | 6 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-07 | 2016-04-13 |  | Temal | 3
9738 | Kavrepalanchok | Saramthali | 8 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-07 | 2016-04-13 |  | Temal | 3
9739 | Kavrepalanchok | Saramthali | 9 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-07 | 2016-04-13 |  | Temal | 3
9740 | Kavrepalanchok | SikharAmbote | 4 | NYF | NYF | NYF-US | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31 |  | Roshi | 3
9741 | Kavrepalanchok | SimalchourSyampati | 1 | CDRA | CDRA-C-GGC | ROTARY | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-13 | 2016-02-18 |  | Namobuddha | 1
9742 | Kavrepalanchok | Simthali | 1 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-27 | 2016-01-31 |  | Bhumlu | 2
9743 | Kavrepalanchok | Simthali | 1 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 2
9744 | Kavrepalanchok | Simthali | 2 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-01-27 | 2016-01-31 |  | Bhumlu | 2
9745 | Kavrepalanchok | Simthali | 2 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 20 | 20 |  |  | Verified | Bhumlu | 2
9746 | Kavrepalanchok | Simthali | 3 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-01-27 | 2016-01-31 |  | Bhumlu | 2
9747 | Kavrepalanchok | Simthali | 3 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 2
9748 | Kavrepalanchok | Simthali | 4 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-01-27 | 2016-01-31 |  | Bhumlu | 2
9749 | Kavrepalanchok | Simthali | 4 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 2
9750 | Kavrepalanchok | Simthali | 5 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-01-27 | 2016-01-31 |  | Bhumlu | 2
9751 | Kavrepalanchok | Simthali | 5 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-02 | 2017-05-05 | Verified | Bhumlu | 2
9752 | Kavrepalanchok | Simthali | 6 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-27 | 2016-01-31 |  | Bhumlu | 2
9753 | Kavrepalanchok | Simthali | 6 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bhumlu | 2
9754 | Kavrepalanchok | Simthali | 7 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-01-27 | 2016-01-31 |  | Bhumlu | 2
9755 | Kavrepalanchok | Simthali | 7 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-03 | 2017-04-25 | Verified | Bhumlu | 2
9756 | Kavrepalanchok | Simthali | 8 | NN | SAGARMATHA | NN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-01-27 | 2016-01-31 |  | Bhumlu | 2
9757 | Kavrepalanchok | Simthali | 8 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-03 | 2017-05-02 |  | Bhumlu | 2
9758 | Kavrepalanchok | Simthali | 9 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-02 | 2017-04-24 | Verified | Bhumlu | 2
9759 | Kavrepalanchok | SipaliChilaune | 1 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 6
9760 | Kavrepalanchok | SipaliChilaune | 2 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 6
9761 | Kavrepalanchok | SipaliChilaune | 3 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  |  | Roshi | 6
9762 | Kavrepalanchok | SipaliChilaune | 4 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 6
9763 | Kavrepalanchok | SipaliChilaune | 5 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 |  |  | Verified | Roshi | 6
9764 | Kavrepalanchok | SipaliChilaune | 6 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 6
9765 | Kavrepalanchok | SipaliChilaune | 7 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 |  |  | Verified | Roshi | 6
9766 | Kavrepalanchok | SipaliChilaune | 8 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 6
9767 | Kavrepalanchok | SipaliChilaune | 9 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  | Verified | Roshi | 6
9768 | Kavrepalanchok | Sisakhani | 1 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 5
9769 | Kavrepalanchok | Sisakhani | 2 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 5
9770 | Kavrepalanchok | Sisakhani | 3 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 |  |  | Verified | Roshi | 5
9771 | Kavrepalanchok | Sisakhani | 4 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 5
9772 | Kavrepalanchok | Sisakhani | 5 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 5
9773 | Kavrepalanchok | Sisakhani | 6 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 5
9774 | Kavrepalanchok | Sisakhani | 7 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 5
9775 | Kavrepalanchok | Sisakhani | 8 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 5
9776 | Kavrepalanchok | Sisakhani | 9 | HELVETAS | NETSA | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Roshi | 5
9777 | Kavrepalanchok | Balting | 2 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 5 | 5 | 2016-06-19 | 2016-07-20 |  | Roshi | 10
9778 | Kavrepalanchok | Balting | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 5 | 5 | 2016-06-19 | 2016-07-20 |  | Roshi | 10
9779 | Kavrepalanchok | Balting | 4 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-27 | 2016-06-02 | In a combine training 11 mason from Balting | Roshi | 10
9780 | Kavrepalanchok | Balting | 4 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-03 | 2016-06-09 | In two group at same venue, same date 17 mason from Balting | Roshi | 10
9781 | Kavrepalanchok | Balting | 5 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-27 | 2016-06-02 |  | Roshi | 10
9782 | Kavrepalanchok | Balting | 6 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-03 | 2016-06-09 |  | Roshi | 10
9783 | Kavrepalanchok | Balting | 7 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-27 | 2016-06-02 |  | Roshi | 10
9784 | Kavrepalanchok | Balting | 7 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-03 | 2016-06-09 |  | Roshi | 10
9785 | Kavrepalanchok | Balting | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09 |  | Roshi | 10
9786 | Kavrepalanchok | BaluwapatiDeupur | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 6 | 6 | 2016-07-17 | 2016-08-21 |  | Mandandeupur | 1
9787 | Kavrepalanchok | BanakhuChor | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 5 | 5 | 2016-07-06 | 2016-08-12 |  | Mahabharat | 6
9788 | Kavrepalanchok | BanakhuChor | 4 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-06 | 2016-08-12 |  | Mahabharat | 6
9789 | Kavrepalanchok | BanakhuChor | 5 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-07-06 | 2016-08-12 |  | Mahabharat | 6
9790 | Kavrepalanchok | BanakhuChor | 6 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-06 | 2016-08-12 |  | Mahabharat | 6
9791 | Kavrepalanchok | BanakhuChor | 7 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-07-06 | 2016-08-12 |  | Mahabharat | 7
9792 | Kavrepalanchok | BanakhuChor | 8 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-07-06 | 2016-08-12 |  | Mahabharat | 7
9793 | Kavrepalanchok | BanakhuChor | 9 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 8 | 8 | 2016-07-06 | 2016-08-12 |  | Mahabharat | 7
9794 | Kavrepalanchok | Bhimkhori | 1 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09 | In a combine training 17 mason from Bhimkhori | Roshi | 11
9795 | Kavrepalanchok | Bhimkhori | 2 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-20 | 2016-05-26 | In a combine training on this date 30 mason from Bhimkhori | Roshi | 11
9796 | Kavrepalanchok | Bhimkhori | 2 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09 |  | Roshi | 11
9797 | Kavrepalanchok | Bhimkhori | 3 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-27 | 2016-06-02 | In two group at same venue, same date 31 mason from Bhimkhori | Roshi | 11
9798 | Kavrepalanchok | Bhimkhori | 3 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-05-20 | 2016-05-26 |  | Roshi | 11
9799 | Kavrepalanchok | Bhimkhori | 3 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-03 | 2016-06-09 |  | Roshi | 11
9800 | Kavrepalanchok | Bhimkhori | 4 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-27 | 2016-06-02 |  | Roshi | 11
9801 | Kavrepalanchok | Bhimkhori | 4 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-03 | 2016-06-09 |  | Roshi | 11
9802 | Kavrepalanchok | Bhimkhori | 6 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-05-20 | 2016-05-26 |  | Roshi | 11
9803 | Kavrepalanchok | Bhimkhori | 6 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-05-27 | 2016-06-02 |  | Roshi | 11
9804 | Kavrepalanchok | Bhimkhori | 6 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09 |  | Roshi | 11
9805 | Kavrepalanchok | Bhimkhori | 7 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-20 | 2016-05-26 |  | Roshi | 12
9806 | Kavrepalanchok | Bhimkhori | 7 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-27 | 2016-06-02 |  | Roshi | 12
9807 | Kavrepalanchok | Bhimkhori | 7 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-03 | 2016-06-09 |  | Roshi | 12
9808 | Kavrepalanchok | Bhimkhori | 8 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-27 | 2016-06-02 |  | Roshi | 12
9809 | Kavrepalanchok | Bhimkhori | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-27 | 2016-06-02 |  | Roshi | 12
9810 | Kavrepalanchok | Bhimkhori | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-03 | 2016-06-09 |  | Roshi | 12
9811 | Kavrepalanchok | Birtadeurali | 4 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-06 | 2016-08-13 |  | Chaurideurali | 8
9812 | Kavrepalanchok | Budhakhani | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-06-19 | 2016-07-20 |  | Mahabharat | 4
9813 | Kavrepalanchok | Dandagaun | 5 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 7 | 7 | 2016-07-06 | 2016-08-07 |  | Khanikhola | 3
9814 | Kavrepalanchok | Dapcha Kashikhand N.P. | 1 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-06-26 | 2016-07-25 |  | Namobuddha | 1
9815 | Kavrepalanchok | Dapcha Kashikhand N.P. | 2 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-06-26 | 2016-07-25 |  | Namobuddha | 2
9816 | Kavrepalanchok | Dapcha Kashikhand N.P. | 9 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 5 | 5 | 2016-06-26 | 2016-07-25 |  | Namobuddha | 7
9817 | Kavrepalanchok | Devitar | 1 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 15 | 15 | 2016-07-14 | 2016-08-14 |  | Dhulikhel | 1
9818 | Kavrepalanchok | Devitar | 2 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 5 | 5 | 2016-07-14 | 2016-08-14 |  | Dhulikhel | 1
9819 | Kavrepalanchok | Devitar | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-07-14 | 2016-08-14 |  | Dhulikhel | 1
9820 | Kavrepalanchok | Devitar | 4 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-14 | 2016-08-14 |  | Banepa | 3
9821 | Kavrepalanchok | Devitar | 6 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 7 | 7 | 2016-07-14 | 2016-08-14 |  | Dhulikhel | 1
9822 | Kavrepalanchok | Devitar | 7 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 5 | 5 | 2016-07-14 | 2016-08-14 |  | Dhulikhel | 1
9823 | Kavrepalanchok | Devitar | 8 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 4 | 4 | 2016-07-14 | 2016-08-14 |  | Dhulikhel | 1
9824 | Kavrepalanchok | Devitar | 9 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 3 | 3 | 2016-07-14 | 2016-08-14 |  | Dhulikhel | 1
9825 | Kavrepalanchok | Foksingtar | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 3 | 3 | 2016-07-06 | 2016-08-07 |  | Mahabharat | 3
9826 | Kavrepalanchok | Foksingtar | 4 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 3 | 3 | 2016-07-06 | 2016-08-13 |  | Mahabharat | 3
9827 | Kavrepalanchok | Foksingtar | 5 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 3 | 3 | 2016-07-06 | 2016-08-13 |  | Mahabharat | 3
9828 | Kavrepalanchok | GairiBisounaDeupur | 1 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-17 | 2016-08-21 |  | Mandandeupur | 6
9829 | Kavrepalanchok | GairiBisounaDeupur | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 6 | 6 | 2016-07-17 | 2016-08-21 |  | Mandandeupur | 6
9830 | Kavrepalanchok | GairiBisounaDeupur | 4 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 3 | 3 | 2016-07-17 | 2016-08-21 |  | Mandandeupur | 6
9831 | Kavrepalanchok | GairiBisounaDeupur | 7 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 6 | 6 | 2016-07-17 | 2016-08-21 |  | Mandandeupur | 5
9832 | Kavrepalanchok | Ghartichhap | 1 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 8 | 8 | 2016-06-26 | 2016-08-07 |  | Mahabharat | 8
9833 | Kavrepalanchok | Ghartichhap | 2 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 3 | 3 | 2016-06-26 | 2016-08-07 |  | Mahabharat | 8
9834 | Kavrepalanchok | Ghartichhap | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-06-26 | 2016-07-25 |  | Mahabharat | 8
9835 | Kavrepalanchok | Ghartichhap | 5 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-07-16 | 2016-08-07 |  | Mahabharat | 8
9836 | Kavrepalanchok | Ghartichhap | 6 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-16 | 2016-08-07 |  | Mahabharat | 8
9837 | Kavrepalanchok | Ghartichhap | 7 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-16 | 2016-08-07 |  | Mahabharat | 8
9838 | Kavrepalanchok | Ghartichhap | 9 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-06-26 | 2016-07-25 |  | Mahabharat | 8
9839 | Kavrepalanchok | Gokule | 1 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-07-16 | 2016-08-07 |  | Mahabharat | 1
9840 | Kavrepalanchok | Gokule | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-07-06 | 2016-08-12 |  | Mahabharat | 1
9841 | Kavrepalanchok | Gokule | 4 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 7 | 7 | 2016-07-06 | 2016-08-13 |  | Mahabharat | 2
9842 | Kavrepalanchok | Gokule | 5 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 7 | 7 | 2016-06-26 | 2016-08-12 |  | Mahabharat | 2
9843 | Kavrepalanchok | Gokule | 6 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 4 | 4 | 2016-06-26 | 2016-08-13 |  | Mahabharat | 2
9844 | Kavrepalanchok | Gokule | 7 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 5 | 5 | 2016-07-06 | 2016-08-13 |  | Mahabharat | 2
9845 | Kavrepalanchok | Gokule | 8 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 4 | 4 | 2016-07-06 | 2016-08-12 |  | Mahabharat | 1
9846 | Kavrepalanchok | Gokule | 9 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 6 | 6 | 2016-07-06 | 2016-08-12 |  | Mahabharat | 2
9847 | Kavrepalanchok | JyamdiMandan | 1 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-16 | 2016-05-22 | Our capacity to train in one group Is 30, so planned 30 but reached may vary depending on situation | Mandandeupur | 11
9848 | Kavrepalanchok | JyamdiMandan | 2 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-05-22 |  | Mandandeupur | 11
9849 | Kavrepalanchok | JyamdiMandan | 3 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-16 | 2016-05-22 |  | Mandandeupur | 11
9850 | Kavrepalanchok | JyamdiMandan | 4 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-16 | 2016-05-22 |  | Mandandeupur | 11
9851 | Kavrepalanchok | JyamdiMandan | 5 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-16 | 2016-05-22 |  | Bhumlu | 9
9852 | Kavrepalanchok | JyamdiMandan | 6 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-05-22 |  | Mandandeupur | 11
9853 | Kavrepalanchok | JyamdiMandan | 7 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-05-22 |  | Bhumlu | 9
9854 | Kavrepalanchok | JyamdiMandan | 8 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-16 | 2016-05-22 |  | Bhumlu | 9
9855 | Kavrepalanchok | JyamdiMandan | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-16 | 2016-05-22 |  | Bhumlu | 9
9856 | Kavrepalanchok | KolatiBhumlu | 1 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-05-24 | 2016-05-30 | Two group of 30/30 at same venue and date, planned 30 but reached may vary depending on situation | Bhumlu | 6
9857 | Kavrepalanchok | KolatiBhumlu | 1 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-31 | 2016-06-06 | Two group of 30/30 at same venue and date, planned 30 but reached may vary depending on situation | Bhumlu | 6
9858 | Kavrepalanchok | KolatiBhumlu | 2 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-05-24 | 2016-05-30 |  | Bhumlu | 6
9859 | Kavrepalanchok | KolatiBhumlu | 3 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 17 | 2016-05-24 | 2016-05-30 |  | Bhumlu | 6
9860 | Kavrepalanchok | KolatiBhumlu | 4 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-05-24 | 2016-05-30 |  | Bhumlu | 6
9861 | Kavrepalanchok | KolatiBhumlu | 4 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-31 | 2016-06-06 |  | Bhumlu | 6
9862 | Kavrepalanchok | KolatiBhumlu | 5 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-05-24 | 2016-05-30 |  | Bhumlu | 6
9863 | Kavrepalanchok | KolatiBhumlu | 6 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-24 | 2016-05-30 |  | Bhumlu | 6
9864 | Kavrepalanchok | KolatiBhumlu | 7 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-24 | 2016-05-30 |  | Bhumlu | 6
9865 | Kavrepalanchok | KolatiBhumlu | 7 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-31 | 2016-06-06 |  | Bhumlu | 6
9866 | Kavrepalanchok | KolatiBhumlu | 8 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-24 | 2016-05-30 |  | Bhumlu | 6
9867 | Kavrepalanchok | KolatiBhumlu | 8 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-31 | 2016-06-06 |  | Bhumlu | 6
9868 | Kavrepalanchok | KolatiBhumlu | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-24 | 2016-05-30 |  | Bhumlu | 6
9869 | Kavrepalanchok | KolatiBhumlu | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-05-31 | 2016-06-06 |  | Bhumlu | 6
9870 | Kavrepalanchok | Machchhegaun | 3 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-05-20 | 2016-05-26 | In a combine training 11 mason from Mechhegaaun | Temal | 8
9871 | Kavrepalanchok | Machchhegaun | 5 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-03 | 2016-06-09 | In two group at same venue, same date 3 mason from Mechhegaun | Temal | 8
9872 | Kavrepalanchok | MahadevsthanMandan | 1 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 5 | 5 | 2016-06-27 | 2016-08-01 |  | Mandandeupur | 7
9873 | Kavrepalanchok | MahadevsthanMandan | 2 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 5 | 5 | 2016-06-27 | 2016-08-01 |  | Mandandeupur | 7
9874 | Kavrepalanchok | MahadevsthanMandan | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-06-27 | 2016-08-01 |  | Mandandeupur | 8
9875 | Kavrepalanchok | MahadevsthanMandan | 4 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-06-27 | 2016-08-01 |  | Mandandeupur | 8
9876 | Kavrepalanchok | MahadevsthanMandan | 5 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-06-27 | 2016-08-01 |  | Mandandeupur | 8
9877 | Kavrepalanchok | MahadevsthanMandan | 9 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 4 | 4 | 2016-06-27 | 2016-08-01 |  | Mandandeupur | 6
9878 | Kavrepalanchok | Mangaltar | 2 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 3 | 3 | 2016-06-19 | 2016-07-20 |  | Roshi | 9
9879 | Kavrepalanchok | Mangaltar | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 2016-06-19 | 2016-07-20 |  | Roshi | 9
9880 | Kavrepalanchok | Mangaltar | 6 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-20 | 2016-05-26 | In a combine training 2 mason from mangaltar | Roshi | 9
9881 | Kavrepalanchok | Mangaltar | 6 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 3 | 3 | 2016-06-19 | 2016-07-20 |  | Roshi | 9
9882 | Kavrepalanchok | Mangaltar | 8 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-03 | 2016-06-09 | In two group at same venue, same date 7 mason from Mangaltar | Roshi | 9
9883 | Kavrepalanchok | Mangaltar | 8 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 2016-06-19 | 2016-07-20 |  | Roshi | 9
9884 | Kavrepalanchok | Mangaltar | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-09 |  | Roshi | 9
9885 | Kavrepalanchok | BanakhuChor | 5 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 6 | 15-Dec-2016 | 21-Dec-2016 |  | Mahabharat | 6
9886 | Kavrepalanchok | BanakhuChor | 5 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 22-Dec-2016 | 28-Dec-2016 |  | Mahabharat | 6
9887 | Kavrepalanchok | Dolalghat | 5 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 15-Dec-2016 | 21-Dec-2016 |  | Bhumlu | 10
9888 | Kavrepalanchok | Dolalghat | 2 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 8-Dec-2016 | 14-Dec-2016 |  | Bhumlu | 10
9889 | Kavrepalanchok | Saping | 8 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 30-Dec-2016 | 5-Jan-2017 |  | Bhumlu | 1
9890 | Kavrepalanchok | Saping | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 26-Jan-2016 | 1-Feb-2017 |  | Bhumlu | 1
9891 | Kavrepalanchok | Saping | 1 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 23-Dec-2016 | 29-Dec-2016 |  | Bhumlu | 1
9892 | Kavrepalanchok | RaviOpi | 1 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 9-Jan-2017 | 17-Jan-2017 |  | Dhulikhel | 2
9893 | Kavrepalanchok | Birtadeurali | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 24-Jan-2017 | 30-Jan-2017 |  | Chaurideurali | 8
9894 | Kavrepalanchok | Gokule | 6 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 1-Feb-2017 | 7-Feb-2017 |  | Mahabharat | 2
9895 | Kavrepalanchok | Gokule | 6 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 12-Feb-2017 | 18-Feb-2017 |  | Mahabharat | 2
9896 | Kavrepalanchok | Ghartichhap | 5 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 20-Feb-2017 | 26-Feb-2017 |  | Mahabharat | 8
9897 | Kavrepalanchok | KanpurKalapani | 1 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 28-Feb-2017 | 6-Mar-2017 |  | Namobuddha | 5
9898 | Kavrepalanchok | KanpurKalapani | 1 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 7-Mar-2017 | 13-Mar-2017 |  | Namobuddha | 5
9899 | Kavrepalanchok | BanakhuChor | 5 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 22-Dec-2016 | 30-Jan-2017 |  | Mahabharat | 6
9900 | Kavrepalanchok | RaviOpi | 1 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 21-Dec-2016 | 10-Feb-2017 |  | Dhulikhel | 2
9901 | Kavrepalanchok | Birtadeurali | 7 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 24-Jan-2017 | 6-Mar-2017 |  | Chaurideurali | 8
9902 | Kavrepalanchok | Birtadeurali | 6 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 4-Feb-2017 | 16-Mar-2017 |  | Chaurideurali | 8
9903 | Kavrepalanchok | Gokule | 6 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 2 | 28-Jan-2017 | 8-Mar-2017 |  | Mahabharat | 2
9904 | Kavrepalanchok | Gokule | 1 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 1 | 4-Feb-2017 | 15-Mar-2017 |  | Mahabharat | 1
9905 | Kavrepalanchok | Gokule | 1 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 6-Feb-2017 | 17-Mar-2017 |  | Mahabharat | 1
9906 | Kavrepalanchok | Gokule | 6 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 12-Feb-2017 | 23-Mar-2017 |  | Mahabharat | 2
9907 | Kavrepalanchok | Saping | 4 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 11-Feb-2017 | 24-Mar-2017 |  | Bhumlu | 1
9908 | Kavrepalanchok | Bhumlutar | 6 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 12-Feb-2017 | 23-Mar-2017 |  | Bhumlu | 8
9909 | Kavrepalanchok | Bhumlutar | 6 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 23-Feb-2017 | 27-Apr-2017 |  | Bhumlu | 8
9910 | Kavrepalanchok | Bhumlutar | 6 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 23-Mar-2017 | 3-May-2017 |  | Bhumlu | 8
9911 | Kavrepalanchok | KanpurKalapani | 7 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 2 | 1 | 28-Mar-2017 | 7-May-2017 |  | Namobuddha | 5
9912 | Kavrepalanchok | KanpurKalapani | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Completed | 1 | 1 | 1-Mar-2017 | 10-Apr-2017 |  | Namobuddha | 5
9913 | Kavrepalanchok | Patalekhet | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-06-21 | 2017-06-27 |  | Dhulikhel | 11
9914 | Kavrepalanchok | NayagaunDeupur | 3 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-07-01 | 2017-07-07 |  | Mandandeupur | 3
9915 | Kavrepalanchok | Patalekhet | 7 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-07-12 | 2017-07-19 |  | Dhulikhel | 11
9916 | Kavrepalanchok | NayagaunDeupur | 3 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-07-29 | 2017-08-04 |  | Mandandeupur | 3
9917 | Kavrepalanchok | Patalekhet | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-08-11 | 2017-08-17 |  | Dhulikhel | 11
9918 | Kavrepalanchok | BaluwapatiDeupur | 1 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-08-10 | 2017-08-16 |  | Mandandeupur | 1
9919 | Kavrepalanchok | NayagaunDeupur | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Ongoing | 1 | 1 | 2017-07-31 | 2017-09-10 |  | Mandandeupur | 3
9920 | Kavrepalanchok | Patalekhet | 9 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Ongoing | 2 | 2 | 2017-07-20 | 2017-08-31 |  | Dhulikhel | 11
9921 | Kavrepalanchok | BaluwapatiDeupur | 1 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Ongoing | 1 | 1 | 2017-08-10 | 2017-09-20 |  | Mandandeupur | 1
9922 | Kavrepalanchok | Patalekhet | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Ongoing | 1 | 1 | 2017-08-03 | 2017-09-15 |  | Dhulikhel | 11
9923 | Kavrepalanchok | Dandagaun | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Ongoing | 2 | 2 | 2017-07-29 | 2017-09-12 | In this training, participants were from two ward i.e. 3 & 5 | Khanikhola | 4
9924 | Kavrepalanchok | Falemetar | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Ongoing | 2 | 2 | 2017-07-29 | 2017-09-12 | In this training, participants were from two ward i.e. 3 & 4 | Khanikhola | 2
9925 | Kavrepalanchok | Budhakhani | 1 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Ongoing | 2 | 2 | 2017-07-27 | 2017-09-10 |  | Mahabharat | 5
9926 | Kavrepalanchok | Falemetar | 4 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Ongoing | 1 | 1 | 2017-08-08 | 2017-09-14 |  | Khanikhola | 1
9927 | Kavrepalanchok | Patalekhet | 9 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-08-03 | 2017-08-09 |  | Dhulikhel | 11
9928 | Kavrepalanchok | Falemetar | 4 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-08-07 | 2017-08-13 |  | Khanikhola | 1
9929 | Kavrepalanchok | Dandagaun | 3 | SABAL | SABAL | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-08-07 | 2017-08-13 |  | Khanikhola | 4
9930 | Kavrepalanchok | Budhakhani | 3 | SABAL | SABAL | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days CTEVT Curriculum (390 Hours Mason Training) | # of trainees | Yes | Ongoing | 1 | 1 | 2017-07-28 | 2017-09-11 |  | Mahabharat | 4
9931 | Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 55 | 55 | 2016-08-01 | 2017-08-07 | Total target in the ward 1 to 5 is 250 Rest are in other wards | Panchkhal | 5
9932 | Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Top Ups | Vulnerable HHs | Shelter condition, Economic condition, Social condiion | # of households | Yes | Ongoing | 56 | 54 | 2016-12-14 | 2018-03-31 | Total target is 50 but others are yet to receive | Panchkhal | 5
9933 | Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Construction,Shelter condition, Economic condition, Social condition | # of constructions | Yes | Ongoing | 34 | 32 | 2017-03-24 | 2018-03-31 | Total target is 24 but others are yet to receive | Panchkhal | 5
9934 | Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour, Shelter condition, Economic condition, Social condiion | # of constructions | Yes | Ongoing | 34 | 33 | 2017-04-15 | 2018-03-31 | Total target is 24 but others are yet to receive | Panchkhal | 5
9935 | Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | NPR. 150,000 | # of households | Yes | Ongoing | 55 | 43 | 2017-03-24 | 2018-03-17 | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive | Panchkhal | 5
9936 | Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Others | Others | (Please specify in Activity Detail) | Hoarding boards messaging safer construction at different locations | # of trainees | Yes | Completed | 600 | 600 | 2016-07-07 | 2016-09-23 | blanket approach | Panchkhal | 5
9937 | Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Technical Assistance | Community reconstruction orientation | 1 session | PASSA-eight activity per session | # of participants | Yes | Completed | 30 | 30 | 2016-09-01 | 2016-09-15 |  | Panchkhal | 5
9938 | Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Beneficiares Verification, Technical Information, Taging beneficiares location , Team composition of engineer, social mobilizer and member from PASSA group | # of households | Yes | Ongoing | 55 | 55 | 2016-08-01 |  | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive | Panchkhal | 5
9939 | Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Technical information design and supervision | # of households supported | Yes | Ongoing | 1000 | 1251 | 2016-07-07 |  | The total target from ward 1 to 5 is 1000 where total reached from 1 to 5 is 442 others are yet to receive | Panchkhal | 5
9940 | Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 16 | 16 | 2016-09-05 | 2016-09-23 | 60 masons from 5 ward are trained and so was planned | Panchkhal | 5
9941 | Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Training | Vocational training | Plumber (CTEVT) | Vocational training for plumber according to CTEVT curriculam | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Panchkhal | 5
9942 | Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Training | Vocational training | Electrician (CTEVT) | Vocational training for electrecian according to CTEVT curriculam | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Panchkhal | 5
9943 | Kavrepalanchok | Panchkhal N.P. | 1 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-18 | 2016-11-23 | 3 times training given to total 10 social mobilizer | Panchkhal | 5
9944 | Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 134 | 134 | 2016-08-01 | 2017-07-31 | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive | Panchkhal | 3
9945 | Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Top Ups | Vulnerable HHs | Shelter condition, Economic condition, Social condiion | # of households | Yes | Ongoing | 63 | 54 | 2016-12-14 | 2018-03-31 | Total target is 50 but others are yet to receive | Panchkhal | 3
9946 | Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Construction, Shelter condition, Economic condition, Social condiion | # of constructions | Yes | Ongoing | 32 | 31 | 2017-03-24 | 2018-03-31 | Total target is 24 but others are yet to receive | Panchkhal | 3
9947 | Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour, Shelter condition, Economic condition, Social condiion | # of constructions | Yes | Completed | 32 | 32 | 2017-04-15 | 2018-03-31 | Total target is 24 but others are yet to receive | Panchkhal | 3
9948 | Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Others | Others | (Please specify in Activity Detail) | Hoarding boards messaging safer construction at different locations | # of trainees | Yes | Completed | 600 | 600 | 2016-07-07 | 2016-09-23 | blanket approach | Panchkhal | 3
9949 | Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Technical Assistance | Community reconstruction orientation | 1 session | PASSA-eight activity per session | # of participants | Yes | Completed | 30 | 30 | 2016-08-05 | 2016-09-11 | As community mobilizers were supporting enrolment, this session was postponded. | Panchkhal | 3
9950 | Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House | Model house construction | # of constructions | Yes | Completed | 1 | 1 | 2016-12-24 | 2017-02-27 | Through Housing support service Center (HSSC) | Panchkhal | 3
9951 | Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Beneficiares Verification, Technical Information, Taging beneficiares location , Team composition is of engineer, social mobilizer and member from PASSA group | # of households | Yes | Ongoing | 134 | 134 | 2016-08-01 |  | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive | Panchkhal | 3
9952 | Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Technical information design and supervision | # of households supported | Yes | Ongoing | 1000 | 1251 | 2016-07-07 |  | The total target from ward 1 to 5 is 1000 where total reached from 1 to 5 is 442 others are yet to receive | Panchkhal | 3
9953 | Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 9 | 9 | 2016-09-05 | 2016-09-23 |  | Panchkhal | 3
9954 | Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-18 | 2016-11-23 | 3 times training given to total 10 social mobilizer | Panchkhal | 3
9955 | Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | Self (Prepared and endorsed from DUDBC) | # of trainees | Yes | Completed | 30 | 28 | 2016-12-24 | 2017-01-27 | Venue is at ward 2, and mason were from ward 1 to 5 | Panchkhal | 3
9956 | Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Training | Vocational training | Plumber (CTEVT) | Vocational training for plumber according to CTEVT curriculam | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Panchkhal | 3
9957 | Kavrepalanchok | Panchkhal N.P. | 2 | HFH | ASF | HFH | Training | Vocational training | Electrician (CTEVT) | Vocational training for Electrician according to CTEVT curriculam | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Panchkhal | 3
9958 | Kavrepalanchok | Panchkhal N.P. | 3 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Top Ups | Vulnerable HHs | Shelter condition, Economic condition, Social condiion | # of households | Yes | Ongoing | 55 | 53 | 2016-12-14 | 2018-03-31 | Total target is 50 but others are yet to receive | Panchkhal | 4
9959 | Kavrepalanchok | Panchkhal N.P. | 3 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Construction, Shelter condition, Economic condition, Social condiion | # of constructions | Yes | Ongoing | 30 | 29 | 2017-03-24 | 2018-03-31 | Total target is 24 but others are yet to receive | Panchkhal | 4
9960 | Kavrepalanchok | Panchkhal N.P. | 3 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour, Shelter condition, Economic condition, Social condiion | # of constructions | Yes | Ongoing | 30 | 29 | 2017-04-15 | 2018-03-31 | Total target is 24 but others are yet to receive | Panchkhal | 4
9961 | Kavrepalanchok | Panchkhal N.P. | 3 | HFH | ASF | HFH | Others | Others | (Please specify in Activity Detail) | Hoarding boards messaging safer construction at different locations | # of trainees | Yes | Completed | 600 | 600 | 2016-07-07 | 2016-09-23 | blanket approach | Panchkhal | 4
9962 | Kavrepalanchok | Panchkhal N.P. | 3 | HFH | ASF | HFH | Technical Assistance | Community reconstruction orientation | 1 session | PASSA-eight activity per session | # of participants | Yes | Completed | 30 | 28 | 2016-08-03 | 2016-08-10 |  | Panchkhal | 4
9963 | Kavrepalanchok | Panchkhal N.P. | 3 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Beneficiares Verification, Technical Information, Taging beneficiares location , Team composition is of engineer, social mobilizer and member from PASSA group | # of households | Yes | Ongoing | 30 | 30 | 2016-08-01 |  | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive | Panchkhal | 4
9964 | Kavrepalanchok | Panchkhal N.P. | 3 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Technical information design and supervision | # of households supported | Yes | Ongoing | 1000 | 1251 | 2016-07-07 |  | The total target from ward 1 to 5 is 1000 where total reached from 1 to 5 is 442 others are yet to receive | Panchkhal | 4
9965 | Kavrepalanchok | Panchkhal N.P. | 3 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 12 | 12 | 2016-09-05 | 2016-09-23 |  | Panchkhal | 4
9966 | Kavrepalanchok | Panchkhal N.P. | 3 | HFH | ASF | HFH | Training | Vocational training | Plumber (CTEVT) | Vocational training for plumber according to CTEVT curriculam | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Panchkhal | 4
9967 | Kavrepalanchok | Panchkhal N.P. | 3 | HFH | ASF | HFH | Training | Vocational training | Electrician (CTEVT) | Vocational training for electrician according to CTEVT curriculam | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Panchkhal | 4
9968 | Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 15 | 15 | 2016-08-01 | 2016-11-18 | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive | Panchkhal | 6
9969 | Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Top Ups | Vulnerable HHs | Shelter condition, Economic condition, Social condiion | # of households | Yes | Ongoing | 59 | 52 | 2016-12-14 | 2018-03-31 | Total target is 50 but others are yet to receive | Panchkhal | 6
9970 | Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Construction, Shelter condition, Economic condition, Social condiion | # of constructions | Yes | Completed | 32 | 32 | 2017-03-24 | 2018-03-31 | Total target is 24 but others are yet to receive | Panchkhal | 6
9971 | Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour, Shelter condition, Economic condition, Social condiion | # of constructions | Yes | Completed | 32 | 32 | 2017-04-15 | 2018-03-31 | Total target is 24 but others are yet to receive | Panchkhal | 6
9972 | Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Others | Others | (Please specify in Activity Detail) | Hoarding boards messaging safer construction at different locations | # of trainees | Yes | Completed | 600 | 600 | 2016-07-07 | 2016-09-23 | blanket approach | Panchkhal | 6
9973 | Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Technical Assistance | Community reconstruction orientation | 1 session | PASSA-eight activity per session | # of participants | Yes | Completed | 30 | 30 | 2016-07-31 | 2016-08-03 |  | Panchkhal | 6
9974 | Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Beneficiares Verification, Technical Information, Taging beneficiares location , Team composition is of engineer, social mobilizer and member from PASSA group | # of households | Yes | Ongoing | 15 | 15 | 2016-08-01 |  | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive | Panchkhal | 6
9975 | Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Technical information design and supervision | # of households supported | Yes | Ongoing | 1000 | 1251 | 2016-07-07 |  | The total target from ward 1 to 5 is 1000 where total reached from 1 to 5 is 442 others are yet to receive | Panchkhal | 6
9976 | Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 12 | 12 | 2016-09-05 | 2016-09-23 |  | Panchkhal | 6
9977 | Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Training | Vocational training | Plumber (CTEVT) | Vocational training for plumber according to CTEVT curriculam | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Panchkhal | 6
9978 | Kavrepalanchok | Panchkhal N.P. | 4 | HFH | ASF | HFH | Training | Vocational training | Electrician (CTEVT) | Vocational training for plumber according to CTEVT curriculam | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Panchkhal | 6
9979 | Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR. 50,000 | # of households | Yes | Completed | 16 | 16 | 2016-08-01 | 2017-07-31 | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive | Panchkhal | 6
9980 | Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Top Ups | Vulnerable HHs | Shelter condition, Economic condition, Social condiion | # of households | Yes | Ongoing | 56 | 53 | 2016-12-14 | 2018-03-31 | Total target is 50 but others are yet to receive | Panchkhal | 6
9981 | Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Construction, Shelter condition, Economic condition, Social condiion | # of constructions | Yes | Completed | 29 | 29 | 2017-03-24 | 2018-03-31 | Total target is 24 but others are yet to receive | Panchkhal | 6
9982 | Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour, Shelter condition, Economic condition, Social condiion | # of constructions | Yes | Completed | 29 | 29 | 2017-04-15 | 2018-03-31 | Total target is 24 but others are yet to receive | Panchkhal | 6
9983 | Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Others | Others | (Please specify in Activity Detail) | Hoarding boards messaging safer construction at different locations | # of trainees | Yes | Completed | 600 | 600 | 2016-07-07 | 2016-09-23 | blanket approach | Panchkhal | 6
9984 | Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Technical Assistance | Community reconstruction orientation | 1 session | PASSA-eight activity per session | # of participants | Yes | Completed | 30 | 30 | 2016-09-05 | 2016-09-09 |  | Panchkhal | 6
9985 | Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Beneficiares Verification, Technical Information, Taging beneficiares location , Team composition is of engineer, social mobilizer and member from PASSA group | # of households | Yes | Ongoing | 9 | 9 | 2016-08-01 |  | Total target in the ward 1 to 5 is 250 but target per ward is yet to receive | Panchkhal | 6
9986 | Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Technical information design and supervision | # of households supported | Yes | Ongoing | 1000 | 1251 | 2016-07-07 |  | The total target from ward 1 to 5 is 1000 where total reached from 1 to 5 is 442 others are yet to receive | Panchkhal | 6
9987 | Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 11 | 11 | 2016-09-05 | 2016-09-23 |  | Panchkhal | 6
9988 | Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Training | Vocational training | Plumber (CTEVT) | Vocational training for plumber according to CTEVT curriculam | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Panchkhal | 6
9989 | Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Training | Vocational training | Electrician (CTEVT) | Vocational training for electrician according to CTEVT curriculam | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Panchkhal | 6
9990 | Kavrepalanchok | Panchkhal N.P. |  | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Drawings | # of households supported | Yes | Ongoing | 1000 | 725 | 2017-03-01 | 2017-07-31 | The total target from ward 1 to 5 is 1000 where total reached from 1 to 5 is 442 others are yet to receive | Panchkhal | 6
9991 | Kavrepalanchok | BaluwapatiDeupur | 3 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 17 | 13 | 2017-03-10 | 2017-10-15 | sill-3, lintel-1 | Mandandeupur | 1
9992 | Kavrepalanchok | BaluwapatiDeupur | 4 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 17 | 10 | 2017-03-10 | 2017-10-15 | foundation-3, plinth-2, lintel-2 | Mandandeupur | 2
9993 | Kavrepalanchok | BaluwapatiDeupur | 6 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Completed | 16 | 16 | 2017-04-10 | 2017-07-15 | completed | Mandandeupur | 1
9994 | Kavrepalanchok | GairiBisounaDeupur | 1 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 5 | 1 | 2017-04-10 | 2017-10-15 | sill-1, lintel-3 | Mandandeupur | 6
9995 | Kavrepalanchok | GairiBisounaDeupur | 3 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 60 | 50 | 2016-08-20 | 2017-10-15 | sill-1, lintel-9 | Mandandeupur | 6
9996 | Kavrepalanchok | GairiBisounaDeupur | 4 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 3 | 1 | 2017-04-15 | 2017-10-15 | plinth-2 | Mandandeupur | 6
9997 | Kavrepalanchok | GairiBisounaDeupur | 7 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 7 | 6 | 2017-04-15 | 2017-10-15 | lintel-1 | Mandandeupur | 5
9998 | Kavrepalanchok | GairiBisounaDeupur | 8 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Completed | 6 | 6 | 2017-04-15 | 2017-07-15 | completed | Mandandeupur | 5
9999 | Kavrepalanchok | GairiBisounaDeupur | 9 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 2 | 2 | 2017-04-15 | 2017-07-15 | completed | Mandandeupur | 5
10000 | Kavrepalanchok | JaisithokMandan | 1 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 3 | 1 | 2017-04-15 | 2017-10-15 | lintel-2 | Mandandeupur | 10
10001 | Kavrepalanchok | JaisithokMandan | 3 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 5 | 2 | 2016-10-15 | 2017-10-15 | plinth-1, lintel-2 | Mandandeupur | 10
10002 | Kavrepalanchok | JaisithokMandan | 6 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 9 | 5 | 2016-11-15 | 2017-10-15 | sill-2, lintel-2 | Mandandeupur | 10
10003 | Kavrepalanchok | JaisithokMandan | 7 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 24 | 14 | 2016-11-15 | 2017-10-15 | plinth-2, sill-4, lintel-4 | Mandandeupur | 10
10004 | Kavrepalanchok | JaisithokMandan | 8 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 7 | 2 | 2017-04-15 | 2017-10-15 | excavation-2, sill-2, lintel-1 | Mandandeupur | 10
10005 | Kavrepalanchok | JaisithokMandan | 9 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 10 | 6 | 2017-04-15 | 2017-10-15 | lintel-1, plinth-1, sill-2 | Mandandeupur | 10
10006 | Kavrepalanchok | MahadevsthanMandan | 2 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Completed | 6 | 6 | 2016-06-01 | 2016-09-15 | completed | Mandandeupur | 7
10007 | Kavrepalanchok | MahadevsthanMandan | 3 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Completed | 64 | 64 | 2016-08-25 | 2017-07-15 | completed | Mandandeupur | 8
10008 | Kavrepalanchok | MahadevsthanMandan | 5 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Completed | 19 | 19 | 2017-04-20 | 2017-06-25 | completed | Mandandeupur | 8
10009 | Kavrepalanchok | NayagaunDeupur | 5 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Completed | 6 | 6 | 2017-08-22 | 2017-07-15 | completed | Mandandeupur | 4
10010 | Kavrepalanchok | NayagaunDeupur | 6 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Completed | 34 | 30 | 2016-08-15 | 2017-02-28 | lintel-2, sill-2 | Mandandeupur | 4
10011 | Kavrepalanchok | NayagaunDeupur | 7 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Ongoing | 32 | 27 | 2016-11-15 | 2017-10-15 | lintel-3, sill-2 | Mandandeupur | 3
10012 | Kavrepalanchok | NayagaunDeupur | 8 | LWF | SJASK | EWDE-DKH-N | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Brick, Cement, Sand, Steel, Truss, Rod, CGI | # of households | Yes | Completed | 7 | 7 | 2017-05-15 | 2017-07-15 | completed | Mandandeupur | 3
10013 | Kavrepalanchok | BaluwapatiDeupur | 1 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-04-18 | 2016-04-24 |  | Mandandeupur | 1
10014 | Kavrepalanchok | BaluwapatiDeupur | 2 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-18 | 2016-04-24 |  | Mandandeupur | 2
10015 | Kavrepalanchok | BaluwapatiDeupur | 4 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-04-18 | 2016-04-24 |  | Mandandeupur | 2
10016 | Kavrepalanchok | BaluwapatiDeupur | 5 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-18 | 2016-04-24 |  | Mandandeupur | 1
10017 | Kavrepalanchok | BaluwapatiDeupur | 6 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-18 | 2016-04-24 |  | Mandandeupur | 1
10018 | Kavrepalanchok | BaluwapatiDeupur | 8 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-18 | 2016-04-24 |  | Mandandeupur | 2
10019 | Kavrepalanchok | GairiBisounaDeupur | 1 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-17 | 2016-03-23 |  | Mandandeupur | 6
10020 | Kavrepalanchok | GairiBisounaDeupur | 2 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-17 | 2016-03-23 |  | Mandandeupur | 5
10021 | Kavrepalanchok | GairiBisounaDeupur | 3 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-03-17 | 2016-03-23 |  | Mandandeupur | 6
10022 | Kavrepalanchok | GairiBisounaDeupur | 4 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-17 | 2016-03-23 |  | Mandandeupur | 6
10023 | Kavrepalanchok | GairiBisounaDeupur | 6 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-17 | 2016-03-23 |  | Mandandeupur | 5
10024 | Kavrepalanchok | GairiBisounaDeupur | 7 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-03-17 | 2016-03-23 |  | Mandandeupur | 5
10025 | Kavrepalanchok | JaisithokMandan | 1 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-04-05 | 2016-04-11 |  | Mandandeupur | 10
10026 | Kavrepalanchok | JaisithokMandan | 2 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-05 | 2016-04-11 |  | Mandandeupur | 10
10027 | Kavrepalanchok | JaisithokMandan | 3 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-05 | 2016-04-11 |  | Mandandeupur | 10
10028 | Kavrepalanchok | JaisithokMandan | 4 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-05 | 2016-04-11 |  | Mandandeupur | 10
10029 | Kavrepalanchok | JaisithokMandan | 5 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-05 | 2016-04-11 |  | Mandandeupur | 10
10030 | Kavrepalanchok | JaisithokMandan | 6 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-05 | 2016-04-11 |  | Mandandeupur | 10
10031 | Kavrepalanchok | JaisithokMandan | 7 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-04-05 | 2016-04-11 |  | Mandandeupur | 10
10032 | Kavrepalanchok | JaisithokMandan | 8 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-05 | 2016-04-11 |  | Mandandeupur | 10
10033 | Kavrepalanchok | JaisithokMandan | 9 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-04-05 | 2016-04-11 |  | Mandandeupur | 10
10034 | Kavrepalanchok | MahadevsthanMandan | 1 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-03-24 | 2016-03-30 |  | Mandandeupur | 7
10035 | Kavrepalanchok | MahadevsthanMandan | 2 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-24 | 2016-03-30 |  | Mandandeupur | 7
10036 | Kavrepalanchok | MahadevsthanMandan | 3 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-03-24 | 2016-03-30 |  | Mandandeupur | 8
10037 | Kavrepalanchok | MahadevsthanMandan | 6 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-24 | 2016-03-30 |  | Mandandeupur | 8
10038 | Kavrepalanchok | MahadevsthanMandan | 8 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-24 | 2016-03-30 |  | Mandandeupur | 6
10039 | Kavrepalanchok | MahadevsthanMandan | 9 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-24 | 2016-03-30 |  | Mandandeupur | 6
10040 | Kavrepalanchok | NayagaunDeupur | 1 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-30 | 2016-04-05 |  | Mandandeupur | 4
10041 | Kavrepalanchok | NayagaunDeupur | 5 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-30 | 2016-04-05 |  | Mandandeupur | 4
10042 | Kavrepalanchok | NayagaunDeupur | 6 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-03-30 | 2016-04-05 |  | Mandandeupur | 4
10043 | Kavrepalanchok | NayagaunDeupur | 7 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-03-30 | 2016-04-05 |  | Mandandeupur | 3
10044 | Kavrepalanchok | NayagaunDeupur | 8 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-03-30 | 2016-04-05 |  | Mandandeupur | 3
10045 | Kavrepalanchok | NayagaunDeupur | 9 | LWF | SJASK | EWDE-DKH-N | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-30 | 2016-04-05 |  | Mandandeupur | 3
10046 | Kavrepalanchok | ChalalGaneshsthan | 2 | ARSOW-N | ARSOW-N | MC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 |  |  |  | Bethanchowk | 4
10047 | Kavrepalanchok | Chyamrangbesi | 2 | ARSOW-N | ARSOW-N | MC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 |  |  |  | Bethanchowk | 1
10048 | Kavrepalanchok | ChyasingKharka |  | ARSOW-N | ARSOW-N | MC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 |  |  |  | Bethanchowk | 5
10049 | Kavrepalanchok | MahankalChaur |  | ARSOW-N | ARSOW-N | MC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 |  |  |  | Bethanchowk | 6
10050 | Kavrepalanchok | Baldthali | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 55 | 55 | 2016-12-05 |  |  | Panauti | 11
10051 | Kavrepalanchok | Baldthali | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 55 | 3 | 2016-10-01 |  |  | Panauti | 11
10052 | Kavrepalanchok | Baldthali | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Planned | 61 | 0 |  |  |  | Panauti | 11
10053 | Kavrepalanchok | Baldthali | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 2 | 2 | 2016-09-08 | 2016-09-08 | Tole level re construction group formation | Panauti | 11
10054 | Kavrepalanchok | Baldthali | 1 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-11 | 2016-07-12 |  | Panauti | 11
10055 | Kavrepalanchok | Baldthali | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 18 | 1 | 2016-11-15 |  |  | Panauti | 11
10056 | Kavrepalanchok | Baldthali | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 18 | 2 | 2016-10-01 |  |  | Panauti | 11
10057 | Kavrepalanchok | Baldthali | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 19 | 5 | 2016-12-17 |  |  | Panauti | 11
10058 | Kavrepalanchok | Baldthali | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 2 | 1 | 2016-09-08 | 2016-09-08 |  | Panauti | 11
10059 | Kavrepalanchok | Baldthali | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 34 | 1 | 2016-12-08 |  |  | Panauti | 11
10060 | Kavrepalanchok | Baldthali | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 34 | 1 | 2016-10-01 |  |  | Panauti | 11
10061 | Kavrepalanchok | Baldthali | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Ongoing | 34 | 2 |  |  |  | Panauti | 11
10062 | Kavrepalanchok | Baldthali | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 2 | 1 | 2016-09-09 | 2016-09-09 |  | Panauti | 11
10063 | Kavrepalanchok | Baldthali | 3 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 4 | 2016-06-11 | 2016-07-12 |  | Panauti | 11
10064 | Kavrepalanchok | Baldthali | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 53 | 120 | 2016-12-07 |  |  | Panauti | 11
10065 | Kavrepalanchok | Baldthali | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Demonstration Construction | House & Toilet |  | # of constructions | Yes | Completed | 1 | 1 | 2016-06-15 | 2016-08-23 | Handover complete formally | Panauti | 11
10066 | Kavrepalanchok | Baldthali | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 53 | 148 | 2016-10-01 |  |  | Panauti | 11
10067 | Kavrepalanchok | Baldthali | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Ongoing | 53 | 53 |  |  |  | Panauti | 11
10068 | Kavrepalanchok | Baldthali | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 3 | 2 | 2016-09-09 | 2016-09-09 |  | Panauti | 11
10069 | Kavrepalanchok | Baldthali | 4 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-11 | 2016-07-12 |  | Panauti | 11
10070 | Kavrepalanchok | Baldthali | 5 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | Financial support on household WASH | Community water scheme | Nepane Water system repair and maintenance, ward no 5 | # of households | Yes | Ongoing | 157 | 34 | 2016-11-09 |  |  | Panauti | 11
10071 | Kavrepalanchok | Baldthali | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 155 | 18 | 2016-12-18 |  |  | Panauti | 11
10072 | Kavrepalanchok | Baldthali | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 155 | 52 | 2016-10-01 |  |  | Panauti | 11
10073 | Kavrepalanchok | Baldthali | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Ongoing | 169 | 155 |  |  |  | Panauti | 11
10074 | Kavrepalanchok | Baldthali | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 6 | 5 | 2016-09-15 | 2016-09-15 |  | Panauti | 11
10075 | Kavrepalanchok | Baldthali | 5 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-11 | 2016-07-12 |  | Panauti | 11
10076 | Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | Financial support on household WASH | Community water scheme | Dada gaun Water system repair and maintenance, ward no 6 | # of households | Yes | Ongoing | 70 | 52 | 2016-12-21 |  |  | Panauti | 11
10077 | Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Transportation Support for HH (Vehicle Support on Request) | # of trainees | Yes | Ongoing | 2 | 18 | 2016-12-07 |  |  | Panauti | 11
10078 | Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 61 | 34 | 2016-12-06 |  |  | Panauti | 11
10079 | Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 61 | 155 | 2016-10-01 |  |  | Panauti | 11
10080 | Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 67 | 61 | 2016-12-17 |  |  | Panauti | 11
10081 | Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 3 | 2 | 2016-09-07 | 2016-09-07 |  | Panauti | 11
10082 | Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-11 | 2016-07-12 |  | Panauti | 11
10083 | Kavrepalanchok | Baldthali | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 29 | 18 | 2016-12-13 |  |  | Panauti | 11
10084 | Kavrepalanchok | Baldthali | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 29 | 34 | 2016-10-01 |  |  | Panauti | 11
10085 | Kavrepalanchok | Baldthali | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Ongoing | 29 | 52 |  |  |  | Panauti | 11
10086 | Kavrepalanchok | Baldthali | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 2 | 1 | 2016-09-13 | 2016-09-13 |  | Panauti | 11
10087 | Kavrepalanchok | Baldthali | 7 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-06-11 | 2016-07-12 |  | Panauti | 11
10088 | Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Transportation Support for HH (Vehicle Support on Request) | # of trainees | Yes | Ongoing | 2 | 18 | 2016-12-07 |  |  | Panauti | 11
10089 | Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 17 | 34 | 2016-11-14 |  |  | Panauti | 11
10090 | Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Demonstration Construction | House & Toilet |  | # of constructions | Yes | Ongoing | 1 | 1 | 2016-07-08 |  |  | Panauti | 11
10091 | Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 17 | 52 | 2016-10-01 |  |  | Panauti | 11
10092 | Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Ongoing | 17 | 61 |  |  |  | Panauti | 11
10093 | Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 2 | 1 | 2016-09-13 | 2016-09-13 |  | Panauti | 11
10094 | Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-11 | 2016-07-12 |  | Panauti | 11
10095 | Kavrepalanchok | Baldthali | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 54 | 18 | 2016-12-01 |  |  | Panauti | 11
10096 | Kavrepalanchok | Baldthali | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 54 | 34 | 2016-10-01 |  |  | Panauti | 11
10097 | Kavrepalanchok | Baldthali | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Ongoing | 58 | 52 |  |  |  | Panauti | 11
10098 | Kavrepalanchok | Baldthali | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 3 | 2 | 2016-09-14 | 2016-09-14 |  | Panauti | 11
10099 | Kavrepalanchok | Baldthali | 9 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-11 | 2016-07-12 |  | Panauti | 11
10100 | Kavrepalanchok | Baldthali |  | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | Financial support on household WASH | Community water scheme | One unit plan | # of households | Yes | Ongoing | 50 | 34 |  |  |  | Panauti | 11
10101 | Kavrepalanchok | Baldthali |  | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Support to enrollment centre (Volunteer Suppot) | # of trainees | Yes | Ongoing | 507 | 18 | 2016-06-29 | 2016-09-25 | Ward wise support is not tracked | Panauti | 11
10102 | Kavrepalanchok | Baldthali |  | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | One VDC Level Committee | # of committees | Yes | Completed | 1 | 1 | 2016-12-14 | 2016-12-14 |  | Panauti | 11
10103 | Kavrepalanchok | ChandeniMandan | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 166 | 155 | 2016-10-19 |  |  | Mandandeupur | 9
10104 | Kavrepalanchok | ChandeniMandan | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 166 | 61 | 2016-10-01 |  |  | Mandandeupur | 9
10105 | Kavrepalanchok | ChandeniMandan | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 168 | 29 | 2016-09-22 |  |  | Mandandeupur | 9
10106 | Kavrepalanchok | ChandeniMandan | 1 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 6 | 5 | 2016-09-24 | 2016-09-24 | Tole level re construction group formation | Mandandeupur | 9
10107 | Kavrepalanchok | ChandeniMandan | 1 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-08-19 | 2016-08-27 |  | Mandandeupur | 9
10108 | Kavrepalanchok | ChandeniMandan | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 77 | 2 | 2016-11-13 |  |  | Mandandeupur | 9
10109 | Kavrepalanchok | ChandeniMandan | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 77 | 4 | 2016-10-01 |  |  | Mandandeupur | 9
10110 | Kavrepalanchok | ChandeniMandan | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 81 | 5 | 2016-09-22 |  |  | Mandandeupur | 9
10111 | Kavrepalanchok | ChandeniMandan | 2 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 4 | 5 | 2016-09-21 | 2016-09-21 |  | Mandandeupur | 9
10112 | Kavrepalanchok | ChandeniMandan | 2 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-08-19 | 2016-08-27 |  | Mandandeupur | 9
10113 | Kavrepalanchok | ChandeniMandan | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 59 | 4 | 2016-11-17 |  |  | Mandandeupur | 9
10114 | Kavrepalanchok | ChandeniMandan | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 59 | 3 |  |  |  | Mandandeupur | 9
10115 | Kavrepalanchok | ChandeniMandan | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 62 | 5 | 2016-09-22 |  |  | Mandandeupur | 9
10116 | Kavrepalanchok | ChandeniMandan | 3 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 3 | 3 | 2016-09-24 | 2016-09-24 |  | Mandandeupur | 9
10117 | Kavrepalanchok | ChandeniMandan | 3 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-08-19 | 2016-08-27 |  | Mandandeupur | 9
10118 | Kavrepalanchok | ChandeniMandan | 4 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | Financial support on household WASH | Community water scheme | Himjyoti water system repair and maintenance, ward no 4 | # of households | Yes | Ongoing | 40 | 4 |  |  |  | Mandandeupur | 9
10119 | Kavrepalanchok | ChandeniMandan | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 117 | 5 | 2016-11-17 |  |  | Mandandeupur | 9
10120 | Kavrepalanchok | ChandeniMandan | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 117 | 5 | 2016-10-01 |  |  | Mandandeupur | 9
10121 | Kavrepalanchok | ChandeniMandan | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 126 | 2 | 2016-09-22 |  |  | Mandandeupur | 9
10122 | Kavrepalanchok | ChandeniMandan | 4 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 5 | 4 | 2016-09-28 | 2016-09-28 |  | Mandandeupur | 9
10123 | Kavrepalanchok | ChandeniMandan | 4 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-08-19 | 2016-08-27 |  | Mandandeupur | 9
10124 | Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | Financial support on household WASH | Community water scheme | Jogitar waster system repair and maintenance, ward no 5 | # of households | Yes | Completed | 115 | 5 | 2016-09-15 | 2016-10-15 |  | Mandandeupur | 9
10125 | Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | Financial support on household WASH | Community water scheme | Phyafulla Water schem construction for ward no 5,6,7,8 upper part (Joint venture maga project- for water system with cost Rs.1 corod 40 lakh) | # of households | Yes | Ongoing | 45 | 3 |  |  |  | Mandandeupur | 9
10126 | Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Transportation Support for HH (Vehicle Support on Request) | # of trainees | Yes | Ongoing | 15 | 2 | 2016-11-19 |  |  | Mandandeupur | 9
10127 | Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 149 | 4 | 2016-11-13 |  |  | Mandandeupur | 9
10128 | Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Demonstration Construction | House & Toilet |  | # of constructions | Yes | Ongoing | 1 | 5 | 2016-09-25 |  |  | Mandandeupur | 9
10129 | Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 149 | 5 | 2016-10-01 |  |  | Mandandeupur | 9
10130 | Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 157 | 2 | 2016-09-22 |  |  | Mandandeupur | 9
10131 | Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 6 | 4 | 2016-11-08 | 2016-11-08 |  | Mandandeupur | 9
10132 | Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-08-19 | 2016-08-27 |  | Mandandeupur | 9
10133 | Kavrepalanchok | ChandeniMandan | 6 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | Financial support on household WASH | Community water scheme | Phyafulla Water schem construction for ward no 5,6,7,8 upper part (Joint venture maga project- for water system with cost Rs.1 corod 40 lakh) | # of households | Yes | Ongoing | 49 | 5 |  |  |  | Mandandeupur | 9
10134 | Kavrepalanchok | ChandeniMandan | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 136 | 3 | 2016-11-14 |  |  | Mandandeupur | 9
10135 | Kavrepalanchok | ChandeniMandan | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 136 | 2 | 2016-10-01 |  |  | Mandandeupur | 9
10136 | Kavrepalanchok | ChandeniMandan | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 142 | 4 | 2016-09-22 |  |  | Mandandeupur | 9
10137 | Kavrepalanchok | ChandeniMandan | 6 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 6 | 5 | 2016-11-07 | 2016-11-07 |  | Mandandeupur | 9
10138 | Kavrepalanchok | ChandeniMandan | 6 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-08-19 | 2016-08-27 |  | Mandandeupur | 9
10139 | Kavrepalanchok | ChandeniMandan | 7 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | Financial support on household WASH | Community water scheme | Phyafulla Water schem construction for ward no 5,6,7,8 upper part (Joint venture maga project- for water system with cost Rs.1 corod 40 lakh) | # of households | Yes | Ongoing | 54 | 2 |  |  |  | Mandandeupur | 9
10140 | Kavrepalanchok | ChandeniMandan | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 54 | 4 | 2016-11-23 |  |  | Mandandeupur | 9
10141 | Kavrepalanchok | ChandeniMandan | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 54 | 3 |  |  |  | Mandandeupur | 9
10142 | Kavrepalanchok | ChandeniMandan | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 61 | 5 | 2016-09-22 |  |  | Mandandeupur | 9
10143 | Kavrepalanchok | ChandeniMandan | 7 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 3 | 3 | 2016-09-27 | 2016-09-27 |  | Mandandeupur | 9
10144 | Kavrepalanchok | ChandeniMandan | 7 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-08-19 | 2016-08-27 |  | Mandandeupur | 9
10145 | Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | Financial support on household WASH | Community water scheme | Phyafulla Water schem construction for ward no 5,6,7,8 upper part (Joint venture maga project- for water system with cost Rs.1 corod 40 lakh) | # of households | Yes | Ongoing | 200 | 4 |  |  | 200 HH of ward no 8,6,7,5, 9 and 1,4,5 Upper part | Mandandeupur | 9
10146 | Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 102 | 5 | 2016-11-18 |  |  | Mandandeupur | 9
10147 | Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Demonstration Construction | House & Toilet |  | # of constructions | Yes | Completed | 1 | 5 | 2016-09-23 |  |  | Mandandeupur | 9
10148 | Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 102 | 2 |  |  |  | Mandandeupur | 9
10149 | Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 107 | 4 | 2016-09-22 |  |  | Mandandeupur | 9
10150 | Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 5 | 3 | 2016-11-07 | 2016-11-07 |  | Mandandeupur | 9
10151 | Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-08-19 | 2016-08-27 |  | Mandandeupur | 9
10152 | Kavrepalanchok | ChandeniMandan | 9 | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Transportation Support for HH (Vehicle Support on Request) | # of trainees | Yes | Ongoing | 9 | 3 | 2016-11-19 |  |  | Mandandeupur | 9
10153 | Kavrepalanchok | ChandeniMandan | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Community reconstruction orientation | 1 session | Duration: In average 3.5 hours, Conduct orientation on earthquake resistance building construction, role of individual during construction of building, NRA guidelines | # of participants | Yes | Ongoing | 80 | 2 | 2016-11-14 |  |  | Mandandeupur | 9
10154 | Kavrepalanchok | ChandeniMandan | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Door-to-door technical assistance | Continuous | Support to select location; lay out support, regular supervision and technical advice | # of households | Yes | Ongoing | 80 | 4 | 2016-10-01 |  |  | Mandandeupur | 9
10155 | Kavrepalanchok | ChandeniMandan | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Conduct meeting and oraint about wash activities program, find out issues on Wash | # of households | Yes | Ongoing | 80 | 5 | 2016-09-22 |  |  | Mandandeupur | 9
10156 | Kavrepalanchok | ChandeniMandan | 9 | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Toll level and ward level reconstruction group formed as per NRA guideline and CN strategy | # of committees | Yes | Completed | 4 | 5 | 2016-11-08 | 2016-11-08 |  | Mandandeupur | 9
10157 | Kavrepalanchok | ChandeniMandan | 9 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 19 | 19 | 2016-08-19 | 2016-08-27 |  | Mandandeupur | 9
10158 | Kavrepalanchok | ChandeniMandan |  | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Support to enrollment centre (Volunteer Suppot) | # of trainees | Yes | Ongoing | 984 | 4 | 2016-06-21 | 2016-10-10 | Ward wise support is not tracked | Mandandeupur | 10
10159 | Kavrepalanchok | ChandeniMandan |  | CARITAS-N | CARITAS-N | CARITAS | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | One VDC Level Committee | # of committees | Yes | Completed | 1 | 3 | 2016-11-15 | 2016-11-15 |  | Mandandeupur | 10
10160 | Kavrepalanchok | Dhulikhel N.P. | 7 | CARITAS-N | CARITAS-N | CARITAS | Training | ToT | Engineers, sub engineers (7 days DUDBC) | Two Event, total 45 Engineer ( 40 Engineer from DUDBC and 5 from Caritas(2 ChandeniMandan+3Baldthali)) | # of trainees | Yes | Completed | 45 | 52 | 2016-10-15 | 2016-11-14 | Venue is Dhulikhel | Dhulikhel | 4
10161 | Kavrepalanchok | RaviOpi |  | CARITAS-N | CARITAS-N | CARITAS | Others | Others | (Please specify in Activity Detail) | Support to enrollment centre (Volunteer Suppot- 8 ) and other logistic support | # of trainees | Yes | Completed | 970 | 155 | 2016-04-10 |  |  | Dhulikhel | 2
10162 | Kavrepalanchok | Sanowangthali | 2 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2017-11-15 | 2017-11-21 |  | Chaurideurali | 1
10163 | Kavrepalanchok | Sanowangthali | 3 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-11-15 | 2017-11-21 |  | Chaurideurali | 1
10164 | Kavrepalanchok | Sanowangthali | 4 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-11-15 | 2017-11-21 |  | Chaurideurali | 1
10165 | Kavrepalanchok | Sanowangthali | 5 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-11-15 | 2017-11-21 |  | Chaurideurali | 1
10166 | Kavrepalanchok | Sanowangthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-11-15 | 2017-11-21 |  | Chaurideurali | 1
10167 | Kavrepalanchok | Sanowangthali | 7 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2017-11-15 | 2017-11-21 |  | Chaurideurali | 1
10168 | Kavrepalanchok | Sanowangthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-11-15 | 2017-11-21 |  | Chaurideurali | 1
10169 | Kavrepalanchok | Sanowangthali | 9 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2017-11-15 | 2017-11-21 |  | Chaurideurali | 1
10170 | Kavrepalanchok | MajhiFeda | 1 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-11-08 | 2017-11-15 |  | Chaurideurali | 3
10171 | Kavrepalanchok | MajhiFeda | 3 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 43 | 43 | 2017-11-08 | 2017-11-15 |  | Chaurideurali | 3
10172 | Kavrepalanchok | MajhiFeda | 8 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-11-08 | 2017-11-15 |  | Chaurideurali | 3
10173 | Kavrepalanchok | MajhiFeda | 9 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2017-11-08 | 2017-11-15 |  | Chaurideurali | 3
10174 | Kavrepalanchok | NagreGagarche | 1 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2017-11-09 | 2017-11-16 |  | Chaurideurali | 2
10175 | Kavrepalanchok | NagreGagarche | 2 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2017-11-09 | 2017-11-16 |  | Chaurideurali | 2
10176 | Kavrepalanchok | NagreGagarche | 3 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 48 | 48 | 2017-11-09 | 2017-11-16 |  | Chaurideurali | 2
10177 | Kavrepalanchok | Baldthali | 1 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | financial amount per beneficiary Rs.50,000/- | # of households | Yes | Ongoing | 65 | 62 |  |  |  | Panauti | 11
10178 | Kavrepalanchok | Baldthali | 1 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | financial amount per beneficiary Rs.1,50,000/- | # of households | Yes | Ongoing | 65 | 37 |  |  |  | Panauti | 11
10179 | Kavrepalanchok | Baldthali | 1 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | financial amount per beneficiary Rs.1,00,000/- | # of households | Yes | Ongoing | 65 | 29 |  |  |  | Panauti | 11
10180 | Kavrepalanchok | Baldthali | 2 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | financial amount per beneficiary Rs.50,000/- | # of households | Yes | Ongoing | 18 | 23 |  |  |  | Panauti | 11
10181 | Kavrepalanchok | Baldthali | 2 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | financial amount per beneficiary Rs.1,50,000/- | # of households | Yes | Ongoing | 18 | 33 |  |  |  | Panauti | 11
10182 | Kavrepalanchok | Baldthali | 2 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | financial amount per beneficiary Rs.1,00,000/- | # of households | Yes | Ongoing | 18 | 11 |  |  |  | Panauti | 11
10183 | Kavrepalanchok | Baldthali | 3 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | financial amount per beneficiary Rs.50,000/- | # of households | Yes | Ongoing | 36 | 52 |  |  |  | Panauti | 11
10184 | Kavrepalanchok | Baldthali | 3 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | financial amount per beneficiary Rs.1,50,000/- | # of households | Yes | Ongoing | 36 | 28 |  |  |  | Panauti | 11
10185 | Kavrepalanchok | Baldthali | 3 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | financial amount per beneficiary Rs.1,00,000/- | # of households | Yes | Ongoing | 36 | 15 |  |  |  | Panauti | 11
10186 | Kavrepalanchok | Baldthali | 4 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | financial amount per beneficiary Rs.50,000/- | # of households | Yes | Ongoing | 53 | 48 |  |  |  | Panauti | 11
10187 | Kavrepalanchok | Baldthali | 4 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | financial amount per beneficiary Rs.1,50,000/- | # of households | Yes | Ongoing | 53 | 34 |  |  |  | Panauti | 11
10188 | Kavrepalanchok | Baldthali | 4 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | financial amount per beneficiary Rs.1,00,000/- | # of households | Yes | Ongoing | 53 | 21 |  |  |  | Panauti | 11
10189 | Kavrepalanchok | Baldthali | 5 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | financial amount per beneficiary Rs.50,000/- | # of households | Yes | Ongoing | 181 | 165 |  |  |  | Panauti | 11
10190 | Kavrepalanchok | Baldthali | 5 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | financial amount per beneficiary Rs.1,50,000/- | # of households | Yes | Ongoing | 181 | 156 |  |  |  | Panauti | 11
10191 | Kavrepalanchok | Baldthali | 5 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | financial amount per beneficiary Rs.1,00,000/- | # of households | Yes | Ongoing | 181 | 91 |  |  |  | Panauti | 11
10192 | Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | financial amount per beneficiary Rs.50,000/- | # of households | Yes | Ongoing | 67 | 62 |  |  |  | Panauti | 11
10193 | Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | financial amount per beneficiary Rs.1,50,000/- | # of households | Yes | Ongoing | 67 | 64 |  |  |  | Panauti | 11
10194 | Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | financial amount per beneficiary Rs.1,00,000/- | # of households | Yes | Ongoing | 67 | 33 |  |  |  | Panauti | 11
10195 | Kavrepalanchok | Baldthali | 7 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | financial amount per beneficiary Rs.50,000/- | # of households | Yes | Ongoing | 42 | 41 |  |  |  | Panauti | 11
10196 | Kavrepalanchok | Baldthali | 7 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | financial amount per beneficiary Rs.1,50,000/- | # of households | Yes | Ongoing | 42 | 28 |  |  |  | Panauti | 11
10197 | Kavrepalanchok | Baldthali | 7 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | financial amount per beneficiary Rs.1,00,000/- | # of households | Yes | Ongoing | 42 | 13 |  |  |  | Panauti | 11
10198 | Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | financial amount per beneficiary Rs.50,000/- | # of households | Yes | Ongoing | 24 | 23 |  |  |  | Panauti | 11
10199 | Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | financial amount per beneficiary Rs.1,50,000/- | # of households | Yes | Ongoing | 24 | 16 |  |  |  | Panauti | 11
10200 | Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | financial amount per beneficiary Rs.1,00,000/- | # of households | Yes | Ongoing | 24 | 9 |  |  |  | Panauti | 11
10201 | Kavrepalanchok | Baldthali | 9 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | financial amount per beneficiary Rs.50,000/- | # of households | Yes | Ongoing | 60 | 56 |  |  |  | Panauti | 11
10202 | Kavrepalanchok | Baldthali | 9 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | financial amount per beneficiary Rs.1,50,000/- | # of households | Yes | Ongoing | 60 | 53 |  |  |  | Panauti | 11
10203 | Kavrepalanchok | Baldthali | 9 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | financial amount per beneficiary Rs.1,00,000/- | # of households | Yes | Ongoing | 60 | 28 |  |  |  | Panauti | 11
10204 | Kavrepalanchok | ChandeniMandan | 1 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | financial amount per beneficiary Rs.50,000/- | # of households | Yes | Ongoing | 174 | 174 |  |  |  | Mandandeupur | 9
10205 | Kavrepalanchok | ChandeniMandan | 1 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | financial amount per beneficiary Rs.1,50,000/- | # of households | Yes | Ongoing | 174 | 161 |  |  |  | Mandandeupur | 9
10206 | Kavrepalanchok | ChandeniMandan | 1 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | financial amount per beneficiary Rs.1,00,000/- | # of households | Yes | Ongoing | 174 | 125 |  |  |  | Mandandeupur | 9
10207 | Kavrepalanchok | ChandeniMandan | 2 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | financial amount per beneficiary Rs.50,000/- | # of households | Yes | Ongoing | 90 | 88 |  |  |  | Mandandeupur | 9
10208 | Kavrepalanchok | ChandeniMandan | 2 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | financial amount per beneficiary Rs.1,50,000/- | # of households | Yes | Ongoing | 90 | 84 |  |  |  | Mandandeupur | 9
10209 | Kavrepalanchok | ChandeniMandan | 2 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | financial amount per beneficiary Rs.1,00,000/- | # of households | Yes | Ongoing | 90 | 53 |  |  |  | Mandandeupur | 9
10210 | Kavrepalanchok | ChandeniMandan | 3 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | financial amount per beneficiary Rs.50,000/- | # of households | Yes | Ongoing | 63 | 63 |  |  |  | Mandandeupur | 9
10211 | Kavrepalanchok | ChandeniMandan | 3 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | financial amount per beneficiary Rs.1,50,000/- | # of households | Yes | Ongoing | 63 | 58 |  |  |  | Mandandeupur | 9
10212 | Kavrepalanchok | ChandeniMandan | 3 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | financial amount per beneficiary Rs.1,00,000/- | # of households | Yes | Ongoing | 63 | 38 |  |  |  | Mandandeupur | 9
10213 | Kavrepalanchok | ChandeniMandan | 4 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | financial amount per beneficiary Rs.50,000/- | # of households | Yes | Ongoing | 128 | 126 |  |  |  | Mandandeupur | 9
10214 | Kavrepalanchok | ChandeniMandan | 4 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | financial amount per beneficiary Rs.1,50,000/- | # of households | Yes | Ongoing | 128 | 117 |  |  |  | Mandandeupur | 9
10215 | Kavrepalanchok | Sanowangthali | 1 | CARITAS-N | CARITAS-N | CARITAS | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-11-15 | 2017-11-21 |  | Chaurideurali | 1
10216 | Kavrepalanchok | ChandeniMandan | 4 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | financial amount per beneficiary Rs.1,00,000/- | # of households | Yes | Ongoing | 128 | 65 |  |  |  | Mandandeupur | 9
10217 | Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | financial amount per beneficiary Rs.50,000/- | # of households | Yes | Ongoing | 178 | 170 |  |  |  | Mandandeupur | 9
10218 | Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | financial amount per beneficiary Rs.1,50,000/- | # of households | Yes | Ongoing | 178 | 157 |  |  |  | Mandandeupur | 9
10219 | Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | financial amount per beneficiary Rs.1,00,000/- | # of households | Yes | Ongoing | 178 | 121 |  |  |  | Mandandeupur | 9
10220 | Kavrepalanchok | ChandeniMandan | 6 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | financial amount per beneficiary Rs.50,000/- | # of households | Yes | Ongoing | 160 | 152 |  |  |  | Mandandeupur | 9
10221 | Kavrepalanchok | ChandeniMandan | 6 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | financial amount per beneficiary Rs.1,50,000/- | # of households | Yes | Ongoing | 160 | 137 |  |  |  | Mandandeupur | 9
10222 | Kavrepalanchok | ChandeniMandan | 6 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | financial amount per beneficiary Rs.1,00,000/- | # of households | Yes | Ongoing | 160 | 66 |  |  |  | Mandandeupur | 9
10223 | Kavrepalanchok | ChandeniMandan | 7 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | financial amount per beneficiary Rs.50,000/- | # of households | Yes | Ongoing | 63 | 58 |  |  |  | Mandandeupur | 9
10224 | Kavrepalanchok | ChandeniMandan | 7 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | financial amount per beneficiary Rs.1,50,000/- | # of households | Yes | Ongoing | 63 | 26 |  |  |  | Mandandeupur | 9
10225 | Kavrepalanchok | ChandeniMandan | 7 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | financial amount per beneficiary Rs.1,00,000/- | # of households | Yes | Ongoing | 63 | 8 |  |  |  | Mandandeupur | 9
10226 | Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | financial amount per beneficiary Rs.50,000/- | # of households | Yes | Ongoing | 123 | 122 |  |  |  | Mandandeupur | 9
10227 | Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | financial amount per beneficiary Rs.1,50,000/- | # of households | Yes | Ongoing | 123 | 107 |  |  |  | Mandandeupur | 9
10228 | Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | financial amount per beneficiary Rs.1,00,000/- | # of households | Yes | Ongoing | 123 | 53 |  |  |  | Mandandeupur | 9
10229 | Kavrepalanchok | ChandeniMandan | 9 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | financial amount per beneficiary Rs.50,000/- | # of households | Yes | Ongoing | 86 | 86 |  |  |  | Mandandeupur | 9
10230 | Kavrepalanchok | ChandeniMandan | 9 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | financial amount per beneficiary Rs.1,50,000/- | # of households | Yes | Ongoing | 86 | 80 |  |  |  | Mandandeupur | 9
10231 | Kavrepalanchok | ChandeniMandan | 9 | CARITAS-N | CARITAS-N | CARITAS | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | financial amount per beneficiary Rs.1,00,000/- | # of households | Yes | Ongoing | 86 | 60 |  |  |  | Mandandeupur | 9
10232 | Kavrepalanchok | Choubas | 1 | HELVETAS | JAYAN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 10 | 10 | 2017-03-05 | 2017-04-30 | Verified | Bhumlu | 4
10233 | Kavrepalanchok | Dhunkharka | 1 | BC | ARSOW-N | BC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre |  | # of participants | Yes | Completed | 129 | 129 | 2016-03-24 | 2016-03-24 |  | Bethanchowk | 3
10234 | Kavrepalanchok | RyaleBhir | 5 | NCRS | NCRS | SP | Reconstruction through contractors | Construction | Private house | Model house smc 1.1 | # of constructions | Yes | Completed | 1 | 1 | 2016-10-20 | 2016-12-31 |  | Panauti | 1
10235 | Kavrepalanchok | Sarasyunkhark | 1 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Temal | 1
10236 | Kavrepalanchok | Sarasyunkhark | 2 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10237 | Kavrepalanchok | Sarasyunkhark | 3 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Temal | 1
10238 | Kavrepalanchok | Sarasyunkhark | 4 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 4 | 4 | 2016-01-01 | 2018-12-31 |  | Temal | 1
10239 | Kavrepalanchok | Sarasyunkhark | 5 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10240 | Kavrepalanchok | Sarasyunkhark | 6 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10241 | Kavrepalanchok | Sarasyunkhark | 7 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10242 | Kavrepalanchok | Sarasyunkhark | 8 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 4 | 4 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10243 | Kavrepalanchok | Sarasyunkhark | 9 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 4 | 4 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10244 | Kavrepalanchok | Sarasyunkhark | 1 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Temal | 1
10245 | Kavrepalanchok | Sarasyunkhark | 2 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10246 | Kavrepalanchok | Sarasyunkhark | 3 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Temal | 1
10247 | Kavrepalanchok | Sarasyunkhark | 4 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Temal | 1
10248 | Kavrepalanchok | Sarasyunkhark | 5 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10249 | Kavrepalanchok | Sarasyunkhark | 6 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10250 | Kavrepalanchok | Sarasyunkhark | 7 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10251 | Kavrepalanchok | Sarasyunkhark | 8 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10252 | Kavrepalanchok | Sarasyunkhark | 9 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10253 | Kavrepalanchok | PokhariNarayansthan | 1 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Temal | 5
10254 | Kavrepalanchok | PokhariNarayansthan | 2 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Temal | 5
10255 | Kavrepalanchok | PokhariNarayansthan | 3 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Temal | 5
10256 | Kavrepalanchok | PokhariNarayansthan | 4 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Temal | 5
10257 | Kavrepalanchok | PokhariNarayansthan | 5 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Temal | 5
10258 | Kavrepalanchok | PokhariNarayansthan | 6 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Temal | 5
10259 | Kavrepalanchok | PokhariNarayansthan | 7 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Temal | 5
10260 | Kavrepalanchok | PokhariNarayansthan | 8 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Temal | 5
10261 | Kavrepalanchok | PokhariNarayansthan | 9 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Temal | 5
10262 | Kavrepalanchok | JyamdiMandan | 1 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Mandandeupur | 11
10263 | Kavrepalanchok | JyamdiMandan | 2 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Mandandeupur | 11
10264 | Kavrepalanchok | JyamdiMandan | 3 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Mandandeupur | 11
10265 | Kavrepalanchok | JyamdiMandan | 4 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Mandandeupur | 11
10266 | Kavrepalanchok | JyamdiMandan | 5 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 9
10267 | Kavrepalanchok | JyamdiMandan | 6 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Mandandeupur | 11
10268 | Kavrepalanchok | JyamdiMandan | 7 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 9
10269 | Kavrepalanchok | JyamdiMandan | 8 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 9
10270 | Kavrepalanchok | JyamdiMandan | 9 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 9
10271 | Kavrepalanchok | Dolalghat | 1 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10272 | Kavrepalanchok | Dolalghat | 2 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10273 | Kavrepalanchok | Dolalghat | 3 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10274 | Kavrepalanchok | Dolalghat | 4 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10275 | Kavrepalanchok | Dolalghat | 5 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10276 | Kavrepalanchok | Dolalghat | 6 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10277 | Kavrepalanchok | Dolalghat | 7 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10278 | Kavrepalanchok | Dolalghat | 8 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10279 | Kavrepalanchok | Dolalghat | 9 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10280 | Kavrepalanchok | Kharelthok | 1 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10281 | Kavrepalanchok | Kharelthok | 2 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10282 | Kavrepalanchok | Kharelthok | 3 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10283 | Kavrepalanchok | Kharelthok | 4 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10284 | Kavrepalanchok | Kharelthok | 5 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10285 | Kavrepalanchok | Kharelthok | 6 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10286 | Kavrepalanchok | Kharelthok | 7 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10287 | Kavrepalanchok | Kharelthok | 8 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10288 | Kavrepalanchok | Kharelthok | 9 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10289 | Kavrepalanchok | Dolalghat | 1 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10290 | Kavrepalanchok | Dolalghat | 2 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10291 | Kavrepalanchok | Dolalghat | 3 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10292 | Kavrepalanchok | Dolalghat | 4 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10293 | Kavrepalanchok | Dolalghat | 5 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10294 | Kavrepalanchok | Dolalghat | 6 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10295 | Kavrepalanchok | Dolalghat | 7 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10296 | Kavrepalanchok | Dolalghat | 8 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10297 | Kavrepalanchok | Dolalghat | 9 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10298 | Kavrepalanchok | JyamdiMandan | 1 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Mandandeupur | 11
10299 | Kavrepalanchok | JyamdiMandan | 2 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Mandandeupur | 11
10300 | Kavrepalanchok | JyamdiMandan | 3 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Mandandeupur | 11
10301 | Kavrepalanchok | JyamdiMandan | 4 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Mandandeupur | 11
10302 | Kavrepalanchok | JyamdiMandan | 5 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 9
10303 | Kavrepalanchok | JyamdiMandan | 6 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Mandandeupur | 11
10304 | Kavrepalanchok | JyamdiMandan | 7 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 9
10305 | Kavrepalanchok | JyamdiMandan | 8 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 9
10306 | Kavrepalanchok | JyamdiMandan | 9 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 9
10307 | Kavrepalanchok | Kharelthok | 1 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10308 | Kavrepalanchok | Kharelthok | 2 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10309 | Kavrepalanchok | Kharelthok | 3 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10310 | Kavrepalanchok | Kharelthok | 4 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10311 | Kavrepalanchok | Kharelthok | 5 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10312 | Kavrepalanchok | Kharelthok | 6 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10313 | Kavrepalanchok | Kharelthok | 7 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10314 | Kavrepalanchok | Kharelthok | 8 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10315 | Kavrepalanchok | Kharelthok | 9 | NRCS | NRCS | DRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10316 | Kavrepalanchok | JyamdiMandan | 1 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Mandandeupur | 11
10317 | Kavrepalanchok | JyamdiMandan | 2 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Completed | 4 | 4 | 2016-01-01 | 2018-12-31 |  | Mandandeupur | 11
10318 | Kavrepalanchok | JyamdiMandan | 3 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Mandandeupur | 11
10319 | Kavrepalanchok | JyamdiMandan | 4 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Mandandeupur | 11
10320 | Kavrepalanchok | JyamdiMandan | 5 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 9
10321 | Kavrepalanchok | JyamdiMandan | 6 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Mandandeupur | 11
10322 | Kavrepalanchok | JyamdiMandan | 8 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 9
10323 | Kavrepalanchok | Dolalghat | 3 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10324 | Kavrepalanchok | Dolalghat | 7 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10325 | Kavrepalanchok | Dolalghat | 8 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10326 | Kavrepalanchok | Dolalghat | 9 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10327 | Kavrepalanchok | Kharelthok | 1 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10328 | Kavrepalanchok | Kharelthok | 3 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10329 | Kavrepalanchok | Kharelthok | 4 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10330 | Kavrepalanchok | Kharelthok | 5 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10331 | Kavrepalanchok | Sarasyunkhark | 1 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Planned | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Temal | 1
10332 | Kavrepalanchok | Sarasyunkhark | 2 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Planned | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10333 | Kavrepalanchok | Sarasyunkhark | 3 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Planned | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Temal | 1
10334 | Kavrepalanchok | Sarasyunkhark | 4 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Planned | 3 | 0 | 2016-01-01 | 2018-12-31 |  | Temal | 1
10335 | Kavrepalanchok | Sarasyunkhark | 5 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Planned | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10336 | Kavrepalanchok | Sarasyunkhark | 6 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Planned | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10337 | Kavrepalanchok | Sarasyunkhark | 7 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Planned | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10338 | Kavrepalanchok | Sarasyunkhark | 8 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Planned | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10339 | Kavrepalanchok | Sarasyunkhark | 9 | NRCS | NRCS | DRC | Training | Short training | Plumber | Capacity building - Short training for plumber | # of trainees |  | Planned | 3 | 0 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10340 | Kavrepalanchok | JyamdiMandan | 1 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2017-10-01 | 2017-11-15 |  | Mandandeupur | 11
10341 | Kavrepalanchok | JyamdiMandan | 2 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 3 | 1 | 2017-10-01 | 2017-11-15 |  | Mandandeupur | 11
10342 | Kavrepalanchok | JyamdiMandan | 3 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 4 | 2017-10-01 | 2017-11-15 |  | Mandandeupur | 11
10343 | Kavrepalanchok | JyamdiMandan | 4 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2017-10-01 | 2017-11-15 |  | Mandandeupur | 11
10344 | Kavrepalanchok | JyamdiMandan | 5 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 1 | 2017-10-01 | 2017-11-15 |  | Bhumlu | 9
10345 | Kavrepalanchok | JyamdiMandan | 6 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 3 | 3 | 2017-10-01 | 2017-11-15 |  | Mandandeupur | 11
10346 | Kavrepalanchok | JyamdiMandan | 7 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2017-10-01 | 2017-11-15 |  | Bhumlu | 9
10347 | Kavrepalanchok | JyamdiMandan | 8 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2017-10-01 | 2017-11-15 |  | Bhumlu | 9
10348 | Kavrepalanchok | JyamdiMandan | 9 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 3 | 2017-10-01 | 2017-11-15 |  | Bhumlu | 9
10349 | Kavrepalanchok | Dolalghat | 1 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2017-10-01 | 2017-11-15 |  | Bhumlu | 10
10350 | Kavrepalanchok | Dolalghat | 2 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 1 | 2017-10-01 | 2017-11-15 |  | Bhumlu | 10
10351 | Kavrepalanchok | Dolalghat | 3 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 3 | 3 | 2017-10-01 | 2017-11-15 |  | Bhumlu | 10
10352 | Kavrepalanchok | Dolalghat | 4 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 3 | 2017-10-01 | 2017-11-15 |  | Bhumlu | 10
10353 | Kavrepalanchok | Dolalghat | 5 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 3 | 2017-10-01 | 2017-11-15 |  | Bhumlu | 10
10354 | Kavrepalanchok | Dolalghat | 6 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 1 | 2017-10-01 | 2017-11-15 |  | Bhumlu | 10
10355 | Kavrepalanchok | Dolalghat | 7 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 3 | 2017-10-01 | 2017-11-15 |  | Bhumlu | 10
10356 | Kavrepalanchok | Dolalghat | 8 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 3 | 4 | 2017-10-01 | 2017-11-15 |  | Bhumlu | 10
10357 | Kavrepalanchok | Dolalghat | 9 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 3 | 2017-10-01 | 2017-11-15 |  | Bhumlu | 10
10358 | Kavrepalanchok | Kharelthok | 1 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 5 | 2017-10-01 | 2017-11-15 |  | Panchkhal | 11
10359 | Kavrepalanchok | Kharelthok | 2 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 1 | 2017-10-01 | 2017-11-15 |  | Panchkhal | 11
10360 | Kavrepalanchok | Kharelthok | 3 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2017-10-01 | 2017-11-15 |  | Panchkhal | 11
10361 | Kavrepalanchok | Kharelthok | 4 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2017-10-01 | 2017-11-15 |  | Panchkhal | 11
10362 | Kavrepalanchok | Kharelthok | 5 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2017-10-01 | 2017-11-15 |  | Panchkhal | 11
10363 | Kavrepalanchok | Kharelthok | 6 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 3 | 2017-10-01 | 2017-11-15 |  | Panchkhal | 11
10364 | Kavrepalanchok | Kharelthok | 7 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 3 | 4 | 2017-10-01 | 2017-11-15 |  | Panchkhal | 11
10365 | Kavrepalanchok | Kharelthok | 8 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 3 | 1 | 2017-10-01 | 2017-11-15 |  | Panchkhal | 11
10366 | Kavrepalanchok | Kharelthok | 9 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Completed | 2 | 2 | 2017-10-01 | 2017-11-15 |  | Panchkhal | 11
10367 | Kavrepalanchok | Sarasyunkhark | 1 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Planned | 3 | 0 | 2016-01-01 | 2018-12-31 |  | Temal | 1
10368 | Kavrepalanchok | Sarasyunkhark | 2 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Planned | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10369 | Kavrepalanchok | Sarasyunkhark | 3 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Planned | 3 | 0 | 2016-01-01 | 2018-12-31 |  | Temal | 1
10370 | Kavrepalanchok | Sarasyunkhark | 4 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Planned | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Temal | 1
10371 | Kavrepalanchok | Sarasyunkhark | 5 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Planned | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10372 | Kavrepalanchok | Sarasyunkhark | 6 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Planned | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10373 | Kavrepalanchok | Sarasyunkhark | 7 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Planned | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10374 | Kavrepalanchok | Sarasyunkhark | 8 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Planned | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10375 | Kavrepalanchok | Sarasyunkhark | 9 | NRCS | NRCS | DRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Planned | 2 | 0 | 2016-01-01 | 2018-12-31 |  | Temal | 2
10376 | Kavrepalanchok | JyamdiMandan | 1 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-01-01 | 2018-12-31 |  | Mandandeupur | 11
10377 | Kavrepalanchok | Dolalghat | 1 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-01-01 | 2018-12-31 |  | Bhumlu | 10
10378 | Kavrepalanchok | Kharelthok | 1 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2016-01-01 | 2018-12-31 |  | Panchkhal | 11
10379 | Kavrepalanchok | Baldthali | 1 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | Top Ups | Transportation for remote areas |  | # of households |  | Ongoing | 30 | 52 |  |  |  | Panauti | 11
10380 | Kavrepalanchok | Baldthali | 2 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | Top Ups | Transportation for remote areas |  | # of households |  | Ongoing | 13 | 18 |  |  |  | Panauti | 11
10381 | Kavrepalanchok | Baldthali | 3 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | Top Ups | Transportation for remote areas |  | # of households |  | Ongoing | 16 | 28 |  |  |  | Panauti | 11
10382 | Kavrepalanchok | Baldthali | 4 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | Top Ups | Transportation for remote areas |  | # of households |  | Ongoing | 19 | 34 |  |  |  | Panauti | 11
10383 | Kavrepalanchok | Baldthali | 5 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | Top Ups | Transportation for remote areas |  | # of households |  | Ongoing | 93 | 157 |  |  |  | Panauti | 11
10384 | Kavrepalanchok | Baldthali | 6 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | Top Ups | Transportation for remote areas |  | # of households |  | Ongoing | 45 | 63 |  |  |  | Panauti | 11
10385 | Kavrepalanchok | Baldthali | 7 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | Top Ups | Transportation for remote areas |  | # of households |  | Ongoing | 14 | 29 |  |  |  | Panauti | 11
10386 | Kavrepalanchok | Baldthali | 8 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | Top Ups | Transportation for remote areas |  | # of households |  | Ongoing | 10 | 16 |  |  |  | Panauti | 11
10387 | Kavrepalanchok | Baldthali | 9 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | Top Ups | Transportation for remote areas |  | # of households |  | Ongoing | 28 | 52 |  |  |  | Panauti | 11
10388 | Kavrepalanchok | ChandeniMandan | 1 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | Top Ups | Transportation for remote areas |  | # of households |  | Ongoing | 102 | 182 |  |  |  | Mandandeupur | 9
10389 | Kavrepalanchok | ChandeniMandan | 2 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | Top Ups | Transportation for remote areas |  | # of households |  | Ongoing | 61 | 86 |  |  |  | Mandandeupur | 9
10390 | Kavrepalanchok | ChandeniMandan | 3 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | Top Ups | Transportation for remote areas |  | # of households |  | Ongoing | 72 | 64 |  |  |  | Mandandeupur | 9
10391 | Kavrepalanchok | ChandeniMandan | 4 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | Top Ups | Transportation for remote areas |  | # of households |  | Ongoing | 86 | 116 |  |  |  | Mandandeupur | 9
10392 | Kavrepalanchok | ChandeniMandan | 5 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | Top Ups | Transportation for remote areas |  | # of households |  | Ongoing | 82 | 165 |  |  |  | Mandandeupur | 9
10393 | Kavrepalanchok | ChandeniMandan | 6 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | Top Ups | Transportation for remote areas |  | # of households |  | Ongoing | 132 | 120 |  |  |  | Mandandeupur | 9
10394 | Kavrepalanchok | ChandeniMandan | 7 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | Top Ups | Transportation for remote areas |  | # of households |  | Ongoing | 9 | 21 |  |  |  | Mandandeupur | 9
10395 | Kavrepalanchok | ChandeniMandan | 8 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | Top Ups | Transportation for remote areas |  | # of households |  | Ongoing | 73 | 115 |  |  |  | Mandandeupur | 9
10396 | Kavrepalanchok | ChandeniMandan | 9 | CARITAS-N | CARITAS-N | CARITAS-N | Financial/Material/Labour Assistance | Top Ups | Transportation for remote areas |  | # of households |  | Ongoing | 63 | 74 |  |  |  | Mandandeupur | 9
10397 | Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Training | Vocational training | Electrician (CTEVT) | Vocational training for electrician according to CTEVT curriculam | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Panchkhal | 6
10398 | Kavrepalanchok | Panchkhal N.P. | 5 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Drawings | # of households supported | Yes | Ongoing | 1000 | 725 | 2017-03-01 | 2017-07-31 | The total target from ward 1 to 5 is 1000 where total reached from 1 to 5 is 442 others are yet to receive | Panchkhal | 6
10399 | Kavrepalanchok | PokhariChauri | 2 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 39 | 39 | 2017-06-12 | 2017-06-18 |  | Chaurideurali | 5
10400 | Kavrepalanchok | Falemetar | 2 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 65 | 65 | 2017-06-12 | 2017-06-18 |  | Khanikhola | 2
10401 | Kavrepalanchok | ChyasingKharka | 2 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 35 | 2017-06-12 | 2017-06-18 |  | Bethanchowk | 5
10402 | Kavrepalanchok | Bhimkhori | 2 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 35 | 2017-06-12 | 2017-06-18 |  | Roshi | 11
10403 | Kavrepalanchok | KatunjeBesi | 2 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 35 | 2017-06-12 | 2017-06-18 |  | Roshi | 7
10404 | Kavrepalanchok | KhaharePangu | 2 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-06-12 | 2017-06-18 |  | Roshi | 1
10405 | Kavrepalanchok | SikharAmbote | 2 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 29 | 29 | 2017-06-12 | 2017-06-18 |  | Roshi | 3
10406 | Kavrepalanchok | KanpurKalapani | 2 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 34 | 34 | 2017-06-12 | 2017-06-18 |  | Namobuddha | 5
10407 | Kavrepalanchok | Panchkhal N.P. | 5 | BVBM | BVBM | BVBM | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households supported |  | Completed | 220 | 142 |  |  |  | Panchkhal | 6
10408 | Kavrepalanchok | Panchkhal N.P. | 5 | BVBM | BVBM | BVBM | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households supported |  | Completed | 220 | 110 |  |  |  | Panchkhal | 6
10409 | Makwanpur | Kalikatar | 2 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | No | Completed | 2 | 2 | 2017-02-23 | 2017-05-23 | Demo house was constructed during mason training. | Kailash | 4
10410 | Makwanpur | Agara | 3 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Thaha | 7
10411 | Makwanpur | Agara | 3 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Thaha | 7
10412 | Makwanpur | Agara | 3 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Thaha | 7
10413 | Makwanpur | Ambhanjyang | 3 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 5
10414 | Makwanpur | Ambhanjyang | 7 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 6
10415 | Makwanpur | Ambhanjyang | 8 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 6
10416 | Makwanpur | Ambhanjyang | 9 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Makawanpurgadhi | 6
10417 | Makwanpur | Ambhanjyang | 9 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Makawanpurgadhi | 6
10418 | Makwanpur | Ambhanjyang | 9 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 6
10419 | Makwanpur | Betini | 1 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 33 | 33 |  |  |  | Bagmati | 9
10420 | Makwanpur | Betini | 2 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 15 | 15 |  |  |  | Bagmati | 9
10421 | Makwanpur | Betini | 2 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Bagmati | 9
10422 | Makwanpur | Betini | 3 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 63 | 63 |  |  |  | Bagmati | 9
10423 | Makwanpur | Betini | 4 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 19 | 19 |  |  |  | Bagmati | 9
10424 | Makwanpur | Betini | 5 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 28 | 28 |  |  |  | Bagmati | 9
10425 | Makwanpur | Betini | 5 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10426 | Makwanpur | Betini | 5 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10427 | Makwanpur | Betini | 6 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 15 | 15 |  |  |  | Bagmati | 9
10428 | Makwanpur | Betini | 7 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 30 | 30 |  |  |  | Bagmati | 9
10429 | Makwanpur | Betini | 8 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 54 | 54 |  |  |  | Bagmati | 9
10430 | Makwanpur | Betini | 9 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 33 | 33 |  |  |  | Bagmati | 9
10431 | Makwanpur | Bhaise | 1 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 2
10432 | Makwanpur | Bhaise | 1 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 2
10433 | Makwanpur | Bhaise | 1 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Bhimphedi | 2
10434 | Makwanpur | Bhaise | 2 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 2
10435 | Makwanpur | Bhaise | 4 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Bhimphedi | 2
10436 | Makwanpur | Bhaise | 9 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 2
10437 | Makwanpur | BhartaPundyadevi | 2 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Kailash | 8
10438 | Makwanpur | BhartaPundyadevi | 4 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Kailash | 7
10439 | Makwanpur | Bhimfedi | 5 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Bhimphedi | 5
10440 | Makwanpur | Bhimfedi | 9 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 5
10441 | Makwanpur | Budhichaur | 1 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 15 | 15 |  |  |  | Makawanpurgadhi | 8
10442 | Makwanpur | Budhichaur | 1 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Makawanpurgadhi | 8
10443 | Makwanpur | Budhichaur | 2 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 11 | 11 |  |  |  | Makawanpurgadhi | 8
10444 | Makwanpur | Budhichaur | 3 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 9 | 9 |  |  |  | Makawanpurgadhi | 8
10445 | Makwanpur | Budhichaur | 3 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Makawanpurgadhi | 8
10446 | Makwanpur | Budhichaur | 4 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 7 | 7 |  |  |  | Makawanpurgadhi | 8
10447 | Makwanpur | Budhichaur | 5 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 21 | 21 |  |  |  | Makawanpurgadhi | 8
10448 | Makwanpur | Budhichaur | 6 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 3 | 3 |  |  |  | Makawanpurgadhi | 8
10449 | Makwanpur | Budhichaur | 7 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 23 | 23 |  |  |  | Makawanpurgadhi | 8
10450 | Makwanpur | Budhichaur | 7 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10451 | Makwanpur | Budhichaur | 8 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 14 | 14 |  |  |  | Makawanpurgadhi | 8
10452 | Makwanpur | Budhichaur | 9 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 14 | 14 |  |  |  | Makawanpurgadhi | 8
10453 | Makwanpur | Chitlang | 1 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 8 | 8 |  |  |  | Thaha | 9
10454 | Makwanpur | Chitlang | 1 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 8 | 8 |  |  |  | Thaha | 9
10455 | Makwanpur | Chitlang | 1 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 21 | 21 |  |  |  | Thaha | 9
10456 | Makwanpur | Chitlang | 1 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 65 |  |  |  | Thaha | 9
10457 | Makwanpur | Chitlang | 1 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Thaha | 9
10458 | Makwanpur | Chitlang | 1 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Thaha | 9
10459 | Makwanpur | Chitlang | 1 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 2 |  |  |  | Thaha | 9
10460 | Makwanpur | Chitlang | 2 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 14 | 14 |  |  |  | Thaha | 9
10461 | Makwanpur | Chitlang | 2 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 14 | 14 |  |  |  | Thaha | 9
10462 | Makwanpur | Chitlang | 2 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Ongoing | 13 | 9 |  |  |  | Thaha | 9
10463 | Makwanpur | Chitlang | 2 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 61 |  |  |  | Thaha | 9
10464 | Makwanpur | Chitlang | 2 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Thaha | 9
10465 | Makwanpur | Chitlang | 2 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Thaha | 9
10466 | Makwanpur | Chitlang | 2 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Thaha | 9
10467 | Makwanpur | Chitlang | 3 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 7 | 7 |  |  |  | Thaha | 9
10468 | Makwanpur | Chitlang | 3 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 7 | 7 |  |  |  | Thaha | 9
10469 | Makwanpur | Chitlang | 3 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 20 | 20 |  |  |  | Thaha | 9
10470 | Makwanpur | Chitlang | 3 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 56 |  |  |  | Thaha | 9
10471 | Makwanpur | Chitlang | 3 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Thaha | 9
10472 | Makwanpur | Chitlang | 3 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Thaha | 9
10473 | Makwanpur | Chitlang | 3 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Thaha | 9
10474 | Makwanpur | Chitlang | 4 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 18 | 18 |  |  |  | Thaha | 9
10475 | Makwanpur | Chitlang | 4 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 18 | 18 |  |  |  | Thaha | 9
10476 | Makwanpur | Chitlang | 4 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 14 | 14 |  |  |  | Thaha | 9
10477 | Makwanpur | Chitlang | 4 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 49 |  |  |  | Thaha | 9
10478 | Makwanpur | Chitlang | 4 | PLAN | CEEDF | ECHO | Technical Assistance | Demonstration Construction | House | 2 rooms, materials used: ciment, rod, aggregated sand, stone, mud, wood, CGI Sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Thaha | 9
10479 | Makwanpur | Chitlang | 4 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Thaha | 9
10480 | Makwanpur | Chitlang | 4 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Thaha | 9
10481 | Makwanpur | Chitlang | 4 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Thaha | 9
10482 | Makwanpur | Chitlang | 5 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 13 | 13 |  |  |  | Thaha | 9
10483 | Makwanpur | Chitlang | 5 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 13 | 13 |  |  |  | Thaha | 9
10484 | Makwanpur | Chitlang | 5 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 10 | 10 |  |  |  | Thaha | 9
10485 | Makwanpur | Chitlang | 5 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 45 |  |  |  | Thaha | 9
10486 | Makwanpur | Chitlang | 5 | PLAN | CEEDF | PLAN-GER | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | A VDC wise committee was formed by the chair of VDC secreatry and it has represnetatives from all wards of VDC. There are even representative from police office, Health Post, School and Political parties. | # of committees | Yes | Completed | 25 | 24 |  |  |  | Thaha | 9
10487 | Makwanpur | Chitlang | 5 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Thaha | 9
10488 | Makwanpur | Chitlang | 5 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Thaha | 9
10489 | Makwanpur | Chitlang | 5 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Thaha | 9
10490 | Makwanpur | Chitlang | 6 | ICCO | CCDN | ECHO | Financial/Material/Labour Assistance | Material support on household WASH | HH toilet repair/rehabilitation | A package of materials worth 9000 NPR per family | # of households | Yes | Completed | 5 | 5 |  |  |  | Thaha | 10
10491 | Makwanpur | Chitlang | 6 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 11 | 11 |  |  |  | Thaha | 10
10492 | Makwanpur | Chitlang | 6 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 15 | 15 |  |  |  | Thaha | 10
10493 | Makwanpur | Chitlang | 6 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 78 |  |  |  | Thaha | 10
10494 | Makwanpur | Chitlang | 6 | ICCO | CCDN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 10 | 3 |  |  |  | Thaha | 10
10495 | Makwanpur | Chitlang | 6 | ICCO | CCDN | ECHO | Training | Short training | Plumber | Self (prepared and emdrosed through MCSIO Mak) | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Thaha | 10
10496 | Makwanpur | Chitlang | 6 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Thaha | 10
10497 | Makwanpur | Chitlang | 6 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Thaha | 10
10498 | Makwanpur | Chitlang | 6 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 2 |  |  |  | Thaha | 10
10499 | Makwanpur | Chitlang | 7 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 11 | 11 |  |  |  | Thaha | 10
10500 | Makwanpur | Chitlang | 7 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 11 | 11 |  |  |  | Thaha | 10
10501 | Makwanpur | Chitlang | 7 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 16 | 16 |  |  |  | Thaha | 10
10502 | Makwanpur | Chitlang | 7 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 73 |  |  |  | Thaha | 10
10503 | Makwanpur | Chitlang | 7 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Thaha | 10
10504 | Makwanpur | Chitlang | 7 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Thaha | 10
10505 | Makwanpur | Chitlang | 7 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Thaha | 10
10506 | Makwanpur | Chitlang | 8 | ICCO | CCDN | ECHO | Financial/Material/Labour Assistance | Material support on household WASH | HH toilet repair/rehabilitation | A package of materials worth 9000 NPR per family | # of households | Yes | Completed | 5 | 5 |  |  |  | Thaha | 9
10507 | Makwanpur | Chitlang | 8 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 14 | 14 |  |  |  | Thaha | 9
10508 | Makwanpur | Chitlang | 8 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 14 | 14 |  |  |  | Thaha | 9
10509 | Makwanpur | Chitlang | 8 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 21 | 21 |  |  |  | Thaha | 9
10510 | Makwanpur | Chitlang | 8 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 80 |  |  |  | Thaha | 9
10511 | Makwanpur | Chitlang | 8 | ICCO | CCDN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 10 | 5 |  |  |  | Thaha | 9
10512 | Makwanpur | Chitlang | 8 | ICCO | CCDN | ECHO | Training | Short training | Plumber | Self (prepared and emdrosed through MCSIO Mak) | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Thaha | 9
10513 | Makwanpur | Chitlang | 8 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Thaha | 9
10514 | Makwanpur | Chitlang | 8 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Thaha | 9
10515 | Makwanpur | Chitlang | 8 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 2 |  |  |  | Thaha | 9
10516 | Makwanpur | Chitlang | 9 | ICCO | CCDN | ECHO | Financial/Material/Labour Assistance | Material support on household WASH | HH toilet repair/rehabilitation | A package of materials worth 9000 NPR per family | # of households | Yes | Completed | 5 | 5 |  |  |  | Thaha | 10
10517 | Makwanpur | Chitlang | 9 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 29 | 29 |  |  |  | Thaha | 10
10518 | Makwanpur | Chitlang | 9 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 23 | 23 |  |  |  | Thaha | 10
10519 | Makwanpur | Chitlang | 9 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 90 |  |  |  | Thaha | 10
10520 | Makwanpur | Chitlang | 9 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Thaha | 10
10521 | Makwanpur | Chitlang | 9 | ICCO | CCDN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 10 | 12 |  |  |  | Thaha | 10
10522 | Makwanpur | Chitlang | 9 | ICCO | CCDN | ECHO | Training | Short training | Plumber | Self (prepared and emdrosed through MCSIO Mak) | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Thaha | 10
10523 | Makwanpur | Chitlang | 9 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Thaha | 10
10524 | Makwanpur | Chitlang | 9 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Thaha | 10
10525 | Makwanpur | Chitlang | 9 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Thaha | 10
10526 | Makwanpur | Dandakharka | 9 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Kailash | 2
10527 | Makwanpur | Dhimal | 5 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 1
10528 | Makwanpur | Fakhel | 1 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 18 | 18 |  |  |  | Indrasarowar | 4
10529 | Makwanpur | Fakhel | 1 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 18 | 18 |  |  |  | Indrasarowar | 4
10530 | Makwanpur | Fakhel | 1 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 31 | 31 |  |  |  | Indrasarowar | 4
10531 | Makwanpur | Fakhel | 1 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 50 |  |  |  | Indrasarowar | 4
10532 | Makwanpur | Fakhel | 1 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 4
10533 | Makwanpur | Fakhel | 1 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 4
10534 | Makwanpur | Fakhel | 1 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 4
10535 | Makwanpur | Fakhel | 2 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 11 | 11 |  |  |  | Indrasarowar | 4
10536 | Makwanpur | Fakhel | 2 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 11 | 11 |  |  |  | Indrasarowar | 4
10537 | Makwanpur | Fakhel | 2 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 28 | 28 |  |  |  | Indrasarowar | 4
10538 | Makwanpur | Fakhel | 2 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 51 |  |  |  | Indrasarowar | 4
10539 | Makwanpur | Fakhel | 2 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 4
10540 | Makwanpur | Fakhel | 2 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 4
10541 | Makwanpur | Fakhel | 2 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 2 |  |  |  | Indrasarowar | 4
10542 | Makwanpur | Fakhel | 3 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 18 | 18 |  |  |  | Indrasarowar | 4
10543 | Makwanpur | Fakhel | 3 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 18 | 18 |  |  |  | Indrasarowar | 4
10544 | Makwanpur | Fakhel | 3 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 29 | 29 |  |  |  | Indrasarowar | 4
10545 | Makwanpur | Fakhel | 3 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 50 |  |  |  | Indrasarowar | 4
10546 | Makwanpur | Fakhel | 3 | PLAN | CEEDF | ECHO | Technical Assistance | Demonstration Construction | House | 2 rooms, materials used: ciment, rod, aggregated sand, stone, mud, wood, CGI Sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 4
10547 | Makwanpur | Fakhel | 3 | PLAN | CEEDF | PLAN-GER | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | A VDC wise committee was formed by the chair of VDC secreatry and it has represnetatives from all wards of VDC. There are even representative from police office, Health Post, School and Political parties. | # of committees | Yes | Completed | 25 | 27 |  |  |  | Indrasarowar | 4
10548 | Makwanpur | Fakhel | 3 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Indrasarowar | 4
10549 | Makwanpur | Fakhel | 3 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 4
10550 | Makwanpur | Fakhel | 3 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 4
10551 | Makwanpur | Fakhel | 4 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 20 | 20 |  |  |  | Indrasarowar | 4
10552 | Makwanpur | Fakhel | 4 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 20 | 20 |  |  |  | Indrasarowar | 4
10553 | Makwanpur | Fakhel | 4 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 23 | 23 |  |  |  | Indrasarowar | 4
10554 | Makwanpur | Fakhel | 4 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 55 |  |  |  | Indrasarowar | 4
10555 | Makwanpur | Fakhel | 4 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Indrasarowar | 4
10556 | Makwanpur | Fakhel | 4 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 4
10557 | Makwanpur | Fakhel | 4 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 4 |  |  |  | Indrasarowar | 4
10558 | Makwanpur | Fakhel | 5 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 13 | 13 |  |  |  | Indrasarowar | 5
10559 | Makwanpur | Fakhel | 5 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 13 | 13 |  |  |  | Indrasarowar | 5
10560 | Makwanpur | Fakhel | 5 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Ongoing | 22 | 20 |  |  |  | Indrasarowar | 5
10561 | Makwanpur | Fakhel | 5 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 62 |  |  |  | Indrasarowar | 5
10562 | Makwanpur | Fakhel | 5 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 5
10563 | Makwanpur | Fakhel | 5 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 5
10564 | Makwanpur | Fakhel | 5 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 5
10565 | Makwanpur | Fakhel | 6 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 5 | 5 |  |  |  | Indrasarowar | 5
10566 | Makwanpur | Fakhel | 6 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 5 | 5 |  |  |  | Indrasarowar | 5
10567 | Makwanpur | Fakhel | 6 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 15 | 15 |  |  |  | Indrasarowar | 5
10568 | Makwanpur | Fakhel | 6 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 50 |  |  |  | Indrasarowar | 5
10569 | Makwanpur | Fakhel | 6 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Indrasarowar | 5
10570 | Makwanpur | Fakhel | 6 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 5
10571 | Makwanpur | Fakhel | 6 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 5
10572 | Makwanpur | Fakhel | 7 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 10 | 10 |  |  |  | Indrasarowar | 5
10573 | Makwanpur | Fakhel | 7 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 10 | 10 |  |  |  | Indrasarowar | 5
10574 | Makwanpur | Fakhel | 7 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Ongoing | 22 | 15 |  |  |  | Indrasarowar | 5
10575 | Makwanpur | Fakhel | 7 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 53 |  |  |  | Indrasarowar | 5
10576 | Makwanpur | Fakhel | 7 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 5
10577 | Makwanpur | Fakhel | 7 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 5
10578 | Makwanpur | Fakhel | 7 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 5
10579 | Makwanpur | Fakhel | 8 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 20 | 20 |  |  |  | Indrasarowar | 5
10580 | Makwanpur | Fakhel | 8 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 20 | 20 |  |  |  | Indrasarowar | 5
10581 | Makwanpur | Fakhel | 8 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 18 | 18 |  |  |  | Indrasarowar | 5
10582 | Makwanpur | Fakhel | 8 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 50 |  |  |  | Indrasarowar | 5
10583 | Makwanpur | Fakhel | 8 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 5
10584 | Makwanpur | Fakhel | 8 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 5
10585 | Makwanpur | Fakhel | 8 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Ongoing | 1 | 0 |  |  |  | Indrasarowar | 5
10586 | Makwanpur | Fakhel | 9 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 10 | 10 |  |  |  | Indrasarowar | 5
10587 | Makwanpur | Fakhel | 9 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 10 | 10 |  |  |  | Indrasarowar | 5
10588 | Makwanpur | Fakhel | 9 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 17 | 17 |  |  |  | Indrasarowar | 5
10589 | Makwanpur | Fakhel | 9 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 41 |  |  |  | Indrasarowar | 5
10590 | Makwanpur | Fakhel | 9 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Indrasarowar | 5
10591 | Makwanpur | Fakhel | 9 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 5
10592 | Makwanpur | Fakhel | 9 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 5
10593 | Makwanpur | Faparbari | 2 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 5
10594 | Makwanpur | Faparbari | 3 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 6
10595 | Makwanpur | Faparbari | 9 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 8
10596 | Makwanpur | Gogane | 1 | BC | CARD | ARC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2 hour per session | # of participants | Yes | Ongoing | 80 | 22 |  |  |  | Kailash | 5
10597 | Makwanpur | Gogane | 1 | BC | CARD | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 Social mobiliser, 1 engineer, 1 builder trainer ( Experienced mason) | # of households | Yes | Ongoing | 47 | 1 |  |  |  | Kailash | 5
10598 | Makwanpur | Gogane | 2 | BC | CARD | ARC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2 hour per session | # of participants | Yes | Ongoing | 40 | 0 |  |  |  | Kailash | 5
10599 | Makwanpur | Gogane | 2 | BC | CARD | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 Social mobiliser, 1 engineer, 1 builder trainer ( Experienced mason) | # of households | Yes | Ongoing | 39 | 2 |  |  |  | Kailash | 5
10600 | Makwanpur | Gogane | 2 | BC | CARD | ARC | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | 1 Architect, Engineer | # of households supported | Yes | Ongoing | 637 | 67 |  |  |  | Kailash | 5
10601 | Makwanpur | Gogane | 3 | BC | CARD | ARC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2 hour per session | # of participants | Yes | Ongoing | 60 | 30 |  |  |  | Kailash | 5
10602 | Makwanpur | Gogane | 3 | BC | CARD | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 Social mobiliser, 1 engineer, 1 builder trainer ( Experienced mason) | # of households | Yes | Ongoing | 46 | 2 |  |  |  | Kailash | 5
10603 | Makwanpur | Gogane | 4 | BC | CARD | ARC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2 hour per session | # of participants | Yes | Ongoing | 60 | 32 |  |  |  | Kailash | 5
10604 | Makwanpur | Gogane | 4 | BC | CARD | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 Social mobiliser, 1 engineer, 1 builder trainer ( Experienced mason) | # of households | Yes | Ongoing | 46 | 10 |  |  |  | Kailash | 5
10605 | Makwanpur | Gogane | 5 | BC | CARD | ARC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2 hour per session | # of participants | Yes | Ongoing | 60 | 27 |  |  |  | Kailash | 5
10606 | Makwanpur | Gogane | 5 | BC | CARD | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 Social mobiliser, 1 engineer, 1 builder trainer ( Experienced mason) | # of households | Yes | Ongoing | 64 | 2 |  |  |  | Kailash | 5
10607 | Makwanpur | Gogane | 6 | BC | CARD | ARC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2 hour per session | # of participants | Yes | Ongoing | 60 | 20 |  |  |  | Kailash | 5
10608 | Makwanpur | Gogane | 6 | BC | CARD | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 Social mobiliser, 1 engineer, 1 builder trainer ( Experienced mason) | # of households | Yes | Ongoing | 92 | 0 |  |  |  | Kailash | 5
10609 | Makwanpur | Gogane | 7 | BC | CARD | ARC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2 hour per session | # of participants | Yes | Ongoing | 80 | 0 |  |  |  | Kailash | 6
10610 | Makwanpur | Gogane | 7 | BC | CARD | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 Social mobiliser, 1 engineer, 1 builder trainer ( Experienced mason) | # of households | Yes | Ongoing | 145 | 6 |  |  |  | Kailash | 6
10611 | Makwanpur | Gogane | 8 | BC | CARD | ARC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2 hour per session | # of participants | Yes | Ongoing | 60 | 30 |  |  |  | Kailash | 6
10612 | Makwanpur | Gogane | 8 | BC | CARD | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 Social mobiliser, 1 engineer, 1 builder trainer ( Experienced mason) | # of households | Yes | Ongoing | 93 | 4 |  |  |  | Kailash | 6
10613 | Makwanpur | Gogane | 9 | BC | CARD | ARC | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2 hour per session | # of participants | Yes | Ongoing | 60 | 20 |  |  |  | Kailash | 6
10614 | Makwanpur | Gogane | 9 | BC | CARD | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 Social mobiliser, 1 engineer, 1 builder trainer ( Experienced mason) | # of households | Yes | Ongoing | 65 | 6 |  |  |  | Kailash | 6
10615 | Makwanpur | Handikhola | 6 | BLF | BNMT | BLF | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Ongoing | 1 | 1 |  |  |  | Manahari | 3
10616 | Makwanpur | Hetauda U.M.N.P. | 2 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Hetauda | 2
10617 | Makwanpur | Hetauda U.M.N.P. | 12 | BLF | BNMT | BLF | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Ongoing | 1 | 1 |  |  |  | Hetauda | 12
10618 | Makwanpur | IpaPanchakanya | 1 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 39 | 39 |  |  |  | Bhimphedi | 8
10619 | Makwanpur | IpaPanchakanya | 2 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 45 | 45 |  |  |  | Bhimphedi | 8
10620 | Makwanpur | IpaPanchakanya | 2 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
10621 | Makwanpur | IpaPanchakanya | 3 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 84 | 84 |  |  |  | Bhimphedi | 8
10622 | Makwanpur | IpaPanchakanya | 4 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 44 | 44 |  |  |  | Bhimphedi | 8
10623 | Makwanpur | IpaPanchakanya | 5 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 50 | 50 |  |  |  | Bhimphedi | 8
10624 | Makwanpur | IpaPanchakanya | 5 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
10625 | Makwanpur | IpaPanchakanya | 6 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 34 | 34 |  |  |  | Bhimphedi | 8
10626 | Makwanpur | IpaPanchakanya | 7 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 25 | 25 |  |  |  | Bhimphedi | 8
10627 | Makwanpur | IpaPanchakanya | 8 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 75 | 75 |  |  |  | Bhimphedi | 8
10628 | Makwanpur | IpaPanchakanya | 8 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
10629 | Makwanpur | IpaPanchakanya | 8 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
10630 | Makwanpur | IpaPanchakanya | 9 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 57 | 57 |  |  |  | Bhimphedi | 8
10631 | Makwanpur | Kalikatar | 1 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Kailash | 3
10632 | Makwanpur | Kalikatar | 1 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Kailash | 3
10633 | Makwanpur | Kalikatar | 8 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Kailash | 4
10634 | Makwanpur | Kogate | 1 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 3 | 3 |  |  |  | Bhimphedi | 7
10635 | Makwanpur | Kogate | 2 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 14 | 14 |  |  |  | Bhimphedi | 7
10636 | Makwanpur | Kogate | 2 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Bhimphedi | 7
10637 | Makwanpur | Kogate | 2 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
10638 | Makwanpur | Kogate | 2 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
10639 | Makwanpur | Kogate | 3 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 6 | 6 |  |  |  | Bhimphedi | 7
10640 | Makwanpur | Kogate | 3 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
10641 | Makwanpur | Kogate | 4 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 3 | 3 |  |  |  | Bhimphedi | 7
10642 | Makwanpur | Kogate | 5 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 3 | 3 |  |  |  | Bhimphedi | 7
10643 | Makwanpur | Kogate | 5 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
10644 | Makwanpur | Kogate | 6 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 8 | 8 |  |  |  | Bhimphedi | 7
10645 | Makwanpur | Kogate | 6 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
10646 | Makwanpur | Kogate | 7 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 3 | 3 |  |  |  | Bhimphedi | 7
10647 | Makwanpur | Kogate | 8 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 4 | 4 |  |  |  | Bhimphedi | 7
10648 | Makwanpur | Kogate | 9 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets. | # of households | Yes | Completed | 17 | 17 |  |  |  | Bhimphedi | 7
10649 | Makwanpur | Kogate | 9 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
10650 | Makwanpur | Kulekhani | 1 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 14 | 14 |  |  |  | Indrasarowar | 2
10651 | Makwanpur | Kulekhani | 1 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 14 | 14 |  |  |  | Indrasarowar | 2
10652 | Makwanpur | Kulekhani | 1 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Ongoing | 27 | 15 |  |  |  | Indrasarowar | 2
10653 | Makwanpur | Kulekhani | 1 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 49 |  |  |  | Indrasarowar | 2
10654 | Makwanpur | Kulekhani | 1 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 2
10655 | Makwanpur | Kulekhani | 1 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 2
10656 | Makwanpur | Kulekhani | 1 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 2
10657 | Makwanpur | Kulekhani | 2 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 16 | 16 |  |  |  | Indrasarowar | 2
10658 | Makwanpur | Kulekhani | 2 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 16 | 16 |  |  |  | Indrasarowar | 2
10659 | Makwanpur | Kulekhani | 2 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 27 | 27 |  |  |  | Indrasarowar | 2
10660 | Makwanpur | Kulekhani | 2 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 45 |  |  |  | Indrasarowar | 2
10661 | Makwanpur | Kulekhani | 2 | PLAN | CEEDF | PLAN-GER | Technical Assistance | Demonstration Construction | House | 2 rooms, materials used: ciment, rod, aggregated sand, stone, mud, wood, CGI Sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 2
10662 | Makwanpur | Kulekhani | 2 | PLAN | CEEDF | ECHO | Technical Assistance | Demonstration Construction | House | 2 rooms, materials used: ciment, rod, aggregated sand, stone, mud, wood, CGI Sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 2
10663 | Makwanpur | Kulekhani | 2 | PLAN | CEEDF | PLAN-GER | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | A VDC wise committee was formed by the chair of VDC secreatry and it has represnetatives from all wards of VDC. There are even representative from police office, Health Post, School and Political parties. | # of committees | Yes | Completed | 25 | 27 |  |  |  | Indrasarowar | 2
10664 | Makwanpur | Kulekhani | 2 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 2
10665 | Makwanpur | Kulekhani | 2 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 2
10666 | Makwanpur | Kulekhani | 2 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 2
10667 | Makwanpur | Kulekhani | 2 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 2
10668 | Makwanpur | Kulekhani | 2 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 3 |  |  |  | Indrasarowar | 2
10669 | Makwanpur | Kulekhani | 3 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 23 | 23 |  |  |  | Indrasarowar | 2
10670 | Makwanpur | Kulekhani | 3 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 23 | 23 |  |  |  | Indrasarowar | 2
10671 | Makwanpur | Kulekhani | 3 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 34 | 34 |  |  |  | Indrasarowar | 2
10672 | Makwanpur | Kulekhani | 3 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 51 |  |  |  | Indrasarowar | 2
10673 | Makwanpur | Kulekhani | 3 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 3 |  |  |  | Indrasarowar | 2
10674 | Makwanpur | Kulekhani | 3 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 2
10675 | Makwanpur | Kulekhani | 3 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 2
10676 | Makwanpur | Kulekhani | 4 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 7 | 7 |  |  |  | Indrasarowar | 2
10677 | Makwanpur | Kulekhani | 4 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 7 | 7 |  |  |  | Indrasarowar | 2
10678 | Makwanpur | Kulekhani | 4 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 10 | 10 |  |  |  | Indrasarowar | 2
10679 | Makwanpur | Kulekhani | 4 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 45 |  |  |  | Indrasarowar | 2
10680 | Makwanpur | Kulekhani | 4 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 2
10681 | Makwanpur | Kulekhani | 4 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 2
10682 | Makwanpur | Kulekhani | 4 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 2
10683 | Makwanpur | Kulekhani | 5 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 21 | 21 |  |  |  | Indrasarowar | 2
10684 | Makwanpur | Kulekhani | 5 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 21 | 21 |  |  |  | Indrasarowar | 2
10685 | Makwanpur | Kulekhani | 5 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 50 | 50 |  |  |  | Indrasarowar | 2
10686 | Makwanpur | Kulekhani | 5 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 45 |  |  |  | Indrasarowar | 2
10687 | Makwanpur | Kulekhani | 5 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 2
10688 | Makwanpur | Kulekhani | 5 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 2
10689 | Makwanpur | Kulekhani | 5 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 2
10690 | Makwanpur | Kulekhani | 6 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 15 | 15 |  |  |  | Indrasarowar | 2
10691 | Makwanpur | Kulekhani | 6 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 15 | 15 |  |  |  | Indrasarowar | 2
10692 | Makwanpur | Kulekhani | 6 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Ongoing | 23 | 23 |  |  |  | Indrasarowar | 2
10693 | Makwanpur | Kulekhani | 6 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 45 |  |  |  | Indrasarowar | 2
10694 | Makwanpur | Kulekhani | 6 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 2
10695 | Makwanpur | Kulekhani | 6 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 2
10696 | Makwanpur | Kulekhani | 6 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 2 |  |  |  | Indrasarowar | 2
10697 | Makwanpur | Kulekhani | 7 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 9 | 9 |  |  |  | Indrasarowar | 2
10698 | Makwanpur | Kulekhani | 7 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 9 | 9 |  |  |  | Indrasarowar | 2
10699 | Makwanpur | Kulekhani | 7 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 14 | 14 |  |  |  | Indrasarowar | 2
10700 | Makwanpur | Kulekhani | 7 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 48 |  |  |  | Indrasarowar | 2
10701 | Makwanpur | Kulekhani | 7 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 2
10702 | Makwanpur | Kulekhani | 7 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 2
10703 | Makwanpur | Kulekhani | 7 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 2
10704 | Makwanpur | Kulekhani | 8 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 11 | 11 |  |  |  | Indrasarowar | 2
10705 | Makwanpur | Kulekhani | 8 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 11 | 11 |  |  |  | Indrasarowar | 2
10706 | Makwanpur | Kulekhani | 8 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 28 | 28 |  |  |  | Indrasarowar | 2
10707 | Makwanpur | Kulekhani | 8 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 52 |  |  |  | Indrasarowar | 2
10708 | Makwanpur | Kulekhani | 8 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 2
10709 | Makwanpur | Kulekhani | 8 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 2
10710 | Makwanpur | Kulekhani | 8 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 2
10711 | Makwanpur | Kulekhani | 9 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 10 | 10 |  |  |  | Indrasarowar | 2
10712 | Makwanpur | Kulekhani | 9 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 10 | 10 |  |  |  | Indrasarowar | 2
10713 | Makwanpur | Kulekhani | 9 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 15 | 0 |  |  |  | Indrasarowar | 2
10714 | Makwanpur | Kulekhani | 9 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 50 |  |  |  | Indrasarowar | 2
10715 | Makwanpur | Kulekhani | 9 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 2
10716 | Makwanpur | Kulekhani | 9 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 2
10717 | Makwanpur | Kulekhani | 9 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 2
10718 | Makwanpur | Kulekhani | 9 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 2
10719 | Makwanpur | Makwanpurgadhi | 1 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 42 | 42 |  |  |  | Makawanpurgadhi | 1
10720 | Makwanpur | Makwanpurgadhi | 2 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 34 | 34 |  |  |  | Makawanpurgadhi | 1
10721 | Makwanpur | Makwanpurgadhi | 3 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 101 | 101 |  |  |  | Makawanpurgadhi | 2
10722 | Makwanpur | Makwanpurgadhi | 4 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 66 | 66 |  |  |  | Makawanpurgadhi | 2
10723 | Makwanpur | Makwanpurgadhi | 4 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 2
10724 | Makwanpur | Makwanpurgadhi | 5 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 58 | 58 |  |  |  | Makawanpurgadhi | 3
10725 | Makwanpur | Makwanpurgadhi | 5 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 3
10726 | Makwanpur | Makwanpurgadhi | 6 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 32 | 32 |  |  |  | Makawanpurgadhi | 3
10727 | Makwanpur | Makwanpurgadhi | 7 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 43 | 43 |  |  |  | Makawanpurgadhi | 4
10728 | Makwanpur | Makwanpurgadhi | 8 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 47 | 47 |  |  |  | Makawanpurgadhi | 4
10729 | Makwanpur | Makwanpurgadhi | 9 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 77 | 77 |  |  |  | Makawanpurgadhi | 5
10730 | Makwanpur | Manahari | 8 | BLF | BNMT | BLF | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Manahari | 9
10731 | Makwanpur | Manthali | 1 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 41 | 41 |  |  |  | Bakaiya | 10
10732 | Makwanpur | Manthali | 2 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 53 | 53 |  |  |  | Bakaiya | 10
10733 | Makwanpur | Manthali | 3 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 44 | 44 |  |  |  | Bakaiya | 10
10734 | Makwanpur | Manthali | 3 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 10
10735 | Makwanpur | Manthali | 4 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 42 | 42 |  |  |  | Bakaiya | 10
10736 | Makwanpur | Manthali | 5 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 37 | 37 |  |  |  | Bakaiya | 10
10737 | Makwanpur | Manthali | 6 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 50 | 50 |  |  |  | Bakaiya | 10
10738 | Makwanpur | Manthali | 7 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 61 | 61 |  |  |  | Bakaiya | 10
10739 | Makwanpur | Manthali | 8 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 33 | 33 |  |  |  | Bakaiya | 10
10740 | Makwanpur | Manthali | 9 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 24 | 24 |  |  |  | Bakaiya | 10
10741 | Makwanpur | Markhu | 1 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 16 | 16 |  |  |  | Indrasarowar | 1
10742 | Makwanpur | Markhu | 1 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 16 | 16 |  |  |  | Indrasarowar | 1
10743 | Makwanpur | Markhu | 1 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 26 | 26 |  |  |  | Indrasarowar | 1
10744 | Makwanpur | Markhu | 1 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 90 |  |  |  | Indrasarowar | 1
10745 | Makwanpur | Markhu | 1 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 1
10746 | Makwanpur | Markhu | 1 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 1
10747 | Makwanpur | Markhu | 1 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Indrasarowar | 1
10748 | Makwanpur | Markhu | 2 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 11 | 11 |  |  |  | Indrasarowar | 1
10749 | Makwanpur | Markhu | 2 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 11 | 11 |  |  |  | Indrasarowar | 1
10750 | Makwanpur | Markhu | 2 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Ongoing | 19 | 8 |  |  |  | Indrasarowar | 1
10751 | Makwanpur | Markhu | 2 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 80 |  |  |  | Indrasarowar | 1
10752 | Makwanpur | Markhu | 2 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 1
10753 | Makwanpur | Markhu | 2 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 1
10754 | Makwanpur | Markhu | 2 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 1
10755 | Makwanpur | Markhu | 3 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 18 | 18 |  |  |  | Indrasarowar | 1
10756 | Makwanpur | Markhu | 3 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 18 | 18 |  |  |  | Indrasarowar | 1
10757 | Makwanpur | Markhu | 3 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 16 | 16 |  |  |  | Indrasarowar | 1
10758 | Makwanpur | Markhu | 3 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 51 |  |  |  | Indrasarowar | 1
10759 | Makwanpur | Markhu | 3 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 1
10760 | Makwanpur | Markhu | 3 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 1
10761 | Makwanpur | Markhu | 3 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 1
10762 | Makwanpur | Markhu | 4 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 19 | 19 |  |  |  | Indrasarowar | 1
10763 | Makwanpur | Markhu | 4 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 19 | 19 |  |  |  | Indrasarowar | 1
10764 | Makwanpur | Markhu | 4 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 18 | 0 |  |  |  | Indrasarowar | 1
10765 | Makwanpur | Markhu | 4 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 48 |  |  |  | Indrasarowar | 1
10766 | Makwanpur | Markhu | 4 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 1
10767 | Makwanpur | Markhu | 4 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 1
10768 | Makwanpur | Markhu | 4 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 1
10769 | Makwanpur | Markhu | 5 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 15 | 15 |  |  |  | Indrasarowar | 1
10770 | Makwanpur | Markhu | 5 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 15 | 15 |  |  |  | Indrasarowar | 1
10771 | Makwanpur | Markhu | 5 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 24 | 24 |  |  |  | Indrasarowar | 1
10772 | Makwanpur | Markhu | 5 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 49 |  |  |  | Indrasarowar | 1
10773 | Makwanpur | Markhu | 5 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 1
10774 | Makwanpur | Markhu | 5 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 1
10775 | Makwanpur | Markhu | 5 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 1
10776 | Makwanpur | Markhu | 6 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 12 | 12 |  |  |  | Indrasarowar | 1
10777 | Makwanpur | Markhu | 6 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 12 | 12 |  |  |  | Indrasarowar | 1
10778 | Makwanpur | Markhu | 6 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 15 | 0 |  |  |  | Indrasarowar | 1
10779 | Makwanpur | Markhu | 6 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 63 |  |  |  | Indrasarowar | 1
10780 | Makwanpur | Markhu | 6 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 1
10781 | Makwanpur | Markhu | 6 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 1
10782 | Makwanpur | Markhu | 6 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 1
10783 | Makwanpur | Markhu | 7 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 17 | 17 |  |  |  | Indrasarowar | 1
10784 | Makwanpur | Markhu | 7 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 17 | 17 |  |  |  | Indrasarowar | 1
10785 | Makwanpur | Markhu | 7 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Planned | 10 | 0 |  |  |  | Indrasarowar | 1
10786 | Makwanpur | Markhu | 7 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 33 |  |  |  | Indrasarowar | 1
10787 | Makwanpur | Markhu | 7 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 1
10788 | Makwanpur | Markhu | 7 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 1
10789 | Makwanpur | Markhu | 7 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 1
10790 | Makwanpur | Markhu | 8 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 10 | 10 |  |  |  | Indrasarowar | 1
10791 | Makwanpur | Markhu | 8 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 10 | 10 |  |  |  | Indrasarowar | 1
10792 | Makwanpur | Markhu | 8 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 16 | 16 |  |  |  | Indrasarowar | 1
10793 | Makwanpur | Markhu | 8 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 47 |  |  |  | Indrasarowar | 1
10794 | Makwanpur | Markhu | 8 | PLAN | CEEDF | PLAN-GER | Technical Assistance | Demonstration Construction | House | 2 rooms, materials used: ciment, rod, aggregated sand, stone, mud, wood, CGI Sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 1
10795 | Makwanpur | Markhu | 8 | PLAN | CEEDF | ECHO | Technical Assistance | Demonstration Construction | House | 2 rooms, materials used: ciment, rod, aggregated sand, stone, mud, wood, CGI Sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 1
10796 | Makwanpur | Markhu | 8 | PLAN | CEEDF | PLAN-GER | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | A VDC wise committee was formed by the chair of VDC secreatry and it has represnetatives from all wards of VDC. There are even representative from police office, Health Post, School and Political parties. | # of committees | Yes | Completed | 25 | 17 |  |  |  | Indrasarowar | 1
10797 | Makwanpur | Markhu | 8 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 1
10798 | Makwanpur | Markhu | 8 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Indrasarowar | 1
10799 | Makwanpur | Markhu | 8 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 1
10800 | Makwanpur | Markhu | 9 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI Sheets and 3 plain sheets | # of households | Yes | Completed | 7 | 7 |  |  |  | Indrasarowar | 1
10801 | Makwanpur | Markhu | 9 | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 7 | 7 |  |  |  | Indrasarowar | 1
10802 | Makwanpur | Markhu | 9 | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Spanner, measuring tape, Hammer, Wood cutter, Iron nails/ hooks and hand gloves | # of households | Yes | Completed | 11 | 11 |  |  |  | Indrasarowar | 1
10803 | Makwanpur | Markhu | 9 | PLAN | CEEDF | ECHO | Technical Assistance | Community reconstruction orientation | 1 session | 3 hours session (BBB awareness program) | # of participants | Yes | Completed | 45 | 53 |  |  |  | Indrasarowar | 1
10804 | Makwanpur | Markhu | 9 | PLAN | CEEDF | ECHO | Training | Other trainings | Other trainings (specify in Activity Detail) | 3 hours session (Local disaster management training) | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 1
10805 | Makwanpur | Markhu | 9 | PLAN | CEEDF | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 8 hours session | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Indrasarowar | 1
10806 | Makwanpur | Markhu | 9 | PLAN | CEEDF | PLAN-GER | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 1
10807 | Makwanpur | Namtar | 4 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Bhimphedi | 9
10808 | Makwanpur | Nibuwatar | 2 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 3
10809 | Makwanpur | Raigaun | 2 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Bagmati | 1
10810 | Makwanpur | Raigaun | 2 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Bagmati | 1
10811 | Makwanpur | Raigaun | 2 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 1
10812 | Makwanpur | Raigaun | 5 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Bagmati | 2
10813 | Makwanpur | SarikhetPalase | 2 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Raksirang | 3
10814 | Makwanpur | SarikhetPalase | 3 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Raksirang | 3
10815 | Makwanpur | Shikharpur | 1 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 8
10816 | Makwanpur | Shikharpur | 6 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 9
10817 | Makwanpur | ShreepurChhatiwan | 5 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Bakaiya | 4
10818 | Makwanpur | ShreepurChhatiwan | 6 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 4
10819 | Makwanpur | ShreepurChhatiwan | 7 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 5
10820 | Makwanpur | ShreepurChhatiwan | 8 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Bakaiya | 5
10821 | Makwanpur | SisneriMahadevsthan | 1 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 13 | 13 |  |  |  | Indrasarowar | 3
10822 | Makwanpur | SisneriMahadevsthan | 2 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 35 | 35 |  |  |  | Indrasarowar | 3
10823 | Makwanpur | SisneriMahadevsthan | 3 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 22 | 22 |  |  |  | Indrasarowar | 3
10824 | Makwanpur | SisneriMahadevsthan | 4 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 25 | 25 |  |  |  | Indrasarowar | 3
10825 | Makwanpur | SisneriMahadevsthan | 5 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 17 | 17 |  |  |  | Indrasarowar | 3
10826 | Makwanpur | SisneriMahadevsthan | 6 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 82 | 82 |  |  |  | Indrasarowar | 3
10827 | Makwanpur | SisneriMahadevsthan | 7 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 19 | 19 |  |  |  | Indrasarowar | 3
10828 | Makwanpur | SisneriMahadevsthan | 8 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 2 | 2 |  |  |  | Indrasarowar | 3
10829 | Makwanpur | SisneriMahadevsthan | 9 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 2 | 2 |  |  |  | Indrasarowar | 3
10830 | Makwanpur | Sukaura | 1 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 27 | 27 |  |  |  | Makawanpurgadhi | 7
10831 | Makwanpur | Sukaura | 2 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 33 | 33 |  |  |  | Makawanpurgadhi | 7
10832 | Makwanpur | Sukaura | 2 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 7
10833 | Makwanpur | Sukaura | 3 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 7
10834 | Makwanpur | Sukaura | 4 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 30 | 30 |  |  |  | Makawanpurgadhi | 7
10835 | Makwanpur | Sukaura | 5 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 18 | 18 |  |  |  | Makawanpurgadhi | 7
10836 | Makwanpur | Sukaura | 6 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 9 | 9 |  |  |  | Makawanpurgadhi | 7
10837 | Makwanpur | Sukaura | 7 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 26 | 26 |  |  |  | Makawanpurgadhi | 7
10838 | Makwanpur | Sukaura | 8 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 20 | 20 |  |  |  | Makawanpurgadhi | 7
10839 | Makwanpur | Sukaura | 9 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 63 | 63 |  |  |  | Makawanpurgadhi | 7
10840 | Makwanpur | Sukaura | 9 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 7
10841 | Makwanpur | Thaha N.P. | 5 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Thaha | 2
10842 | Makwanpur | Thaha N.P. | 9 | ICCO | CCDN | ECHO | Financial/Material/Labour Assistance | Material support on household WASH | HH toilet repair/rehabilitation | A package of materials worth 9000 NPR per family | # of households | Yes | Completed | 30 | 30 |  |  |  | Thaha | 4
10843 | Makwanpur | Thaha N.P. | 9 | ICCO | CCDN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 15 | 12 |  |  |  | Thaha | 4
10844 | Makwanpur | Thaha N.P. | 9 | ICCO | CCDN | ECHO | Training | Short training | Plumber | Self (prepared and emdrosed through MCSIO Mak) | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Thaha | 4
10845 | Makwanpur | Thaha N.P. | 10 | ICCO | CCDN | ECHO | Financial/Material/Labour Assistance | Material support on household WASH | HH toilet repair/rehabilitation | A package of materials worth 9000 NPR per family | # of households | Yes | Completed | 30 | 30 |  |  |  | Thaha | 5
10846 | Makwanpur | Thaha N.P. | 10 | ICCO | CCDN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 15 | 11 |  |  |  | Thaha | 5
10847 | Makwanpur | Thaha N.P. | 10 | ICCO | CCDN | ECHO | Training | Short training | Plumber | Self (prepared and emdrosed through MCSIO Mak) | # of trainees | Yes | Completed | 7 | 7 |  |  |  | Thaha | 5
10848 | Makwanpur | Thaha N.P. | 12 | ICCO | CCDN | ECHO | Financial/Material/Labour Assistance | Material support on household WASH | HH toilet repair/rehabilitation | A package of materials worth 9000 NPR per family | # of households | Yes | Completed | 30 | 30 |  |  |  | Thaha | 1
10849 | Makwanpur | Thaha N.P. | 12 | ICCO | CCDN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 15 | 13 |  |  |  | Thaha | 1
10850 | Makwanpur | Thaha N.P. | 12 | ICCO | CCDN | ECHO | Training | Short training | Plumber | Self (prepared and emdrosed through MCSIO Mak) | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Thaha | 1
10851 | Makwanpur | Thaha N.P. | 14 | ICCO | CCDN | ECHO | Financial/Material/Labour Assistance | Material support on household WASH | HH toilet repair/rehabilitation | A package of materials worth 9000 NPR per family | # of households | Yes | Completed | 30 | 30 |  |  |  | Thaha | 6
10852 | Makwanpur | Thaha N.P. | 14 | ICCO | CCDN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC | # of trainees | Yes | Completed | 15 | 19 |  |  |  | Thaha | 6
10853 | Makwanpur | Thaha N.P. | 14 | ICCO | CCDN | ECHO | Training | Short training | Plumber | Self (prepared and emdrosed through MCSIO Mak) | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Thaha | 6
10854 | Makwanpur | Thingan | 1 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 8 | 8 |  |  |  | Bakaiya | 11
10855 | Makwanpur | Thingan | 2 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 31 | 31 |  |  |  | Bakaiya | 11
10856 | Makwanpur | Thingan | 3 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 30 | 30 |  |  |  | Bakaiya | 12
10857 | Makwanpur | Thingan | 3 | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 12
10858 | Makwanpur | Thingan | 4 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 34 | 34 |  |  |  | Bakaiya | 12
10859 | Makwanpur | Thingan | 4 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 12
10860 | Makwanpur | Thingan | 5 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 55 | 55 |  |  |  | Bakaiya | 11
10861 | Makwanpur | Thingan | 5 | CS | Sabal | USAID | Training | Vocational training | Carpenter (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 11
10862 | Makwanpur | Thingan | 5 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 11
10863 | Makwanpur | Thingan | 6 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 29 | 29 |  |  |  | Bakaiya | 12
10864 | Makwanpur | Thingan | 7 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 17 | 17 |  |  |  | Bakaiya | 12
10865 | Makwanpur | Thingan | 8 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 15 | 15 |  |  |  | Bakaiya | 12
10866 | Makwanpur | Thingan | 9 | PLAN | CEEDF | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | 2 bundel CGI sheets | # of households | Yes | Completed | 30 | 30 |  |  |  | Bakaiya | 12
10867 | Makwanpur | TistungDeurali | 3 | CS | Sabal | USAID | Training | Vocational training | Plumber (CTEVT) | 390 hours based on CTEVT curriculum, Two from ward no 1 and one from ward no. 2 | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Thaha | 11
10868 | Makwanpur | TistungDeurali | 9 | CS | Sabal | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) | CTEVT curriculum for level-I, but it was run for 65 days ( 36 days class and 30 days on the job) | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Thaha | 12
10869 | Makwanpur | Agara | 1 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 33 | 32 |  |  |  | Thaha | 8
10870 | Makwanpur | Agara | 1 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 33 | 31 |  |  |  | Thaha | 8
10871 | Makwanpur | Agara | 1 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 33 | 30 |  |  |  | Thaha | 8
10872 | Makwanpur | Agara | 1 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Thaha | 8
10873 | Makwanpur | Agara | 1 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 33 | 30 |  |  |  | Thaha | 8
10874 | Makwanpur | Agara | 1 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 |  |  |  | Thaha | 8
10875 | Makwanpur | Agara | 1 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 |  |  |  | Thaha | 8
10876 | Makwanpur | Agara | 2 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 36 | 36 |  |  |  | Thaha | 7
10877 | Makwanpur | Agara | 2 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Completed | 36 | 36 |  |  |  | Thaha | 7
10878 | Makwanpur | Agara | 2 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 36 | 35 |  |  |  | Thaha | 7
10879 | Makwanpur | Agara | 2 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Thaha | 7
10880 | Makwanpur | Agara | 2 | TEARFUND | RADO | DEC | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Thaha | 7
10881 | Makwanpur | Agara | 2 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 36 | 35 |  |  |  | Thaha | 7
10882 | Makwanpur | Agara | 2 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 |  |  |  | Thaha | 7
10883 | Makwanpur | Agara | 2 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 |  |  |  | Thaha | 7
10884 | Makwanpur | Agara | 3 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 49 | 48 |  |  |  | Thaha | 7
10885 | Makwanpur | Agara | 3 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Completed | 49 | 48 |  |  |  | Thaha | 7
10886 | Makwanpur | Agara | 3 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 49 | 48 |  |  |  | Thaha | 7
10887 | Makwanpur | Agara | 3 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Thaha | 7
10888 | Makwanpur | Agara | 3 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 49 | 48 |  |  |  | Thaha | 7
10889 | Makwanpur | Agara | 3 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 |  |  |  | Thaha | 7
10890 | Makwanpur | Agara | 3 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 15 |  |  |  | Thaha | 7
10891 | Makwanpur | Agara | 4 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply new | Rs 2200986 cash support for 207 household | # of households | Yes | Completed | 207 | 207 |  |  |  | Thaha | 7
10892 | Makwanpur | Agara | 4 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 21 | 21 |  |  |  | Thaha | 7
10893 | Makwanpur | Agara | 4 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 21 | 20 |  |  |  | Thaha | 7
10894 | Makwanpur | Agara | 4 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 21 | 17 |  |  |  | Thaha | 7
10895 | Makwanpur | Agara | 4 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Thaha | 7
10896 | Makwanpur | Agara | 4 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 21 | 20 |  |  |  | Thaha | 7
10897 | Makwanpur | Agara | 4 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 |  |  |  | Thaha | 7
10898 | Makwanpur | Agara | 4 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 15 |  |  |  | Thaha | 7
10899 | Makwanpur | Agara | 5 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 22 | 22 |  |  |  | Thaha | 7
10900 | Makwanpur | Agara | 5 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 22 | 20 |  |  |  | Thaha | 7
10901 | Makwanpur | Agara | 5 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 22 | 20 |  |  |  | Thaha | 7
10902 | Makwanpur | Agara | 5 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Thaha | 7
10903 | Makwanpur | Agara | 5 | TEARFUND | RADO | DEC | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Thaha | 7
10904 | Makwanpur | Agara | 5 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 22 | 20 |  |  |  | Thaha | 7
10905 | Makwanpur | Agara | 5 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 |  |  |  | Thaha | 7
10906 | Makwanpur | Agara | 5 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 |  |  |  | Thaha | 7
10907 | Makwanpur | Agara | 6 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 21 | 21 |  |  |  | Thaha | 7
10908 | Makwanpur | Agara | 6 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 21 | 19 |  |  |  | Thaha | 7
10909 | Makwanpur | Agara | 6 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 21 | 20 |  |  |  | Thaha | 7
10910 | Makwanpur | Agara | 6 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Thaha | 7
10911 | Makwanpur | Agara | 6 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 21 | 20 |  |  |  | Thaha | 7
10912 | Makwanpur | Agara | 6 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 |  |  |  | Thaha | 7
10913 | Makwanpur | Agara | 6 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 |  |  |  | Thaha | 7
10914 | Makwanpur | Agara | 7 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 43 | 43 |  |  |  | Thaha | 8
10915 | Makwanpur | Agara | 7 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Completed | 43 | 43 |  |  |  | Thaha | 8
10916 | Makwanpur | Agara | 7 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 43 | 42 |  |  |  | Thaha | 8
10917 | Makwanpur | Agara | 7 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Thaha | 8
10918 | Makwanpur | Agara | 7 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Completed | 43 | 43 |  |  |  | Thaha | 8
10919 | Makwanpur | Agara | 7 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 |  |  |  | Thaha | 8
10920 | Makwanpur | Agara | 7 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 |  |  |  | Thaha | 8
10921 | Makwanpur | Agara | 8 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 50 | 50 |  |  |  | Thaha | 8
10922 | Makwanpur | Agara | 8 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Completed | 50 | 50 |  |  |  | Thaha | 8
10923 | Makwanpur | Agara | 8 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Completed | 50 | 50 |  |  |  | Thaha | 8
10924 | Makwanpur | Agara | 8 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Thaha | 8
10925 | Makwanpur | Agara | 8 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Completed | 50 | 50 |  |  |  | Thaha | 8
10926 | Makwanpur | Agara | 8 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 3 | 3 |  |  |  | Thaha | 8
10927 | Makwanpur | Agara | 8 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 |  |  |  | Thaha | 8
10928 | Makwanpur | Agara | 9 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply new | Rs 556498 cash support for 89 households | # of households | Yes | Completed | 89 | 89 |  |  |  | Thaha | 8
10929 | Makwanpur | Agara | 9 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 25 | 25 |  |  |  | Thaha | 8
10930 | Makwanpur | Agara | 9 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 25 | 24 |  |  |  | Thaha | 8
10931 | Makwanpur | Agara | 9 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 25 | 25 |  |  |  | Thaha | 8
10932 | Makwanpur | Agara | 9 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Thaha | 8
10933 | Makwanpur | Agara | 9 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Completed | 25 | 25 |  |  |  | Thaha | 8
10934 | Makwanpur | Agara | 9 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 |  |  |  | Thaha | 8
10935 | Makwanpur | Agara | 9 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 |  |  |  | Thaha | 8
10936 | Makwanpur | Ambhanjyang | 1 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 2 | 1 |  |  |  | Makawanpurgadhi | 5
10937 | Makwanpur | Ambhanjyang | 3 | TEARFUND | RADO | DEC | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 5
10938 | Makwanpur | Ambhanjyang | 3 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 2 | 1 |  |  |  | Makawanpurgadhi | 5
10939 | Makwanpur | Ambhanjyang | 5 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Makawanpurgadhi | 6
10940 | Makwanpur | Ambhanjyang | 7 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 2 | 3 |  |  |  | Makawanpurgadhi | 6
10941 | Makwanpur | Betini | 1 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10942 | Makwanpur | Betini | 1 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10943 | Makwanpur | Betini | 1 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Bagmati | 9
10944 | Makwanpur | Betini | 2 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10945 | Makwanpur | Betini | 2 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10946 | Makwanpur | Betini | 2 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 5 | 7 |  |  |  | Bagmati | 9
10947 | Makwanpur | Betini | 3 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10948 | Makwanpur | Betini | 3 | TEARFUND | RADO | ZOA | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10949 | Makwanpur | Betini | 3 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10950 | Makwanpur | Betini | 3 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 8 | 8 |  |  |  | Bagmati | 9
10951 | Makwanpur | Betini | 4 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10952 | Makwanpur | Betini | 4 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10953 | Makwanpur | Betini | 4 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 8 | 7 |  |  |  | Bagmati | 9
10954 | Makwanpur | Betini | 5 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10955 | Makwanpur | Betini | 5 | TEARFUND | RADO | ZOA | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10956 | Makwanpur | Betini | 5 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10957 | Makwanpur | Betini | 5 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 5 | 8 |  |  |  | Bagmati | 9
10958 | Makwanpur | Betini | 6 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10959 | Makwanpur | Betini | 6 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10960 | Makwanpur | Betini | 6 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 5 | 5 |  |  |  | Bagmati | 9
10961 | Makwanpur | Betini | 7 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10962 | Makwanpur | Betini | 7 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10963 | Makwanpur | Betini | 7 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 5 | 6 |  |  |  | Bagmati | 9
10964 | Makwanpur | Betini | 8 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10965 | Makwanpur | Betini | 8 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10966 | Makwanpur | Betini | 8 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 5 | 7 |  |  |  | Bagmati | 9
10967 | Makwanpur | Betini | 9 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10968 | Makwanpur | Betini | 9 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bagmati | 9
10969 | Makwanpur | Betini | 9 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 5 | 6 |  |  |  | Bagmati | 9
10970 | Makwanpur | Budhichaur | 1 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10971 | Makwanpur | Budhichaur | 1 | TEARFUND | RADO | ZOA | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10972 | Makwanpur | Budhichaur | 1 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10973 | Makwanpur | Budhichaur | 1 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 12 |  |  |  | Makawanpurgadhi | 8
10974 | Makwanpur | Budhichaur | 2 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10975 | Makwanpur | Budhichaur | 2 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10976 | Makwanpur | Budhichaur | 2 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Makawanpurgadhi | 8
10977 | Makwanpur | Budhichaur | 3 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10978 | Makwanpur | Budhichaur | 3 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10979 | Makwanpur | Budhichaur | 3 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Makawanpurgadhi | 8
10980 | Makwanpur | Budhichaur | 4 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10981 | Makwanpur | Budhichaur | 4 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10982 | Makwanpur | Budhichaur | 4 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Makawanpurgadhi | 8
10983 | Makwanpur | Budhichaur | 5 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10984 | Makwanpur | Budhichaur | 5 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10985 | Makwanpur | Budhichaur | 5 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Makawanpurgadhi | 8
10986 | Makwanpur | Budhichaur | 6 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10987 | Makwanpur | Budhichaur | 6 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10988 | Makwanpur | Budhichaur | 6 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 4 |  |  |  | Makawanpurgadhi | 8
10989 | Makwanpur | Budhichaur | 7 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10990 | Makwanpur | Budhichaur | 7 | TEARFUND | RADO | ZOA | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10991 | Makwanpur | Budhichaur | 7 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10992 | Makwanpur | Budhichaur | 7 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Makawanpurgadhi | 8
10993 | Makwanpur | Budhichaur | 8 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10994 | Makwanpur | Budhichaur | 8 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10995 | Makwanpur | Budhichaur | 8 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 4 |  |  |  | Makawanpurgadhi | 8
10996 | Makwanpur | Budhichaur | 9 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10997 | Makwanpur | Budhichaur | 9 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 8
10998 | Makwanpur | Budhichaur | 9 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 |  |  |  | Makawanpurgadhi | 8
10999 | Makwanpur | IpaPanchakanya | 1 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11000 | Makwanpur | IpaPanchakanya | 1 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11001 | Makwanpur | IpaPanchakanya | 1 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Bhimphedi | 8
11002 | Makwanpur | IpaPanchakanya | 2 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11003 | Makwanpur | IpaPanchakanya | 2 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11004 | Makwanpur | IpaPanchakanya | 2 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Bhimphedi | 8
11005 | Makwanpur | IpaPanchakanya | 3 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11006 | Makwanpur | IpaPanchakanya | 3 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11007 | Makwanpur | IpaPanchakanya | 3 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 8 |  |  |  | Bhimphedi | 8
11008 | Makwanpur | IpaPanchakanya | 4 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11009 | Makwanpur | IpaPanchakanya | 4 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11010 | Makwanpur | IpaPanchakanya | 4 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Bhimphedi | 8
11011 | Makwanpur | IpaPanchakanya | 5 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11012 | Makwanpur | IpaPanchakanya | 5 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11013 | Makwanpur | IpaPanchakanya | 5 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Bhimphedi | 8
11014 | Makwanpur | IpaPanchakanya | 6 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11015 | Makwanpur | IpaPanchakanya | 6 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11016 | Makwanpur | IpaPanchakanya | 6 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Bhimphedi | 8
11017 | Makwanpur | IpaPanchakanya | 7 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11018 | Makwanpur | IpaPanchakanya | 7 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11019 | Makwanpur | IpaPanchakanya | 7 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Bhimphedi | 8
11020 | Makwanpur | IpaPanchakanya | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11021 | Makwanpur | IpaPanchakanya | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11022 | Makwanpur | IpaPanchakanya | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11023 | Makwanpur | IpaPanchakanya | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11024 | Makwanpur | IpaPanchakanya | 8 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 8 |  |  |  | Bhimphedi | 8
11025 | Makwanpur | IpaPanchakanya | 9 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11026 | Makwanpur | IpaPanchakanya | 9 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 8
11027 | Makwanpur | IpaPanchakanya | 9 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Bhimphedi | 8
11028 | Makwanpur | Kogate | 1 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
11029 | Makwanpur | Kogate | 1 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
11030 | Makwanpur | Kogate | 1 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Bhimphedi | 7
11031 | Makwanpur | Kogate | 2 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
11032 | Makwanpur | Kogate | 2 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 |  |  |  | Bhimphedi | 7
11033 | Makwanpur | Kogate | 3 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
11034 | Makwanpur | Kogate | 3 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
11035 | Makwanpur | Kogate | 3 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
11036 | Makwanpur | Kogate | 3 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 |  |  |  | Bhimphedi | 7
11037 | Makwanpur | Kogate | 4 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
11038 | Makwanpur | Kogate | 4 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
11039 | Makwanpur | Kogate | 4 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 4 |  |  |  | Bhimphedi | 7
11040 | Makwanpur | Kogate | 5 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
11041 | Makwanpur | Kogate | 5 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 4 |  |  |  | Bhimphedi | 7
11042 | Makwanpur | Kogate | 6 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
11043 | Makwanpur | Kogate | 6 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
11044 | Makwanpur | Kogate | 6 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Bhimphedi | 7
11045 | Makwanpur | Kogate | 7 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
11046 | Makwanpur | Kogate | 7 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
11047 | Makwanpur | Kogate | 7 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Bhimphedi | 7
11048 | Makwanpur | Kogate | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
11049 | Makwanpur | Kogate | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
11050 | Makwanpur | Kogate | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
11051 | Makwanpur | Kogate | 8 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Bhimphedi | 7
11052 | Makwanpur | Kogate | 9 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
11053 | Makwanpur | Kogate | 9 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 7
11054 | Makwanpur | Kogate | 9 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 4 |  |  |  | Bhimphedi | 7
11055 | Makwanpur | Makwanpurgadhi | 1 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 1
11056 | Makwanpur | Makwanpurgadhi | 1 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Makawanpurgadhi | 1
11057 | Makwanpur | Makwanpurgadhi | 2 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Makawanpurgadhi | 1
11058 | Makwanpur | Makwanpurgadhi | 3 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 2
11059 | Makwanpur | Makwanpurgadhi | 3 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 |  |  |  | Makawanpurgadhi | 2
11060 | Makwanpur | Makwanpurgadhi | 4 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 2
11061 | Makwanpur | Makwanpurgadhi | 4 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 2
11062 | Makwanpur | Makwanpurgadhi | 4 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Makawanpurgadhi | 2
11063 | Makwanpur | Makwanpurgadhi | 5 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 3
11064 | Makwanpur | Makwanpurgadhi | 5 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 8 |  |  |  | Makawanpurgadhi | 3
11065 | Makwanpur | Makwanpurgadhi | 6 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 3
11066 | Makwanpur | Makwanpurgadhi | 6 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 3
11067 | Makwanpur | Makwanpurgadhi | 6 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 |  |  |  | Makawanpurgadhi | 3
11068 | Makwanpur | Makwanpurgadhi | 7 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 10 |  |  |  | Makawanpurgadhi | 4
11069 | Makwanpur | Makwanpurgadhi | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 4
11070 | Makwanpur | Makwanpurgadhi | 8 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Makawanpurgadhi | 4
11071 | Makwanpur | Makwanpurgadhi | 9 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 5
11072 | Makwanpur | Makwanpurgadhi | 9 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Makawanpurgadhi | 5
11073 | Makwanpur | Manthali | 1 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 10
11074 | Makwanpur | Manthali | 1 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Bakaiya | 10
11075 | Makwanpur | Manthali | 2 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 10
11076 | Makwanpur | Manthali | 2 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Bakaiya | 10
11077 | Makwanpur | Manthali | 3 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 10
11078 | Makwanpur | Manthali | 3 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 10
11079 | Makwanpur | Manthali | 3 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 |  |  |  | Bakaiya | 10
11080 | Makwanpur | Manthali | 4 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 10
11081 | Makwanpur | Manthali | 4 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Bakaiya | 10
11082 | Makwanpur | Manthali | 5 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 10
11083 | Makwanpur | Manthali | 5 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Bakaiya | 10
11084 | Makwanpur | Manthali | 6 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 10
11085 | Makwanpur | Manthali | 6 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Bakaiya | 10
11086 | Makwanpur | Manthali | 7 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 10
11087 | Makwanpur | Manthali | 7 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 10
11088 | Makwanpur | Manthali | 7 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 |  |  |  | Bakaiya | 10
11089 | Makwanpur | Manthali | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 10
11090 | Makwanpur | Manthali | 8 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Bakaiya | 10
11091 | Makwanpur | Manthali | 9 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Bakaiya | 10
11092 | Makwanpur | Manthali | 9 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 4 |  |  |  | Bakaiya | 10
11093 | Makwanpur | SisneriMahadevsthan | 1 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 3
11094 | Makwanpur | SisneriMahadevsthan | 1 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 3
11095 | Makwanpur | SisneriMahadevsthan | 1 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Indrasarowar | 3
11096 | Makwanpur | SisneriMahadevsthan | 2 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 3
11097 | Makwanpur | SisneriMahadevsthan | 2 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 3
11098 | Makwanpur | SisneriMahadevsthan | 2 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Indrasarowar | 3
11099 | Makwanpur | SisneriMahadevsthan | 3 | TEARFUND | RADO | ZOA | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 3
11100 | Makwanpur | SisneriMahadevsthan | 3 | TEARFUND | RADO | ZOA | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 3
11101 | Makwanpur | SisneriMahadevsthan | 3 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 3
11102 | Makwanpur | SisneriMahadevsthan | 3 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Indrasarowar | 3
11103 | Makwanpur | SisneriMahadevsthan | 4 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 3
11104 | Makwanpur | SisneriMahadevsthan | 4 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 1 |  |  |  | Indrasarowar | 3
11105 | Makwanpur | SisneriMahadevsthan | 4 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Indrasarowar | 3
11106 | Makwanpur | SisneriMahadevsthan | 5 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 3
11107 | Makwanpur | SisneriMahadevsthan | 5 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 3
11108 | Makwanpur | SisneriMahadevsthan | 5 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Indrasarowar | 3
11109 | Makwanpur | SisneriMahadevsthan | 6 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 3
11110 | Makwanpur | SisneriMahadevsthan | 6 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Indrasarowar | 3
11111 | Makwanpur | SisneriMahadevsthan | 7 | TEARFUND | RADO | ZOA | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 3
11112 | Makwanpur | SisneriMahadevsthan | 7 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 3
11113 | Makwanpur | SisneriMahadevsthan | 7 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Indrasarowar | 3
11114 | Makwanpur | SisneriMahadevsthan | 8 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 3
11115 | Makwanpur | SisneriMahadevsthan | 8 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 |  |  |  | Indrasarowar | 3
11116 | Makwanpur | SisneriMahadevsthan | 9 | TEARFUND | RADO | ZOA | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Indrasarowar | 3
11117 | Makwanpur | SisneriMahadevsthan | 9 | TEARFUND | RADO | ZOA | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Indrasarowar | 3
11118 | Makwanpur | Sukaura | 1 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 7
11119 | Makwanpur | Sukaura | 1 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 5 |  |  |  | Makawanpurgadhi | 7
11120 | Makwanpur | Sukaura | 2 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 7
11121 | Makwanpur | Sukaura | 2 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 7
11122 | Makwanpur | Sukaura | 2 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 8 |  |  |  | Makawanpurgadhi | 7
11123 | Makwanpur | Sukaura | 3 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 7
11124 | Makwanpur | Sukaura | 3 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 2 |  |  |  | Makawanpurgadhi | 7
11125 | Makwanpur | Sukaura | 4 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 7
11126 | Makwanpur | Sukaura | 4 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Makawanpurgadhi | 7
11127 | Makwanpur | Sukaura | 5 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 7
11128 | Makwanpur | Sukaura | 5 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Makawanpurgadhi | 7
11129 | Makwanpur | Sukaura | 6 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 4 |  |  |  | Makawanpurgadhi | 7
11130 | Makwanpur | Sukaura | 7 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 7
11131 | Makwanpur | Sukaura | 7 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Ongoing | 1 | 1 |  |  |  | Makawanpurgadhi | 7
11132 | Makwanpur | Sukaura | 7 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 |  |  |  | Makawanpurgadhi | 7
11133 | Makwanpur | Sukaura | 8 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 7
11134 | Makwanpur | Sukaura | 8 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Makawanpurgadhi | 7
11135 | Makwanpur | Sukaura | 9 | TEARFUND | RADO | TEAR-NET | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 1 | 1 |  |  |  | Makawanpurgadhi | 7
11136 | Makwanpur | Sukaura | 9 | TEARFUND | RADO | TEAR-NET | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 6 | 7 |  |  |  | Makawanpurgadhi | 7
11137 | Makwanpur | TistungDeurali | 1 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 15 | 13 |  |  |  | Thaha | 11
11138 | Makwanpur | TistungDeurali | 1 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 15 | 12 |  |  |  | Thaha | 11
11139 | Makwanpur | TistungDeurali | 1 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 15 | 13 |  |  |  | Thaha | 11
11140 | Makwanpur | TistungDeurali | 1 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Thaha | 11
11141 | Makwanpur | TistungDeurali | 1 | TEARFUND | RADO | DEC | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Thaha | 11
11142 | Makwanpur | TistungDeurali | 1 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 15 | 13 |  |  |  | Thaha | 11
11143 | Makwanpur | TistungDeurali | 1 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 |  |  |  | Thaha | 11
11144 | Makwanpur | TistungDeurali | 1 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 17 |  |  |  | Thaha | 11
11145 | Makwanpur | TistungDeurali | 2 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply new | Rs 253829 cash support for 44 households | # of households | Yes | Completed | 44 | 44 |  |  |  | Thaha | 11
11146 | Makwanpur | TistungDeurali | 2 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 36 | 36 |  |  |  | Thaha | 11
11147 | Makwanpur | TistungDeurali | 2 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 36 | 31 |  |  |  | Thaha | 11
11148 | Makwanpur | TistungDeurali | 2 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 36 | 30 |  |  |  | Thaha | 11
11149 | Makwanpur | TistungDeurali | 2 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Thaha | 11
11150 | Makwanpur | TistungDeurali | 2 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 36 | 30 |  |  |  | Thaha | 11
11151 | Makwanpur | TistungDeurali | 2 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 |  |  |  | Thaha | 11
11152 | Makwanpur | TistungDeurali | 2 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 14 |  |  |  | Thaha | 11
11153 | Makwanpur | TistungDeurali | 3 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 33 | 32 |  |  |  | Thaha | 11
11154 | Makwanpur | TistungDeurali | 3 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 33 | 31 |  |  |  | Thaha | 11
11155 | Makwanpur | TistungDeurali | 3 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 33 | 31 |  |  |  | Thaha | 11
11156 | Makwanpur | TistungDeurali | 3 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Thaha | 11
11157 | Makwanpur | TistungDeurali | 3 | TEARFUND | RADO | DEC | Technical Assistance | Demonstration Construction | House | 1 room, materials used- Rod, Ciment, Stone, Mud, Wood and CGI sheet | # of constructions | Yes | Completed | 1 | 1 |  |  |  | Thaha | 11
11158 | Makwanpur | TistungDeurali | 3 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 33 | 31 |  |  |  | Thaha | 11
11159 | Makwanpur | TistungDeurali | 3 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 |  |  |  | Thaha | 11
11160 | Makwanpur | TistungDeurali | 3 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 18 |  |  |  | Thaha | 11
11161 | Makwanpur | TistungDeurali | 4 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply new | Rs 1300602 cash support for 104 households | # of households | Yes | Completed | 104 | 104 |  |  |  | Thaha | 12
11162 | Makwanpur | TistungDeurali | 4 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 28 | 28 |  |  |  | Thaha | 12
11163 | Makwanpur | TistungDeurali | 4 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Completed | 28 | 28 |  |  |  | Thaha | 12
11164 | Makwanpur | TistungDeurali | 4 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Completed | 28 | 28 |  |  |  | Thaha | 12
11165 | Makwanpur | TistungDeurali | 4 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Thaha | 12
11166 | Makwanpur | TistungDeurali | 4 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Completed | 28 | 28 |  |  |  | Thaha | 12
11167 | Makwanpur | TistungDeurali | 4 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 |  |  |  | Thaha | 12
11168 | Makwanpur | TistungDeurali | 4 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 |  |  |  | Thaha | 12
11169 | Makwanpur | TistungDeurali | 5 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 46 | 44 |  |  |  | Thaha | 11
11170 | Makwanpur | TistungDeurali | 5 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 46 | 44 |  |  |  | Thaha | 11
11171 | Makwanpur | TistungDeurali | 5 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 46 | 43 |  |  |  | Thaha | 11
11172 | Makwanpur | TistungDeurali | 5 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Thaha | 11
11173 | Makwanpur | TistungDeurali | 5 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 46 | 43 |  |  |  | Thaha | 11
11174 | Makwanpur | TistungDeurali | 5 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 |  |  |  | Thaha | 11
11175 | Makwanpur | TistungDeurali | 5 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 15 |  |  |  | Thaha | 11
11176 | Makwanpur | TistungDeurali | 6 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 33 | 32 |  |  |  | Thaha | 12
11177 | Makwanpur | TistungDeurali | 6 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Completed | 33 | 32 |  |  |  | Thaha | 12
11178 | Makwanpur | TistungDeurali | 6 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 33 | 27 |  |  |  | Thaha | 12
11179 | Makwanpur | TistungDeurali | 6 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Thaha | 12
11180 | Makwanpur | TistungDeurali | 6 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 33 | 32 |  |  |  | Thaha | 12
11181 | Makwanpur | TistungDeurali | 6 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 3 | 2 |  |  |  | Thaha | 12
11182 | Makwanpur | TistungDeurali | 6 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 13 |  |  |  | Thaha | 12
11183 | Makwanpur | TistungDeurali | 7 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 22 | 21 |  |  |  | Thaha | 12
11184 | Makwanpur | TistungDeurali | 7 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 22 | 20 |  |  |  | Thaha | 12
11185 | Makwanpur | TistungDeurali | 7 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 22 | 12 |  |  |  | Thaha | 12
11186 | Makwanpur | TistungDeurali | 7 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Thaha | 12
11187 | Makwanpur | TistungDeurali | 7 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 22 | 21 |  |  |  | Thaha | 12
11188 | Makwanpur | TistungDeurali | 7 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 3 | 3 |  |  |  | Thaha | 12
11189 | Makwanpur | TistungDeurali | 7 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 14 |  |  |  | Thaha | 12
11190 | Makwanpur | TistungDeurali | 8 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 25 | 24 |  |  |  | Thaha | 12
11191 | Makwanpur | TistungDeurali | 8 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Completed | 25 | 24 |  |  |  | Thaha | 12
11192 | Makwanpur | TistungDeurali | 8 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 25 | 24 |  |  |  | Thaha | 12
11193 | Makwanpur | TistungDeurali | 8 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Thaha | 12
11194 | Makwanpur | TistungDeurali | 8 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 25 | 20 |  |  |  | Thaha | 12
11195 | Makwanpur | TistungDeurali | 8 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 |  |  |  | Thaha | 12
11196 | Makwanpur | TistungDeurali | 8 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 |  |  |  | Thaha | 12
11197 | Makwanpur | TistungDeurali | 9 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | Financial support on household WASH | HH water supply new | Rs 811682 cash support for 35 households | # of households | Yes | Completed | 35 | 35 |  |  |  | Thaha | 12
11198 | Makwanpur | TistungDeurali | 9 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs 50000per household | # of households | Yes | Completed | 62 | 60 |  |  |  | Thaha | 12
11199 | Makwanpur | TistungDeurali | 9 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs 90000per household | # of households | Yes | Ongoing | 62 | 59 |  |  |  | Thaha | 12
11200 | Makwanpur | TistungDeurali | 9 | TEARFUND | RADO | DEC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs 110000per household | # of households | Yes | Ongoing | 62 | 59 |  |  |  | Thaha | 12
11201 | Makwanpur | TistungDeurali | 9 | TEARFUND | RADO | DEC | Technical Assistance | Community reconstruction orientation | 1 session | 2 -3 hours for each session | # of participants | Yes | Completed | 1 | 1 |  |  |  | Thaha | 12
11202 | Makwanpur | TistungDeurali | 9 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and Technical coordinator ( Senior Engineer), Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) | # of households | Yes | Ongoing | 62 | 50 |  |  |  | Thaha | 12
11203 | Makwanpur | TistungDeurali | 9 | TEARFUND | RADO | DEC | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer for two VDC, 1 social mobilizer and Technical coordinator ( Senior Engineer) Generally 5 visits per house ( Lay out, DPC, Seal, Lintal, Roofing) for model house construction | # of households | Yes | Completed | 2 | 2 |  |  |  | Thaha | 12
11204 | Makwanpur | TistungDeurali | 9 | TEARFUND | RADO | DEC | Training | Short training | Masons (7 days DUDBC, rural or urban) | 5 days mason training using DUDBC curriculum | # of trainees | Yes | Completed | 16 | 16 |  |  |  | Thaha | 12
11205 | Makwanpur | Chitlang | 4 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1.5 hours each session | # of participants | Yes | Ongoing | 400 | 390 | 2016-07-22 | 2016-12-23 |  | Thaha | 9
11206 | Makwanpur | Chitlang | 4 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Information Center for reconstruction process in Chitlang | # of households supported | Yes | Completed | 125 | 125 | 2016-01-09 | 2017-02-16 |  | Thaha | 9
11207 | Makwanpur | Chitlang | 7 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1.5 hours each session | # of participants | Yes | Ongoing | 300 | 260 | 2016-07-22 | 2016-12-26 |  | Thaha | 10
11208 | Makwanpur | Chitlang | 9 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1.5 hours each session | # of participants | Yes | Ongoing | 200 | 160 | 2016-07-22 | 2016-12-23 |  | Thaha | 10
11209 | Makwanpur | Chitlang | 4 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and 1-2 project staffs | # of households | Yes | Ongoing | 70 | 67 | 2017-02-28 | 2018-02-28 | 2 Constructions were completed before Lumanti's intervention | Thaha | 9
11210 | Makwanpur | Chitlang | 7 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and 1-2 project staffs | # of households | Yes | Ongoing | 33 | 31 | 2017-02-28 | 2018-02-28 |  | Thaha | 10
11211 | Makwanpur | Chitlang | 9 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Door-to-door technical assistance | Continuous | 1 engineer, 1 social mobilizer and 1-2 project staffs | # of households | Yes | Completed | 22 | 22 | 2017-02-28 | 2018-02-28 |  | Thaha | 10
11212 | Makwanpur | Chitlang | 4 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 50000 per household | # of households | Yes | Ongoing | 70 | 67 | 2016-11-01 | 2018-02-28 |  | Thaha | 9
11213 | Makwanpur | Chitlang | 7 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 50000 per household | # of households | Yes | Ongoing | 33 | 32 | 2016-11-01 | 2018-02-28 |  | Thaha | 10
11214 | Makwanpur | Chitlang | 9 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 50000 per household | # of households | Yes | Completed | 23 | 23 | 2016-11-01 | 2018-02-28 |  | Thaha | 10
11215 | Makwanpur | Chitlang | 4 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Planned | 5 | 0 | 2017-02-25 | 2018-02-28 |  | Thaha | 9
11216 | Makwanpur | Chitlang | 7 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Planned | 3 | 0 | 2017-02-25 | 2018-02-28 |  | Thaha | 10
11217 | Makwanpur | Chitlang | 9 | Lumanti | Lumanti | MSEREOR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC Curriculum | # of trainees | Yes | Planned | 2 | 0 | 2017-02-25 | 2018-02-28 |  | Thaha | 10
11218 | Makwanpur | Chitlang | 4 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 per household | # of households | Yes | Ongoing | 70 | 42 | 2017-05-05 | 2018-02-28 |  | Thaha | 9
11219 | Makwanpur | Chitlang | 7 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 per household | # of households | Yes | Ongoing | 33 | 20 | 2017-05-05 | 2018-02-28 |  | Thaha | 10
11220 | Makwanpur | Chitlang | 9 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 per household | # of households | Yes | Ongoing | 22 | 20 | 2017-05-05 | 2018-02-28 |  | Thaha | 10
11221 | Makwanpur | Chitlang | 4 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Retrofitting | 80000 per household | # of households | Yes | Planned | 1 | 0 | 2017-03-01 |  |  | Thaha | 9
11222 | Makwanpur | Chitlang | 7 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Retrofitting | 80000 per household | # of households | Yes | Planned | 1 | 0 | 2017-03-01 |  |  | Thaha | 10
11223 | Makwanpur | Chitlang | 9 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Retrofitting | 80000 per household | # of households | Yes | Planned | 1 | 0 | 2017-03-01 |  |  | Thaha | 10
11224 | Makwanpur | Chitlang | 4 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Soap, Water, Posters, Flipchart, orientation | # of households | Yes | Ongoing | 90 | 60 | 2017-03-01 | 2018-02-28 |  | Thaha | 9
11225 | Makwanpur | Chitlang | 7 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Soap, Water, Posters, Flipchart, orientation | # of households | Yes | Planned | 36 | 0 | 2017-03-01 |  |  | Thaha | 10
11226 | Makwanpur | Chitlang | 9 | Lumanti | Lumanti | MSEREOR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Soap, Water, Posters, Flipchart, orientation | # of households | Yes | Planned | 24 | 0 | 2017-03-01 |  |  | Thaha | 10
11227 | Makwanpur | Chitlang | 4 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | 100000 per household | # of households | Yes | Ongoing | 70 | 30 | 2017-09-04 | 2018-02-28 |  | Thaha | 9
11228 | Makwanpur | Chitlang | 7 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | 100000 per household | # of households | Yes | Ongoing | 33 | 13 | 2017-09-04 | 2018-02-28 |  | Thaha | 10
11229 | Makwanpur | Chitlang | 9 | Lumanti | Lumanti | MSEREOR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | 100000 per household | # of households | Yes | Ongoing | 22 | 19 | 2017-09-04 | 2018-02-28 |  | Thaha | 10
11230 | Makwanpur | Ambhanjyang | 1 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-02 | 2017-07-30 | Planning data - National Level | Makawanpurgadhi | 5
11231 | Makwanpur | Ambhanjyang | 1 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-02 | 2017-07-30 | Planning data - National Level | Makawanpurgadhi | 5
11232 | Makwanpur | Ambhanjyang | 2 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-05-28 | 2017-07-20 | Planning data - National Level | Makawanpurgadhi | 5
11233 | Makwanpur | Ambhanjyang | 2 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-05-28 | 2017-07-20 | Planning data - National Level | Makawanpurgadhi | 5
11234 | Makwanpur | Ambhanjyang | 2 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-05-28 | 2017-07-20 | Planning data - National Level | Makawanpurgadhi | 5
11235 | Makwanpur | Ambhanjyang | 2 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-05-28 | 2017-07-20 | Planning data - National Level | Makawanpurgadhi | 5
11236 | Makwanpur | Ambhanjyang | 2 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-05-28 | 2017-07-20 | Planning data - National Level | Makawanpurgadhi | 5
11237 | Makwanpur | Ambhanjyang | 4 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-05-23 | 2017-07-27 | Planning data - National Level | Makawanpurgadhi | 5
11238 | Makwanpur | Ambhanjyang | 4 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-05-23 | 2017-07-27 | Planning data - National Level | Makawanpurgadhi | 5
11239 | Makwanpur | Ambhanjyang | 5 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-07 | 2017-06-06 | Planning data - National Level | Makawanpurgadhi | 6
11240 | Makwanpur | Ambhanjyang | 5 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-07 | 2017-06-06 | Planning data - National Level | Makawanpurgadhi | 6
11241 | Makwanpur | Ambhanjyang | 6 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-07 | 2017-04-26 | Planning data - National Level | Makawanpurgadhi | 6
11242 | Makwanpur | Ambhanjyang | 6 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-07 | 2017-04-26 | Planning data - National Level | Makawanpurgadhi | 6
11243 | Makwanpur | Ambhanjyang | 9 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-05-30 | 2017-07-29 | Planning data - National Level | Makawanpurgadhi | 6
11244 | Makwanpur | Ambhanjyang | 9 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-05-30 | 2017-07-29 | Planning data - National Level | Makawanpurgadhi | 6
11245 | Makwanpur | Ambhanjyang | 4 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-25 | 2017-07-01 |  | Makawanpurgadhi | 5
11246 | Makwanpur | Betini | 1 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-28 | 2017-05-20 | Planning data - National Level | Bagmati | 9
11247 | Makwanpur | Betini | 1 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-28 | 2017-05-20 | Planning data - National Level | Bagmati | 9
11248 | Makwanpur | Betini | 2 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-27 | 2017-04-17 | Planning data - National Level | Bagmati | 9
11249 | Makwanpur | Betini | 2 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-27 | 2017-04-17 | Planning data - National Level | Bagmati | 9
11250 | Makwanpur | Betini | 3 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-24 | 2017-04-14 |  | Bagmati | 9
11251 | Makwanpur | Betini | 3 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-24 | 2017-04-14 | Planning data - National Level | Bagmati | 9
11252 | Makwanpur | Betini | 3 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-24 | 2017-04-14 | Planning data - National Level | Bagmati | 9
11253 | Makwanpur | Betini | 4 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-15 | 2017-05-05 | Planning data - National Level | Bagmati | 9
11254 | Makwanpur | Betini | 4 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-15 | 2017-05-05 | Planning data - National Level | Bagmati | 9
11255 | Makwanpur | Betini | 5 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-23 | 2017-04-13 | Planning data - National Level | Bagmati | 9
11256 | Makwanpur | Betini | 5 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-23 | 2017-04-13 | Planning data - National Level | Bagmati | 9
11257 | Makwanpur | Betini | 8 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-12 | 2017-06-11 | Planning data - National Level | Bagmati | 9
11258 | Makwanpur | Betini | 8 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-12 | 2017-06-11 | Planning data - National Level | Bagmati | 9
11259 | Makwanpur | Bhaise | 2 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-27 | 2017-04-26 | Planning data - National Level | Bhimphedi | 2
11260 | Makwanpur | Bhaise | 2 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-27 | 2017-04-26 | Planning data - National Level | Bhimphedi | 2
11261 | Makwanpur | Bhaise | 4 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-05-22 | 2017-07-20 | Planning data - National Level | Bhimphedi | 2
11262 | Makwanpur | Bhaise | 4 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-05-22 | 2017-07-20 | Planning data - National Level | Bhimphedi | 2
11263 | Makwanpur | Bhaise | 6 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-05 | 2017-05-05 | Planning data - National Level | Bhimphedi | 1
11264 | Makwanpur | Bhaise | 6 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-05 | 2017-05-05 | Planning data - National Level | Bhimphedi | 1
11265 | Makwanpur | Bhaise | 7 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-07-03 | 2017-08-20 | Planning data - National Level | Bhimphedi | 1
11266 | Makwanpur | Bhaise | 7 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-07-03 | 2017-08-20 | Planning data - National Level | Bhimphedi | 1
11267 | Makwanpur | Bhaise | 9 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | Yes | Completed | 2 | 2 | 2017-06-04 | 2017-07-30 | Planning data - National Level | Bhimphedi | 2
11268 | Makwanpur | Bhaise | 9 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-04 | 2017-07-30 | Planning data - National Level | Bhimphedi | 2
11269 | Makwanpur | BhartaPundyadevi | 2 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-21 | 2017-04-27 |  | Kailash | 8
11270 | Makwanpur | BhartaPundyadevi | 1 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-09 | 2017-07-30 | Planning data - National Level | Kailash | 6
11271 | Makwanpur | BhartaPundyadevi | 1 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-09 | 2017-07-30 | Planning data - National Level | Kailash | 6
11272 | Makwanpur | BhartaPundyadevi | 2 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-22 | 2017-06-12 | Planning data - National Level | Kailash | 8
11273 | Makwanpur | BhartaPundyadevi | 2 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-22 | 2017-06-12 | Planning data - National Level | Kailash | 8
11274 | Makwanpur | BhartaPundyadevi | 4 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-27 | 2017-07-17 | Planning data - National Level | Kailash | 7
11275 | Makwanpur | BhartaPundyadevi | 4 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-27 | 2017-07-17 | Planning data - National Level | Kailash | 7
11276 | Makwanpur | BhartaPundyadevi | 7 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-27 | 2017-06-18 | Planning data - National Level | Kailash | 8
11277 | Makwanpur | BhartaPundyadevi | 7 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-27 | 2017-06-18 | Planning data - National Level | Kailash | 8
11278 | Makwanpur | BhartaPundyadevi | 8 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-05-28 | 2017-07-17 | Planning data - National Level | Kailash | 7
11279 | Makwanpur | BhartaPundyadevi | 8 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-05-28 | 2017-07-17 | Planning data - National Level | Kailash | 7
11280 | Makwanpur | BhartaPundyadevi | 3 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | Yes | Completed | 1 | 1 | 2017-05-07 | 2017-06-29 | Planning data - National Level | Kailash | 8
11281 | Makwanpur | BhartaPundyadevi | 3 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 5 | 5 | 2017-05-07 | 2017-06-29 | Planning data - National Level | Kailash | 8
11282 | Makwanpur | Bhimfedi | 1 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | Yes | Completed | 2 | 2 | 2017-04-21 | 2017-06-11 | Planning data - National Level | Bhimphedi | 6
11283 | Makwanpur | Bhimfedi | 1 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-21 | 2017-06-11 | Planning data - National Level | Bhimphedi | 6
11284 | Makwanpur | Bhimfedi | 1 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-20 | 2017-08-10 | Planning data - National Level | Bhimphedi | 6
11285 | Makwanpur | Bhimfedi | 1 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-20 | 2017-08-10 | Planning data - National Level | Bhimphedi | 6
11286 | Makwanpur | Bhimfedi | 4 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-26 | 2017-08-15 | Planning data - National Level | Bhimphedi | 6
11287 | Makwanpur | Bhimfedi | 4 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-26 | 2017-08-15 | Planning data - National Level | Bhimphedi | 6
11288 | Makwanpur | Bhimfedi | 4 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-18 | 2017-06-10 | Planning data - National Level | Bhimphedi | 6
11289 | Makwanpur | Bhimfedi | 4 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-18 | 2017-06-10 | Planning data - National Level | Bhimphedi | 6
11290 | Makwanpur | Bhimfedi | 5 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-21 | 2017-06-11 | Planning data - National Level | Bhimphedi | 5
11291 | Makwanpur | Bhimfedi | 5 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-21 | 2017-06-11 | Planning data - National Level | Bhimphedi | 5
11292 | Makwanpur | Bhimfedi | 6 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-19 | 2017-06-10 | Planning data - National Level | Bhimphedi | 5
11293 | Makwanpur | Bhimfedi | 6 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-19 | 2017-06-10 | Planning data - National Level | Bhimphedi | 5
11294 | Makwanpur | Bhimfedi | 7 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-23 | 2017-06-13 | Planning data - National Level | Bhimphedi | 5
11295 | Makwanpur | Bhimfedi | 7 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-23 | 2017-06-13 | Planning data - National Level | Bhimphedi | 5
11296 | Makwanpur | Bhimfedi | 8 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-07-02 | 2017-08-15 | Planning data - National Level | Bhimphedi | 6
11297 | Makwanpur | Bhimfedi | 8 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-07-02 | 2017-08-15 | Planning data - National Level | Bhimphedi | 6
11298 | Makwanpur | Dandakharka | 4 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-15 | 2017-06-21 |  | Kailash | 1
11299 | Makwanpur | Dandakharka | 1 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-18 | 2017-06-08 | Planning data - National Level | Kailash | 1
11300 | Makwanpur | Dandakharka | 1 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-18 | 2017-06-08 | Planning data - National Level | Kailash | 1
11301 | Makwanpur | Dandakharka | 2 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-07-11 | 2017-08-30 | Planning data - National Level | Kailash | 1
11302 | Makwanpur | Dandakharka | 2 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-07-11 | 2017-08-30 | Planning data - National Level | Kailash | 1
11303 | Makwanpur | Dandakharka | 3 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-11 | 2017-05-31 | Planning data - National Level | Kailash | 1
11304 | Makwanpur | Dandakharka | 3 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-11 | 2017-05-31 | Planning data - National Level | Kailash | 1
11305 | Makwanpur | Dandakharka | 4 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-03 | 2017-05-24 | Planning data - National Level | Kailash | 1
11306 | Makwanpur | Dandakharka | 4 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-03 | 2017-05-24 | Planning data - National Level | Kailash | 1
11307 | Makwanpur | Dandakharka | 5 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-03 | 2017-05-24 | Planning data - National Level | Kailash | 2
11308 | Makwanpur | Dandakharka | 5 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-03 | 2017-05-24 | Planning data - National Level | Kailash | 2
11309 | Makwanpur | Dandakharka | 5 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-07-11 | 2017-08-30 | Planning data - National Level | Kailash | 2
11310 | Makwanpur | Dandakharka | 5 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-07-11 | 2017-08-30 | Planning data - National Level | Kailash | 2
11311 | Makwanpur | Dandakharka | 7 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-05 | 2017-07-24 | Planning data - National Level | Kailash | 2
11312 | Makwanpur | Dandakharka | 7 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-05 | 2017-07-24 | Planning data - National Level | Kailash | 2
11313 | Makwanpur | Dandakharka | 8 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-22 | 2017-06-12 | Planning data - National Level | Kailash | 2
11314 | Makwanpur | Dandakharka | 8 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-22 | 2017-06-12 | Planning data - National Level | Kailash | 2
11315 | Makwanpur | Dandakharka | 8 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-07-11 | 2017-08-30 | Planning data - National Level | Kailash | 2
11316 | Makwanpur | Dandakharka | 8 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-07-11 | 2017-08-30 | Planning data - National Level | Kailash | 2
11317 | Makwanpur | Fakhel | 2 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Indrasarowar | 4
11318 | Makwanpur | Fakhel | 2 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-10 | 2017-07-30 | Planning data - National Level | Indrasarowar | 4
11319 | Makwanpur | Fakhel | 2 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-10 | 2017-07-30 | Planning data - National Level | Indrasarowar | 4
11320 | Makwanpur | Fakhel | 3 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-13 | 2017-08-01 | Planning data - National Level | Indrasarowar | 4
11321 | Makwanpur | Fakhel | 3 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-13 | 2017-08-01 | Planning data - National Level | Indrasarowar | 4
11322 | Makwanpur | Fakhel | 3 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-23 | 2017-08-11 | Planning data - National Level | Indrasarowar | 4
11323 | Makwanpur | Fakhel | 3 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-23 | 2017-08-11 | Planning data - National Level | Indrasarowar | 4
11324 | Makwanpur | Fakhel | 4 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-09 | 2017-07-29 | Planning data - National Level | Indrasarowar | 4
11325 | Makwanpur | Fakhel | 4 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-09 | 2017-07-29 | Planning data - National Level | Indrasarowar | 4
11326 | Makwanpur | Fakhel | 8 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-07 | 2017-07-28 | Planning data - National Level | Indrasarowar | 5
11327 | Makwanpur | Fakhel | 8 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-07 | 2017-07-28 | Planning data - National Level | Indrasarowar | 5
11328 | Makwanpur | Faparbari | 1 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Bagmati | 4
11329 | Makwanpur | Faparbari | 1 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-28 | 2017-06-16 | Planning data - National Level | Bagmati | 4
11330 | Makwanpur | Faparbari | 1 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-28 | 2017-06-16 | Planning data - National Level | Bagmati | 4
11331 | Makwanpur | Faparbari | 2 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-24 | 2017-04-14 | Planning data - National Level | Bagmati | 5
11332 | Makwanpur | Faparbari | 2 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-24 | 2017-04-14 | Planning data - National Level | Bagmati | 5
11333 | Makwanpur | Faparbari | 3 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-15 | 2017-06-08 | Planning data - National Level | Bagmati | 6
11334 | Makwanpur | Faparbari | 3 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-15 | 2017-06-08 | Planning data - National Level | Bagmati | 6
11335 | Makwanpur | Faparbari | 5 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-28 | 2017-04-18 | Planning data - National Level | Bagmati | 7
11336 | Makwanpur | Faparbari | 5 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-28 | 2017-04-18 | Planning data - National Level | Bagmati | 7
11337 | Makwanpur | Faparbari | 6 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-26 | 2017-04-16 | Planning data - National Level | Bagmati | 8
11338 | Makwanpur | Faparbari | 6 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-26 | 2017-04-16 | Planning data - National Level | Bagmati | 8
11339 | Makwanpur | Faparbari | 8 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-23 | 2017-04-13 | Planning data - National Level | Bagmati | 6
11340 | Makwanpur | Faparbari | 8 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-23 | 2017-04-13 | Planning data - National Level | Bagmati | 6
11341 | Makwanpur | Faparbari | 9 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-22 | 2017-05-11 | Planning data - National Level | Bagmati | 8
11342 | Makwanpur | Faparbari | 9 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-22 | 2017-05-11 | Planning data - National Level | Bagmati | 8
11343 | Makwanpur | Kalikatar | 6 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-31 | 2017-04-06 | Demo house was constructed during mason training. | Kailash | 3
11344 | Makwanpur | Kalikatar | 2 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-23 | 2017-05-23 | Demo house was constructed during mason training. | Kailash | 4
11345 | Makwanpur | Kalikatar | 3 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-21 | 2017-04-12 | Demo house was constructed during mason training. | Kailash | 3
11346 | Makwanpur | Kalikatar | 3 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-21 | 2017-04-12 | Demo house was constructed during mason training. | Kailash | 3
11347 | Makwanpur | Kalikatar | 4 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-24 | 2017-05-14 | Demo house was constructed during mason training. | Kailash | 4
11348 | Makwanpur | Kalikatar | 4 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-24 | 2017-05-14 | Demo house was constructed during mason training. | Kailash | 4
11349 | Makwanpur | Kalikatar | 7 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-09 | 2017-04-30 | Demo house was constructed during mason training. | Kailash | 4
11350 | Makwanpur | Kalikatar | 7 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-09 | 2017-04-30 | Demo house was constructed during mason training. | Kailash | 4
11351 | Makwanpur | Kalikatar | 9 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-22 | 2017-04-13 | Demo house was constructed during mason training. | Kailash | 4
11352 | Makwanpur | Kalikatar | 9 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-22 | 2017-04-13 | Demo house was constructed during mason training. | Kailash | 4
11353 | Makwanpur | Kankada | 1 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-27 | 2017-04-26 | Demo house was constructed during mason training. | Raksirang | 6
11354 | Makwanpur | Kankada | 1 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-27 | 2017-04-26 | Demo house was constructed during mason training. | Raksirang | 6
11355 | Makwanpur | Kankada | 2 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-13 | 2017-06-12 | Demo house was constructed during mason training. | Raksirang | 8
11356 | Makwanpur | Kankada | 2 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-13 | 2017-06-12 | Demo house was constructed during mason training. | Raksirang | 8
11357 | Makwanpur | Kankada | 3 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-05-22 | 2017-07-12 | Demo house was constructed during mason training. | Raksirang | 8
11358 | Makwanpur | Kankada | 3 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-05-22 | 2017-07-12 | Demo house was constructed during mason training. | Raksirang | 8
11359 | Makwanpur | Kankada | 4 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-05-26 | 2017-07-20 | Demo house was constructed during mason training. | Raksirang | 8
11360 | Makwanpur | Kankada | 4 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-05-26 | 2017-07-20 | Demo house was constructed during mason training. | Raksirang | 8
11361 | Makwanpur | Kankada | 4 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-22 | 2017-04-26 |  | Raksirang | 8
11362 | Makwanpur | Kankada | 4 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-22 | 2017-04-26 |  | Raksirang | 8
11363 | Makwanpur | Kankada | 5 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-19 | 2017-08-09 | Demo house was constructed during mason training. | Raksirang | 6
11364 | Makwanpur | Kankada | 5 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-19 | 2017-08-09 | Demo house was constructed during mason training. | Raksirang | 6
11365 | Makwanpur | Kankada | 6 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-19 | 2017-06-18 | Demo house was constructed during mason training. | Raksirang | 7
11366 | Makwanpur | Kankada | 6 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-19 | 2017-06-18 | Demo house was constructed during mason training. | Raksirang | 7
11367 | Makwanpur | Kankada | 7 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-01 | 2017-07-30 | Demo house was constructed during mason training. | Raksirang | 7
11368 | Makwanpur | Kankada | 7 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-01 | 2017-07-30 | Demo house was constructed during mason training. | Raksirang | 7
11369 | Makwanpur | Khairang | 1 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  | Demo house was constructed during mason training. | Raksirang | 9
11370 | Makwanpur | Khairang | 1 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-08 | 2017-04-27 | Demo house was constructed during mason training. | Raksirang | 9
11371 | Makwanpur | Khairang | 1 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-08 | 2017-04-27 | Demo house was constructed during mason training. | Raksirang | 9
11372 | Makwanpur | Khairang | 3 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-23 | 2017-04-15 | Demo house was constructed during mason training. | Raksirang | 9
11373 | Makwanpur | Khairang | 3 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-23 | 2017-04-15 | Demo house was constructed during mason training. | Raksirang | 9
11374 | Makwanpur | Khairang | 6 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-21 | 2017-06-11 | Demo house was constructed during mason training. | Raksirang | 9
11375 | Makwanpur | Khairang | 6 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-21 | 2017-06-11 | Demo house was constructed during mason training. | Raksirang | 9
11376 | Makwanpur | Khairang | 7 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-22 | 2017-04-14 | Demo house was constructed during mason training. | Raksirang | 9
11377 | Makwanpur | Khairang | 7 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-22 | 2017-04-14 | Demo house was constructed during mason training. | Raksirang | 9
11378 | Makwanpur | Khairang | 9 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-23 | 2017-04-15 | Demo house was constructed during mason training. | Raksirang | 9
11379 | Makwanpur | Khairang | 9 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-23 | 2017-04-15 | Demo house was constructed during mason training. | Raksirang | 9
11380 | Makwanpur | Khairang | 9 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-11 | 2017-07-31 | Demo house was constructed during mason training. | Raksirang | 9
11381 | Makwanpur | Khairang | 9 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-11 | 2017-07-31 | Demo house was constructed during mason training. | Raksirang | 9
11382 | Makwanpur | Kulekhani | 1 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-05-29 | 2017-07-19 | Demo house was constructed during mason training. | Indrasarowar | 2
11383 | Makwanpur | Kulekhani | 1 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-05-29 | 2017-07-19 | Demo house was constructed during mason training. | Indrasarowar | 2
11384 | Makwanpur | Kulekhani | 2 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-15 | 2017-08-04 | Demo house was constructed during mason training. | Indrasarowar | 2
11385 | Makwanpur | Kulekhani | 2 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-15 | 2017-08-04 | Demo house was constructed during mason training. | Indrasarowar | 2
11386 | Makwanpur | Kulekhani | 3 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-05-29 | 2017-07-19 | Demo house was constructed during mason training. | Indrasarowar | 2
11387 | Makwanpur | Kulekhani | 3 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-05-29 | 2017-07-19 | Demo house was constructed during mason training. | Indrasarowar | 2
11388 | Makwanpur | Kulekhani | 5 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-07-03 | 2017-08-22 | Demo house was constructed during mason training. | Indrasarowar | 2
11389 | Makwanpur | Kulekhani | 5 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-07-03 | 2017-08-22 | Demo house was constructed during mason training. | Indrasarowar | 2
11390 | Makwanpur | Kulekhani | 5 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-01 | 2017-07-20 | Demo house was constructed during mason training. | Indrasarowar | 2
11391 | Makwanpur | Kulekhani | 5 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-01 | 2017-07-20 | Demo house was constructed during mason training. | Indrasarowar | 2
11392 | Makwanpur | Kulekhani | 7 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-12 | 2017-07-31 |  | Indrasarowar | 2
11393 | Makwanpur | Kulekhani | 7 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-12 | 2017-07-31 |  | Indrasarowar | 2
11394 | Makwanpur | Manthali | 5 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  | Demo house was constructed during mason training. | Bakaiya | 10
11395 | Makwanpur | Manthali | 5 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-15 | 2017-05-05 | Demo house was constructed during mason training. | Bakaiya | 10
11396 | Makwanpur | Manthali | 5 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-15 | 2017-05-05 | Demo house was constructed during mason training. | Bakaiya | 10
11397 | Makwanpur | Manthali | 6 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-24 | 2017-05-13 | Demo house was constructed during mason training. | Bakaiya | 10
11398 | Makwanpur | Manthali | 6 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-24 | 2017-05-13 | Demo house was constructed during mason training. | Bakaiya | 10
11399 | Makwanpur | Manthali | 7 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-03 | 2017-04-22 | Demo house was constructed during mason training. | Bakaiya | 10
11400 | Makwanpur | Manthali | 7 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-03 | 2017-04-22 | Demo house was constructed during mason training. | Bakaiya | 10
11401 | Makwanpur | Manthali | 8 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-25 | 2017-06-14 | Demo house was constructed during mason training. | Bakaiya | 10
11402 | Makwanpur | Manthali | 8 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-25 | 2017-06-14 | Demo house was constructed during mason training. | Bakaiya | 10
11403 | Makwanpur | Manthali | 9 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-25 | 2017-05-14 | Demo house was constructed during mason training. | Bakaiya | 10
11404 | Makwanpur | Manthali | 9 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-25 | 2017-05-14 | Demo house was constructed during mason training. | Bakaiya | 10
11405 | Makwanpur | Markhu | 1 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  | Demo house was constructed during mason training. | Indrasarowar | 1
11406 | Makwanpur | Markhu | 2 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-01 | 2017-07-20 | Demo house was constructed during mason training. | Indrasarowar | 1
11407 | Makwanpur | Markhu | 2 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-01 | 2017-07-20 | Demo house was constructed during mason training. | Indrasarowar | 1
11408 | Makwanpur | Markhu | 3 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-10 | 2017-07-30 | Demo house was constructed during mason training. | Indrasarowar | 1
11409 | Makwanpur | Markhu | 3 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-10 | 2017-07-30 | Demo house was constructed during mason training. | Indrasarowar | 1
11410 | Makwanpur | Markhu | 5 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-19 | 2017-08-07 | Demo house was constructed during mason training. | Indrasarowar | 1
11411 | Makwanpur | Markhu | 5 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-19 | 2017-08-07 | Demo house was constructed during mason training. | Indrasarowar | 1
11412 | Makwanpur | Markhu | 7 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-03 | 2017-07-23 | Demo house was constructed during mason training. | Indrasarowar | 1
11413 | Makwanpur | Markhu | 7 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-03 | 2017-07-23 | Demo house was constructed during mason training. | Indrasarowar | 1
11414 | Makwanpur | Markhu | 8 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-16 | 2017-08-05 | Demo house was constructed during mason training. | Indrasarowar | 1
11415 | Makwanpur | Markhu | 8 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-16 | 2017-08-05 | Demo house was constructed during mason training. | Indrasarowar | 1
11416 | Makwanpur | Namtar | 6 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-08 | 2017-05-14 | Demo house was constructed during mason training. | Kailash | 10
11417 | Makwanpur | Namtar | 1 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-21 | 2017-04-11 | Demo house was constructed during mason training. | Bhimphedi | 9
11418 | Makwanpur | Namtar | 1 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-21 | 2017-04-11 | Demo house was constructed during mason training. | Bhimphedi | 9
11419 | Makwanpur | Namtar | 2 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-23 | 2017-05-12 | Demo house was constructed during mason training. | Kailash | 9
11420 | Makwanpur | Namtar | 2 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-23 | 2017-05-12 | Demo house was constructed during mason training. | Kailash | 9
11421 | Makwanpur | Namtar | 3 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-24 | 2017-04-15 | Demo house was constructed during mason training. | Bhimphedi | 9
11422 | Makwanpur | Namtar | 3 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-24 | 2017-04-15 | Demo house was constructed during mason training. | Bhimphedi | 9
11423 | Makwanpur | Namtar | 4 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-08 | 2017-07-29 | Demo house was constructed during mason training. | Bhimphedi | 9
11424 | Makwanpur | Namtar | 4 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-08 | 2017-07-29 | Demo house was constructed during mason training. | Bhimphedi | 9
11425 | Makwanpur | Namtar | 6 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-25 | 2017-05-15 | Demo house was constructed during mason training. | Kailash | 10
11426 | Makwanpur | Namtar | 6 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-25 | 2017-05-15 | Demo house was constructed during mason training. | Kailash | 10
11427 | Makwanpur | Namtar | 9 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-01 | 2017-04-19 | Demo house was constructed during mason training. | Kailash | 10
11428 | Makwanpur | Namtar | 9 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-01 | 2017-04-19 | Demo house was constructed during mason training. | Kailash | 10
11429 | Makwanpur | Nibuwatar | 3 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-05-26 | 2017-07-20 | Demo house was constructed during mason training. | Bhimphedi | 3
11430 | Makwanpur | Nibuwatar | 3 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-05-26 | 2017-07-20 | Demo house was constructed during mason training. | Bhimphedi | 3
11431 | Makwanpur | Nibuwatar | 3 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-19 | 2017-08-13 | Demo house was constructed during mason training. | Bhimphedi | 3
11432 | Makwanpur | Nibuwatar | 3 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-19 | 2017-08-13 | Demo house was constructed during mason training. | Bhimphedi | 3
11433 | Makwanpur | Nibuwatar | 4 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-05 | 2017-08-13 | Demo house was constructed during mason training. | Bhimphedi | 3
11434 | Makwanpur | Nibuwatar | 4 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-05 | 2017-08-13 | Demo house was constructed during mason training. | Bhimphedi | 3
11435 | Makwanpur | Nibuwatar | 5 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-27 | 2017-04-26 | Demo house was constructed during mason training. | Bhimphedi | 3
11436 | Makwanpur | Nibuwatar | 5 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-27 | 2017-04-26 | Demo house was constructed during mason training. | Bhimphedi | 3
11437 | Makwanpur | Nibuwatar | 7 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-07 | 2017-08-06 | Demo house was constructed during mason training. | Bhimphedi | 4
11438 | Makwanpur | Nibuwatar | 7 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-07 | 2017-08-06 | Demo house was constructed during mason training. | Bhimphedi | 4
11439 | Makwanpur | Nibuwatar | 8 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-18 | 2017-08-08 | Demo house was constructed during mason training. | Bhimphedi | 4
11440 | Makwanpur | Nibuwatar | 8 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-18 | 2017-08-08 | Demo house was constructed during mason training. | Bhimphedi | 4
11441 | Makwanpur | Raigaun | 1 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  | Demo house was constructed during mason training. | Bagmati | 1
11442 | Makwanpur | Raigaun | 1 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-26 | 2017-04-16 | Demo house was constructed during mason training. | Bagmati | 1
11443 | Makwanpur | Raigaun | 1 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-26 | 2017-04-16 | Demo house was constructed during mason training. | Bagmati | 1
11444 | Makwanpur | Raigaun | 2 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-26 | 2017-04-16 | Demo house was constructed during mason training. | Bagmati | 1
11445 | Makwanpur | Raigaun | 2 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-26 | 2017-04-16 | Demo house was constructed during mason training. | Bagmati | 1
11446 | Makwanpur | Raigaun | 3 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-22 | 2017-04-12 | Demo house was constructed during mason training. | Bagmati | 1
11447 | Makwanpur | Raigaun | 3 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-22 | 2017-04-12 | Demo house was constructed during mason training. | Bagmati | 1
11448 | Makwanpur | Raigaun | 4 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-28 | 2017-04-20 | Demo house was constructed during mason training. | Bagmati | 2
11449 | Makwanpur | Raigaun | 4 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-28 | 2017-04-20 | Demo house was constructed during mason training. | Bagmati | 2
11450 | Makwanpur | Raigaun | 5 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-27 | 2017-04-17 | Demo house was constructed during mason training. | Bagmati | 2
11451 | Makwanpur | Raigaun | 5 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-27 | 2017-04-17 | Demo house was constructed during mason training. | Bagmati | 2
11452 | Makwanpur | Raigaun | 6 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-18 | 2017-05-08 | Demo house was constructed during mason training. | Bagmati | 2
11453 | Makwanpur | Raigaun | 6 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-18 | 2017-05-08 | Demo house was constructed during mason training. | Bagmati | 2
11454 | Makwanpur | Raksirang | 2 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-13 | 2017-07-20 | Demo house was constructed during mason training. | Raksirang | 4
11455 | Makwanpur | Raksirang | 2 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-13 | 2017-07-20 | Demo house was constructed during mason training. | Raksirang | 4
11456 | Makwanpur | Raksirang | 4 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-16 | 2017-05-15 | Demo house was constructed during mason training. | Raksirang | 4
11457 | Makwanpur | Raksirang | 4 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-16 | 2017-05-15 | Demo house was constructed during mason training. | Raksirang | 4
11458 | Makwanpur | Raksirang | 8 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-05-22 | 2017-07-12 | Demo house was constructed during mason training. | Raksirang | 5
11459 | Makwanpur | Raksirang | 8 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-05-22 | 2017-07-12 | Demo house was constructed during mason training. | Raksirang | 5
11460 | Makwanpur | Raksirang | 8 | HELVETAS | TCN | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-04 | 2017-07-20 | Demo house was constructed during mason training. | Raksirang | 5
11461 | Makwanpur | Raksirang | 8 | HELVETAS | TCN | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-04 | 2017-07-20 | Demo house was constructed during mason training. | Raksirang | 5
11462 | Makwanpur | Raksirang | 9 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-26 | 2017-08-17 | Demo house was constructed during mason training. | Raksirang | 5
11463 | Makwanpur | Raksirang | 9 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-26 | 2017-08-17 | Demo house was constructed during mason training. | Raksirang | 5
11464 | Makwanpur | Raksirang | 9 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-26 | 2017-08-17 |  | Raksirang | 5
11465 | Makwanpur | Raksirang | 9 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-26 | 2017-08-17 |  | Raksirang | 5
11466 | Makwanpur | SarikhetPalase | 1 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-07 | 2017-05-28 | Demo house was constructed during mason training. | Raksirang | 3
11467 | Makwanpur | SarikhetPalase | 1 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-07 | 2017-05-28 | Demo house was constructed during mason training. | Raksirang | 3
11468 | Makwanpur | SarikhetPalase | 2 | HELVETAS | BCC | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  | Demo house was constructed during mason training. | Raksirang | 3
11469 | Makwanpur | SarikhetPalase | 2 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | Yes | Completed | 2 | 2 | 2017-04-09 | 2017-05-30 | Demo house was constructed during mason training. | Raksirang | 3
11470 | Makwanpur | SarikhetPalase | 2 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2015-12-20 | 2016-01-24 | Demo house was constructed during mason training. | Raksirang | 3
11471 | Makwanpur | SarikhetPalase | 3 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | Yes | Completed | 2 | 2 | 2017-04-09 | 2017-05-30 | Demo house was constructed during mason training. | Raksirang | 3
11472 | Makwanpur | SarikhetPalase | 3 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-09 | 2017-05-30 | Demo house was constructed during mason training. | Raksirang | 3
11473 | Makwanpur | SarikhetPalase | 4 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | Yes | Completed | 2 | 2 | 2017-04-21 | 2017-06-11 | Demo house was constructed during mason training. | Raksirang | 3
11474 | Makwanpur | SarikhetPalase | 4 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-21 | 2017-06-11 | Demo house was constructed during mason training. | Raksirang | 3
11475 | Makwanpur | SarikhetPalase | 6 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | Yes | Completed | 2 | 2 | 2017-04-21 | 2017-06-11 | Demo house was constructed during mason training. | Raksirang | 2
11476 | Makwanpur | SarikhetPalase | 6 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-21 | 2017-06-11 | Demo house was constructed during mason training. | Raksirang | 2
11477 | Makwanpur | SarikhetPalase | 3 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | Yes | Completed | 2 | 2 | 2017-07-06 | 2017-08-24 | Demo house was constructed during mason training. | Raksirang | 3
11478 | Makwanpur | SarikhetPalase | 3 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-07-06 | 2017-08-24 | Demo house was constructed during mason training. | Raksirang | 3
11479 | Makwanpur | SarikhetPalase | 8 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | Yes | Completed | 2 | 2 | 2017-04-09 | 2017-05-30 | Demo house was constructed during mason training. | Raksirang | 1
11480 | Makwanpur | SarikhetPalase | 8 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-09 | 2017-05-30 | Demo house was constructed during mason training. | Raksirang | 1
11481 | Makwanpur | Shikharpur | 2 | HELVETAS | KITE | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  | Demo house was constructed during mason training. | Bakaiya | 8
11482 | Makwanpur | Shikharpur | 1 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-25 | 2017-04-15 | Demo house was constructed during mason training. | Bakaiya | 8
11483 | Makwanpur | Shikharpur | 1 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-25 | 2017-04-15 | Demo house was constructed during mason training. | Bakaiya | 8
11484 | Makwanpur | Shikharpur | 3 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-16 | 2017-05-06 | Demo house was constructed during mason training. | Bakaiya | 8
11485 | Makwanpur | Shikharpur | 3 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-16 | 2017-05-06 | Demo house was constructed during mason training. | Bakaiya | 8
11486 | Makwanpur | Shikharpur | 4 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-18 | 2017-04-13 | Demo house was constructed during mason training. | Bakaiya | 8
11487 | Makwanpur | Shikharpur | 4 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-18 | 2017-04-13 | Demo house was constructed during mason training. | Bakaiya | 8
11488 | Makwanpur | Shikharpur | 5 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-26 | 2017-04-16 | Demo house was constructed during mason training. | Bakaiya | 9
11489 | Makwanpur | Shikharpur | 5 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-26 | 2017-04-16 | Demo house was constructed during mason training. | Bakaiya | 9
11490 | Makwanpur | Shikharpur | 6 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-27 | 2017-06-18 | Demo house was constructed during mason training. | Bakaiya | 9
11491 | Makwanpur | Shikharpur | 6 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-27 | 2017-06-18 | Demo house was constructed during mason training. | Bakaiya | 9
11492 | Makwanpur | Shikharpur | 8 | HELVETAS | KITE | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-22 | 2017-06-15 | Demo house was constructed during mason training. | Bakaiya | 9
11493 | Makwanpur | Shikharpur | 8 | HELVETAS | KITE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-22 | 2017-06-15 | Demo house was constructed during mason training. | Bakaiya | 9
11494 | Makwanpur | ShreepurChhatiwan | 1 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-21 | 2017-04-10 | Demo house was constructed during mason training. | Bakaiya | 3
11495 | Makwanpur | ShreepurChhatiwan | 1 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-21 | 2017-04-10 | Demo house was constructed during mason training. | Bakaiya | 3
11496 | Makwanpur | ShreepurChhatiwan | 2 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-26 | 2017-04-16 | Demo house was constructed during mason training. | Bakaiya | 3
11497 | Makwanpur | ShreepurChhatiwan | 2 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-26 | 2017-04-16 | Demo house was constructed during mason training. | Bakaiya | 3
11498 | Makwanpur | ShreepurChhatiwan | 3 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  | Demo house was constructed during mason training. | Bakaiya | 4
11499 | Makwanpur | ShreepurChhatiwan | 3 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-20 | 2017-04-10 | Demo house was constructed during mason training. | Bakaiya | 4
11500 | Makwanpur | ShreepurChhatiwan | 3 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-20 | 2017-04-10 | Demo house was constructed during mason training. | Bakaiya | 4
11501 | Makwanpur | ShreepurChhatiwan | 4 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-13 | 2017-04-30 | Demo house was constructed during mason training. | Bakaiya | 7
11502 | Makwanpur | ShreepurChhatiwan | 4 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-13 | 2017-04-30 | Demo house was constructed during mason training. | Bakaiya | 7
11503 | Makwanpur | ShreepurChhatiwan | 5 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-05-18 | 2017-07-08 | Demo house was constructed during mason training. | Bakaiya | 4
11504 | Makwanpur | ShreepurChhatiwan | 5 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-05-18 | 2017-07-08 | Demo house was constructed during mason training. | Bakaiya | 4
11505 | Makwanpur | ShreepurChhatiwan | 5 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-07-13 | 2017-08-31 | Demo house was constructed during mason training. | Bakaiya | 4
11506 | Makwanpur | ShreepurChhatiwan | 5 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-07-13 | 2017-08-31 | Demo house was constructed during mason training. | Bakaiya | 4
11507 | Makwanpur | ShreepurChhatiwan | 7 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-02-21 | 2017-04-10 | Demo house was constructed during mason training. | Bakaiya | 5
11508 | Makwanpur | ShreepurChhatiwan | 7 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-02-21 | 2017-04-10 | Demo house was constructed during mason training. | Bakaiya | 5
11509 | Makwanpur | ShreepurChhatiwan | 8 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-20 | 2017-05-08 | Demo house was constructed during mason training. | Bakaiya | 5
11510 | Makwanpur | ShreepurChhatiwan | 8 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-20 | 2017-05-08 | Demo house was constructed during mason training. | Bakaiya | 5
11511 | Makwanpur | SisneriMahadevsthan | 1 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-26 | 2017-06-16 | Demo house was constructed during mason training. | Indrasarowar | 3
11512 | Makwanpur | SisneriMahadevsthan | 1 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-26 | 2017-06-16 | Demo house was constructed during mason training. | Indrasarowar | 3
11513 | Makwanpur | SisneriMahadevsthan | 1 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | Yes | Completed | 2 | 2 | 2017-07-12 | 2017-08-30 |  | Indrasarowar | 3
11514 | Makwanpur | SisneriMahadevsthan | 1 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-07-12 | 2017-08-30 |  | Indrasarowar | 3
11515 | Makwanpur | SisneriMahadevsthan | 2 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-18 | 2017-06-10 | Demo house was constructed during mason training. | Indrasarowar | 3
11516 | Makwanpur | SisneriMahadevsthan | 2 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-18 | 2017-06-10 | Demo house was constructed during mason training. | Indrasarowar | 3
11517 | Makwanpur | SisneriMahadevsthan | 3 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-18 | 2017-06-10 | Demo house was constructed during mason training. | Indrasarowar | 3
11518 | Makwanpur | SisneriMahadevsthan | 3 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-18 | 2017-06-10 | Demo house was constructed during mason training. | Indrasarowar | 3
11519 | Makwanpur | SisneriMahadevsthan | 4 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-18 | 2017-06-10 | Demo house was constructed during mason training. | Indrasarowar | 3
11520 | Makwanpur | SisneriMahadevsthan | 4 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-18 | 2017-06-10 | Demo house was constructed during mason training. | Indrasarowar | 3
11521 | Makwanpur | SisneriMahadevsthan | 2 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-29 | 2017-08-18 | Demo house was constructed during mason training. | Indrasarowar | 3
11522 | Makwanpur | SisneriMahadevsthan | 2 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-29 | 2017-08-18 | Demo house was constructed during mason training. | Indrasarowar | 3
11523 | Makwanpur | SisneriMahadevsthan | 6 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-26 | 2017-06-16 | Demo house was constructed during mason training. | Indrasarowar | 3
11524 | Makwanpur | SisneriMahadevsthan | 6 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-26 | 2017-06-16 | Demo house was constructed during mason training. | Indrasarowar | 3
11525 | Makwanpur | SisneriMahadevsthan | 4 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-29 | 2017-08-18 | Demo house was constructed during mason training. | Indrasarowar | 3
11526 | Makwanpur | SisneriMahadevsthan | 4 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-29 | 2017-08-18 | Demo house was constructed during mason training. | Indrasarowar | 3
11527 | Makwanpur | SisneriMahadevsthan | 9 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-06-29 | 2017-08-18 | Demo house was constructed during mason training. | Indrasarowar | 3
11528 | Makwanpur | SisneriMahadevsthan | 9 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-06-29 | 2017-08-18 | Demo house was constructed during mason training. | Indrasarowar | 3
11529 | Makwanpur | SisneriMahadevsthan | 9 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-04-26 | 2017-06-16 | Demo house was constructed during mason training. | Indrasarowar | 3
11530 | Makwanpur | SisneriMahadevsthan | 9 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-04-26 | 2017-06-16 | Demo house was constructed during mason training. | Indrasarowar | 3
11531 | Makwanpur | Thingan | 2 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-29 | 2017-05-23 | Planning data - National Level | Bakaiya | 11
11532 | Makwanpur | Thingan | 2 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-29 | 2017-05-23 | Planning data - National Level | Bakaiya | 11
11533 | Makwanpur | Thingan | 3 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-20 | 2017-05-10 | Planning data - National Level | Bakaiya | 12
11534 | Makwanpur | Thingan | 3 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-20 | 2017-05-10 | Planning data - National Level | Bakaiya | 12
11535 | Makwanpur | Thingan | 4 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-20 | 2017-05-10 | Planning data - National Level | Bakaiya | 12
11536 | Makwanpur | Thingan | 4 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-20 | 2017-05-10 | Planning data - National Level | Bakaiya | 12
11537 | Makwanpur | Thingan | 5 | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Bakaiya | 11
11538 | Makwanpur | Thingan | 5 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-30 | 2017-05-25 | Planning data - National Level | Bakaiya | 11
11539 | Makwanpur | Thingan | 5 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-30 | 2017-05-25 | Planning data - National Level | Bakaiya | 11
11540 | Makwanpur | Thingan | 6 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-30 | 2017-05-25 | Planning data - National Level | Bakaiya | 12
11541 | Makwanpur | Thingan | 6 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-30 | 2017-05-25 | Planning data - National Level | Bakaiya | 12
11542 | Makwanpur | Thingan | 9 | HELVETAS | SODEC-N | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | No | Completed | 2 | 2 | 2017-03-30 | 2017-05-25 | Planning data - National Level | Bakaiya | 12
11543 | Makwanpur | Thingan | 9 | HELVETAS | SODEC-N | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 10 | 10 | 2017-03-30 | 2017-05-25 | Planning data - National Level | Bakaiya | 12
11544 | Makwanpur | BhartaPundyadevi | 9 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | Yes | Completed | 1 | 1 | 2017-05-07 | 2017-06-29 |  | Kailash | 8
11545 | Makwanpur | BhartaPundyadevi | 9 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 5 | 5 | 2017-05-07 | 2017-06-29 |  | Kailash | 8
11546 | Makwanpur | SisneriMahadevsthan | 2 | HELVETAS | BCC | DFID | Technical Assistance | Demonstration Construction | House | Demonstration construction houses provide a practical demonstration of earthquake resilient construction elements. The construction should be accompanied by communication and outreach activities and events to ensure maximum dissemination of the information to the community. | # of constructions | Yes | Completed | 1 | 1 | 2017-07-12 | 2017-08-30 |  | Indrasarowar | 3
11547 | Makwanpur | SisneriMahadevsthan | 2 | HELVETAS | BCC | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days on-the-job training according to the NRA Training Strategy. The OJT training refer to a 50-day training model for new masons through building a demo house based on CTEVT curriculum. | # of trainees | Yes | Completed | 5 | 5 | 2017-07-12 | 2017-08-30 |  | Indrasarowar | 3
11548 | Makwanpur | Bhaise | All | CS | Sabal | USAID | Training | Vocational training | Electrician (CTEVT) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Bhimphedi | 2
11549 | Makwanpur | Chitlang | ALL | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 |  |  |  | Thaha | 9
11550 | Makwanpur | Chitlang | ALL | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 30 | 30 |  |  |  | Thaha | 9
11551 | Makwanpur | Dhimal | All | Americares | BNMT | Americares | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bakaiya | 2
11552 | Makwanpur | Dhimal | All | Americares | BNMT | Americares | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Ongoing | 9 | 6 |  |  | #event is unit | Bakaiya | 2
11553 | Makwanpur | Fakhel | ALL | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 |  |  |  | Indrasarowar | 5
11554 | Makwanpur | Fakhel | ALL | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Ongoing | 30 | 30 |  |  |  | Indrasarowar | 5
11555 | Makwanpur | Fakhel | All | Americares | BNMT | Americares | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Indrasarowar | 5
11556 | Makwanpur | Fakhel | All | Americares | BNMT | Americares | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Ongoing | 9 | 9 |  |  |  | Indrasarowar | 5
11557 | Makwanpur | Fakhel | ALL | PLAN | CEEDF | ECHO | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | A VDC wise committee was formed by the chair of VDC secreatry and it has represnetatives from all wards of VDC. There are even representative from police office, Health Post, School and Political parties. | # of committees | Yes | Planned | 0 | 0 |  |  |  | Indrasarowar | 5
11558 | Makwanpur | Handikhola | All | BLF | BNMT | BLF | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Completed | 2 | 2 |  |  |  | Manahari | 3
11559 | Makwanpur | Hetauda U.M.N.P. | All | Americares | BNMT | Americares | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Hetauda | 19
11560 | Makwanpur | Hetauda U.M.N.P. | All | Americares | BNMT | Americares | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Ongoing | 9 | 9 |  |  |  | Hetauda | 19
11561 | Makwanpur | Hetauda U.M.N.P. | All | BLF | BNMT | BLF | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Completed | 2 | 2 |  |  |  | Hetauda | 19
11562 | Makwanpur | Khairang | All | Americares | BNMT | Americares | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Raksirang | 9
11563 | Makwanpur | Khairang | All | Americares | BNMT | Americares | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Completed | 9 | 9 |  |  |  | Raksirang | 9
11564 | Makwanpur | Kulekhani | ALL | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 |  |  |  | Indrasarowar | 2
11565 | Makwanpur | Kulekhani | ALL | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 30 | 30 |  |  |  | Indrasarowar | 2
11566 | Makwanpur | Kulekhani | ALL | PLAN | CEEDF | ECHO | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | A VDC wise committee was formed by the chair of VDC secreatry and it has represnetatives from all wards of VDC. There are even representative from police office, Health Post, School and Political parties. | # of committees | Yes | Planned | 0 | 0 |  |  |  | Indrasarowar | 2
11567 | Makwanpur | Makwanpurgadhi | All | Americares | BNMT | Americares | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Makawanpurgadhi | 5
11568 | Makwanpur | Makwanpurgadhi | All | Americares | BNMT | Americares | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Ongoing | 9 | 7 |  |  |  | Makawanpurgadhi | 5
11569 | Makwanpur | Manahari | All | BLF | BNMT | BLF | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Completed | 2 | 2 |  |  |  | Manahari | 9
11570 | Makwanpur | Manahari | All | CS | Sabal | USAID | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Planned | 20 | 0 |  |  |  | Manahari | 9
11571 | Makwanpur | Markhu | ALL | PLAN | CEEDF | PLAN-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 8 | 8 |  |  |  | Indrasarowar | 1
11572 | Makwanpur | Markhu | ALL | PLAN | CEEDF | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 30 | 30 |  |  |  | Indrasarowar | 1
11573 | Makwanpur | Markhu | ALL | PLAN | CEEDF | ECHO | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | A VDC wise committee was formed by the chair of VDC secreatry and it has represnetatives from all wards of VDC. There are even representative from police office, Health Post, School qnd Political parties. | # of committees | Yes | Planned | 0 | 0 |  |  |  | Indrasarowar | 1
11574 | Makwanpur | Nibuwatar | All | Americares | BNMT | Americares | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bhimphedi | 4
11575 | Makwanpur | Nibuwatar | All | Americares | BNMT | Americares | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Completed | 9 | 5 |  |  |  | Bhimphedi | 4
11576 | Makwanpur | SarikhetPalase | ALL | CS | Sabal | USAID | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) | 390 hours based on CTEVT curriculum | # of trainees | Yes | Planned | 20 | 0 |  |  |  | Raksirang | 3
11577 | Makwanpur | TistungDeurali | All | Americares | BNMT | Americares | Technical Assistance | Community toilet construction | Community toilet construction | Community toilet construction near school | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Thaha | 12
11578 | Makwanpur | TistungDeurali | All | Americares | BNMT | Americares | Technical Assistance | Hygiene and sanitation promotion | Hygiene and Sanitation Promotion | It aims to capture all household through teacher , FCHV, Healthpost management committee, ward citizenship forum, VWASH | # of households | Yes | Ongoing | 9 | 9 |  |  |  | Thaha | 12
11579 | Makwanpur | Bhimfedi |  | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Bhimphedi | 6
11580 | Makwanpur | SisneriMahadevsthan |  | HELVETAS | SODEC-N | DFID | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-07-12 | 2017-08-30 | Demo house was constructed during mason training. | Indrasarowar | 3
11581 | Makwanpur | Dandakharka | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 5 | 5 | 2016-01-01 | 2018-12-31 |  | Kailash | 1
11582 | Makwanpur | Dandakharka | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 4 | 4 | 2016-01-01 | 2018-12-31 |  | Kailash | 1
11583 | Makwanpur | Dandakharka | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kailash | 1
11584 | Makwanpur | Dandakharka | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kailash | 1
11585 | Makwanpur | Dandakharka | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kailash | 2
11586 | Makwanpur | Dandakharka | 6 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kailash | 1
11587 | Makwanpur | Dandakharka | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kailash | 2
11588 | Makwanpur | Dandakharka | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kailash | 2
11589 | Makwanpur | Dandakharka | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kailash | 2
11590 | Makwanpur | Gogane | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 16 | 16 | 2016-01-01 | 2018-12-31 |  | Kailash | 5
11591 | Makwanpur | Gogane | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kailash | 5
11592 | Makwanpur | Gogane | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kailash | 5
11593 | Makwanpur | Gogane | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kailash | 5
11594 | Makwanpur | Gogane | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kailash | 5
11595 | Makwanpur | Gogane | 6 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kailash | 5
11596 | Makwanpur | Gogane | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kailash | 6
11597 | Makwanpur | Gogane | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kailash | 6
11598 | Makwanpur | Gogane | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kailash | 6
11599 | Makwanpur | Khairang | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 5 | 5 | 2016-01-01 | 2018-12-31 |  | Raksirang | 9
11600 | Makwanpur | Khairang | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 4 | 4 | 2016-01-01 | 2018-12-31 |  | Raksirang | 9
11601 | Makwanpur | Khairang | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Raksirang | 9
11602 | Makwanpur | Khairang | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Raksirang | 9
11603 | Makwanpur | Khairang | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Raksirang | 9
11604 | Makwanpur | Khairang | 6 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Raksirang | 9
11605 | Makwanpur | Khairang | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Raksirang | 9
11606 | Makwanpur | Khairang | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Raksirang | 9
11607 | Makwanpur | Khairang | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Raksirang | 9
11608 | Makwanpur | Namtar | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Bhimphedi | 9
11609 | Makwanpur | Namtar | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Kailash | 9
11610 | Makwanpur | Namtar | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Bhimphedi | 9
11611 | Makwanpur | Namtar | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Bhimphedi | 9
11612 | Makwanpur | Namtar | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Kailash | 9
11613 | Makwanpur | Namtar | 6 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Kailash | 10
11614 | Makwanpur | Namtar | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Kailash | 9
11615 | Makwanpur | Namtar | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 5 | 5 | 2016-01-01 | 2018-12-31 |  | Kailash | 10
11616 | Makwanpur | Namtar | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Kailash | 10
11617 | Makwanpur | Thaha N.P. | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Thaha | 1
11618 | Makwanpur | Thaha N.P. | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Thaha | 2
11619 | Makwanpur | Thaha N.P. | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Thaha | 2
11620 | Makwanpur | Thaha N.P. | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Thaha | 2
11621 | Makwanpur | Thaha N.P. | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Thaha | 2
11622 | Makwanpur | Thaha N.P. | 6 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Thaha | 3
11623 | Makwanpur | Thaha N.P. | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Thaha | 3
11624 | Makwanpur | Thaha N.P. | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Thaha | 4
11625 | Makwanpur | Thaha N.P. | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Thaha | 4
11626 | Makwanpur | Thaha N.P. | 10 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Thaha | 5
11627 | Makwanpur | Thaha N.P. | 11 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Thaha | 5
11628 | Makwanpur | Thaha N.P. | 12 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Thaha | 1
11629 | Makwanpur | Thaha N.P. | 13 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Thaha | 6
11630 | Makwanpur | Thaha N.P. | 14 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Thaha | 6
11631 | Makwanpur | Thaha N.P. | 15 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Thaha | 6
11632 | Makwanpur | Gogane | 1 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 47 | 41 | 2016-09-01 | 2018-12-31 |  | Kailash | 5
11633 | Makwanpur | Gogane | 2 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 39 | 39 | 2016-11-17 | 2016-12-15 |  | Kailash | 5
11634 | Makwanpur | Gogane | 3 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 46 | 40 | 2016-11-17 | 2016-12-15 |  | Kailash | 5
11635 | Makwanpur | Gogane | 4 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 46 | 38 | 2016-11-17 | 2016-12-15 |  | Kailash | 5
11636 | Makwanpur | Gogane | 5 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 64 | 51 | 2016-11-17 | 2016-12-15 |  | Kailash | 5
11637 | Makwanpur | Gogane | 6 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 92 | 72 | 2016-11-17 | 2016-12-15 |  | Kailash | 5
11638 | Makwanpur | Gogane | 7 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 145 | 132 | 2016-11-17 | 2016-12-15 |  | Kailash | 6
11639 | Makwanpur | Gogane | 8 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 93 | 80 | 2016-11-17 | 2016-12-15 |  | Kailash | 6
11640 | Makwanpur | Gogane | 9 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 65 | 54 | 2016-11-17 | 2016-12-15 |  | Kailash | 6
11641 | Makwanpur | Gogane | 1 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 47 | 34 |  |  |  | Kailash | 5
11642 | Makwanpur | Gogane | 2 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 39 | 18 | 2016-09-01 | 2018-12-31 |  | Kailash | 5
11643 | Makwanpur | Gogane | 3 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 46 | 55 | 2016-09-01 | 2018-12-31 |  | Kailash | 5
11644 | Makwanpur | Gogane | 4 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 46 | 97 | 2016-09-01 | 2018-12-31 |  | Kailash | 5
11645 | Makwanpur | Gogane | 5 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 64 | 84 | 2016-09-01 | 2018-12-31 |  | Kailash | 5
11646 | Makwanpur | Gogane | 6 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 92 | 73 | 2016-09-01 | 2018-12-31 |  | Kailash | 5
11647 | Makwanpur | Gogane | 7 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 145 | 34 | 2016-09-01 | 2018-12-31 |  | Kailash | 6
11648 | Makwanpur | Gogane | 8 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 93 | 61 | 2016-09-01 | 2018-12-31 |  | Kailash | 6
11649 | Makwanpur | Gogane | 9 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 65 | 78 | 2016-09-01 | 2018-12-31 |  | Kailash | 6
11650 | Makwanpur | Gogane | 1 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 47 | 8 | 2016-09-01 | 2018-12-31 |  | Kailash | 5
11651 | Makwanpur | Gogane | 2 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 39 | 14 | 2016-09-01 | 2018-12-31 |  | Kailash | 5
11652 | Makwanpur | Gogane | 3 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 46 | 40 | 2016-09-01 | 2018-12-31 |  | Kailash | 5
11653 | Makwanpur | Gogane | 4 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 46 | 44 | 2016-09-01 | 2018-12-31 |  | Kailash | 5
11654 | Makwanpur | Gogane | 5 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 64 | 60 | 2016-09-01 | 2018-12-31 |  | Kailash | 5
11655 | Makwanpur | Gogane | 6 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 92 | 50 | 2016-09-01 | 2018-12-31 |  | Kailash | 5
11656 | Makwanpur | Gogane | 7 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 145 | 18 | 2016-09-01 | 2018-12-31 |  | Kailash | 6
11657 | Makwanpur | Gogane | 8 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 93 | 27 | 2016-09-01 | 2018-12-31 |  | Kailash | 6
11658 | Makwanpur | Gogane | 9 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 65 | 53 | 2016-09-01 | 2018-12-31 |  | Kailash | 6
11659 | Makwanpur | Gogane | 1 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 47 | 47 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kailash | 5
11660 | Makwanpur | Gogane | 2 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 39 | 39 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kailash | 5
11661 | Makwanpur | Gogane | 3 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 46 | 46 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kailash | 5
11662 | Makwanpur | Gogane | 4 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 46 | 46 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kailash | 5
11663 | Makwanpur | Gogane | 5 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 64 | 64 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kailash | 5
11664 | Makwanpur | Gogane | 6 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 92 | 92 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kailash | 5
11665 | Makwanpur | Gogane | 7 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 145 | 145 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kailash | 6
11666 | Makwanpur | Gogane | 8 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 93 | 93 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kailash | 6
11667 | Makwanpur | Gogane | 9 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 65 | 65 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kailash | 6
11668 | Nuwakot | BagesworiChokade | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 2
11669 | Nuwakot | BagesworiChokade | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 3
11670 | Nuwakot | BagesworiChokade | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 3
11671 | Nuwakot | BagesworiChokade | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 2
11672 | Nuwakot | BagesworiChokade | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 2
11673 | Nuwakot | BagesworiChokade | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 3
11674 | Nuwakot | BagesworiChokade | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 2
11675 | Nuwakot | BagesworiChokade | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 3
11676 | Nuwakot | BagesworiChokade | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 2
11677 | Nuwakot | BagesworiChokade | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 2
11678 | Nuwakot | BagesworiChokade | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 3
11679 | Nuwakot | BagesworiChokade | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 3
11680 | Nuwakot | BagesworiChokade | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 2
11681 | Nuwakot | BagesworiChokade | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 2
11682 | Nuwakot | BagesworiChokade | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 3
11683 | Nuwakot | BagesworiChokade | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 2
11684 | Nuwakot | BagesworiChokade | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 3
11685 | Nuwakot | BagesworiChokade | 7 | GON - PAF | CDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 10 | 10 | 2017-06-09 | 2017-06-15 |  | Suryagadhi | 3
11686 | Nuwakot | BagesworiChokade | 9 | GON - PAF | CDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 25 | 25 | 2017-06-24 | 2017-06-30 |  | Suryagadhi | 3
11687 | Nuwakot | Balkumari | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 5
11688 | Nuwakot | Balkumari | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 5
11689 | Nuwakot | Balkumari | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 5
11690 | Nuwakot | Balkumari | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 5
11691 | Nuwakot | Balkumari | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 5
11692 | Nuwakot | Balkumari | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 5
11693 | Nuwakot | Balkumari | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 5
11694 | Nuwakot | Balkumari | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 5
11695 | Nuwakot | Balkumari | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 5
11696 | Nuwakot | Balkumari | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 5
11697 | Nuwakot | Balkumari | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 5
11698 | Nuwakot | Balkumari | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 5
11699 | Nuwakot | Balkumari | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 5
11700 | Nuwakot | Balkumari | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 5
11701 | Nuwakot | Balkumari | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 5
11702 | Nuwakot | Balkumari | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 5
11703 | Nuwakot | Balkumari | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 5
11704 | Nuwakot | Balkumari | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 5
11705 | Nuwakot | Balkumari | All | OXFAM-GB | CARDSN | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 30 | 30 | 2017-09-07 | 2017-09-13 |  | Dupcheshwar | 5
11706 | Nuwakot | Balkumari | All | OXFAM-GB | CARDSN | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 30 | 30 | 2017-09-07 | 2017-09-13 |  | Dupcheshwar | 5
11707 | Nuwakot | Balkumari | All | OXFAM-GB | CARDSN | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 28 | 28 | 2018-01-01 | 2018-01-06 |  | Dupcheshwar | 5
11708 | Nuwakot | Barsunchet | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 1
11709 | Nuwakot | Barsunchet | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 1
11710 | Nuwakot | Barsunchet | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 1
11711 | Nuwakot | Barsunchet | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 1
11712 | Nuwakot | Barsunchet | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 1
11713 | Nuwakot | Barsunchet | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 1
11714 | Nuwakot | Barsunchet | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 1
11715 | Nuwakot | Barsunchet | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 1
11716 | Nuwakot | Barsunchet | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 1
11717 | Nuwakot | Barsunchet | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 1
11718 | Nuwakot | Barsunchet | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 1
11719 | Nuwakot | Barsunchet | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 1
11720 | Nuwakot | Barsunchet | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 1
11721 | Nuwakot | Barsunchet | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 1
11722 | Nuwakot | Barsunchet | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 1
11723 | Nuwakot | Barsunchet | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 1
11724 | Nuwakot | Barsunchet | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 1
11725 | Nuwakot | Barsunchet | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 1
11726 | Nuwakot | Belkot | 2 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 10
11727 | Nuwakot | Belkot | 3 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 10
11728 | Nuwakot | Belkot | 5 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 11
11729 | Nuwakot | Belkot | 6 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 11
11730 | Nuwakot | Belkot | 7 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 11
11731 | Nuwakot | Belkot | 8 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 4 | 4 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 11
11732 | Nuwakot | Belkot | 2 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2017-06-09 | 2017-06-15 |  | Belkotgadhi | 10
11733 | Nuwakot | Belkot | 3 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 4 | 4 | 2017-06-09 | 2017-06-15 |  | Belkotgadhi | 10
11734 | Nuwakot | Belkot | 4 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2017-06-09 | 2017-06-15 |  | Belkotgadhi | 1
11735 | Nuwakot | Belkot | 2 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 13 | 13 | 2017-06-24 | 2017-06-30 |  | Belkotgadhi | 10
11736 | Nuwakot | Belkot | 3 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2017-06-24 | 2017-06-30 |  | Belkotgadhi | 10
11737 | Nuwakot | Belkot | 4 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2017-06-24 | 2017-06-30 |  | Belkotgadhi | 1
11738 | Nuwakot | Betini | All | OXFAM-GB | KCDC | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 60 | 60 | 2016-12-21 | 2017-01-07 |  | Dupcheshwar | 4
11739 | Nuwakot | Betini | All | OXFAM-GB | KCDC | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 60 | 60 | 2016-12-21 | 2017-01-07 |  | Dupcheshwar | 4
11740 | Nuwakot | Betini | 1 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 75 | 2017-03-07 |  |  | Dupcheshwar | 4
11741 | Nuwakot | Betini | 2 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 51 | 2017-03-07 |  |  | Dupcheshwar | 4
11742 | Nuwakot | Betini | 3 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 83 | 2017-03-07 |  |  | Dupcheshwar | 4
11743 | Nuwakot | Betini | 4 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 53 | 2017-03-08 |  |  | Dupcheshwar | 4
11744 | Nuwakot | Betini | 5 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 64 | 2017-03-08 |  |  | Dupcheshwar | 4
11745 | Nuwakot | Betini | 6 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 43 | 2017-03-09 |  |  | Dupcheshwar | 4
11746 | Nuwakot | Betini | 7 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 53 | 2017-03-10 |  |  | Dupcheshwar | 4
11747 | Nuwakot | Betini | 8 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 106 | 2017-03-09 |  |  | Dupcheshwar | 4
11748 | Nuwakot | Betini | 9 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 46 | 2017-03-10 |  |  | Dupcheshwar | 4
11749 | Nuwakot | Betini | All | OXFAM-GB | KCDC | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 16 | 16 | 2017-02-26 | 2017-04-17 |  | Dupcheshwar | 4
11750 | Nuwakot | Betini | All | OXFAM-GB | KCDC | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 16 | 16 | 2017-02-26 | 2017-04-17 |  | Dupcheshwar | 4
11751 | Nuwakot | Betini | 1 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 8 | 2017-10-01 |  |  | Dupcheshwar | 4
11752 | Nuwakot | Betini | 2 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 8 | 2017-10-01 |  |  | Dupcheshwar | 4
11753 | Nuwakot | Betini | 3 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 9 | 2017-10-01 |  |  | Dupcheshwar | 4
11754 | Nuwakot | Betini | 4 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 8 | 2017-10-01 |  |  | Dupcheshwar | 4
11755 | Nuwakot | Betini | 5 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 8 | 2017-10-01 |  |  | Dupcheshwar | 4
11756 | Nuwakot | Betini | 6 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 9 | 2017-10-01 |  |  | Dupcheshwar | 4
11757 | Nuwakot | Betini | 7 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 8 | 2017-10-01 |  |  | Dupcheshwar | 4
11758 | Nuwakot | Betini | 8 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 9 | 2017-10-01 |  |  | Dupcheshwar | 4
11759 | Nuwakot | Betini | 9 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 8 | 2017-10-01 |  |  | Dupcheshwar | 4
11760 | Nuwakot | Betini | 1 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 4
11761 | Nuwakot | Betini | 2 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 4
11762 | Nuwakot | Betini | 3 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 4
11763 | Nuwakot | Betini | 4 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 4
11764 | Nuwakot | Betini | 5 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 4
11765 | Nuwakot | Betini | 6 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 4
11766 | Nuwakot | Betini | 7 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 4
11767 | Nuwakot | Betini | 8 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 4
11768 | Nuwakot | Betini | 9 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 4
11769 | Nuwakot | Betini | 4 | GON - PAF | CDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 12 | 12 | 2017-06-09 | 2017-06-15 |  | Dupcheshwar | 4
11770 | Nuwakot | Bhadratar | 1 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-25 | 2016-06-01 |  | Panchakanya | 5
11771 | Nuwakot | Bhadratar | 3 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-25 | 2016-06-01 |  | Panchakanya | 5
11772 | Nuwakot | Bhalche | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kispang | 1
11773 | Nuwakot | Bhalche | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kispang | 1
11774 | Nuwakot | Bhalche | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kispang | 1
11775 | Nuwakot | Bhalche | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kispang | 1
11776 | Nuwakot | Bhalche | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kispang | 1
11777 | Nuwakot | Bhalche | 6 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kispang | 1
11778 | Nuwakot | Bhalche | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kispang | 1
11779 | Nuwakot | Bhalche | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Kispang | 1
11780 | Nuwakot | Bhalche | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 16 | 16 | 2016-01-01 | 2018-12-31 |  | Kispang | 1
11781 | Nuwakot | Bhalche | 1 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 130 | 129 | 2016-05-20 | 2016-08-14 |  | Kispang | 1
11782 | Nuwakot | Bhalche | 2 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 174 | 171 | 2016-05-20 | 2016-08-14 |  | Kispang | 1
11783 | Nuwakot | Bhalche | 3 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 86 | 86 | 2016-05-20 | 2016-08-14 |  | Kispang | 1
11784 | Nuwakot | Bhalche | 4 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 126 | 124 | 2016-05-20 | 2016-08-14 |  | Kispang | 1
11785 | Nuwakot | Bhalche | 5 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 83 | 81 | 2016-05-20 | 2016-08-14 |  | Kispang | 1
11786 | Nuwakot | Bhalche | 6 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 82 | 77 | 2016-05-20 | 2016-08-14 |  | Kispang | 1
11787 | Nuwakot | Bhalche | 7 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 84 | 84 | 2016-05-20 | 2016-08-14 |  | Kispang | 1
11788 | Nuwakot | Bhalche | 8 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 117 | 117 | 2016-05-20 | 2016-08-14 |  | Kispang | 1
11789 | Nuwakot | Bhalche | 9 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 123 | 121 | 2016-05-20 | 2016-08-14 |  | Kispang | 1
11790 | Nuwakot | Bhalche | 1 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 130 | 34 | 2017-06-06 | 2017-12-06 |  | Kispang | 1
11791 | Nuwakot | Bhalche | 2 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 174 | 26 | 2017-06-06 | 2017-12-06 |  | Kispang | 1
11792 | Nuwakot | Bhalche | 3 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 86 | 28 | 2017-06-06 | 2017-12-06 |  | Kispang | 1
11793 | Nuwakot | Bhalche | 4 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 126 | 27 | 2017-06-06 | 2017-12-06 |  | Kispang | 1
11794 | Nuwakot | Bhalche | 5 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 83 | 45 | 2017-06-06 | 2017-12-06 |  | Kispang | 1
11795 | Nuwakot | Bhalche | 6 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 82 | 34 | 2017-06-06 | 2017-12-06 |  | Kispang | 1
11796 | Nuwakot | Bhalche | 7 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 84 | 38 | 2017-06-06 | 2017-12-06 |  | Kispang | 1
11797 | Nuwakot | Bhalche | 8 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 117 | 21 | 2017-06-06 | 2017-12-06 |  | Kispang | 1
11798 | Nuwakot | Bhalche | 9 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 123 | 39 | 2017-06-06 | 2017-12-06 |  | Kispang | 1
11799 | Nuwakot | Bhalche | 1 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 130 | 15 | 2016-09-01 | 2018-12-31 |  | Kispang | 1
11800 | Nuwakot | Bhalche | 2 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 174 | 22 | 2016-09-01 | 2018-12-31 |  | Kispang | 1
11801 | Nuwakot | Bhalche | 3 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 86 | 20 | 2016-09-01 | 2018-12-31 |  | Kispang | 1
11802 | Nuwakot | Bhalche | 4 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 126 | 20 | 2016-09-01 | 2018-12-31 |  | Kispang | 1
11803 | Nuwakot | Bhalche | 5 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 83 | 14 | 2016-09-01 | 2018-12-31 |  | Kispang | 1
11804 | Nuwakot | Bhalche | 6 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 82 | 14 | 2016-09-01 | 2018-12-31 |  | Kispang | 1
11805 | Nuwakot | Bhalche | 7 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 84 | 37 | 2016-09-01 | 2018-12-31 |  | Kispang | 1
11806 | Nuwakot | Bhalche | 8 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 117 | 10 | 2016-09-01 | 2018-12-31 |  | Kispang | 1
11807 | Nuwakot | Bhalche | 9 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 123 | 15 | 2016-09-01 | 2018-12-31 |  | Kispang | 1
11808 | Nuwakot | Bhalche | 1 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 130 | 130 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kispang | 1
11809 | Nuwakot | Bhalche | 2 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 174 | 174 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kispang | 1
11810 | Nuwakot | Bhalche | 3 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 86 | 86 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kispang | 1
11811 | Nuwakot | Bhalche | 4 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 126 | 126 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kispang | 1
11812 | Nuwakot | Bhalche | 5 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 83 | 83 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kispang | 1
11813 | Nuwakot | Bhalche | 6 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 82 | 82 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kispang | 1
11814 | Nuwakot | Bhalche | 7 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 84 | 84 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kispang | 1
11815 | Nuwakot | Bhalche | 8 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 117 | 117 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kispang | 1
11816 | Nuwakot | Bhalche | 9 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 123 | 123 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kispang | 1
11817 | Nuwakot | Bhalche | 3 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 7 | 7 | 2017-07-10 | 2017-07-17 |  | Kispang | 1
11818 | Nuwakot | Bidur N.P. | 5 | ACF | EA | ECHO | Technical Assistance | Demonstration Construction | House | Stone machinary, iron pillars, use of hood and plywod 2 storeys house | # of constructions | Yes | Completed | 1 | 1 | 2016-04-01 | 2016-06-07 |  | Bidur | 5
11819 | Nuwakot | Bidur N.P. | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 1
11820 | Nuwakot | Bidur N.P. | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 2
11821 | Nuwakot | Bidur N.P. | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 2
11822 | Nuwakot | Bidur N.P. | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 4
11823 | Nuwakot | Bidur N.P. | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 5
11824 | Nuwakot | Bidur N.P. | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 6
11825 | Nuwakot | Bidur N.P. | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 5
11826 | Nuwakot | Bidur N.P. | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 8
11827 | Nuwakot | Bidur N.P. | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 9
11828 | Nuwakot | Bidur N.P. | 10 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 1
11829 | Nuwakot | Bidur N.P. | 11 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 1
11830 | Nuwakot | Bidur N.P. | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 1
11831 | Nuwakot | Bidur N.P. | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 2
11832 | Nuwakot | Bidur N.P. | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 2
11833 | Nuwakot | Bidur N.P. | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 4
11834 | Nuwakot | Bidur N.P. | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 5
11835 | Nuwakot | Bidur N.P. | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 6
11836 | Nuwakot | Bidur N.P. | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 5
11837 | Nuwakot | Bidur N.P. | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 8
11838 | Nuwakot | Bidur N.P. | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 9
11839 | Nuwakot | Bidur N.P. | 10 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 1
11840 | Nuwakot | Bidur N.P. | 11 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 1
11841 | Nuwakot | Bidur N.P. | 6 | ICMOD | ICMOD | IDRC | Training | Other trainings | Other trainings (specify in Activity Detail) | Training for the construction of Participatory 3D Model for 11 beneficiaries | # of trainees | Yes | Completed | 6 | 6 | 2016-06-12 | 2016-06-18 |  | Bidur | 6
11842 | Nuwakot | Bidur N.P. | 6 | ICMOD | ICMOD | IDRC | Training | Other trainings | Other trainings (specify in Activity Detail) | Cement Soil Stabilized Block Production training for 22 beneficiaries | # of trainees | Yes | Completed | 11 | 11 | 2016-12-11 | 2017-01-05 |  | Bidur | 6
11843 | Nuwakot | Bidur N.P. | 6 | ICMOD | ICMOD | IDRC | Technical Assistance | Door-to-door technical assistance | Continuous | Door to door technical assistance including engineer and social mobilizer for beneficiaries using CSSB house technology | # of households | Yes | Ongoing | 75 | 56 | 2017-05-04 |  |  | Bidur | 6
11844 | Nuwakot | Bidur N.P. | 6 | ICMOD | ICMOD | IDRC | Technical Assistance | Household toilet construction | Household toilet construction | Technial Assistance in household toilet construction with the provision of door-door technical Asistance | # of households | Yes | Ongoing | 32 | 0 | 2017-10-29 |  |  | Bidur | 6
11845 | Nuwakot | Bidur N.P. | 3 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2017-06-24 | 2017-06-30 |  | Bidur | 2
11846 | Nuwakot | Bidur N.P. | All | SCI | CDC | SCI | Technical Assistance | Communication and Outreach | PSA Radio broadcasting | Broadcasting through 3 FM twice a day | # of episodes | Yes | Completed | 6 | 6 | 2016-09-01 | 2017-03-31 |  | Bidur | 1
11847 | Nuwakot | Bidur N.P. | 2 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 91 | 91 | 2016-04-01 | 2016-09-30 |  | Bidur | 2
11848 | Nuwakot | Bidur N.P. | 3 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 191 | 191 | 2016-04-01 | 2016-09-30 |  | Bidur | 2
11849 | Nuwakot | Bidur N.P. | 9 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 149 | 149 | 2016-04-01 | 2016-09-30 |  | Bidur | 9
11850 | Nuwakot | Bidur N.P. | 2 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 318 | 318 | 2016-02-10 | 2016-07-01 |  | Bidur | 2
11851 | Nuwakot | Bidur N.P. | 3 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 369 | 369 | 2016-02-10 | 2016-07-01 |  | Bidur | 2
11852 | Nuwakot | Bidur N.P. | 9 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 806 | 806 | 2016-02-10 | 2016-07-01 |  | Bidur | 9
11853 | Nuwakot | Budhasing | 1 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 62 | 2017-02-08 | 2017-02-08 |  | Tarakeshwar | 4
11854 | Nuwakot | Budhasing | 2 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 48 | 2017-03-13 | 2017-03-13 |  | Tarakeshwar | 4
11855 | Nuwakot | Budhasing | 3 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 113 | 2017-01-31 | 2017-02-03 |  | Tarakeshwar | 4
11856 | Nuwakot | Budhasing | 4 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 36 | 2017-02-01 | 2017-02-01 |  | Tarakeshwar | 4
11857 | Nuwakot | Budhasing | 5 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 77 | 2017-02-01 | 2017-02-02 |  | Tarakeshwar | 4
11858 | Nuwakot | Budhasing | 6 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 40 | 2017-02-01 | 2017-02-01 |  | Tarakeshwar | 4
11859 | Nuwakot | Budhasing | 7 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 99 | 2017-02-01 | 2017-02-02 |  | Tarakeshwar | 4
11860 | Nuwakot | Budhasing | 8 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 55 | 2017-02-02 | 2017-02-02 |  | Tarakeshwar | 4
11861 | Nuwakot | Budhasing | 9 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 27 | 2017-02-02 | 2017-02-02 |  | Tarakeshwar | 1
11862 | Nuwakot | Budhasing | All | OXFAM-GB | SSS | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 50 | 100 | 2016-12-16 | 2017-02-20 |  | Tarakeshwar | 4
11863 | Nuwakot | Budhasing | All | OXFAM-GB | SSS | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 50 | 100 | 2016-12-16 | 2017-02-20 |  | Tarakeshwar | 4
11864 | Nuwakot | Bungtang | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 2
11865 | Nuwakot | Bungtang | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 2
11866 | Nuwakot | Bungtang | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 2
11867 | Nuwakot | Bungtang | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 2
11868 | Nuwakot | Bungtang | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 2
11869 | Nuwakot | Bungtang | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 2
11870 | Nuwakot | Bungtang | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 2
11871 | Nuwakot | Bungtang | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 2
11872 | Nuwakot | Bungtang | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 2
11873 | Nuwakot | Bungtang | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 2
11874 | Nuwakot | Bungtang | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 2
11875 | Nuwakot | Bungtang | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 2
11876 | Nuwakot | Bungtang | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 2
11877 | Nuwakot | Bungtang | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 2
11878 | Nuwakot | Bungtang | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 2
11879 | Nuwakot | Bungtang | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 2
11880 | Nuwakot | Bungtang | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 2
11881 | Nuwakot | Bungtang | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 2
11882 | Nuwakot | Charghare | 1 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 |  | Bidur | 6
11883 | Nuwakot | Charghare | 4 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 |  | Bidur | 12
11884 | Nuwakot | Charghare | 5 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-17 | 2016-06-23 |  | Bidur | 12
11885 | Nuwakot | Charghare | 6 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 |  | Bidur | 12
11886 | Nuwakot | Charghare | 7 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 |  | Bidur | 12
11887 | Nuwakot | Charghare | 8 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 4 | 4 | 2016-06-17 | 2016-06-23 |  | Bidur | 12
11888 | Nuwakot | Charghare | 9 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-17 | 2016-06-23 |  | Bidur | 12
11889 | Nuwakot | Charghare | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 6
11890 | Nuwakot | Charghare | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 6
11891 | Nuwakot | Charghare | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 12
11892 | Nuwakot | Charghare | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 12
11893 | Nuwakot | Charghare | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 12
11894 | Nuwakot | Charghare | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 12
11895 | Nuwakot | Charghare | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 12
11896 | Nuwakot | Charghare | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 12
11897 | Nuwakot | Charghare | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 12
11898 | Nuwakot | Charghare | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 6
11899 | Nuwakot | Charghare | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 6
11900 | Nuwakot | Charghare | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 12
11901 | Nuwakot | Charghare | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 12
11902 | Nuwakot | Charghare | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 12
11903 | Nuwakot | Charghare | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 12
11904 | Nuwakot | Charghare | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 12
11905 | Nuwakot | Charghare | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 12
11906 | Nuwakot | Charghare | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 12
11907 | Nuwakot | Charghare | 6 | ICMOD | ICMOD | IDRC | Training | Other trainings | Other trainings (specify in Activity Detail) | Training for the construction of Participatory 3D Model for 11 beneficiaries | # of trainees | Yes | Completed | 6 | 6 | 2016-06-12 | 2016-06-18 |  | Bidur | 12
11908 | Nuwakot | Charghare | 6 | ICMOD | ICMOD | IDRC | Training | Other trainings | Other trainings (specify in Activity Detail) | Cement Soil Stabilized Block Production training for 22 beneficiaries | # of trainees | Yes | Completed | 11 | 11 | 2016-12-11 | 2017-01-05 |  | Bidur | 12
11909 | Nuwakot | Charghare | 6 | ICMOD | ICMOD | IDRC | Technical Assistance | Door-to-door technical assistance | Continuous | Door to door technical assistance including engineer and social mobilizer for beneficiaries using CSSB house technology | # of households | Yes | Ongoing | 19 | 18 | 2017-05-04 |  |  | Bidur | 12
11910 | Nuwakot | Charghare | 6 | ICMOD | ICMOD | IDRC | Technical Assistance | Household toilet construction | Household toilet construction | Technial Assistance in household toilet construction with the provision of door-door technical Asistance | # of households | Yes | Ongoing | 12 | 2 | 2017-10-29 |  |  | Bidur | 12
11911 | Nuwakot | Chaughada | 4 | MI | RSDC | ADH | Technical Assistance | Community reconstruction orientation | 4-5 sessions | orinetation to the participants | # of participants | Yes | Ongoing | 255 | 300 | 2016-12-01 |  |  | Panchakanya | 1
11912 | Nuwakot | Chaughada | 4 | MI | RSDC | ADH | Technical Assistance | Door-to-door technical assistance | Continuous | Door to door visit and provide technical support | # of households | Yes | Ongoing | 255 | 202 | 2016-12-01 |  |  | Panchakanya | 1
11913 | Nuwakot | Chaughada | 4 | MI | RSDC | ADH | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Formation of committees and sub-committees | # of committees | Yes | Completed | 7 | 7 | 2016-12-01 | 2017-03-31 |  | Panchakanya | 1
11914 | Nuwakot | Chaughada | 4 | MI | RSDC | ADH | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Household level orientation and technical assistance | # of households | Yes | Ongoing | 255 | 200 | 2016-12-01 |  |  | Panchakanya | 1
11915 | Nuwakot | Chaughada | 4 | MI | RSDC | ADH | Technical Assistance | Community orientation on toilet construction | 2-3 sessions | Group facilitation for toilet construction | # of participants | Yes | Ongoing | 255 | 300 | 2016-12-01 |  |  | Panchakanya | 1
11916 | Nuwakot | Chaughada | 4 | MI | RSDC | ADH | Technical Assistance | Household orientation on toilet construction | 2-3 sessions | Household visit and orientation | # of households | Yes | Ongoing | 255 | 200 | 2016-12-01 |  |  | Panchakanya | 1
11917 | Nuwakot | Chaughada | 4 | MI | RSDC | ADH | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | Group facilitation and household visit | # of households | Yes | Ongoing | 255 | 60 | 2016-12-01 |  |  | Panchakanya | 1
11918 | Nuwakot | Chaughada | 4 | MI | RSDC | ADH | Technical Assistance | Household drinking water schemes | Household drinking water schemes | Group facilitation and household visit to see possibilities | # of households | Yes | Ongoing | 255 | 60 | 2016-12-01 |  |  | Panchakanya | 1
11919 | Nuwakot | Chaughada | 4 | MI | RSDC | ADH | Training | Short training | Masons (7 days DUDBC, rural or urban) | Local masons and local individual train for skilled masons in earthquake resilients house re-construction | # of trainees | Yes | Completed | 25 | 29 | 2017-04-04 | 2017-04-10 |  | Panchakanya | 1
11920 | Nuwakot | Chaughada | 4 | MI | RSDC | ADH | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Facilate and support for GoN | # of households | Yes | Ongoing | 255 | 195 | 2016-12-01 |  |  | Panchakanya | 1
11921 | Nuwakot | Chaughada | 4 | MI | RSDC | ADH | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Facilate and support for GoN | # of households | Yes | Ongoing | 255 | 127 | 2016-12-01 |  |  | Panchakanya | 1
11922 | Nuwakot | Chaughada | 4 | MI | RSDC | ADH | Financial/Material/Labour Assistance | Material support on household WASH | Household toilet/hygiene kits | Toilet repair/rehabilitation and also promote hygiene | # of households | Yes | Ongoing | 255 | 100 | 2016-12-01 |  |  | Panchakanya | 1
11923 | Nuwakot | Chaughada | 4 | MI | RSDC | ADH | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme | Community level water supply schemes | # of households | Yes | Ongoing | 255 | 60 | 2016-12-01 |  |  | Panchakanya | 1
11924 | Nuwakot | Chaughada | 4 | MI | RSDC | ADH | Financial/Material/Labour Assistance | Material support on household WASH | HH water supply repair/rehabilitation | Community level water supply schemes distribution to households | # of households | Yes | Ongoing | 255 | 60 | 2016-12-01 |  |  | Panchakanya | 1
11925 | Nuwakot | Chauthe | 1 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-06-07 |  | Kakani | 3
11926 | Nuwakot | Chauthe | 1 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-06-07 |  | Kakani | 3
11927 | Nuwakot | Chauthe | 2 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-06-07 |  | Kakani | 3
11928 | Nuwakot | Chauthe | 2 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-06-07 |  | Kakani | 3
11929 | Nuwakot | Chauthe | 3 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 5 | 5 | 2016-05-16 | 2016-06-07 |  | Kakani | 3
11930 | Nuwakot | Chauthe | 3 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 5 | 5 | 2016-05-16 | 2016-06-07 |  | Kakani | 3
11931 | Nuwakot | Chauthe | 4 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 4 | 4 | 2016-05-16 | 2016-06-07 |  | Kakani | 3
11932 | Nuwakot | Chauthe | 4 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 4 | 4 | 2016-05-16 | 2016-06-07 |  | Kakani | 3
11933 | Nuwakot | Chauthe | 6 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 2 | 2 | 2016-05-16 | 2016-06-07 |  | Kakani | 3
11934 | Nuwakot | Chauthe | 6 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-05-16 | 2016-06-07 |  | Kakani | 3
11935 | Nuwakot | Chauthe | 7 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 7 | 7 | 2016-05-16 | 2016-06-07 |  | Kakani | 3
11936 | Nuwakot | Chauthe | 7 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 7 | 7 | 2016-05-16 | 2016-06-07 |  | Kakani | 3
11937 | Nuwakot | Chauthe | 8 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 5 | 5 | 2016-05-16 | 2016-06-07 |  | Kakani | 3
11938 | Nuwakot | Chauthe | 8 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 5 | 5 | 2016-05-16 | 2016-06-07 |  | Kakani | 3
11939 | Nuwakot | Chauthe | 9 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-06-07 |  | Kakani | 3
11940 | Nuwakot | Chauthe | 9 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-06-07 |  | Kakani | 3
11941 | Nuwakot | Chhap | 6 | GON - PAF | CARDSN | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 25 | 25 | 2017-11-02 | 2017-11-11 |  | Shivapuri | 2
11942 | Nuwakot | Dangsing | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 1
11943 | Nuwakot | Dangsing | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 1
11944 | Nuwakot | Dangsing | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 1
11945 | Nuwakot | Dangsing | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 1
11946 | Nuwakot | Dangsing | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 1
11947 | Nuwakot | Dangsing | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 1
11948 | Nuwakot | Dangsing | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 1
11949 | Nuwakot | Dangsing | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 1
11950 | Nuwakot | Dangsing | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 1
11951 | Nuwakot | Dangsing | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 1
11952 | Nuwakot | Dangsing | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 1
11953 | Nuwakot | Dangsing | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 1
11954 | Nuwakot | Dangsing | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 1
11955 | Nuwakot | Dangsing | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 1
11956 | Nuwakot | Dangsing | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 1
11957 | Nuwakot | Dangsing | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 1
11958 | Nuwakot | Dangsing | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 1
11959 | Nuwakot | Dangsing | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 1
11960 | Nuwakot | Dangsing | 1 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 4 | 4 | 2016-05-30 | 2016-06-06 |  | Tarakeshwar | 1
11961 | Nuwakot | Dangsing | 1 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 1 | 1 | 2016-09-27 | 2016-10-03 |  | Tarakeshwar | 1
11962 | Nuwakot | Dangsing | 1 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 4 | 4 | 2016-05-30 | 2016-06-06 |  | Tarakeshwar | 1
11963 | Nuwakot | Dangsing | 1 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 5 | 4 | 2016-09-27 | 2016-10-03 |  | Tarakeshwar | 1
11964 | Nuwakot | Dangsing | 1 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 50 days OJT training on the basis of CTVT curriculum | # of trainees | Yes | Completed | 8 | 8 | 2017-01-05 | 2017-11-30 |  | Tarakeshwar | 1
11965 | Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 50000 NPR per HH | # of households | Yes | Completed | 94 | 94 | 2016-10-06 | 2016-10-06 |  | Tarakeshwar | 1
11966 | Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 NPR per HH | # of households | Yes | Completed | 28 | 28 | 2016-01-26 | 2016-01-26 |  | Tarakeshwar | 1
11967 | Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 6 | 6 | 2016-05-30 | 2016-06-06 |  | Tarakeshwar | 1
11968 | Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 19 | 19 | 2016-09-27 | 2016-10-03 |  | Tarakeshwar | 1
11969 | Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1 hour per session | # of participants | Yes | Completed | 94 | 93 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 1
11970 | Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Technical Assistance | Demonstration Construction | House | Composite structure, Scaled down demo house in section | # of constructions | Yes | Completed | 1 | 1 | 2016-09-27 | 2016-10-03 |  | Tarakeshwar | 1
11971 | Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Sub Engineer and Social mobilizer | # of households | Yes | Completed | 94 | 93 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 1
11972 | Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Technical Assistance | Household reconstruction orientation | 1 session | 1 hour per session | # of households | Yes | Completed | 94 | 93 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 1
11973 | Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | 94 members in 3 committee | # of committees | Yes | Completed | 94 | 94 | 2016-10-06 | 2016-10-06 |  | Tarakeshwar | 1
11974 | Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 6 | 6 | 2016-05-30 | 2016-06-06 |  | Tarakeshwar | 1
11975 | Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 7 | 19 | 2016-09-27 | 2016-10-03 |  | Tarakeshwar | 1
11976 | Nuwakot | Dangsing | 2 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days OJT training on the basis of CTVT curriculum | # of trainees | Yes | Completed | 8 | 8 | 2017-01-05 | 2017-11-30 |  | Tarakeshwar | 1
11977 | Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 50000 NPR per HH | # of households | Yes | Completed | 16 | 16 | 2016-10-06 | 2016-10-06 |  | Tarakeshwar | 1
11978 | Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 NPR per HH | # of households | Yes | Completed | 8 | 8 | 2016-01-26 | 2016-01-26 |  | Tarakeshwar | 1
11979 | Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 2 | 2 | 2016-05-30 | 2016-06-06 |  | Tarakeshwar | 1
11980 | Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 2 | 2 | 2016-09-27 | 2016-10-03 |  | Tarakeshwar | 1
11981 | Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1 hour per session | # of participants | Yes | Completed | 94 | 93 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 1
11982 | Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Sub Engineer and Social mobilizer | # of households | Yes | Completed | 94 | 93 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 1
11983 | Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Technical Assistance | Household reconstruction orientation | 1 session | 1 hour per session | # of households | Yes | Completed | 94 | 93 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 1
11984 | Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | 16 members in 1 committee | # of committees | Yes | Completed | 16 | 16 | 2016-10-06 | 2016-10-06 |  | Tarakeshwar | 1
11985 | Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-05-30 | 2016-06-06 |  | Tarakeshwar | 1
11986 | Nuwakot | Dangsing | 3 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-09-27 | 2016-10-03 |  | Tarakeshwar | 1
11987 | Nuwakot | Dangsing | 4 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 13 | 13 | 2016-05-30 | 2016-06-06 |  | Tarakeshwar | 1
11988 | Nuwakot | Dangsing | 4 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 4 | 4 | 2016-09-27 | 2016-10-03 |  | Tarakeshwar | 1
11989 | Nuwakot | Dangsing | 4 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 13 | 13 | 2016-05-30 | 2016-06-06 |  | Tarakeshwar | 1
11990 | Nuwakot | Dangsing | 4 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 4 | 4 | 2016-09-27 | 2016-10-03 |  | Tarakeshwar | 1
11991 | Nuwakot | Dangsing | 5 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 1 | 1 | 2016-05-30 | 2016-06-06 |  | Tarakeshwar | 1
11992 | Nuwakot | Dangsing | 5 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 1 | 1 | 2016-09-27 | 2016-10-03 |  | Tarakeshwar | 1
11993 | Nuwakot | Dangsing | 5 | SCI | CDC | SCI | Technical Assistance | Demonstration Construction | House | Stone masonry in mud mortar, Scaled down demo house in section | # of constructions | Yes | Completed | 1 | 1 | 2016-05-30 | 2016-06-06 |  | Tarakeshwar | 1
11994 | Nuwakot | Dangsing | 5 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-05-30 | 2016-06-06 |  | Tarakeshwar | 1
11995 | Nuwakot | Dangsing | 5 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-09-27 | 2016-10-03 |  | Tarakeshwar | 1
11996 | Nuwakot | Dangsing | 6 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 1 | 1 | 2016-05-30 | 2016-06-06 |  | Tarakeshwar | 1
11997 | Nuwakot | Dangsing | 6 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-05-30 | 2016-06-06 |  | Tarakeshwar | 1
11998 | Nuwakot | Dangsing | 7 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 1 | 1 | 2016-05-30 | 2016-06-06 |  | Tarakeshwar | 1
11999 | Nuwakot | Dangsing | 7 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 3 | 3 | 2016-09-27 | 2016-10-03 |  | Tarakeshwar | 1
12000 | Nuwakot | Dangsing | 7 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-05-30 | 2016-06-06 |  | Tarakeshwar | 1
12001 | Nuwakot | Dangsing | 7 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 3 | 3 | 2016-09-27 | 2016-10-03 |  | Tarakeshwar | 1
12002 | Nuwakot | Dangsing | 7 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days OJT training on the basis of CTVT curriculum | # of trainees | Yes | Completed | 6 | 6 | 2017-01-05 | 2017-11-30 |  | Tarakeshwar | 1
12003 | Nuwakot | Dangsing | 9 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days OJT training on the basis of CTVT curriculum | # of trainees | Yes | Completed | 6 | 6 | 2017-01-05 | 2017-11-30 |  | Tarakeshwar | 1
12004 | Nuwakot | Deurali | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 3
12005 | Nuwakot | Deurali | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 3
12006 | Nuwakot | Deurali | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 3
12007 | Nuwakot | Deurali | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 3
12008 | Nuwakot | Deurali | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 3
12009 | Nuwakot | Deurali | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 3
12010 | Nuwakot | Deurali | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 3
12011 | Nuwakot | Deurali | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 3
12012 | Nuwakot | Deurali | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 3
12013 | Nuwakot | Deurali | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 3
12014 | Nuwakot | Deurali | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 3
12015 | Nuwakot | Deurali | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 3
12016 | Nuwakot | Deurali | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 3
12017 | Nuwakot | Deurali | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 3
12018 | Nuwakot | Deurali | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 3
12019 | Nuwakot | Deurali | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 3
12020 | Nuwakot | Deurali | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 3
12021 | Nuwakot | Deurali | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 3
12022 | Nuwakot | Gaunkharka | 1 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 38 | 2016-09-14 |  |  | Dupcheshwar | 2
12023 | Nuwakot | Gaunkharka | 2 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 72 | 2016-09-15 |  |  | Dupcheshwar | 2
12024 | Nuwakot | Gaunkharka | 3 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 60 | 2016-09-16 |  |  | Dupcheshwar | 2
12025 | Nuwakot | Gaunkharka | 4 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 78 | 2016-09-17 |  |  | Dupcheshwar | 2
12026 | Nuwakot | Gaunkharka | 5 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 50 | 2016-09-18 |  |  | Dupcheshwar | 2
12027 | Nuwakot | Gaunkharka | 6 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 80 | 2016-11-11 |  |  | Dupcheshwar | 2
12028 | Nuwakot | Gaunkharka | 7 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 69 | 2016-11-12 |  |  | Dupcheshwar | 2
12029 | Nuwakot | Gaunkharka | 8 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 79 | 2016-11-13 |  |  | Dupcheshwar | 2
12030 | Nuwakot | Gaunkharka | 9 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 82 | 2016-11-14 |  |  | Dupcheshwar | 2
12031 | Nuwakot | Gaunkharka | All | OXFAM-GB | CARDSN | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 50 | 62 | 2016-11-22 | 2016-12-01 |  | Dupcheshwar | 2
12032 | Nuwakot | Gaunkharka | All | OXFAM-GB | CARDSN | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 50 | 62 | 2016-11-22 | 2016-12-01 |  | Dupcheshwar | 2
12033 | Nuwakot | Gaunkharka | All | OXFAM-GB | CARDSN | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 16 | 16 | 2017-02-26 | 2017-04-17 |  | Dupcheshwar | 2
12034 | Nuwakot | Gaunkharka | All | OXFAM-GB | CARDSN | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 16 | 16 | 2017-02-26 | 2017-04-17 |  | Dupcheshwar | 2
12035 | Nuwakot | Gaunkharka | 1 | OXFAM-GB | CARDSN | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12036 | Nuwakot | Gaunkharka | 2 | OXFAM-GB | CARDSN | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12037 | Nuwakot | Gaunkharka | 4 | OXFAM-GB | CARDSN | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12038 | Nuwakot | Gaunkharka | 5 | OXFAM-GB | CARDSN | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12039 | Nuwakot | Gaunkharka | 6 | OXFAM-GB | CARDSN | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12040 | Nuwakot | Gaunkharka | 7 | OXFAM-GB | CARDSN | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12041 | Nuwakot | Gaunkharka | 8 | OXFAM-GB | CARDSN | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12042 | Nuwakot | Gaunkharka | 9 | OXFAM-GB | CARDSN | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12043 | Nuwakot | Gaunkharka | 1 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Demonstration Construction | House | Individual House construction from 50 days mason OJT as per CTEVT course | # of constructions | Yes | Completed | 1 | 1 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12044 | Nuwakot | Gaunkharka | 2 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Demonstration Construction | House | Individual House construction from 50 days mason OJT as per CTEVT course | # of constructions | Yes | Completed | 1 | 1 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12045 | Nuwakot | Gaunkharka | 4 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Demonstration Construction | House | Individual House construction from 50 days mason OJT as per CTEVT course | # of constructions | Yes | Completed | 1 | 1 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12046 | Nuwakot | Gaunkharka | 5 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Demonstration Construction | House | Individual House construction from 50 days mason OJT as per CTEVT course | # of constructions | Yes | Completed | 1 | 1 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12047 | Nuwakot | Gaunkharka | 6 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Demonstration Construction | House | Individual House construction from 50 days mason OJT as per CTEVT course | # of constructions | Yes | Completed | 1 | 1 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12048 | Nuwakot | Gaunkharka | 7 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Demonstration Construction | House | Individual House construction from 50 days mason OJT as per CTEVT course | # of constructions | Yes | Completed | 1 | 1 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12049 | Nuwakot | Gaunkharka | 8 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Demonstration Construction | House | Individual House construction from 50 days mason OJT as per CTEVT course | # of constructions | Yes | Completed | 1 | 1 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12050 | Nuwakot | Gaunkharka | 9 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Demonstration Construction | House | Individual House construction from 50 days mason OJT as per CTEVT course | # of constructions | Yes | Completed | 1 | 1 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12051 | Nuwakot | Gaunkharka | 1 | OXFAM-GB | CARDSN | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12052 | Nuwakot | Gaunkharka | 2 | OXFAM-GB | CARDSN | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12053 | Nuwakot | Gaunkharka | 4 | OXFAM-GB | CARDSN | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12054 | Nuwakot | Gaunkharka | 5 | OXFAM-GB | CARDSN | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12055 | Nuwakot | Gaunkharka | 6 | OXFAM-GB | CARDSN | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12056 | Nuwakot | Gaunkharka | 7 | OXFAM-GB | CARDSN | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12057 | Nuwakot | Gaunkharka | 7 | OXFAM-GB | CARDSN | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12058 | Nuwakot | Gaunkharka | 9 | OXFAM-GB | CARDSN | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-25 |  | Dupcheshwar | 2
12059 | Nuwakot | Gaunkharka | 1 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 12 | 2017-10-01 |  |  | Dupcheshwar | 2
12060 | Nuwakot | Gaunkharka | 2 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 12 | 2017-10-01 |  |  | Dupcheshwar | 2
12061 | Nuwakot | Gaunkharka | 3 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 12 | 2017-10-01 |  |  | Dupcheshwar | 2
12062 | Nuwakot | Gaunkharka | 4 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 12 | 2017-10-01 |  |  | Dupcheshwar | 2
12063 | Nuwakot | Gaunkharka | 5 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 11 | 2017-10-01 |  |  | Dupcheshwar | 2
12064 | Nuwakot | Gaunkharka | 6 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 12 | 2017-10-01 |  |  | Dupcheshwar | 2
12065 | Nuwakot | Gaunkharka | 7 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 12 | 2017-10-01 |  |  | Dupcheshwar | 2
12066 | Nuwakot | Gaunkharka | 8 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 12 | 2017-10-01 |  |  | Dupcheshwar | 2
12067 | Nuwakot | Gaunkharka | 9 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 12 | 2017-10-01 |  |  | Dupcheshwar | 2
12068 | Nuwakot | Gaunkharka | 1 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 2
12069 | Nuwakot | Gaunkharka | 2 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 2
12070 | Nuwakot | Gaunkharka | 3 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 2
12071 | Nuwakot | Gaunkharka | 4 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 2
12072 | Nuwakot | Gaunkharka | 5 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 2
12073 | Nuwakot | Gaunkharka | 6 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 2
12074 | Nuwakot | Gaunkharka | 7 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 2
12075 | Nuwakot | Gaunkharka | 8 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 2
12076 | Nuwakot | Gaunkharka | 9 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 2
12077 | Nuwakot | Gerkhu | 1 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 |  | Bidur | 11
12078 | Nuwakot | Gerkhu | 3 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2016-06-17 | 2016-06-23 |  | Bidur | 10
12079 | Nuwakot | Gerkhu | 4 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 |  | Bidur | 10
12080 | Nuwakot | Gerkhu | 9 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 |  | Bidur | 10
12081 | Nuwakot | Ghyangphedi | 3 | GON - PAF | CDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 25 | 25 | 2018-05-26 | 2017-06-01 |  | Dupcheshwar | 1
12082 | Nuwakot | Gorsyang | 4 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-25 | 2016-06-01 |  | Tarakeshwar | 5
12083 | Nuwakot | Gorsyang | 7 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-25 | 2016-06-01 |  | Tarakeshwar | 5
12084 | Nuwakot | Gorsyang | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 1
12085 | Nuwakot | Gorsyang | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 5
12086 | Nuwakot | Gorsyang | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 5
12087 | Nuwakot | Gorsyang | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 5
12088 | Nuwakot | Gorsyang | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 5
12089 | Nuwakot | Gorsyang | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 5
12090 | Nuwakot | Gorsyang | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 5
12091 | Nuwakot | Gorsyang | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 5
12092 | Nuwakot | Gorsyang | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 6
12093 | Nuwakot | Gorsyang | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 1
12094 | Nuwakot | Gorsyang | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 5
12095 | Nuwakot | Gorsyang | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 5
12096 | Nuwakot | Gorsyang | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 5
12097 | Nuwakot | Gorsyang | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 5
12098 | Nuwakot | Gorsyang | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 5
12099 | Nuwakot | Gorsyang | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 5
12100 | Nuwakot | Gorsyang | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 5
12101 | Nuwakot | Gorsyang | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 6
12102 | Nuwakot | Gorsyang | 1 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days OJT training on the basis of CTVT curriculum | # of trainees | Yes | Completed | 6 | 6 | 2017-01-05 | 2017-11-30 |  | Tarakeshwar | 1
12103 | Nuwakot | Gorsyang | 2 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 2 | 2 | 2016-05-30 | 2016-06-05 |  | Tarakeshwar | 5
12104 | Nuwakot | Gorsyang | 2 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-05-30 | 2016-06-05 |  | Tarakeshwar | 5
12105 | Nuwakot | Gorsyang | 3 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 7 | 7 | 2016-05-30 | 2016-06-05 |  | Tarakeshwar | 5
12106 | Nuwakot | Gorsyang | 3 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 7 | 7 | 2016-05-30 | 2016-06-05 |  | Tarakeshwar | 5
12107 | Nuwakot | Gorsyang | 3 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days OJT training on the basis of CTVT curriculum | # of trainees | Yes | Completed | 5 | 5 | 2017-01-05 | 2017-11-30 |  | Tarakeshwar | 5
12108 | Nuwakot | Gorsyang | 4 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 2 | 2 | 2016-05-30 | 2016-06-05 |  | Tarakeshwar | 5
12109 | Nuwakot | Gorsyang | 4 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-05-30 | 2016-06-05 |  | Tarakeshwar | 5
12110 | Nuwakot | Gorsyang | 4 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days OJT training on the basis of CTVT curriculum | # of trainees | Yes | Completed | 9 | 9 | 2017-01-05 | 2017-11-30 |  | Tarakeshwar | 5
12111 | Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 500000 NPR per HH | # of households | Yes | Completed | 22 | 22 | 2016-08-24 | 2016-08-24 |  | Tarakeshwar | 5
12112 | Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 NPR per HH | # of households | Yes | Completed | 1 | 1 | 2016-01-30 | 2016-01-30 |  | Tarakeshwar | 5
12113 | Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 3 | 3 | 2016-05-30 | 2016-06-05 |  | Tarakeshwar | 5
12114 | Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 2 | 2 | 2016-09-20 | 2016-09-26 |  | Tarakeshwar | 5
12115 | Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1 hour per session | # of participants | Yes | Completed | 22 | 22 | 2016-08-24 | 2017-11-30 |  | Tarakeshwar | 5
12116 | Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Sub Engineer and Social mobilizer | # of households | Yes | Completed | 22 | 22 | 2016-08-24 | 2017-11-30 |  | Tarakeshwar | 5
12117 | Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Technical Assistance | Household reconstruction orientation | 1 session | 1 hour per session | # of households | Yes | Completed | 22 | 22 | 2016-08-24 | 2017-11-30 |  | Tarakeshwar | 5
12118 | Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | 22 members in 1 committee | # of committees | Yes | Completed | 1 | 1 | 2016-08-24 | 2016-08-24 |  | Tarakeshwar | 5
12119 | Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-09-20 | 2016-09-26 |  | Tarakeshwar | 5
12120 | Nuwakot | Gorsyang | 5 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 3 | 3 | 2016-05-30 | 2016-06-05 |  | Tarakeshwar | 5
12121 | Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 500000 NPR per HH | # of households | Yes | Completed | 20 | 20 | 2016-08-24 | 2016-08-24 |  | Tarakeshwar | 5
12122 | Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 NPR per HH | # of households | Yes | Completed | 9 | 9 | 2016-01-30 | 2016-01-30 |  | Tarakeshwar | 5
12123 | Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 7 | 7 | 2016-05-30 | 2016-06-05 |  | Tarakeshwar | 5
12124 | Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 3 | 3 | 2016-09-20 | 2016-09-26 |  | Tarakeshwar | 5
12125 | Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1 hour per session | # of participants | Yes | Completed | 20 | 20 | 2016-08-24 | 2017-11-30 |  | Tarakeshwar | 5
12126 | Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Sub Engineer and Social mobilizer | # of households | Yes | Completed | 20 | 20 | 2016-08-24 | 2017-11-30 |  | Tarakeshwar | 5
12127 | Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Technical Assistance | Household reconstruction orientation | 1 session | 1 hour per session | # of households | Yes | Completed | 20 | 20 | 2016-08-24 | 2017-11-30 |  | Tarakeshwar | 5
12128 | Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | 20 members in 1 committee | # of committees | Yes | Completed | 1 | 1 | 2016-08-24 | 2016-08-24 |  | Tarakeshwar | 5
12129 | Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 3 | 3 | 2016-09-20 | 2016-09-26 |  | Tarakeshwar | 5
12130 | Nuwakot | Gorsyang | 6 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 7 | 7 | 2016-05-30 | 2016-06-05 |  | Tarakeshwar | 5
12131 | Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 500000 NPR per HH | # of households | Yes | Completed | 56 | 56 | 2016-08-24 | 2016-08-24 |  | Tarakeshwar | 5
12132 | Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 NPR per HH | # of households | Yes | Completed | 22 | 22 | 2016-01-30 | 2016-01-30 |  | Tarakeshwar | 5
12133 | Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 4 | 4 | 2016-05-30 | 2016-06-05 |  | Tarakeshwar | 5
12134 | Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 14 | 14 | 2016-09-20 | 2016-09-26 |  | Tarakeshwar | 5
12135 | Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1 hour per session | # of participants | Yes | Completed | 56 | 56 | 2016-08-24 | 2017-11-30 |  | Tarakeshwar | 5
12136 | Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Technical Assistance | Demonstration Construction | House | Brick masonry in cement motar, Scaled down demo house in section | # of constructions | Yes | Completed | 1 | 1 | 2016-05-30 | 2016-06-05 |  | Tarakeshwar | 5
12137 | Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Sub Engineer and Social mobilizer | # of households | Yes | Completed | 56 | 56 | 2016-08-24 | 2017-11-30 |  | Tarakeshwar | 5
12138 | Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Technical Assistance | Household reconstruction orientation | 1 session | 1 hour per session | # of households | Yes | Completed | 56 | 56 | 2016-08-24 | 2017-11-30 |  | Tarakeshwar | 5
12139 | Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | 56 members in 3 committee | # of committees | Yes | Completed | 3 | 3 | 2016-08-24 | 2016-08-24 |  | Tarakeshwar | 5
12140 | Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Training | Other trainings | Other trainings (specify in Activity Detail) | Compressed Stabilized Earthen Block (CSEB) Production | # of trainees | Yes | Completed | 18 | 18 | 2016-12-19 | 2016-12-25 |  | Tarakeshwar | 5
12141 | Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 14 | 14 | 2016-09-20 | 2016-09-26 |  | Tarakeshwar | 5
12142 | Nuwakot | Gorsyang | 7 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 4 | 4 | 2016-05-30 | 2016-06-05 |  | Tarakeshwar | 5
12143 | Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 500000 NPR per HH | # of households | Yes | Completed | 32 | 32 | 2016-08-24 | 2016-08-24 |  | Tarakeshwar | 5
12144 | Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 NPR per HH | # of households | Yes | Completed | 11 | 11 | 2016-01-30 | 2016-01-30 |  | Tarakeshwar | 5
12145 | Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 2 | 2 | 2016-05-30 | 2016-06-05 |  | Tarakeshwar | 5
12146 | Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 9 | 9 | 2016-09-20 | 2016-09-26 |  | Tarakeshwar | 5
12147 | Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1 hour per session | # of participants | Yes | Completed | 32 | 32 | 2016-08-24 | 2017-11-30 |  | Tarakeshwar | 5
12148 | Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Technical Assistance | Demonstration Construction | House | Composite structure, Scaled down demo house in section | # of constructions | Yes | Completed | 1 | 1 | 2016-09-20 | 2016-09-26 |  | Tarakeshwar | 5
12149 | Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Sub Engineer and Social mobilizer | # of households | Yes | Completed | 32 | 32 | 2016-08-24 | 2017-11-30 |  | Tarakeshwar | 5
12150 | Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Technical Assistance | Household reconstruction orientation | 1 session | 1 hour per session | # of households | Yes | Completed | 32 | 32 | 2016-08-24 | 2017-11-30 |  | Tarakeshwar | 5
12151 | Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | 32 members in 1 committee | # of committees | Yes | Completed | 1 | 1 | 2016-08-24 | 2016-08-24 |  | Tarakeshwar | 5
12152 | Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 9 | 9 | 2016-09-20 | 2016-09-26 |  | Tarakeshwar | 5
12153 | Nuwakot | Gorsyang | 8 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-05-30 | 2016-06-05 |  | Tarakeshwar | 5
12154 | Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 500000 NPR per HH | # of households | Yes | Completed | 10 | 10 | 2016-08-24 | 2016-08-24 |  | Tarakeshwar | 6
12155 | Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 NPR per HH | # of households | Yes | Completed | 6 | 6 | 2016-01-30 | 2016-01-30 |  | Tarakeshwar | 6
12156 | Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 3 | 3 | 2016-05-30 | 2016-06-05 |  | Tarakeshwar | 6
12157 | Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 2 | 2 | 2016-09-20 | 2016-09-26 |  | Tarakeshwar | 6
12158 | Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1 hour per session | # of participants | Yes | Completed | 10 | 10 | 2016-08-24 | 2017-11-30 |  | Tarakeshwar | 6
12159 | Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Sub Engineer and Social mobilizer | # of households | Yes | Completed | 10 | 10 | 2016-08-24 | 2017-11-30 |  | Tarakeshwar | 6
12160 | Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Technical Assistance | Household reconstruction orientation | 1 session | 1 hour per session | # of households | Yes | Completed | 10 | 10 | 2016-08-24 | 2017-11-30 |  | Tarakeshwar | 6
12161 | Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | 10 members in 1 committee | # of committees | Yes | Completed | 1 | 1 | 2016-08-24 | 2016-08-24 |  | Tarakeshwar | 6
12162 | Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-09-20 | 2016-09-26 |  | Tarakeshwar | 6
12163 | Nuwakot | Gorsyang | 9 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 3 | 3 | 2016-05-30 | 2016-06-05 |  | Tarakeshwar | 6
12164 | Nuwakot | Jiling | 1 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 8
12165 | Nuwakot | Jiling | 2 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 8
12166 | Nuwakot | Jiling | 4 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 8
12167 | Nuwakot | Jiling | 5 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 8
12168 | Nuwakot | Jiling | 6 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 9
12169 | Nuwakot | Jiling | 7 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 9
12170 | Nuwakot | Jiling | 8 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 9
12171 | Nuwakot | Jiling | 9 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 9
12172 | Nuwakot | Jiling | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 8
12173 | Nuwakot | Jiling | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 8
12174 | Nuwakot | Jiling | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 8
12175 | Nuwakot | Jiling | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 8
12176 | Nuwakot | Jiling | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 8
12177 | Nuwakot | Jiling | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 9
12178 | Nuwakot | Jiling | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 9
12179 | Nuwakot | Jiling | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 9
12180 | Nuwakot | Jiling | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 9
12181 | Nuwakot | Jiling | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 8
12182 | Nuwakot | Jiling | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 8
12183 | Nuwakot | Jiling | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 8
12184 | Nuwakot | Jiling | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 8
12185 | Nuwakot | Jiling | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 8
12186 | Nuwakot | Jiling | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 9
12187 | Nuwakot | Jiling | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 9
12188 | Nuwakot | Jiling | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 9
12189 | Nuwakot | Jiling | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 9
12190 | Nuwakot | Kakani | 3 | GON - PAF | CARDSN | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 25 | 25 | 2016-09-12 | 2016-09-19 |  | Kakani | 4
12191 | Nuwakot | Kakani | 2 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 10 | 10 | 2017-06-09 | 2017-06-15 |  | Kakani | 4
12192 | Nuwakot | Kakani | 1 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 7 | 7 | 2017-06-09 | 2017-06-15 |  | Kakani | 4
12193 | Nuwakot | Kalikahalde | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Suryagadhi | 4
12194 | Nuwakot | Kalikahalde | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Suryagadhi | 4
12195 | Nuwakot | Kalikahalde | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Suryagadhi | 4
12196 | Nuwakot | Kalikahalde | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Suryagadhi | 4
12197 | Nuwakot | Kalikahalde | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Suryagadhi | 4
12198 | Nuwakot | Kalikahalde | 6 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Suryagadhi | 4
12199 | Nuwakot | Kalikahalde | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Suryagadhi | 4
12200 | Nuwakot | Kalikahalde | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Suryagadhi | 4
12201 | Nuwakot | Kalikahalde | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Suryagadhi | 4
12202 | Nuwakot | Kalikahalde | 1 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 52 | 52 | 2016-04-01 | 2016-09-30 |  | Suryagadhi | 4
12203 | Nuwakot | Kalikahalde | 2 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 80 | 80 | 2016-04-01 | 2016-09-30 |  | Suryagadhi | 4
12204 | Nuwakot | Kalikahalde | 3 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 85 | 85 | 2016-04-01 | 2016-09-30 |  | Suryagadhi | 4
12205 | Nuwakot | Kalikahalde | 4 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 62 | 62 | 2016-04-01 | 2016-09-30 |  | Suryagadhi | 4
12206 | Nuwakot | Kalikahalde | 5 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 72 | 72 | 2016-04-01 | 2016-09-30 |  | Suryagadhi | 4
12207 | Nuwakot | Kalikahalde | 6 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 53 | 53 | 2016-04-01 | 2016-09-30 |  | Suryagadhi | 4
12208 | Nuwakot | Kalikahalde | 7 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 73 | 73 | 2016-04-01 | 2016-09-30 |  | Suryagadhi | 4
12209 | Nuwakot | Kalikahalde | 8 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 154 | 154 | 2016-04-01 | 2016-09-30 |  | Suryagadhi | 4
12210 | Nuwakot | Kalikahalde | 9 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 85 | 85 | 2016-04-01 | 2016-09-30 |  | Suryagadhi | 4
12211 | Nuwakot | Kalikahalde | 1 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 106 | 106 | 2016-02-10 | 2016-07-01 |  | Suryagadhi | 4
12212 | Nuwakot | Kalikahalde | 2 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 118 | 118 | 2016-02-10 | 2016-07-01 |  | Suryagadhi | 4
12213 | Nuwakot | Kalikahalde | 3 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 124 | 124 | 2016-02-10 | 2016-07-01 |  | Suryagadhi | 4
12214 | Nuwakot | Kalikahalde | 4 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 112 | 112 | 2016-02-10 | 2016-07-01 |  | Suryagadhi | 4
12215 | Nuwakot | Kalikahalde | 5 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 95 | 95 | 2016-02-10 | 2016-07-01 |  | Suryagadhi | 4
12216 | Nuwakot | Kalikahalde | 6 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 69 | 69 | 2016-02-10 | 2016-07-01 |  | Suryagadhi | 4
12217 | Nuwakot | Kalikahalde | 7 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 74 | 74 | 2016-02-10 | 2016-07-01 |  | Suryagadhi | 4
12218 | Nuwakot | Kalikahalde | 8 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 215 | 215 | 2016-02-10 | 2016-07-01 |  | Suryagadhi | 4
12219 | Nuwakot | Kalikahalde | 9 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 119 | 119 | 2016-02-10 | 2016-07-01 |  | Suryagadhi | 4
12220 | Nuwakot | Kalyanpur | 1 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-06-23 | 2016-06-30 |  | Bidur | 13
12221 | Nuwakot | Kalyanpur | 2 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-23 | 2016-06-30 |  | Bidur | 13
12222 | Nuwakot | Kalyanpur | 8 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-23 | 2016-06-30 |  | Bidur | 13
12223 | Nuwakot | Kalyanpur | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 13
12224 | Nuwakot | Kalyanpur | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 13
12225 | Nuwakot | Kalyanpur | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 13
12226 | Nuwakot | Kalyanpur | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 13
12227 | Nuwakot | Kalyanpur | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 13
12228 | Nuwakot | Kalyanpur | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 13
12229 | Nuwakot | Kalyanpur | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 13
12230 | Nuwakot | Kalyanpur | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 13
12231 | Nuwakot | Kalyanpur | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 13
12232 | Nuwakot | Kalyanpur | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 13
12233 | Nuwakot | Kalyanpur | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 13
12234 | Nuwakot | Kalyanpur | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 13
12235 | Nuwakot | Kalyanpur | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 13
12236 | Nuwakot | Kalyanpur | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 13
12237 | Nuwakot | Kalyanpur | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 13
12238 | Nuwakot | Kalyanpur | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 13
12239 | Nuwakot | Kalyanpur | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 13
12240 | Nuwakot | Kalyanpur | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 13
12241 | Nuwakot | Kaule | 3 | BC | NRCS | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-01-25 | 2016-01-29 |  | Kispang | 3
12242 | Nuwakot | Kaule | 5 | BC | NRCS | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2016-01-25 | 2016-01-29 |  | Kispang | 3
12243 | Nuwakot | Kaule | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 3
12244 | Nuwakot | Kaule | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 3
12245 | Nuwakot | Kaule | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 3
12246 | Nuwakot | Kaule | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 3
12247 | Nuwakot | Kaule | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 3
12248 | Nuwakot | Kaule | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 3
12249 | Nuwakot | Kaule | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 3
12250 | Nuwakot | Kaule | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 3
12251 | Nuwakot | Kaule | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 3
12252 | Nuwakot | Kaule | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 3
12253 | Nuwakot | Kaule | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 3
12254 | Nuwakot | Kaule | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 3
12255 | Nuwakot | Kaule | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 3
12256 | Nuwakot | Kaule | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 3
12257 | Nuwakot | Kaule | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 3
12258 | Nuwakot | Kaule | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 3
12259 | Nuwakot | Kaule | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 3
12260 | Nuwakot | Kaule | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 3
12261 | Nuwakot | Kaule | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 12 | 12 | 2016-01-01 | 2018-12-31 |  | Kispang | 3
12262 | Nuwakot | Kaule | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 9 | 9 | 2016-01-01 | 2018-12-31 |  | Kispang | 3
12263 | Nuwakot | Kaule | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 9 | 9 | 2016-01-01 | 2018-12-31 |  | Kispang | 3
12264 | Nuwakot | Kaule | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 9 | 9 | 2016-01-01 | 2018-12-31 |  | Kispang | 3
12265 | Nuwakot | Kaule | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 9 | 9 | 2016-01-01 | 2018-12-31 |  | Kispang | 3
12266 | Nuwakot | Kaule | 6 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 9 | 9 | 2016-01-01 | 2018-12-31 |  | Kispang | 3
12267 | Nuwakot | Kaule | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 9 | 9 | 2016-01-01 | 2018-12-31 |  | Kispang | 3
12268 | Nuwakot | Kaule | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 9 | 9 | 2016-01-01 | 2018-12-31 |  | Kispang | 3
12269 | Nuwakot | Kaule | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 9 | 9 | 2016-01-01 | 2018-12-31 |  | Kispang | 3
12270 | Nuwakot | Kaule | 1 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 126 | 125 | 2016-01-25 | 2016-12-15 |  | Kispang | 3
12271 | Nuwakot | Kaule | 2 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 119 | 117 | 2016-01-25 | 2016-12-15 |  | Kispang | 3
12272 | Nuwakot | Kaule | 3 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 87 | 83 | 2016-01-25 | 2016-12-15 |  | Kispang | 3
12273 | Nuwakot | Kaule | 4 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 125 | 124 | 2016-01-25 | 2016-12-15 |  | Kispang | 3
12274 | Nuwakot | Kaule | 5 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 136 | 135 | 2016-01-25 | 2016-12-15 |  | Kispang | 3
12275 | Nuwakot | Kaule | 6 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 82 | 65 | 2016-01-25 | 2016-12-15 |  | Kispang | 3
12276 | Nuwakot | Kaule | 7 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 88 | 85 | 2016-01-25 | 2016-12-15 |  | Kispang | 3
12277 | Nuwakot | Kaule | 8 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 104 | 102 | 2016-01-25 | 2016-12-15 |  | Kispang | 3
12278 | Nuwakot | Kaule | 9 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 86 | 84 | 2016-01-25 | 2016-12-15 |  | Kispang | 3
12279 | Nuwakot | Kaule | 1 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 126 | 60 | 2017-06-06 | 2017-12-06 |  | Kispang | 3
12280 | Nuwakot | Kaule | 2 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 119 | 17 | 2017-06-06 | 2017-12-06 |  | Kispang | 3
12281 | Nuwakot | Kaule | 3 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 87 | 17 | 2017-06-06 | 2017-12-06 |  | Kispang | 3
12282 | Nuwakot | Kaule | 4 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 125 | 20 | 2017-06-06 | 2017-12-06 |  | Kispang | 3
12283 | Nuwakot | Kaule | 5 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 136 | 5 | 2017-06-06 | 2017-12-06 |  | Kispang | 3
12284 | Nuwakot | Kaule | 6 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 82 | 8 | 2017-06-06 | 2017-12-06 |  | Kispang | 3
12285 | Nuwakot | Kaule | 7 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 88 | 22 | 2017-06-06 | 2017-12-06 |  | Kispang | 3
12286 | Nuwakot | Kaule | 8 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 104 | 22 | 2017-06-06 | 2017-12-06 |  | Kispang | 3
12287 | Nuwakot | Kaule | 9 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 86 | 26 | 2017-06-06 | 2017-12-06 |  | Kispang | 3
12288 | Nuwakot | Kaule | 1 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 126 | 18 | 2016-09-01 | 2018-12-31 |  | Kispang | 3
12289 | Nuwakot | Kaule | 2 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 119 | 9 | 2016-09-01 | 2018-12-31 |  | Kispang | 3
12290 | Nuwakot | Kaule | 3 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 87 | 9 | 2016-09-01 | 2018-12-31 |  | Kispang | 3
12291 | Nuwakot | Kaule | 4 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 125 | 10 | 2016-09-01 | 2018-12-31 |  | Kispang | 3
12292 | Nuwakot | Kaule | 5 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 136 | 1 | 2016-09-01 | 2018-12-31 |  | Kispang | 3
12293 | Nuwakot | Kaule | 6 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 82 | 0 | 2016-09-01 | 2018-12-31 |  | Kispang | 3
12294 | Nuwakot | Kaule | 7 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 88 | 9 | 2016-09-01 | 2018-12-31 |  | Kispang | 3
12295 | Nuwakot | Kaule | 8 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 104 | 6 | 2016-09-01 | 2018-12-31 |  | Kispang | 3
12296 | Nuwakot | Kaule | 9 | NRCS | NRCS | ARC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 86 | 13 | 2016-09-01 | 2018-12-31 |  | Kispang | 3
12297 | Nuwakot | Kaule | 1 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 126 | 126 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kispang | 3
12298 | Nuwakot | Kaule | 2 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 119 | 119 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kispang | 3
12299 | Nuwakot | Kaule | 3 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 87 | 87 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kispang | 3
12300 | Nuwakot | Kaule | 4 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 125 | 125 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kispang | 3
12301 | Nuwakot | Kaule | 5 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 136 | 136 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kispang | 3
12302 | Nuwakot | Kaule | 6 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 82 | 82 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kispang | 3
12303 | Nuwakot | Kaule | 7 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 88 | 88 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kispang | 3
12304 | Nuwakot | Kaule | 8 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 104 | 104 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kispang | 3
12305 | Nuwakot | Kaule | 9 | NRCS | NRCS | ARC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 86 | 86 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Kispang | 3
12306 | Nuwakot | KhadagBhanjyang | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 6
12307 | Nuwakot | KhadagBhanjyang | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 6
12308 | Nuwakot | KhadagBhanjyang | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 6
12309 | Nuwakot | KhadagBhanjyang | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 3
12310 | Nuwakot | KhadagBhanjyang | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 3
12311 | Nuwakot | KhadagBhanjyang | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 3
12312 | Nuwakot | KhadagBhanjyang | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 3
12313 | Nuwakot | KhadagBhanjyang | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 3
12314 | Nuwakot | KhadagBhanjyang | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 3
12315 | Nuwakot | KhadagBhanjyang | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 6
12316 | Nuwakot | KhadagBhanjyang | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 6
12317 | Nuwakot | KhadagBhanjyang | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 6
12318 | Nuwakot | KhadagBhanjyang | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 3
12319 | Nuwakot | KhadagBhanjyang | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 3
12320 | Nuwakot | KhadagBhanjyang | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 3
12321 | Nuwakot | KhadagBhanjyang | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 3
12322 | Nuwakot | KhadagBhanjyang | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 3
12323 | Nuwakot | KhadagBhanjyang | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 3
12324 | Nuwakot | KhadagBhanjyang | 1 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 58 | 2016-11-23 | 2016-11-23 |  | Tarakeshwar | 6
12325 | Nuwakot | KhadagBhanjyang | 2 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 58 | 2016-11-24 | 2016-11-24 |  | Tarakeshwar | 6
12326 | Nuwakot | KhadagBhanjyang | 3 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 44 | 2016-11-25 | 2016-11-25 |  | Tarakeshwar | 6
12327 | Nuwakot | KhadagBhanjyang | 4 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 173 | 2016-08-24 | 2016-08-24 |  | Bidur | 3
12328 | Nuwakot | KhadagBhanjyang | 5 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 66 | 2016-09-29 | 2016-09-29 |  | Bidur | 3
12329 | Nuwakot | KhadagBhanjyang | 6 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 89 | 2017-01-01 | 2017-03-15 |  | Bidur | 3
12330 | Nuwakot | KhadagBhanjyang | 7 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 44 | 2017-01-01 | 2017-03-15 |  | Bidur | 3
12331 | Nuwakot | KhadagBhanjyang | 8 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 90 | 2017-01-01 | 2017-03-15 |  | Bidur | 3
12332 | Nuwakot | KhadagBhanjyang | 9 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 43 | 2017-01-01 | 2017-03-15 |  | Bidur | 3
12333 | Nuwakot | KhadagBhanjyang | 7 | OXFAM-GB | SSS | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 16 | 16 | 2017-01-01 | 2017-03-03 |  | Bidur | 3
12334 | Nuwakot | KhadagBhanjyang | All | OXFAM-GB | SSS | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 60 | 63 | 2016-11-11 | 2016-12-01 |  | Tarakeshwar | 6
12335 | Nuwakot | KhadagBhanjyang | All | OXFAM-GB | SSS | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 60 | 63 | 2016-11-11 | 2016-12-01 |  | Tarakeshwar | 6
12336 | Nuwakot | KhadagBhanjyang | All | OXFAM-GB | SSS | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 16 | 16 | 2017-01-01 | 2017-03-03 |  | Tarakeshwar | 6
12337 | Nuwakot | Kharanitar | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 3
12338 | Nuwakot | Kharanitar | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 3
12339 | Nuwakot | Kharanitar | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 3
12340 | Nuwakot | Kharanitar | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 3
12341 | Nuwakot | Kharanitar | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 3
12342 | Nuwakot | Kharanitar | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 3
12343 | Nuwakot | Kharanitar | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 3
12344 | Nuwakot | Kharanitar | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 3
12345 | Nuwakot | Kharanitar | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 3
12346 | Nuwakot | Kharanitar | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 3
12347 | Nuwakot | Kharanitar | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 3
12348 | Nuwakot | Kharanitar | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 3
12349 | Nuwakot | Kharanitar | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 3
12350 | Nuwakot | Kharanitar | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 3
12351 | Nuwakot | Kharanitar | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 3
12352 | Nuwakot | Kharanitar | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 3
12353 | Nuwakot | Kharanitar | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 3
12354 | Nuwakot | Kharanitar | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 3
12355 | Nuwakot | KholegaunKhanigau | 3 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-02 | 2016-06-08 |  | Likhu | 1
12356 | Nuwakot | KholegaunKhanigau | 4 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2016-06-02 | 2016-06-08 |  | Likhu | 1
12357 | Nuwakot | KholegaunKhanigau | 7 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2016-06-02 | 2016-06-08 |  | Likhu | 2
12358 | Nuwakot | KholegaunKhanigau | 8 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-02 | 2016-06-08 |  | Likhu | 1
12359 | Nuwakot | KholegaunKhanigau | 9 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2016-06-02 | 2016-06-08 |  | Likhu | 2
12360 | Nuwakot | KholegaunKhanigau | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 1
12361 | Nuwakot | KholegaunKhanigau | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 1
12362 | Nuwakot | KholegaunKhanigau | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 1
12363 | Nuwakot | KholegaunKhanigau | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 1
12364 | Nuwakot | KholegaunKhanigau | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 2
12365 | Nuwakot | KholegaunKhanigau | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 2
12366 | Nuwakot | KholegaunKhanigau | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 2
12367 | Nuwakot | KholegaunKhanigau | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 1
12368 | Nuwakot | KholegaunKhanigau | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 2
12369 | Nuwakot | KholegaunKhanigau | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 1
12370 | Nuwakot | KholegaunKhanigau | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 1
12371 | Nuwakot | KholegaunKhanigau | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 1
12372 | Nuwakot | KholegaunKhanigau | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 1
12373 | Nuwakot | KholegaunKhanigau | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 2
12374 | Nuwakot | KholegaunKhanigau | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 2
12375 | Nuwakot | KholegaunKhanigau | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 2
12376 | Nuwakot | KholegaunKhanigau | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 1
12377 | Nuwakot | KholegaunKhanigau | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 2
12378 | Nuwakot | Kintang | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 4
12379 | Nuwakot | Kintang | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 4
12380 | Nuwakot | Kintang | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 4
12381 | Nuwakot | Kintang | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 4
12382 | Nuwakot | Kintang | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 4
12383 | Nuwakot | Kintang | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 4
12384 | Nuwakot | Kintang | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 4
12385 | Nuwakot | Kintang | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 4
12386 | Nuwakot | Kintang | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 4
12387 | Nuwakot | Kintang | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 4
12388 | Nuwakot | Kintang | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 4
12389 | Nuwakot | Kintang | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 4
12390 | Nuwakot | Kintang | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 4
12391 | Nuwakot | Kintang | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 4
12392 | Nuwakot | Kintang | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 4
12393 | Nuwakot | Kintang | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 4
12394 | Nuwakot | Kintang | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 4
12395 | Nuwakot | Kintang | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 4
12396 | Nuwakot | Kumari | 5 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 3 | 1 | 2017-07-10 | 2017-07-17 |  | Belkotgadhi | 4
12397 | Nuwakot | Kumari | 6 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2017-07-10 | 2017-07-17 |  | Belkotgadhi | 2
12398 | Nuwakot | Kumari | 7 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 4 | 4 | 2017-07-10 | 2017-07-17 |  | Belkotgadhi | 3
12399 | Nuwakot | Kumari | 9 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2017-07-10 | 2017-07-17 |  | Belkotgadhi | 2
12400 | Nuwakot | Lachyang | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 9 | 9 | 2016-01-01 | 2018-12-31 |  | Suryagadhi | 1
12401 | Nuwakot | Lachyang | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Suryagadhi | 1
12402 | Nuwakot | Lachyang | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Suryagadhi | 1
12403 | Nuwakot | Lachyang | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Suryagadhi | 1
12404 | Nuwakot | Lachyang | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Suryagadhi | 1
12405 | Nuwakot | Lachyang | 6 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Suryagadhi | 1
12406 | Nuwakot | Lachyang | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Suryagadhi | 1
12407 | Nuwakot | Lachyang | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Suryagadhi | 1
12408 | Nuwakot | Lachyang | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Suryagadhi | 2
12409 | Nuwakot | Madanpur | 1 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-02 | 2016-06-08 |  | Belkotgadhi | 13
12410 | Nuwakot | Madanpur | 2 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-02 | 2016-06-08 |  | Belkotgadhi | 13
12411 | Nuwakot | Madanpur | 3 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-02 | 2016-06-08 |  | Belkotgadhi | 12
12412 | Nuwakot | Madanpur | 4 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-02 | 2016-06-08 |  | Belkotgadhi | 12
12413 | Nuwakot | Madanpur | 5 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-02 | 2016-06-08 |  | Belkotgadhi | 12
12414 | Nuwakot | Madanpur | 6 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-02 | 2016-06-08 |  | Belkotgadhi | 13
12415 | Nuwakot | Madanpur | 8 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-02 | 2016-06-08 |  | Kakani | 6
12416 | Nuwakot | Madanpur | 9 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-02 | 2016-06-08 |  | Belkotgadhi | 13
12417 | Nuwakot | Madanpur | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 13
12418 | Nuwakot | Madanpur | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 13
12419 | Nuwakot | Madanpur | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 12
12420 | Nuwakot | Madanpur | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 12
12421 | Nuwakot | Madanpur | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 12
12422 | Nuwakot | Madanpur | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 13
12423 | Nuwakot | Madanpur | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 6
12424 | Nuwakot | Madanpur | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 6
12425 | Nuwakot | Madanpur | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 13
12426 | Nuwakot | Madanpur | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 13
12427 | Nuwakot | Madanpur | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 13
12428 | Nuwakot | Madanpur | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 12
12429 | Nuwakot | Madanpur | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 12
12430 | Nuwakot | Madanpur | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 12
12431 | Nuwakot | Madanpur | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 13
12432 | Nuwakot | Madanpur | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 6
12433 | Nuwakot | Madanpur | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 6
12434 | Nuwakot | Madanpur | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 13
12435 | Nuwakot | Madanpur | All | OXFAM-GB | CARDSN | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 16 | 16 | 2017-01-01 | 2017-03-03 |  | Kakani | 13
12436 | Nuwakot | Madanpur | 1 | OXFAM-GB | CARDSN | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 2 | 2 | 2017-01-01 | 2017-03-03 |  | Belkotgadhi | 13
12437 | Nuwakot | Madanpur | 1 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 80 | 2017-02-14 | 2017-02-14 |  | Belkotgadhi | 13
12438 | Nuwakot | Madanpur | 2 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 150 | 2017-02-13 | 2017-03-02 |  | Belkotgadhi | 13
12439 | Nuwakot | Madanpur | 3 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 50 | 2017-02-09 | 2017-02-09 |  | Belkotgadhi | 12
12440 | Nuwakot | Madanpur | 4 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 134 | 2017-02-10 | 2017-02-10 |  | Belkotgadhi | 12
12441 | Nuwakot | Madanpur | 5 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 53 | 2016-09-01 | 2016-09-01 |  | Belkotgadhi | 12
12442 | Nuwakot | Madanpur | 6 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 45 | 2017-02-09 | 2017-02-09 |  | Belkotgadhi | 13
12443 | Nuwakot | Madanpur | 7 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 59 | 2017-02-15 | 2017-02-15 |  | Kakani | 6
12444 | Nuwakot | Madanpur | 8 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 155 | 2017-02-08 | 2017-02-08 |  | Kakani | 6
12445 | Nuwakot | Madanpur | 9 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 84 | 2016-08-17 | 2016-08-17 |  | Belkotgadhi | 13
12446 | Nuwakot | Madanpur | 2 | OXFAM-GB | CARDSN | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 3 | 3 | 2017-01-01 | 2017-03-03 |  | Belkotgadhi | 13
12447 | Nuwakot | Madanpur | 3 | OXFAM-GB | CARDSN | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 1 | 1 | 2017-01-01 | 2017-03-03 |  | Belkotgadhi | 12
12448 | Nuwakot | Madanpur | 5 | OXFAM-GB | CARDSN | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 1 | 1 | 2017-01-01 | 2017-03-03 |  | Belkotgadhi | 12
12449 | Nuwakot | Madanpur | 6 | OXFAM-GB | CARDSN | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 2 | 2 | 2017-01-01 | 2017-03-03 |  | Belkotgadhi | 13
12450 | Nuwakot | Madanpur | 7 | OXFAM-GB | CARDSN | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 2 | 2 | 2017-01-01 | 2017-03-03 |  | Kakani | 6
12451 | Nuwakot | Madanpur | 9 | OXFAM-GB | CARDSN | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 5 | 5 | 2017-01-01 | 2017-03-03 |  | Belkotgadhi | 13
12452 | Nuwakot | Madanpur | All | OXFAM-GB | CARDSN | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 60 | 86 | 2016-06-24 | 2016-10-26 |  | Kakani | 13
12453 | Nuwakot | Madanpur | All | OXFAM-GB | CARDSN | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 60 | 86 | 2016-06-24 | 2016-10-26 |  | Kakani | 13
12454 | Nuwakot | Manakamana | All | BC | WR | BC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 99 | 99 | 2016-03-28 | 2016-04-23 |  | Kispang | 5
12455 | Nuwakot | Manakamana | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 5
12456 | Nuwakot | Manakamana | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 5
12457 | Nuwakot | Manakamana | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 5
12458 | Nuwakot | Manakamana | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 5
12459 | Nuwakot | Manakamana | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 5
12460 | Nuwakot | Manakamana | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 5
12461 | Nuwakot | Manakamana | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 5
12462 | Nuwakot | Manakamana | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 5
12463 | Nuwakot | Manakamana | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 5
12464 | Nuwakot | Manakamana | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 5
12465 | Nuwakot | Manakamana | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 5
12466 | Nuwakot | Manakamana | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 5
12467 | Nuwakot | Manakamana | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 5
12468 | Nuwakot | Manakamana | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 5
12469 | Nuwakot | Manakamana | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 5
12470 | Nuwakot | Manakamana | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 5
12471 | Nuwakot | Manakamana | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 5
12472 | Nuwakot | Manakamana | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 5
12473 | Nuwakot | Manakamana | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kispang | 5
12474 | Nuwakot | Manakamana | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Kispang | 5
12475 | Nuwakot | Manakamana | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 10 | 10 | 2016-01-01 | 2018-12-31 |  | Kispang | 5
12476 | Nuwakot | Manakamana | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 4 | 4 | 2016-01-01 | 2018-12-31 |  | Kispang | 5
12477 | Nuwakot | Manakamana | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 5 | 5 | 2016-01-01 | 2018-12-31 |  | Kispang | 5
12478 | Nuwakot | Manakamana | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Kispang | 5
12479 | Nuwakot | Manakamana | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 1 | 1 | 2016-01-01 | 2018-12-31 |  | Kispang | 5
12480 | Nuwakot | Narjamandap | 1 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 45 | 45 | 2016-04-01 | 2016-09-30 |  | Tadi | 5
12481 | Nuwakot | Narjamandap | 2 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 155 | 155 | 2016-04-01 | 2016-09-30 |  | Tadi | 5
12482 | Nuwakot | Narjamandap | 3 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 131 | 131 | 2016-04-01 | 2016-09-30 |  | Tadi | 5
12483 | Nuwakot | Narjamandap | 4 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 78 | 78 | 2016-04-01 | 2016-09-30 |  | Tadi | 5
12484 | Nuwakot | Narjamandap | 5 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 89 | 89 | 2016-04-01 | 2016-09-30 |  | Tadi | 6
12485 | Nuwakot | Narjamandap | 6 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 126 | 126 | 2016-04-01 | 2016-09-30 |  | Tadi | 6
12486 | Nuwakot | Narjamandap | 7 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 59 | 59 | 2016-04-01 | 2016-09-30 |  | Tadi | 6
12487 | Nuwakot | Narjamandap | 8 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 82 | 82 | 2016-04-01 | 2016-09-30 |  | Tadi | 6
12488 | Nuwakot | Narjamandap | 9 | WVIN | GYEC | WVIN | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction | Toilet construction materials support | # of households | Yes | Completed | 139 | 139 | 2016-04-01 | 2016-09-30 |  | Tadi | 6
12489 | Nuwakot | Narjamandap | 1 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 91 | 91 | 2016-02-10 | 2016-07-01 |  | Tadi | 5
12490 | Nuwakot | Narjamandap | 2 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 245 | 245 | 2016-02-10 | 2016-07-01 |  | Tadi | 5
12491 | Nuwakot | Narjamandap | 3 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 195 | 195 | 2016-02-10 | 2016-07-01 |  | Tadi | 5
12492 | Nuwakot | Narjamandap | 4 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 195 | 195 | 2016-02-10 | 2016-07-01 |  | Tadi | 5
12493 | Nuwakot | Narjamandap | 5 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 112 | 112 | 2016-02-10 | 2016-07-01 |  | Tadi | 6
12494 | Nuwakot | Narjamandap | 6 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 149 | 149 | 2016-02-10 | 2016-07-01 |  | Tadi | 6
12495 | Nuwakot | Narjamandap | 7 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 106 | 106 | 2016-02-10 | 2016-07-01 |  | Tadi | 6
12496 | Nuwakot | Narjamandap | 8 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 94 | 94 | 2016-02-10 | 2016-07-01 |  | Tadi | 6
12497 | Nuwakot | Narjamandap | 9 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 166 | 166 | 2016-02-10 | 2016-07-01 |  | Tadi | 6
12498 | Nuwakot | Okharpauwa | 4 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 10 | 10 | 2017-07-10 | 2017-07-17 |  | Kakani | 2
12499 | Nuwakot | Okharpauwa | 1 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2017-07-10 | 2017-07-17 |  | Kakani | 1
12500 | Nuwakot | Okharpauwa | 2 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2017-07-10 | 2017-07-17 |  | Kakani | 2
12501 | Nuwakot | Okharpauwa | 5 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2017-07-10 | 2017-07-17 |  | Kakani | 2
12502 | Nuwakot | Okharpauwa | 6 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2017-07-10 | 2017-07-17 |  | Kakani | 2
12503 | Nuwakot | Ralukadevi | All | OXFAM-GB | SSS | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 60 | 56 | 2017-02-13 | 2017-03-01 |  | Tadi | 2
12504 | Nuwakot | Ralukadevi | All | OXFAM-GB | SSS | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 60 | 56 | 2017-02-13 | 2017-03-01 |  | Tadi | 2
12505 | Nuwakot | Ralukadevi | 1 | OXFAM-GB | SSS | OXFAM-GB | Training | Retrofitting training | Skilled construction workers | On the Job Training on Retrofitting as per Build Change course | # of trainees | Yes | Completed | 6 | 6 | 2017-10-28 | 2018-12-01 |  | Tadi | 2
12506 | Nuwakot | Ralukadevi | 8 | OXFAM-GB | SSS | OXFAM-GB | Training | Retrofitting training | Skilled construction workers | On the Job Training on Retrofitting as per Build Change course | # of trainees | Yes | Completed | 6 | 6 | 2017-11-09 | 2018-12-01 |  | Tadi | 3
12507 | Nuwakot | Ratmate | 1 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 7
12508 | Nuwakot | Ratmate | 2 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 7 | 7 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 7
12509 | Nuwakot | Ratmate | 3 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 7
12510 | Nuwakot | Ratmate | 4 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 7
12511 | Nuwakot | Ratmate | 5 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 7
12512 | Nuwakot | Ratmate | 6 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 7
12513 | Nuwakot | Ratmate | 9 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-05-22 | 2016-05-28 |  | Belkotgadhi | 7
12514 | Nuwakot | Rautbesi | All | OXFAM-GB | KCDC | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 60 | 59 | 2016-06-16 | 2016-06-26 |  | Dupcheshwar | 3
12515 | Nuwakot | Rautbesi | 1 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 80 | 2017-02-28 |  |  | Dupcheshwar | 3
12516 | Nuwakot | Rautbesi | 2 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 36 | 2017-03-02 |  |  | Dupcheshwar | 3
12517 | Nuwakot | Rautbesi | 3 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 23 | 2017-03-01 |  |  | Dupcheshwar | 3
12518 | Nuwakot | Rautbesi | 4 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 58 | 2017-03-02 |  |  | Dupcheshwar | 3
12519 | Nuwakot | Rautbesi | 5 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 33 | 2017-02-28 |  |  | Dupcheshwar | 3
12520 | Nuwakot | Rautbesi | 6 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 59 | 2017-03-03 |  |  | Dupcheshwar | 3
12521 | Nuwakot | Rautbesi | 7 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 48 | 2017-03-03 |  |  | Dupcheshwar | 3
12522 | Nuwakot | Rautbesi | 8 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 36 | 2017-03-06 |  |  | Dupcheshwar | 6
12523 | Nuwakot | Rautbesi | 9 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Ongoing | 90 | 28 | 2017-03-06 |  |  | Dupcheshwar | 6
12524 | Nuwakot | Rautbesi | All | OXFAM-GB | KCDC | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 60 | 59 | 2016-06-16 |  |  | Dupcheshwar | 3
12525 | Nuwakot | Rautbesi | 1 | OXFAM-GB | KCDC | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-15 |  | Dupcheshwar | 3
12526 | Nuwakot | Rautbesi | 2 | OXFAM-GB | KCDC | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-15 |  | Dupcheshwar | 3
12527 | Nuwakot | Rautbesi | 3 | OXFAM-GB | KCDC | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-15 |  | Dupcheshwar | 3
12528 | Nuwakot | Rautbesi | 4 | OXFAM-GB | KCDC | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-15 |  | Dupcheshwar | 3
12529 | Nuwakot | Rautbesi | 5 | OXFAM-GB | KCDC | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-15 |  | Dupcheshwar | 3
12530 | Nuwakot | Rautbesi | 7 | OXFAM-GB | KCDC | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-15 |  | Dupcheshwar | 3
12531 | Nuwakot | Rautbesi | 1 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Demonstration Construction | House | Individual House construction from 50 days mason OJT as per CTEVT course | # of constructions | Yes | Completed | 1 | 1 | 2018-12-01 | 2018-03-15 |  | Dupcheshwar | 3
12532 | Nuwakot | Rautbesi | 1 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Demonstration Construction | House | Individual House construction from 50 days mason OJT as per CTEVT course | # of constructions | Yes | Completed | 1 | 1 | 2018-12-01 | 2018-03-15 |  | Dupcheshwar | 3
12533 | Nuwakot | Rautbesi | 3 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Demonstration Construction | House | Individual House construction from 50 days mason OJT as per CTEVT course | # of constructions | Yes | Completed | 1 | 1 | 2018-12-01 | 2018-03-15 |  | Dupcheshwar | 3
12534 | Nuwakot | Rautbesi | 4 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Demonstration Construction | House | Individual House construction from 50 days mason OJT as per CTEVT course | # of constructions | Yes | Completed | 1 | 1 | 2018-12-01 | 2018-03-15 |  | Dupcheshwar | 3
12535 | Nuwakot | Rautbesi | 5 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Demonstration Construction | House | Individual House construction from 50 days mason OJT as per CTEVT course | # of constructions | Yes | Completed | 1 | 1 | 2018-12-01 | 2018-03-15 |  | Dupcheshwar | 3
12536 | Nuwakot | Rautbesi | 7 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Demonstration Construction | House | Individual House construction from 50 days mason OJT as per CTEVT course | # of constructions | Yes | Completed | 1 | 1 | 2018-12-01 | 2018-03-15 |  | Dupcheshwar | 3
12537 | Nuwakot | Rautbesi | 1 | OXFAM-GB | KCDC | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-15 |  | Dupcheshwar | 3
12538 | Nuwakot | Rautbesi | 2 | OXFAM-GB | KCDC | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-15 |  | Dupcheshwar | 3
12539 | Nuwakot | Rautbesi | 3 | OXFAM-GB | KCDC | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-15 |  | Dupcheshwar | 3
12540 | Nuwakot | Rautbesi | 4 | OXFAM-GB | KCDC | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-15 |  | Dupcheshwar | 3
12541 | Nuwakot | Rautbesi | 5 | OXFAM-GB | KCDC | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-15 |  | Dupcheshwar | 3
12542 | Nuwakot | Rautbesi | 7 | OXFAM-GB | KCDC | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 10 | 10 | 2018-12-01 | 2018-03-15 |  | Dupcheshwar | 3
12543 | Nuwakot | Rautbesi | 1 | OXFAM-GB | KCDC | OXFAM-GB | Training | Retrofitting training | Skilled construction workers | On the Job Training on Retrofitting as per Build Change course | # of trainees | Yes | Completed | 6 | 6 | 2017-10-01 | 2017-12-15 |  | Dupcheshwar | 3
12544 | Nuwakot | Rautbesi | 1 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 5 | 2017-10-01 |  |  | Dupcheshwar | 3
12545 | Nuwakot | Rautbesi | 2 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 6 | 2017-10-01 |  |  | Dupcheshwar | 3
12546 | Nuwakot | Rautbesi | 3 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 5 | 2017-10-01 |  |  | Dupcheshwar | 3
12547 | Nuwakot | Rautbesi | 4 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 6 | 2017-10-01 |  |  | Dupcheshwar | 3
12548 | Nuwakot | Rautbesi | 5 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 5 | 2017-10-01 |  |  | Dupcheshwar | 3
12549 | Nuwakot | Rautbesi | 6 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 6 | 2017-10-01 |  |  | Dupcheshwar | 3
12550 | Nuwakot | Rautbesi | 7 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 6 | 2017-10-01 |  |  | Dupcheshwar | 3
12551 | Nuwakot | Rautbesi | 8 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 6 | 2017-10-01 |  |  | Dupcheshwar | 6
12552 | Nuwakot | Rautbesi | 9 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 5 | 2017-10-01 |  |  | Dupcheshwar | 6
12553 | Nuwakot | Rautbesi | 1 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 3
12554 | Nuwakot | Rautbesi | 2 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 3
12555 | Nuwakot | Rautbesi | 3 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 3
12556 | Nuwakot | Rautbesi | 4 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 3
12557 | Nuwakot | Rautbesi | 5 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 3
12558 | Nuwakot | Rautbesi | 6 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 3
12559 | Nuwakot | Rautbesi | 7 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 3
12560 | Nuwakot | Rautbesi | 8 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 6
12561 | Nuwakot | Rautbesi | 9 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 6
12562 | Nuwakot | Rautbesi | 5 | GON - PAF | CDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2017-06-09 | 2017-06-15 |  | Dupcheshwar | 3
12563 | Nuwakot | Salme | 1 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House | One Demo house construction for all 9 wards. | # of constructions | Yes | Completed | 1 | 1 | 2017-01-02 | 2017-02-03 |  | Kispang | 4
12564 | Nuwakot | Salme | 1 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Site measurment by site supervisors to start house constrction. | # of households | Yes | Ongoing | 539 | 539 | 2016-11-20 |  |  | Kispang | 4
12565 | Nuwakot | Salme | 1 | HFH | ASF | HFH | Technical Assistance | Household reconstruction orientation | 1 session | Orientation given in Skilled Mason Training, Community and PASSA meeting. | # of households | Yes | Completed | 560 | 560 | 2016-07-09 | 2016-10-02 |  | Kispang | 4
12566 | Nuwakot | Salme | 1 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) | Two groups mason were given skilled mason training | # of trainees | Yes | Completed | 60 | 60 | 2016-09-17 | 2016-10-02 |  | Kispang | 4
12567 | Nuwakot | Salme | 1 | HFH | ASF | HFH | Training | Short training | Social mobilizer | Participatory Approach For Safe Shelter (PASSA) training given to Social Mobilizers | # of trainees | Yes | Completed | 1 | 1 | 2016-07-12 | 2016-07-16 |  | Kispang | 4
12568 | Nuwakot | Salme | 1 | HFH | ASF | HFH | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees | Yes | Completed | 30 | 30 | 2016-08-17 | 2016-08-23 |  | Kispang | 4
12569 | Nuwakot | Salme | 1 | HFH | ASF | HFH | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-01-02 | 2017-02-02 |  | Kispang | 4
12570 | Nuwakot | Salme | 2 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12571 | Nuwakot | Salme | 2 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Site measurment by site supervisors to start house constrction. | # of households | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12572 | Nuwakot | Salme | 2 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12573 | Nuwakot | Salme | 2 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12574 | Nuwakot | Salme | 2 | HFH | ASF | HFH | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12575 | Nuwakot | Salme | 2 | HFH | ASF | HFH | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12576 | Nuwakot | Salme | 3 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12577 | Nuwakot | Salme | 3 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Site measurment by site supervisors to start house constrction. | # of households | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12578 | Nuwakot | Salme | 3 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12579 | Nuwakot | Salme | 3 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12580 | Nuwakot | Salme | 3 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12581 | Nuwakot | Salme | 3 | HFH | ASF | HFH | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12582 | Nuwakot | Salme | 3 | HFH | ASF | HFH | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12583 | Nuwakot | Salme | 4 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12584 | Nuwakot | Salme | 4 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Site measurment by site supervisors to start house constrction. | # of households | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12585 | Nuwakot | Salme | 4 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12586 | Nuwakot | Salme | 4 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12587 | Nuwakot | Salme | 4 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12588 | Nuwakot | Salme | 4 | HFH | ASF | HFH | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12589 | Nuwakot | Salme | 4 | HFH | ASF | HFH | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12590 | Nuwakot | Salme | 5 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12591 | Nuwakot | Salme | 5 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Site measurment by site supervisors to start house constrction. | # of households | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12592 | Nuwakot | Salme | 5 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12593 | Nuwakot | Salme | 5 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12594 | Nuwakot | Salme | 5 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12595 | Nuwakot | Salme | 5 | HFH | ASF | HFH | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12596 | Nuwakot | Salme | 5 | HFH | ASF | HFH | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12597 | Nuwakot | Salme | 6 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12598 | Nuwakot | Salme | 6 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Site measurment by site supervisors to start house constrction. | # of households | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12599 | Nuwakot | Salme | 6 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12600 | Nuwakot | Salme | 6 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12601 | Nuwakot | Salme | 6 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12602 | Nuwakot | Salme | 6 | HFH | ASF | HFH | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12603 | Nuwakot | Salme | 6 | HFH | ASF | HFH | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12604 | Nuwakot | Salme | 7 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12605 | Nuwakot | Salme | 7 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Site supervisors are visiting the sites for technical assistance | # of households | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12606 | Nuwakot | Salme | 7 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12607 | Nuwakot | Salme | 7 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12608 | Nuwakot | Salme | 7 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12609 | Nuwakot | Salme | 7 | HFH | ASF | HFH | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12610 | Nuwakot | Salme | 7 | HFH | ASF | HFH | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12611 | Nuwakot | Salme | 8 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12612 | Nuwakot | Salme | 8 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Site supervisors are visiting the sites for technical assistance | # of households | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12613 | Nuwakot | Salme | 8 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12614 | Nuwakot | Salme | 8 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12615 | Nuwakot | Salme | 8 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12616 | Nuwakot | Salme | 8 | HFH | ASF | HFH | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12617 | Nuwakot | Salme | 8 | HFH | ASF | HFH | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12618 | Nuwakot | Salme | 9 | HFH | ASF | HFH | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12619 | Nuwakot | Salme | 9 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12620 | Nuwakot | Salme | 9 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | Site supervisors are visiting the sites for technical assistance | # of households | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12621 | Nuwakot | Salme | 9 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12622 | Nuwakot | Salme | 9 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12623 | Nuwakot | Salme | 9 | HFH | ASF | HFH | Training | Short training | Social mobilizer |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12624 | Nuwakot | Salme | 9 | HFH | ASF | HFH | Training | ToT | Engineers, sub engineers (7 days DUDBC) | DUDBC | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12625 | Nuwakot | Salme | 9 | HFH | ASF | HFH | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Kispang | 4
12626 | Nuwakot | Salme | 2 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2017-07-10 | 2017-07-17 |  | Kispang | 4
12627 | Nuwakot | Samari | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 5
12628 | Nuwakot | Samari | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 6
12629 | Nuwakot | Samari | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 6
12630 | Nuwakot | Samari | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 5
12631 | Nuwakot | Samari | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 6
12632 | Nuwakot | Samari | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 6
12633 | Nuwakot | Samari | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 5
12634 | Nuwakot | Samari | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 5
12635 | Nuwakot | Samari | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Meghang | 5
12636 | Nuwakot | Samari | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 5
12637 | Nuwakot | Samari | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 6
12638 | Nuwakot | Samari | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 6
12639 | Nuwakot | Samari | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 5
12640 | Nuwakot | Samari | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 6
12641 | Nuwakot | Samari | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 6
12642 | Nuwakot | Samari | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 5
12643 | Nuwakot | Samari | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 5
12644 | Nuwakot | Samari | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Meghang | 5
12645 | Nuwakot | Samari | 1 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 30 | 2017-01-18 | 2017-01-18 |  | Meghang | 5
12646 | Nuwakot | Samari | 2 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 44 | 2017-01-19 | 2017-01-19 |  | Meghang | 6
12647 | Nuwakot | Samari | 3 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 65 | 2017-01-20 | 2017-01-20 |  | Meghang | 6
12648 | Nuwakot | Samari | 4 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 54 | 2017-01-21 | 2017-01-21 |  | Meghang | 5
12649 | Nuwakot | Samari | 5 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 89 | 2017-01-19 | 2017-01-22 |  | Meghang | 6
12650 | Nuwakot | Samari | 6 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 38 | 2017-01-20 | 2017-01-20 |  | Meghang | 6
12651 | Nuwakot | Samari | 7 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 40 | 2017-01-21 | 2017-01-21 |  | Meghang | 5
12652 | Nuwakot | Samari | 8 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 38 | 2017-01-21 | 2017-01-21 |  | Meghang | 5
12653 | Nuwakot | Samari | 9 | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 42 | 2017-01-22 | 2017-01-22 |  | Meghang | 5
12654 | Nuwakot | Samari | 1 | OXFAM-GB | SSS | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 9 | 9 | 2016-05-13 | 2016-06-04 |  | Meghang | 5
12655 | Nuwakot | Samari | 1 | OXFAM-GB | SSS | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 9 | 9 | 2016-05-13 | 2016-06-04 |  | Meghang | 5
12656 | Nuwakot | Samari | 2 | OXFAM-GB | SSS | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 2 | 2 | 2016-05-13 | 2016-06-04 |  | Meghang | 6
12657 | Nuwakot | Samari | 2 | OXFAM-GB | SSS | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 2 | 2 | 2016-05-13 | 2016-06-04 |  | Meghang | 6
12658 | Nuwakot | Samari | 3 | OXFAM-GB | SSS | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-04 |  | Meghang | 6
12659 | Nuwakot | Samari | 3 | OXFAM-GB | SSS | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 7 | 7 | 2016-05-13 | 2016-06-04 |  | Meghang | 6
12660 | Nuwakot | Samari | 4 | OXFAM-GB | SSS | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 4 | 4 | 2016-05-13 | 2016-06-04 |  | Meghang | 5
12661 | Nuwakot | Samari | 4 | OXFAM-GB | SSS | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 4 | 4 | 2016-05-13 | 2016-06-04 |  | Meghang | 5
12662 | Nuwakot | Samari | 5 | OXFAM-GB | SSS | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 10 | 10 | 2016-05-13 | 2016-06-04 |  | Meghang | 6
12663 | Nuwakot | Samari | 5 | OXFAM-GB | SSS | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-05-13 | 2016-06-04 |  | Meghang | 6
12664 | Nuwakot | Samari | 6 | OXFAM-GB | SSS | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 5 | 5 | 2016-05-13 | 2016-06-04 |  | Meghang | 6
12665 | Nuwakot | Samari | 6 | OXFAM-GB | SSS | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 5 | 5 | 2016-05-13 | 2016-06-04 |  | Meghang | 6
12666 | Nuwakot | Samari | 7 | OXFAM-GB | SSS | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 6 | 6 | 2016-05-13 | 2016-06-04 |  | Meghang | 5
12667 | Nuwakot | Samari | 7 | OXFAM-GB | SSS | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-05-13 | 2016-06-04 |  | Meghang | 5
12668 | Nuwakot | Samari | 8 | OXFAM-GB | SSS | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 6 | 6 | 2016-05-13 | 2016-06-04 |  | Meghang | 5
12669 | Nuwakot | Samari | 8 | OXFAM-GB | SSS | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 6 | 6 | 2016-05-13 | 2016-06-04 |  | Meghang | 5
12670 | Nuwakot | Samari | 9 | OXFAM-GB | SSS | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 10 | 10 | 2016-05-13 | 2016-06-04 |  | Meghang | 5
12671 | Nuwakot | Samari | 9 | OXFAM-GB | SSS | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 10 | 10 | 2016-05-13 | 2016-06-04 |  | Meghang | 5
12672 | Nuwakot | Samari | All | OXFAM-GB | SSS | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 30 | 28 | 2017-02-13 | 2017-02-20 |  | Meghang | 6
12673 | Nuwakot | Samari | All | OXFAM-GB | SSS | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 30 | 28 | 2017-02-13 | 2017-02-20 |  | Meghang | 6
12674 | Nuwakot | Samari | All | OXFAM-GB | SSS | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 16 | 14 | 2017-02-26 | 2017-04-17 |  | Meghang | 6
12675 | Nuwakot | Samari | All | OXFAM-GB | SSS | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 16 | 14 | 2017-02-26 | 2017-04-17 |  | Meghang | 6
12676 | Nuwakot | Samari | All | OXFAM-GB | SSS | OXFAM-GB | Technical Assistance | Demonstration Construction | House | Individual House construction from 50 days mason OJT as per CTEVT course | # of constructions | Yes | Planned | 5 | 0 |  |  |  | Meghang | 6
12677 | Nuwakot | Samundratar | 1 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 56 | 56 | 2016-04-02 | 2016-04-02 |  | Dupcheshwar | 6
12678 | Nuwakot | Samundratar | 1 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 2 | 1 | 2016-04-11 | 2016-05-31 |  | Dupcheshwar | 6
12679 | Nuwakot | Samundratar | 2 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 52 | 52 | 2016-04-03 | 2016-04-03 |  | Dupcheshwar | 6
12680 | Nuwakot | Samundratar | 2 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-04-11 | 2016-05-31 |  | Dupcheshwar | 6
12681 | Nuwakot | Samundratar | 2 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-04-11 | 2016-05-31 |  | Dupcheshwar | 6
12682 | Nuwakot | Samundratar | 2 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2015-11-27 | 2015-12-07 |  | Dupcheshwar | 6
12683 | Nuwakot | Samundratar | 3 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 39 | 39 | 2016-04-04 | 2016-04-04 |  | Dupcheshwar | 6
12684 | Nuwakot | Samundratar | 3 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-04-11 | 2016-05-31 |  | Dupcheshwar | 6
12685 | Nuwakot | Samundratar | 3 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-04-11 | 2016-05-31 |  | Dupcheshwar | 6
12686 | Nuwakot | Samundratar | 3 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2015-11-27 | 2015-12-07 |  | Dupcheshwar | 6
12687 | Nuwakot | Samundratar | 4 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 55 | 55 | 2016-04-05 | 2016-04-05 |  | Dupcheshwar | 6
12688 | Nuwakot | Samundratar | 4 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2016-04-11 | 2016-05-31 |  | Dupcheshwar | 6
12689 | Nuwakot | Samundratar | 4 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-04-11 | 2016-05-31 |  | Dupcheshwar | 6
12690 | Nuwakot | Samundratar | 4 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2015-11-27 | 2015-12-07 |  | Dupcheshwar | 6
12691 | Nuwakot | Samundratar | 5 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 63 | 63 | 2016-04-06 | 2016-04-06 |  | Dupcheshwar | 6
12692 | Nuwakot | Samundratar | 5 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2016-04-11 | 2016-05-31 |  | Dupcheshwar | 6
12693 | Nuwakot | Samundratar | 5 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 4 | 4 | 2016-04-11 | 2016-05-31 |  | Dupcheshwar | 6
12694 | Nuwakot | Samundratar | 5 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2015-11-27 | 2015-12-07 |  | Dupcheshwar | 6
12695 | Nuwakot | Samundratar | 6 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 68 | 68 | 2016-04-07 | 2016-04-07 |  | Dupcheshwar | 6
12696 | Nuwakot | Samundratar | 6 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 2 | 1 | 2016-04-11 | 2016-05-31 |  | Dupcheshwar | 6
12697 | Nuwakot | Samundratar | 6 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 4 | 4 | 2016-04-11 | 2016-05-31 |  | Dupcheshwar | 6
12698 | Nuwakot | Samundratar | 6 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2015-11-27 | 2015-12-07 |  | Dupcheshwar | 6
12699 | Nuwakot | Samundratar | 7 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 97 | 97 | 2016-04-08 | 2016-04-08 |  | Dupcheshwar | 6
12700 | Nuwakot | Samundratar | 7 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2016-04-11 | 2016-05-31 |  | Dupcheshwar | 6
12701 | Nuwakot | Samundratar | 7 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 12 | 12 | 2016-04-11 | 2016-05-31 |  | Dupcheshwar | 6
12702 | Nuwakot | Samundratar | 7 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 10 | 10 | 2015-11-27 | 2015-12-07 |  | Dupcheshwar | 6
12703 | Nuwakot | Samundratar | 8 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 80 | 80 | 2016-04-09 | 2016-04-09 |  | Dupcheshwar | 6
12704 | Nuwakot | Samundratar | 8 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-04-11 | 2016-05-31 |  | Dupcheshwar | 6
12705 | Nuwakot | Samundratar | 9 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 35 | 35 | 2016-04-10 | 2016-04-10 |  | Dupcheshwar | 6
12706 | Nuwakot | Samundratar | 9 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-04-11 | 2016-05-31 |  | Dupcheshwar | 6
12707 | Nuwakot | Samundratar | 9 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-04-11 | 2016-05-31 |  | Dupcheshwar | 6
12708 | Nuwakot | Samundratar | 9 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2015-11-27 | 2015-12-07 |  | Dupcheshwar | 6
12709 | Nuwakot | Shikharbesi | All | OXFAM-GB | CARDSN | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 60 | 60 | 2017-02-27 | 2017-03-15 |  | Dupcheshwar | 7
12710 | Nuwakot | Shikharbesi | All | OXFAM-GB | CARDSN | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 60 | 60 | 2017-02-20 | 2017-03-07 |  | Dupcheshwar | 7
12711 | Nuwakot | Shikharbesi | 5 | OXFAM-GB | CARDSN | OXFAM-GB | Training | Retrofitting training | Skilled construction workers | On the Job Training on Retrofitting as per Build Change course | # of trainees | Yes | Completed | 6 | 6 | 2017-10-30 | 2018-12-01 |  | Dupcheshwar | 7
12712 | Nuwakot | Shikharbesi | 6 | OXFAM-GB | CARDSN | OXFAM-GB | Training | Retrofitting training | Skilled construction workers | On the Job Training on Retrofitting as per Build Change course | # of trainees | Yes | Completed | 6 | 6 | 2017-11-01 | 2018-12-01 |  | Dupcheshwar | 7
12713 | Nuwakot | Shikharbesi | 1 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 6 | 2017-10-01 |  |  | Dupcheshwar | 7
12714 | Nuwakot | Shikharbesi | 2 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 6 | 2017-10-01 |  |  | Dupcheshwar | 7
12715 | Nuwakot | Shikharbesi | 3 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 5 | 2017-10-01 |  |  | Dupcheshwar | 7
12716 | Nuwakot | Shikharbesi | 4 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 6 | 2017-10-01 |  |  | Dupcheshwar | 7
12717 | Nuwakot | Shikharbesi | 5 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 5 | 2017-10-01 |  |  | Dupcheshwar | 7
12718 | Nuwakot | Shikharbesi | 6 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 6 | 2017-10-01 |  |  | Dupcheshwar | 7
12719 | Nuwakot | Shikharbesi | 7 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 6 | 2017-10-01 |  |  | Dupcheshwar | 7
12720 | Nuwakot | Shikharbesi | 8 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 5 | 2017-10-01 |  |  | Dupcheshwar | 7
12721 | Nuwakot | Shikharbesi | 9 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Door-to-door technical assistance | Continuous | Door-to-door technical assitance from Mobile Team | # of households | Yes | Ongoing | 80 | 5 | 2017-10-01 |  |  | Dupcheshwar | 7
12722 | Nuwakot | Shikharbesi | 1 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 7
12723 | Nuwakot | Shikharbesi | 2 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 7
12724 | Nuwakot | Shikharbesi | 3 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 7
12725 | Nuwakot | Shikharbesi | 4 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 7
12726 | Nuwakot | Shikharbesi | 5 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 7
12727 | Nuwakot | Shikharbesi | 6 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 7
12728 | Nuwakot | Shikharbesi | 7 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 7
12729 | Nuwakot | Shikharbesi | 8 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 7
12730 | Nuwakot | Shikharbesi | 9 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Support through information center | # of households supported | Yes | Planned | 20 | 0 |  |  |  | Dupcheshwar | 7
12731 | Nuwakot | Shikharbesi | 1 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Planned | 40 | 0 |  |  |  | Dupcheshwar | 7
12732 | Nuwakot | Shikharbesi | 2 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Planned | 40 | 0 |  |  |  | Dupcheshwar | 7
12733 | Nuwakot | Shikharbesi | 3 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Planned | 40 | 0 |  |  |  | Dupcheshwar | 7
12734 | Nuwakot | Shikharbesi | 4 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Planned | 40 | 0 |  |  |  | Dupcheshwar | 7
12735 | Nuwakot | Shikharbesi | 5 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Planned | 40 | 0 |  |  |  | Dupcheshwar | 7
12736 | Nuwakot | Shikharbesi | 6 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Planned | 40 | 0 |  |  |  | Dupcheshwar | 7
12737 | Nuwakot | Shikharbesi | 7 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Planned | 40 | 0 |  |  |  | Dupcheshwar | 7
12738 | Nuwakot | Shikharbesi | 8 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Planned | 40 | 0 |  |  |  | Dupcheshwar | 7
12739 | Nuwakot | Shikharbesi | 9 | OXFAM-GB | CARDSN | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 2.5 hours community orientation per session | # of participants | Yes | Planned | 40 | 0 |  |  |  | Dupcheshwar | 7
12740 | Nuwakot | Shikharbesi | 2 | GON - PAF | CDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 25 | 25 | 2017-05-19 | 2017-05-25 |  | Dupcheshwar | 7
12741 | Nuwakot | Shikharbesi | 4 | GON - PAF | CDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 9 | 9 | 2017-06-24 | 2017-06-30 |  | Dupcheshwar | 7
12742 | Nuwakot | Shikharbesi | 6 | GON - PAF | CDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2017-06-24 | 2017-06-30 |  | Dupcheshwar | 7
12743 | Nuwakot | Shikharbesi | 7 | GON - PAF | CDC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 15 | 15 | 2017-06-24 | 2017-06-30 |  | Dupcheshwar | 7
12744 | Nuwakot | Likhu | 1 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2017-06-24 | 2017-06-30 |  | Shivapuri | 3
12745 | Nuwakot | Likhu | 3 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 17 | 17 | 2017-06-24 | 2017-06-30 |  | Shivapuri | 3
12746 | Nuwakot | Sikre | 1 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 62 | 62 | 2016-04-11 | 2016-04-11 |  | Shivapuri | 4
12747 | Nuwakot | Sikre | 1 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 8 | 8 | 2016-04-11 | 2016-05-31 |  | Shivapuri | 4
12748 | Nuwakot | Sikre | 1 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2016-04-11 | 2016-05-31 |  | Shivapuri | 4
12749 | Nuwakot | Sikre | 1 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2015-11-25 | 2015-12-05 |  | Shivapuri | 4
12750 | Nuwakot | Sikre | 2 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 62 | 62 | 2016-04-12 | 2016-04-12 |  | Shivapuri | 4
12751 | Nuwakot | Sikre | 2 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2016-04-11 | 2016-05-31 |  | Shivapuri | 4
12752 | Nuwakot | Sikre | 2 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-04-11 | 2016-05-31 |  | Shivapuri | 4
12753 | Nuwakot | Sikre | 2 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 4 | 4 | 2015-11-25 | 2015-12-05 |  | Shivapuri | 4
12754 | Nuwakot | Sikre | 2 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (50 days OJT CTEVT) | The training conducted in ward no 8 covering all ward female beneficiaries through demo house of two rooms on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-10-26 | 2016-12-22 |  | Shivapuri | 4
12755 | Nuwakot | Sikre | 3 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 56 | 56 | 2016-04-13 | 2016-04-13 |  | Shivapuri | 4
12756 | Nuwakot | Sikre | 3 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-04-11 | 2016-05-31 |  | Shivapuri | 4
12757 | Nuwakot | Sikre | 3 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 4 | 4 | 2015-11-25 | 2015-12-05 |  | Shivapuri | 4
12758 | Nuwakot | Sikre | 4 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 64 | 64 | 2016-04-14 | 2016-04-14 |  | Shivapuri | 4
12759 | Nuwakot | Sikre | 4 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 4 | 4 | 2016-04-11 | 2016-05-31 |  | Shivapuri | 4
12760 | Nuwakot | Sikre | 4 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 8 | 8 | 2015-11-25 | 2015-12-05 |  | Shivapuri | 4
12761 | Nuwakot | Sikre | 4 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (50 days OJT CTEVT) | The training conducted in ward no 8 covering all ward female beneficiaries through demo house of two rooms on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 7 | 7 | 2016-10-26 | 2016-12-22 |  | Shivapuri | 4
12762 | Nuwakot | Sikre | 5 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 54 | 54 | 2016-04-15 | 2016-04-15 |  | Shivapuri | 4
12763 | Nuwakot | Sikre | 5 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2016-04-11 | 2016-05-31 |  | Shivapuri | 4
12764 | Nuwakot | Sikre | 5 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2016-04-11 | 2016-05-31 |  | Shivapuri | 4
12765 | Nuwakot | Sikre | 5 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2015-11-25 | 2015-12-05 |  | Shivapuri | 4
12766 | Nuwakot | Sikre | 5 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (50 days OJT CTEVT) | The training conducted in ward no 8 covering all ward female beneficiaries through demo house of two rooms on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-10-26 | 2016-12-22 |  | Shivapuri | 4
12767 | Nuwakot | Sikre | 6 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 46 | 46 | 2016-04-16 | 2016-04-16 |  | Shivapuri | 4
12768 | Nuwakot | Sikre | 7 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 60 | 60 | 2016-04-17 | 2016-04-17 |  | Shivapuri | 4
12769 | Nuwakot | Sikre | 7 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-04-11 | 2016-05-31 |  | Shivapuri | 4
12770 | Nuwakot | Sikre | 7 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2016-04-11 | 2016-05-31 |  | Shivapuri | 4
12771 | Nuwakot | Sikre | 7 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2015-11-25 | 2015-12-05 |  | Shivapuri | 4
12772 | Nuwakot | Sikre | 7 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (50 days OJT CTEVT) | The training conducted in ward no 8 covering all ward female beneficiaries through demo house of two rooms on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-10-26 | 2016-12-22 |  | Shivapuri | 4
12773 | Nuwakot | Sikre | 8 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 64 | 64 | 2016-04-18 | 2016-04-18 |  | Shivapuri | 4
12774 | Nuwakot | Sikre | 8 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-04-11 | 2016-05-31 |  | Shivapuri | 4
12775 | Nuwakot | Sikre | 8 | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | 10 days training on the basis of DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2015-11-25 | 2015-12-05 |  | Shivapuri | 4
12776 | Nuwakot | Sikre | 8 | GIZ | GIZ | GIZ | Training | Vocational training | New masons (50 days OJT CTEVT) | The training conducted in ward no 8 covering all ward female beneficiaries through demo house of two rooms on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2016-10-26 | 2016-12-22 |  | Shivapuri | 4
12777 | Nuwakot | Sikre | 9 | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Toolkits are distributed in batch or group | # of households | Yes | Completed | 28 | 28 | 2016-04-19 | 2016-04-19 |  | Shivapuri | 4
12778 | Nuwakot | Sikre | 9 | GIZ | GIZ | GIZ | Training | Short training | Carpenter | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 6 | 6 | 2016-04-11 | 2016-05-31 |  | Shivapuri | 4
12779 | Nuwakot | Sikre | 9 | GIZ | GIZ | GIZ | Training | Short training | Electrician | 25 days training on the basis of CTEVT curriculumn | # of trainees | Yes | Completed | 3 | 3 | 2016-04-11 | 2016-05-31 |  | Shivapuri | 4
12780 | Nuwakot | Sundaradevi | 1 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 4
12781 | Nuwakot | Sundaradevi | 2 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 4
12782 | Nuwakot | Sundaradevi | 3 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 4
12783 | Nuwakot | Sundaradevi | 4 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 4
12784 | Nuwakot | Sundaradevi | 5 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 4
12785 | Nuwakot | Sundaradevi | 6 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 4
12786 | Nuwakot | Sundaradevi | 7 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 4
12787 | Nuwakot | Sundaradevi | 8 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 4
12788 | Nuwakot | Sundaradevi | 9 | EOI |  |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 4
12789 | Nuwakot | Sundaradevi | 1 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 4
12790 | Nuwakot | Sundaradevi | 2 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 4
12791 | Nuwakot | Sundaradevi | 3 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 4
12792 | Nuwakot | Sundaradevi | 4 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 4
12793 | Nuwakot | Sundaradevi | 5 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 4
12794 | Nuwakot | Sundaradevi | 6 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 4
12795 | Nuwakot | Sundaradevi | 7 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 4
12796 | Nuwakot | Sundaradevi | 8 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 4
12797 | Nuwakot | Sundaradevi | 9 | EOI |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 4
12798 | Nuwakot | Sundaradevi | 1 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 84 | 84 | 2016-02-10 | 2016-07-01 |  | Tadi | 4
12799 | Nuwakot | Sundaradevi | 2 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 104 | 104 | 2016-02-10 | 2016-07-01 |  | Tadi | 4
12800 | Nuwakot | Sundaradevi | 3 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 38 | 38 | 2016-02-10 | 2016-07-01 |  | Tadi | 4
12801 | Nuwakot | Sundaradevi | 4 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 72 | 72 | 2016-02-10 | 2016-07-01 |  | Tadi | 4
12802 | Nuwakot | Sundaradevi | 5 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 53 | 53 | 2016-02-10 | 2016-07-01 |  | Tadi | 4
12803 | Nuwakot | Sundaradevi | 6 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 58 | 58 | 2016-02-10 | 2016-07-01 |  | Tadi | 4
12804 | Nuwakot | Sundaradevi | 7 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 51 | 51 | 2016-02-10 | 2016-07-01 |  | Tadi | 4
12805 | Nuwakot | Sundaradevi | 8 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 66 | 66 | 2016-02-10 | 2016-07-01 |  | Tadi | 4
12806 | Nuwakot | Sundaradevi | 9 | WVIN | WVIN | WVIN | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI + tools kit Distribution to HH | # of households | Yes | Completed | 49 | 49 | 2016-02-10 | 2016-07-01 |  | Tadi | 4
12807 | Nuwakot | Suryamati | 2 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 5 | 5 | 2016-05-25 | 2016-06-01 |  | Likhu | 3
12808 | Nuwakot | Suryamati | 3 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-05-25 | 2016-06-01 |  | Likhu | 3
12809 | Nuwakot | Suryamati | 9 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-05-25 | 2016-06-01 |  | Likhu | 3
12810 | Nuwakot | Suryamati | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Likhu | 3
12811 | Nuwakot | Suryamati | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Likhu | 3
12812 | Nuwakot | Suryamati | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Likhu | 3
12813 | Nuwakot | Suryamati | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Likhu | 3
12814 | Nuwakot | Suryamati | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Likhu | 3
12815 | Nuwakot | Suryamati | 6 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Likhu | 3
12816 | Nuwakot | Suryamati | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Likhu | 3
12817 | Nuwakot | Suryamati | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Likhu | 3
12818 | Nuwakot | Suryamati | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 3 | 3 | 2016-01-01 | 2018-12-31 |  | Likhu | 3
12819 | Nuwakot | Suryamati | 3 | GON - PAF | CARDSN | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 25 | 25 | 2017-10-22 | 2017-10-29 |  | Likhu | 3
12820 | Nuwakot | Talakhu | 5 | GON - PAF | RUDEC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2017-07-10 | 2017-07-17 |  | Shivapuri | 1
12821 | Nuwakot | Taruka | 1 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 2
12822 | Nuwakot | Taruka | 2 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 2
12823 | Nuwakot | Taruka | 3 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 2
12824 | Nuwakot | Taruka | 4 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 2
12825 | Nuwakot | Taruka | 5 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 3
12826 | Nuwakot | Taruka | 6 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 3
12827 | Nuwakot | Taruka | 7 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 3
12828 | Nuwakot | Taruka | 8 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 3
12829 | Nuwakot | Taruka | 9 | SCI | CDC | SCI | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 3
12830 | Nuwakot | Taruka | 1 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 7 | 3 | 2016-05-16 | 2016-05-24 |  | Tarakeshwar | 2
12831 | Nuwakot | Taruka | 1 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 7 | 7 | 2016-05-16 | 2016-05-24 |  | Tarakeshwar | 2
12832 | Nuwakot | Taruka | 2 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 5 | 14 | 2016-05-16 | 2016-05-24 |  | Tarakeshwar | 2
12833 | Nuwakot | Taruka | 2 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 5 | 5 | 2016-05-16 | 2016-05-24 |  | Tarakeshwar | 2
12834 | Nuwakot | Taruka | 3 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 1 | 9 | 2016-05-16 | 2016-05-24 |  | Tarakeshwar | 2
12835 | Nuwakot | Taruka | 3 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-05-24 |  | Tarakeshwar | 2
12836 | Nuwakot | Taruka | 4 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 50000 NPR per HH | # of households | Yes | Completed | 68 | 68 | 2016-10-06 | 2016-10-06 |  | Tarakeshwar | 2
12837 | Nuwakot | Taruka | 4 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 NPR per HH | # of households | Yes | Completed | 20 | 20 | 2016-01-30 | 2016-01-30 |  | Tarakeshwar | 2
12838 | Nuwakot | Taruka | 4 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 20 | 2 | 2016-05-16 | 2016-05-24 |  | Tarakeshwar | 2
12839 | Nuwakot | Taruka | 4 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 14 | 14 | 2016-09-20 | 2016-09-26 |  | Tarakeshwar | 2
12840 | Nuwakot | Taruka | 4 | SCI | CDC | SCI | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1 hour per session | # of participants | Yes | Completed | 68 | 59 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 2
12841 | Nuwakot | Taruka | 4 | SCI | CDC | SCI | Technical Assistance | Demonstration Construction | House | Stone masonry in mud mortar, Scaled down demo house in section | # of constructions | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-05-24 |  | Tarakeshwar | 2
12842 | Nuwakot | Taruka | 4 | SCI | CDC | SCI | Technical Assistance | Demonstration Construction | House | Brick masonry in cement motar, Scaled down demo house in section | # of constructions | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-05-24 |  | Tarakeshwar | 2
12843 | Nuwakot | Taruka | 4 | SCI | CDC | SCI | Technical Assistance | Demonstration Construction | House | Composite structure, Scaled down demo house in section | # of constructions | Yes | Completed | 1 | 1 | 2016-09-20 | 2016-09-26 |  | Tarakeshwar | 2
12844 | Nuwakot | Taruka | 4 | SCI | CDC | SCI | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Sub Engineer and Social mobilizer | # of households | Yes | Completed | 68 | 68 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 2
12845 | Nuwakot | Taruka | 4 | SCI | CDC | SCI | Technical Assistance | Household reconstruction orientation | 1 session | 1 hour per session | # of households | Yes | Completed | 68 | 54 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 2
12846 | Nuwakot | Taruka | 4 | SCI | CDC | SCI | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | 68 members in 4 committee | # of committees | Yes | Completed | 4 | 4 | 2016-10-06 | 2016-10-06 |  | Tarakeshwar | 2
12847 | Nuwakot | Taruka | 4 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 20 | 20 | 2016-05-16 | 2016-05-24 |  | Tarakeshwar | 2
12848 | Nuwakot | Taruka | 4 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 14 | 14 | 2016-09-20 | 2016-09-26 |  | Tarakeshwar | 2
12849 | Nuwakot | Taruka | 5 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 4 | 4 | 2016-05-16 | 2016-05-24 |  | Tarakeshwar | 3
12850 | Nuwakot | Taruka | 5 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 4 | 4 | 2016-05-16 | 2016-05-24 |  | Tarakeshwar | 3
12851 | Nuwakot | Taruka | 7 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 11 | 11 | 2016-05-16 | 2016-05-24 |  | Tarakeshwar | 3
12852 | Nuwakot | Taruka | 7 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 11 | 11 | 2016-05-16 | 2016-05-24 |  | Tarakeshwar | 3
12853 | Nuwakot | Taruka | 8 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 2 | 2 | 2016-05-16 | 2016-05-24 |  | Tarakeshwar | 3
12854 | Nuwakot | Taruka | 8 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 2 | 2 | 2016-05-16 | 2016-05-24 |  | Tarakeshwar | 3
12855 | Nuwakot | Taruka | 9 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | 50000 NPR per HH | # of households | Yes | Completed | 32 | 32 | 2016-10-06 | 2016-10-06 |  | Tarakeshwar | 3
12856 | Nuwakot | Taruka | 9 | SCI | CDC | SCI | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | 150000 NPR per HH | # of households | Yes | Completed | 16 | 16 | 2016-01-30 | 2016-01-30 |  | Tarakeshwar | 3
12857 | Nuwakot | Taruka | 9 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-05-24 |  | Tarakeshwar | 3
12858 | Nuwakot | Taruka | 9 | SCI | CDC | SCI | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Toolkits for builders distributed in batch or group | # of kits | Yes | Completed | 16 | 16 | 2016-09-20 | 2016-09-26 |  | Tarakeshwar | 3
12859 | Nuwakot | Taruka | 9 | SCI | CDC | SCI | Technical Assistance | Community reconstruction orientation | 2-3 sessions | 1 hour per session | # of participants | Yes | Completed | 32 | 32 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 3
12860 | Nuwakot | Taruka | 9 | SCI | CDC | SCI | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, Sub Engineer and Social mobilizer | # of households | Yes | Completed | 32 | 32 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 3
12861 | Nuwakot | Taruka | 9 | SCI | CDC | SCI | Technical Assistance | Household reconstruction orientation | 1 session | 1 hour per session | # of households | Yes | Completed | 32 | 32 | 2016-10-06 | 2017-11-30 |  | Tarakeshwar | 3
12862 | Nuwakot | Taruka | 9 | SCI | CDC | SCI | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | 32 members in 3 committee | # of committees | Yes | Completed | 3 | 3 | 2016-10-06 | 2016-10-06 |  | Tarakeshwar | 3
12863 | Nuwakot | Taruka | 9 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-05-24 |  | Tarakeshwar | 3
12864 | Nuwakot | Taruka | 9 | SCI | CDC | SCI | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days existing masons training on the basis of DUDBC Curriculum | # of trainees | Yes | Completed | 16 | 16 | 2016-09-20 | 2016-09-26 |  | Tarakeshwar | 3
12865 | Nuwakot | Thansing | 5 | GON - PAF | CARDSN | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 25 | 25 | 2016-09-22 | 2016-09-29 |  | Likhu | 5
12866 | Nuwakot | Thaprek | 1 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-05-25 | 2016-06-01 |  | Panchakanya | 4
12867 | Nuwakot | Thaprek | 3 | OXFAM-GB | KCDC | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 1 | 1 | 2017-01-01 | 2017-03-03 |  | Panchakanya | 4
12868 | Nuwakot | Thaprek | 4 | OXFAM-GB | KCDC | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 1 | 1 | 2017-01-01 | 2017-03-03 |  | Panchakanya | 4
12869 | Nuwakot | Thaprek | 1 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 57 | 2017-02-16 | 2017-02-16 |  | Panchakanya | 4
12870 | Nuwakot | Thaprek | 2 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 63 | 2017-02-20 | 2017-02-20 |  | Panchakanya | 4
12871 | Nuwakot | Thaprek | 3 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 61 | 2017-02-26 | 2017-02-26 |  | Panchakanya | 4
12872 | Nuwakot | Thaprek | 4 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 67 | 2017-02-17 | 2017-02-17 |  | Panchakanya | 4
12873 | Nuwakot | Thaprek | 5 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 65 | 2016-09-01 | 2016-09-01 |  | Panchakanya | 4
12874 | Nuwakot | Thaprek | 6 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 50 | 2017-02-20 | 2017-02-20 |  | Panchakanya | 4
12875 | Nuwakot | Thaprek | 7 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 59 | 2016-11-01 | 2016-11-01 |  | Panchakanya | 4
12876 | Nuwakot | Thaprek | 8 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 50 | 2016-11-01 | 2016-11-01 |  | Panchakanya | 4
12877 | Nuwakot | Thaprek | 9 | OXFAM-GB | KCDC | OXFAM-GB | Technical Assistance | Community reconstruction orientation | 1 session | 2.5 hours community orientation per session | # of participants | Yes | Completed | 50 | 60 | 2016-11-02 | 2016-11-02 |  | Panchakanya | 4
12878 | Nuwakot | Thaprek | 5 | OXFAM-GB | KCDC | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 2 | 2 | 2017-01-01 | 2017-03-03 |  | Panchakanya | 4
12879 | Nuwakot | Thaprek | 7 | OXFAM-GB | KCDC | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 4 | 4 | 2017-01-01 | 2017-03-03 |  | Panchakanya | 4
12880 | Nuwakot | Thaprek | 8 | OXFAM-GB | KCDC | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 3 | 3 | 2017-01-01 | 2017-03-03 |  | Panchakanya | 4
12881 | Nuwakot | Thaprek | 9 | OXFAM-GB | KCDC | OXFAM-GB | Training | Vocational training | New masons (50 days OJT CTEVT) | 50 days mason OJT as per CTEVT course | # of trainees | Yes | Completed | 5 | 5 | 2017-01-01 | 2017-03-03 |  | Panchakanya | 4
12882 | Nuwakot | Thaprek | All | OXFAM-GB | KCDC | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of Masons training (7 days DUDBC, rural) | # of kits | Yes | Completed | 60 | 60 | 2016-11-17 | 2016-12-31 |  | Panchakanya | 4
12883 | Nuwakot | Thaprek | All | OXFAM-GB | KCDC | OXFAM-GB | Training | Short training | Masons (7 days DUDBC, rural or urban) | Masons (7 days DUDBC, rural) | # of trainees | Yes | Completed | 60 | 60 | 2016-11-17 | 2016-12-31 |  | Panchakanya | 4
12884 | Nuwakot | Thaprek | All | OXFAM-GB | KCDC | OXFAM-GB | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Tool kit for each participant of 50 days On the Job training | # of kits | Yes | Completed | 16 | 16 | 2017-01-01 | 2017-03-03 |  | Panchakanya | 4
12885 | Nuwakot | Tupche | 1 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 4 | 4 | 2016-06-17 | 2016-06-23 |  | Bidur | 7
12886 | Nuwakot | Tupche | 5 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 |  | Bidur | 7
12887 | Nuwakot | Tupche | 6 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 |  | Bidur | 8
12888 | Nuwakot | Tupche | 7 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 |  | Bidur | 7
12889 | Nuwakot | Tupche | 8 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 1 | 1 | 2016-06-17 | 2016-06-23 |  | Bidur | 8
12890 | Nuwakot | Tupche | 9 | ACF | ITDSN | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) | 7 days short training skilled mason according to DUDBC curriculumn | # of trainees | Yes | Completed | 2 | 2 | 2016-06-17 | 2016-06-23 |  | Bidur | 9
12891 | Nuwakot | Tupche | 6 | HFH | ASF | HFH | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Planned | 0 | 0 |  |  |  | Bidur | 8
12892 | Nuwakot | Tupche | 6 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-01-01 | 2017-11-30 |  | Bidur | 8
12893 | Nuwakot | Tupche | 6 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | 1 technical site supervisor, 2 social mobilizers | # of households | Yes | Ongoing | 143 | 143 | 2016-11-01 |  |  | Bidur | 8
12894 | Nuwakot | Tupche | 6 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 1 | 1 | 2016-11-01 | 2017-11-30 |  | Bidur | 8
12895 | Nuwakot | Tupche | 6 | HFH | ASF | HFH | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Ongoing | 143 | 143 | 2016-11-01 |  |  | Bidur | 8
12896 | Nuwakot | Tupche | 6 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-11-10 | 2016-11-16 |  | Bidur | 8
12897 | Nuwakot | Tupche | 6 | HFH | ASF | HFH | Training | Short training | Social mobilizer | Conducted PASSA training | # of trainees | Yes | Completed | 1 | 1 | 2016-10-01 | 2016-10-31 |  | Bidur | 8
12898 | Nuwakot | Tupche | 8 | HFH | ASF | HFH | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Planned | 0 | 0 |  |  |  | Bidur | 8
12899 | Nuwakot | Tupche | 8 | HFH | ASF | HFH | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-01-01 | 2017-11-30 |  | Bidur | 8
12900 | Nuwakot | Tupche | 8 | HFH | ASF | HFH | Technical Assistance | Door-to-door technical assistance | Continuous | 1 technical site supervisor, 2 social mobilizers | # of households | Yes | Ongoing | 77 | 77 | 2016-11-01 |  |  | Bidur | 8
12901 | Nuwakot | Tupche | 8 | HFH | ASF | HFH | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 1 | 1 | 2016-11-01 | 2017-11-30 |  | Bidur | 8
12902 | Nuwakot | Tupche | 8 | HFH | ASF | HFH | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Ongoing | 77 | 77 | 2016-11-01 |  |  | Bidur | 8
12903 | Nuwakot | Tupche | 8 | HFH | ASF | HFH | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-11-10 | 2016-11-16 |  | Bidur | 8
12904 | Nuwakot | Tupche | 8 | HFH | ASF | HFH | Training | Short training | Social mobilizer | Conducted PASSA training | # of trainees | Yes | Completed | 1 | 1 | 2016-10-01 | 2016-10-31 |  | Bidur | 8
12905 | Nuwakot | Tupche | 1 | HFH | ASF | HFH | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 60 | 60 | 2016-06-01 | 2017-11-30 |  | Bidur | 7
12906 | Nuwakot | Tupche | 2 | HFH |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Planned | 0 | 0 |  |  |  | Bidur | 7
12907 | Nuwakot | Urleni | 1 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 4 | 4 | 2016-01-01 | 2018-12-31 |  | Tadi | 1
12908 | Nuwakot | Urleni | 2 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Tadi | 1
12909 | Nuwakot | Urleni | 3 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Tadi | 1
12910 | Nuwakot | Urleni | 4 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Tadi | 1
12911 | Nuwakot | Urleni | 5 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Tadi | 1
12912 | Nuwakot | Urleni | 6 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Tadi | 1
12913 | Nuwakot | Urleni | 7 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Tadi | 1
12914 | Nuwakot | Urleni | 8 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Tadi | 1
12915 | Nuwakot | Urleni | 9 | NRCS | NRCS | ARC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees | Yes | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Tadi | 1
12916 | Nuwakot | Urleni | 1 | OXFAM-GB | OXFAM-GB | OXFAM-GB | Reconstruction through contractors | Construction | Private house | Housing construction for resettlement | # of constructions | Yes | Ongoing | 73 | 0 | 2017-12-01 |  |  | Tadi | 1
12917 | Nuwakot | Deurali | 3 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Resource center | # of households supported | Yes | Ongoing | 300 | 41 | 2017-02-26 |  |  | Meghang | 3
12918 | Nuwakot | Kaule | 3 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Resource center | # of households supported | Yes | Ongoing | 300 | 333 | 2017-02-26 |  |  | Kispang | 3
12919 | Nuwakot | Gorsyang | 2 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Resource center | # of households supported | Yes | Ongoing | 300 | 3 | 2017-02-26 |  |  | Tarakeshwar | 5
12920 | Nuwakot | Kharanitar | 1 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Resource center | # of households supported | Yes | Ongoing | 300 | 84 | 2017-02-26 |  |  | Tadi | 3
12921 | Nuwakot | Sundaradevi | 2 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Resource center | # of households supported | Yes | Ongoing | 300 | 287 | 2017-02-26 |  |  | Tadi | 4
12922 | Nuwakot | Chhap | 1 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Resource center | # of households supported | Yes | Ongoing | 300 | 0 | 2017-02-26 |  |  | Shivapuri | 2
12923 | Nuwakot | Dangsing | 1 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Resource center | # of households supported | Yes | Ongoing | 300 | 3 | 2017-02-26 |  |  | Tarakeshwar | 1
12924 | Nuwakot | Kakani | 5 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Resource center | # of households supported | Yes | Ongoing | 300 | 3 | 2017-02-26 |  |  | Kakani | 4
12925 | Nuwakot | Belkot | 9 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Resource center | # of households supported | Yes | Ongoing | 300 | 17 | 2017-02-26 |  |  | Belkotgadhi | 1
12926 | Nuwakot | Thansing | 6 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Resource center | # of households supported | Yes | Ongoing | 300 | 12 | 2017-02-26 |  |  | Likhu | 5
12927 | Nuwakot | Thaprek | 4 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Resource center | # of households supported | Yes | Ongoing | 300 | 165 | 2017-11-01 |  |  | Panchakanya | 4
12928 | Nuwakot | BagesworiChokade | 3 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Resource center | # of households supported | Yes | Ongoing | 300 | 31 | 2017-12-01 |  |  | Suryagadhi | 3
12929 | Nuwakot | Samari | 6 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Stone cutting enterprise | # of households supported | Yes | Ongoing | 30 | 2 | 2017-02-28 |  |  | Meghang | 6
12930 | Nuwakot | Kalyanpur | 6 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Stone cutting enterprise | # of households supported | Yes | Ongoing | 30 | 8 | 2017-11-01 |  |  | Bidur | 13
12931 | Nuwakot | Salme | 4 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Stone cutting enterprise | # of households supported | Yes | Ongoing | 30 | 3 | 2017-03-03 |  |  | Kispang | 4
12932 | Nuwakot | Dangsing | 1 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Stone cutting enterprise | # of households supported | Yes | Ongoing | 30 | 1 | 2017-03-03 |  |  | Tarakeshwar | 1
12933 | Nuwakot | Belkot | 2 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Stone cutting enterprise | # of households supported | Yes | Ongoing | 30 | 0 | 2018-01-01 |  |  | Belkotgadhi | 10
12934 | Nuwakot | Lachyang | 3 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Stone cutting enterprise | # of households supported | Yes | Ongoing | 30 | 3 | 2017-11-01 |  |  | Suryagadhi | 1
12935 | Nuwakot | Gorsyang | 5 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB enterprise | # of households supported | Yes | Ongoing | 30 | 8 | 2017-02-09 |  |  | Tarakeshwar | 5
12936 | Nuwakot | Kakani | 5 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB enterprise | # of households supported | Yes | Ongoing | 30 | 33 | 2017-04-18 |  |  | Kakani | 4
12937 | Nuwakot | Belkot | 9 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB enterprise | # of households supported | Yes | Ongoing | 30 | 3 | 2017-09-01 |  |  | Belkotgadhi | 1
12938 | Nuwakot | Bidur N.P. | 5 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB enterprise | # of households supported | Yes | Ongoing | 30 | 32 | 2017-02-01 |  |  | Bidur | 5
12939 | Nuwakot | Kaule | 3 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB enterprise | # of households supported | Yes | Ongoing | 30 | 18 | 2017-04-18 |  |  | Kispang | 3
12940 | Nuwakot | Deurali | 3 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB enterprise | # of households supported | Yes | Ongoing | 30 | 27 | 2017-05-19 |  |  | Meghang | 3
12941 | Nuwakot | Ralukadevi | 3 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB enterprise | # of households supported | Yes | Ongoing | 30 | 8 | 2018-01-01 |  |  | Tadi | 2
12942 | Nuwakot | Thaprek | 4 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB enterprise | # of households supported | Yes | Ongoing | 30 | 12 | 2017-10-09 |  |  | Panchakanya | 4
12943 | Nuwakot | Ghyangphedi | 1 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB enterprise | # of households supported | Yes | Ongoing | 30 | 8 | 2017-11-01 |  |  | Dupcheshwar | 1
12944 | Nuwakot | Gerkhu | 3 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB enterprise | # of households supported | Yes | Ongoing | 30 | 2 | 2018-01-01 |  |  | Bidur | 10
12945 | Nuwakot | Tupche | 1 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB enterprise | # of households supported | Yes | Ongoing | 30 | 2 | 2017-12-01 |  |  | Bidur | 7
12946 | Nuwakot | Kakani | 5 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB enterprise | # of households supported | Yes | Ongoing | 30 | 2 | 2017-12-01 |  |  | Kakani | 4
12947 | Nuwakot | Manakamana | 5 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB enterprise | # of households supported | Yes | Ongoing | 30 | 12 | 2017-09-01 |  |  | Kispang | 5
12948 | Nuwakot | Chaughada | 4 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB enterprise | # of households supported | Yes | Ongoing | 30 | 5 | 2017-10-01 |  |  | Panchakanya | 1
12949 | Nuwakot | Samundratar | 6 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB enterprise | # of households supported | Yes | Ongoing | 30 | 0 | 2018-03-01 |  |  | Dupcheshwar | 6
12950 | Nuwakot | Bidur N.P. | 5 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB modal house | # of households supported | Yes | Ongoing | 1 | 1 | 2017-09-01 |  |  | Bidur | 5
12951 | Nuwakot | Gorsyang | 5 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB modal house | # of households supported | Yes | Ongoing | 1 | 1 | 2017-09-13 |  |  | Tarakeshwar | 5
12952 | Nuwakot | Fikuri | 6 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB modal house | # of households supported | Yes | Ongoing | 1 | 1 | 2017-10-15 |  |  | Kispang | 2
12953 | Nuwakot | Deurali | 3 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB modal house | # of households supported | Yes | Ongoing | 1 | 1 | 2017-10-14 |  |  | Meghang | 3
12954 | Nuwakot | Ghyangphedi | 1 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB modal house | # of households supported | Yes | Ongoing | 1 | 1 | 2017-09-13 |  |  | Dupcheshwar | 1
12955 | Nuwakot | Ralukadevi | 3 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB modal house | # of households supported | Yes | Ongoing | 1 | 1 | 2017-10-15 |  |  | Tadi | 2
12956 | Nuwakot | Tupche | 1 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB modal house | # of households supported | Yes | Ongoing | 1 | 1 | 2017-10-14 |  |  | Bidur | 7
12957 | Nuwakot | Kakani | 5 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | CSEB modal house | # of households supported | Yes | Ongoing | 1 | 1 | 2017-09-13 |  |  | Kakani | 4
12958 | Nuwakot | Narjamandap | 5 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Timber Treatment Plant | # of households supported | Yes | Ongoing | 30 | 56 | 2017-08-09 |  |  | Tadi | 6
12959 | Nuwakot | Thansing | 6 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Timber Treatment Plant | # of households supported | Yes | Ongoing | 30 | 37 | 2017-03-01 |  |  | Likhu | 5
12960 | Nuwakot | Belkot | 1 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Timber Treatment Plant | # of households supported | Yes | Ongoing | 30 | 23 | 2017-04-15 |  |  | Belkotgadhi | 10
12961 | Nuwakot | Charghare | 3 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Timber Treatment Plant | # of households supported | Yes | Ongoing | 30 | 16 | 2017-03-01 |  |  | Bidur | 12
12962 | Nuwakot | Bhalche | 1 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Timber Treatment Plant | # of households supported | Yes | Ongoing | 30 | 18 | 2017-04-15 |  |  | Kispang | 1
12963 | Nuwakot | Bidur N.P. | 1 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Timber Treatment Plant | # of households supported | Yes | Ongoing | 30 | 13 | 2017-03-01 |  |  | Bidur | 1
12964 | Nuwakot | Bidur N.P. | 4 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Gitti Production | # of households supported | Yes | Ongoing | 30 | 57 | 2017-09-01 |  |  | Bidur | 4
12965 | Nuwakot | Bidur N.P. | 9 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Gitti Production | # of households supported | Yes | Ongoing | 30 | 59 | 2017-09-13 |  |  | Bidur | 9
12966 | Nuwakot | Bidur N.P. | 1 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Gitti Production | # of households supported | Yes | Ongoing | 30 | 57 | 2017-10-15 |  |  | Bidur | 1
12967 | Nuwakot | Bidur N.P. | 9 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Gitti Production | # of households supported | Yes | Ongoing | 30 | 48 | 2017-10-14 |  |  | Bidur | 9
12968 | Nuwakot | Kalyanpur | 6 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Gitti Production | # of households supported | Yes | Ongoing | 30 | 64 | 2017-09-13 |  |  | Bidur | 13
12969 | Nuwakot | Samari | 6 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Gitti Production | # of households supported | Yes | Ongoing | 30 | 82 | 2017-10-15 |  |  | Meghang | 6
12970 | Nuwakot | Samari | 6 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Gitti Production | # of households supported | Yes | Ongoing | 30 | 83 | 2017-10-14 |  |  | Meghang | 6
12971 | Nuwakot | Manakamana | 5 | PA | SSS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Gitti Production | # of households supported | Yes | Ongoing | 30 | 74 | 2017-09-13 |  |  | Kispang | 5
12972 | Nuwakot | Bidur N.P. | 5 | PA | SSS | DFID | Training | Other trainings | Other trainings (specify in Activity Detail) | CSEB block building and model house building, 30 days training | # of households supported | Yes | Completed | 10 | 10 | 2017-08-11 | 2017-09-09 |  | Bidur | 5
12973 | Nuwakot | Gorsyang | 4 | PA | SSS | DFID | Training | Other trainings | Other trainings (specify in Activity Detail) | CSEB block building and model house building, 30 days training | # of households supported | Yes | Completed | 10 | 10 | 2017-06-14 | 2017-07-13 |  | Tarakeshwar | 5
12974 | Nuwakot | Ghyangphedi | 1 | PA | SSS | DFID | Training | Other trainings | Other trainings (specify in Activity Detail) | CSEB block building and model house building, 30 days training | # of households supported | Yes | Completed | 10 | 10 | 2017-11-25 | 2017-12-25 |  | Dupcheshwar | 1
12975 | Nuwakot | Ralukadevi | 2 | PA | SSS | DFID | Training | Other trainings | Other trainings (specify in Activity Detail) | CSEB block building and model house building, 30 days training | # of households supported | Yes | Completed | 10 | 10 | 2017-11-26 | 2017-12-26 |  | Tadi | 2
12976 | Nuwakot | Kakani | 5 | PA | SSS | DFID | Training | Other trainings | Other trainings (specify in Activity Detail) | CSEB block building and model house building, 30 days training | # of households supported | Yes | Completed | 10 | 10 | 2017-09-02 | 2017-10-02 |  | Kakani | 4
12977 | Nuwakot | Fikuri | 2 | PA | SSS | DFID | Training | Other trainings | Other trainings (specify in Activity Detail) | CSEB block building and model house building, 30 days training | # of households supported | Yes | Completed | 10 | 10 | 2017-10-15 | 2017-11-15 |  | Kispang | 2
12978 | Nuwakot | Deurali | 3 | PA | SSS | DFID | Training | Other trainings | Other trainings (specify in Activity Detail) | CSEB block building and model house building, 30 days training | # of households supported | Yes | Completed | 10 | 10 | 2017-10-16 | 2017-11-16 |  | Meghang | 3
12979 | Nuwakot | Bidur N.P. | 5 | PA | SSS | DFID | Training | Other trainings | Other trainings (specify in Activity Detail) | CSEB block building and model house building, 30 days training | # of households supported | Yes | Completed | 10 | 10 | 2017-11-26 | 2017-12-25 |  | Bidur | 5
12980 | Nuwakot | Belkot | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 10
12981 | Nuwakot | Belkot | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 10
12982 | Nuwakot | Belkot | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 10
12983 | Nuwakot | Belkot | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 10
12984 | Nuwakot | Belkot | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 10
12985 | Nuwakot | Belkot | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 10
12986 | Nuwakot | Belkot | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 1
12987 | Nuwakot | Belkot | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 1
12988 | Nuwakot | Belkot | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 11
12989 | Nuwakot | Belkot | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 11
12990 | Nuwakot | Belkot | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 11
12991 | Nuwakot | Belkot | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 11
12992 | Nuwakot | Belkot | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 11
12993 | Nuwakot | Belkot | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 11
12994 | Nuwakot | Belkot | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 11
12995 | Nuwakot | Belkot | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 11
12996 | Nuwakot | Belkot | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 1
12997 | Nuwakot | Belkot | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 1
12998 | Nuwakot | Betini | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 4
12999 | Nuwakot | Betini | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 4
13000 | Nuwakot | Betini | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 4
13001 | Nuwakot | Betini | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 4
13002 | Nuwakot | Betini | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 4
13003 | Nuwakot | Betini | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 4
13004 | Nuwakot | Betini | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 4
13005 | Nuwakot | Betini | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 4
13006 | Nuwakot | Betini | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 4
13007 | Nuwakot | Betini | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 4
13008 | Nuwakot | Betini | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 4
13009 | Nuwakot | Betini | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 4
13010 | Nuwakot | Betini | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 4
13011 | Nuwakot | Betini | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 4
13012 | Nuwakot | Betini | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 4
13013 | Nuwakot | Betini | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 4
13014 | Nuwakot | Betini | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 4
13015 | Nuwakot | Betini | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 4
13016 | Nuwakot | Bhadratar | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 5
13017 | Nuwakot | Bhadratar | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 5
13018 | Nuwakot | Bhadratar | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 5
13019 | Nuwakot | Bhadratar | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 5
13020 | Nuwakot | Bhadratar | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 5
13021 | Nuwakot | Bhadratar | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 5
13022 | Nuwakot | Bhadratar | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 5
13023 | Nuwakot | Bhadratar | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 5
13024 | Nuwakot | Bhadratar | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 5
13025 | Nuwakot | Bhadratar | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 5
13026 | Nuwakot | Bhadratar | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 5
13027 | Nuwakot | Bhadratar | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 5
13028 | Nuwakot | Bhadratar | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 5
13029 | Nuwakot | Bhadratar | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 5
13030 | Nuwakot | Bhadratar | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 5
13031 | Nuwakot | Bhadratar | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 5
13032 | Nuwakot | Bhadratar | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 5
13033 | Nuwakot | Bhadratar | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 5
13034 | Nuwakot | Bhalche | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 1
13035 | Nuwakot | Bhalche | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 1
13036 | Nuwakot | Bhalche | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 1
13037 | Nuwakot | Bhalche | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 1
13038 | Nuwakot | Bhalche | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 1
13039 | Nuwakot | Bhalche | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 1
13040 | Nuwakot | Bhalche | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 1
13041 | Nuwakot | Bhalche | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 1
13042 | Nuwakot | Bhalche | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 1
13043 | Nuwakot | Bhalche | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 1
13044 | Nuwakot | Bhalche | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 1
13045 | Nuwakot | Bhalche | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 1
13046 | Nuwakot | Bhalche | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 1
13047 | Nuwakot | Bhalche | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 1
13048 | Nuwakot | Bhalche | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 1
13049 | Nuwakot | Bhalche | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 1
13050 | Nuwakot | Bhalche | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 1
13051 | Nuwakot | Bhalche | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 1
13052 | Nuwakot | Bidur N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 840 | 288 | 2015-10-01 | 2017-03-30 |  | Bidur | 1
13053 | Nuwakot | Bidur N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 280 | 7 | 2015-10-01 | 2017-03-30 |  | Bidur | 1
13054 | Nuwakot | Bidur N.P. | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 280 | 68 | 2015-10-01 | 2017-03-30 |  | Bidur | 1
13055 | Nuwakot | Bidur N.P. | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 4 | 2015-10-01 | 2017-03-30 |  | Bidur | 1
13056 | Nuwakot | Bidur N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 840 | 198 | 2015-10-01 | 2017-03-30 |  | Bidur | 2
13057 | Nuwakot | Bidur N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 312 | 3 | 2015-10-01 | 2017-03-30 |  | Bidur | 2
13058 | Nuwakot | Bidur N.P. | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 312 | 66 | 2015-10-01 | 2017-03-30 |  | Bidur | 2
13059 | Nuwakot | Bidur N.P. | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 1 | 2015-10-01 | 2017-03-30 |  | Bidur | 2
13060 | Nuwakot | Bidur N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 840 | 270 | 2015-10-01 | 2017-03-30 |  | Bidur | 2
13061 | Nuwakot | Bidur N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 442 | 16 | 2015-10-01 | 2017-03-30 |  | Bidur | 2
13062 | Nuwakot | Bidur N.P. | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 442 | 199 | 2015-10-01 | 2017-03-30 |  | Bidur | 2
13063 | Nuwakot | Bidur N.P. | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 51 | 2015-10-01 | 2017-03-30 |  | Bidur | 2
13064 | Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 840 | 327 | 2015-10-01 | 2017-03-30 |  | Bidur | 4
13065 | Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 347 | 13 | 2015-10-01 | 2017-03-30 |  | Bidur | 4
13066 | Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 347 | 278 | 2015-10-01 | 2018-03-30 |  | Bidur | 4
13067 | Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Training | Other trainings | Other trainings (specify in Activity Detail) |  | # of trainees | Yes | Completed | 96 | 149 | 2015-10-01 | 2018-03-30 |  | Bidur | 4
13068 | Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Training | ToT | Social mobilizer (curriculum, specify in comment) |  | # of trainees | Yes | Completed | 45 | 28 | 2017-06-20 | 2017-06-24 |  | Bidur | 4
13069 | Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Training | Retrofitting training | Engineers, sub-engineers |  | # of trainees | Yes | Completed | 32 | 27 | 2018-04-25 | 2018-04-27 |  | Bidur | 4
13070 | Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 27 | 2015-10-01 | 2017-03-30 |  | Bidur | 4
13071 | Nuwakot | Bidur N.P. | 4 | NSET | NSET | USAID | Training | ToT | Engineers, sub engineers (7 days DUDBC) |  | # of trainees | Yes | Completed | 384 | 329 | 2015-10-01 | 2018-04-26 |  | Bidur | 4
13072 | Nuwakot | Bidur N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 840 | 357 | 2015-10-01 | 2017-03-30 |  | Bidur | 5
13073 | Nuwakot | Bidur N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 503 | 10 | 2015-10-01 | 2017-03-30 |  | Bidur | 5
13074 | Nuwakot | Bidur N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 503 | 125 | 2015-10-01 | 2017-03-30 |  | Bidur | 5
13075 | Nuwakot | Bidur N.P. | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 41 | 2015-10-01 | 2017-03-30 |  | Bidur | 5
13076 | Nuwakot | Bidur N.P. | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 3 | 2015-10-01 | 2017-03-30 |  | Bidur | 5
13077 | Nuwakot | Bidur N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 840 | 328 | 2015-10-01 | 2017-03-30 |  | Bidur | 6
13078 | Nuwakot | Bidur N.P. | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-10-01 | 2017-03-30 |  | Bidur | 5
13079 | Nuwakot | Bidur N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 326 | 13 | 2015-10-01 | 2017-03-30 |  | Bidur | 6
13080 | Nuwakot | Bidur N.P. | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 326 | 78 | 2015-10-01 | 2017-03-30 |  | Bidur | 6
13081 | Nuwakot | Bidur N.P. | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 13 | 2015-10-01 | 2017-03-30 |  | Bidur | 6
13082 | Nuwakot | Bidur N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 840 | 377 | 2015-10-01 | 2017-03-30 |  | Bidur | 5
13083 | Nuwakot | Bidur N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 395 | 4 | 2015-10-01 | 2017-03-30 |  | Bidur | 5
13084 | Nuwakot | Bidur N.P. | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 395 | 89 | 2015-10-01 | 2017-03-30 |  | Bidur | 5
13085 | Nuwakot | Bidur N.P. | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 32 | 2015-10-01 | 2017-03-30 |  | Bidur | 5
13086 | Nuwakot | Bidur N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 840 | 449 | 2015-10-01 | 2017-03-30 |  | Bidur | 8
13087 | Nuwakot | Bidur N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 660 | 19 | 2015-10-01 | 2017-03-30 |  | Bidur | 8
13088 | Nuwakot | Bidur N.P. | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 660 | 98 | 2015-10-01 | 2017-03-30 |  | Bidur | 8
13089 | Nuwakot | Bidur N.P. | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 14 | 2015-10-01 | 2017-03-30 |  | Bidur | 8
13090 | Nuwakot | Bidur N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 840 | 399 | 2015-10-01 | 2017-03-30 |  | Bidur | 9
13091 | Nuwakot | Bidur N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 725 | 31 | 2015-10-01 | 2017-03-30 |  | Bidur | 9
13092 | Nuwakot | Bidur N.P. | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 725 | 58 | 2015-10-01 | 2017-03-30 |  | Bidur | 9
13093 | Nuwakot | Bidur N.P. | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 68 | 2015-10-01 | 2017-03-30 |  | Bidur | 9
13094 | Nuwakot | Bidur N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 840 | 46 | 2015-10-01 | 2017-03-30 |  | Bidur | 1
13095 | Nuwakot | Bidur N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 131 | 2 | 2015-10-01 | 2017-03-30 |  | Bidur | 1
13096 | Nuwakot | Bidur N.P. | 10 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 131 | 44 | 2015-10-01 | 2017-03-30 |  | Bidur | 1
13097 | Nuwakot | Bidur N.P. | 10 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 3 | 2015-10-01 | 2017-03-30 |  | Bidur | 1
13098 | Nuwakot | Bidur N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Completed | 840 | 1 | 2015-10-01 | 2017-03-30 |  | Bidur | 1
13099 | Nuwakot | Bidur N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 59 | 1 | 2015-10-01 | 2017-03-30 |  | Bidur | 1
13100 | Nuwakot | Bidur N.P. | 11 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Completed | 59 | 69 | 2015-10-01 | 2017-03-30 |  | Bidur | 1
13101 | Nuwakot | Bidur N.P. | 11 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 1 | 2015-10-01 | 2017-03-30 |  | Bidur | 1
13102 | Nuwakot | Budhasing | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 4
13103 | Nuwakot | Budhasing | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 4
13104 | Nuwakot | Budhasing | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 4
13105 | Nuwakot | Budhasing | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 4
13106 | Nuwakot | Budhasing | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 4
13107 | Nuwakot | Budhasing | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 4
13108 | Nuwakot | Budhasing | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 4
13109 | Nuwakot | Budhasing | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 4
13110 | Nuwakot | Budhasing | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 4
13111 | Nuwakot | Budhasing | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 4
13112 | Nuwakot | Budhasing | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 4
13113 | Nuwakot | Budhasing | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 4
13114 | Nuwakot | Budhasing | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 4
13115 | Nuwakot | Budhasing | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 4
13116 | Nuwakot | Budhasing | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 4
13117 | Nuwakot | Budhasing | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 4
13118 | Nuwakot | Budhasing | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 1
13119 | Nuwakot | Budhasing | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 1
13120 | Nuwakot | Charghare | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 6
13121 | Nuwakot | Charghare | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 6
13122 | Nuwakot | Charghare | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 6
13123 | Nuwakot | Charghare | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 6
13124 | Nuwakot | Charghare | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 12
13125 | Nuwakot | Charghare | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 12
13126 | Nuwakot | Charghare | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 12
13127 | Nuwakot | Charghare | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 12
13128 | Nuwakot | Charghare | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 12
13129 | Nuwakot | Charghare | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 12
13130 | Nuwakot | Charghare | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 12
13131 | Nuwakot | Charghare | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 12
13132 | Nuwakot | Charghare | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 12
13133 | Nuwakot | Charghare | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 12
13134 | Nuwakot | Charghare | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 12
13135 | Nuwakot | Charghare | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 12
13136 | Nuwakot | Charghare | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 12
13137 | Nuwakot | Charghare | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 12
13138 | Nuwakot | Chaturale | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 321 | 2015-10-01 |  |  | Kakani | 7
13139 | Nuwakot | Chaturale | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 7
13140 | Nuwakot | Chaturale | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 105 | 72 | 2015-10-01 |  |  | Kakani | 7
13141 | Nuwakot | Chaturale | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 105 | 20 | 2015-10-01 |  |  | Kakani | 7
13142 | Nuwakot | Chaturale | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 10 | 2015-10-01 |  |  | Kakani | 7
13143 | Nuwakot | Chaturale | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 7
13144 | Nuwakot | Chaturale | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 143 | 2015-10-01 |  |  | Kakani | 7
13145 | Nuwakot | Chaturale | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 7
13146 | Nuwakot | Chaturale | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 86 | 79 | 2015-10-01 |  |  | Kakani | 7
13147 | Nuwakot | Chaturale | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 86 | 14 | 2015-10-01 |  |  | Kakani | 7
13148 | Nuwakot | Chaturale | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 19 | 2015-10-01 |  |  | Kakani | 7
13149 | Nuwakot | Chaturale | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 7
13150 | Nuwakot | Chaturale | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 374 | 2015-10-01 |  |  | Kakani | 7
13151 | Nuwakot | Chaturale | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-03-29 |  |  | Kakani | 7
13152 | Nuwakot | Chaturale | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 74 | 39 | 2015-10-01 |  |  | Kakani | 7
13153 | Nuwakot | Chaturale | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 74 | 15 | 2015-10-01 |  |  | Kakani | 7
13154 | Nuwakot | Chaturale | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 30 | 2015-10-01 |  |  | Kakani | 7
13155 | Nuwakot | Chaturale | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 7 | 2018-03-29 |  |  | Kakani | 7
13156 | Nuwakot | Chaturale | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 205 | 2015-10-01 |  |  | Kakani | 7
13157 | Nuwakot | Chaturale | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-03-22 |  |  | Kakani | 7
13158 | Nuwakot | Chaturale | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 76 | 29 | 2015-10-01 |  |  | Kakani | 7
13159 | Nuwakot | Chaturale | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 76 | 16 | 2015-10-01 |  |  | Kakani | 7
13160 | Nuwakot | Chaturale | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 10 | 2015-10-01 |  |  | Kakani | 7
13161 | Nuwakot | Chaturale | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 7 | 2018-03-22 |  |  | Kakani | 7
13162 | Nuwakot | Chaturale | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 114 | 2015-10-01 |  |  | Kakani | 7
13163 | Nuwakot | Chaturale | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2018-02-25 | 2018-04-17 |  | Kakani | 7
13164 | Nuwakot | Chaturale | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 45 | 24 | 2015-10-01 |  |  | Kakani | 7
13165 | Nuwakot | Chaturale | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 45 | 10 | 2015-10-01 |  |  | Kakani | 7
13166 | Nuwakot | Chaturale | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 7 | 2015-10-01 |  |  | Kakani | 7
13167 | Nuwakot | Chaturale | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 7 | 2018-02-25 | 2018-04-17 |  | Kakani | 7
13168 | Nuwakot | Chaturale | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 217 | 2015-10-01 |  |  | Kakani | 7
13169 | Nuwakot | Chaturale | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2018-03-15 | 2018-05-07 |  | Kakani | 7
13170 | Nuwakot | Chaturale | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 92 | 72 | 2015-10-01 |  |  | Kakani | 7
13171 | Nuwakot | Chaturale | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 92 | 5 | 2015-10-01 |  |  | Kakani | 7
13172 | Nuwakot | Chaturale | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 20 | 2015-10-01 |  |  | Kakani | 7
13173 | Nuwakot | Chaturale | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 7 | 2018-03-15 | 2018-05-07 |  | Kakani | 7
13174 | Nuwakot | Chaturale | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 184 | 2015-10-01 |  |  | Kakani | 7
13175 | Nuwakot | Chaturale | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-03-23 |  |  | Kakani | 7
13176 | Nuwakot | Chaturale | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 121 | 96 | 2015-10-01 |  |  | Kakani | 7
13177 | Nuwakot | Chaturale | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 121 | 28 | 2015-10-01 |  |  | Kakani | 7
13178 | Nuwakot | Chaturale | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 10 | 2015-10-01 |  |  | Kakani | 7
13179 | Nuwakot | Chaturale | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 7 | 2018-03-23 |  |  | Kakani | 7
13180 | Nuwakot | Chaturale | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 243 | 2015-10-01 |  |  | Kakani | 7
13181 | Nuwakot | Chaturale | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2018-02-14 | 2018-04-12 |  | Kakani | 7
13182 | Nuwakot | Chaturale | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 95 | 46 | 2015-10-01 |  |  | Kakani | 7
13183 | Nuwakot | Chaturale | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 95 | 4 | 2015-10-01 |  |  | Kakani | 7
13184 | Nuwakot | Chaturale | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 17 | 2015-10-01 |  |  | Kakani | 7
13185 | Nuwakot | Chaturale | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2018-02-14 | 2018-04-12 |  | Kakani | 7
13186 | Nuwakot | Chaturale | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 107 | 2015-10-01 |  |  | Kakani | 7
13187 | Nuwakot | Chaturale | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 7
13188 | Nuwakot | Chaturale | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 67 | 46 | 2015-10-01 |  |  | Kakani | 7
13189 | Nuwakot | Chaturale | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 67 | 0 | 2015-10-01 |  |  | Kakani | 7
13190 | Nuwakot | Chaturale | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 15 | 1 | 2015-10-01 |  |  | Kakani | 7
13191 | Nuwakot | Chaturale | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 7
13192 | Nuwakot | Chaughada | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 1
13193 | Nuwakot | Chaughada | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 1
13194 | Nuwakot | Chaughada | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 4
13195 | Nuwakot | Chaughada | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 4
13196 | Nuwakot | Chaughada | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 4
13197 | Nuwakot | Chaughada | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 4
13198 | Nuwakot | Chaughada | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 1
13199 | Nuwakot | Chaughada | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 1
13200 | Nuwakot | Chaughada | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 4
13201 | Nuwakot | Chaughada | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 4
13202 | Nuwakot | Chaughada | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 4
13203 | Nuwakot | Chaughada | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 4
13204 | Nuwakot | Chaughada | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 4
13205 | Nuwakot | Chaughada | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 4
13206 | Nuwakot | Chaughada | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 4
13207 | Nuwakot | Chaughada | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 4
13208 | Nuwakot | Chaughada | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 1
13209 | Nuwakot | Chaughada | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 1
13210 | Nuwakot | Chhap | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 51 | 2015-10-01 |  |  | Shivapuri | 2
13211 | Nuwakot | Chhap | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-04-06 |  |  | Shivapuri | 2
13212 | Nuwakot | Chhap | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 58 | 43 | 2015-10-01 |  |  | Shivapuri | 2
13213 | Nuwakot | Chhap | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 58 | 48 | 2015-10-01 |  |  | Shivapuri | 2
13214 | Nuwakot | Chhap | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 10 | 2015-10-01 |  |  | Shivapuri | 2
13215 | Nuwakot | Chhap | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 6 | 2018-04-06 |  |  | Shivapuri | 2
13216 | Nuwakot | Chhap | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 143 | 2015-10-01 |  |  | Shivapuri | 2
13217 | Nuwakot | Chhap | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-03-26 |  |  | Shivapuri | 2
13218 | Nuwakot | Chhap | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 64 | 57 | 2015-10-01 |  |  | Shivapuri | 2
13219 | Nuwakot | Chhap | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 64 | 16 | 2015-10-01 |  |  | Shivapuri | 2
13220 | Nuwakot | Chhap | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 19 | 2015-10-01 |  |  | Shivapuri | 2
13221 | Nuwakot | Chhap | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 6 | 2018-03-26 |  |  | Shivapuri | 2
13222 | Nuwakot | Chhap | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 65 | 2015-10-01 |  |  | Shivapuri | 2
13223 | Nuwakot | Chhap | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 2
13224 | Nuwakot | Chhap | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 54 | 49 | 2015-10-01 |  |  | Shivapuri | 2
13225 | Nuwakot | Chhap | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 54 | 42 | 2015-10-01 |  |  | Shivapuri | 2
13226 | Nuwakot | Chhap | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 17 | 2015-10-01 |  |  | Shivapuri | 2
13227 | Nuwakot | Chhap | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 2
13228 | Nuwakot | Chhap | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 109 | 2015-10-01 |  |  | Shivapuri | 2
13229 | Nuwakot | Chhap | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 2
13230 | Nuwakot | Chhap | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 52 | 35 | 2015-10-01 |  |  | Shivapuri | 2
13231 | Nuwakot | Chhap | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 52 | 1 | 2015-10-01 |  |  | Shivapuri | 2
13232 | Nuwakot | Chhap | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 7 | 2015-10-01 |  |  | Shivapuri | 2
13233 | Nuwakot | Chhap | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 2
13234 | Nuwakot | Chhap | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 155 | 2015-10-01 |  |  | Shivapuri | 2
13235 | Nuwakot | Chhap | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2018-02-20 | 2018-05-03 |  | Shivapuri | 2
13236 | Nuwakot | Chhap | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 64 | 54 | 2015-10-01 |  |  | Shivapuri | 2
13237 | Nuwakot | Chhap | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 64 | 11 | 2015-10-01 |  |  | Shivapuri | 2
13238 | Nuwakot | Chhap | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 14 | 2015-10-01 |  |  | Shivapuri | 2
13239 | Nuwakot | Chhap | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2018-02-20 | 2018-05-03 |  | Shivapuri | 2
13240 | Nuwakot | Chhap | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 270 | 2015-10-01 |  |  | Shivapuri | 2
13241 | Nuwakot | Chhap | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-11-29 | 2018-02-02 |  | Shivapuri | 2
13242 | Nuwakot | Chhap | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 77 | 71 | 2015-10-01 |  |  | Shivapuri | 2
13243 | Nuwakot | Chhap | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 77 | 0 | 2015-10-01 |  |  | Shivapuri | 2
13244 | Nuwakot | Chhap | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 18 | 2015-10-01 |  |  | Shivapuri | 2
13245 | Nuwakot | Chhap | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-11-29 | 2018-02-02 |  | Shivapuri | 2
13246 | Nuwakot | Chhap | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 524 | 2015-10-01 |  |  | Shivapuri | 2
13247 | Nuwakot | Chhap | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2018-03-08 | 2018-05-11 |  | Shivapuri | 2
13248 | Nuwakot | Chhap | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 46 | 40 | 2015-10-01 |  |  | Shivapuri | 2
13249 | Nuwakot | Chhap | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 46 | 197 | 2015-10-01 |  |  | Shivapuri | 2
13250 | Nuwakot | Chhap | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 35 | 2015-10-01 |  |  | Shivapuri | 2
13251 | Nuwakot | Chhap | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2018-03-08 | 2018-05-11 |  | Shivapuri | 2
13252 | Nuwakot | Chhap | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 187 | 2015-10-01 |  |  | Shivapuri | 2
13253 | Nuwakot | Chhap | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2018-01-21 | 2018-03-27 |  | Shivapuri | 2
13254 | Nuwakot | Chhap | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 31 | 24 | 2015-10-01 |  |  | Shivapuri | 2
13255 | Nuwakot | Chhap | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 31 | 7 | 2015-10-01 |  |  | Shivapuri | 2
13256 | Nuwakot | Chhap | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 4 | 2015-10-01 |  |  | Shivapuri | 2
13257 | Nuwakot | Chhap | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2018-01-21 | 2018-03-27 |  | Shivapuri | 2
13258 | Nuwakot | Chhap | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 99 | 2015-10-01 |  |  | Shivapuri | 2
13259 | Nuwakot | Chhap | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 2
13260 | Nuwakot | Chhap | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 102 | 100 | 2015-10-01 |  |  | Shivapuri | 2
13261 | Nuwakot | Chhap | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 102 | 0 | 2015-10-01 |  |  | Shivapuri | 2
13262 | Nuwakot | Chhap | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 15 | 27 | 2015-10-01 |  |  | Shivapuri | 2
13263 | Nuwakot | Chhap | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 2
13264 | Nuwakot | Duipipal | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 6
13265 | Nuwakot | Duipipal | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 6
13266 | Nuwakot | Duipipal | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 6
13267 | Nuwakot | Duipipal | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 6
13268 | Nuwakot | Duipipal | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 5
13269 | Nuwakot | Duipipal | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 5
13270 | Nuwakot | Duipipal | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 5
13271 | Nuwakot | Duipipal | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 5
13272 | Nuwakot | Duipipal | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 4
13273 | Nuwakot | Duipipal | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 4
13274 | Nuwakot | Duipipal | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 5
13275 | Nuwakot | Duipipal | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 5
13276 | Nuwakot | Duipipal | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 6
13277 | Nuwakot | Duipipal | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 6
13278 | Nuwakot | Duipipal | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 5
13279 | Nuwakot | Duipipal | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 5
13280 | Nuwakot | Duipipal | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 4
13281 | Nuwakot | Duipipal | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 4
13282 | Nuwakot | Fikuri | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 2
13283 | Nuwakot | Fikuri | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 2
13284 | Nuwakot | Fikuri | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 2
13285 | Nuwakot | Fikuri | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 2
13286 | Nuwakot | Fikuri | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 2
13287 | Nuwakot | Fikuri | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 2
13288 | Nuwakot | Fikuri | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 2
13289 | Nuwakot | Fikuri | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 2
13290 | Nuwakot | Fikuri | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 2
13291 | Nuwakot | Fikuri | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 2
13292 | Nuwakot | Fikuri | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 2
13293 | Nuwakot | Fikuri | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 2
13294 | Nuwakot | Fikuri | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 2
13295 | Nuwakot | Fikuri | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 2
13296 | Nuwakot | Fikuri | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 2
13297 | Nuwakot | Fikuri | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 2
13298 | Nuwakot | Fikuri | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 2
13299 | Nuwakot | Fikuri | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 2
13300 | Nuwakot | Ganeshthan | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 5
13301 | Nuwakot | Ganeshthan | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 5
13302 | Nuwakot | Ganeshthan | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 5
13303 | Nuwakot | Ganeshthan | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 5
13304 | Nuwakot | Ganeshthan | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 5
13305 | Nuwakot | Ganeshthan | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 5
13306 | Nuwakot | Ganeshthan | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 5
13307 | Nuwakot | Ganeshthan | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 5
13308 | Nuwakot | Ganeshthan | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 5
13309 | Nuwakot | Ganeshthan | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 5
13310 | Nuwakot | Ganeshthan | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 5
13311 | Nuwakot | Ganeshthan | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 5
13312 | Nuwakot | Ganeshthan | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 5
13313 | Nuwakot | Ganeshthan | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 5
13314 | Nuwakot | Ganeshthan | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 5
13315 | Nuwakot | Ganeshthan | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 5
13316 | Nuwakot | Ganeshthan | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 5
13317 | Nuwakot | Ganeshthan | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 5
13318 | Nuwakot | Gaunkharka | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 2
13319 | Nuwakot | Gaunkharka | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 2
13320 | Nuwakot | Gaunkharka | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 2
13321 | Nuwakot | Gaunkharka | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 2
13322 | Nuwakot | Gaunkharka | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 2
13323 | Nuwakot | Gaunkharka | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 2
13324 | Nuwakot | Gaunkharka | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 2
13325 | Nuwakot | Gaunkharka | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 2
13326 | Nuwakot | Gaunkharka | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 2
13327 | Nuwakot | Gaunkharka | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 2
13328 | Nuwakot | Gaunkharka | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 2
13329 | Nuwakot | Gaunkharka | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 2
13330 | Nuwakot | Gaunkharka | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 2
13331 | Nuwakot | Gaunkharka | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 2
13332 | Nuwakot | Gaunkharka | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 2
13333 | Nuwakot | Gaunkharka | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 2
13334 | Nuwakot | Gaunkharka | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 2
13335 | Nuwakot | Gaunkharka | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 2
13336 | Nuwakot | Gerkhu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 11
13337 | Nuwakot | Gerkhu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 11
13338 | Nuwakot | Gerkhu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 11
13339 | Nuwakot | Gerkhu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 11
13340 | Nuwakot | Gerkhu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 10
13341 | Nuwakot | Gerkhu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 10
13342 | Nuwakot | Gerkhu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 10
13343 | Nuwakot | Gerkhu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 10
13344 | Nuwakot | Gerkhu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 11
13345 | Nuwakot | Gerkhu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 11
13346 | Nuwakot | Gerkhu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 11
13347 | Nuwakot | Gerkhu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 11
13348 | Nuwakot | Gerkhu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 10
13349 | Nuwakot | Gerkhu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 10
13350 | Nuwakot | Gerkhu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 11
13351 | Nuwakot | Gerkhu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 11
13352 | Nuwakot | Gerkhu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 10
13353 | Nuwakot | Gerkhu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 10
13354 | Nuwakot | Ghyangphedi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 1
13355 | Nuwakot | Ghyangphedi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 1
13356 | Nuwakot | Ghyangphedi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 1
13357 | Nuwakot | Ghyangphedi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 1
13358 | Nuwakot | Ghyangphedi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 1
13359 | Nuwakot | Ghyangphedi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 1
13360 | Nuwakot | Ghyangphedi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 1
13361 | Nuwakot | Ghyangphedi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 1
13362 | Nuwakot | Ghyangphedi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 1
13363 | Nuwakot | Ghyangphedi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 1
13364 | Nuwakot | Ghyangphedi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 1
13365 | Nuwakot | Ghyangphedi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 1
13366 | Nuwakot | Ghyangphedi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 1
13367 | Nuwakot | Ghyangphedi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 1
13368 | Nuwakot | Ghyangphedi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 1
13369 | Nuwakot | Ghyangphedi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 1
13370 | Nuwakot | Ghyangphedi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 1
13371 | Nuwakot | Ghyangphedi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 1
13372 | Nuwakot | Kabilas | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 2
13373 | Nuwakot | Kabilas | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 2
13374 | Nuwakot | Kabilas | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 2
13375 | Nuwakot | Kabilas | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 2
13376 | Nuwakot | Kabilas | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 2
13377 | Nuwakot | Kabilas | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 2
13378 | Nuwakot | Kabilas | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 2
13379 | Nuwakot | Kabilas | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 2
13380 | Nuwakot | Kabilas | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 2
13381 | Nuwakot | Kabilas | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 2
13382 | Nuwakot | Kabilas | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 2
13383 | Nuwakot | Kabilas | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 2
13384 | Nuwakot | Kabilas | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 2
13385 | Nuwakot | Kabilas | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 2
13386 | Nuwakot | Kabilas | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 2
13387 | Nuwakot | Kabilas | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 2
13388 | Nuwakot | Kabilas | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 2
13389 | Nuwakot | Kabilas | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 2
13390 | Nuwakot | Kakani | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 4
13391 | Nuwakot | Kakani | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 4
13392 | Nuwakot | Kakani | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 4
13393 | Nuwakot | Kakani | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 4
13394 | Nuwakot | Kakani | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 4
13395 | Nuwakot | Kakani | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 4
13396 | Nuwakot | Kakani | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 4
13397 | Nuwakot | Kakani | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 4
13398 | Nuwakot | Kakani | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 4
13399 | Nuwakot | Kakani | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 4
13400 | Nuwakot | Kakani | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 5
13401 | Nuwakot | Kakani | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 5
13402 | Nuwakot | Kakani | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 5
13403 | Nuwakot | Kakani | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 5
13404 | Nuwakot | Kakani | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 5
13405 | Nuwakot | Kakani | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 5
13406 | Nuwakot | Kakani | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 5
13407 | Nuwakot | Kakani | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 5
13408 | Nuwakot | Kalikahalde | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 4
13409 | Nuwakot | Kalikahalde | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 4
13410 | Nuwakot | Kalikahalde | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 4
13411 | Nuwakot | Kalikahalde | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 4
13412 | Nuwakot | Kalikahalde | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 4
13413 | Nuwakot | Kalikahalde | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 4
13414 | Nuwakot | Kalikahalde | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 4
13415 | Nuwakot | Kalikahalde | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 4
13416 | Nuwakot | Kalikahalde | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 4
13417 | Nuwakot | Kalikahalde | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 4
13418 | Nuwakot | Kalikahalde | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 4
13419 | Nuwakot | Kalikahalde | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 4
13420 | Nuwakot | Kalikahalde | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 4
13421 | Nuwakot | Kalikahalde | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 4
13422 | Nuwakot | Kalikahalde | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 4
13423 | Nuwakot | Kalikahalde | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 4
13424 | Nuwakot | Kalikahalde | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 4
13425 | Nuwakot | Kalikahalde | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 4
13426 | Nuwakot | Kalyanpur | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 13
13427 | Nuwakot | Kalyanpur | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 13
13428 | Nuwakot | Kalyanpur | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 13
13429 | Nuwakot | Kalyanpur | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 13
13430 | Nuwakot | Kalyanpur | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 13
13431 | Nuwakot | Kalyanpur | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 13
13432 | Nuwakot | Kalyanpur | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 13
13433 | Nuwakot | Kalyanpur | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 13
13434 | Nuwakot | Kalyanpur | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 13
13435 | Nuwakot | Kalyanpur | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 13
13436 | Nuwakot | Kalyanpur | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 13
13437 | Nuwakot | Kalyanpur | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 13
13438 | Nuwakot | Kalyanpur | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 13
13439 | Nuwakot | Kalyanpur | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 13
13440 | Nuwakot | Kalyanpur | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 13
13441 | Nuwakot | Kalyanpur | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 13
13442 | Nuwakot | Kalyanpur | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 13
13443 | Nuwakot | Kalyanpur | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 13
13444 | Nuwakot | Kharanitar | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 3
13445 | Nuwakot | Kharanitar | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 3
13446 | Nuwakot | Kharanitar | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 3
13447 | Nuwakot | Kharanitar | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 3
13448 | Nuwakot | Kharanitar | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 3
13449 | Nuwakot | Kharanitar | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 3
13450 | Nuwakot | Kharanitar | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 3
13451 | Nuwakot | Kharanitar | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 3
13452 | Nuwakot | Kharanitar | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 3
13453 | Nuwakot | Kharanitar | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 3
13454 | Nuwakot | Kharanitar | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 3
13455 | Nuwakot | Kharanitar | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 3
13456 | Nuwakot | Kharanitar | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-09-02 | 2017-10-22 |  | Tadi | 3
13457 | Nuwakot | Kharanitar | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-09-02 | 2017-10-22 |  | Tadi | 3
13458 | Nuwakot | Kharanitar | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-09-20 | 2017-11-09 |  | Tadi | 3
13459 | Nuwakot | Kharanitar | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-09-20 | 2017-11-09 |  | Tadi | 3
13460 | Nuwakot | Kharanitar | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 3
13461 | Nuwakot | Kharanitar | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 3
13462 | Nuwakot | Kumari | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 3
13463 | Nuwakot | Kumari | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 3
13464 | Nuwakot | Kumari | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 3
13465 | Nuwakot | Kumari | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 3
13466 | Nuwakot | Kumari | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 3
13467 | Nuwakot | Kumari | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 3
13468 | Nuwakot | Kumari | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 3
13469 | Nuwakot | Kumari | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 3
13470 | Nuwakot | Kumari | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 4
13471 | Nuwakot | Kumari | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 4
13472 | Nuwakot | Kumari | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 2
13473 | Nuwakot | Kumari | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 2
13474 | Nuwakot | Kumari | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 3
13475 | Nuwakot | Kumari | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 3
13476 | Nuwakot | Kumari | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 2
13477 | Nuwakot | Kumari | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 2
13478 | Nuwakot | Kumari | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 2
13479 | Nuwakot | Kumari | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 2
13480 | Nuwakot | Lachyang | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 1
13481 | Nuwakot | Lachyang | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 1
13482 | Nuwakot | Lachyang | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 1
13483 | Nuwakot | Lachyang | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 1
13484 | Nuwakot | Lachyang | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 1
13485 | Nuwakot | Lachyang | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 1
13486 | Nuwakot | Lachyang | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 1
13487 | Nuwakot | Lachyang | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 1
13488 | Nuwakot | Lachyang | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 1
13489 | Nuwakot | Lachyang | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 1
13490 | Nuwakot | Lachyang | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 1
13491 | Nuwakot | Lachyang | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 1
13492 | Nuwakot | Lachyang | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 1
13493 | Nuwakot | Lachyang | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 1
13494 | Nuwakot | Lachyang | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 1
13495 | Nuwakot | Lachyang | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 1
13496 | Nuwakot | Lachyang | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Suryagadhi | 2
13497 | Nuwakot | Lachyang | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Suryagadhi | 2
13498 | Nuwakot | Likhu | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 304 | 2015-10-01 |  |  | Shivapuri | 3
13499 | Nuwakot | Likhu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 3
13500 | Nuwakot | Likhu | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 131 | 43 | 2015-10-01 |  |  | Shivapuri | 3
13501 | Nuwakot | Likhu | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 131 | 13 | 2015-10-01 |  |  | Shivapuri | 3
13502 | Nuwakot | Likhu | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 4 | 2015-10-01 |  |  | Shivapuri | 3
13503 | Nuwakot | Likhu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 3
13504 | Nuwakot | Likhu | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 290 | 2015-10-01 |  |  | Shivapuri | 3
13505 | Nuwakot | Likhu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 3
13506 | Nuwakot | Likhu | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 143 | 54 | 2015-10-01 |  |  | Shivapuri | 3
13507 | Nuwakot | Likhu | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 143 | 10 | 2015-10-01 |  |  | Shivapuri | 3
13508 | Nuwakot | Likhu | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 13 | 2015-10-01 |  |  | Shivapuri | 3
13509 | Nuwakot | Likhu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 3
13510 | Nuwakot | Likhu | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 213 | 2015-10-01 |  |  | Shivapuri | 3
13511 | Nuwakot | Likhu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-04-16 |  |  | Shivapuri | 3
13512 | Nuwakot | Likhu | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 123 | 27 | 2015-10-01 |  |  | Shivapuri | 3
13513 | Nuwakot | Likhu | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 123 | 11 | 2015-10-01 |  |  | Shivapuri | 3
13514 | Nuwakot | Likhu | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 7 | 2015-10-01 |  |  | Shivapuri | 3
13515 | Nuwakot | Likhu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2018-04-16 |  |  | Shivapuri | 3
13516 | Nuwakot | Likhu | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 205 | 2015-10-01 |  |  | Shivapuri | 3
13517 | Nuwakot | Likhu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 3
13518 | Nuwakot | Likhu | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Planned | 94 | 64 | 2015-10-01 |  |  | Shivapuri | 3
13519 | Nuwakot | Likhu | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 94 | 8 | 2015-10-01 |  |  | Shivapuri | 3
13520 | Nuwakot | Likhu | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 11 | 2015-10-01 |  |  | Shivapuri | 3
13521 | Nuwakot | Likhu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 6 |  |  |  | Shivapuri | 3
13522 | Nuwakot | Likhu | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 167 | 2015-10-01 |  |  | Shivapuri | 3
13523 | Nuwakot | Likhu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 3
13524 | Nuwakot | Likhu | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 99 | 47 | 2015-10-01 |  |  | Shivapuri | 3
13525 | Nuwakot | Likhu | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 99 | 12 | 2015-10-01 |  |  | Shivapuri | 3
13526 | Nuwakot | Likhu | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 9 | 2015-10-01 |  |  | Shivapuri | 3
13527 | Nuwakot | Likhu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 3
13528 | Nuwakot | Likhu | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 477 | 2015-10-01 |  |  | Shivapuri | 3
13529 | Nuwakot | Likhu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 3
13530 | Nuwakot | Likhu | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 99 | 63 | 2015-10-01 |  |  | Shivapuri | 3
13531 | Nuwakot | Likhu | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 99 | 13 | 2015-10-01 |  |  | Shivapuri | 3
13532 | Nuwakot | Likhu | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 10 | 2015-10-01 |  |  | Shivapuri | 3
13533 | Nuwakot | Likhu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 3
13534 | Nuwakot | Likhu | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 265 | 2015-10-01 |  |  | Shivapuri | 3
13535 | Nuwakot | Likhu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 3
13536 | Nuwakot | Likhu | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 191 | 71 | 2015-10-01 |  |  | Shivapuri | 3
13537 | Nuwakot | Likhu | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 191 | 15 | 2015-10-01 |  |  | Shivapuri | 3
13538 | Nuwakot | Likhu | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 10 | 2015-10-01 |  |  | Shivapuri | 3
13539 | Nuwakot | Likhu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 3
13540 | Nuwakot | Likhu | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 316 | 2015-10-01 |  |  | Shivapuri | 3
13541 | Nuwakot | Likhu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 3
13542 | Nuwakot | Likhu | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 111 | 79 | 2015-10-01 |  |  | Shivapuri | 3
13543 | Nuwakot | Likhu | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 111 | 9 | 2015-10-01 |  |  | Shivapuri | 3
13544 | Nuwakot | Likhu | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 17 | 2015-10-01 |  |  | Shivapuri | 3
13545 | Nuwakot | Likhu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 3
13546 | Nuwakot | Likhu | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 404 | 2015-10-01 |  |  | Shivapuri | 3
13547 | Nuwakot | Likhu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-02-23 |  |  | Shivapuri | 3
13548 | Nuwakot | Likhu | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 103 | 78 | 2015-10-01 |  |  | Shivapuri | 3
13549 | Nuwakot | Likhu | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 103 | 14 | 2015-10-01 |  |  | Shivapuri | 3
13550 | Nuwakot | Likhu | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 15 | 12 | 2015-10-01 |  |  | Shivapuri | 3
13551 | Nuwakot | Likhu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 6 | 2018-02-23 |  |  | Shivapuri | 3
13552 | Nuwakot | Mahakali | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 560 | 308 | 2015-10-01 |  |  | Shivapuri | 5
13553 | Nuwakot | Mahakali | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-04-10 | 2017-07-17 |  | Shivapuri | 5
13554 | Nuwakot | Mahakali | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 236 | 49 | 2015-10-01 |  |  | Shivapuri | 5
13555 | Nuwakot | Mahakali | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 236 | 15 | 2015-10-01 |  |  | Shivapuri | 5
13556 | Nuwakot | Mahakali | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 15 | 2015-10-01 |  |  | Shivapuri | 5
13557 | Nuwakot | Mahakali | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-04-10 | 2017-07-17 |  | Shivapuri | 5
13558 | Nuwakot | Mahakali | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 560 | 175 | 2015-10-01 |  |  | Shivapuri | 5
13559 | Nuwakot | Mahakali | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 5
13560 | Nuwakot | Mahakali | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 239 | 66 | 2015-10-01 |  |  | Shivapuri | 5
13561 | Nuwakot | Mahakali | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 239 | 5 | 2015-10-01 |  |  | Shivapuri | 5
13562 | Nuwakot | Mahakali | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 13 | 2015-10-01 |  |  | Shivapuri | 5
13563 | Nuwakot | Mahakali | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 5
13564 | Nuwakot | Mahakali | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 560 | 294 | 2015-10-01 |  |  | Shivapuri | 5
13565 | Nuwakot | Mahakali | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 5
13566 | Nuwakot | Mahakali | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 176 | 88 | 2015-10-01 |  |  | Shivapuri | 5
13567 | Nuwakot | Mahakali | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 176 | 20 | 2015-10-01 |  |  | Shivapuri | 5
13568 | Nuwakot | Mahakali | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 7 | 2015-10-01 |  |  | Shivapuri | 5
13569 | Nuwakot | Mahakali | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 5
13570 | Nuwakot | Mahakali | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 560 | 221 | 2015-10-01 |  |  | Shivapuri | 5
13571 | Nuwakot | Mahakali | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 5
13572 | Nuwakot | Mahakali | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 257 | 54 | 2015-10-01 |  |  | Shivapuri | 5
13573 | Nuwakot | Mahakali | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 257 | 10 | 2015-10-01 |  |  | Shivapuri | 5
13574 | Nuwakot | Mahakali | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 6 | 2015-10-01 |  |  | Shivapuri | 5
13575 | Nuwakot | Mahakali | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 5
13576 | Nuwakot | Mahakali | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 560 | 682 | 2015-10-01 |  |  | Shivapuri | 5
13577 | Nuwakot | Mahakali | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-12-03 | 2018-03-11 |  | Shivapuri | 5
13578 | Nuwakot | Mahakali | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 162 | 137 | 2015-10-01 |  |  | Shivapuri | 5
13579 | Nuwakot | Mahakali | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 162 | 17 | 2015-10-01 |  |  | Shivapuri | 5
13580 | Nuwakot | Mahakali | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 30 | 2015-10-01 |  |  | Shivapuri | 5
13581 | Nuwakot | Mahakali | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 5 | 2017-12-03 | 2018-03-11 |  | Shivapuri | 5
13582 | Nuwakot | Mahakali | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 560 | 215 | 2015-10-01 |  |  | Shivapuri | 5
13583 | Nuwakot | Mahakali | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-03-12 |  |  | Shivapuri | 5
13584 | Nuwakot | Mahakali | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 108 | 64 | 2015-10-01 |  |  | Shivapuri | 5
13585 | Nuwakot | Mahakali | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 108 | 8 | 2015-10-01 |  |  | Shivapuri | 5
13586 | Nuwakot | Mahakali | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 21 | 2015-10-01 |  |  | Shivapuri | 5
13587 | Nuwakot | Mahakali | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 6 | 2018-03-12 |  |  | Shivapuri | 5
13588 | Nuwakot | Mahakali | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 560 | 166 | 2015-10-01 |  |  | Shivapuri | 5
13589 | Nuwakot | Mahakali | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 5
13590 | Nuwakot | Mahakali | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 180 | 49 | 2015-10-01 |  |  | Shivapuri | 5
13591 | Nuwakot | Mahakali | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 180 | 12 | 2015-10-01 |  |  | Shivapuri | 5
13592 | Nuwakot | Mahakali | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 5 | 2015-10-01 |  |  | Shivapuri | 5
13593 | Nuwakot | Mahakali | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 5
13594 | Nuwakot | Mahakali | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 560 | 133 | 2015-10-01 |  |  | Shivapuri | 5
13595 | Nuwakot | Mahakali | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 5
13596 | Nuwakot | Mahakali | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 384 | 44 | 2015-10-01 |  |  | Shivapuri | 5
13597 | Nuwakot | Mahakali | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 384 | 13 | 2015-10-01 |  |  | Shivapuri | 5
13598 | Nuwakot | Mahakali | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 9 | 2015-10-01 |  |  | Shivapuri | 5
13599 | Nuwakot | Mahakali | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 5
13600 | Nuwakot | Mahakali | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 560 | 133 | 2015-10-01 |  |  | Shivapuri | 5
13601 | Nuwakot | Mahakali | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 5
13602 | Nuwakot | Mahakali | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 400 | 52 | 2015-10-01 |  |  | Shivapuri | 5
13603 | Nuwakot | Mahakali | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 400 | 0 | 2015-10-01 |  |  | Shivapuri | 5
13604 | Nuwakot | Mahakali | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 15 | 11 | 2015-10-01 |  |  | Shivapuri | 5
13605 | Nuwakot | Mahakali | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 5
13606 | Nuwakot | Narjamandap | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 5
13607 | Nuwakot | Narjamandap | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 5
13608 | Nuwakot | Narjamandap | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-08-31 | 2017-10-20 |  | Tadi | 5
13609 | Nuwakot | Narjamandap | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-08-31 | 2017-10-20 |  | Tadi | 5
13610 | Nuwakot | Narjamandap | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 5
13611 | Nuwakot | Narjamandap | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 5
13612 | Nuwakot | Narjamandap | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 5
13613 | Nuwakot | Narjamandap | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 5
13614 | Nuwakot | Narjamandap | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 6
13615 | Nuwakot | Narjamandap | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 6
13616 | Nuwakot | Narjamandap | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 6
13617 | Nuwakot | Narjamandap | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 6
13618 | Nuwakot | Narjamandap | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 6
13619 | Nuwakot | Narjamandap | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 6
13620 | Nuwakot | Narjamandap | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 6
13621 | Nuwakot | Narjamandap | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 6
13622 | Nuwakot | Narjamandap | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 6
13623 | Nuwakot | Narjamandap | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 6
13624 | Nuwakot | Okharpauwa | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 1
13625 | Nuwakot | Okharpauwa | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 1
13626 | Nuwakot | Okharpauwa | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 2
13627 | Nuwakot | Okharpauwa | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 2
13628 | Nuwakot | Okharpauwa | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 2
13629 | Nuwakot | Okharpauwa | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 2
13630 | Nuwakot | Okharpauwa | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 2
13631 | Nuwakot | Okharpauwa | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 2
13632 | Nuwakot | Okharpauwa | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 2
13633 | Nuwakot | Okharpauwa | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 2
13634 | Nuwakot | Okharpauwa | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 2
13635 | Nuwakot | Okharpauwa | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 2
13636 | Nuwakot | Okharpauwa | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 1
13637 | Nuwakot | Okharpauwa | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 1
13638 | Nuwakot | Okharpauwa | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 1
13639 | Nuwakot | Okharpauwa | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 1
13640 | Nuwakot | Okharpauwa | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kakani | 1
13641 | Nuwakot | Okharpauwa | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kakani | 1
13642 | Nuwakot | Panchkanya | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 3
13643 | Nuwakot | Panchkanya | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 3
13644 | Nuwakot | Panchkanya | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 3
13645 | Nuwakot | Panchkanya | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 3
13646 | Nuwakot | Panchkanya | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 3
13647 | Nuwakot | Panchkanya | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 3
13648 | Nuwakot | Panchkanya | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 3
13649 | Nuwakot | Panchkanya | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 3
13650 | Nuwakot | Panchkanya | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 3
13651 | Nuwakot | Panchkanya | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 3
13652 | Nuwakot | Panchkanya | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 3
13653 | Nuwakot | Panchkanya | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 3
13654 | Nuwakot | Panchkanya | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 3
13655 | Nuwakot | Panchkanya | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 3
13656 | Nuwakot | Panchkanya | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 3
13657 | Nuwakot | Panchkanya | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 3
13658 | Nuwakot | Panchkanya | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 3
13659 | Nuwakot | Panchkanya | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 3
13660 | Nuwakot | Ralukadevi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 2
13661 | Nuwakot | Ralukadevi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 2
13662 | Nuwakot | Ralukadevi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 2
13663 | Nuwakot | Ralukadevi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 2
13664 | Nuwakot | Ralukadevi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-08-26 | 2017-10-15 |  | Tadi | 2
13665 | Nuwakot | Ralukadevi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-08-26 | 2017-10-15 |  | Tadi | 2
13666 | Nuwakot | Ralukadevi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 2
13667 | Nuwakot | Ralukadevi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 2
13668 | Nuwakot | Ralukadevi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 2
13669 | Nuwakot | Ralukadevi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 2
13670 | Nuwakot | Ralukadevi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 2
13671 | Nuwakot | Ralukadevi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 2
13672 | Nuwakot | Ralukadevi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 3
13673 | Nuwakot | Ralukadevi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 3
13674 | Nuwakot | Ralukadevi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 3
13675 | Nuwakot | Ralukadevi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 3
13676 | Nuwakot | Ralukadevi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-08-30 | 2017-10-19 |  | Tadi | 3
13677 | Nuwakot | Ralukadevi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-08-30 | 2017-10-19 |  | Tadi | 3
13678 | Nuwakot | Ratmate | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 7
13679 | Nuwakot | Ratmate | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 7
13680 | Nuwakot | Ratmate | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 7
13681 | Nuwakot | Ratmate | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 7
13682 | Nuwakot | Ratmate | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 7
13683 | Nuwakot | Ratmate | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 7
13684 | Nuwakot | Ratmate | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 7
13685 | Nuwakot | Ratmate | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 7
13686 | Nuwakot | Ratmate | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 7
13687 | Nuwakot | Ratmate | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 7
13688 | Nuwakot | Ratmate | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 7
13689 | Nuwakot | Ratmate | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 7
13690 | Nuwakot | Ratmate | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 7
13691 | Nuwakot | Ratmate | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 7
13692 | Nuwakot | Ratmate | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 7
13693 | Nuwakot | Ratmate | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 7
13694 | Nuwakot | Ratmate | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Belkotgadhi | 7
13695 | Nuwakot | Ratmate | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Belkotgadhi | 7
13696 | Nuwakot | Rautbesi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 3
13697 | Nuwakot | Rautbesi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 3
13698 | Nuwakot | Rautbesi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 3
13699 | Nuwakot | Rautbesi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 3
13700 | Nuwakot | Rautbesi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 3
13701 | Nuwakot | Rautbesi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 3
13702 | Nuwakot | Rautbesi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 3
13703 | Nuwakot | Rautbesi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 3
13704 | Nuwakot | Rautbesi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 3
13705 | Nuwakot | Rautbesi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 3
13706 | Nuwakot | Rautbesi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 3
13707 | Nuwakot | Rautbesi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 3
13708 | Nuwakot | Rautbesi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 3
13709 | Nuwakot | Rautbesi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 3
13710 | Nuwakot | Rautbesi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 6
13711 | Nuwakot | Rautbesi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 6
13712 | Nuwakot | Rautbesi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 6
13713 | Nuwakot | Rautbesi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 6
13714 | Nuwakot | Salme | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 4
13715 | Nuwakot | Salme | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 4
13716 | Nuwakot | Salme | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 4
13717 | Nuwakot | Salme | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 4
13718 | Nuwakot | Salme | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 4
13719 | Nuwakot | Salme | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 4
13720 | Nuwakot | Salme | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 4
13721 | Nuwakot | Salme | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 4
13722 | Nuwakot | Salme | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 4
13723 | Nuwakot | Salme | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 4
13724 | Nuwakot | Salme | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 4
13725 | Nuwakot | Salme | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 4
13726 | Nuwakot | Salme | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 4
13727 | Nuwakot | Salme | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 4
13728 | Nuwakot | Salme | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 4
13729 | Nuwakot | Salme | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 4
13730 | Nuwakot | Salme | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Kispang | 4
13731 | Nuwakot | Salme | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Kispang | 4
13732 | Nuwakot | Samundradevi | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 560 | 191 | 2015-10-01 |  |  | Shivapuri | 6
13733 | Nuwakot | Samundradevi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 6
13734 | Nuwakot | Samundradevi | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 80 | 62 | 2015-10-01 |  |  | Shivapuri | 6
13735 | Nuwakot | Samundradevi | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 80 | 50 | 2015-10-01 |  |  | Shivapuri | 6
13736 | Nuwakot | Samundradevi | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 25 | 2015-10-01 |  |  | Shivapuri | 6
13737 | Nuwakot | Samundradevi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 6
13738 | Nuwakot | Samundradevi | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 560 | 171 | 2015-10-01 |  |  | Shivapuri | 6
13739 | Nuwakot | Samundradevi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-02-15 |  |  | Shivapuri | 6
13740 | Nuwakot | Samundradevi | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 96 | 49 | 2015-10-01 |  |  | Shivapuri | 6
13741 | Nuwakot | Samundradevi | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 96 | 52 | 2015-10-01 |  |  | Shivapuri | 6
13742 | Nuwakot | Samundradevi | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 16 | 2015-10-01 |  |  | Shivapuri | 6
13743 | Nuwakot | Samundradevi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 6 | 2018-02-15 |  |  | Shivapuri | 6
13744 | Nuwakot | Samundradevi | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 560 | 417 | 2015-10-01 |  |  | Shivapuri | 6
13745 | Nuwakot | Samundradevi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2018-02-14 | 2018-04-11 |  | Shivapuri | 6
13746 | Nuwakot | Samundradevi | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 139 | 91 | 2015-10-01 |  |  | Shivapuri | 6
13747 | Nuwakot | Samundradevi | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 139 | 78 | 2015-10-01 |  |  | Shivapuri | 6
13748 | Nuwakot | Samundradevi | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 32 | 2015-10-01 |  |  | Shivapuri | 6
13749 | Nuwakot | Samundradevi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 5 | 2018-02-14 | 2018-04-11 |  | Shivapuri | 6
13750 | Nuwakot | Samundradevi | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 560 | 268 | 2015-10-01 |  |  | Shivapuri | 6
13751 | Nuwakot | Samundradevi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 6
13752 | Nuwakot | Samundradevi | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 114 | 76 | 2015-10-01 |  |  | Shivapuri | 6
13753 | Nuwakot | Samundradevi | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 114 | 39 | 2015-10-01 |  |  | Shivapuri | 6
13754 | Nuwakot | Samundradevi | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 14 | 2015-10-01 |  |  | Shivapuri | 6
13755 | Nuwakot | Samundradevi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 6
13756 | Nuwakot | Samundradevi | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 560 | 177 | 2015-10-01 |  |  | Shivapuri | 6
13757 | Nuwakot | Samundradevi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 6
13758 | Nuwakot | Samundradevi | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 86 | 63 | 2015-10-01 |  |  | Shivapuri | 6
13759 | Nuwakot | Samundradevi | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 86 | 35 | 2015-10-01 |  |  | Shivapuri | 6
13760 | Nuwakot | Samundradevi | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 14 | 2015-10-01 |  |  | Shivapuri | 6
13761 | Nuwakot | Samundradevi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 6
13762 | Nuwakot | Samundradevi | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 560 | 143 | 2015-10-01 |  |  | Shivapuri | 6
13763 | Nuwakot | Samundradevi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 6
13764 | Nuwakot | Samundradevi | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 65 | 44 | 2015-10-01 |  |  | Shivapuri | 6
13765 | Nuwakot | Samundradevi | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 65 | 90 | 2015-10-01 |  |  | Shivapuri | 6
13766 | Nuwakot | Samundradevi | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 4 | 2015-10-01 |  |  | Shivapuri | 6
13767 | Nuwakot | Samundradevi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 6
13768 | Nuwakot | Samundradevi | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 560 | 91 | 2015-10-01 |  |  | Shivapuri | 6
13769 | Nuwakot | Samundradevi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2018-01-14 | 2018-03-10 |  | Shivapuri | 6
13770 | Nuwakot | Samundradevi | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 60 | 26 | 2015-10-01 |  |  | Shivapuri | 6
13771 | Nuwakot | Samundradevi | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 60 | 49 | 2015-10-01 |  |  | Shivapuri | 6
13772 | Nuwakot | Samundradevi | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 2 | 2015-10-01 |  |  | Shivapuri | 6
13773 | Nuwakot | Samundradevi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2018-01-14 | 2018-03-10 |  | Shivapuri | 6
13774 | Nuwakot | Samundradevi | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 560 | 229 | 2015-10-01 |  |  | Shivapuri | 6
13775 | Nuwakot | Samundradevi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-05-01 | 2017-06-24 |  | Shivapuri | 6
13776 | Nuwakot | Samundradevi | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 102 | 63 | 2015-10-01 |  |  | Shivapuri | 6
13777 | Nuwakot | Samundradevi | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 102 | 45 | 2015-10-01 |  |  | Shivapuri | 6
13778 | Nuwakot | Samundradevi | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 6 | 2015-10-01 |  |  | Shivapuri | 6
13779 | Nuwakot | Samundradevi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 4 | 2017-05-01 | 2017-06-24 |  | Shivapuri | 6
13780 | Nuwakot | Samundradevi | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 560 | 275 | 2015-10-01 |  |  | Shivapuri | 6
13781 | Nuwakot | Samundradevi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-03-21 |  |  | Shivapuri | 6
13782 | Nuwakot | Samundradevi | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 112 | 55 | 2015-10-01 |  |  | Shivapuri | 6
13783 | Nuwakot | Samundradevi | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 112 | 56 | 2015-10-01 |  |  | Shivapuri | 6
13784 | Nuwakot | Samundradevi | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 15 | 7 | 2015-10-01 |  |  | Shivapuri | 6
13785 | Nuwakot | Samundradevi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 6 | 2018-03-21 |  |  | Shivapuri | 6
13786 | Nuwakot | Samundratar | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 6
13787 | Nuwakot | Samundratar | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 6
13788 | Nuwakot | Samundratar | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 6
13789 | Nuwakot | Samundratar | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 6
13790 | Nuwakot | Samundratar | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 6
13791 | Nuwakot | Samundratar | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 6
13792 | Nuwakot | Samundratar | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 6
13793 | Nuwakot | Samundratar | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 6
13794 | Nuwakot | Samundratar | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 6
13795 | Nuwakot | Samundratar | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 6
13796 | Nuwakot | Samundratar | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 6
13797 | Nuwakot | Samundratar | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 6
13798 | Nuwakot | Samundratar | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 6
13799 | Nuwakot | Samundratar | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 6
13800 | Nuwakot | Samundratar | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 6
13801 | Nuwakot | Samundratar | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 6
13802 | Nuwakot | Samundratar | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 6
13803 | Nuwakot | Samundratar | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 6
13804 | Nuwakot | Shikharbesi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 7
13805 | Nuwakot | Shikharbesi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 7
13806 | Nuwakot | Shikharbesi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 7
13807 | Nuwakot | Shikharbesi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 7
13808 | Nuwakot | Shikharbesi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 7
13809 | Nuwakot | Shikharbesi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 7
13810 | Nuwakot | Shikharbesi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 7
13811 | Nuwakot | Shikharbesi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 7
13812 | Nuwakot | Shikharbesi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 7
13813 | Nuwakot | Shikharbesi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 7
13814 | Nuwakot | Shikharbesi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 7
13815 | Nuwakot | Shikharbesi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 7
13816 | Nuwakot | Shikharbesi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 7
13817 | Nuwakot | Shikharbesi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 7
13818 | Nuwakot | Shikharbesi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 7
13819 | Nuwakot | Shikharbesi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 7
13820 | Nuwakot | Shikharbesi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Dupcheshwar | 7
13821 | Nuwakot | Shikharbesi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Dupcheshwar | 7
13822 | Nuwakot | Sikre | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 199 | 2015-10-01 |  |  | Shivapuri | 4
13823 | Nuwakot | Sikre | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2018-02-21 | 2018-04-20 |  | Shivapuri | 4
13824 | Nuwakot | Sikre | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 66 | 45 | 2015-10-01 |  |  | Shivapuri | 4
13825 | Nuwakot | Sikre | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 66 | 9 | 2015-10-01 |  |  | Shivapuri | 4
13826 | Nuwakot | Sikre | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 7 | 2015-10-01 |  |  | Shivapuri | 4
13827 | Nuwakot | Sikre | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 7 | 2018-02-21 | 2018-04-20 |  | Shivapuri | 4
13828 | Nuwakot | Sikre | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 108 | 2015-10-01 |  |  | Shivapuri | 4
13829 | Nuwakot | Sikre | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-03-09 |  |  | Shivapuri | 4
13830 | Nuwakot | Sikre | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 47 | 34 | 2015-10-01 |  |  | Shivapuri | 4
13831 | Nuwakot | Sikre | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 47 | 8 | 2015-10-01 |  |  | Shivapuri | 4
13832 | Nuwakot | Sikre | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 7 | 2015-10-01 |  |  | Shivapuri | 4
13833 | Nuwakot | Sikre | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 5 | 2018-03-09 |  |  | Shivapuri | 4
13834 | Nuwakot | Sikre | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 141 | 2015-10-01 |  |  | Shivapuri | 4
13835 | Nuwakot | Sikre | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-04-13 |  |  | Shivapuri | 4
13836 | Nuwakot | Sikre | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 59 | 42 | 2015-10-01 |  |  | Shivapuri | 4
13837 | Nuwakot | Sikre | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 59 | 15 | 2015-10-01 |  |  | Shivapuri | 4
13838 | Nuwakot | Sikre | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 3 | 2015-10-01 |  |  | Shivapuri | 4
13839 | Nuwakot | Sikre | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 | 2018-04-13 |  |  | Shivapuri | 4
13840 | Nuwakot | Sikre | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 500 | 2015-10-01 |  |  | Shivapuri | 4
13841 | Nuwakot | Sikre | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2018-02-22 | 2018-04-17 |  | Shivapuri | 4
13842 | Nuwakot | Sikre | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Planned | 59 | 47 | 2015-10-01 |  |  | Shivapuri | 4
13843 | Nuwakot | Sikre | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 59 | 22 | 2015-10-01 |  |  | Shivapuri | 4
13844 | Nuwakot | Sikre | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 13 | 2015-10-01 |  |  | Shivapuri | 4
13845 | Nuwakot | Sikre | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 7 | 2018-02-22 | 2018-04-17 |  | Shivapuri | 4
13846 | Nuwakot | Sikre | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 278 | 2015-10-01 |  |  | Shivapuri | 4
13847 | Nuwakot | Sikre | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 4
13848 | Nuwakot | Sikre | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 55 | 46 | 2015-10-01 |  |  | Shivapuri | 4
13849 | Nuwakot | Sikre | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 55 | 7 | 2015-10-01 |  |  | Shivapuri | 4
13850 | Nuwakot | Sikre | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 9 | 2015-10-01 |  |  | Shivapuri | 4
13851 | Nuwakot | Sikre | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 0 |  |  |  | Shivapuri | 4
13852 | Nuwakot | Sikre | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 187 | 2015-10-01 |  |  | Shivapuri | 4
13853 | Nuwakot | Sikre | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 4
13854 | Nuwakot | Sikre | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 36 | 41 | 2015-10-01 |  |  | Shivapuri | 4
13855 | Nuwakot | Sikre | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 36 | 5 | 2015-10-01 |  |  | Shivapuri | 4
13856 | Nuwakot | Sikre | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 8 | 2015-10-01 |  |  | Shivapuri | 4
13857 | Nuwakot | Sikre | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 4
13858 | Nuwakot | Sikre | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 104 | 2015-10-01 |  |  | Shivapuri | 4
13859 | Nuwakot | Sikre | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 4
13860 | Nuwakot | Sikre | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 61 | 39 | 2015-10-01 |  |  | Shivapuri | 4
13861 | Nuwakot | Sikre | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 61 | 8 | 2015-10-01 |  |  | Shivapuri | 4
13862 | Nuwakot | Sikre | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 1 | 2015-10-01 |  |  | Shivapuri | 4
13863 | Nuwakot | Sikre | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 4
13864 | Nuwakot | Sikre | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 134 | 2015-10-01 |  |  | Shivapuri | 4
13865 | Nuwakot | Sikre | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 4
13866 | Nuwakot | Sikre | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 66 | 38 | 2015-10-01 |  |  | Shivapuri | 4
13867 | Nuwakot | Sikre | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 66 | 79 | 2015-10-01 |  |  | Shivapuri | 4
13868 | Nuwakot | Sikre | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 22 | 0 |  |  |  | Shivapuri | 4
13869 | Nuwakot | Sikre | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 4
13870 | Nuwakot | Sikre | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 104 | 2015-10-01 |  |  | Shivapuri | 4
13871 | Nuwakot | Sikre | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 4
13872 | Nuwakot | Sikre | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 30 | 13 | 2015-10-01 |  |  | Shivapuri | 4
13873 | Nuwakot | Sikre | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 30 | 0 | 2015-10-01 |  |  | Shivapuri | 4
13874 | Nuwakot | Sikre | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Planned | 15 | 0 |  |  |  | Shivapuri | 4
13875 | Nuwakot | Sikre | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 4
13876 | Nuwakot | Sundaradevi | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 4
13877 | Nuwakot | Sundaradevi | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 4
13878 | Nuwakot | Sundaradevi | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 4
13879 | Nuwakot | Sundaradevi | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 4
13880 | Nuwakot | Sundaradevi | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 4
13881 | Nuwakot | Sundaradevi | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 4
13882 | Nuwakot | Sundaradevi | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 4
13883 | Nuwakot | Sundaradevi | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 4
13884 | Nuwakot | Sundaradevi | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 4
13885 | Nuwakot | Sundaradevi | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 4
13886 | Nuwakot | Sundaradevi | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 4
13887 | Nuwakot | Sundaradevi | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 4
13888 | Nuwakot | Sundaradevi | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 4
13889 | Nuwakot | Sundaradevi | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 4
13890 | Nuwakot | Sundaradevi | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 4
13891 | Nuwakot | Sundaradevi | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 4
13892 | Nuwakot | Sundaradevi | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 4
13893 | Nuwakot | Sundaradevi | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 4
13894 | Nuwakot | Sunkhani | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 7
13895 | Nuwakot | Sunkhani | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 7
13896 | Nuwakot | Sunkhani | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 7
13897 | Nuwakot | Sunkhani | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 7
13898 | Nuwakot | Sunkhani | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 7
13899 | Nuwakot | Sunkhani | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 7
13900 | Nuwakot | Sunkhani | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 7
13901 | Nuwakot | Sunkhani | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 7
13902 | Nuwakot | Sunkhani | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 7
13903 | Nuwakot | Sunkhani | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 7
13904 | Nuwakot | Sunkhani | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 7
13905 | Nuwakot | Sunkhani | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 7
13906 | Nuwakot | Sunkhani | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 7
13907 | Nuwakot | Sunkhani | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 7
13908 | Nuwakot | Sunkhani | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 7
13909 | Nuwakot | Sunkhani | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 7
13910 | Nuwakot | Sunkhani | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 7
13911 | Nuwakot | Sunkhani | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 7
13912 | Nuwakot | Suryamati | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 3
13913 | Nuwakot | Suryamati | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 3
13914 | Nuwakot | Suryamati | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 3
13915 | Nuwakot | Suryamati | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 3
13916 | Nuwakot | Suryamati | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 3
13917 | Nuwakot | Suryamati | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 3
13918 | Nuwakot | Suryamati | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 3
13919 | Nuwakot | Suryamati | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 3
13920 | Nuwakot | Suryamati | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 3
13921 | Nuwakot | Suryamati | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 3
13922 | Nuwakot | Suryamati | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 3
13923 | Nuwakot | Suryamati | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 3
13924 | Nuwakot | Suryamati | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 3
13925 | Nuwakot | Suryamati | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 3
13926 | Nuwakot | Suryamati | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 3
13927 | Nuwakot | Suryamati | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 3
13928 | Nuwakot | Suryamati | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 3
13929 | Nuwakot | Suryamati | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 3
13930 | Nuwakot | Talakhu | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 148 | 2015-10-01 |  |  | Shivapuri | 1
13931 | Nuwakot | Talakhu | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 1
13932 | Nuwakot | Talakhu | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 115 | 90 | 2015-10-01 |  |  | Shivapuri | 1
13933 | Nuwakot | Talakhu | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 115 | 13 | 2015-10-01 |  |  | Shivapuri | 1
13934 | Nuwakot | Talakhu | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 7 | 2015-10-01 |  |  | Shivapuri | 1
13935 | Nuwakot | Talakhu | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 1
13936 | Nuwakot | Talakhu | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 431 | 2015-10-01 |  |  | Shivapuri | 1
13937 | Nuwakot | Talakhu | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-03-25 |  |  | Shivapuri | 1
13938 | Nuwakot | Talakhu | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 101 | 79 | 2015-10-01 |  |  | Shivapuri | 1
13939 | Nuwakot | Talakhu | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 101 | 6 | 2015-10-01 |  |  | Shivapuri | 1
13940 | Nuwakot | Talakhu | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 15 | 2015-10-01 |  |  | Shivapuri | 1
13941 | Nuwakot | Talakhu | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 7 | 2018-03-25 |  |  | Shivapuri | 1
13942 | Nuwakot | Talakhu | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 546 | 2015-10-01 |  |  | Shivapuri | 1
13943 | Nuwakot | Talakhu | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-04-03 |  |  | Shivapuri | 1
13944 | Nuwakot | Talakhu | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 97 | 99 | 2015-10-01 |  |  | Shivapuri | 1
13945 | Nuwakot | Talakhu | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 97 | 16 | 2015-10-01 |  |  | Shivapuri | 1
13946 | Nuwakot | Talakhu | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 34 | 2015-10-01 |  |  | Shivapuri | 1
13947 | Nuwakot | Talakhu | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 6 | 2018-04-03 |  |  | Shivapuri | 1
13948 | Nuwakot | Talakhu | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 227 | 2015-10-01 |  |  | Shivapuri | 1
13949 | Nuwakot | Talakhu | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 1 | 2017-12-04 | 2018-02-01 |  | Shivapuri | 1
13950 | Nuwakot | Talakhu | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Planned | 56 | 54 | 2015-10-01 |  |  | Shivapuri | 1
13951 | Nuwakot | Talakhu | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 56 | 148 | 2015-10-01 |  |  | Shivapuri | 1
13952 | Nuwakot | Talakhu | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 5 | 2015-10-01 |  |  | Shivapuri | 1
13953 | Nuwakot | Talakhu | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-12-04 | 2018-02-01 |  | Shivapuri | 1
13954 | Nuwakot | Talakhu | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 109 | 2015-10-01 |  |  | Shivapuri | 1
13955 | Nuwakot | Talakhu | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-05-08 |  |  | Shivapuri | 1
13956 | Nuwakot | Talakhu | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 73 | 70 | 2015-10-01 |  |  | Shivapuri | 1
13957 | Nuwakot | Talakhu | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 73 | 9 | 2015-10-01 |  |  | Shivapuri | 1
13958 | Nuwakot | Talakhu | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 11 | 2015-10-01 |  |  | Shivapuri | 1
13959 | Nuwakot | Talakhu | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 6 | 2018-05-08 |  |  | Shivapuri | 1
13960 | Nuwakot | Talakhu | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 72 | 2015-10-01 |  |  | Shivapuri | 1
13961 | Nuwakot | Talakhu | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 1
13962 | Nuwakot | Talakhu | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 89 | 80 | 2015-10-01 |  |  | Shivapuri | 1
13963 | Nuwakot | Talakhu | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 89 | 5 | 2015-10-01 |  |  | Shivapuri | 1
13964 | Nuwakot | Talakhu | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 6 | 2015-10-01 |  |  | Shivapuri | 1
13965 | Nuwakot | Talakhu | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 1
13966 | Nuwakot | Talakhu | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 243 | 2015-10-01 |  |  | Shivapuri | 1
13967 | Nuwakot | Talakhu | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-03-20 |  |  | Shivapuri | 1
13968 | Nuwakot | Talakhu | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 112 | 103 | 2015-10-01 |  |  | Shivapuri | 1
13969 | Nuwakot | Talakhu | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 112 | 13 | 2015-10-01 |  |  | Shivapuri | 1
13970 | Nuwakot | Talakhu | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 13 | 2015-10-01 |  |  | Shivapuri | 1
13971 | Nuwakot | Talakhu | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 7 | 2018-03-20 |  |  | Shivapuri | 1
13972 | Nuwakot | Talakhu | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 90 | 2015-10-01 |  |  | Shivapuri | 1
13973 | Nuwakot | Talakhu | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 1
13974 | Nuwakot | Talakhu | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 73 | 61 | 2015-10-01 |  |  | Shivapuri | 1
13975 | Nuwakot | Talakhu | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 73 | 19 | 2015-10-01 |  |  | Shivapuri | 1
13976 | Nuwakot | Talakhu | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 7 | 2015-10-01 |  |  | Shivapuri | 1
13977 | Nuwakot | Talakhu | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 1
13978 | Nuwakot | Talakhu | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 504 | 186 | 2015-10-01 |  |  | Shivapuri | 1
13979 | Nuwakot | Talakhu | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 1
13980 | Nuwakot | Talakhu | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 99 | 95 | 2015-10-01 |  |  | Shivapuri | 1
13981 | Nuwakot | Talakhu | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 99 | 11 | 2015-10-01 |  |  | Shivapuri | 1
13982 | Nuwakot | Talakhu | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 15 | 22 | 2015-10-01 |  |  | Shivapuri | 1
13983 | Nuwakot | Talakhu | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 1
13984 | Nuwakot | Taruka | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 2
13985 | Nuwakot | Taruka | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 2
13986 | Nuwakot | Taruka | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 2
13987 | Nuwakot | Taruka | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 2
13988 | Nuwakot | Taruka | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 2
13989 | Nuwakot | Taruka | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 2
13990 | Nuwakot | Taruka | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 2
13991 | Nuwakot | Taruka | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 2
13992 | Nuwakot | Taruka | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 3
13993 | Nuwakot | Taruka | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 3
13994 | Nuwakot | Taruka | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 3
13995 | Nuwakot | Taruka | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 3
13996 | Nuwakot | Taruka | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 3
13997 | Nuwakot | Taruka | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 3
13998 | Nuwakot | Taruka | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 3
13999 | Nuwakot | Taruka | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 3
14000 | Nuwakot | Taruka | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tarakeshwar | 3
14001 | Nuwakot | Taruka | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tarakeshwar | 3
14002 | Nuwakot | Thanapati | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 604 | 192 | 2015-10-01 |  |  | Shivapuri | 8
14003 | Nuwakot | Thanapati | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-04-02 |  |  | Shivapuri | 8
14004 | Nuwakot | Thanapati | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 111 | 78 | 2015-10-01 |  |  | Shivapuri | 8
14005 | Nuwakot | Thanapati | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 111 | 8 | 2015-10-01 |  |  | Shivapuri | 8
14006 | Nuwakot | Thanapati | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 25 | 2015-10-01 |  |  | Shivapuri | 8
14007 | Nuwakot | Thanapati | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 6 | 2018-04-02 |  |  | Shivapuri | 8
14008 | Nuwakot | Thanapati | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 604 | 143 | 2015-10-01 |  |  | Shivapuri | 8
14009 | Nuwakot | Thanapati | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-03-23 |  |  | Shivapuri | 8
14010 | Nuwakot | Thanapati | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 109 | 75 | 2015-10-01 |  |  | Shivapuri | 8
14011 | Nuwakot | Thanapati | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 109 | 28 | 2015-10-01 |  |  | Shivapuri | 8
14012 | Nuwakot | Thanapati | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 19 | 2015-10-01 |  |  | Shivapuri | 8
14013 | Nuwakot | Thanapati | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 6 | 2018-03-23 |  |  | Shivapuri | 8
14014 | Nuwakot | Thanapati | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 604 | 150 | 2015-10-01 |  |  | Shivapuri | 8
14015 | Nuwakot | Thanapati | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2018-03-22 | 2018-05-11 |  | Shivapuri | 8
14016 | Nuwakot | Thanapati | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 52 | 41 | 2015-10-01 |  |  | Shivapuri | 8
14017 | Nuwakot | Thanapati | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 52 | 25 | 2015-10-01 |  |  | Shivapuri | 8
14018 | Nuwakot | Thanapati | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 23 | 2015-10-01 |  |  | Shivapuri | 8
14019 | Nuwakot | Thanapati | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2018-03-22 | 2018-05-11 |  | Shivapuri | 8
14020 | Nuwakot | Thanapati | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 604 | 92 | 2015-10-01 |  |  | Shivapuri | 8
14021 | Nuwakot | Thanapati | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-12-17 | 2018-03-10 |  | Shivapuri | 8
14022 | Nuwakot | Thanapati | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 32 | 27 | 2015-10-01 |  |  | Shivapuri | 8
14023 | Nuwakot | Thanapati | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 32 | 7 | 2015-10-01 |  |  | Shivapuri | 8
14024 | Nuwakot | Thanapati | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 16 | 2015-10-01 |  |  | Shivapuri | 8
14025 | Nuwakot | Thanapati | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-12-17 | 2018-03-10 |  | Shivapuri | 8
14026 | Nuwakot | Thanapati | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 604 | 56 | 2015-10-01 |  |  | Likhu | 6
14027 | Nuwakot | Thanapati | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 6
14028 | Nuwakot | Thanapati | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 38 | 27 | 2015-10-01 |  |  | Likhu | 6
14029 | Nuwakot | Thanapati | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 38 | 15 | 2015-10-01 |  |  | Likhu | 6
14030 | Nuwakot | Thanapati | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 1 | 2015-10-01 |  |  | Likhu | 6
14031 | Nuwakot | Thanapati | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 6
14032 | Nuwakot | Thanapati | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 604 | 175 | 2015-10-01 |  |  | Shivapuri | 8
14033 | Nuwakot | Thanapati | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-12-27 | 2018-03-11 |  | Shivapuri | 8
14034 | Nuwakot | Thanapati | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 75 | 49 | 2015-10-01 |  |  | Shivapuri | 8
14035 | Nuwakot | Thanapati | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 75 | 4 | 2015-10-01 |  |  | Shivapuri | 8
14036 | Nuwakot | Thanapati | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 17 | 2015-10-01 |  |  | Shivapuri | 8
14037 | Nuwakot | Thanapati | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-12-27 | 2018-03-11 |  | Shivapuri | 8
14038 | Nuwakot | Thanapati | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 604 | 399 | 2015-10-01 |  |  | Shivapuri | 8
14039 | Nuwakot | Thanapati | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-05-04 | 2017-07-09 |  | Shivapuri | 8
14040 | Nuwakot | Thanapati | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 57 | 37 | 2015-10-01 |  |  | Shivapuri | 8
14041 | Nuwakot | Thanapati | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 57 | 11 | 2015-10-01 |  |  | Shivapuri | 8
14042 | Nuwakot | Thanapati | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 24 | 2015-10-01 |  |  | Shivapuri | 8
14043 | Nuwakot | Thanapati | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-05-04 | 2017-07-09 |  | Shivapuri | 8
14044 | Nuwakot | Thanapati | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 604 | 316 | 2015-10-01 |  |  | Shivapuri | 8
14045 | Nuwakot | Thanapati | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-03-27 |  |  | Shivapuri | 8
14046 | Nuwakot | Thanapati | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 66 | 28 | 2015-10-01 |  |  | Shivapuri | 8
14047 | Nuwakot | Thanapati | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 66 | 18 | 2015-10-01 |  |  | Shivapuri | 8
14048 | Nuwakot | Thanapati | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 9 | 2015-10-01 |  |  | Shivapuri | 8
14049 | Nuwakot | Thanapati | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 6 | 2018-03-27 |  |  | Shivapuri | 8
14050 | Nuwakot | Thanapati | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 600 | 186 | 2015-10-01 |  |  | Shivapuri | 8
14051 | Nuwakot | Thanapati | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Shivapuri | 8
14052 | Nuwakot | Thanapati | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 129 | 36 | 2015-10-01 |  |  | Shivapuri | 8
14053 | Nuwakot | Thanapati | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 129 | 2 | 2015-10-01 |  |  | Shivapuri | 8
14054 | Nuwakot | Thanapati | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 15 | 6 | 2015-10-01 |  |  | Shivapuri | 8
14055 | Nuwakot | Thanapati | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Shivapuri | 8
14056 | Nuwakot | Thansing | 1 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 716 | 2015-10-01 |  |  | Likhu | 6
14057 | Nuwakot | Thansing | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2018-02-21 | 2018-04-18 |  | Likhu | 6
14058 | Nuwakot | Thansing | 1 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 210 | 101 | 2015-10-01 |  |  | Likhu | 6
14059 | Nuwakot | Thansing | 1 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 210 | 138 | 2015-10-01 |  |  | Likhu | 6
14060 | Nuwakot | Thansing | 1 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 7 | 2015-10-01 |  |  | Likhu | 6
14061 | Nuwakot | Thansing | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 7 | 2018-02-21 | 2018-04-18 |  | Likhu | 6
14062 | Nuwakot | Thansing | 2 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 63 | 2015-10-01 |  |  | Likhu | 6
14063 | Nuwakot | Thansing | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 6
14064 | Nuwakot | Thansing | 2 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 142 | 50 | 2015-10-01 |  |  | Likhu | 6
14065 | Nuwakot | Thansing | 2 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 142 | 19 | 2015-10-01 |  |  | Likhu | 6
14066 | Nuwakot | Thansing | 2 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 4 | 2015-10-01 |  |  | Likhu | 6
14067 | Nuwakot | Thansing | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 6
14068 | Nuwakot | Thansing | 3 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 210 | 2015-10-01 |  |  | Likhu | 6
14069 | Nuwakot | Thansing | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 1 | 0 | 2018-03-19 |  |  | Likhu | 6
14070 | Nuwakot | Thansing | 3 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 135 | 75 | 2015-10-01 |  |  | Likhu | 6
14071 | Nuwakot | Thansing | 3 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 135 | 17 | 2015-10-01 |  |  | Likhu | 6
14072 | Nuwakot | Thansing | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 12 | 2015-10-01 |  |  | Likhu | 6
14073 | Nuwakot | Thansing | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 6 | 7 | 2018-03-19 |  |  | Likhu | 6
14074 | Nuwakot | Thansing | 4 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 672 | 2015-10-01 |  |  | Likhu | 6
14075 | Nuwakot | Thansing | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 6
14076 | Nuwakot | Thansing | 4 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 103 | 99 | 2015-10-01 |  |  | Likhu | 6
14077 | Nuwakot | Thansing | 4 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 103 | 8 | 2015-10-01 |  |  | Likhu | 6
14078 | Nuwakot | Thansing | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 8 | 2015-10-01 |  |  | Likhu | 6
14079 | Nuwakot | Thansing | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 6
14080 | Nuwakot | Thansing | 5 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 380 | 2015-10-01 |  |  | Likhu | 5
14081 | Nuwakot | Thansing | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 5
14082 | Nuwakot | Thansing | 5 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 179 | 150 | 2015-10-01 |  |  | Likhu | 5
14083 | Nuwakot | Thansing | 5 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 179 | 18 | 2015-10-01 |  |  | Likhu | 5
14084 | Nuwakot | Thansing | 5 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 19 | 2015-10-01 |  |  | Likhu | 5
14085 | Nuwakot | Thansing | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 5
14086 | Nuwakot | Thansing | 6 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 369 | 2015-10-01 |  |  | Likhu | 5
14087 | Nuwakot | Thansing | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 5
14088 | Nuwakot | Thansing | 6 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 190 | 187 | 2015-10-01 |  |  | Likhu | 5
14089 | Nuwakot | Thansing | 6 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 190 | 14 | 2015-10-01 |  |  | Likhu | 5
14090 | Nuwakot | Thansing | 6 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 7 | 2015-10-01 |  |  | Likhu | 5
14091 | Nuwakot | Thansing | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 5
14092 | Nuwakot | Thansing | 7 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 80 | 2015-10-01 |  |  | Likhu | 5
14093 | Nuwakot | Thansing | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Likhu | 5
14094 | Nuwakot | Thansing | 7 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 62 | 34 | 2015-10-01 |  |  | Likhu | 5
14095 | Nuwakot | Thansing | 7 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 62 | 15 | 2015-10-01 |  |  | Likhu | 5
14096 | Nuwakot | Thansing | 7 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 8 | 2015-10-01 |  |  | Likhu | 5
14097 | Nuwakot | Thansing | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Likhu | 5
14098 | Nuwakot | Thansing | 8 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 226 | 2015-10-01 |  |  | Kakani | 8
14099 | Nuwakot | Thansing | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-12-17 | 2018-03-09 |  | Kakani | 8
14100 | Nuwakot | Thansing | 8 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 360 | 123 | 2015-10-01 |  |  | Kakani | 8
14101 | Nuwakot | Thansing | 8 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 360 | 13 | 2015-10-01 |  |  | Kakani | 8
14102 | Nuwakot | Thansing | 8 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 22 | 94 | 2015-10-01 |  |  | Kakani | 8
14103 | Nuwakot | Thansing | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-12-17 | 2018-03-09 |  | Kakani | 8
14104 | Nuwakot | Thansing | 9 | NSET | NSET | USAID | Technical Assistance | Community reconstruction orientation | 4-5 sessions |  | # of participants | Yes | Ongoing | 616 | 450 | 2015-10-01 |  |  | Kakani | 8
14105 | Nuwakot | Thansing | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-12-22 | 2018-03-16 |  | Kakani | 8
14106 | Nuwakot | Thansing | 9 | NSET | NSET | USAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 203 | 107 | 2015-10-01 |  |  | Kakani | 8
14107 | Nuwakot | Thansing | 9 | NSET | NSET | USAID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Ongoing | 203 | 14 | 2015-10-01 |  |  | Kakani | 8
14108 | Nuwakot | Thansing | 9 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 16 | 55 | 2015-10-01 |  |  | Kakani | 8
14109 | Nuwakot | Thansing | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 8 | 2017-12-22 | 2018-03-16 |  | Kakani | 8
14110 | Nuwakot | Thaprek | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 4
14111 | Nuwakot | Thaprek | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 4
14112 | Nuwakot | Thaprek | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 4
14113 | Nuwakot | Thaprek | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 4
14114 | Nuwakot | Thaprek | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 4
14115 | Nuwakot | Thaprek | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 4
14116 | Nuwakot | Thaprek | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 4
14117 | Nuwakot | Thaprek | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 4
14118 | Nuwakot | Thaprek | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 4
14119 | Nuwakot | Thaprek | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 4
14120 | Nuwakot | Thaprek | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 4
14121 | Nuwakot | Thaprek | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 4
14122 | Nuwakot | Thaprek | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 4
14123 | Nuwakot | Thaprek | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 4
14124 | Nuwakot | Thaprek | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 4
14125 | Nuwakot | Thaprek | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 4
14126 | Nuwakot | Thaprek | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Panchakanya | 4
14127 | Nuwakot | Thaprek | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Panchakanya | 4
14128 | Nuwakot | Tupche | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 7
14129 | Nuwakot | Tupche | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 7
14130 | Nuwakot | Tupche | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 7
14131 | Nuwakot | Tupche | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 7
14132 | Nuwakot | Tupche | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 7
14133 | Nuwakot | Tupche | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 7
14134 | Nuwakot | Tupche | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 7
14135 | Nuwakot | Tupche | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 7
14136 | Nuwakot | Tupche | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 7
14137 | Nuwakot | Tupche | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 7
14138 | Nuwakot | Tupche | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 8
14139 | Nuwakot | Tupche | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 8
14140 | Nuwakot | Tupche | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 7
14141 | Nuwakot | Tupche | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 7
14142 | Nuwakot | Tupche | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 8
14143 | Nuwakot | Tupche | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 8
14144 | Nuwakot | Tupche | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Bidur | 9
14145 | Nuwakot | Tupche | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Bidur | 9
14146 | Nuwakot | Urleni | 1 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 1
14147 | Nuwakot | Urleni | 1 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 1
14148 | Nuwakot | Urleni | 2 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 1
14149 | Nuwakot | Urleni | 2 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 1
14150 | Nuwakot | Urleni | 3 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 1
14151 | Nuwakot | Urleni | 3 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 1
14152 | Nuwakot | Urleni | 4 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 1
14153 | Nuwakot | Urleni | 4 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 1
14154 | Nuwakot | Urleni | 5 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 1
14155 | Nuwakot | Urleni | 5 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 1
14156 | Nuwakot | Urleni | 6 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 1
14157 | Nuwakot | Urleni | 6 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 1
14158 | Nuwakot | Urleni | 7 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 1
14159 | Nuwakot | Urleni | 7 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 1
14160 | Nuwakot | Urleni | 8 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 1
14161 | Nuwakot | Urleni | 8 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 1
14162 | Nuwakot | Urleni | 9 | NSET | NSET | USAID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 1 | 0 |  |  |  | Tadi | 1
14163 | Nuwakot | Urleni | 9 | NSET | NSET | USAID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Planned | 6 | 0 |  |  |  | Tadi | 1
14164 | Nuwakot | Kalikahalde | 4 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 27 | 2017-06-04 | 2017-06-10 |  | Suryagadhi | 4
14165 | Nuwakot | Kharanitar | 3 | NSET | NSET | USAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 27 | 2017-06-04 | 2017-06-10 |  | Tadi | 3
14166 | Nuwakot | Manakamana | 1 | WR | NJS | WR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC - rural | # of trainees | Yes | Completed | 5 | 5 | 2016-04-17 | 2016-04-23 |  | Kispang | 5
14167 | Nuwakot | Manakamana | 3 | WR | NJS | WR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC - rural | # of trainees | Yes | Completed | 4 | 4 | 2016-04-17 | 2016-04-23 |  | Kispang | 5
14168 | Nuwakot | Manakamana | 4 | WR | NJS | WR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs. 50,000/- per household | # of households | Yes | Completed | 131 | 131 | 2016-08-17 | 2017-10-10 |  | Kispang | 5
14169 | Nuwakot | Manakamana | 4 | WR | NJS | WR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs. Rs. 150,000/- as per the govenrment grant distribution guidelines | # of households | Yes | Completed | 131 | 127 | 2016-11-25 | 2017-11-30 |  | Kispang | 5
14170 | Nuwakot | Manakamana | 4 | WR | NJS | WR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs. 100,000/- As per the Government grants distribuiton guidelines | # of households | Yes | Completed | 131 | 127 | 2016-12-15 | 2017-11-30 |  | Kispang | 5
14171 | Nuwakot | Manakamana | 4 | WR | NJS | WR | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 131 | 127 | 2016-09-01 | 2017-01-10 |  | Kispang | 5
14172 | Nuwakot | Manakamana | 4 | WR | NJS | WR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Providing transport support for construction of houses,house are under constructionn | # of households | Yes | Completed | 131 | 127 | 2016-05-01 | 2017-11-30 |  | Kispang | 5
14173 | Nuwakot | Manakamana | 4 | WR | NJS | WR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | tools | # of households | Yes | Completed | 131 | 127 | 2016-05-01 | 2017-10-15 |  | Kispang | 5
14174 | Nuwakot | Manakamana | 4 | WR | NJS | WR | Financial/Material/Labour Assistance | Top Ups | Vulnerable HHs | Rs. 50,000/- per household | # of households | Yes | Completed | 131 | 127 | 2016-11-25 | 2017-11-30 |  | Kispang | 5
14175 | Nuwakot | Manakamana | 4 | WR | NJS | WR | Technical Assistance | Demonstration Construction | House | Model Panel Construction (no. of constructions) model house | # of constructions | Yes | Completed | 1 | 1 | 2016-05-01 | 2016-11-21 |  | Kispang | 5
14176 | Nuwakot | Manakamana | 4 | WR | NJS | WR | Technical Assistance | Door-to-door technical assistance | Continuous | Inspection, monitoring, supervisio and facialition | # of households | Yes | Completed | 131 | 127 | 2016-05-01 | 2017-11-30 |  | Kispang | 5
14177 | Nuwakot | Manakamana | 4 | WR | NJS | WR | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | One Reconstruction Coordintion Committee is formed in each ward | # of committees | Yes | Completed | 1 | 1 | 2016-05-01 | 2016-11-15 |  | Kispang | 5
14178 | Nuwakot | Manakamana | 4 | WR | NJS | WR | Training | Short training | Carpenter | CTEVT for Carpenter (12person trained) | # of trainees | Yes | Completed | 12 | 12 | 2016-10-23 | 2016-10-29 |  | Kispang | 5
14179 | Nuwakot | Manakamana | 4 | WR | NJS | WR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC - rural | # of trainees | Yes | Completed | 24 | 24 | 2016-04-17 | 2016-04-23 |  | Kispang | 5
14180 | Nuwakot | Manakamana | 4 | WR | NJS | WR | Training | Vocational training | New masons (50 days OJT CTEVT) | DUDBC/CTEVT/NRA | # of trainees | Yes | Completed | 10 | 20 | 2017-02-09 | 2017-04-10 |  | Kispang | 5
14181 | Nuwakot | Manakamana | 4 | WR | NJS | WR | Reconstruction through contractors | Construction | Private house |  | # of constructions | Yes | Completed | 1 | 1 | 2017-09-01 | 2017-10-15 |  | Kispang | 5
14182 | Nuwakot | Manakamana | 4 | WR | NJS | WR | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Providing technical support such as design of house and BOQ | # of households supported | Yes | Completed | 131 | 127 | 2016-08-17 | 2017-11-30 |  | Kispang | 5
14183 | Nuwakot | Manakamana | 4 | WR | NJS | WR | Technical Assistance | Household reconstruction orientation | 2-3 sessions | Assist in enrollemnt and disbursement if the housing grants | # of households | Yes | Completed | 131 | 127 | 2016-07-01 | 2017-11-30 |  | Kispang | 5
14184 | Nuwakot | Manakamana | 5 | WR | NJS | WR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC - rural | # of trainees | Yes | Completed | 5 | 1 | 2016-04-17 | 2016-04-23 |  | Kispang | 5
14185 | Nuwakot | Manakamana | 6 | WR | NJS | WR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs. 50,000/- per household | # of households | Yes | Completed | 86 | 86 | 2016-08-17 | 2017-10-15 |  | Kispang | 5
14186 | Nuwakot | Manakamana | 6 | WR | NJS | WR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs. Rs. 150,000/- as per the govenrment grant distribution guidelines | # of households | Yes | Completed | 86 | 86 | 2016-11-25 | 2017-11-30 |  | Kispang | 5
14187 | Nuwakot | Manakamana | 6 | WR | NJS | WR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs. 100,000/- As per the Government grants distribuiton guidelines | # of households | Yes | Completed | 86 | 85 | 2016-12-15 | 2017-11-30 |  | Kispang | 5
14188 | Nuwakot | Manakamana | 6 | WR | NJS | WR | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 86 | 86 | 2016-08-01 | 2017-01-10 |  | Kispang | 5
14189 | Nuwakot | Manakamana | 6 | WR | NJS | WR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Providing transport support for construction of houses, house are under construction | # of households | Yes | Completed | 86 | 85 | 2016-05-01 | 2017-11-30 |  | Kispang | 5
14190 | Nuwakot | Manakamana | 6 | WR | NJS | WR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | tools | # of households | Yes | Completed | 86 | 86 | 2016-05-01 | 2017-11-30 |  | Kispang | 5
14191 | Nuwakot | Manakamana | 6 | WR | NJS | WR | Financial/Material/Labour Assistance | Top Ups | Vulnerable HHs | Rs. 50,000/- per household | # of households | Yes | Completed | 86 | 85 | 2016-11-25 | 2017-11-30 |  | Kispang | 5
14192 | Nuwakot | Manakamana | 6 | WR | NJS | WR | Technical Assistance | Demonstration Construction | House | Model Panel Construction (no. of constructions) model house | # of constructions | Yes | Completed | 3 | 3 | 2016-05-01 | 2016-11-21 |  | Kispang | 5
14193 | Nuwakot | Manakamana | 6 | WR | NJS | WR | Technical Assistance | Door-to-door technical assistance | Continuous | Inspection, monitoring, supervisio and facialition | # of households | Yes | Completed | 86 | 86 | 2016-05-01 | 2017-11-30 |  | Kispang | 5
14194 | Nuwakot | Manakamana | 6 | WR | NJS | WR | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | One Reconstruction Coordintion Committee is formed in each ward | # of committees | Yes | Completed | 1 | 1 | 2016-05-01 | 2016-11-15 |  | Kispang | 5
14195 | Nuwakot | Manakamana | 6 | WR | NJS | WR | Training | Short training | Carpenter | CTEVT for Carpenter (8 person trained ) | # of trainees | Yes | Completed | 8 | 8 | 2016-10-23 | 2016-10-29 |  | Kispang | 5
14196 | Nuwakot | Manakamana | 6 | WR | NJS | WR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC - rural | # of trainees | Yes | Completed | 20 | 19 | 2016-04-05 | 2016-04-11 |  | Kispang | 5
14197 | Nuwakot | Manakamana | 6 | WR | NJS | WR | Training | Vocational training | New masons (50 days OJT CTEVT) | DUDBC/CTEVT/NRA | # of trainees | Yes | Completed | 10 | 11 | 2017-02-10 | 2017-04-10 |  | Kispang | 5
14198 | Nuwakot | Manakamana | 6 | WR | NJS | WR | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Providing technical support such as design of house and BOQ | # of households supported | Yes | Completed | 157 | 155 | 2016-09-15 | 2017-11-30 |  | Kispang | 5
14199 | Nuwakot | Manakamana | 6 | WR | NJS | WR | Technical Assistance | Household reconstruction orientation | 2-3 sessions | Assist in enrollemnt, disbursement if the housing grants | # of households | Yes | Completed | 86 | 85 | 2016-07-01 | 2017-11-30 |  | Kispang | 5
14200 | Nuwakot | Manakamana | 7 | WR | NJS | WR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Rs. 50,000/- per household | # of households | Yes | Completed | 71 | 71 | 2016-08-17 | 2017-10-15 |  | Kispang | 5
14201 | Nuwakot | Manakamana | 7 | WR | NJS | WR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Rs. Rs. 150,000/- as per the govenrment grant distribution guidelines | # of households | Yes | Completed | 71 | 69 | 2016-11-25 | 2017-11-30 |  | Kispang | 5
14202 | Nuwakot | Manakamana | 7 | WR | NJS | WR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Rs. 100,000/- As per the Government grants distribuiton guidelines | # of households | Yes | Completed | 71 | 69 | 2016-12-15 | 2017-11-30 |  | Kispang | 5
14203 | Nuwakot | Manakamana | 7 | WR | NJS | WR | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits |  | # of kits | Yes | Completed | 71 | 71 | 2016-08-01 | 2017-01-10 |  | Kispang | 5
14204 | Nuwakot | Manakamana | 7 | WR | NJS | WR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Providin transport support for construction of houses,house are under construction | # of households | Yes | Completed | 71 | 69 | 2016-05-01 | 2017-11-30 |  | Kispang | 5
14205 | Nuwakot | Manakamana | 7 | WR | NJS | WR | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | tools | # of households | Yes | Completed | 71 | 71 | 2016-05-01 | 2017-11-30 |  | Kispang | 5
14206 | Nuwakot | Manakamana | 7 | WR | NJS | WR | Financial/Material/Labour Assistance | Top Ups | Vulnerable HHs | Rs. 50,000/- per household | # of households | Yes | Completed | 71 | 69 | 2016-11-25 | 2017-11-30 |  | Kispang | 5
14207 | Nuwakot | Manakamana | 7 | WR | NJS | WR | Technical Assistance | Demonstration Construction | House | Model Panel Construction (no. of constructions) model house | # of constructions | Yes | Completed | 2 | 2 | 2016-05-01 | 2016-11-21 |  | Kispang | 5
14208 | Nuwakot | Manakamana | 7 | WR | NJS | WR | Technical Assistance | Door-to-door technical assistance | Continuous | Inspection, monitoring, supervisio and facialition | # of households | Yes | Completed | 71 | 69 | 2016-05-01 | 2017-11-30 |  | Kispang | 5
14209 | Nuwakot | Manakamana | 7 | WR | NJS | WR | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | One Reconstruction Coordintion Committee is formed in each ward | # of committees | Yes | Completed | 1 | 1 | 2016-05-01 | 2016-11-16 |  | Kispang | 5
14210 | Nuwakot | Manakamana | 7 | WR | NJS | WR | Training | Short training | Carpenter | CTEVT for Carpenter (12 person trained ) | # of trainees | Yes | Completed | 12 | 12 | 2016-10-23 | 2016-10-29 |  | Kispang | 5
14211 | Nuwakot | Manakamana | 7 | WR | NJS | WR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC - rural | # of trainees | Yes | Completed | 21 | 21 | 2016-03-22 | 2016-03-30 |  | Kispang | 5
14212 | Nuwakot | Manakamana | 7 | WR | NJS | WR | Training | Vocational training | New masons (50 days OJT CTEVT) | DUDBC/CTEVT/NRA | # of trainees | Yes | Completed | 10 | 9 | 2017-02-11 | 2017-04-10 |  | Kispang | 5
14213 | Nuwakot | Manakamana | 7 | WR | NJS | WR | Technical Assistance | Household reconstruction orientation | 2-3 sessions | Assist in enrollment, disbursement if the housing grants | # of households | Yes | Completed | 71 | 71 | 2016-07-01 | 2017-11-30 |  | Kispang | 5
14214 | Nuwakot | Manakamana | 7 | WR | NJS | WR | Reconstruction through contractors | Construction | Private house | Community Building | # of constructions | Yes | Completed | 1 | 1 | 2017-07-01 | 2017-11-30 |  | Kispang | 5
14215 | Nuwakot | Manakamana | 8 | WR | NJS | WR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC - rural | # of trainees | Yes | Completed | 10 | 8 | 2016-04-05 | 2016-04-11 |  | Kispang | 5
14216 | Nuwakot | Manakamana | 4 | WR | NJS | WR | Technical Assistance | Community reconstruction orientation | 4-5 sessions | New Updates from NRA and new message of Organiztion is communicated through community reconstrcuion orientation | # of participants | Yes | Completed | 1000 | 1025 | 2016-07-01 | 2017-11-30 |  | Kispang | 5
14217 | Nuwakot | Manakamana | 9 | WR | NJS | WR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC - rural | # of trainees | Yes | Completed | 10 | 13 | 2016-04-05 | 2016-04-11 |  | Kispang | 5
14218 | Nuwakot | Manakamana | 6 | WR | NJS | WR | Technical Assistance | Community reconstruction orientation | 4-5 sessions | New Updates from NRA and new message of Organiztion is communicated through community reconstrcuion orientation | # of participants | Yes | Completed | 1000 | 980 | 2016-07-01 | 2017-11-30 |  | Kispang | 5
14219 | Nuwakot | Manakamana | 7 | WR | NJS | WR | Technical Assistance | Community reconstruction orientation | 4-5 sessions | New Updates from NRA and new message of Organiztion is communicated through community reconstrcuion orientation | # of participants | Yes | Completed | 1000 | 950 | 2016-07-01 | 2017-11-30 |  | Kispang | 5
14220 | Nuwakot | Tupche | 3 | WR | NJS | WR | Training | Short training | Masons (7 days DUDBC, rural or urban) | DUDBC - rural | # of trainees | Yes | Completed | 1 | 1 | 2016-04-17 | 2016-04-23 |  | Bidur | 7
14221 | Okhaldhunga | Baksa | 6 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-04-09 |  | Manebhanjyang | 2
14222 | Okhaldhunga | Balakhu | 1 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2017-05-03 | 2017-05-09 |  | Sunkoshi | 1
14223 | Okhaldhunga | Baruneshwor | 1 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-04-12 | Planning data - National Level | Molung | 2
14224 | Okhaldhunga | Baruneshwor | 2 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-02 | 2017-03-24 | Planning data - National Level | Molung | 2
14225 | Okhaldhunga | Baruneshwor | 2 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-19 | 2017-04-12 | Planning data - National Level | Molung | 2
14226 | Okhaldhunga | Baruneshwor | 3 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-02-03 | 2017-03-25 | Planning data - National Level | Molung | 2
14227 | Okhaldhunga | Baruneshwor | 3 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-04-12 | Planning data - National Level | Molung | 2
14228 | Okhaldhunga | Baruneshwor | 4 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-02-02 | 2017-03-24 | Planning data - National Level | Molung | 2
14229 | Okhaldhunga | Baruneshwor | 4 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-02-19 | 2017-04-12 | Planning data - National Level | Molung | 2
14230 | Okhaldhunga | Baruneshwor | 5 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-02-02 | 2017-03-24 | Planning data - National Level | Molung | 2
14231 | Okhaldhunga | Baruneshwor | 5 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-02 | 2016-04-30 |  | Molung | 2
14232 | Okhaldhunga | Baruneshwor | 5 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-02-19 | 2017-04-12 | Planning data - National Level | Molung | 2
14233 | Okhaldhunga | Baruneshwor | 6 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 4 | 4 | 2017-02-03 | 2017-03-25 | Planning data - National Level | Molung | 2
14234 | Okhaldhunga | Baruneshwor | 6 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 19 | 19 | 2017-02-19 | 2017-04-12 | Planning data - National Level | Molung | 2
14235 | Okhaldhunga | Baruneshwor | 7 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-02 | 2016-04-30 |  | Molung | 2
14236 | Okhaldhunga | Baruneshwor | 9 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-03 | 2017-03-25 | Planning data - National Level | Siddhicharan | 7
14237 | Okhaldhunga | Baruneshwor | 9 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-19 |  | Planning data - National Level | Siddhicharan | 7
14238 | Okhaldhunga | Betini | 3 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-02 | 2016-04-30 |  | Siddhicharan | 10
14239 | Okhaldhunga | Betini | 4 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-02 | 2016-04-30 |  | Siddhicharan | 10
14240 | Okhaldhunga | Bhadaure | 8 | HELVETAS | FECOFUN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2017-05-11 | 2017-05-17 |  | Chisankhugadhi | 6
14241 | Okhaldhunga | Bhussinga | 1 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 8
14242 | Okhaldhunga | Bhussinga | 1 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 8
14243 | Okhaldhunga | Bhussinga | 1 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 |  | Khijidemba | 8
14244 | Okhaldhunga | Bhussinga | 2 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 8
14245 | Okhaldhunga | Bhussinga | 3 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 8
14246 | Okhaldhunga | Bhussinga | 3 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 8
14247 | Okhaldhunga | Bhussinga | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 |  | Khijidemba | 8
14248 | Okhaldhunga | Bhussinga | 4 | UMN |  |  | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | total construction of houses | # of constructions | Yes | Completed | 6 | 6 |  |  | Full construction of house | Khijidemba | 8
14249 | Okhaldhunga | Bhussinga | 4 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 8
14250 | Okhaldhunga | Bhussinga | 4 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 8
14251 | Okhaldhunga | Bhussinga | 5 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 8
14252 | Okhaldhunga | Bhussinga | 6 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 8
14253 | Okhaldhunga | Bhussinga | 6 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 8
14254 | Okhaldhunga | Bhussinga | 7 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-12-23 | 2016-02-26 |  | Khijidemba | 8
14255 | Okhaldhunga | Bhussinga | 7 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 8
14256 | Okhaldhunga | Bhussinga | 7 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 8
14257 | Okhaldhunga | Bhussinga | 7 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-24 | 2016-02-19 |  | Khijidemba | 8
14258 | Okhaldhunga | Bhussinga | 8 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 8
14259 | Okhaldhunga | Bhussinga | 8 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 8
14260 | Okhaldhunga | Bhussinga | 9 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 8
14261 | Okhaldhunga | Bigutar | 1 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-05-03 | 2017-05-12 |  | Siddhicharan | 7
14262 | Okhaldhunga | Bigutar | 2 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-03 | 2017-05-12 |  | Siddhicharan | 7
14263 | Okhaldhunga | Bigutar | 2 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-02 | 2016-04-30 |  | Siddhicharan | 7
14264 | Okhaldhunga | Bigutar | 3 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-03 | 2017-05-12 |  | Siddhicharan | 7
14265 | Okhaldhunga | Bigutar | 5 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-03 | 2017-05-12 |  | Siddhicharan | 7
14266 | Okhaldhunga | Bigutar | 6 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2017-05-03 | 2017-05-12 |  | Siddhicharan | 7
14267 | Okhaldhunga | Bigutar | 8 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-03 | 2017-05-12 |  | Siddhicharan | 7
14268 | Okhaldhunga | Bigutar | 9 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-03 | 2017-05-12 |  | Siddhicharan | 7
14269 | Okhaldhunga | Bilandu | 1 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Champadevi | 8
14270 | Okhaldhunga | Bilandu | 2 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-05-15 | 2017-07-10 |  | Champadevi | 8
14271 | Okhaldhunga | Bilandu | 2 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 |  |  |  | Champadevi | 8
14272 | Okhaldhunga | Bilandu | 3 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 4 | 4 | 2017-05-15 | 2017-07-10 |  | Champadevi | 8
14273 | Okhaldhunga | Bilandu | 3 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 |  |  |  | Champadevi | 8
14274 | Okhaldhunga | Bilandu | 5 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Champadevi | 8
14275 | Okhaldhunga | Bilandu | 6 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 4 | 4 | 2017-05-15 | 2017-07-10 |  | Champadevi | 9
14276 | Okhaldhunga | Bilandu | 6 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Champadevi | 9
14277 | Okhaldhunga | Bilandu | 8 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-05-15 | 2017-07-10 |  | Champadevi | 9
14278 | Okhaldhunga | Bilandu | 9 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 4 | 4 | 2017-05-15 | 2017-07-10 |  | Champadevi | 9
14279 | Okhaldhunga | Bilandu | 9 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Champadevi | 9
14280 | Okhaldhunga | Chyanam | 1 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-15 | 2017-07-10 |  | Sunkoshi | 7
14281 | Okhaldhunga | Chyanam | 2 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-15 | 2017-07-10 |  | Sunkoshi | 7
14282 | Okhaldhunga | Chyanam | 3 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-15 | 2017-07-10 |  | Sunkoshi | 7
14283 | Okhaldhunga | Chyanam | 4 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-05-15 | 2017-07-10 | Planning data - National Level | Sunkoshi | 8
14284 | Okhaldhunga | Chyanam | 4 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 8 | 8 | 2017-05-15 | 2017-07-10 | Planning data - National Level | Sunkoshi | 8
14285 | Okhaldhunga | Chyanam | 5 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-05-15 | 2017-07-10 | Planning data - National Level | Sunkoshi | 8
14286 | Okhaldhunga | Chyanam | 5 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 12 | 12 | 2017-05-15 | 2017-07-10 | Planning data - National Level | Sunkoshi | 8
14287 | Okhaldhunga | Chyanam | 6 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-15 | 2017-07-10 |  | Sunkoshi | 7
14288 | Okhaldhunga | Chyanam | 7 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-05-15 | 2017-07-10 | Planning data - National Level | Sunkoshi | 7
14289 | Okhaldhunga | Chyanam | 7 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 8 | 8 | 2017-05-15 | 2017-07-10 | Planning data - National Level | Sunkoshi | 7
14290 | Okhaldhunga | Chyanam | 8 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 12 | 12 | 2017-05-15 | 2017-07-10 |  | Sunkoshi | 8
14291 | Okhaldhunga | Diyale | 6 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-04-09 |  | Chisankhugadhi | 3
14292 | Okhaldhunga | Fediguth | 1 | HELVETAS |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Champadevi | 4
14293 | Okhaldhunga | Fediguth | 1 | HELVETAS | TRACE |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Champadevi | 4
14294 | Okhaldhunga | Fediguth | 2 | HELVETAS |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Champadevi | 4
14295 | Okhaldhunga | Fediguth | 2 | HELVETAS | TRACE |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 19 | 19 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Champadevi | 4
14296 | Okhaldhunga | Fediguth | 3 | HELVETAS |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Champadevi | 4
14297 | Okhaldhunga | Fediguth | 3 | HELVETAS | TRACE |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Champadevi | 4
14298 | Okhaldhunga | Fediguth | 5 | HELVETAS |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Champadevi | 5
14299 | Okhaldhunga | Fediguth | 5 | HELVETAS | TRACE |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Champadevi | 5
14300 | Okhaldhunga | Fediguth | 7 | HELVETAS |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Champadevi | 5
14301 | Okhaldhunga | Fediguth | 7 | HELVETAS | TRACE |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Champadevi | 5
14302 | Okhaldhunga | Fediguth | 9 | HELVETAS |  |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 3 | 3 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Champadevi | 4
14303 | Okhaldhunga | Fediguth | 9 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-05-15 | 2017-07-10 |  | Champadevi | 4
14304 | Okhaldhunga | Fediguth | 9 | HELVETAS | TRACE |  | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Champadevi | 4
14305 | Okhaldhunga | Fulbari | 1 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Construction Carpenter Treaning | # of trainees | Yes | Completed | 1 | 1 | 2015-12-21 | 2016-02-20 | Event Id-Efsr-2JTI-01-0008/2015 | Champadevi | 6
14306 | Okhaldhunga | Fulbari | 2 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 2 | 2 | 2015-12-21 | 2016-02-19 | Event Id-Efsr-2JTI-01-0002/2015 | Champadevi | 6
14307 | Okhaldhunga | Fulbari | 2 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 2 | 2 | 2015-12-21 | 2016-02-20 |  | Champadevi | 6
14308 | Okhaldhunga | Fulbari | 2 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-21 | 2016-02-20 | Event Id-Efsr-2JTI-01-0007/2015 | Champadevi | 6
14309 | Okhaldhunga | Fulbari | 3 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-21 | 2016-02-20 |  | Champadevi | 6
14310 | Okhaldhunga | Fulbari | 3 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-21 | 2016-02-19 |  | Champadevi | 6
14311 | Okhaldhunga | Fulbari | 3 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-21 | 2016-02-20 |  | Champadevi | 6
14312 | Okhaldhunga | Fulbari | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-21 | 2016-02-20 |  | Champadevi | 6
14313 | Okhaldhunga | Fulbari | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-21 | 2016-02-20 |  | Champadevi | 6
14314 | Okhaldhunga | Fulbari | 5 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-21 | 2016-02-19 |  | Champadevi | 6
14315 | Okhaldhunga | Fulbari | 5 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-21 | 2016-02-20 |  | Champadevi | 6
14316 | Okhaldhunga | Fulbari | 6 | HELVETAS | JTI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 4 | 4 | 2016-03-25 | 2016-02-28 |  | Champadevi | 6
14317 | Okhaldhunga | Fulbari | 6 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-03-11 | 2017-04-29 |  | Champadevi | 6
14318 | Okhaldhunga | Fulbari | 6 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 4 | 4 | 2017-05-09 | 2017-06-27 |  | Champadevi | 6
14319 | Okhaldhunga | Fulbari | 6 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-21 | 2016-02-20 |  | Champadevi | 6
14320 | Okhaldhunga | Fulbari | 6 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-21 | 2016-02-19 |  | Champadevi | 6
14321 | Okhaldhunga | Fulbari | 6 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-21 | 2016-02-20 |  | Champadevi | 6
14322 | Okhaldhunga | Fulbari | 6 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-03-10 | 2017-04-28 |  | Champadevi | 6
14323 | Okhaldhunga | Fulbari | 7 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-21 | 2016-02-20 |  | Champadevi | 7
14324 | Okhaldhunga | Fulbari | 8 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-03-10 | 2017-04-28 |  | Champadevi | 7
14325 | Okhaldhunga | Fulbari | 8 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 3 | 3 | 2017-05-11 | 2017-06-28 |  | Champadevi | 7
14326 | Okhaldhunga | Fulbari | 8 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 27 | 27 | 2017-02-19 | 2017-04-09 |  | Champadevi | 7
14327 | Okhaldhunga | Fulbari | 9 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 4 | 4 | 2017-02-27 | 2017-04-17 |  | Champadevi | 7
14328 | Okhaldhunga | Fulbari | 9 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 3 | 3 | 2017-05-09 | 2017-06-27 |  | Champadevi | 7
14329 | Okhaldhunga | Fulbari | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-21 | 2016-02-20 |  | Champadevi | 7
14330 | Okhaldhunga | Fulbari | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-21 | 2016-02-20 |  | Champadevi | 7
14331 | Okhaldhunga | Fulbari | 9 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 33 | 33 | 2017-02-27 | 2017-04-17 |  | Champadevi | 7
14332 | Okhaldhunga | Gamnangtar | 1 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Construction Carpenter Treaning | # of trainees | Yes | Completed | 5 | 5 | 2016-06-26 | 2016-08-25 | Event id-Efsr-2JTI-01-0006/2016 | Likhu | 6
14333 | Okhaldhunga | Gamnangtar | 1 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 7 | 7 | 2016-06-26 | 2016-08-25 | Event id-Efsr-2JTI-01-0003/2016 | Likhu | 6
14334 | Okhaldhunga | Gamnangtar | 1 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-25 | 2016-05-01 |  | Likhu | 6
14335 | Okhaldhunga | Gamnangtar | 2 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-25 | 2016-05-01 |  | Likhu | 6
14336 | Okhaldhunga | Gamnangtar | 3 | MEDAIR | LCDF |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-06-18 | 2016-06-29 |  | Likhu | 6
14337 | Okhaldhunga | Gamnangtar | 3 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-25 | 2016-05-01 |  | Likhu | 6
14338 | Okhaldhunga | Gamnangtar | 4 | MEDAIR | LCDF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 4 | 4 | 2016-04-19 | 2016-04-23 |  | Likhu | 6
14339 | Okhaldhunga | Gamnangtar | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-21 | Event id-Efsr-2JTI-01-0001/2016 | Likhu | 6
14340 | Okhaldhunga | Gamnangtar | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 4 | 4 | 2016-06-25 | 2016-08-25 | Event id-Efsr-2JTI-01-0002/2016 | Likhu | 6
14341 | Okhaldhunga | Gamnangtar | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-26 | 2016-08-25 |  | Likhu | 6
14342 | Okhaldhunga | Gamnangtar | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-26 | 2016-08-25 |  | Likhu | 6
14343 | Okhaldhunga | Gamnangtar | 4 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-25 | 2016-05-01 |  | Likhu | 6
14344 | Okhaldhunga | Gamnangtar | 5 | MEDAIR | LCDF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 5 | 5 | 2016-04-19 | 2016-04-23 |  | Likhu | 6
14345 | Okhaldhunga | Gamnangtar | 5 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-21 |  | Likhu | 6
14346 | Okhaldhunga | Gamnangtar | 5 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-25 | 2016-08-25 |  | Likhu | 6
14347 | Okhaldhunga | Gamnangtar | 5 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-26 | 2016-08-25 |  | Likhu | 6
14348 | Okhaldhunga | Gamnangtar | 5 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-25 | 2016-05-01 |  | Likhu | 6
14349 | Okhaldhunga | Gamnangtar | 6 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-25 | 2016-05-01 |  | Likhu | 7
14350 | Okhaldhunga | Gamnangtar | 7 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-08-21 |  | Likhu | 7
14351 | Okhaldhunga | Gamnangtar | 7 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-25 | 2016-05-01 |  | Likhu | 7
14352 | Okhaldhunga | Gamnangtar | 8 | MEDAIR | LCDF |  | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-06-03 | 2016-06-25 |  | Likhu | 7
14353 | Okhaldhunga | Gamnangtar | 8 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-22 | 2016-08-21 |  | Likhu | 7
14354 | Okhaldhunga | Gamnangtar | 8 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-25 | 2016-08-25 |  | Likhu | 7
14355 | Okhaldhunga | Gamnangtar | 8 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-26 | 2016-08-25 |  | Likhu | 7
14356 | Okhaldhunga | Gamnangtar | 8 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-25 | 2016-05-01 |  | Likhu | 7
14357 | Okhaldhunga | Gamnangtar | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-08-21 |  | Likhu | 7
14358 | Okhaldhunga | Gamnangtar | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-26 | 2016-08-25 |  | Likhu | 7
14359 | Okhaldhunga | Gamnangtar | 9 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-25 | 2016-05-01 |  | Likhu | 7
14360 | Okhaldhunga | Kalikadevi | 1 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-22 | 2016-04-26 |  | Champadevi | 3
14361 | Okhaldhunga | Kalikadevi | 2 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-22 | 2016-04-26 |  | Champadevi | 3
14362 | Okhaldhunga | Kalikadevi | 3 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-22 | 2016-04-26 |  | Champadevi | 3
14363 | Okhaldhunga | Kalikadevi | 4 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-26 |  | Champadevi | 7
14364 | Okhaldhunga | Kalikadevi | 5 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-22 | 2016-04-26 |  | Champadevi | 3
14365 | Okhaldhunga | Kalikadevi | 6 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-26 |  | Champadevi | 3
14366 | Okhaldhunga | Kalikadevi | 7 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-22 | 2016-04-26 |  | Champadevi | 3
14367 | Okhaldhunga | Kalikadevi | 8 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-26 |  | Champadevi | 3
14368 | Okhaldhunga | Kalikadevi | 9 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-22 | 2016-04-26 |  | Champadevi | 3
14369 | Okhaldhunga | Kaptigaun(Khigikati) | 1 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 4
14370 | Okhaldhunga | Kaptigaun(Khigikati) | 2 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 4
14371 | Okhaldhunga | Kaptigaun(Khigikati) | 3 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 4
14372 | Okhaldhunga | Kaptigaun(Khigikati) | 4 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 4
14373 | Okhaldhunga | Kaptigaun(Khigikati) | 5 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 4
14374 | Okhaldhunga | Kaptigaun(Khigikati) | 8 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 4
14375 | Okhaldhunga | Kaptigaun(Khigikati) | 9 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 4
14376 | Okhaldhunga | Katunje | 1 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-05-15 | 2017-07-10 |  | Sunkoshi | 9
14377 | Okhaldhunga | Katunje | 1 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 8 | 8 |  |  | Planning data - National Level | Sunkoshi | 9
14378 | Okhaldhunga | Katunje | 2 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-05-15 | 2017-07-10 |  | Sunkoshi | 9
14379 | Okhaldhunga | Katunje | 2 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 9 |  |  | Planning data - National Level | Sunkoshi | 9
14380 | Okhaldhunga | Katunje | 3 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 |  |  | Planning data - National Level | Sunkoshi | 9
14381 | Okhaldhunga | Katunje | 5 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-05-15 | 2017-07-10 |  | Sunkoshi | 9
14382 | Okhaldhunga | Katunje | 5 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 |  |  | Planning data - National Level | Sunkoshi | 9
14383 | Okhaldhunga | Katunje | 6 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-05-15 | 2017-07-10 |  | Sunkoshi | 10
14384 | Okhaldhunga | Katunje | 6 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 |  |  | Planning data - National Level | Sunkoshi | 10
14385 | Okhaldhunga | Katunje | 7 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-05-15 | 2017-07-10 |  | Sunkoshi | 10
14386 | Okhaldhunga | Katunje | 7 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 15 | 15 |  |  | Planning data - National Level | Sunkoshi | 10
14387 | Okhaldhunga | Katunje | 8 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-05-15 | 2017-07-10 |  | Sunkoshi | 10
14388 | Okhaldhunga | Katunje | 8 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 |  |  | Planning data - National Level | Sunkoshi | 10
14389 | Okhaldhunga | Katunje | 9 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-05-15 | 2017-07-10 |  | Sunkoshi | 10
14390 | Okhaldhunga | Katunje | 9 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 9 |  |  | Planning data - National Level | Sunkoshi | 10
14391 | Okhaldhunga | KhijiChandeshwori | 1 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-05-03 | 2017-06-21 |  | Khijidemba | 3
14392 | Okhaldhunga | KhijiChandeshwori | 1 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 3
14393 | Okhaldhunga | KhijiChandeshwori | 1 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-22 | 2016-04-26 |  | Khijidemba | 3
14394 | Okhaldhunga | KhijiChandeshwori | 1 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 8 | 8 | 2017-05-04 | 2017-06-25 | Planning data - National Level | Khijidemba | 3
14395 | Okhaldhunga | KhijiChandeshwori | 2 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-05-03 | 2017-06-21 | Planning data - National Level | Khijidemba | 3
14396 | Okhaldhunga | KhijiChandeshwori | 2 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 3
14397 | Okhaldhunga | KhijiChandeshwori | 2 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-04 | 2017-06-25 | Planning data - National Level | Khijidemba | 3
14398 | Okhaldhunga | KhijiChandeshwori | 3 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-05-03 | 2017-06-21 | Planning data - National Level | Khijidemba | 3
14399 | Okhaldhunga | KhijiChandeshwori | 3 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 3
14400 | Okhaldhunga | KhijiChandeshwori | 3 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 3
14401 | Okhaldhunga | KhijiChandeshwori | 3 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-22 | 2016-04-26 |  | Khijidemba | 3
14402 | Okhaldhunga | KhijiChandeshwori | 3 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-04 | 2017-06-25 | Planning data - National Level | Khijidemba | 3
14403 | Okhaldhunga | KhijiChandeshwori | 4 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 3
14404 | Okhaldhunga | KhijiChandeshwori | 4 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-04 | 2017-06-25 | Planning data - National Level | Khijidemba | 3
14405 | Okhaldhunga | KhijiChandeshwori | 5 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-05-03 | 2017-06-21 | Planning data - National Level | Khijidemba | 3
14406 | Okhaldhunga | KhijiChandeshwori | 5 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 |  |  | mason training implemented by them self | Khijidemba | 3
14407 | Okhaldhunga | KhijiChandeshwori | 5 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 3
14408 | Okhaldhunga | KhijiChandeshwori | 5 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-26 |  | Khijidemba | 3
14409 | Okhaldhunga | KhijiChandeshwori | 5 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-04 | 2017-06-25 | Planning data - National Level | Khijidemba | 3
14410 | Okhaldhunga | KhijiChandeshwori | 6 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-05-03 | 2017-06-21 | Planning data - National Level | Khijidemba | 3
14411 | Okhaldhunga | KhijiChandeshwori | 6 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 |  |  | mason training implemented by them self | Khijidemba | 3
14412 | Okhaldhunga | KhijiChandeshwori | 6 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 3
14413 | Okhaldhunga | KhijiChandeshwori | 6 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-26 |  | Khijidemba | 3
14414 | Okhaldhunga | KhijiChandeshwori | 6 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 22 | 22 | 2017-05-04 | 2017-06-25 | Planning data - National Level | Khijidemba | 3
14415 | Okhaldhunga | KhijiChandeshwori | 7 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-05-03 | 2017-06-21 | Planning data - National Level | Khijidemba | 3
14416 | Okhaldhunga | KhijiChandeshwori | 7 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 3
14417 | Okhaldhunga | KhijiChandeshwori | 7 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 3
14418 | Okhaldhunga | KhijiChandeshwori | 7 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-04 | 2017-06-25 | Planning data - National Level | Khijidemba | 3
14419 | Okhaldhunga | KhijiChandeshwori | 8 | UMN |  |  | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | total construction of houses | # of constructions | Yes | Completed | 1 | 1 |  |  | Full construction of house | Khijidemba | 3
14420 | Okhaldhunga | KhijiChandeshwori | 8 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-05-03 | 2017-06-21 | Planning data - National Level | Khijidemba | 3
14421 | Okhaldhunga | KhijiChandeshwori | 8 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 3
14422 | Okhaldhunga | KhijiChandeshwori | 8 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 3
14423 | Okhaldhunga | KhijiChandeshwori | 8 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-26 |  | Khijidemba | 3
14424 | Okhaldhunga | KhijiChandeshwori | 8 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-05-04 | 2017-06-25 | Planning data - National Level | Khijidemba | 3
14425 | Okhaldhunga | KhijiChandeshwori | 9 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 3
14426 | Okhaldhunga | Khijifalate | 1 | UMN |  |  | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | total construction of houses | # of constructions | Yes | Completed | 1 | 1 |  |  | Full construction of house | Khijidemba | 5
14427 | Okhaldhunga | Khijifalate | 1 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 5
14428 | Okhaldhunga | Khijifalate | 1 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Construction Carpenter Treaning | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-21 | Event id-Efsr-2JTI-01-0007/2016 | Khijidemba | 5
14429 | Okhaldhunga | Khijifalate | 1 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 4 | 4 | 2016-06-22 | 2016-08-21 | Event id-Efsr-2JTI-01-0005/2016 | Khijidemba | 5
14430 | Okhaldhunga | Khijifalate | 2 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 |  |  | mason training implemented by them self | Khijidemba | 5
14431 | Okhaldhunga | Khijifalate | 2 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 5
14432 | Okhaldhunga | Khijifalate | 2 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-22 | 2016-08-21 |  | Khijidemba | 5
14433 | Okhaldhunga | Khijifalate | 3 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 5
14434 | Okhaldhunga | Khijifalate | 3 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 5
14435 | Okhaldhunga | Khijifalate | 3 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-21 |  | Khijidemba | 5
14436 | Okhaldhunga | Khijifalate | 4 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 5
14437 | Okhaldhunga | Khijifalate | 4 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 5
14438 | Okhaldhunga | Khijifalate | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-21 |  | Khijidemba | 5
14439 | Okhaldhunga | Khijifalate | 5 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 5
14440 | Okhaldhunga | Khijifalate | 6 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 6
14441 | Okhaldhunga | Khijifalate | 6 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 6
14442 | Okhaldhunga | Khijifalate | 6 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-08-21 |  | Khijidemba | 6
14443 | Okhaldhunga | Khijifalate | 7 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 6
14444 | Okhaldhunga | Khijifalate | 7 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 6
14445 | Okhaldhunga | Khijifalate | 8 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 6
14446 | Okhaldhunga | Khijifalate | 8 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 6
14447 | Okhaldhunga | Khijifalate | 8 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-04-09 |  | Khijidemba | 6
14448 | Okhaldhunga | Khijifalate | 9 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 6
14449 | Okhaldhunga | Khijifalate | 9 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 6
14450 | Okhaldhunga | Khijifalate | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 10 | 10 | 2016-06-22 | 2016-08-21 | Event id-Efsr-2JTI-01-0004/2016 | Khijidemba | 6
14451 | Okhaldhunga | Khijifalate | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-22 | 2016-08-21 |  | Khijidemba | 6
14452 | Okhaldhunga | Kuntadevi | 2 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-04-09 |  | Molung | 1
14453 | Okhaldhunga | Kuntadevi | 9 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-02 | 2016-04-30 |  | Molung | 1
14454 | Okhaldhunga | Madhavpur | 1 | USAID-SABAL | KOSIS-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-06-29 |  | Manebhanjyang | 9
14455 | Okhaldhunga | Madhavpur | 1 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-05-03 | 2017-05-18 |  | Manebhanjyang | 9
14456 | Okhaldhunga | Madhavpur | 3 | USAID-SABAL | KOSIS-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-06-29 |  | Manebhanjyang | 9
14457 | Okhaldhunga | Madhavpur | 4 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-05-03 | 2017-05-18 |  | Manebhanjyang | 9
14458 | Okhaldhunga | Madhavpur | 5 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-05-03 | 2017-05-18 |  | Manebhanjyang | 9
14459 | Okhaldhunga | Madhavpur | 7 | USAID-SABAL | KOSIS-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-06-29 |  | Manebhanjyang | 9
14460 | Okhaldhunga | Madhavpur | 7 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-03 | 2017-05-18 |  | Manebhanjyang | 9
14461 | Okhaldhunga | Madhavpur | 8 | USAID-SABAL | KOSIS-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-06-29 |  | Manebhanjyang | 9
14462 | Okhaldhunga | Madhavpur | 8 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-03 | 2017-05-18 |  | Manebhanjyang | 9
14463 | Okhaldhunga | Madhavpur | 9 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-03 | 2017-05-18 |  | Manebhanjyang | 9
14464 | Okhaldhunga | Madhavpur | 9 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-12 | 2017-05-18 |  | Manebhanjyang | 9
14465 | Okhaldhunga | Manebhanjyang | 2 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-12 | 2017-05-18 |  | Manebhanjyang | 5
14466 | Okhaldhunga | Manebhanjyang | 4 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-03 | 2017-05-18 |  | Manebhanjyang | 5
14467 | Okhaldhunga | Manebhanjyang | 5 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-05-03 | 2017-05-18 |  | Manebhanjyang | 5
14468 | Okhaldhunga | Manebhanjyang | 6 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-03 | 2017-05-18 |  | Manebhanjyang | 5
14469 | Okhaldhunga | Manebhanjyang | 8 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-12 | 2017-05-18 |  | Manebhanjyang | 5
14470 | Okhaldhunga | Manebhanjyang | 9 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-03 | 2017-05-18 |  | Manebhanjyang | 5
14471 | Okhaldhunga | Moli | 8 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-02 | 2016-04-30 |  | Manebhanjyang | 1
14472 | Okhaldhunga | Mulkharka | 1 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-26 |  | Sunkoshi | 5
14473 | Okhaldhunga | Mulkharka | 1 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 23 | 23 | 2017-05-19 | 2017-05-25 |  | Sunkoshi | 5
14474 | Okhaldhunga | Mulkharka | 1 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 29 | 29 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Sunkoshi | 5
14475 | Okhaldhunga | Mulkharka | 2 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-04-09 |  | Sunkoshi | 5
14476 | Okhaldhunga | Mulkharka | 2 | HELVETAS |  | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-03-01 | 2017-04-19 |  | Sunkoshi | 5
14477 | Okhaldhunga | Mulkharka | 2 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-22 | 2016-04-26 |  | Sunkoshi | 5
14478 | Okhaldhunga | Mulkharka | 2 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 19 | 19 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Sunkoshi | 5
14479 | Okhaldhunga | Mulkharka | 3 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-04-09 |  | Sunkoshi | 5
14480 | Okhaldhunga | Mulkharka | 3 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-04-22 | 2016-04-26 |  | Sunkoshi | 5
14481 | Okhaldhunga | Mulkharka | 3 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-19 | 2017-05-25 |  | Sunkoshi | 5
14482 | Okhaldhunga | Mulkharka | 3 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 8 | 8 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Sunkoshi | 5
14483 | Okhaldhunga | Mulkharka | 4 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-26 |  | Sunkoshi | 5
14484 | Okhaldhunga | Mulkharka | 6 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-04-09 |  | Sunkoshi | 6
14485 | Okhaldhunga | Mulkharka | 6 | HELVETAS |  | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-04-09 |  | Sunkoshi | 6
14486 | Okhaldhunga | Mulkharka | 6 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-22 | 2016-04-26 |  | Sunkoshi | 6
14487 | Okhaldhunga | Mulkharka | 6 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Sunkoshi | 6
14488 | Okhaldhunga | Mulkharka | 7 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-04-09 |  | Sunkoshi | 6
14489 | Okhaldhunga | Mulkharka | 7 | HELVETAS |  | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-20 | 2017-04-10 |  | Sunkoshi | 6
14490 | Okhaldhunga | Mulkharka | 7 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-22 | 2016-04-26 |  | Sunkoshi | 6
14491 | Okhaldhunga | Mulkharka | 7 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Sunkoshi | 6
14492 | Okhaldhunga | Mulkharka | 8 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-04-22 | 2016-04-26 |  | Sunkoshi | 6
14493 | Okhaldhunga | Mulkharka | 9 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 4 | 4 | 2017-02-19 | 2017-04-09 |  | Sunkoshi | 6
14494 | Okhaldhunga | Mulkharka | 9 | HELVETAS |  | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 4 | 4 | 2017-02-20 | 2017-04-10 |  | Sunkoshi | 6
14495 | Okhaldhunga | Mulkharka | 9 | ACTED | YSC | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-04-22 | 2016-04-26 |  | Sunkoshi | 6
14496 | Okhaldhunga | Mulkharka | 9 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Sunkoshi | 6
14497 | Okhaldhunga | Narmedeshwor | 1 | MEDAIR | LCDF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-10 | 2016-05-16 |  | Likhu | 3
14498 | Okhaldhunga | Narmedeshwor | 2 | MEDAIR | LCDF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-10 | 2016-05-16 |  | Likhu | 3
14499 | Okhaldhunga | Narmedeshwor | 3 | MEDAIR |  |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 3 | 3 | 2016-04-29 | 2016-05-03 |  | Likhu | 3
14500 | Okhaldhunga | Narmedeshwor | 1 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-05-14 | 2017-07-14 | Planning data - National Level | Likhu | 3
14501 | Okhaldhunga | Narmedeshwor | 3 | MEDAIR | LCDF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-10 | 2016-05-16 |  | Likhu | 3
14502 | Okhaldhunga | Narmedeshwor | 4 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-05-14 | 2017-07-14 | Planning data - National Level | Likhu | 3
14503 | Okhaldhunga | Narmedeshwor | 4 | MEDAIR | LCDF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-10 | 2016-05-16 |  | Likhu | 3
14504 | Okhaldhunga | Narmedeshwor | 5 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-05-14 | 2017-07-14 | Planning data - National Level | Likhu | 3
14505 | Okhaldhunga | Narmedeshwor | 5 | MEDAIR | LCDF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-10 | 2016-05-16 |  | Likhu | 3
14506 | Okhaldhunga | Narmedeshwor | 6 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-14 | 2017-07-14 | Planning data - National Level | Likhu | 3
14507 | Okhaldhunga | Narmedeshwor | 6 | MEDAIR | LCDF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-10 | 2016-05-16 |  | Likhu | 3
14508 | Okhaldhunga | Narmedeshwor | 7 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-05-14 | 2017-07-14 | Planning data - National Level | Likhu | 3
14509 | Okhaldhunga | Narmedeshwor | 7 | MEDAIR | LCDF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-10 | 2016-05-16 |  | Likhu | 3
14510 | Okhaldhunga | Narmedeshwor | 8 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 12 | 12 | 2017-05-14 | 2017-07-14 | Planning data - National Level | Likhu | 3
14511 | Okhaldhunga | Narmedeshwor | 8 | MEDAIR | LCDF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-05-10 | 2016-05-16 |  | Likhu | 3
14512 | Okhaldhunga | Narmedeshwor | 9 | MEDAIR |  |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 6 | 6 | 2016-04-29 | 2016-05-03 |  | Likhu | 3
14513 | Okhaldhunga | Narmedeshwor | 9 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 | 2017-05-14 | 2017-07-14 | Planning data - National Level | Likhu | 3
14514 | Okhaldhunga | Narmedeshwor | 9 | MEDAIR | LCDF |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-10 | 2016-05-16 |  | Likhu | 3
14515 | Okhaldhunga | Palapu | 1 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Construction Carpenter Treaning | # of trainees | Yes | Completed | 2 | 2 | 2015-12-27 | 2016-02-26 | Event Id-Efsr-2JTI-01-0010/2015 | Champadevi | 1
14516 | Okhaldhunga | Palapu | 2 | HELVETAS | JTI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-26 | 2016-02-29 |  | Champadevi | 1
14517 | Okhaldhunga | Palapu | 2 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 5 | 5 | 2015-12-27 | 2016-02-26 | Event Id-Efsr-2JTI-01-0005/2015 | Champadevi | 1
14518 | Okhaldhunga | Palapu | 2 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 2 | 2 | 2015-12-27 | 2016-02-26 | Event Id-Efsr-2JTI-01-0006/2015 | Champadevi | 1
14519 | Okhaldhunga | Palapu | 3 | HELVETAS | JTI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-26 | 2016-02-29 |  | Champadevi | 1
14520 | Okhaldhunga | Palapu | 3 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-27 | 2016-02-26 |  | Champadevi | 1
14521 | Okhaldhunga | Palapu | 3 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26 |  | Champadevi | 1
14522 | Okhaldhunga | Palapu | 4 | HELVETAS | JTI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-26 | 2016-02-29 |  | Champadevi | 1
14523 | Okhaldhunga | Palapu | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-27 | 2016-02-26 |  | Champadevi | 1
14524 | Okhaldhunga | Palapu | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26 |  | Champadevi | 1
14525 | Okhaldhunga | Palapu | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-27 | 2016-02-26 |  | Champadevi | 1
14526 | Okhaldhunga | Palapu | 5 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26 |  | Champadevi | 1
14527 | Okhaldhunga | Palapu | 5 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-27 | 2016-02-26 |  | Champadevi | 1
14528 | Okhaldhunga | Palapu | 6 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-27 | 2016-02-26 |  | Champadevi | 2
14529 | Okhaldhunga | Palapu | 7 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26 |  | Champadevi | 2
14530 | Okhaldhunga | Palapu | 8 | HELVETAS | JTI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-26 | 2016-02-29 |  | Champadevi | 2
14531 | Okhaldhunga | Palapu | 8 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 8 | 8 | 2015-12-27 | 2016-02-26 |  | Champadevi | 2
14532 | Okhaldhunga | Palapu | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26 |  | Champadevi | 2
14533 | Okhaldhunga | Palte | 2 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-18 | 2017-04-26 |  | Molung | 7
14534 | Okhaldhunga | Palte | 7 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-05-18 | 2017-04-26 |  | Molung | 7
14535 | Okhaldhunga | Palte | 8 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-05-18 | 2017-04-26 |  | Molung | 7
14536 | Okhaldhunga | Pokali | 1 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 2 | 2 | 2015-12-24 | 2016-02-19 | Event id-efcr-35 Phipi-01-0004/2015 | Likhu | 9
14537 | Okhaldhunga | Pokali | 2 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-24 | 2016-02-19 |  | Likhu | 9
14538 | Okhaldhunga | Pokali | 3 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-02-24 |  | Likhu | 9
14539 | Okhaldhunga | Pokali | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Building Electrician Treaning | # of trainees | Yes | Completed | 2 | 2 | 2016-01-05 | 2016-02-29 | Event id-efcr-35 Phipi-01-0008/2015 | Likhu | 9
14540 | Okhaldhunga | Pokali | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 4 | 4 | 2015-12-24 | 2016-02-19 | Event id-efcr-35 Phipi-01-0005/2015 | Likhu | 9
14541 | Okhaldhunga | Pokali | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-24 | 2016-02-19 |  | Likhu | 9
14542 | Okhaldhunga | Pokali | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-05 | 2016-02-29 |  | Likhu | 9
14543 | Okhaldhunga | Pokali | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 2 | 2 | 2016-06-12 | 2016-08-12 | Event id-efcr-35 Phipi-01-0003/2016 | Likhu | 9
14544 | Okhaldhunga | Pokali | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 |  | Likhu | 9
14545 | Okhaldhunga | Pokali | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-24 | 2016-02-19 |  | Likhu | 9
14546 | Okhaldhunga | Pokali | 6 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-02-24 |  | Likhu | 9
14547 | Okhaldhunga | Pokali | 6 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-24 | 2016-02-19 |  | Likhu | 9
14548 | Okhaldhunga | Pokali | 6 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-05 | 2016-02-29 |  | Likhu | 9
14549 | Okhaldhunga | Pokali | 7 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 |  | Likhu | 9
14550 | Okhaldhunga | Pokali | 7 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-12 | 2016-08-12 |  | Likhu | 9
14551 | Okhaldhunga | Pokali | 8 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2015-12-22 | 2016-02-24 |  | Likhu | 9
14552 | Okhaldhunga | Pokali | 8 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-12 | 2016-08-12 |  | Likhu | 9
14553 | Okhaldhunga | Pokali | 9 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 |  | Khijidemba | 6
14554 | Okhaldhunga | Pokhare | 3 | HELVETAS | FECOFUN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-11 | 2017-05-17 |  | Chisankhugadhi | 2
14555 | Okhaldhunga | Pokhare | 4 | HELVETAS | FECOFUN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-11 | 2017-05-17 |  | Chisankhugadhi | 2
14556 | Okhaldhunga | Pokhare | 8 | HELVETAS | FECOFUN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-11 | 2017-05-17 |  | Chisankhugadhi | 2
14557 | Okhaldhunga | Prapcha | 1 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-02-22 | 2017-04-15 | Planning data - National Level | Molung | 3
14558 | Okhaldhunga | Prapcha | 2 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Molung | 3
14559 | Okhaldhunga | Prapcha | 2 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-02-22 | 2017-04-15 | Planning data - National Level | Molung | 3
14560 | Okhaldhunga | Prapcha | 3 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Molung | 5
14561 | Okhaldhunga | Prapcha | 3 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-02-22 | 2017-04-15 | Planning data - National Level | Molung | 5
14562 | Okhaldhunga | Prapcha | 4 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 3 | 3 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Molung | 5
14563 | Okhaldhunga | Prapcha | 4 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 14 | 14 | 2017-02-22 | 2017-04-15 | Planning data - National Level | Molung | 5
14564 | Okhaldhunga | Prapcha | 5 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Molung | 5
14565 | Okhaldhunga | Prapcha | 5 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-02-22 | 2017-04-15 | Planning data - National Level | Molung | 5
14566 | Okhaldhunga | Prapcha | 6 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-02-22 | 2017-04-15 | Planning data - National Level | Molung | 5
14567 | Okhaldhunga | Prapcha | 8 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Molung | 5
14568 | Okhaldhunga | Prapcha | 8 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 13 | 13 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Molung | 5
14569 | Okhaldhunga | Prapcha | 9 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Molung | 5
14570 | Okhaldhunga | Prapcha | 9 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Molung | 5
14571 | Okhaldhunga | Prapcha | 9 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-04-09 |  | Molung | 5
14572 | Okhaldhunga | Prapcha | 9 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Molung | 5
14573 | Okhaldhunga | Ragadeep | 2 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-04-09 |  | Molung | 8
14574 | Okhaldhunga | Ragadeep | 5 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-05-03 | 2017-05-12 |  | Molung | 8
14575 | Okhaldhunga | Ragadeep | 6 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-05-03 | 2017-05-12 |  | Molung | 8
14576 | Okhaldhunga | Ragani | 1 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 1
14577 | Okhaldhunga | Ragani | 1 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 1
14578 | Okhaldhunga | Ragani | 1 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 | Event id-efcr-35 Phipi-01-0006/2015 | Khijidemba | 1
14579 | Okhaldhunga | Ragani | 2 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 |  |  | mason training implemented by them self | Khijidemba | 1
14580 | Okhaldhunga | Ragani | 2 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 1
14581 | Okhaldhunga | Ragani | 3 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 1
14582 | Okhaldhunga | Ragani | 3 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 1
14583 | Okhaldhunga | Ragani | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Construction Carpenter Treaning | # of trainees | Yes | Completed | 5 | 5 | 2016-06-10 | 2016-08-10 | Event id-efcr-35 Phipi-01-0007/2016 | Khijidemba | 1
14584 | Okhaldhunga | Ragani | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 3 | 3 | 2016-06-10 | 2016-08-10 | Event id-efcr-35 Phipi-01-0004/2016 | Khijidemba | 1
14585 | Okhaldhunga | Ragani | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 2 | 2 | 2016-06-10 | 2016-08-10 | Event id-efcr-35 Phipi-01-0005/2016 | Khijidemba | 1
14586 | Okhaldhunga | Ragani | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-12-24 | 2016-02-19 |  | Khijidemba | 1
14587 | Okhaldhunga | Ragani | 4 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 3 | 3 | 2015-12-21 | 2016-02-23 |  | Khijidemba | 1
14588 | Okhaldhunga | Ragani | 4 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 1
14589 | Okhaldhunga | Ragani | 4 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 1
14590 | Okhaldhunga | Ragani | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 |  | Khijidemba | 1
14591 | Okhaldhunga | Ragani | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-10 | 2016-08-10 |  | Khijidemba | 1
14592 | Okhaldhunga | Ragani | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-10 | 2016-06-10 |  | Khijidemba | 1
14593 | Okhaldhunga | Ragani | 5 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2015-12-21 | 2016-02-23 |  | Khijidemba | 1
14594 | Okhaldhunga | Ragani | 5 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 1
14595 | Okhaldhunga | Ragani | 5 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 1
14596 | Okhaldhunga | Ragani | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-10 | 2016-06-10 | Event Id-Efsr-2JTI-01-0001/2015 | Khijidemba | 1
14597 | Okhaldhunga | Ragani | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 |  | Khijidemba | 1
14598 | Okhaldhunga | Ragani | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-10 | 2016-08-10 |  | Khijidemba | 1
14599 | Okhaldhunga | Ragani | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-10 | 2016-08-10 |  | Khijidemba | 1
14600 | Okhaldhunga | Ragani | 6 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-12-21 | 2016-02-23 |  | Khijidemba | 2
14601 | Okhaldhunga | Ragani | 6 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 |  |  | mason training implemented by them self | Khijidemba | 2
14602 | Okhaldhunga | Ragani | 6 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 2
14603 | Okhaldhunga | Ragani | 6 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 |  | Khijidemba | 2
14604 | Okhaldhunga | Ragani | 6 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-10 | 2016-08-10 |  | Khijidemba | 2
14605 | Okhaldhunga | Ragani | 6 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-04-09 |  | Khijidemba | 2
14606 | Okhaldhunga | Ragani | 7 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 2
14607 | Okhaldhunga | Ragani | 7 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 2
14608 | Okhaldhunga | Ragani | 7 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 |  | Khijidemba | 2
14609 | Okhaldhunga | Ragani | 8 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 2
14610 | Okhaldhunga | Ragani | 8 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 2
14611 | Okhaldhunga | Ragani | 9 | UMN |  |  | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | total construction of houses | # of constructions | Yes | Completed | 2 | 2 |  |  | Full construction of house | Khijidemba | 2
14612 | Okhaldhunga | Ragani | 9 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 |  |  | mason training implemented by them self | Khijidemba | 2
14613 | Okhaldhunga | Ragani | 9 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 2
14614 | Okhaldhunga | Ragani | 9 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-10 | 2016-08-10 |  | Khijidemba | 2
14615 | Okhaldhunga | Raniban | 1 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-05-08 | 2017-06-26 | Planning data - National Level | Champadevi | 10
14616 | Okhaldhunga | Raniban | 1 | USAID-SABAL | FORD-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-07-01 |  | Champadevi | 10
14617 | Okhaldhunga | Raniban | 1 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 |  |  | Planning data - National Level | Champadevi | 10
14618 | Okhaldhunga | Raniban | 1 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-05-21 | 2016-05-27 |  | Champadevi | 10
14619 | Okhaldhunga | Raniban | 2 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-05-08 | 2017-06-26 | Planning data - National Level | Champadevi | 10
14620 | Okhaldhunga | Raniban | 2 | MEDAIR | LCDF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 3 | 3 | 2016-05-08 | 2016-05-12 |  | Champadevi | 10
14621 | Okhaldhunga | Raniban | 2 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 |  |  | Planning data - National Level | Champadevi | 10
14622 | Okhaldhunga | Raniban | 2 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-21 | 2016-05-27 |  | Champadevi | 10
14623 | Okhaldhunga | Raniban | 3 | USAID-SABAL | FORD-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-07-01 |  | Champadevi | 10
14624 | Okhaldhunga | Raniban | 3 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-21 | 2016-05-27 |  | Champadevi | 10
14625 | Okhaldhunga | Raniban | 4 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-05-08 | 2017-06-26 | Planning data - National Level | Champadevi | 10
14626 | Okhaldhunga | Raniban | 4 | USAID-SABAL | FORD-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-07-01 |  | Champadevi | 10
14627 | Okhaldhunga | Raniban | 4 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-14 | 2017-07-05 | Planning data - National Level | Champadevi | 10
14628 | Okhaldhunga | Raniban | 4 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-21 | 2016-05-27 |  | Champadevi | 10
14629 | Okhaldhunga | Raniban | 5 | MEDAIR | LCDF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 6 | 6 | 2016-05-08 | 2016-05-12 |  | Champadevi | 10
14630 | Okhaldhunga | Raniban | 5 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-05-21 | 2016-05-27 |  | Champadevi | 10
14631 | Okhaldhunga | Raniban | 7 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-05-08 | 2017-06-26 | Planning data - National Level | Champadevi | 10
14632 | Okhaldhunga | Raniban | 7 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 12 | 12 | 2017-05-28 | 2017-07-25 | Planning data - National Level | Champadevi | 10
14633 | Okhaldhunga | Raniban | 8 | USAID-SABAL | FORD-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-07-01 |  | Champadevi | 10
14634 | Okhaldhunga | Raniban | 9 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-06-13 | 2017-08-08 | Planning data - National Level | Champadevi | 10
14635 | Okhaldhunga | Raniban | 9 | MEDAIR |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-05-21 | 2016-05-27 |  | Champadevi | 10
14636 | Okhaldhunga | Rawadolu | 1 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 11 | 11 |  |  | mason training implemented by them self | Khijidemba | 7
14637 | Okhaldhunga | Rawadolu | 1 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 7
14638 | Okhaldhunga | Rawadolu | 2 | UMN |  |  | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | total construction of houses | # of constructions | Yes | Completed | 1 | 1 |  |  | Full construction of house | Khijidemba | 7
14639 | Okhaldhunga | Rawadolu | 2 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-12-20 | 2016-02-22 |  | Khijidemba | 7
14640 | Okhaldhunga | Rawadolu | 2 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 7
14641 | Okhaldhunga | Rawadolu | 2 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 7
14642 | Okhaldhunga | Rawadolu | 2 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 2 | 2 | 2015-12-24 | 2016-02-19 | Event id-efcr-35 Phipi-01-0007/2015 | Khijidemba | 7
14643 | Okhaldhunga | Rawadolu | 3 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 |  |  | mason training implemented by them self | Khijidemba | 7
14644 | Okhaldhunga | Rawadolu | 4 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 7
14645 | Okhaldhunga | Rawadolu | 4 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 7
14646 | Okhaldhunga | Rawadolu | 5 | UMN |  |  | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | total construction of houses | # of constructions | Yes | Completed | 1 | 1 |  |  | Full construction of house | Khijidemba | 7
14647 | Okhaldhunga | Rawadolu | 5 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 7
14648 | Okhaldhunga | Rawadolu | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-24 | 2016-02-19 |  | Khijidemba | 7
14649 | Okhaldhunga | Rawadolu | 6 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 7
14650 | Okhaldhunga | Rawadolu | 6 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Khijidemba | 7
14651 | Okhaldhunga | Rawadolu | 7 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 7
14652 | Okhaldhunga | Rawadolu | 8 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 10 | 10 |  |  | mason training implemented by them self | Khijidemba | 7
14653 | Okhaldhunga | Rawadolu | 9 | UMN |  |  | Technical Assistance | community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 12 | 12 |  |  | mason training implemented by them self | Khijidemba | 7
14654 | Okhaldhunga | Shreechaur | 1 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Molung | 5
14655 | Okhaldhunga | Shreechaur | 1 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Molung | 5
14656 | Okhaldhunga | Shreechaur | 1 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-18 | 2017-04-26 |  | Molung | 5
14657 | Okhaldhunga | Shreechaur | 1 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-02-19 | 2017-04-12 |  | Molung | 5
14658 | Okhaldhunga | Shreechaur | 2 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Molung | 5
14659 | Okhaldhunga | Shreechaur | 2 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Molung | 5
14660 | Okhaldhunga | Shreechaur | 2 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 | 2017-02-19 | 2017-04-12 |  | Molung | 5
14661 | Okhaldhunga | Shreechaur | 3 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Molung | 5
14662 | Okhaldhunga | Shreechaur | 3 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-25 | 2016-01-29 |  | Molung | 5
14663 | Okhaldhunga | Shreechaur | 3 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-02-19 | 2017-04-12 | Planning data - National Level | Molung | 5
14664 | Okhaldhunga | Shreechaur | 4 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Molung | 6
14665 | Okhaldhunga | Shreechaur | 4 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Molung | 6
14666 | Okhaldhunga | Shreechaur | 4 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-18 | 2017-04-26 |  | Molung | 6
14667 | Okhaldhunga | Shreechaur | 4 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-02-19 | 2017-04-12 | Planning data - National Level | Molung | 6
14668 | Okhaldhunga | Shreechaur | 5 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Molung | 6
14669 | Okhaldhunga | Shreechaur | 5 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-25 | 2016-01-29 |  | Molung | 6
14670 | Okhaldhunga | Shreechaur | 5 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-04-12 | Planning data - National Level | Molung | 6
14671 | Okhaldhunga | Shreechaur | 6 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Molung | 6
14672 | Okhaldhunga | Shreechaur | 6 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Molung | 6
14673 | Okhaldhunga | Shreechaur | 6 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-02-19 | 2017-04-12 | Planning data - National Level | Molung | 6
14674 | Okhaldhunga | Shreechaur | 7 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Molung | 6
14675 | Okhaldhunga | Shreechaur | 7 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-25 | 2016-01-29 |  | Molung | 6
14676 | Okhaldhunga | Shreechaur | 7 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-05-18 | 2017-04-26 |  | Molung | 6
14677 | Okhaldhunga | Shreechaur | 7 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 12 | 12 | 2017-02-19 | 2017-04-12 | Planning data - National Level | Molung | 6
14678 | Okhaldhunga | Shreechaur | 7 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-04-09 |  | Molung | 6
14679 | Okhaldhunga | Shreechaur | 8 | HELVETAS | F-SKILL | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-19 | 2017-04-09 | Planning data - National Level | Molung | 6
14680 | Okhaldhunga | Shreechaur | 8 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-25 | 2016-01-29 |  | Molung | 6
14681 | Okhaldhunga | Shreechaur | 8 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-05-18 | 2017-04-26 |  | Molung | 6
14682 | Okhaldhunga | Shreechaur | 8 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 15 | 15 | 2017-02-19 | 2017-04-12 | Planning data - National Level | Molung | 6
14683 | Okhaldhunga | Shreechaur | 9 | ACTED | YSC | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-01-29 |  | Molung | 6
14684 | Okhaldhunga | Shreechaur | 9 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-18 | 2017-04-26 |  | Molung | 6
14685 | Okhaldhunga | Siddhicharan N.P. | 1 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 31 | 31 | 2016-03-02 | 2016-04-30 |  | Siddhicharan | 5
14686 | Okhaldhunga | Siddhicharan N.P. | 2 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-03-02 | 2016-04-30 |  | Siddhicharan | 5
14687 | Okhaldhunga | Siddhicharan N.P. | 3 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-03-02 | 2016-04-30 |  | Siddhicharan | 11
14688 | Okhaldhunga | Siddhicharan N.P. | 4 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-03-02 | 2016-04-30 |  | Siddhicharan | 11
14689 | Okhaldhunga | Siddhicharan N.P. | 5 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-02 | 2016-04-30 |  | Siddhicharan | 12
14690 | Okhaldhunga | Siddhicharan N.P. | 6 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-03-02 | 2016-04-30 |  | Siddhicharan | 9
14691 | Okhaldhunga | Siddhicharan N.P. | 7 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 28 | 28 | 2016-03-02 | 2016-04-30 |  | Siddhicharan | 9
14692 | Okhaldhunga | Siddhicharan N.P. | 8 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-03-02 | 2016-04-30 |  | Siddhicharan | 8
14693 | Okhaldhunga | Siddhicharan N.P. | 9 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-03-02 | 2016-04-30 |  | Siddhicharan | 8
14694 | Okhaldhunga | Siddhicharan N.P. | 10 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-02 | 2016-04-30 |  | Siddhicharan | 3
14695 | Okhaldhunga | Siddhicharan N.P. | 11 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-03-02 | 2016-04-30 |  | Siddhicharan | 3
14696 | Okhaldhunga | Singhadevi | 1 | HELVETAS | JTI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-24 | 2016-02-27 |  | Likhu | 1
14697 | Okhaldhunga | Singhadevi | 1 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26 | Event Id-Efsr-2JTI-01-0003/2015 | Likhu | 1
14698 | Okhaldhunga | Singhadevi | 2 | MEDAIR |  |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 4 | 4 | 2016-05-17 | 2016-05-21 |  | Likhu | 1
14699 | Okhaldhunga | Singhadevi | 3 | USAID-SABAL | FORD-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-06-26 |  | Likhu | 1
14700 | Okhaldhunga | Singhadevi | 3 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26 |  | Likhu | 1
14701 | Okhaldhunga | Singhadevi | 4 | USAID-SABAL | FORD-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-06-26 |  | Likhu | 1
14702 | Okhaldhunga | Singhadevi | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Construction Carpenter Treaning | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26 | Event Id-Efsr-2JTI-01-0009/2015 | Likhu | 1
14703 | Okhaldhunga | Singhadevi | 4 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26 | Event Id-Efsr-2JTI-01-0004/2015 | Likhu | 1
14704 | Okhaldhunga | Singhadevi | 5 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-27 | 2016-02-26 |  | Likhu | 1
14705 | Okhaldhunga | Singhadevi | 5 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-27 | 2016-02-26 |  | Likhu | 1
14706 | Okhaldhunga | Singhadevi | 6 | HELVETAS | JTI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-24 | 2016-02-27 |  | Likhu | 2
14707 | Okhaldhunga | Singhadevi | 6 | MEDAIR |  |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 5 | 5 | 2016-05-17 | 2016-05-21 |  | Likhu | 2
14708 | Okhaldhunga | Singhadevi | 6 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26 |  | Likhu | 2
14709 | Okhaldhunga | Singhadevi | 7 | HELVETAS | JTI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-24 | 2016-02-27 |  | Likhu | 2
14710 | Okhaldhunga | Singhadevi | 7 | USAID-SABAL | FORD-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-06-26 |  | Likhu | 2
14711 | Okhaldhunga | Singhadevi | 7 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-27 | 2016-02-26 |  | Likhu | 2
14712 | Okhaldhunga | Singhadevi | 7 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-27 | 2016-02-26 |  | Likhu | 2
14713 | Okhaldhunga | Singhadevi | 8 | USAID-SABAL | FORD-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-06-26 |  | Likhu | 2
14714 | Okhaldhunga | Singhadevi | 8 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-27 | 2016-02-26 |  | Likhu | 2
14715 | Okhaldhunga | Singhadevi | 8 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26 |  | Likhu | 2
14716 | Okhaldhunga | Singhadevi | 9 | HELVETAS | JTI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-24 | 2016-02-27 |  | Likhu | 2
14717 | Okhaldhunga | Singhadevi | 9 | HELVETAS | TRACE | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-05-15 | 2017-07-03 |  | Likhu | 2
14718 | Okhaldhunga | Singhadevi | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-27 | 2016-02-26 |  | Likhu | 2
14719 | Okhaldhunga | Singhadevi | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-27 | 2016-02-26 |  | Likhu | 2
14720 | Okhaldhunga | Singhadevi | 9 | HELVETAS | JTI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-27 | 2016-02-26 |  | Likhu | 2
14721 | Okhaldhunga | SisneriMahadevsthan | 2 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-04-09 |  | Sunkoshi | 3
14722 | Okhaldhunga | SisneriMahadevsthan | 3 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-05-03 | 2017-05-09 |  | Sunkoshi | 3
14723 | Okhaldhunga | SisneriMahadevsthan | 4 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-05-03 | 2017-05-09 |  | Sunkoshi | 3
14724 | Okhaldhunga | SisneriMahadevsthan | 6 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-05-03 | 2017-05-09 |  | Sunkoshi | 4
14725 | Okhaldhunga | SisneriMahadevsthan | 8 | GON |  |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-03 | 2017-05-09 |  | Sunkoshi | 4
14726 | Okhaldhunga | Taluwa | 3 | HELVETAS | F-SKILL | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-02-19 | 2017-04-09 |  | Siddhicharan | 1
14727 | Okhaldhunga | Tarkerabari | 2 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-12-23 | 2016-02-25 |  | Likhu | 8
14728 | Okhaldhunga | Tarkerabari | 2 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Construction Carpenter Treaning | # of trainees | Yes | Completed | 1 | 1 | 2016-06-12 | 2016-08-12 | Event id-efcr-35 Phipi-01-0006/2016 | Likhu | 8
14729 | Okhaldhunga | Tarkerabari | 2 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Construction Carpenter Treaning | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-29 | Event id-efcr-35 Phipi-01-0010/2015 | Likhu | 8
14730 | Okhaldhunga | Tarkerabari | 2 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 5 | 5 | 2016-06-12 | 2016-08-12 | Event id-efcr-35 Phipi-01-0002/2016 | Likhu | 8
14731 | Okhaldhunga | Tarkerabari | 2 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-12 | 2016-08-12 | Event id-efcr-35 Phipi-01-0001/2016 | Likhu | 8
14732 | Okhaldhunga | Tarkerabari | 3 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2015-12-23 | 2016-02-25 |  | Likhu | 8
14733 | Okhaldhunga | Tarkerabari | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 | Event id-efcr-35 Phipi-01-0003/2015 | Likhu | 8
14734 | Okhaldhunga | Tarkerabari | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-12 | 2016-08-12 |  | Likhu | 8
14735 | Okhaldhunga | Tarkerabari | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-12 | 2016-08-12 |  | Likhu | 8
14736 | Okhaldhunga | Tarkerabari | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-12 | 2016-08-12 |  | Likhu | 8
14737 | Okhaldhunga | Tarkerabari | 4 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-12-23 | 2016-02-25 |  | Likhu | 8
14738 | Okhaldhunga | Tarkerabari | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-12 | 2016-08-12 |  | Likhu | 8
14739 | Okhaldhunga | Tarkerabari | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-24 | 2016-02-19 |  | Likhu | 8
14740 | Okhaldhunga | Tarkerabari | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 |  | Likhu | 8
14741 | Okhaldhunga | Tarkerabari | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-07 | 2016-02-29 |  | Likhu | 8
14742 | Okhaldhunga | Tarkerabari | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 |  | Likhu | 8
14743 | Okhaldhunga | Tarkerabari | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-12 | 2016-08-12 |  | Likhu | 8
14744 | Okhaldhunga | Tarkerabari | 6 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-24 | 2016-02-19 |  | Likhu | 8
14745 | Okhaldhunga | Tarkerabari | 6 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-29 |  | Likhu | 8
14746 | Okhaldhunga | Tarkerabari | 6 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-12 | 2016-08-12 |  | Likhu | 8
14747 | Okhaldhunga | Tarkerabari | 7 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-29 |  | Likhu | 8
14748 | Okhaldhunga | Tarkerabari | 8 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2015-12-23 | 2016-02-25 |  | Likhu | 8
14749 | Okhaldhunga | Tarkerabari | 8 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 3 | 2 | 2016-01-07 | 2016-02-29 |  | Likhu | 8
14750 | Okhaldhunga | Tarkerabari | 8 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 |  | Likhu | 8
14751 | Okhaldhunga | Tarkerabari | 8 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-12 | 2016-08-12 |  | Likhu | 8
14752 | Okhaldhunga | Tarkerabari | 9 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 |  | Likhu | 8
14753 | Okhaldhunga | Tarkerabari | 9 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-12 | 2016-08-12 |  | Likhu | 8
14754 | Okhaldhunga | Thakle | 2 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-12 | 2017-05-18 |  | Manebhanjyang | 6
14755 | Okhaldhunga | Thakle | 3 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-05-12 | 2017-05-18 |  | Manebhanjyang | 6
14756 | Okhaldhunga | Thakle | 4 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-12 | 2017-05-18 |  | Manebhanjyang | 6
14757 | Okhaldhunga | Thakle | 5 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-12 | 2017-05-18 |  | Manebhanjyang | 6
14758 | Okhaldhunga | Thakle | 6 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-05-12 | 2017-05-18 |  | Manebhanjyang | 6
14759 | Okhaldhunga | Thakle | 9 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-12 | 2017-05-18 |  | Manebhanjyang | 6
14760 | Okhaldhunga | Thoksel | 1 | USAID-SABAL | KOSIS-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-07-04 |  | Manebhanjyang | 7
14761 | Okhaldhunga | Thoksel | 2 | USAID-SABAL | KOSIS-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-07-04 |  | Manebhanjyang | 7
14762 | Okhaldhunga | Thoksel | 3 | USAID-SABAL | KOSIS-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-07-04 |  | Manebhanjyang | 7
14763 | Okhaldhunga | Thoksel | 3 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-12 | 2017-05-18 |  | Manebhanjyang | 7
14764 | Okhaldhunga | Thoksel | 4 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-05-12 | 2017-05-18 |  | Manebhanjyang | 7
14765 | Okhaldhunga | Thoksel | 6 | USAID-SABAL | KOSIS-N | USAID | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 25 | 25 | 2015-12-01 | 2016-07-04 |  | Manebhanjyang | 8
14766 | Okhaldhunga | Thoksel | 8 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-12 | 2017-05-18 |  | Manebhanjyang | 8
14767 | Okhaldhunga | Thoksel | 9 | GON | SAHAS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-12 | 2017-05-18 |  | Manebhanjyang | 8
14768 | Okhaldhunga | Ubu | 2 | GON |  |  | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-02 | 2016-04-30 |  | Manebhanjyang | 3
14769 | Okhaldhunga | Yasam | 1 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 | Event id-efcr-35 Phipi-01-0001/2015 | Likhu | 4
14770 | Okhaldhunga | Yasam | 2 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 |  | Likhu | 4
14771 | Okhaldhunga | Yasam | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 |  | Likhu | 4
14772 | Okhaldhunga | Yasam | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Construction Carpenter Treaning | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 | Event id-efcr-35 Phipi-01-0009/2015 | Likhu | 4
14773 | Okhaldhunga | Yasam | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-24 | 2016-02-19 |  | Likhu | 4
14774 | Okhaldhunga | Yasam | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 |  | Likhu | 4
14775 | Okhaldhunga | Yasam | 6 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-26 |  | Likhu | 5
14776 | Okhaldhunga | Yasam | 6 | MEDAIR | LCDF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 4 | 4 | 2016-05-28 | 2016-06-01 |  | Likhu | 5
14777 | Okhaldhunga | Yasam | 6 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | Stone Layer Mason oss Treaning | # of trainees | Yes | Completed | 1 | 1 | 2015-12-24 | 2016-02-19 | Event id-efcr-35 Phipi-01-0002/2015 | Likhu | 5
14778 | Okhaldhunga | Yasam | 6 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-24 | 2016-02-19 |  | Likhu | 5
14779 | Okhaldhunga | Yasam | 6 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Saipu VDC-Ramechhap district | # of trainees | Yes | Completed | 1 | 1 | 2016-11-08 | 2016-12-28 |  | Likhu | 5
14780 | Okhaldhunga | Yasam | 7 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2015-12-24 | 2016-02-26 |  | Likhu | 5
14781 | Okhaldhunga | Yasam | 7 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-24 | 2016-02-19 |  | Likhu | 5
14782 | Okhaldhunga | Yasam | 7 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-24 | 2016-02-19 |  | Likhu | 5
14783 | Okhaldhunga | Yasam | 8 | MEDAIR | LCDF |  | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 5 | 5 | 2016-05-28 | 2016-06-01 |  | Likhu | 5
14784 | Okhaldhunga | Yasam | 8 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-24 | 2016-02-19 |  | Likhu | 5
14785 | Okhaldhunga | Yasam | 8 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-24 | 2016-02-19 |  | Likhu | 5
14786 | Okhaldhunga | Yasam | 9 | HELVETAS | PHPI | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2015-12-24 | 2016-02-26 |  | Likhu | 5
14787 | Okhaldhunga | Yasam | 9 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-12-24 | 2016-02-19 |  | Likhu | 5
14788 | Okhaldhunga | Singhadevi | 1 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Likhu | 1
14789 | Okhaldhunga | Singhadevi | 5 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Likhu | 1
14790 | Okhaldhunga | Singhadevi | 7 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Likhu | 2
14791 | Okhaldhunga | Singhadevi | 9 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 |  |  |  | Likhu | 2
14792 | Okhaldhunga | Fediguth | 6 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Champadevi | 5
14793 | Okhaldhunga | Palapu | 4 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Champadevi | 1
14794 | Okhaldhunga | Chyanam | 3 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Sunkoshi | 7
14795 | Okhaldhunga | Katunje | 1 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Sunkoshi | 9
14796 | Okhaldhunga | Fediguth | 1 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Champadevi | 4
14797 | Okhaldhunga | Fediguth | 2 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 8 | 8 |  |  |  | Champadevi | 4
14798 | Okhaldhunga | Fulbari | 3 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Champadevi | 6
14799 | Okhaldhunga | Singhadevi | 5 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Likhu | 1
14800 | Okhaldhunga | Singhadevi | 9 | HELVETAS | TRACE | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Likhu | 2
14801 | Okhaldhunga | Narmedeshwor | 4 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | construction carpenter | # of trainees | Yes | Completed | 2 | 2 | 2017-05-14 | 2017-05-20 |  | Likhu | 3
14802 | Okhaldhunga | Narmedeshwor | 5 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-05-14 | 2017-05-20 |  | Likhu | 3
14803 | Okhaldhunga | Narmedeshwor | 6 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-14 | 2017-05-20 |  | Likhu | 3
14804 | Okhaldhunga | Narmedeshwor | 7 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-14 | 2017-05-20 |  | Likhu | 3
14805 | Okhaldhunga | Narmedeshwor | 8 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-14 | 2017-05-20 |  | Likhu | 3
14806 | Okhaldhunga | Narmedeshwor | 9 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-14 | 2017-05-20 |  | Likhu | 3
14807 | Okhaldhunga | Singhadevi | 2 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) | Construction Carpenter | # of trainees | Yes | Completed | 1 | 1 | 2017-05-07 | 2017-05-13 |  | Likhu | 1
14808 | Okhaldhunga | Singhadevi | 4 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-07 | 2017-05-13 |  | Likhu | 1
14809 | Okhaldhunga | Singhadevi | 7 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2017-05-07 | 2017-05-13 |  | Likhu | 2
14810 | Okhaldhunga | Singhadevi | 8 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-07 | 2017-05-13 |  | Likhu | 2
14811 | Okhaldhunga | KhijiChandeshwori | 1 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-21 | 2017-05-27 |  | Khijidemba | 3
14812 | Okhaldhunga | KhijiChandeshwori | 3 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-05-21 | 2017-05-27 |  | Khijidemba | 3
14813 | Okhaldhunga | KhijiChandeshwori | 5 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-21 | 2017-05-27 |  | Khijidemba | 3
14814 | Okhaldhunga | KhijiChandeshwori | 6 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-21 | 2017-05-27 |  | Khijidemba | 3
14815 | Okhaldhunga | KhijiChandeshwori | 7 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-21 | 2017-05-27 |  | Khijidemba | 3
14816 | Okhaldhunga | KhijiChandeshwori | 9 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-21 | 2017-05-27 |  | Khijidemba | 3
14817 | Okhaldhunga | Fulbari | 3 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-06-25 | 2017-07-01 |  | Champadevi | 6
14818 | Okhaldhunga | Fulbari | 4 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-06-25 | 2017-07-01 |  | Champadevi | 6
14819 | Okhaldhunga | Fulbari | 6 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-06-25 | 2017-07-01 |  | Champadevi | 6
14820 | Okhaldhunga | Fediguth | 2 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-07-16 | 2017-07-22 |  | Champadevi | 4
14821 | Okhaldhunga | Mulkharka | 1 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2017-07-30 | 2017-08-05 |  | Sunkoshi | 5
14822 | Okhaldhunga | Mulkharka | 2 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-07-30 | 2017-08-05 |  | Sunkoshi | 5
14823 | Okhaldhunga | Mulkharka | 3 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-07-30 | 2017-08-05 |  | Sunkoshi | 5
14824 | Okhaldhunga | Mulkharka | 4 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-07-30 | 2017-08-05 |  | Sunkoshi | 5
14825 | Okhaldhunga | Mulkharka | 7 | HELVETAS | TRACE | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-07-30 | 2017-08-05 |  | Sunkoshi | 6
14826 | Okhaldhunga | Katunje | 1 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-06-21 | 2017-06-27 |  | Sunkoshi | 9
14827 | Okhaldhunga | Katunje | 2 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-06-21 | 2017-06-27 |  | Sunkoshi | 9
14828 | Okhaldhunga | Katunje | 5 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-06-21 | 2017-06-27 |  | Sunkoshi | 9
14829 | Okhaldhunga | Katunje | 6 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-06-21 | 2017-06-27 |  | Sunkoshi | 10
14830 | Okhaldhunga | Katunje | 7 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-06-21 | 2017-06-27 |  | Sunkoshi | 10
14831 | Okhaldhunga | Bilandu | 1 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-06-12 | 2017-06-18 |  | Champadevi | 8
14832 | Okhaldhunga | Bilandu | 2 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-06-12 | 2017-06-18 |  | Champadevi | 8
14833 | Okhaldhunga | Bilandu | 3 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-06-12 | 2017-06-18 |  | Champadevi | 8
14834 | Okhaldhunga | Bilandu | 5 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-06-12 | 2017-06-18 |  | Champadevi | 8
14835 | Okhaldhunga | Bilandu | 6 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-06-12 | 2017-06-18 |  | Champadevi | 9
14836 | Okhaldhunga | Bilandu | 7 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-06-12 | 2017-06-18 |  | Champadevi | 9
14837 | Okhaldhunga | Bilandu | 9 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-06-12 | 2017-06-18 |  | Champadevi | 9
14838 | Okhaldhunga | Chyanam | 1 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-07-04 | 2017-07-10 |  | Sunkoshi | 7
14839 | Okhaldhunga | Chyanam | 2 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-07-04 | 2017-07-10 |  | Sunkoshi | 7
14840 | Okhaldhunga | Chyanam | 3 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-07-04 | 2017-07-10 |  | Sunkoshi | 7
14841 | Okhaldhunga | Chyanam | 6 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-07-04 | 2017-07-10 |  | Sunkoshi | 7
14842 | Okhaldhunga | Chyanam | 8 | HELVETAS | F-SKILL | DFID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2017-07-04 | 2017-07-10 |  | Sunkoshi | 8
14843 | Okhaldhunga | Mamkha | 7 | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2018-01-23 | 2018-01-29 |  | Chisankhugadhi | 7
14844 | Okhaldhunga | Mamkha | 8 | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2018-01-23 | 2018-01-29 |  | Chisankhugadhi | 7
14845 | Okhaldhunga | Serna | 5 | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2018-01-23 | 2018-01-29 |  | Chisankhugadhi | 5
14846 | Okhaldhunga | Fediguth | 2 | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2018-02-06 | 2018-02-12 |  | Champadevi | 4
14847 | Okhaldhunga | Fediguth | 3 | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2018-02-06 | 2018-02-12 |  | Champadevi | 4
14848 | Okhaldhunga | Fediguth | 4 | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2018-02-06 | 2018-02-12 |  | Champadevi | 5
14849 | Okhaldhunga | Fediguth | 9 | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2018-02-06 | 2018-02-12 |  | Champadevi | 4
14850 | Okhaldhunga | Ketuke |  | HELVETAS | FECOFUN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2017-05-11 | 2017-05-17 |  | Manebhanjyang | 4
14851 | Okhaldhunga | Ketuke |  | HELVETAS | FECOFUN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-11 | 2017-05-17 |  | Manebhanjyang | 4
14852 | Okhaldhunga | Manebhanjyang |  | HELVETAS | FECOFUN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-05-11 | 2017-05-17 |  | Manebhanjyang | 5
14853 | Okhaldhunga | Pokhare |  | HELVETAS | FECOFUN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-05-11 | 2017-05-17 |  | Chisankhugadhi | 2
14854 | Okhaldhunga | Ubu |  | GON | FECOFUN |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 23 | 23 | 2017-05-11 | 2017-05-17 |  | Manebhanjyang | 3
14855 | Okhaldhunga | Ragani | 4 | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2018-03-07 | 2018-03-13 |  | Khijidemba | 1
14856 | Okhaldhunga | Ragani | 5 | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2018-03-07 | 2018-03-13 |  | Khijidemba | 1
14857 | Okhaldhunga | Ragani | 6 | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2018-03-07 | 2018-03-13 |  | Khijidemba | 2
14858 | Okhaldhunga | Ragani | 7 | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2018-03-07 | 2018-03-13 |  | Khijidemba | 2
14859 | Okhaldhunga | Ragani | 8 | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2018-03-07 | 2018-03-13 |  | Khijidemba | 2
14860 | Okhaldhunga | Ragani | 9 | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2018-03-07 | 2018-03-13 |  | Khijidemba | 2
14861 | Okhaldhunga | Thoksel | 7 | GON | DLPIU | DLPIU | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 27 | 27 | 2018-02-12 | 2018-02-18 |  | Manebhanjyang | 8
14862 | Okhaldhunga | Ketuke | 4 | GON | DLPIU | DLPIU | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 35 | 2018-02-16 | 2018-02-22 |  | Manebhanjyang | 4
14863 | Okhaldhunga | Siddhicharan N.P. | 5 | GON | DLPIU | DLPIU | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2018-01-22 | 2018-01-28 |  | Siddhicharan | 12
14864 | Okhaldhunga | Siddhicharan N.P. | 5 | GON | DLPIU | DLPIU | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2018-01-22 | 2018-01-28 |  | Siddhicharan | 12
14865 | Okhaldhunga | Betini | 6 | GON | DLPIU | DLPIU | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2018-01-22 | 2018-01-28 |  | Siddhicharan | 10
14866 | Okhaldhunga | Harkapur | 3 | NRCS | NRCS | IFRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Planned | 30 | 0 | 2016-01-01 | 2018-12-31 |  | Molung | 4
14867 | Okhaldhunga | Prapcha | 3 | NRCS | NRCS | IFRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Planned | 30 | 0 | 2016-01-01 | 2018-12-31 |  | Molung | 5
14868 | Okhaldhunga | Harkapur | 1 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 11 | 11 | 2016-01-01 | 2018-12-31 |  | Molung | 4
14869 | Okhaldhunga | Harkapur | 2 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 23 | 23 | 2016-01-01 | 2018-12-31 |  | Molung | 4
14870 | Okhaldhunga | Harkapur | 3 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 12 | 12 | 2016-01-01 | 2018-12-31 |  | Molung | 4
14871 | Okhaldhunga | Harkapur | 4 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 22 | 22 | 2016-01-01 | 2018-12-31 |  | Molung | 4
14872 | Okhaldhunga | Harkapur | 5 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 15 | 15 | 2016-01-01 | 2018-12-31 |  | Molung | 4
14873 | Okhaldhunga | Harkapur | 6 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 26 | 26 | 2016-01-01 | 2018-12-31 |  | Molung | 4
14874 | Okhaldhunga | Harkapur | 7 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Molung | 3
14875 | Okhaldhunga | Harkapur | 8 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 25 | 25 | 2016-01-01 | 2018-12-31 |  | Molung | 3
14876 | Okhaldhunga | Harkapur | 9 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Molung | 3
14877 | Okhaldhunga | Prapcha | 1 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 6 | 6 | 2016-01-01 | 2018-12-31 |  | Molung | 3
14878 | Okhaldhunga | Prapcha | 2 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 8 | 8 | 2016-01-01 | 2018-12-31 |  | Molung | 3
14879 | Okhaldhunga | Prapcha | 3 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 7 | 7 | 2016-01-01 | 2018-12-31 |  | Molung | 5
14880 | Okhaldhunga | Prapcha | 4 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 12 | 12 | 2016-01-01 | 2018-12-31 |  | Molung | 5
14881 | Okhaldhunga | Prapcha | 5 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 |  |  |  | Molung | 5
14882 | Okhaldhunga | Prapcha | 6 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 2 | 2 | 2016-01-01 | 2018-12-31 |  | Molung | 5
14883 | Okhaldhunga | Prapcha | 7 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 1 | 1 |  |  |  | Molung | 5
14884 | Okhaldhunga | Prapcha | 8 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 8 | 8 | 2016-01-01 | 2018-12-31 |  | Molung | 5
14885 | Okhaldhunga | Prapcha | 9 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 13 | 13 | 2016-01-01 | 2018-12-31 |  | Molung | 5
14886 | Okhaldhunga | Siddhicharan N.P. | 1 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 42 | 42 | 2016-01-01 | 2018-12-31 |  | Siddhicharan | 5
14887 | Okhaldhunga | Siddhicharan N.P. | 2 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 17 | 17 | 2016-01-01 | 2018-12-31 |  | Siddhicharan | 5
14888 | Okhaldhunga | Harkapur | 1 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Cash support for shelter construction | # of households | Yes | Completed | 21 | 21 | 2017-06-20 | 2018-01-19 |  | Molung | 4
14889 | Okhaldhunga | Harkapur | 2 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Cash support for shelter construction | # of households | Yes | Ongoing | 41 | 40 | 2016-05-12 | 2016-06-15 |  | Molung | 4
14890 | Okhaldhunga | Harkapur | 3 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Cash support for shelter construction | # of households | Yes | Ongoing | 65 | 63 | 2016-05-12 | 2016-06-15 |  | Molung | 4
14891 | Okhaldhunga | Harkapur | 4 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Cash support for shelter construction | # of households | Yes | Completed | 16 | 16 | 2016-05-12 | 2016-06-15 |  | Molung | 4
14892 | Okhaldhunga | Harkapur | 5 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Cash support for shelter construction | # of households | Yes | Completed | 30 | 30 | 2016-05-12 | 2016-06-15 |  | Molung | 4
14893 | Okhaldhunga | Harkapur | 6 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Cash support for shelter construction | # of households | Yes | Ongoing | 52 | 48 | 2016-05-12 | 2016-06-15 |  | Molung | 4
14894 | Okhaldhunga | Harkapur | 7 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Cash support for shelter construction | # of households | Yes | Ongoing | 33 | 32 | 2016-05-12 | 2016-06-15 |  | Molung | 3
14895 | Okhaldhunga | Harkapur | 8 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Cash support for shelter construction | # of households | Yes | Ongoing | 46 | 45 | 2016-05-12 | 2016-06-15 |  | Molung | 3
14896 | Okhaldhunga | Harkapur | 9 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Cash support for shelter construction | # of households | Yes | Ongoing | 23 | 21 | 2016-05-12 | 2016-06-15 |  | Molung | 3
14897 | Okhaldhunga | Prapcha | 1 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Cash support for shelter construction | # of households | Yes | Ongoing | 22 | 20 | 2016-06-18 | 2016-06-24 |  | Molung | 3
14898 | Okhaldhunga | Prapcha | 2 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Cash support for shelter construction | # of households | Yes | Completed | 42 | 42 | 2016-06-18 | 2016-06-24 |  | Molung | 3
14899 | Okhaldhunga | Prapcha | 3 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Cash support for shelter construction | # of households | Yes | Ongoing | 12 | 11 | 2016-06-18 | 2016-06-24 |  | Molung | 5
14900 | Okhaldhunga | Prapcha | 4 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Cash support for shelter construction | # of households | Yes | Completed | 23 | 23 | 2016-06-18 | 2016-06-24 |  | Molung | 5
14901 | Okhaldhunga | Prapcha | 5 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Cash support for shelter construction | # of households | Yes | Completed | 8 | 8 | 2016-09-01 | 2018-12-31 |  | Molung | 5
14902 | Okhaldhunga | Prapcha | 6 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Cash support for shelter construction | # of households | Yes | Completed | 21 | 21 | 2016-06-18 | 2016-06-24 |  | Molung | 5
14903 | Okhaldhunga | Prapcha | 7 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Cash support for shelter construction | # of households | Yes | Completed | 16 | 16 | 2016-09-01 | 2018-12-31 |  | Molung | 5
14904 | Okhaldhunga | Prapcha | 8 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Cash support for shelter construction | # of households | Yes | Completed | 16 | 16 | 2016-06-18 | 2016-06-24 |  | Molung | 5
14905 | Okhaldhunga | Prapcha | 9 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | Cash support for shelter construction | # of households | Yes | Ongoing | 33 | 32 | 2016-06-18 | 2016-06-24 |  | Molung | 5
14906 | Okhaldhunga | Harkapur | 1 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Cash support for shelter construction | # of households | Yes | Ongoing | 21 | 8 | 2016-05-12 | 2016-06-15 |  | Molung | 4
14907 | Okhaldhunga | Harkapur | 2 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Cash support for shelter construction | # of households | Yes | Ongoing | 41 | 2 | 2016-09-01 | 2018-12-31 |  | Molung | 4
14908 | Okhaldhunga | Harkapur | 3 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Cash support for shelter construction | # of households | Yes | Ongoing | 65 | 17 | 2016-09-01 | 2018-12-31 |  | Molung | 4
14909 | Okhaldhunga | Harkapur | 4 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Cash support for shelter construction | # of households | Yes | Ongoing | 16 | 9 | 2016-09-01 | 2018-12-31 |  | Molung | 4
14910 | Okhaldhunga | Harkapur | 5 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Cash support for shelter construction | # of households | Yes | Ongoing | 30 | 13 | 2016-09-01 | 2018-12-31 |  | Molung | 4
14911 | Okhaldhunga | Harkapur | 6 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Cash support for shelter construction | # of households | Yes | Ongoing | 52 | 3 | 2016-09-01 | 2018-12-31 |  | Molung | 4
14912 | Okhaldhunga | Harkapur | 7 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Cash support for shelter construction | # of households | Yes | Ongoing | 33 | 13 | 2016-09-01 | 2018-12-31 |  | Molung | 3
14913 | Okhaldhunga | Harkapur | 8 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Cash support for shelter construction | # of households | Yes | Ongoing | 46 | 7 | 2016-09-01 | 2018-12-31 |  | Molung | 3
14914 | Okhaldhunga | Harkapur | 9 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Cash support for shelter construction | # of households | Yes | Ongoing | 23 | 3 | 2016-09-01 | 2018-12-31 |  | Molung | 3
14915 | Okhaldhunga | Prapcha | 1 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Cash support for shelter construction | # of households | Yes | Ongoing | 22 | 10 | 2016-09-01 | 2018-12-31 |  | Molung | 3
14916 | Okhaldhunga | Prapcha | 2 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Cash support for shelter construction | # of households | Yes | Ongoing | 42 | 19 | 2016-09-01 | 2018-12-31 |  | Molung | 3
14917 | Okhaldhunga | Prapcha | 3 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Cash support for shelter construction | # of households | Yes | Ongoing | 12 | 11 | 2016-09-01 | 2018-12-31 |  | Molung | 5
14918 | Okhaldhunga | Prapcha | 4 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Cash support for shelter construction | # of households | Yes | Ongoing | 23 | 17 | 2016-09-01 | 2018-12-31 |  | Molung | 5
14919 | Okhaldhunga | Prapcha | 5 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Cash support for shelter construction | # of households | Yes | Ongoing | 8 | 9 | 2016-09-01 | 2018-12-31 |  | Molung | 5
14920 | Okhaldhunga | Prapcha | 6 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Cash support for shelter construction | # of households | Yes | Ongoing | 21 | 13 | 2016-09-01 | 2018-12-31 |  | Molung | 5
14921 | Okhaldhunga | Prapcha | 7 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Cash support for shelter construction | # of households | Yes | Ongoing | 16 | 10 | 2016-09-01 | 2018-12-31 |  | Molung | 5
14922 | Okhaldhunga | Prapcha | 8 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Cash support for shelter construction | # of households | Yes | Ongoing | 16 | 12 | 2016-09-01 | 2018-12-31 |  | Molung | 5
14923 | Okhaldhunga | Prapcha | 9 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | Cash support for shelter construction | # of households | Yes | Ongoing | 33 | 22 | 2016-09-01 | 2018-12-31 |  | Molung | 5
14924 | Okhaldhunga | Harkapur | 1 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Cash support for shelter construction | # of households | Yes | Ongoing | 21 | 5 | 2016-09-01 | 2018-12-31 |  | Molung | 4
14925 | Okhaldhunga | Harkapur | 2 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Cash support for shelter construction | # of households | Yes | Ongoing | 41 | 2 | 2016-09-01 | 2018-12-31 |  | Molung | 4
14926 | Okhaldhunga | Harkapur | 3 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Cash support for shelter construction | # of households | Yes | Ongoing | 65 | 9 | 2016-09-01 | 2018-12-31 |  | Molung | 4
14927 | Okhaldhunga | Harkapur | 4 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Cash support for shelter construction | # of households | Yes | Ongoing | 16 | 4 | 2016-09-01 | 2018-12-31 |  | Molung | 4
14928 | Okhaldhunga | Harkapur | 5 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Cash support for shelter construction | # of households | Yes | Ongoing | 30 | 7 | 2016-09-01 | 2018-12-31 |  | Molung | 4
14929 | Okhaldhunga | Harkapur | 6 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Cash support for shelter construction | # of households | Yes | Ongoing | 52 | 1 | 2016-09-01 | 2018-12-31 |  | Molung | 4
14930 | Okhaldhunga | Harkapur | 7 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Cash support for shelter construction | # of households | Yes | Ongoing | 33 | 9 | 2016-09-01 | 2018-12-31 |  | Molung | 3
14931 | Okhaldhunga | Harkapur | 8 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Cash support for shelter construction | # of households | Yes | Ongoing | 46 | 3 | 2016-09-01 | 2018-12-31 |  | Molung | 3
14932 | Okhaldhunga | Harkapur | 9 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Cash support for shelter construction | # of households | Yes | Ongoing | 23 | 3 | 2016-09-01 | 2018-12-31 |  | Molung | 3
14933 | Okhaldhunga | Prapcha | 1 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Cash support for shelter construction | # of households | Yes | Ongoing | 22 | 7 | 2016-09-01 | 2018-12-31 |  | Molung | 3
14934 | Okhaldhunga | Prapcha | 2 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Cash support for shelter construction | # of households | Yes | Ongoing | 42 | 13 | 2016-09-01 | 2018-12-31 |  | Molung | 3
14935 | Okhaldhunga | Prapcha | 3 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Cash support for shelter construction | # of households | Yes | Ongoing | 12 | 9 | 2016-09-01 | 2018-12-31 |  | Molung | 5
14936 | Okhaldhunga | Prapcha | 4 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Cash support for shelter construction | # of households | Yes | Ongoing | 23 | 15 | 2016-09-01 | 2018-12-31 |  | Molung | 5
14937 | Okhaldhunga | Prapcha | 5 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Cash support for shelter construction | # of households | Yes | Completed | 8 | 8 | 2017-01-15 | 2018-12-31 |  | Molung | 5
14938 | Okhaldhunga | Prapcha | 6 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Cash support for shelter construction | # of households | Yes | Ongoing | 21 | 8 | 2016-09-01 | 2018-12-31 |  | Molung | 5
14939 | Okhaldhunga | Prapcha | 7 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Cash support for shelter construction | # of households | Yes | Ongoing | 16 | 6 | 2017-01-15 | 2018-12-31 |  | Molung | 5
14940 | Okhaldhunga | Prapcha | 8 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Cash support for shelter construction | # of households | Yes | Ongoing | 16 | 12 | 2016-09-01 | 2018-12-31 |  | Molung | 5
14941 | Okhaldhunga | Prapcha | 9 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | Cash support for shelter construction | # of households | Yes | Ongoing | 33 | 21 | 2016-09-01 | 2018-12-31 |  | Molung | 5
14942 | Okhaldhunga | Harkapur | 1 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous | Oreintation on Building back safer | # of households | Yes | Completed | 21 | 21 | 2016-09-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Molung | 4
14943 | Okhaldhunga | Harkapur | 2 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous | Oreintation on Building back safer | # of households | Yes | Completed | 41 | 41 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Molung | 4
14944 | Okhaldhunga | Harkapur | 3 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous | Oreintation on Building back safer | # of households | Yes | Completed | 65 | 65 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Molung | 4
14945 | Okhaldhunga | Harkapur | 4 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous | Oreintation on Building back safer | # of households | Yes | Completed | 16 | 16 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Molung | 4
14946 | Okhaldhunga | Harkapur | 5 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous | Oreintation on Building back safer | # of households | Yes | Completed | 30 | 30 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Molung | 4
14947 | Okhaldhunga | Harkapur | 6 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous | Oreintation on Building back safer | # of households | Yes | Completed | 52 | 52 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Molung | 4
14948 | Okhaldhunga | Harkapur | 7 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous | Oreintation on Building back safer | # of households | Yes | Completed | 33 | 33 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Molung | 3
14949 | Okhaldhunga | Harkapur | 8 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous | Oreintation on Building back safer | # of households | Yes | Completed | 46 | 46 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Molung | 3
14950 | Okhaldhunga | Harkapur | 9 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous | Oreintation on Building back safer | # of households | Yes | Completed | 23 | 23 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Molung | 3
14951 | Okhaldhunga | Prapcha | 1 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous | Oreintation on Building back safer | # of households | Yes | Completed | 22 | 22 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Molung | 3
14952 | Okhaldhunga | Prapcha | 2 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous | Oreintation on Building back safer | # of households | Yes | Completed | 42 | 42 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Molung | 3
14953 | Okhaldhunga | Prapcha | 3 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous | Oreintation on Building back safer | # of households | Yes | Completed | 12 | 12 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Molung | 5
14954 | Okhaldhunga | Prapcha | 4 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous | Oreintation on Building back safer | # of households | Yes | Completed | 23 | 23 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Molung | 5
14955 | Okhaldhunga | Prapcha | 5 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous | Oreintation on Building back safer | # of households | Yes | Completed | 8 | 8 | 2017-03-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Molung | 5
14956 | Okhaldhunga | Prapcha | 6 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous | Oreintation on Building back safer | # of households | Yes | Completed | 21 | 21 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Molung | 5
14957 | Okhaldhunga | Prapcha | 7 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous | Oreintation on Building back safer | # of households | Yes | Completed | 16 | 16 | 2017-03-01 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Molung | 5
14958 | Okhaldhunga | Prapcha | 8 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous | Oreintation on Building back safer | # of households | Yes | Completed | 16 | 16 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Molung | 5
14959 | Okhaldhunga | Prapcha | 9 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous | Oreintation on Building back safer | # of households | Yes | Completed | 33 | 33 | 2017-01-15 | 2018-12-31 | As technical assistance is provided by Red Cross technical staff, no additionl budget is required for this. | Molung | 5
14960 | Okhaldhunga | Rawadolu | 7 | GON | DLPIU | DLPIU | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2018-01-26 | 2018-02-01 |  | Khijidemba | 7
14961 | Okhaldhunga | Tarkerabari | 8 | GON | DLPIU | DLPIU | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2018-02-05 | 2018-02-11 |  | Likhu | 8
14962 | Okhaldhunga | Moli | 1 | GON | DLPIU | DLPIU | Training | Short training | Masons (7 days DUDBC, rural or urban) |  |  | Yes | Completed | 30 | 30 | 2018-05-14 | 2018-05-20 |  | Manebhanjyang | 1
14963 | Okhaldhunga | Prapcha | 4 | GON | DLPIU | DLPIU | Training | Short training | Masons (7 days DUDBC, rural or urban) |  |  | Yes | Completed | 27 | 27 |  |  |  | Molung | 5
14964 | Okhaldhunga | Shreechaur | 6 | GON | DLPIU | DLPIU | Training | Short training | Masons (7 days DUDBC, rural or urban) |  |  | Yes | Completed | 27 | 27 |  |  |  | Molung | 6
14965 | Ramechhap | Bhujee | 1 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 13 | 13 |  |  |  | Umakunda | 7
14966 | Ramechhap | Bhujee | 2 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 13 | 13 |  |  |  | Umakunda | 7
14967 | Ramechhap | Bhujee | 3 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 13 | 13 |  |  |  | Umakunda | 7
14968 | Ramechhap | Bhujee | 4 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 13 | 13 |  |  |  | Umakunda | 7
14969 | Ramechhap | Bhujee | 5 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 13 | 13 |  |  |  | Umakunda | 7
14970 | Ramechhap | Bhujee | 6 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 13 | 13 |  |  |  | Umakunda | 7
14971 | Ramechhap | Bhujee | 7 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 13 | 13 |  |  |  | Umakunda | 7
14972 | Ramechhap | Bhujee | 8 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 13 | 13 |  |  |  | Umakunda | 7
14973 | Ramechhap | Bhujee | 9 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 16 | 16 |  |  |  | Umakunda | 7
14974 | Ramechhap | Bhujee | 1 | ACTED | ECARDS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC 5Days Training | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18 |  | Umakunda | 7
14975 | Ramechhap | Bhujee | 2 | ACTED | ECARDS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC 5Days Training | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18 |  | Umakunda | 7
14976 | Ramechhap | Bhujee | 3 | ACTED | ECARDS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC 5Days Training | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18 |  | Umakunda | 7
14977 | Ramechhap | Bhujee | 4 | ACTED | ECARDS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC 5Days Training | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18 |  | Umakunda | 7
14978 | Ramechhap | Bhujee | 5 | ACTED | ECARDS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC 5Days Training | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18 |  | Umakunda | 7
14979 | Ramechhap | Bhujee | 6 | ACTED | ECARDS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC 5Days Training | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18 |  | Umakunda | 7
14980 | Ramechhap | Bhujee | 7 | ACTED | ECARDS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC 5Days Training | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18 |  | Umakunda | 7
14981 | Ramechhap | Bhujee | 8 | ACTED | ECARDS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC 5Days Training | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18 |  | Umakunda | 7
14982 | Ramechhap | Bhujee | 9 | ACTED | ECARDS |  | Training | Short training | Masons (other curriculums, specify in Activity Detail) | DUDBC 5Days Training | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18 |  | Umakunda | 7
14983 | Ramechhap | Guptesor | 1 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 9 | 9 |  |  |  | Umakunda | 6
14984 | Ramechhap | Guptesor | 2 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 9 | 9 |  |  |  | Umakunda | 6
14985 | Ramechhap | Guptesor | 3 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 9 | 9 |  |  |  | Umakunda | 6
14986 | Ramechhap | Guptesor | 4 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 9 | 9 |  |  |  | Umakunda | 6
14987 | Ramechhap | Guptesor | 5 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 9 | 9 |  |  |  | Umakunda | 6
14988 | Ramechhap | Guptesor | 6 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 9 | 9 |  |  |  | Umakunda | 6
14989 | Ramechhap | Guptesor | 7 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 9 | 9 |  |  |  | Umakunda | 6
14990 | Ramechhap | Guptesor | 8 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 9 | 9 |  |  |  | Umakunda | 6
14991 | Ramechhap | Guptesor | 9 | ACTED | ECARDS | DFID | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Labour Assistance: NPR 4,700 | # of constructions | Yes | Completed | 11 | 11 |  |  |  | Umakunda | 6
14992 | Ramechhap | Guptesor | 1 | ACTED | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18 |  | Umakunda | 6
14993 | Ramechhap | Guptesor | 2 | ACTED | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-14 | 2016-02-18 |  | Umakunda | 6
14994 | Ramechhap | Guptesor | 3 | ACTED | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18 |  | Umakunda | 6
14995 | Ramechhap | Guptesor | 4 | ACTED | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-14 | 2016-02-18 |  | Umakunda | 6
14996 | Ramechhap | Guptesor | 5 | ACTED | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-14 | 2016-02-18 |  | Umakunda | 6
14997 | Ramechhap | Guptesor | 6 | ACTED | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-14 | 2016-02-18 |  | Umakunda | 6
14998 | Ramechhap | Guptesor | 7 | ACTED | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-14 | 2016-02-18 |  | Umakunda | 6
14999 | Ramechhap | Guptesor | 8 | ACTED | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-14 | 2016-02-18 |  | Umakunda | 6
15000 | Ramechhap | Guptesor | 9 | ACTED | ECARDS |  | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-14 | 2016-02-18 |  | Umakunda | 6
15001 | Ramechhap | Pakarbas | 3 | CDS | CDS | MCC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 17 | 17 | 2017-08-29 | 2017-09-04 |  | Khadadevi | 4
15002 | Ramechhap | Rakathum | 1 | CDS | CDS | MCC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2017-09-20 | 2017-09-26 |  | Khadadevi | 1
15003 | Ramechhap | Manthali N.P. | 6 | CDS | CDS | MCC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2017-08-29 | 2017-09-04 |  | Manthali | 3
15004 | Ramechhap | Manthali N.P. | 8 | CDS | CDS | MCC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-09-20 | 2017-09-26 |  | Manthali | 4
15005 | Ramechhap | Makadum | 2 | CSIDB | CSIDB | NRA | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 24 | 24 | 2017-01-09 | 2017-02-19 |  | Khadadevi | 6
15006 | Ramechhap | Ramechhap N.P. | 5 | CSIDB | CSIDB | NRA | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-01-15 | 2017-02-23 |  | Ramechhap | 8
15007 | Ramechhap | Manthali N.P. | 2 | CSIDB | CSIDB | NRA | Training | Vocational training | Semiskilled construction workers (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-01-24 | 2017-03-04 |  | Manthali | 1
15008 | Ramechhap | Bhirpani | 3 | CSIDB | CSIDB | NRA | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 16 | 16 | 2017-03-30 | 2017-05-10 |  | Khadadevi | 3
15009 | Ramechhap | Bhirpani | 7 | CSIDB | CSIDB | NRA | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-05-22 | 2017-07-01 |  | Khadadevi | 3
15010 | Ramechhap | BamtiBhandar | 2 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 31 | 31 | 2016-01-01 | 2016-02-28 |  | Umakunda | 2
15011 | Ramechhap | BamtiBhandar | 3 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 18 | 18 | 2016-01-01 | 2016-02-28 |  | Umakunda | 2
15012 | Ramechhap | BamtiBhandar | 6 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 132 | 132 | 2016-01-01 | 2016-02-28 |  | Umakunda | 2
15013 | Ramechhap | Chuchure | 1 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 95 | 95 | 2016-01-01 | 2016-02-28 |  | Gokulganga | 1
15014 | Ramechhap | Chuchure | 4 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 40 | 40 | 2016-01-01 | 2016-02-28 |  | Gokulganga | 1
15015 | Ramechhap | Chuchure | 7 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 56 | 56 | 2016-01-01 | 2016-02-28 |  | Gokulganga | 1
15016 | Ramechhap | Chuchure | 8 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 132 | 132 | 2016-01-01 | 2016-02-28 |  | Gokulganga | 1
15017 | Ramechhap | Gumdel | 2 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 48 | 48 | 2016-01-01 | 2016-02-28 |  | Umakunda | 1
15018 | Ramechhap | Gumdel | 3 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 98 | 98 | 2016-01-01 | 2016-02-28 |  | Umakunda | 1
15019 | Ramechhap | Gumdel | 4 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 55 | 55 | 2016-01-01 | 2016-02-28 |  | Umakunda | 1
15020 | Ramechhap | Gumdel | 6 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 105 | 105 | 2016-01-01 | 2016-02-28 |  | Umakunda | 1
15021 | Ramechhap | Gumdel | 7 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 32 | 32 | 2016-01-01 | 2016-02-28 |  | Umakunda | 1
15022 | Ramechhap | Gumdel | 8 | GOAL | CDS | DFID | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 69 | 69 | 2016-01-01 | 2016-02-28 |  | Umakunda | 1
15023 | Ramechhap | Kubukasthali | 3 | GOAL | CDS | ECHO | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 193 | 193 | 2016-01-01 | 2016-02-28 |  | Umakunda | 3
15024 | Ramechhap | Kubukasthali | 4 | GOAL | CDS | ECHO | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 204 | 207 | 2016-01-01 | 2016-02-28 |  | Umakunda | 3
15025 | Ramechhap | Pritee | 2 | GOAL | CDS | ECHO | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 152 | 152 | 2016-01-01 | 2016-02-28 |  | Umakunda | 5
15026 | Ramechhap | Pritee | 5 | GOAL | CDS | ECHO | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 30 | 30 | 2016-01-01 | 2016-02-28 |  | Umakunda | 5
15027 | Ramechhap | Pritee | 7 | GOAL | CDS | ECHO | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 142 | 142 | 2016-01-01 | 2016-02-28 |  | Umakunda | 4
15028 | Ramechhap | Those | 1 | GOAL | CDS | ECHO | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 133 | 133 | 2016-01-01 | 2016-02-28 |  | Gokulganga | 2
15029 | Ramechhap | Those | 2 | GOAL | CDS | ECHO | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 88 | 88 | 2016-01-01 | 2016-02-28 |  | Gokulganga | 2
15030 | Ramechhap | Those | 3 | GOAL | CDS | ECHO | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 118 | 118 | 2016-01-01 | 2016-02-28 |  | Gokulganga | 2
15031 | Ramechhap | Farpu | 6 | GON - DUDBC | GON - DUDBC | GON - DUDBC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-06-17 | 2017-06-23 |  | Gokulganga | 6
15032 | Ramechhap | BamtiBhandar | 1 | HELVETAS | KBPS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-17 |  | Umakunda | 2
15033 | Ramechhap | BamtiBhandar | 2 | HELVETAS | KBPS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-17 |  | Umakunda | 2
15034 | Ramechhap | BamtiBhandar | 3 | HELVETAS | KBPS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-17 |  | Umakunda | 2
15035 | Ramechhap | BamtiBhandar | 4 | HELVETAS | KBPS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-17 |  | Umakunda | 2
15036 | Ramechhap | BamtiBhandar | 7 | HELVETAS | KBPS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-17 |  | Umakunda | 2
15037 | Ramechhap | BamtiBhandar | 9 | HELVETAS | KBPS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-17 |  | Umakunda | 2
15038 | Ramechhap | Betali | 1 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12 |  | Gokulganga | 4
15039 | Ramechhap | Betali | 3 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12 |  | Gokulganga | 4
15040 | Ramechhap | Betali | 6 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12 |  | Gokulganga | 4
15041 | Ramechhap | Betali | 1 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-26 | 2016-02-13 |  | Gokulganga | 4
15042 | Ramechhap | Betali | 1 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-17 | 2016-02-04 |  | Gokulganga | 4
15043 | Ramechhap | Betali | 2 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-26 | 2016-02-13 |  | Gokulganga | 4
15044 | Ramechhap | Betali | 2 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-17 | 2016-02-04 |  | Gokulganga | 4
15045 | Ramechhap | Betali | 3 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-26 | 2016-02-13 |  | Gokulganga | 4
15046 | Ramechhap | Betali | 3 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-17 | 2016-02-04 |  | Gokulganga | 4
15047 | Ramechhap | Betali | 4 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-26 | 2016-02-13 |  | Gokulganga | 4
15048 | Ramechhap | Betali | 4 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-17 | 2016-02-04 |  | Gokulganga | 4
15049 | Ramechhap | Betali | 6 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-26 | 2016-02-13 |  | Gokulganga | 4
15050 | Ramechhap | Betali | 6 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-12-17 | 2016-02-04 |  | Gokulganga | 4
15051 | Ramechhap | Betali | 8 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-17 | 2016-02-04 |  | Gokulganga | 4
15052 | Ramechhap | Betali | 9 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-26 | 2016-02-13 |  | Gokulganga | 4
15053 | Ramechhap | Betali | 9 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-17 | 2016-02-04 |  | Gokulganga | 4
15054 | Ramechhap | Bhujee | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-23 | 2017-06-24 |  | Umakunda | 7
15055 | Ramechhap | Bhujee | 7 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-23 | 2017-06-24 |  | Umakunda | 7
15056 | Ramechhap | Bhujee | 9 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 20 | 20 | 2017-04-23 | 2017-06-24 |  | Umakunda | 7
15057 | Ramechhap | Chuchure | 3 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-12 |  | Gokulganga | 1
15058 | Ramechhap | Chuchure | 5 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-12 |  | Gokulganga | 1
15059 | Ramechhap | Chuchure | 2 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-15 | 2016-02-03 |  | Gokulganga | 1
15060 | Ramechhap | Chuchure | 2 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-15 | 2016-02-02 |  | Gokulganga | 1
15061 | Ramechhap | Chuchure | 3 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-15 | 2016-02-03 |  | Gokulganga | 1
15062 | Ramechhap | Chuchure | 3 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 | 2015-12-15 | 2016-02-02 |  | Gokulganga | 1
15063 | Ramechhap | Chuchure | 5 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-15 | 2016-02-03 |  | Gokulganga | 1
15064 | Ramechhap | Chuchure | 5 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-12-15 | 2016-02-02 |  | Gokulganga | 1
15065 | Ramechhap | Chuchure | 6 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-15 | 2016-02-02 |  | Gokulganga | 1
15066 | Ramechhap | Dimipokhari | 2 | HELVETAS | MTSDI | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-28 | 2016-08-23 |  | Sunapati | 2
15067 | Ramechhap | Dimipokhari | 3 | HELVETAS | MTSDI | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-28 | 2016-08-23 |  | Sunapati | 2
15068 | Ramechhap | Dimipokhari | 5 | HELVETAS | MTSDI | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-28 | 2016-08-23 |  | Sunapati | 2
15069 | Ramechhap | Dimipokhari | 6 | HELVETAS | MTSDI | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 3 | 3 | 2016-06-28 | 2016-08-23 |  | Sunapati | 2
15070 | Ramechhap | Dimipokhari | 7 | HELVETAS | MTSDI | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-28 | 2016-08-23 |  | Sunapati | 2
15071 | Ramechhap | Dimipokhari | 8 | HELVETAS | MTSDI | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 3 | 3 | 2016-06-28 | 2016-08-23 |  | Sunapati | 2
15072 | Ramechhap | Dimipokhari | 1 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-28 | 2016-08-24 |  | Sunapati | 2
15073 | Ramechhap | Dimipokhari | 1 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-28 | 2016-08-23 |  | Sunapati | 2
15074 | Ramechhap | Dimipokhari | 2 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-28 | 2016-08-24 |  | Sunapati | 2
15075 | Ramechhap | Dimipokhari | 2 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-28 | 2016-08-23 |  | Sunapati | 2
15076 | Ramechhap | Dimipokhari | 3 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-28 | 2016-08-24 |  | Sunapati | 2
15077 | Ramechhap | Dimipokhari | 3 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-28 | 2016-08-23 |  | Sunapati | 2
15078 | Ramechhap | Dimipokhari | 4 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-28 | 2016-08-24 |  | Sunapati | 2
15079 | Ramechhap | Dimipokhari | 5 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-28 | 2016-08-24 |  | Sunapati | 2
15080 | Ramechhap | Dimipokhari | 5 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-28 | 2016-08-23 |  | Sunapati | 2
15081 | Ramechhap | Dimipokhari | 6 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-28 | 2016-08-23 |  | Sunapati | 2
15082 | Ramechhap | Dimipokhari | 7 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-28 | 2016-08-23 |  | Sunapati | 2
15083 | Ramechhap | Dimipokhari | 8 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-28 | 2016-08-23 |  | Sunapati | 2
15084 | Ramechhap | Dimipokhari | 9 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-28 | 2016-08-23 |  | Sunapati | 2
15085 | Ramechhap | Farpu | 2 | HELVETAS | CS | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2015-12-08 | 2016-02-03 |  | Gokulganga | 6
15086 | Ramechhap | Farpu | 4 | HELVETAS | CS | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2015-12-08 | 2016-02-03 |  | Gokulganga | 6
15087 | Ramechhap | Farpu | 5 | HELVETAS | CS | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 3 | 3 | 2015-12-08 | 2016-02-03 |  | Gokulganga | 6
15088 | Ramechhap | Farpu | 9 | HELVETAS | CS | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 3 | 3 | 2015-12-08 | 2016-02-03 |  | Gokulganga | 6
15089 | Ramechhap | Farpu | 1 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-08 | 2016-02-03 |  | Gokulganga | 6
15090 | Ramechhap | Farpu | 2 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-08 | 2016-02-03 |  | Gokulganga | 6
15091 | Ramechhap | Farpu | 4 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-08 | 2016-02-03 |  | Gokulganga | 6
15092 | Ramechhap | Farpu | 5 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-09 | 2016-08-05 |  | Gokulganga | 6
15093 | Ramechhap | Farpu | 5 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-12-08 | 2016-02-03 |  | Gokulganga | 6
15094 | Ramechhap | Farpu | 5 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-09 | 2016-08-08 |  | Gokulganga | 6
15095 | Ramechhap | Farpu | 6 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-09 | 2016-08-05 |  | Gokulganga | 6
15096 | Ramechhap | Farpu | 6 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-09 | 2016-08-08 |  | Gokulganga | 6
15097 | Ramechhap | Farpu | 7 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-09 | 2016-08-05 |  | Gokulganga | 6
15098 | Ramechhap | Farpu | 7 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-08 | 2016-02-03 |  | Gokulganga | 6
15099 | Ramechhap | Farpu | 7 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-09 | 2016-08-08 |  | Gokulganga | 6
15100 | Ramechhap | Farpu | 8 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-08 | 2016-02-03 |  | Gokulganga | 6
15101 | Ramechhap | Farpu | 9 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-09 | 2016-08-05 |  | Gokulganga | 6
15102 | Ramechhap | Farpu | 9 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-12-08 | 2016-02-03 |  | Gokulganga | 6
15103 | Ramechhap | Farpu | 9 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-09 | 2016-08-08 |  | Gokulganga | 6
15104 | Ramechhap | Gumdel | 4 | HELVETAS | KBPS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-29 | 2017-06-20 |  | Umakunda | 1
15105 | Ramechhap | Gumdel | 7 | HELVETAS | KBPS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-29 | 2017-06-20 |  | Umakunda | 1
15106 | Ramechhap | GunsiBhadaure | 3 | HELVETAS | MTSDI | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-30 | 2016-09-09 |  | Sunapati | 1
15107 | Ramechhap | GunsiBhadaure | 4 | HELVETAS | MTSDI | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-30 | 2016-09-09 |  | Sunapati | 1
15108 | Ramechhap | GunsiBhadaure | 9 | HELVETAS | MTSDI | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2016-06-30 | 2016-09-09 |  | Doramba | 5
15109 | Ramechhap | GunsiBhadaure | 1 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-07-08 | 2016-09-04 |  | Sunapati | 1
15110 | Ramechhap | GunsiBhadaure | 1 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-30 | 2016-09-09 |  | Sunapati | 1
15111 | Ramechhap | GunsiBhadaure | 2 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-30 | 2016-09-09 |  | Sunapati | 1
15112 | Ramechhap | GunsiBhadaure | 3 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-30 | 2016-09-09 |  | Sunapati | 1
15113 | Ramechhap | GunsiBhadaure | 4 | HELVETAS | MTSDI | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-07-08 | 2016-09-04 |  | Sunapati | 1
15114 | Ramechhap | GunsiBhadaure | 4 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-30 | 2016-09-09 |  | Sunapati | 1
15115 | Ramechhap | GunsiBhadaure | 5 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-30 | 2016-09-09 |  | Sunapati | 1
15116 | Ramechhap | GunsiBhadaure | 8 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-30 | 2016-09-09 |  | Doramba | 5
15117 | Ramechhap | GunsiBhadaure | 9 | HELVETAS | MTSDI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-30 | 2016-09-09 |  | Doramba | 5
15118 | Ramechhap | Guptesor | 1 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-23 | 2017-06-27 |  | Umakunda | 6
15119 | Ramechhap | Guptesor | 2 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-23 | 2017-06-27 |  | Umakunda | 6
15120 | Ramechhap | Guptesor | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-23 | 2017-06-27 |  | Umakunda | 6
15121 | Ramechhap | Guptesor | 4 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-23 | 2017-06-27 |  | Umakunda | 6
15122 | Ramechhap | Guptesor | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-23 | 2017-06-27 |  | Umakunda | 6
15123 | Ramechhap | Guptesor | 7 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-23 | 2017-06-27 |  | Umakunda | 6
15124 | Ramechhap | Guptesor | 8 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-23 | 2017-06-27 |  | Umakunda | 6
15125 | Ramechhap | Khimti | 3 | HELVETAS | CS | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2015-12-12 | 2016-02-08 |  | Likhu | 6
15126 | Ramechhap | Khimti | 4 | HELVETAS | CS | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2015-12-12 | 2016-02-08 |  | Likhu | 6
15127 | Ramechhap | Khimti | 1 | HELVETAS | CS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-12 | 2016-02-08 |  | Likhu | 6
15128 | Ramechhap | Khimti | 1 | HELVETAS | CS | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-12 | 2016-02-08 |  | Likhu | 6
15129 | Ramechhap | Khimti | 2 | HELVETAS | CS | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-12 | 2016-02-08 |  | Likhu | 6
15130 | Ramechhap | Khimti | 3 | HELVETAS | CS | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-12 | 2016-02-08 |  | Likhu | 6
15131 | Ramechhap | Khimti | 3 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-12 | 2016-01-30 |  | Likhu | 6
15132 | Ramechhap | Khimti | 4 | HELVETAS | CS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-12 | 2016-02-08 |  | Likhu | 6
15133 | Ramechhap | Khimti | 4 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-12 | 2016-01-30 |  | Likhu | 6
15134 | Ramechhap | Khimti | 5 | HELVETAS | CS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-12 | 2016-02-08 |  | Likhu | 6
15135 | Ramechhap | Khimti | 5 | HELVETAS | CS | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-12 | 2016-02-08 |  | Likhu | 6
15136 | Ramechhap | Khimti | 6 | HELVETAS | CS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-12 | 2016-02-08 |  | Likhu | 6
15137 | Ramechhap | Khimti | 6 | HELVETAS | CS | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-12 | 2016-02-08 |  | Likhu | 6
15138 | Ramechhap | Khimti | 7 | HELVETAS | CS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-12 | 2016-02-08 |  | Likhu | 6
15139 | Ramechhap | Khimti | 7 | HELVETAS | CS | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-12 | 2016-02-08 |  | Likhu | 6
15140 | Ramechhap | Khimti | 7 | HELVETAS | CS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-12 | 2016-01-30 |  | Likhu | 6
15141 | Ramechhap | Khimti | 8 | HELVETAS | CS | SDC | Training | Vocational training | Electrician (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-12 | 2016-02-08 |  | Likhu | 6
15142 | Ramechhap | Kubukasthali | 1 | HELVETAS | KBPS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-19 |  | Umakunda | 3
15143 | Ramechhap | Kubukasthali | 2 | HELVETAS | KBPS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-19 |  | Umakunda | 3
15144 | Ramechhap | Kubukasthali | 3 | HELVETAS | KBPS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-19 |  | Umakunda | 3
15145 | Ramechhap | Kubukasthali | 4 | HELVETAS | KBPS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-19 |  | Umakunda | 3
15146 | Ramechhap | Kubukasthali | 5 | HELVETAS | KBPS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-19 |  | Umakunda | 3
15147 | Ramechhap | Kubukasthali | 6 | HELVETAS | KBPS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-19 |  | Umakunda | 3
15148 | Ramechhap | Kubukasthali | 7 | HELVETAS | KBPS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-19 |  | Umakunda | 3
15149 | Ramechhap | Kubukasthali | 8 | HELVETAS | KBPS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-19 |  | Umakunda | 3
15150 | Ramechhap | Kubukasthali | 9 | HELVETAS | KBPS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-20 | 2017-06-19 |  | Umakunda | 3
15151 | Ramechhap | Lakhanpur | 2 | HELVETAS | SODEC-N | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-16 | 2016-08-15 |  | Doramba | 6
15152 | Ramechhap | Lakhanpur | 3 | HELVETAS | SODEC-N | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-16 | 2016-08-15 |  | Doramba | 6
15153 | Ramechhap | Lakhanpur | 5 | HELVETAS | SODEC-N | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-16 | 2016-08-15 |  | Doramba | 6
15154 | Ramechhap | Lakhanpur | 8 | HELVETAS | SODEC-N | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-16 | 2016-08-15 |  | Doramba | 7
15155 | Ramechhap | Lakhanpur | 2 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-16 | 2016-08-15 |  | Doramba | 6
15156 | Ramechhap | Lakhanpur | 3 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-16 | 2016-08-15 |  | Doramba | 6
15157 | Ramechhap | Lakhanpur | 4 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-06-16 | 2016-08-15 |  | Doramba | 6
15158 | Ramechhap | Lakhanpur | 5 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-16 | 2016-08-15 |  | Doramba | 6
15159 | Ramechhap | Lakhanpur | 6 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-16 | 2016-08-15 |  | Doramba | 7
15160 | Ramechhap | Lakhanpur | 7 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-16 | 2016-08-15 |  | Doramba | 7
15161 | Ramechhap | Lakhanpur | 8 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-16 | 2016-08-15 |  | Doramba | 7
15162 | Ramechhap | Manthali N.P. | 13 | HELVETAS | TRACE | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 10 | 10 | 2016-06-27 | 2016-08-20 |  | Manthali | 7
15163 | Ramechhap | Manthali N.P. | 14 | HELVETAS | TRACE | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 4 | 4 | 2016-06-27 | 2016-08-20 |  | Manthali | 7
15164 | Ramechhap | Manthali N.P. | 13 | HELVETAS | TRACE | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-07-27 | 2016-09-20 |  | Manthali | 7
15165 | Ramechhap | Manthali N.P. | 13 | HELVETAS | TRACE | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-06-26 | 2016-09-24 |  | Manthali | 7
15166 | Ramechhap | Manthali N.P. | 14 | HELVETAS | TRACE | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-07-27 | 2016-09-20 |  | Manthali | 7
15167 | Ramechhap | Manthali N.P. | 14 | HELVETAS | TRACE | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-07-02 | 2016-08-31 |  | Manthali | 7
15168 | Ramechhap | Namadi | 1 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 3 | 3 | 2015-12-16 | 2016-02-12 |  | Gokulganga | 5
15169 | Ramechhap | Namadi | 6 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-12 |  | Gokulganga | 5
15170 | Ramechhap | Namadi | 8 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-12 |  | Gokulganga | 5
15171 | Ramechhap | Namadi | 9 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12 |  | Gokulganga | 5
15172 | Ramechhap | Namadi | 1 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-22 | 2016-08-19 |  | Gokulganga | 5
15173 | Ramechhap | Namadi | 1 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-17 | 2016-02-03 |  | Gokulganga | 5
15174 | Ramechhap | Namadi | 1 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 13 | 13 | 2016-06-22 | 2016-08-24 |  | Gokulganga | 5
15175 | Ramechhap | Namadi | 2 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-08-24 |  | Gokulganga | 5
15176 | Ramechhap | Namadi | 6 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-19 |  | Gokulganga | 5
15177 | Ramechhap | Namadi | 6 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-17 | 2016-02-03 |  | Gokulganga | 5
15178 | Ramechhap | Namadi | 6 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-22 | 2016-08-24 |  | Gokulganga | 5
15179 | Ramechhap | Namadi | 7 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-19 |  | Gokulganga | 5
15180 | Ramechhap | Namadi | 7 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-17 | 2016-02-03 |  | Gokulganga | 5
15181 | Ramechhap | Namadi | 7 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-22 | 2016-08-24 |  | Gokulganga | 5
15182 | Ramechhap | Namadi | 8 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-08-19 |  | Gokulganga | 5
15183 | Ramechhap | Namadi | 8 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-17 | 2016-02-03 |  | Gokulganga | 5
15184 | Ramechhap | Namadi | 8 | HELVETAS | ANS | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-22 | 2016-08-24 |  | Gokulganga | 5
15185 | Ramechhap | Namadi | 9 | HELVETAS | ANS | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-19 |  | Gokulganga | 5
15186 | Ramechhap | Namadi | 9 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-17 | 2016-02-03 |  | Gokulganga | 5
15187 | Ramechhap | Pritee | 1 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-18 | 2017-06-21 |  | Umakunda | 4
15188 | Ramechhap | Pritee | 2 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 20 | 20 | 2017-04-18 | 2017-06-21 |  | Umakunda | 5
15189 | Ramechhap | Pritee | 3 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-18 | 2017-06-21 |  | Umakunda | 5
15190 | Ramechhap | Pritee | 5 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-18 | 2017-06-21 |  | Umakunda | 5
15191 | Ramechhap | Pritee | 7 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-18 | 2017-06-21 |  | Umakunda | 4
15192 | Ramechhap | Pritee | 9 | HELVETAS | PHPI | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) | House constructed during OJT | # of trainees | Yes | Completed | 10 | 10 | 2017-04-18 | 2017-06-21 |  | Umakunda | 4
15193 | Ramechhap | Rasanalu | 2 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2016-06-28 | 2016-09-09 |  | Gokulganga | 3
15194 | Ramechhap | Rasanalu | 3 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2016-06-28 | 2016-09-09 |  | Gokulganga | 3
15195 | Ramechhap | Rasanalu | 2 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-06-29 | 2016-08-29 |  | Gokulganga | 3
15196 | Ramechhap | Rasanalu | 2 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-06-29 | 2016-08-29 |  | Gokulganga | 3
15197 | Ramechhap | Rasanalu | 3 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-29 | 2016-08-29 |  | Gokulganga | 3
15198 | Ramechhap | Rasanalu | 5 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-29 | 2016-08-29 |  | Gokulganga | 3
15199 | Ramechhap | Those | 3 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 7 | 7 | 2015-12-16 | 2016-02-12 |  | Gokulganga | 2
15200 | Ramechhap | Those | 6 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-12 |  | Gokulganga | 2
15201 | Ramechhap | Those | 8 | HELVETAS | BDCC | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-12 |  | Gokulganga | 2
15202 | Ramechhap | Those | 2 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-16 | 2016-08-04 |  | Gokulganga | 2
15203 | Ramechhap | Those | 2 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-16 | 2016-08-04 |  | Gokulganga | 2
15204 | Ramechhap | Those | 3 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-03 |  | Gokulganga | 2
15205 | Ramechhap | Those | 3 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-16 | 2016-08-04 |  | Gokulganga | 2
15206 | Ramechhap | Those | 3 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-17 | 2016-02-03 |  | Gokulganga | 2
15207 | Ramechhap | Those | 3 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-06-16 | 2016-08-04 |  | Gokulganga | 2
15208 | Ramechhap | Those | 4 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-03 |  | Gokulganga | 2
15209 | Ramechhap | Those | 5 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-03 |  | Gokulganga | 2
15210 | Ramechhap | Those | 5 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-17 | 2016-02-03 |  | Gokulganga | 2
15211 | Ramechhap | Those | 6 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-17 | 2016-02-03 |  | Gokulganga | 2
15212 | Ramechhap | Those | 7 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-16 | 2016-02-03 |  | Gokulganga | 2
15213 | Ramechhap | Those | 7 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-16 | 2016-08-04 |  | Gokulganga | 2
15214 | Ramechhap | Those | 7 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-17 | 2016-02-03 |  | Gokulganga | 2
15215 | Ramechhap | Those | 7 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-16 | 2016-08-04 |  | Gokulganga | 2
15216 | Ramechhap | Those | 8 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-12-16 | 2016-02-03 |  | Gokulganga | 2
15217 | Ramechhap | Those | 8 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-12-17 | 2016-02-03 |  | Gokulganga | 2
15218 | Ramechhap | Those | 9 | HELVETAS | BDCC | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-16 | 2016-02-03 |  | Gokulganga | 2
15219 | Ramechhap | Those | 9 | HELVETAS | BDCC | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 9 | 2015-12-17 | 2016-02-03 |  | Gokulganga | 2
15220 | Ramechhap | Tilpung | 1 | HELVETAS | SBPK | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-01-27 | 2017-04-24 |  | Likhu | 7
15221 | Ramechhap | Tilpung | 4 | HELVETAS | SBPK | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-01-27 | 2017-04-24 |  | Likhu | 7
15222 | Ramechhap | Tilpung | 5 | HELVETAS | SBPK | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-01-27 | 2017-04-24 |  | Likhu | 7
15223 | Ramechhap | Tilpung | 7 | HELVETAS | SBPK | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-01-27 | 2017-04-24 |  | Likhu | 7
15224 | Ramechhap | Tilpung | 8 | HELVETAS | SBPK | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-01-27 | 2017-04-24 |  | Likhu | 7
15225 | Ramechhap | Tilpung | 9 | HELVETAS | SBPK | SDC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-01-27 | 2017-04-24 |  | Likhu | 7
15226 | Ramechhap | Tilpung | 1 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2017-01-27 | 2017-04-13 |  | Likhu | 7
15227 | Ramechhap | Tilpung | 1 | HELVETAS | SBPK | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-27 | 2017-04-13 |  | Likhu | 7
15228 | Ramechhap | Tilpung | 4 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-01-27 | 2017-04-13 |  | Likhu | 7
15229 | Ramechhap | Tilpung | 4 | HELVETAS | SBPK | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-27 | 2017-04-13 |  | Likhu | 7
15230 | Ramechhap | Tilpung | 5 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-01-27 | 2017-04-13 |  | Likhu | 7
15231 | Ramechhap | Tilpung | 5 | HELVETAS | SBPK | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-01-27 | 2017-04-13 |  | Likhu | 7
15232 | Ramechhap | Tilpung | 7 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-01-27 | 2017-04-13 |  | Likhu | 7
15233 | Ramechhap | Tilpung | 7 | HELVETAS | SBPK | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-27 | 2017-04-13 |  | Likhu | 7
15234 | Ramechhap | Tilpung | 8 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2017-01-27 | 2017-04-13 |  | Likhu | 7
15235 | Ramechhap | Tilpung | 8 | HELVETAS | SBPK | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 11 | 11 | 2017-01-27 | 2017-04-13 |  | Likhu | 7
15236 | Ramechhap | Tilpung | 9 | HELVETAS | SBPK | SDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2017-01-27 | 2017-04-13 |  | Likhu | 7
15237 | Ramechhap | Tilpung | 9 | HELVETAS | SBPK | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-27 | 2017-04-13 |  | Likhu | 7
15238 | Ramechhap | Tokarpur | 3 | HELVETAS | SODEC-N | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-21 |  | Doramba | 3
15239 | Ramechhap | Tokarpur | 6 | HELVETAS | SODEC-N | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-21 |  | Doramba | 3
15240 | Ramechhap | Tokarpur | 7 | HELVETAS | SODEC-N | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-08-21 |  | Doramba | 3
15241 | Ramechhap | Tokarpur | 8 | HELVETAS | SODEC-N | SDC | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-08-21 |  | Doramba | 5
15242 | Ramechhap | Tokarpur | 3 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-22 | 2016-08-21 |  | Doramba | 3
15243 | Ramechhap | Tokarpur | 4 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-22 | 2016-08-21 |  | Doramba | 3
15244 | Ramechhap | Tokarpur | 5 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-08-21 |  | Doramba | 3
15245 | Ramechhap | Tokarpur | 6 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-08-21 |  | Doramba | 3
15246 | Ramechhap | Tokarpur | 7 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-06-22 | 2016-08-21 |  | Doramba | 3
15247 | Ramechhap | Tokarpur | 8 | HELVETAS | SODEC-N | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-06-22 | 2016-08-21 |  | Doramba | 5
15248 | Ramechhap | Dimipokhari | 5 | HELVETAS | F-SKILL | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-28 | 2016-08-23 |  | Sunapati | 2
15249 | Ramechhap | Dimipokhari | 6 | HELVETAS | F-SKILL | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-28 | 2016-08-23 |  | Sunapati | 2
15250 | Ramechhap | Dimipokhari | 7 | HELVETAS | F-SKILL | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-28 | 2016-08-23 |  | Sunapati | 2
15251 | Ramechhap | Dimipokhari | 8 | HELVETAS | F-SKILL | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-28 | 2016-08-23 |  | Sunapati | 2
15252 | Ramechhap | Manthali N.P. | 13 | HELVETAS | F-SKILL | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2016-06-26 | 2016-08-20 |  | Manthali | 7
15253 | Ramechhap | Manthali N.P. | 14 | HELVETAS | F-SKILL | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-06-25 | 2016-08-19 |  | Manthali | 7
15254 | Ramechhap | Dimipokhari | 2 | HELVETAS | TRACE | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-09-20 | 2016-12-20 |  | Sunapati | 2
15255 | Ramechhap | Dimipokhari | 3 | HELVETAS | TRACE | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-09-20 | 2016-12-20 |  | Sunapati | 2
15256 | Ramechhap | Dimipokhari | 4 | HELVETAS | TRACE | SDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-09-20 | 2016-12-20 |  | Sunapati | 2
15257 | Ramechhap | Manthali N.P. | 3 | HI | UNHCR | UNHCR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 3 | 3 | 2015-08-15 | 2016-01-30 | Safer construction techniques training was condicted for beneficiaries | Manthali | 2
15258 | Ramechhap | Manthali N.P. | 5 | HI | UNHCR | UNHCR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 14 | 14 | 2015-08-15 | 2016-01-30 | Safer construction techniques training was condicted for beneficiaries | Manthali | 3
15259 | Ramechhap | Manthali N.P. | 6 | HI | UNHCR | UNHCR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 2 | 2 | 2015-08-15 | 2016-01-30 | Safer construction techniques training was condicted for beneficiaries | Manthali | 3
15260 | Ramechhap | Manthali N.P. | 7 | HI | UNHCR | UNHCR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 30 | 30 | 2015-08-15 | 2016-01-30 | Safer construction techniques training was condicted for beneficiaries | Manthali | 4
15261 | Ramechhap | Manthali N.P. | 8 | HI | UNHCR | UNHCR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 16 | 16 | 2015-08-15 | 2016-01-30 | Safer construction techniques training was condicted for beneficiaries | Manthali | 4
15262 | Ramechhap | Namadi | 1 | HI | UNHCR | UNHCR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 101 | 101 | 2015-08-15 | 2016-01-30 | Safer construction techniques training was condicted for beneficiaries | Gokulganga | 5
15263 | Ramechhap | Namadi | 2 | HI | CESVI | UNHCR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 56 | 56 | 2015-08-15 | 2016-01-30 | Safer construction techniques training was condicted for beneficiaries | Gokulganga | 5
15264 | Ramechhap | Namadi | 4 | HI | UNHCR | UNHCR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 127 | 127 | 2015-08-15 | 2016-01-30 | Safer construction techniques training was condicted for beneficiaries | Gokulganga | 5
15265 | Ramechhap | Namadi | 7 | HI | UNHCR | UNHCR | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 1 | 1 | 2015-08-15 | 2016-01-30 | Safer construction techniques training was condicted for beneficiaries | Gokulganga | 5
15266 | Ramechhap | Manthali N.P. | 1 | IOM | IOM | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 97 | 97 | 2016-03-07 | 2016-03-22 | distribution conduceted in beneificiaries Village | Manthali | 1
15267 | Ramechhap | Manthali N.P. | 2 | IOM | IOM | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 82 | 82 | 2016-03-07 | 2016-03-22 | distribution conduceted in beneificiaries Village | Manthali | 1
15268 | Ramechhap | Manthali N.P. | 3 | IOM | IOM | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 54 | 54 | 2016-03-07 | 2016-03-22 | distribution conduceted in beneificiaries Village | Manthali | 2
15269 | Ramechhap | Manthali N.P. | 4 | IOM | IOM | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 26 | 26 | 2016-03-07 | 2016-03-22 | distribution conduceted in beneificiaries Village | Manthali | 2
15270 | Ramechhap | Manthali N.P. | 6 | IOM | IOM | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 73 | 73 | 2016-03-07 | 2016-03-22 | distribution conduceted in beneificiaries Village | Manthali | 3
15271 | Ramechhap | Manthali N.P. | 7 | IOM | IOM | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 65 | 65 | 2016-03-07 | 2016-03-22 | distribution conduceted in beneificiaries Village | Manthali | 4
15272 | Ramechhap | Puranagau | 1 | IOM | IOM | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 138 | 138 | 2016-03-17 | 2016-03-22 |  | Manthali | 9
15273 | Ramechhap | Puranagau | 9 | IOM | IOM | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 122 | 122 | 2016-03-17 | 2016-03-22 | distribution conduceted in beneificiaries Village | Manthali | 9
15274 | Ramechhap | Duragau | 7 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Saipu VDC | # of trainees | Yes | Completed | 1 | 1 | 2016-11-08 | 2016-12-28 |  | Likhu | 1
15275 | Ramechhap | Gothgau | 4 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Saipu VDC | # of trainees | Yes | Completed | 1 | 1 | 2016-11-08 | 2016-12-28 |  | Ramechhap | 1
15276 | Ramechhap | Saipu | 2 | KFS | CMES | KFS | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2016-11-08 | 2017-01-15 |  | Likhu | 2
15277 | Ramechhap | Saipu | 4 | KFS | CMES | KFS | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-11-08 | 2017-01-15 |  | Likhu | 2
15278 | Ramechhap | Saipu | 6 | KFS | CMES | KFS | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 3 | 3 | 2016-03-15 | 2016-06-15 |  | Likhu | 2
15279 | Ramechhap | Saipu | 7 | KFS | CMES | KFS | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-06-15 |  | Likhu | 2
15280 | Ramechhap | Saipu | 8 | KFS | CMES | KFS | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 1 | 1 | 2016-11-08 | 2017-01-15 |  | Likhu | 2
15281 | Ramechhap | Saipu | 9 | KFS | CMES | KFS | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | Yes | Completed | 2 | 2 | 2016-11-08 | 2017-01-15 |  | Likhu | 2
15282 | Ramechhap | Saipu | 1 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-27 | 2016-05-18 |  | Likhu | 2
15283 | Ramechhap | Saipu | 1 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-11-08 | 2016-12-28 |  | Likhu | 2
15284 | Ramechhap | Saipu | 1 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-27 | 2016-05-18 |  | Likhu | 2
15285 | Ramechhap | Saipu | 2 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-11-08 | 2016-12-28 |  | Likhu | 2
15286 | Ramechhap | Saipu | 2 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-27 | 2016-05-18 |  | Likhu | 2
15287 | Ramechhap | Saipu | 2 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-11-08 | 2016-12-28 |  | Likhu | 2
15288 | Ramechhap | Saipu | 2 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-03-27 | 2016-05-18 |  | Likhu | 2
15289 | Ramechhap | Saipu | 3 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-11-08 | 2016-12-28 |  | Likhu | 2
15290 | Ramechhap | Saipu | 3 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-27 | 2016-05-18 |  | Likhu | 2
15291 | Ramechhap | Saipu | 3 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-11-08 | 2016-12-28 |  | Likhu | 2
15292 | Ramechhap | Saipu | 3 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-27 | 2016-05-18 |  | Likhu | 2
15293 | Ramechhap | Saipu | 4 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-27 | 2016-05-18 |  | Likhu | 2
15294 | Ramechhap | Saipu | 4 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-11-08 | 2016-12-28 |  | Likhu | 2
15295 | Ramechhap | Saipu | 5 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-27 | 2016-05-18 |  | Likhu | 2
15296 | Ramechhap | Saipu | 5 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-27 | 2016-05-18 |  | Likhu | 2
15297 | Ramechhap | Saipu | 6 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-11-08 | 2016-12-28 |  | Likhu | 2
15298 | Ramechhap | Saipu | 6 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-27 | 2016-05-18 |  | Likhu | 2
15299 | Ramechhap | Saipu | 6 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-11-08 | 2016-12-28 |  | Likhu | 2
15300 | Ramechhap | Saipu | 6 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-27 | 2016-05-18 |  | Likhu | 2
15301 | Ramechhap | Saipu | 7 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-11-08 | 2016-12-28 |  | Likhu | 2
15302 | Ramechhap | Saipu | 7 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-11-08 | 2016-12-28 |  | Likhu | 2
15303 | Ramechhap | Saipu | 7 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-27 | 2016-05-18 |  | Likhu | 2
15304 | Ramechhap | Saipu | 8 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-27 | 2016-05-18 |  | Likhu | 2
15305 | Ramechhap | Saipu | 8 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 12 | 12 | 2016-11-08 | 2016-12-28 |  | Likhu | 2
15306 | Ramechhap | Saipu | 8 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-27 | 2016-05-18 |  | Likhu | 2
15307 | Ramechhap | Saipu | 9 | KFS | CMES | KFS | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-27 | 2016-05-18 |  | Likhu | 2
15308 | Ramechhap | Saipu | 9 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-11-08 | 2016-12-28 |  | Likhu | 2
15309 | Ramechhap | Saipu | 9 | KFS | CMES | KFS | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-03-27 | 2016-05-18 |  | Likhu | 2
15310 | Ramechhap | Saipu | 6 | KFS | KFS | KFS | Training | Short training | Carpenter | Bamboo Carpentry (10 days basic bomboo carpentry, joinery & awareness training) | # of trainees | Yes | Completed | 10 | 10 | 2016-11-12 | 2016-11-21 |  | Likhu | 2
15311 | Ramechhap | Saipu | 1 | KFS | KFS | KFS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 25 | 16 | 2018-01-01 | 2018-12-31 |  | Likhu | 2
15312 | Ramechhap | Saipu | 2 | KFS | KFS | KFS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 25 | 13 | 2018-01-01 | 2018-12-31 |  | Likhu | 2
15313 | Ramechhap | Saipu | 3 | KFS | KFS | KFS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 25 | 2018-01-01 | 2018-12-31 |  | Likhu | 2
15314 | Ramechhap | Saipu | 4 | KFS | KFS | KFS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 30 | 37 | 2018-01-01 | 2018-12-31 |  | Likhu | 2
15315 | Ramechhap | Saipu | 5 | KFS | KFS | KFS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 9 | 2018-01-01 | 2018-12-31 |  | Likhu | 2
15316 | Ramechhap | Saipu | 6 | KFS | KFS | KFS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 21 | 2018-01-01 | 2018-12-31 |  | Likhu | 2
15317 | Ramechhap | Saipu | 7 | KFS | KFS | KFS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 18 | 2018-01-01 | 2018-12-31 |  | Likhu | 2
15318 | Ramechhap | Saipu | 8 | KFS | KFS | KFS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 15 | 2018-01-01 | 2018-12-31 |  | Likhu | 2
15319 | Ramechhap | Saipu | 9 | KFS | KFS | KFS | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 20 | 18 | 2018-01-01 | 2018-12-31 |  | Likhu | 2
15320 | Ramechhap | Bijulikot | 3 | MEDAIR | CDS | MEDAIR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR 50,000 | # of households | Yes | Ongoing | 153 | 152 | 2016-09-19 |  |  | Likhu | 3
15321 | Ramechhap | Bijulikot | 3 | MEDAIR | CDS | MEDAIR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | NPR 150,000 | # of households | Yes | Ongoing | 153 | 146 | 2016-11-20 |  |  | Likhu | 3
15322 | Ramechhap | Bijulikot | 3 | MEDAIR | CDS | MEDAIR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | NPR 75,000 | # of households | Yes | Ongoing | 153 | 138 | 2017-01-02 |  |  | Likhu | 3
15323 | Ramechhap | Bijulikot | 6 | MEDAIR | CDS | MEDAIR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I | NPR 50,000 | # of households | Yes | Ongoing | 157 | 157 | 2016-09-19 |  |  | Likhu | 4
15324 | Ramechhap | Bijulikot | 6 | MEDAIR | CDS | MEDAIR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II | NPR 150,000 | # of households | Yes | Ongoing | 157 | 156 | 2016-11-20 |  |  | Likhu | 4
15325 | Ramechhap | Bijulikot | 6 | MEDAIR | CDS | MEDAIR | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III | NPR 75,000 | # of households | Yes | Ongoing | 157 | 153 | 2017-01-02 |  |  | Likhu | 4
15326 | Ramechhap | Bijulikot | 1 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 6 | 6 | 2015-01-27 | 2016-02-02 |  | Likhu | 3
15327 | Ramechhap | Bijulikot | 2 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 4 | 4 | 2015-01-27 | 2016-02-02 |  | Likhu | 3
15328 | Ramechhap | Bijulikot | 2 | MEDAIR | CDS | MEDAIR | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-05-07 | 2016-05-28 |  | Likhu | 3
15329 | Ramechhap | Bijulikot | 3 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 6 | 6 | 2015-01-27 | 2016-02-02 |  | Likhu | 3
15330 | Ramechhap | Bijulikot | 3 | MEDAIR | CDS | MEDAIR | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 153 | 147 | 2016-10-15 |  |  | Likhu | 3
15331 | Ramechhap | Bijulikot | 4 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 4 | 4 | 2015-01-27 | 2016-02-02 |  | Likhu | 3
15332 | Ramechhap | Bijulikot | 5 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 4 | 4 | 2015-01-27 | 2016-02-02 |  | Likhu | 4
15333 | Ramechhap | Bijulikot | 6 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 4 | 4 | 2015-01-27 | 2016-02-02 |  | Likhu | 4
15334 | Ramechhap | Bijulikot | 6 | MEDAIR | CDS | MEDAIR | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 157 | 156 | 2016-10-15 |  |  | Likhu | 4
15335 | Ramechhap | Bijulikot | 7 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 4 | 4 | 2015-01-27 | 2016-02-02 |  | Likhu | 4
15336 | Ramechhap | Bijulikot | 7 | MEDAIR | CDS | MEDAIR | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-05-07 | 2016-05-28 |  | Likhu | 4
15337 | Ramechhap | Bijulikot | 8 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 4 | 4 | 2015-01-27 | 2016-02-02 |  | Likhu | 4
15338 | Ramechhap | Bijulikot | 9 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 8 | 8 | 2015-01-27 | 2016-02-02 |  | Likhu | 4
15339 | Ramechhap | Bijulikot | 1 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-09 | 2016-02-13 |  | Likhu | 3
15340 | Ramechhap | Bijulikot | 2 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-08-25 | 2016-08-31 |  | Likhu | 3
15341 | Ramechhap | Bijulikot | 2 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-09 | 2016-02-13 |  | Likhu | 3
15342 | Ramechhap | Bijulikot | 3 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 14 | 14 | 2016-08-25 | 2016-08-31 |  | Likhu | 3
15343 | Ramechhap | Bijulikot | 3 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-02-09 | 2016-02-13 |  | Likhu | 3
15344 | Ramechhap | Bijulikot | 3 | MEDAIR | CDS | MEDAIR | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 88 | 93 | 2017-02-10 | 2018-04-01 |  | Likhu | 3
15345 | Ramechhap | Bijulikot | 4 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-09 | 2016-02-13 |  | Likhu | 3
15346 | Ramechhap | Bijulikot | 5 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-09 | 2016-02-13 |  | Likhu | 4
15347 | Ramechhap | Bijulikot | 6 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2016-08-25 | 2016-08-31 |  | Likhu | 4
15348 | Ramechhap | Bijulikot | 6 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-09 | 2016-02-13 |  | Likhu | 4
15349 | Ramechhap | Bijulikot | 6 | MEDAIR | CDS | MEDAIR | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 87 | 82 | 2017-02-10 | 2018-04-01 |  | Likhu | 4
15350 | Ramechhap | Bijulikot | 7 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-09 | 2016-02-13 |  | Likhu | 4
15351 | Ramechhap | Bijulikot | 8 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-09 | 2016-02-13 |  | Likhu | 4
15352 | Ramechhap | Bijulikot | 9 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-02-09 | 2016-02-13 |  | Likhu | 4
15353 | Ramechhap | Himganga | 1 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-02-22 |  | Ramechhap | 4
15354 | Ramechhap | Himganga | 2 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-02-22 |  | Ramechhap | 4
15355 | Ramechhap | Himganga | 3 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-02-22 |  | Ramechhap | 4
15356 | Ramechhap | Himganga | 4 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2016-02-11 | 2016-02-22 |  | Ramechhap | 4
15357 | Ramechhap | Himganga | 5 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-02-22 |  | Ramechhap | 4
15358 | Ramechhap | Himganga | 6 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-02-22 |  | Ramechhap | 4
15359 | Ramechhap | Himganga | 7 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2016-02-11 | 2016-02-22 |  | Ramechhap | 4
15360 | Ramechhap | Himganga | 8 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 7 | 7 | 2016-02-11 | 2016-02-22 |  | Ramechhap | 4
15361 | Ramechhap | Himganga | 9 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 6 | 6 | 2016-02-11 | 2016-02-22 |  | Ramechhap | 4
15362 | Ramechhap | Himganga | 1 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-17 | 2016-02-21 |  | Ramechhap | 4
15363 | Ramechhap | Himganga | 2 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-17 | 2016-02-21 |  | Ramechhap | 4
15364 | Ramechhap | Himganga | 3 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-02-17 | 2016-02-21 |  | Ramechhap | 4
15365 | Ramechhap | Himganga | 4 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-17 | 2016-02-21 |  | Ramechhap | 4
15366 | Ramechhap | Himganga | 5 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-17 | 2016-02-21 |  | Ramechhap | 4
15367 | Ramechhap | Himganga | 6 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-17 | 2016-02-21 |  | Ramechhap | 4
15368 | Ramechhap | Himganga | 7 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-02-17 | 2016-02-21 |  | Ramechhap | 4
15369 | Ramechhap | Himganga | 8 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-17 | 2016-02-21 |  | Ramechhap | 4
15370 | Ramechhap | Himganga | 9 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-02-17 | 2016-02-21 |  | Ramechhap | 4
15371 | Ramechhap | Sanghutar | 1 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 6 | 6 | 2016-02-22 | 2016-02-29 |  | Ramechhap | 3
15372 | Ramechhap | Sanghutar | 2 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 6 | 6 | 2016-02-22 | 2016-02-29 |  | Ramechhap | 3
15373 | Ramechhap | Sanghutar | 3 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 6 | 6 | 2016-02-22 | 2016-02-29 |  | Ramechhap | 3
15374 | Ramechhap | Sanghutar | 4 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2016-02-22 | 2016-02-29 |  | Ramechhap | 3
15375 | Ramechhap | Sanghutar | 5 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2016-02-22 | 2016-02-29 |  | Ramechhap | 3
15376 | Ramechhap | Sanghutar | 6 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2016-02-22 | 2016-02-29 |  | Ramechhap | 3
15377 | Ramechhap | Sanghutar | 7 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2016-02-22 | 2016-02-29 |  | Ramechhap | 3
15378 | Ramechhap | Sanghutar | 8 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 6 | 6 | 2016-02-22 | 2016-02-29 |  | Ramechhap | 3
15379 | Ramechhap | Sanghutar | 9 | MEDAIR | CDS | MEDAIR | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2016-02-22 | 2016-02-29 |  | Ramechhap | 3
15380 | Ramechhap | Sanghutar | 1 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-01 | 2016-03-06 |  | Ramechhap | 3
15381 | Ramechhap | Sanghutar | 2 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-03-06 |  | Ramechhap | 3
15382 | Ramechhap | Sanghutar | 3 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-03-06 |  | Ramechhap | 3
15383 | Ramechhap | Sanghutar | 4 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-01 | 2016-03-06 |  | Ramechhap | 3
15384 | Ramechhap | Sanghutar | 5 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-03-06 |  | Ramechhap | 3
15385 | Ramechhap | Sanghutar | 6 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-03-06 |  | Ramechhap | 3
15386 | Ramechhap | Sanghutar | 7 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-01 | 2016-03-06 |  | Ramechhap | 3
15387 | Ramechhap | Sanghutar | 8 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-01 | 2016-03-06 |  | Ramechhap | 3
15388 | Ramechhap | Sanghutar | 9 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-03-01 | 2016-03-06 |  | Ramechhap | 3
15389 | Ramechhap | Bijulikot | 1 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 12 | 10 | 2017-08-15 |  |  | Likhu | 3
15390 | Ramechhap | Bijulikot | 2 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 12 | 6 | 2017-08-15 |  |  | Likhu | 3
15391 | Ramechhap | Bijulikot | 3 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 10 | 8 | 2017-08-15 |  |  | Likhu | 3
15392 | Ramechhap | Bijulikot | 4 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 12 | 12 | 2017-08-15 |  |  | Likhu | 3
15393 | Ramechhap | Bijulikot | 5 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 12 | 12 | 2017-08-15 |  |  | Likhu | 4
15394 | Ramechhap | Bijulikot | 6 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 11 | 5 | 2017-08-15 |  |  | Likhu | 4
15395 | Ramechhap | Bijulikot | 7 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 12 | 14 | 2017-08-15 |  |  | Likhu | 4
15396 | Ramechhap | Bijulikot | 8 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 12 | 12 | 2017-08-15 |  |  | Likhu | 4
15397 | Ramechhap | Bijulikot | 9 | MEDAIR | CDS | MEDAIR | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Ongoing | 12 | 14 | 2017-08-15 |  |  | Likhu | 4
15398 | Ramechhap | Bijulikot | 1 | MEDAIR | CDS | MEDAIR | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Planned | 41 | 0 | 2017-09-01 |  |  | Likhu | 3
15399 | Ramechhap | Bijulikot | 2 | MEDAIR | CDS | MEDAIR | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Planned | 41 | 0 | 2017-09-01 |  |  | Likhu | 3
15400 | Ramechhap | Bijulikot | 4 | MEDAIR | CDS | MEDAIR | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Planned | 41 | 0 | 2017-09-01 |  |  | Likhu | 3
15401 | Ramechhap | Bijulikot | 5 | MEDAIR | CDS | MEDAIR | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Planned | 41 | 0 | 2017-09-01 |  |  | Likhu | 4
15402 | Ramechhap | Bijulikot | 7 | MEDAIR | CDS | MEDAIR | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Planned | 41 | 0 | 2017-09-01 |  |  | Likhu | 4
15403 | Ramechhap | Bijulikot | 8 | MEDAIR | CDS | MEDAIR | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Planned | 40 | 0 | 2017-09-01 |  |  | Likhu | 4
15404 | Ramechhap | Bijulikot | 9 | MEDAIR | CDS | MEDAIR | Training | Vocational training | New masons (other curriculums, specify in Activity Detail) |  | # of trainees | Yes | Planned | 40 | 0 | 2017-09-01 |  |  | Likhu | 4
15405 | Ramechhap | Bijulikot | 1 | MEDAIR | CDS | MEDAIR | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 107 | 87 | 2017-08-01 |  |  | Likhu | 3
15406 | Ramechhap | Bijulikot | 2 | MEDAIR | CDS | MEDAIR | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 170 | 149 | 2017-08-01 |  |  | Likhu | 3
15407 | Ramechhap | Bijulikot | 3 | MEDAIR | CDS | MEDAIR | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 4 | 2 | 2017-08-01 |  |  | Likhu | 3
15408 | Ramechhap | Bijulikot | 4 | MEDAIR | CDS | MEDAIR | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 140 | 139 | 2017-08-01 |  |  | Likhu | 3
15409 | Ramechhap | Bijulikot | 5 | MEDAIR | CDS | MEDAIR | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 95 | 86 | 2017-08-01 |  |  | Likhu | 4
15410 | Ramechhap | Bijulikot | 6 | MEDAIR | Door-to-door technical assistance | Continuous | Ongoing | Door-to-door technical assistance | Continuous | Ongoing |  |  | Ongoing | 6 | 6 | 2017-08-01 |  |  | Likhu | 4
15411 | Ramechhap | Bijulikot | 7 | MEDAIR | CDS | MEDAIR | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 186 | 176 | 2017-08-01 |  |  | Likhu | 4
15412 | Ramechhap | Bijulikot | 8 | MEDAIR | CDS | MEDAIR | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 115 | 111 | 2017-08-01 |  |  | Likhu | 4
15413 | Ramechhap | Bijulikot | 9 | MEDAIR | CDS | MEDAIR | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 158 | 152 | 2017-08-01 |  |  | Likhu | 4
15414 | Ramechhap | Bijulikot | 1 | MEDAIR | CDS | MEDAIR | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center |  | # of households supported | Yes | Planned | 1 | 0 | 2017-08-01 |  |  | Likhu | 3
15415 | Ramechhap | Bijulikot | 1 | MEDAIR | CDS | MEDAIR | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Completed | 1 | 1 | 2016-11-01 | 2016-11-30 |  | Likhu | 3
15416 | Ramechhap | Bijulikot | 1 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 10 | 10 | 2017-08-01 | 2017-09-30 |  | Likhu | 3
15417 | Ramechhap | Bijulikot | 2 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 15 | 15 | 2017-06-01 | 2017-07-30 |  | Likhu | 3
15418 | Ramechhap | Bijulikot | 4 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 15 | 15 | 2017-06-01 | 2017-07-30 |  | Likhu | 3
15419 | Ramechhap | Bijulikot | 5 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 8 | 8 | 2017-06-01 | 2017-07-30 |  | Likhu | 4
15420 | Ramechhap | Bijulikot | 7 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 16 | 16 | 2017-06-01 | 2017-07-30 |  | Likhu | 4
15421 | Ramechhap | Bijulikot | 8 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 12 | 12 | 2017-06-01 | 2017-08-30 |  | Likhu | 4
15422 | Ramechhap | Bijulikot | 9 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household reconstruction orientation | 4-5 sessions |  | # of households | Yes | Completed | 14 | 14 | 2017-06-01 | 2017-08-30 |  | Likhu | 4
15423 | Ramechhap | Bijulikot | 1 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Ongoing | 107 | 87 | 2017-08-01 |  |  | Likhu | 3
15424 | Ramechhap | Bijulikot | 2 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Ongoing | 170 | 149 | 2017-08-01 |  |  | Likhu | 3
15425 | Ramechhap | Bijulikot | 3 | MEDAIR |  |  |  | Household reconstruction orientation | 1 session | Ongoing |  |  | Ongoing | 4 | 2 | 2017-08-01 |  |  | Likhu | 3
15426 | Ramechhap | Bijulikot | 4 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Ongoing | 140 | 139 | 2017-08-01 |  |  | Likhu | 3
15427 | Ramechhap | Bijulikot | 5 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Ongoing | 95 | 86 | 2017-08-01 |  |  | Likhu | 4
15428 | Ramechhap | Bijulikot | 6 | MEDAIR |  |  |  | Household reconstruction orientation | 1 session |  |  |  | Ongoing | 6 | 6 | 2017-08-01 |  |  | Likhu | 4
15429 | Ramechhap | Bijulikot | 7 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Ongoing | 186 | 176 | 2017-08-01 |  |  | Likhu | 4
15430 | Ramechhap | Bijulikot | 8 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Ongoing | 115 | 111 | 2017-08-01 |  |  | Likhu | 4
15431 | Ramechhap | Bijulikot | 9 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household reconstruction orientation | 1 session |  | # of households | Yes | Ongoing | 158 | 152 | 2017-08-01 |  |  | Likhu | 4
15432 | Ramechhap | Bijulikot | 3 | MEDAIR | CDS | MEDAIR | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction |  | # of households | Yes | Ongoing | 153 | 150 | 2016-07-01 |  |  | Likhu | 3
15433 | Ramechhap | Bijulikot | 6 | MEDAIR | CDS | MEDAIR | Financial/Material/Labour Assistance | Financial support on household WASH | HH toilet construction |  | # of households | Yes | Ongoing | 157 | 156 | 2016-07-01 |  |  | Likhu | 4
15434 | Ramechhap | Bijulikot | 1 | MEDAIR | CDS | MEDAIR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Completed | 8 | 9 | 2017-07-01 | 2017-09-30 |  | Likhu | 3
15435 | Ramechhap | Bijulikot | 2 | MEDAIR | CDS | MEDAIR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Completed | 8 | 8 | 2017-07-01 | 2017-09-30 |  | Likhu | 3
15436 | Ramechhap | Bijulikot | 3 | MEDAIR | CDS | MEDAIR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Completed | 8 | 9 | 2017-07-01 | 2017-09-30 |  | Likhu | 3
15437 | Ramechhap | Bijulikot | 4 | MEDAIR | CDS | MEDAIR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Completed | 8 | 8 | 2017-07-01 | 2017-09-30 |  | Likhu | 3
15438 | Ramechhap | Bijulikot | 5 | MEDAIR | CDS | MEDAIR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Completed | 8 | 8 | 2017-07-01 | 2017-09-30 |  | Likhu | 4
15439 | Ramechhap | Bijulikot | 6 | MEDAIR | CDS | MEDAIR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Completed | 8 | 9 | 2017-07-01 | 2017-09-30 |  | Likhu | 4
15440 | Ramechhap | Bijulikot | 7 | MEDAIR | CDS | MEDAIR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Completed | 8 | 9 | 2017-07-01 | 2017-09-30 |  | Likhu | 4
15441 | Ramechhap | Bijulikot | 8 | MEDAIR | CDS | MEDAIR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Completed | 8 | 9 | 2017-07-01 | 2017-09-30 |  | Likhu | 4
15442 | Ramechhap | Bijulikot | 9 | MEDAIR | CDS | MEDAIR | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion |  | # of households | Yes | Completed | 8 | 8 | 2017-07-01 | 2017-09-30 |  | Likhu | 4
15443 | Ramechhap | Bijulikot | 1 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household orientation on toilet construction | 4-5 sessions |  | # of households | Yes | Planned | 107 | 0 | 2017-07-01 |  |  | Likhu | 3
15444 | Ramechhap | Bijulikot | 2 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household orientation on toilet construction | 4-5 sessions |  | # of households | Yes | Planned | 169 | 0 | 2017-07-01 |  |  | Likhu | 3
15445 | Ramechhap | Bijulikot | 3 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household orientation on toilet construction | 4-5 sessions |  | # of households | Yes | Planned | 153 | 0 | 2017-07-01 |  |  | Likhu | 3
15446 | Ramechhap | Bijulikot | 4 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household orientation on toilet construction | 4-5 sessions |  | # of households | Yes | Planned | 138 | 0 | 2017-07-01 |  |  | Likhu | 3
15447 | Ramechhap | Bijulikot | 5 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household orientation on toilet construction | 4-5 sessions |  | # of households | Yes | Planned | 95 | 0 | 2017-07-01 |  |  | Likhu | 4
15448 | Ramechhap | Bijulikot | 6 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household orientation on toilet construction | 4-5 sessions |  | # of households | Yes | Planned | 157 | 0 | 2017-07-01 |  |  | Likhu | 4
15449 | Ramechhap | Bijulikot | 7 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household orientation on toilet construction | 4-5 sessions |  | # of households | Yes | Planned | 178 | 0 | 2017-07-01 |  |  | Likhu | 4
15450 | Ramechhap | Bijulikot | 8 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household orientation on toilet construction | 4-5 sessions |  | # of households | Yes | Planned | 114 | 0 | 2017-07-01 |  |  | Likhu | 4
15451 | Ramechhap | Bijulikot | 9 | MEDAIR | CDS | MEDAIR | Technical Assistance | Household orientation on toilet construction | 4-5 sessions |  | # of households | Yes | Planned | 152 | 0 | 2017-07-01 |  |  | Likhu | 4
15452 | Ramechhap | Bijulikot | 2 | MEDAIR | CDS | MEDAIR | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Completed | 1 | 1 | 2016-11-01 | 2016-11-30 |  | Likhu | 3
15453 | Ramechhap | Bijulikot | 3 | MEDAIR | CDS | MEDAIR | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Completed | 1 | 1 | 2016-11-01 | 2016-11-30 |  | Likhu | 3
15454 | Ramechhap | Bijulikot | 4 | MEDAIR | CDS | MEDAIR | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Completed | 1 | 1 | 2016-11-01 | 2016-11-30 |  | Likhu | 3
15455 | Ramechhap | Bijulikot | 5 | MEDAIR | CDS | MEDAIR | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Completed | 1 | 1 | 2016-11-01 | 2016-11-30 |  | Likhu | 4
15456 | Ramechhap | Bijulikot | 6 | MEDAIR | CDS | MEDAIR | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Completed | 1 | 1 | 2016-11-01 | 2016-11-30 |  | Likhu | 4
15457 | Ramechhap | Bijulikot | 7 | MEDAIR | CDS | MEDAIR | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Completed | 1 | 1 | 2016-11-01 | 2016-11-30 |  | Likhu | 4
15458 | Ramechhap | Bijulikot | 8 | MEDAIR | CDS | MEDAIR | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Completed | 1 | 1 | 2016-11-01 | 2016-11-30 |  | Likhu | 4
15459 | Ramechhap | Bijulikot | 9 | MEDAIR | CDS | MEDAIR | Technical Assistance | Communication and Outreach | Production of IEC materials/manual |  | # of copies | Yes | Completed | 1 | 1 | 2016-11-01 | 2016-11-30 |  | Likhu | 4
15460 | Ramechhap | Dadhuwa | 1 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20 |  | Doramba | 1
15461 | Ramechhap | Dadhuwa | 2 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20 |  | Doramba | 1
15462 | Ramechhap | Dadhuwa | 2 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-06 | 2016-02-20 |  | Doramba | 1
15463 | Ramechhap | Dadhuwa | 3 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20 |  | Doramba | 1
15464 | Ramechhap | Dadhuwa | 3 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20 |  | Doramba | 1
15465 | Ramechhap | Dadhuwa | 4 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20 |  | Doramba | 1
15466 | Ramechhap | Dadhuwa | 4 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-06 | 2016-02-20 |  | Doramba | 1
15467 | Ramechhap | Dadhuwa | 5 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20 |  | Doramba | 1
15468 | Ramechhap | Dadhuwa | 5 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-06 | 2016-02-20 |  | Doramba | 1
15469 | Ramechhap | Dadhuwa | 6 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-06 | 2016-02-20 |  | Doramba | 1
15470 | Ramechhap | Dadhuwa | 8 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-06 | 2016-02-20 |  | Doramba | 1
15471 | Ramechhap | Dadhuwa | 8 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20 |  | Doramba | 1
15472 | Ramechhap | Gelu | 1 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training | Manthali | 12
15473 | Ramechhap | Gelu | 2 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 15 | 15 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training | Manthali | 12
15474 | Ramechhap | Gelu | 3 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 12 | 12 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training | Manthali | 12
15475 | Ramechhap | Gelu | 4 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training | Manthali | 12
15476 | Ramechhap | Gelu | 5 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 9 | 9 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training | Manthali | 11
15477 | Ramechhap | Gelu | 6 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 11 | 11 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training | Manthali | 11
15478 | Ramechhap | Gelu | 7 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 19 | 19 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training | Manthali | 11
15479 | Ramechhap | Gelu | 8 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 5 | 5 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training | Manthali | 11
15480 | Ramechhap | Gelu | 9 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 3 | 3 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training | Manthali | 11
15481 | Ramechhap | Gelu | 1 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 2 | 2 | 2016-03-02 | 2016-03-08 |  | Manthali | 12
15482 | Ramechhap | Gelu | 2 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 6 | 6 | 2016-03-02 | 2016-03-08 |  | Manthali | 12
15483 | Ramechhap | Gelu | 3 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 2 | 2 | 2016-03-02 | 2016-03-08 |  | Manthali | 12
15484 | Ramechhap | Gelu | 4 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 2 | 2 | 2016-03-02 | 2016-03-08 |  | Manthali | 12
15485 | Ramechhap | Gelu | 5 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 2 | 2 | 2016-03-02 | 2016-03-08 |  | Manthali | 11
15486 | Ramechhap | Gelu | 6 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 2 | 2 | 2016-03-02 | 2016-03-08 |  | Manthali | 11
15487 | Ramechhap | Gelu | 8 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 2 | 2 | 2016-03-02 | 2016-03-08 |  | Manthali | 11
15488 | Ramechhap | Gelu | 9 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 2 | 2 | 2016-03-02 | 2016-03-08 |  | Manthali | 11
15489 | Ramechhap | Manthali N.P. | 15 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 37 | 37 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training | Manthali | 8
15490 | Ramechhap | Manthali N.P. | 16 | RRN | RRN | AJJDC | Technical Assistance | Community reconstruction orientation | 2-3 sessions |  | # of participants | Yes | Completed | 26 | 26 | 2015-03-09 | 2015-10-09 | 7 days Training Social Mobilizatio and DRR Content highlighted in the training | Manthali | 8
15491 | Ramechhap | Manthali N.P. | 15 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 14 | 14 | 2016-03-02 | 2016-03-08 |  | Manthali | 8
15492 | Ramechhap | Manthali N.P. | 16 | RRN | RRN | BMZ-WHH | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT 7 days Mason Training | # of trainees | Yes | Completed | 6 | 6 | 2016-03-02 | 2016-03-08 |  | Manthali | 8
15493 | Ramechhap | Phulasi | 1 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20 |  | Manthali | 13
15494 | Ramechhap | Phulasi | 1 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20 |  | Manthali | 13
15495 | Ramechhap | Phulasi | 2 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-06 | 2016-02-20 |  | Manthali | 13
15496 | Ramechhap | Phulasi | 3 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-01-06 | 2016-02-20 |  | Manthali | 13
15497 | Ramechhap | Phulasi | 4 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-06 | 2016-02-20 |  | Manthali | 13
15498 | Ramechhap | Phulasi | 5 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-06 | 2016-02-20 |  | Manthali | 13
15499 | Ramechhap | Phulasi | 5 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20 |  | Manthali | 13
15500 | Ramechhap | Phulasi | 6 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20 |  | Manthali | 14
15501 | Ramechhap | Phulasi | 7 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20 |  | Manthali | 14
15502 | Ramechhap | Phulasi | 7 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-06 | 2016-02-20 |  | Manthali | 14
15503 | Ramechhap | Tokarpur | 1 | RRN | RRN | AJJDC | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-06 | 2016-02-20 |  | Doramba | 3
15504 | Ramechhap | Tokarpur | 5 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-01-06 | 2016-02-20 |  | Doramba | 3
15505 | Ramechhap | Tokarpur | 6 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-06 | 2016-02-20 |  | Doramba | 3
15506 | Ramechhap | Tokarpur | 7 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-06 | 2016-02-20 |  | Doramba | 3
15507 | Ramechhap | Tokarpur | 8 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-06 | 2016-02-20 |  | Doramba | 5
15508 | Ramechhap | Tokarpur | 9 | RRN | RRN | AJJDC | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-06 | 2016-02-20 |  | Doramba | 5
15509 | Ramechhap | BamtiBhandar | 5 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Umakunda | 2
15510 | Ramechhap | BamtiBhandar | 6 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Umakunda | 2
15511 | Ramechhap | BamtiBhandar | 8 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Umakunda | 2
15512 | Ramechhap | Bethan | 4 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Sunapati | 4
15513 | Ramechhap | Bhadaure | 5 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11 |  | Khadadevi | 8
15514 | Ramechhap | Bhadaure | 7 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Khadadevi | 8
15515 | Ramechhap | Bhirpani | 5 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11 |  | Khadadevi | 3
15516 | Ramechhap | Bhirpani | 6 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Khadadevi | 3
15517 | Ramechhap | Bhirpani | 6 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Khadadevi | 3
15518 | Ramechhap | Bhirpani | 7 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Khadadevi | 3
15519 | Ramechhap | Bhirpani | 8 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Khadadevi | 3
15520 | Ramechhap | Bhujee | 6 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Umakunda | 7
15521 | Ramechhap | Bijulikot | 3 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11 |  | Likhu | 3
15522 | Ramechhap | Bijulikot | 5 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Likhu | 4
15523 | Ramechhap | Bijulikot | 5 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Likhu | 4
15524 | Ramechhap | Bijulikot | 5 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Likhu | 4
15525 | Ramechhap | Bijulikot | 6 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Likhu | 4
15526 | Ramechhap | Bijulikot | 6 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Likhu | 4
15527 | Ramechhap | Bijulikot | 8 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Likhu | 4
15528 | Ramechhap | Chanakhu | 2 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Manthali | 10
15529 | Ramechhap | Chanakhu | 5 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Manthali | 10
15530 | Ramechhap | Chanakhu | 6 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11 |  | Manthali | 10
15531 | Ramechhap | Chanakhu | 7 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Manthali | 10
15532 | Ramechhap | Chanakhu | 7 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Manthali | 10
15533 | Ramechhap | Dadhuwa | 6 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Doramba | 1
15534 | Ramechhap | Dimipokhari | 5 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 3 | 3 | 2016-01-07 | 2016-02-11 |  | Sunapati | 2
15535 | Ramechhap | Doramba | 6 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Doramba | 2
15536 | Ramechhap | Doramba | 7 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Doramba | 2
15537 | Ramechhap | Doramba | 8 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11 |  | Doramba | 2
15538 | Ramechhap | Duragau | 1 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 5 | 5 | 2016-01-07 | 2016-02-11 |  | Likhu | 1
15539 | Ramechhap | Duragau | 2 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Likhu | 1
15540 | Ramechhap | Duragau | 5 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Likhu | 1
15541 | Ramechhap | Duragau | 7 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Likhu | 1
15542 | Ramechhap | Duragau | 8 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Likhu | 1
15543 | Ramechhap | Gumdel | 1 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11 |  | Umakunda | 1
15544 | Ramechhap | Gumdel | 3 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Umakunda | 1
15545 | Ramechhap | Gunsibhadaure | 3 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Sunapati | 1
15546 | Ramechhap | Gunsibhadaure | 4 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Sunapati | 1
15547 | Ramechhap | Hiledevi | 5 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Sunapati | 3
15548 | Ramechhap | Himganga | 1 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Ramechhap | 4
15549 | Ramechhap | Himganga | 5 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Ramechhap | 4
15550 | Ramechhap | Himganga | 5 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Ramechhap | 4
15551 | Ramechhap | Himganga | 6 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 4 | 4 | 2016-01-07 | 2016-02-11 |  | Ramechhap | 4
15552 | Ramechhap | Himganga | 6 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Ramechhap | 4
15553 | Ramechhap | Himganga | 7 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Ramechhap | 4
15554 | Ramechhap | Himganga | 9 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Ramechhap | 4
15555 | Ramechhap | Khadadevi | 3 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Khadadevi | 7
15556 | Ramechhap | Khadadevi | 6 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 3 | 3 | 2016-01-07 | 2016-02-11 |  | Khadadevi | 7
15557 | Ramechhap | Kubukasthali | 1 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Umakunda | 3
15558 | Ramechhap | Kubukasthali | 5 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 3 | 3 | 2016-01-07 | 2016-02-11 |  | Umakunda | 3
15559 | Ramechhap | Kubukasthali | 8 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Umakunda | 3
15560 | Ramechhap | Kubukasthali | 9 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Umakunda | 3
15561 | Ramechhap | Lakhanpur | 4 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Doramba | 6
15562 | Ramechhap | Lakhanpur | 4 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11 |  | Doramba | 6
15563 | Ramechhap | Lakhanpur | 5 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Doramba | 6
15564 | Ramechhap | Namadi | 2 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Gokulganga | 5
15565 | Ramechhap | Pritee | 3 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Umakunda | 5
15566 | Ramechhap | Pritee | 4 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Umakunda | 4
15567 | Ramechhap | Pritee | 5 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Umakunda | 5
15568 | Ramechhap | Pritee | 6 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Umakunda | 5
15569 | Ramechhap | Rampur | 2 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Ramechhap | 5
15570 | Ramechhap | Rampur | 3 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Ramechhap | 5
15571 | Ramechhap | Rampur | 4 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Ramechhap | 5
15572 | Ramechhap | Rasanalu | 6 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11 |  | Gokulganga | 3
15573 | Ramechhap | Saipu | 2 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Likhu | 2
15574 | Ramechhap | Saipu | 3 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11 |  | Likhu | 2
15575 | Ramechhap | Saipu | 6 | SABAL | SABAL |  | Training | Vocational training | Electrician (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Likhu | 2
15576 | Ramechhap | Saipu | 6 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 2 | 2 | 2016-01-07 | 2016-02-11 |  | Likhu | 2
15577 | Ramechhap | Saipu | 7 | SABAL | SABAL |  | Training | Vocational training | Carpenter (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Likhu | 2
15578 | Ramechhap | Saipu | 7 | SABAL | SABAL |  | Training | Vocational training | Plumber (CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Likhu | 2
15579 | Ramechhap | Saipu | 8 | SABAL | SABAL |  | Training | Vocational training | New masons (50 days OJT CTEVT) | Training was conducted in Manthali N.P. | # of trainees | Yes | Completed | 1 | 1 | 2016-01-07 | 2016-02-11 |  | Likhu | 2
15580 | Ramechhap | Manthali N.P. | 4 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 437 | 351 | 2017-03-01 | 2018-02-28 |  | Manthali | 2
15581 | Ramechhap | Manthali N.P. | 5 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 378 | 310 | 2017-03-01 | 2018-02-28 |  | Manthali | 3
15582 | Ramechhap | Manthali N.P. | 15 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 448 | 277 | 2017-03-01 | 2018-02-28 |  | Manthali | 8
15583 | Ramechhap | khimti | 1 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 216 | 164 | 2017-03-01 | 2018-02-28 |  | Likhu | 6
15584 | Ramechhap | Gelu | 1 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 359 | 293 | 2017-09-01 | 2018-02-28 |  | Manthali | 12
15585 | Ramechhap | Duragau | 1 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 45 | 37 | 2017-09-01 | 2018-02-28 |  | Likhu | 1
15586 | Ramechhap | Manthali N.P. | 6 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 335 | 222 | 2017-09-01 | 2018-02-28 |  | Manthali | 3
15587 | Ramechhap | khimti | 2 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 78 | 45 | 2017-09-01 | 2018-02-28 |  | Likhu | 6
15588 | Ramechhap | khimti | 3 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 112 | 100 | 2017-09-01 | 2018-02-28 |  | Likhu | 6
15589 | Ramechhap | khimti | 4 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 141 | 100 | 2017-09-01 | 2018-02-28 |  | Likhu | 6
15590 | Ramechhap | khimti | 5 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 96 | 69 | 2017-09-01 | 2018-02-28 |  | Likhu | 6
15591 | Ramechhap | khimti | 6 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 60 | 48 | 2017-09-01 | 2018-02-28 |  | Likhu | 6
15592 | Ramechhap | khimti | 7 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 48 | 44 | 2017-09-01 | 2018-02-28 |  | Likhu | 6
15593 | Ramechhap | khimti | 8 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 55 | 43 | 2017-09-01 | 2018-02-28 |  | Likhu | 6
15594 | Ramechhap | khimti | 9 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 72 | 53 | 2017-09-01 | 2018-02-28 |  | Likhu | 6
15595 | Ramechhap | Gelu | 2 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 155 | 140 | 2017-09-01 | 2018-02-28 |  | Manthali | 12
15596 | Ramechhap | Gelu | 3 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 161 | 136 | 2017-09-01 | 2018-02-28 |  | Manthali | 12
15597 | Ramechhap | Gelu | 4 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 77 | 69 | 2017-09-01 | 2018-02-28 |  | Manthali | 12
15598 | Ramechhap | Gelu | 5 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 203 | 102 | 2017-09-01 | 2018-02-28 |  | Manthali | 11
15599 | Ramechhap | Gelu | 6 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 143 | 62 | 2017-09-01 | 2018-02-28 |  | Manthali | 11
15600 | Ramechhap | Gelu | 7 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 115 | 75 | 2017-09-01 | 2018-02-28 |  | Manthali | 11
15601 | Ramechhap | Gelu | 8 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 58 | 50 | 2017-09-01 | 2018-02-28 |  | Manthali | 11
15602 | Ramechhap | Gelu | 9 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 88 | 60 | 2017-09-01 | 2018-02-28 |  | Manthali | 11
15603 | Ramechhap | Duragau | 2 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 71 | 57 | 2017-09-01 | 2018-02-28 |  | Likhu | 1
15604 | Ramechhap | Duragau | 3 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 62 | 53 | 2017-09-01 | 2018-02-28 |  | Likhu | 1
15605 | Ramechhap | Duragau | 4 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 66 | 62 | 2017-09-01 | 2018-02-28 |  | Likhu | 1
15606 | Ramechhap | Duragau | 5 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 43 | 5 | 2017-09-01 | 2018-02-28 |  | Likhu | 1
15607 | Ramechhap | Duragau | 6 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 86 | 31 | 2017-09-01 | 2018-02-28 |  | Likhu | 1
15608 | Ramechhap | Duragau | 7 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 101 | 86 | 2017-09-01 | 2018-02-28 |  | Likhu | 1
15609 | Ramechhap | Duragau | 8 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 88 | 61 | 2017-09-01 | 2018-02-28 |  | Likhu | 1
15610 | Ramechhap | Duragau | 9 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 54 | 46 | 2017-09-01 | 2018-02-28 |  | Likhu | 1
15611 | Ramechhap | Manthali N.P. | 16 | SW Nepal | SW Nepal | SDC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 271 | 125 | 2017-09-01 | 2018-02-28 |  | Manthali | 8
15612 | Ramechhap | Pritee | 4 | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-12-30 | 2018-01-04 |  | Umakunda | 4
15613 | Ramechhap | Namadi | 5 | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-12-30 | 2018-01-04 |  | Gokulganga | 5
15614 | Ramechhap | Tokarpur | 3 | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2018-01-07 | 2018-01-13 |  | Doramba | 3
15615 | Ramechhap | Makadum | 6 | NRA | NRA | NRA | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2018-01-07 | 2018-01-13 |  | Khadadevi | 6
15616 | Ramechhap | BamtiBhandar | All | GOAL | CDS | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 28 | 28 | 2016-01-01 | 2016-02-28 |  | Umakunda | 2
15617 | Ramechhap | BamtiBhandar | All | GOAL | CDS | DFID | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Umakunda | 2
15618 | Ramechhap | Chuchure | All | GOAL | CDS | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 225 | 225 | 2016-01-01 | 2016-02-28 |  | Gokulganga | 1
15619 | Ramechhap | Chuchure | All | GOAL | CDS | DFID | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Gokulganga | 1
15620 | Ramechhap | Gumdel | All | GOAL | CDS | IOM | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 225 | 225 | 2016-01-01 | 2016-02-28 |  | Umakunda | 1
15621 | Ramechhap | Gumdel | All | GOAL | CDS | DFID | Others | Others | (Please specify in Activity Detail) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Umakunda | 1
15622 | Ramechhap | Manthali N.P. | 1 | GON - DUDBC | GON - DUDBC | GON - DUDBC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 26 | 2017-06-24 | 2017-06-30 |  | Manthali | 1
15623 | Ramechhap | Ramechhap N.P. |  | GON - DUDBC | GON - DUDBC | GON - DUDBC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 28 | 2017-06-25 | 2017-07-01 |  | Ramechhap | 9
15624 | Ramechhap | NagaDaha | 5 | GON - DUDBC | GON - DUDBC | WB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-06-10 | 2017-06-16 |  | Likhu | 5
15625 | Ramechhap | BamtiBhandar |  | GON - PAF | NSSS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-04-29 | 2017-05-05 |  | Umakunda | 2
15626 | Ramechhap | BamtiBhandar |  | GON - PAF | NSSS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-11 | 2017-06-17 |  | Umakunda | 2
15627 | Ramechhap | GunsiBhadaure |  | GON - PAF | NMSRC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-15 | 2017-06-21 |  | Sunapati | 1
15628 | Ramechhap | Guptesor |  | GON - PAF | MSWC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-11 | 2017-06-17 |  | Umakunda | 6
15629 | Ramechhap | Ramechhap N.P. | 5 | GON - PAF | SCSS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-04-29 | 2017-05-05 | Kathajor | Ramechhap | 8
15630 | Ramechhap | Manthali N.P. |  | GON - PAF | SYS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-11 | 2017-06-17 | Chisapani | Manthali | 8
15631 | Ramechhap | Pakarbas |  | GON - PAF | CDS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-04-30 | 2017-06-07 |  | Khadadevi | 4
15632 | Ramechhap | Ramechhap N.P. |  | GON - PAF | CDS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-10 | 2017-06-16 |  | Ramechhap | 9
15633 | Ramechhap | Ramechhap N.P. |  | GON - PAF | CHRDP | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-11 | 2017-06-17 |  | Ramechhap | 9
15634 | Ramechhap | Rakathum |  | GON - PAF | NMSRC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-04-28 | 2017-05-04 |  | Khadadevi | 1
15635 | Ramechhap | Hiledevi |  | GON - PAF | SYC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-04-29 | 2017-05-05 |  | Sunapati | 3
15636 | Ramechhap | Khadadevi |  | GON - PAF | NMSRC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-23 | 2017-06-29 |  | Khadadevi | 7
15637 | Ramechhap | Guptesor | 3 | GON - PAF | PSKK | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-11 | 2017-06-17 |  | Umakunda | 6
15638 | Ramechhap | NagaDaha |  | GON - PAF | CHRDP | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 22 | 2017-04-29 | 2017-05-05 |  | Likhu | 5
15639 | Ramechhap | Doramba |  | GON - PAF | JYC | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 19 | 2017-05-01 | 2017-05-06 |  | Doramba | 2
15640 | Ramechhap | Chuchure |  | GON - PAF | NSSS | GON - PAF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2017-06-18 | 2017-06-24 |  | Gokulganga | 1
15641 | Ramechhap | Doramba | All | HCI | YSP |  | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 41 | 41 | 2016-03-15 | 2016-04-30 |  | Doramba | 2
15642 | Ramechhap | Khimti | All | HCI | YSP |  | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 25 | 25 | 2016-03-01 | 2016-03-31 |  | Likhu | 6
15643 | Ramechhap | Saipu | All | HCI | YSP |  | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 41 | 41 | 2016-03-01 | 2016-03-31 |  | Likhu | 2
15644 | Ramechhap | Saipu | All | KFS |  | KFS | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | No | Planned | 590 | 0 |  |  |  | Likhu | 2
15645 | Ramechhap | Saipu | All | KFS |  | KFS | Others | Others | (Please specify in Activity Detail) | Plan is for two secondary school located in ward no. 7 and 8 respectively and health post which represents all the wards | # of trainees | Yes | Planned | 2 | 0 |  |  |  | Likhu | 2
15646 | Ramechhap | Bhirpani | All | MCC | CDS |  | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | No | Planned | 4 | 0 |  |  | yet to be approved | Khadadevi | 3
15647 | Ramechhap | Manthali N.P. | All | MCC | CDS |  | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | No | Planned | 20 | 0 |  |  | yet to be approved | Manthali | 8
15648 | Ramechhap | Pakarbas | All | MCC | CDS |  | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | No | Planned | 5 | 0 |  |  | yet to be approved | Khadadevi | 5
15649 | Ramechhap | Rakathum | All | MCC | CDS |  | Technical Assistance | Demonstration Construction | House | House constructed during OJT | # of constructions | No | Planned | 4 | 0 |  |  | yet to be approved | Khadadevi | 1
15650 | Ramechhap | Ramechhap N.P. | ALL | MEDAIR | CDS | MEDAIR | Technical Assistance | Communication and Outreach | PSA Radio broadcasting |  | # of episodes | Yes | Ongoing | 20 | 15 | 2017-08-01 |  |  | #N/A | #N/A
15651 | Ramechhap | Bhirpani | ALL | tdh-GER | CDS | tdh-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 50 | 50 | 2016-05-01 | 2016-05-25 | CGI Sheets | Khadadevi | 3
15652 | Ramechhap | Khadadevi | ALL | tdh-GER | CDS | tdh-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 30 | 30 | 2016-05-01 | 2016-05-25 | CGI Sheets | Khadadevi | 7
15653 | Ramechhap | Majuwa | ALL | tdh-GER | CDS | tdh-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 25 | 25 | 2016-05-01 | 2016-05-25 | CGI Sheets | Khadadevi | 2
15654 | Ramechhap | Rakathum | ALL | tdh-GER | CDS | tdh-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 25 | 25 | 2016-05-01 | 2016-05-25 | CGI Sheets | Khadadevi | 1
15655 | Ramechhap | Tokarpur | ALL | TDH-GER | CDS | tdh-GER | Financial/Material/Labour Assistance | In kind/material support in housing | Construction |  | # of households | Yes | Completed | 50 | 50 | 2016-05-01 | 2016-05-25 | CGI Sheets | Doramba | 3
15656 | Ramechhap | Manthali N.P. | 16 | CSIDB | CSIDB | CSIDB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2018-01-20 | 2018-01-27 |  | Manthali | 8
15657 | Ramechhap | Ramechhap N.P. | 7 | CSIDB | CSIDB | CSIDB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2018-01-22 | 2018-01-28 |  | Ramechhap | 7
15658 | Ramechhap | BamtiBhandar | 2 | CSIDB | CSIDB | CSIDB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2018-02-01 | 2018-02-07 |  | Umakunda | 2
15659 | Ramechhap | Those | 3 | CSIDB | CSIDB | CSIDB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2018-02-01 | 2018-02-07 |  | Gokulganga | 2
15660 | Ramechhap | NagaDaha | 5 | CSIDB | CSIDB | CSIDB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 27 | 27 | 2018-02-09 | 2018-02-15 |  | Likhu | 5
15661 | Ramechhap | Bhirpani | 3 | CSIDB | CSIDB | CSIDB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2018-02-04 | 2018-02-11 |  | Khadadevi | 3
15662 | Ramechhap | Hiledevi | 3 | CSIDB | CSIDB | CSIDB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2018-02-25 | 2018-03-03 |  | Sunapati | 3
15663 | Ramechhap | Ramechhap N.P. | 2 | GON - DUDBC | GON - DUDBC | GON - DUDBC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2018-01-05 | 2018-01-11 |  | Ramechhap | 6
15664 | Ramechhap | Doramba | 4 | GON - DUDBC | GON - DUDBC | GON - DUDBC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2018-02-18 | 2018-02-24 |  | Doramba | 2
15665 | Ramechhap | Ramechhap N.P. | 7 | GON - DUDBC | GON - DUDBC | GON - DUDBC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 35 | 2018-02-11 | 2018-02-17 |  | Ramechhap | 7
15666 | Ramechhap | Duragau | 1 | GON - DUDBC | GON - DUDBC | GON - DUDBC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 32 | 2018-01-24 | 2018-01-30 |  | Likhu | 1
15667 | Ramechhap | Gelu | 9 | GON - DUDBC | GON - DUDBC | GON - DUDBC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 27 | 2018-01-17 | 2018-01-24 |  | Manthali | 11
15668 | Ramechhap | Khaniyapani | 5 | GON - DUDBC | GON - DUDBC | GON - DUDBC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-12-16 | 2017-12-22 |  | Sunapati | 5
15669 | Ramechhap | Khadadevi | 5 | GON - DUDBC | GON - DUDBC | GON - DUDBC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-12-23 | 2017-12-29 |  | Khadadevi | 7
15670 | Ramechhap | Rasanalu | 3 | GON - DUDBC | GON - DUDBC | GON - DUDBC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 33 | 2017-12-30 | 2018-01-05 |  | Gokulganga | 3
15671 | Ramechhap | Tilpung | 7 | GON - DUDBC | GON - DUDBC | GON - DUDBC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2018-02-06 | 2018-02-12 |  | Likhu | 7
15672 | Ramechhap | Manthali N.P. | 11 | GON - DUDBC | GON - DUDBC | GON - DUDBC | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2018-01-08 | 2018-01-14 |  | Manthali | 6
15673 | Ramechhap | Manthali N.P. | 2 | NRCS | NRCS | IFRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Planned | 30 | 0 | 2016-01-01 | 2018-12-31 |  | Manthali | 1
15674 | Ramechhap | Rampur | 6 | NRCS | NRCS | IFRC | Training | Short training | Carpenter | Capacity building - Short training for carpenter | # of trainees |  | Planned | 30 | 0 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15675 | Ramechhap | Manthali N.P. | 2 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 30 | 30 | 2016-01-01 | 2018-12-31 |  | Manthali | 1
15676 | Ramechhap | Manthali N.P. | 2 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 60 | 61 | 2016-01-01 | 2018-12-31 |  | Manthali | 1
15677 | Ramechhap | Rampur | 6 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 30 | 30 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15678 | Ramechhap | Rampur | 1 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 18 | 18 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15679 | Ramechhap | Rampur | 2 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 8 | 8 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15680 | Ramechhap | Rampur | 3 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 9 | 9 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15681 | Ramechhap | Rampur | 4 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 14 | 14 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15682 | Ramechhap | Rampur | 5 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 20 | 20 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15683 | Ramechhap | Rampur | 6 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 14 | 14 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15684 | Ramechhap | Rampur | 7 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 12 | 12 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15685 | Ramechhap | Rampur | 8 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 14 | 14 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15686 | Ramechhap | Rampur | 9 | NRCS | NRCS | IFRC | Training | Short training | Masons (7 days DUDBC, rural or urban) | Capacity building - Short training for mason | # of trainees |  | Completed | 11 | 11 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15687 | Ramechhap | Manthali N.P. | 2 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 426 | 359 | 2017-06-21 | 2018-01-20 |  | Manthali | 1
15688 | Ramechhap | Rampur | 1 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 62 | 61 | 2016-05-13 | 2016-07-03 |  | Ramechhap | 5
15689 | Ramechhap | Rampur | 2 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 74 | 70 | 2016-05-13 | 2016-07-03 |  | Ramechhap | 5
15690 | Ramechhap | Rampur | 3 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 79 | 78 | 2017-06-21 | 2018-01-20 |  | Ramechhap | 5
15691 | Ramechhap | Rampur | 4 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 80 | 80 | 2016-05-13 | 2016-07-03 |  | Ramechhap | 5
15692 | Ramechhap | Rampur | 5 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 93 | 92 | 2016-05-13 | 2016-07-03 |  | Ramechhap | 5
15693 | Ramechhap | Rampur | 6 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 79 | 78 | 2016-05-13 | 2016-07-03 |  | Ramechhap | 5
15694 | Ramechhap | Rampur | 7 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 47 | 47 | 2016-05-13 | 2016-07-03 |  | Ramechhap | 5
15695 | Ramechhap | Rampur | 8 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 61 | 57 | 2016-05-13 | 2016-07-03 |  | Ramechhap | 5
15696 | Ramechhap | Rampur | 9 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Ongoing | 68 | 64 | 2016-05-13 | 2016-07-03 |  | Ramechhap | 5
15697 | Ramechhap | Manthali N.P. | 2 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 426 | 44 | 2016-05-31 | 2016-07-13 |  | Manthali | 1
15698 | Ramechhap | Rampur | 1 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 62 | 79 | 2016-09-01 | 2018-12-31 | Technical assistant is provided by NRCS staff | Ramechhap | 5
15699 | Ramechhap | Rampur | 2 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 74 | 86 | 2016-01-22 | 2016-04-25 |  | Ramechhap | 5
15700 | Ramechhap | Rampur | 3 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 79 | 29 | 2016-05-13 | 2016-07-03 |  | Ramechhap | 5
15701 | Ramechhap | Rampur | 4 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 80 | 18 | 2016-09-01 | 2018-12-31 | Technical assistant is provided by NRCS staff | Ramechhap | 5
15702 | Ramechhap | Rampur | 5 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 93 | 14 | 2016-09-01 | 2018-12-31 | Technical assistant is provided by NRCS staff | Ramechhap | 5
15703 | Ramechhap | Rampur | 6 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 79 | 14 | 2016-09-01 | 2018-12-31 | Technical assistant is provided by NRCS staff | Ramechhap | 5
15704 | Ramechhap | Rampur | 7 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 47 | 25 | 2016-09-01 | 2018-12-31 | Technical assistant is provided by NRCS staff | Ramechhap | 5
15705 | Ramechhap | Rampur | 8 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 61 | 61 | 2016-09-01 | 2018-12-31 | Technical assistant is provided by NRCS staff | Ramechhap | 5
15706 | Ramechhap | Rampur | 9 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Ongoing | 68 | 66 | 2016-09-01 | 2018-12-31 | Technical assistant is provided by NRCS staff | Ramechhap | 5
15707 | Ramechhap | Manthali N.P. | 2 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Planned | 426 | 41 | 2016-01-15 | 2016-04-29 |  | Manthali | 1
15708 | Ramechhap | Rampur | 1 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 62 | 35 | 2016-09-01 | 2018-12-31 |  | Ramechhap | 5
15709 | Ramechhap | Rampur | 2 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 74 | 45 | 2016-09-01 | 2018-12-31 | Technical assistant is provided by NRCS staff | Ramechhap | 5
15710 | Ramechhap | Rampur | 3 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 79 | 9 | 2016-09-01 | 2018-12-31 | Technical assistant is provided by NRCS staff | Ramechhap | 5
15711 | Ramechhap | Rampur | 4 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 80 | 6 | 2016-09-01 | 2018-12-31 |  | Ramechhap | 5
15712 | Ramechhap | Rampur | 5 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 93 | 2 | 2016-09-01 | 2018-12-31 |  | Ramechhap | 5
15713 | Ramechhap | Rampur | 6 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 79 | 5 | 2016-09-01 | 2018-12-31 |  | Ramechhap | 5
15714 | Ramechhap | Rampur | 7 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 47 | 14 | 2016-09-01 | 2018-12-31 |  | Ramechhap | 5
15715 | Ramechhap | Rampur | 8 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 61 | 27 | 2016-09-01 | 2018-12-31 |  | Ramechhap | 5
15716 | Ramechhap | Rampur | 9 | NRCS | NRCS | IFRC | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Ongoing | 68 | 43 | 2016-09-01 | 2018-12-31 |  | Ramechhap | 5
15717 | Ramechhap | Bhirpani | 7 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-01-20 | 2016-04-19 |  | Khadadevi | 3
15718 | Ramechhap | Khimti | 1 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-01-19 | 2016-04-22 |  | Likhu | 6
15719 | Ramechhap | Manthali N.P. | 2 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-09-01 | 2018-12-31 | Technical assistant is provided by NRCS staff | Manthali | 1
15720 | Ramechhap | Puranagau | 6 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-01-25 | 2016-04-20 |  | Manthali | 9
15721 | Ramechhap | Rampur | 6 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-09-01 | 2018-12-31 |  | Ramechhap | 5
15722 | Ramechhap | Tilpung | 5 | NRCS | NRCS | SRC | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-01-21 | 2016-04-18 |  | Likhu | 7
15723 | Ramechhap | Manthali N.P. | 2 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 887 | 887 | 2016-01-01 | 2018-12-31 | The total number of door to door technical assistance has been increased from 1069 to 1862 | Manthali | 1
15724 | Ramechhap | Rampur | 1 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 76 | 76 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15725 | Ramechhap | Rampur | 2 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 95 | 95 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15726 | Ramechhap | Rampur | 3 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 108 | 108 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15727 | Ramechhap | Rampur | 4 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 95 | 95 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15728 | Ramechhap | Rampur | 5 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 143 | 143 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15729 | Ramechhap | Rampur | 6 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 160 | 160 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15730 | Ramechhap | Rampur | 7 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 81 | 81 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15731 | Ramechhap | Rampur | 8 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 123 | 123 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15732 | Ramechhap | Rampur | 9 | NRCS | NRCS | IFRC | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 94 | 94 | 2016-01-01 | 2018-12-31 |  | Ramechhap | 5
15733 | Ramechhap | Lakhanpur | 7 | CSIDB | CSIDB | CSIDB | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 25 | 2018-03-12 | 2018-03-18 |  | Doramba | 7
15734 | Rasuwa | Jibjibe(Nilkantha) | ALL | Lumanti | Lumanti | CORDAID | Technical Assistance | Communication and Outreach | PSA Radio broadcasting |  | # of episodes | Yes | Completed | 1 | 1 | 2015-07-01 | 2015-12-30 |  | Kalika | 3
15735 | Rasuwa | Jibjibe(Nilkantha) | All | Lumanti | Lumanti | CORDAID | Technical Assistance | Communication and Outreach | PSA Radio broadcasting |  | # of episodes | Yes | Completed | 8 | 8 | 2015-12-01 | 2016-01-02 |  | Kalika | 3
15736 | Rasuwa | Laharepouwa | All | Lumanti | Lumanti | CORDAID | Technical Assistance | Communication and Outreach | PSA Radio broadcasting |  | # of episodes | Yes | Completed | 1 | 1 | 2015-07-01 | 2015-12-30 |  | Uttargaya | 5
15737 | Rasuwa | Laharepouwa | All | Lumanti | Lumanti | CORDAID | Technical Assistance | Communication and Outreach | PSA Radio broadcasting |  | # of episodes | Yes | Completed | 8 | 8 | 2015-12-01 | 2016-01-01 |  | Uttargaya | 5
15738 | Rasuwa | Yarsa | All | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-09-01 | 2017-11-10 |  | Naukunda | 1
15739 | Rasuwa | Ramche | All | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-09-01 | 2017-11-10 |  | Kalika | 1
15740 | Rasuwa | Yarsa | ALL | LWF | MANEKOR | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI Distribution per HH two bundels | # of households | Yes | Completed | 91 | 91 | 2015-09-01 | 2016-05-10 |  | Naukunda | 1
15741 | Rasuwa | Yarsa | ALL | LWF | MANEKOR | Islamic Relief | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI Distribution per HH two bundels | # of households | Yes | Completed | 609 | 609 | 2015-09-01 | 2015-10-25 |  | Naukunda | 1
15742 | Rasuwa | Chilime | ALL | LWF | MANEKOR | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI Distribution per HH two bundels | # of households | Yes | Completed | 90 | 90 | 2015-09-10 | 2016-05-10 |  | Parbati Kunda | 5
15743 | Rasuwa | Gatlang | ALL | LWF | MANEKOR | Islamic Relief | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI Distribution per HH two bundels | # of households | Yes | Completed | 588 | 588 | 2015-06-01 | 2015-10-25 |  | Parbati Kunda | 3
15744 | Rasuwa | Goljung | ALL | LWF | MANEKOR | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI Distribution per HH two bundels | # of households | Yes | Completed | 90 | 90 | 2015-09-01 | 2016-10-25 |  | Parbati Kunda | 4
15745 | Rasuwa | Goljung | ALL | LWF | MANEKOR | Islamic Relief | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | CGI Distribution per HH two bundels | # of households | Yes | Completed | 355 | 355 | 2015-06-01 | 2015-10-25 |  | Parbati Kunda | 4
15746 | Rasuwa | Gatlang | All | LWF | MANEKOR | Islamic Relief | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-11-06 | 2017-11-13 |  | Parbati Kunda | 3
15747 | Rasuwa | Goljung | All | LWF | MANEKOR | Islamic Relief | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-12-11 | 2017-12-16 |  | Parbati Kunda | 4
15748 | Rasuwa | Haku | All | OM-N | OM-N | OM-N | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Transportation of Building Materials | # of constructions | No | Ongoing | 752 | 0 | 2017-03-01 | 2018-12-31 |  | Parbati Kunda | 1
15749 | Rasuwa | Haku | All | OM-N | OM-N | OM-N | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Ongoing | 6 | 0 | 2017-03-01 | 2018-12-31 |  | Parbati Kunda | 1
15750 | Rasuwa | Haku | All | OM-N | OM-N | OM-N | Technical Assistance | Demonstration Construction | House | Stone masonary in mud mortar (4 Room) | # of constructions | Yes | Ongoing | 6 | 6 | 2017-03-01 | 2018-12-31 |  | Parbati Kunda | 1
15751 | Rasuwa | Haku | All | OM-N | OM-N | OM-N | Training | Other trainings | Other trainings (specify in Activity Detail) | Literacy Classes | # of trainees | Yes | Ongoing | 75 | 45 | 2015-08-01 | 2018-12-31 |  | Parbati Kunda | 1
15752 | Rasuwa | Haku | All | OM-N | OM-N | OM-N | Training | Vocational training | Carpenter (CTEVT) |  | # of trainees | Yes | Ongoing | 60 | 30 | 2017-03-01 | 2018-12-31 |  | Parbati Kunda | 1
15753 | Rasuwa | Haku | All | OM-N | OM-N | OM-N | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Ongoing | 60 | 61 | 2017-03-01 | 2018-12-31 |  | Parbati Kunda | 1
15754 | Rasuwa | Langtang | All | OM-N | OM-N | OM-N | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Transportation of Building Materials | # of constructions | Yes | Ongoing | 110 | 110 | 2016-08-01 | 2017-06-30 |  | Gosaikunda | 4
15755 | Rasuwa | Gatlang | 1 to 7 and 9 | CL | PN | CL | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Ongoing | 378 | 360 |  |  |  | Parbati Kunda | 3
15756 | Rasuwa | Gatlang | 2 to 7 and 9 | CL | PN | CL | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Planned | 2 | 0 |  |  |  | Parbati Kunda | 3
15757 | Rasuwa | Syafru | All | PA | JJMS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Resource centers | # of households supported | Yes | Ongoing | 1 | 1 |  |  |  | Gosaikunda | 5
15758 | Rasuwa | Gatlang | All | PA | JJMS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Resource centers | # of households supported | Yes | Ongoing | 1 | 1 |  |  |  | Parbati Kunda | 3
15759 | Rasuwa | Saramthali | All | PA | JJMS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Resource centers | # of households supported | Yes | Ongoing | 1 | 1 |  |  |  | Naukunda | 3
15760 | Rasuwa | Laharepouwa | All | PA | JJMS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Resource centers | # of households supported | Yes | Ongoing | 1 | 1 |  |  |  | Uttargaya | 5
15761 | Rasuwa | Dandagoun | All | PA | JJMS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Resource centers | # of households supported | Yes | Ongoing | 1 | 1 |  |  |  | Uttargaya | 2
15762 | Rasuwa | Bhorle | All | PA | JJMS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Stone cutting enterprises | # of households supported | Yes | Ongoing | 1 | 1 |  |  |  | Naukunda | 5
15763 | Rasuwa | Gatlang | All | PA | JJMS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Stone cutting enterprises | # of households supported | Yes | Ongoing | 1 | 1 |  |  |  | Parbati Kunda | 3
15764 | Rasuwa | Goljung | All | PA | JJMS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Stone cutting enterprises | # of households supported | Yes | Ongoing | 1 | 1 |  |  |  | Parbati Kunda | 4
15765 | Rasuwa | Jibjibe(Nilkantha) | All | PA | JJMS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Compressed Stabilizer Earth Brick | # of households supported | Yes | Ongoing | 1 | 1 |  |  |  | Kalika | 3
15766 | Rasuwa | Laharepouwa | All | PA | JJMS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Compressed Stabilizer Earth Brick | # of households supported | Yes | Ongoing | 1 | 1 |  |  |  | Uttargaya | 5
15767 | Rasuwa | Jibjibe(Nilkantha) | All | PA | JJMS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Timber treatment plant | # of households supported | Yes | Ongoing | 1 | 1 |  |  |  | Kalika | 3
15768 | Rasuwa | Thulogoun | 2,3 | BC | BC | ARC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre | Build Back Safer Theater program | # of participants | Yes | Completed | 123 | 123 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
15769 | Rasuwa | Thulogoun | 8,9 | BC | BC | ARC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre | Build Back Safer Theater program | # of participants | Yes | Completed | 108 | 108 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
15770 | Rasuwa | Gatlang | ALL | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session | Minimum 75 people in group | # of participants | Yes | Completed | 399 | 399 |  |  |  | Parbati Kunda | 3
15771 | Rasuwa | Haku | ALL | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session | Minimum 75 people in group | # of participants | Yes | Completed | 483 | 483 |  |  |  | Parbati Kunda | 1
15772 | Rasuwa | Jibjibe(Nilkantha) | 3,4 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 57 | 57 | 2016-12-17 | 2016-12-17 |  | Kalika | 3
15773 | Rasuwa | Thulogoun | 2,3 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 36 | 36 | 2016-12-06 | 2016-12-06 |  | Uttargaya | 3
15774 | Rasuwa | Thulogoun | 4,5 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 52 | 52 | 2016-12-08 | 2016-12-08 |  | Uttargaya | 3
15775 | Rasuwa | Dandagoun | ALL | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 654 | 654 |  |  |  | Uttargaya | 2
15776 | Rasuwa | Syafru | ALL | GIZ | GIZ | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 620 | 620 | 2016-04-15 | 2016-04-25 |  | Gosaikunda | 5
15777 | Rasuwa | Syafru | ALL | GIZ | GOAL | GIZ | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits |  | # of households | Yes | Completed | 656 | 656 |  |  |  | Gosaikunda | 5
15778 | Rasuwa | Bhorle | All | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | VDC Level Reconstruction Coordination Committee(VLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Naukunda | 5
15779 | Rasuwa | Bhorle | All | GoN | GoN | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 35 | 2017-07-15 | 2017-07-22 |  | Naukunda | 5
15780 | Rasuwa | Bridhim | All | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | VDC Level Reconstruction Coordination Committee(VLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 3
15781 | Rasuwa | Dandagoun | All | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | VDC Level Reconstruction Coordination Committee(VLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 2
15782 | Rasuwa | Dhunche | All | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | VDC Level Reconstruction Coordination Committee(VLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 6
15783 | Rasuwa | Gatlang | All | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | VDC Level Reconstruction Coordination Committee(VLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Parbati Kunda | 3
15784 | Rasuwa | Langtang | All | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | VDC Level Reconstruction Coordination Committee(VLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 4
15785 | Rasuwa | Ramche | All | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | VDC Level Reconstruction Coordination Committee(VLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Kalika | 1
15786 | Rasuwa | Syafru | All | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | VDC Level Reconstruction Coordination Committee(VLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 5
15787 | Rasuwa | Thulogoun | All | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | VDC Level Reconstruction Coordination Committee(VLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 3
15788 | Rasuwa | Thuman | All | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | VDC Level Reconstruction Coordination Committee(VLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 1
15789 | Rasuwa | Timure | All | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | VDC Level Reconstruction Coordination Committee(VLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 2
15790 | Rasuwa | Dandagoun | ALL | LDF | LDF | GON - PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Completed | 433 | 433 |  |  |  | Uttargaya | 2
15791 | Rasuwa | Dhunche | ALL | LDF | LDF | GON - PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Completed | 369 | 369 |  |  |  | Gosaikunda | 6
15792 | Rasuwa | Saramthali | ALL | LDF | LDF | GON - PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Completed | 775 | 775 |  |  |  | Naukunda | 3
15793 | Rasuwa | Yarsa | ALL | LWF | BATAS | DEC-ii | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-15 | 2017-03-15 |  | Naukunda | 1
15794 | Rasuwa | Laharepouwa | ALL | NAF | NAF | GON - PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Completed | 1120 | 1120 |  |  |  | Uttargaya | 5
15795 | Rasuwa | Ramche | ALL | NAF | NAF | GON - PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Completed | 446 | 446 |  |  |  | Kalika | 1
15796 | Rasuwa | Syafru | ALL | NAF | NAF | GON - PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Completed | 390 | 390 |  |  |  | Gosaikunda | 5
15797 | Rasuwa | Goljung | ALL | PPY | PPY | GON - PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Completed | 286 | 286 |  |  |  | Parbati Kunda | 4
15798 | Rasuwa | Thuman | ALL | PPY | PPY | GON - PAF | Technical Assistance | Community reconstruction orientation | 2-3 sessions | Minimum 75 people in group | # of participants | Yes | Completed | 232 | 232 |  |  |  | Gosaikunda | 1
15799 | Rasuwa | Laharepouwa | ALL | GON | NRA | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 31 | 31 | 2018-01-04 | 2018-01-10 |  | Uttargaya | 5
15800 | Rasuwa | Dhunche | ALL | GON | NRA | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2018-01-25 | 2018-02-02 |  | Gosaikunda | 6
15801 | Rasuwa | Jibjibe(Nilkantha) | All | GON | NRA | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 21 | 21 | 2017-12-25 | 2018-01-02 |  | Kalika | 3
15802 | Rasuwa | Yarsa | All | GON | NRA | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 19 | 2018-03-15 | 2018-03-20 |  | Naukunda | 1
15803 | Rasuwa | Gatlang | ALL | GON | DLPIU | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2018-01-20 | 2018-01-27 |  | Parbati Kunda | 3
15804 | Rasuwa | Laharepouwa | ALL | GON | DLPIU | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 | 2018-01-28 | 2018-01-02 |  | Uttargaya | 5
15805 | Rasuwa | Laharepouwa | All | GON | CSIDB | GoN | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 30 | 30 |  |  |  | Uttargaya | 5
15806 | Rasuwa | Bhorle | 2 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-23 | 2017-02-13 |  | Naukunda | 6
15807 | Rasuwa | Bhorle | 2 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-23 | 2017-02-13 |  | Naukunda | 6
15808 | Rasuwa | Bhorle | 4 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2017-04-30 | 2017-07-26 |  | Naukunda | 5
15809 | Rasuwa | Bhorle | 4 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-30 | 2017-02-20 |  | Naukunda | 5
15810 | Rasuwa | Bhorle | 4 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-30 | 2017-07-26 |  | Naukunda | 5
15811 | Rasuwa | Bhorle | 4 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-30 | 2017-02-20 |  | Naukunda | 5
15812 | Rasuwa | Bhorle | 5 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-18 | 2017-02-08 |  | Naukunda | 5
15813 | Rasuwa | Bhorle | 5 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-18 | 2017-02-08 |  | Naukunda | 5
15814 | Rasuwa | Bhorle | 7 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-18 | 2017-02-08 |  | Naukunda | 5
15815 | Rasuwa | Bhorle | 7 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-18 | 2017-02-08 |  | Naukunda | 5
15816 | Rasuwa | Bhorle | 8 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2017-01-21 | 2017-03-11 |  | Kalika | 4
15817 | Rasuwa | Bhorle | 8 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-01-21 | 2017-03-11 |  | Kalika | 4
15818 | Rasuwa | Bhorle | 8 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-21 | 2017-03-11 |  | Kalika | 4
15819 | Rasuwa | Bhorle | 8 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-21 | 2017-03-11 |  | Kalika | 4
15820 | Rasuwa | Bhorle | 9 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 4 | 4 | 2017-06-01 | 2017-07-27 |  | Kalika | 4
15821 | Rasuwa | Bhorle | 9 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-06-01 | 2017-07-27 |  | Kalika | 4
15822 | Rasuwa | Bhorle | 8 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 8 | 8 | 2017-05-30 | 2017-06-05 |  | Kalika | 4
15823 | Rasuwa | Bhorle | 7 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 1 | 1 | 2017-05-30 | 2017-06-05 |  | Naukunda | 5
15824 | Rasuwa | Bhorle | 9 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 1 | 1 | 2017-05-30 | 2017-06-05 |  | Kalika | 4
15825 | Rasuwa | Bhorle | 3 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 10 | 10 | 2017-06-07 | 2017-06-13 |  | Naukunda | 6
15826 | Rasuwa | Bridhim | 8 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-03-13 | 2017-07-20 |  | Gosaikunda | 3
15827 | Rasuwa | Bridhim | 8 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-13 | 2017-07-20 |  | Gosaikunda | 3
15828 | Rasuwa | Chilime | 8 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-03-20 | 2017-07-18 |  | Parbati Kunda | 5
15829 | Rasuwa | Chilime | 8 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-20 | 2017-07-18 |  | Parbati Kunda | 5
15830 | Rasuwa | Dandagoun | 1 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Brick masonary in cement mortar (10*10 Room size) | # of constructions | Yes | Completed | 2 | 2 | 2017-01-07 | 2017-02-27 |  | Uttargaya | 2
15831 | Rasuwa | Dandagoun | 1 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-07 | 2017-03-27 |  | Uttargaya | 2
15832 | Rasuwa | Dandagoun | 4 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary In Mud Mortar .12*12 And 12*12Room Size | # of constructions | Yes | Completed | 2 | 2 | 2017-01-07 | 2017-02-27 |  | Uttargaya | 2
15833 | Rasuwa | Dandagoun | 4 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-01-07 | 2017-03-17 |  | Uttargaya | 2
15834 | Rasuwa | Dandagoun | 6 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary In Mud Mortar .10*10 And 12*12Room Size | # of constructions | Yes | Completed | 4 | 4 | 2017-01-06 | 2017-02-26 |  | Uttargaya | 2
15835 | Rasuwa | Dandagoun | 6 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-01-06 | 2017-03-16 |  | Uttargaya | 2
15836 | Rasuwa | Dandagoun | 7 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary In Mud Mortar .10*10 Room Size | # of constructions | Yes | Completed | 2 | 2 | 2017-01-06 | 2017-02-26 |  | Uttargaya | 1
15837 | Rasuwa | Dandagoun | 7 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-01-25 | 2017-03-15 |  | Uttargaya | 1
15838 | Rasuwa | Dandagoun | 7 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-06 | 2017-03-16 |  | Uttargaya | 1
15839 | Rasuwa | Dandagoun | 7 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-16 | 2017-03-16 |  | Uttargaya | 1
15840 | Rasuwa | Dandagoun | 1 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 9 | 9 | 2017-06-11 | 2017-06-17 |  | Uttargaya | 2
15841 | Rasuwa | Dandagoun | 8 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 1 | 1 | 2017-06-11 | 2017-06-17 |  | Uttargaya | 1
15842 | Rasuwa | Gatlang | 1 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-02-20 | 2017-06-20 |  | Parbati Kunda | 3
15843 | Rasuwa | Gatlang | 1 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-02-27 | 2017-06-25 |  | Parbati Kunda | 3
15844 | Rasuwa | Gatlang | 7 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 4 | 4 | 2017-02-17 | 2017-06-20 |  | Parbati Kunda | 2
15845 | Rasuwa | Gatlang | 7 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-02-24 | 2017-06-25 |  | Parbati Kunda | 2
15846 | Rasuwa | Gatlang | 8 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 4 | 4 | 2017-01-25 | 2017-03-15 |  | Parbati Kunda | 2
15847 | Rasuwa | Gatlang | 8 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-01-06 | 2017-03-06 |  | Parbati Kunda | 2
15848 | Rasuwa | Goljung | 6 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-03-05 | 2017-07-25 |  | Parbati Kunda | 4
15849 | Rasuwa | Goljung | 6 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-05 | 2017-07-25 |  | Parbati Kunda | 4
15850 | Rasuwa | Goljung | 7 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 4 | 4 | 2017-02-07 | 2017-04-27 |  | Parbati Kunda | 4
15851 | Rasuwa | Goljung | 7 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-02-26 | 2017-04-16 |  | Parbati Kunda | 4
15852 | Rasuwa | Goljung | 9 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-03-05 | 2017-07-25 |  | Parbati Kunda | 4
15853 | Rasuwa | Goljung | 9 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-05 | 2017-07-25 |  | Parbati Kunda | 4
15854 | Rasuwa | Goljung | 4 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 4 | 4 | 2017-06-18 | 2017-06-24 |  | Parbati Kunda | 4
15855 | Rasuwa | Goljung | 5 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 1 | 1 | 2017-06-18 | 2017-06-24 |  | Parbati Kunda | 4
15856 | Rasuwa | Goljung | 6 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 2 | 2 | 2017-06-18 | 2017-06-24 |  | Parbati Kunda | 4
15857 | Rasuwa | Goljung | 8 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 1 | 1 | 2017-06-18 | 2017-06-24 |  | Parbati Kunda | 4
15858 | Rasuwa | Goljung | 9 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 2 | 2 | 2017-06-18 | 2017-06-24 |  | Parbati Kunda | 4
15859 | Rasuwa | Haku | 1 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 6 | 6 | 2017-01-10 | 2017-03-16 |  | Parbati Kunda | 2
15860 | Rasuwa | Haku | 1 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-01-10 | 2017-03-16 |  | Parbati Kunda | 2
15861 | Rasuwa | Haku | 2 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-03-17 | 2017-06-05 |  | Parbati Kunda | 2
15862 | Rasuwa | Haku | 2 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-03-17 | 2017-06-05 |  | Parbati Kunda | 2
15863 | Rasuwa | Haku | 1 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 9 | 9 |  |  |  | Parbati Kunda | 2
15864 | Rasuwa | Haku | 2 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Parbati Kunda | 2
15865 | Rasuwa | Jibjibe(Nilkantha) | 2 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-04-19 | 2017-07-22 |  | Kalika | 3
15866 | Rasuwa | Jibjibe(Nilkantha) | 2 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-10 | 2017-07-27 |  | Kalika | 3
15867 | Rasuwa | Jibjibe(Nilkantha) | 4 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-10 | 2017-07-27 |  | Kalika | 3
15868 | Rasuwa | Jibjibe(Nilkantha) | 4 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-06-10 | 2017-07-27 |  | Kalika | 3
15869 | Rasuwa | Jibjibe(Nilkantha) | 4 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 4 | 4 | 2016-12-18 | 2017-02-08 |  | Kalika | 3
15870 | Rasuwa | Jibjibe(Nilkantha) | 4 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-01-16 | 2017-02-06 |  | Kalika | 3
15871 | Rasuwa | Jibjibe(Nilkantha) | 5 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-14 | 2017-02-18 |  | Kalika | 2
15872 | Rasuwa | Jibjibe(Nilkantha) | 5 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-06-13 | 2017-07-29 |  | Kalika | 2
15873 | Rasuwa | Jibjibe(Nilkantha) | 5 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-11-29 | 2017-02-18 |  | Kalika | 2
15874 | Rasuwa | Jibjibe(Nilkantha) | 5 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-04-19 | 2017-07-22 |  | Kalika | 2
15875 | Rasuwa | Jibjibe(Nilkantha) | 6 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-11-29 | 2017-01-12 |  | Kalika | 2
15876 | Rasuwa | Jibjibe(Nilkantha) | 6 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-14 | 2017-01-12 |  | Kalika | 2
15877 | Rasuwa | Jibjibe(Nilkantha) | 7 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | (1.1) Brick Masonry in Cement Mortar. 10'x 10'Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-01-13 | 2016-03-08 |  | Kalika | 2
15878 | Rasuwa | Jibjibe(Nilkantha) | 7 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-13 | 2016-03-08 |  | Kalika | 2
15879 | Rasuwa | Jibjibe(Nilkantha) | 8 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-14 | 2017-01-12 |  | Kalika | 5
15880 | Rasuwa | Jibjibe(Nilkantha) | 8 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-06-10 | 2017-07-27 |  | Kalika | 5
15881 | Rasuwa | Jibjibe(Nilkantha) | 8 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-14 | 2017-01-12 |  | Kalika | 5
15882 | Rasuwa | Jibjibe(Nilkantha) | 8 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-06-13 | 2017-07-29 |  | Kalika | 5
15883 | Rasuwa | Jibjibe(Nilkantha) | 9 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-14 | 2017-02-18 |  | Kalika | 5
15884 | Rasuwa | Jibjibe(Nilkantha) | 9 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-25 | 2017-03-09 |  | Kalika | 5
15885 | Rasuwa | Jibjibe(Nilkantha) | 9 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-25 | 2017-03-09 |  | Kalika | 5
15886 | Rasuwa | Jibjibe(Nilkantha) | 9 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-14 | 2017-02-18 |  | Kalika | 5
15887 | Rasuwa | Jibjibe(Nilkantha) | 9 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 10 | 10 | 2017-05-30 | 2017-06-05 |  | Kalika | 5
15888 | Rasuwa | Jibjibe(Nilkantha) | 7 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 10 | 10 | 2017-05-03 | 2017-05-10 |  | Kalika | 2
15889 | Rasuwa | Laharepouwa | 1 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-01-12 | 2017-04-16 |  | Uttargaya | 5
15890 | Rasuwa | Laharepouwa | 1 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-12 | 2017-04-16 |  | Uttargaya | 5
15891 | Rasuwa | Laharepouwa | 6 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 4 | 4 | 2017-05-24 | 2017-07-16 |  | Uttargaya | 4
15892 | Rasuwa | Laharepouwa | 6 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-05-24 | 2017-07-16 |  | Uttargaya | 4
15893 | Rasuwa | Laharepouwa | 7 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 6 | 6 | 2017-01-12 | 2017-04-16 |  | Uttargaya | 4
15894 | Rasuwa | Laharepouwa | 7 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-01-12 | 2017-04-16 |  | Uttargaya | 4
15895 | Rasuwa | Laharepouwa | 7 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-05-15 | 2017-06-16 |  | Uttargaya | 4
15896 | Rasuwa | Laharepouwa | 7 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-05-15 | 2017-06-16 |  | Uttargaya | 4
15897 | Rasuwa | Laharepouwa | 9 | HELVETAS | CMES | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 6 | 6 | 2017-05-29 | 2017-07-15 |  | Uttargaya | 5
15898 | Rasuwa | Laharepouwa | 9 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 30 | 30 | 2017-05-29 | 2017-07-15 |  | Uttargaya | 5
15899 | Rasuwa | Laharepouwa | 4 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 10 | 10 | 2017-06-20 | 2017-06-26 |  | Uttargaya | 4
15900 | Rasuwa | Laharepouwa | 4 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 9 | 9 | 2017-06-20 | 2017-06-26 |  | Uttargaya | 4
15901 | Rasuwa | Laharepouwa | 6 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 1 | 1 | 2017-06-20 | 2017-06-26 |  | Uttargaya | 4
15902 | Rasuwa | Ramche | 2 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Brick masonary in cement mortar (16.6*11) One room) + Varanda | # of constructions | Yes | Completed | 2 | 2 | 2017-01-14 | 2017-03-14 |  | Kalika | 1
15903 | Rasuwa | Ramche | 2 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-14 | 2017-03-14 |  | Kalika | 1
15904 | Rasuwa | Ramche | 3 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary In Mud Mortar (9*9 Room Size) | # of constructions | Yes | Completed | 2 | 2 | 2017-01-16 | 2017-03-18 |  | Kalika | 1
15905 | Rasuwa | Ramche | 3 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-01-16 | 2017-03-25 |  | Kalika | 1
15906 | Rasuwa | Ramche | 3 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-16 | 2017-03-18 |  | Kalika | 1
15907 | Rasuwa | Ramche | 3 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 5 | 5 | 2017-01-16 | 2017-03-25 |  | Kalika | 1
15908 | Rasuwa | Ramche | 4 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2017-01-16 | 2017-03-30 |  | Kalika | 1
15909 | Rasuwa | Ramche | 4 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-16 | 2017-03-30 |  | Kalika | 1
15910 | Rasuwa | Ramche | 9 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary In Mud Mortar .10*10 And 10*10 Room Size | # of constructions | Yes | Completed | 4 | 4 | 2017-01-16 | 2017-03-30 |  | Kalika | 1
15911 | Rasuwa | Ramche | 9 | HELVETAS | CMES | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 20 | 20 | 2017-01-16 | 2017-03-30 |  | Kalika | 1
15912 | Rasuwa | Ramche | 7 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Kalika | 1
15913 | Rasuwa | Ramche | 8 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Kalika | 1
15914 | Rasuwa | Ramche | 9 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Kalika | 1
15915 | Rasuwa | Ramche | 2 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Kalika | 1
15916 | Rasuwa | Ramche | 3 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Kalika | 1
15917 | Rasuwa | Ramche | 4 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 6 | 6 |  |  |  | Kalika | 1
15918 | Rasuwa | Saramthali | 2 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-10 | 2017-01-21 |  | Naukunda | 4
15919 | Rasuwa | Saramthali | 2 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-10 | 2017-01-21 |  | Naukunda | 4
15920 | Rasuwa | Saramthali | 3 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2017-01-16 | 2017-06-15 |  | Naukunda | 4
15921 | Rasuwa | Saramthali | 3 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2017-01-16 | 2017-06-15 |  | Naukunda | 4
15922 | Rasuwa | Saramthali | 4 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-25 | 2017-02-16 |  | Naukunda | 4
15923 | Rasuwa | Saramthali | 4 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-25 | 2017-02-16 |  | Naukunda | 4
15924 | Rasuwa | Saramthali | 6 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-03 | 2017-01-20 |  | Naukunda | 3
15925 | Rasuwa | Saramthali | 6 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-03 | 2017-01-20 |  | Naukunda | 3
15926 | Rasuwa | Saramthali | 7 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-05 | 2017-01-25 |  | Naukunda | 3
15927 | Rasuwa | Saramthali | 7 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-05 | 2017-01-25 |  | Naukunda | 3
15928 | Rasuwa | Saramthali | 8 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-18 | 2017-02-16 |  | Naukunda | 3
15929 | Rasuwa | Saramthali | 8 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 | 2016-12-25 | 2017-02-19 |  | Naukunda | 3
15930 | Rasuwa | Saramthali | 8 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-18 | 2017-02-16 |  | Naukunda | 3
15931 | Rasuwa | Saramthali | 8 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-25 | 2017-02-19 |  | Naukunda | 3
15932 | Rasuwa | Saramthali | 9 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-18 | 2017-02-27 |  | Naukunda | 3
15933 | Rasuwa | Saramthali | 9 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar .10'x10' Room Size | # of constructions | Yes | Completed | 2 | 2 | 2016-12-25 | 2017-03-18 |  | Naukunda | 3
15934 | Rasuwa | Saramthali | 9 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-18 | 2017-02-27 |  | Naukunda | 3
15935 | Rasuwa | Saramthali | 9 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 | 2016-12-25 | 2017-03-18 |  | Naukunda | 3
15936 | Rasuwa | Saramthali | 3 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 10 | 10 | 2017-06-06 | 2017-06-12 |  | Naukunda | 4
15937 | Rasuwa | Saramthali | 7 | HELVETAS | GMTI | DFID | Training | Short training | Carpenter | 7 days Construction carpentry Training | # of trainees | Yes | Completed | 10 | 10 | 2017-06-07 | 2017-06-13 |  | Naukunda | 3
15938 | Rasuwa | Yarsa | 9 | HELVETAS | GMTI | DFID | Training | Vocational training | New masons (50 days OJT CTEVT) |  | # of trainees | Yes | Completed | 10 | 10 |  |  |  | Naukunda | 6
15939 | Rasuwa | Yarsa | 9 | HELVETAS | GMTI | DFID | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 2 | 2 |  |  |  | Naukunda | 6
15940 | Rasuwa | Dandagoun | 8 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-01 | 2016-01-01 |  | Uttargaya | 1
15941 | Rasuwa | Dandagoun | 9 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-01 | 2016-01-01 |  | Uttargaya | 1
15942 | Rasuwa | Haku | 2 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (other curriculums, specify in Activity Detail) | CTEVT | # of trainees | Yes | Completed | 1 | 1 | 2015-09-02 | 2016-04-30 |  | Parbati Kunda | 2
15943 | Rasuwa | Haku | 8 | Lumanti | Lumanti | CORDAID | Training | Vocational training | Electrician (CTEVT) | CTEVT | # of trainees | Yes | Completed | 6 | 6 | 2016-04-15 | 2016-07-15 |  | Uttargaya | 1
15944 | Rasuwa | Haku | 8 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2015-09-02 | 2016-04-30 |  | Uttargaya | 1
15945 | Rasuwa | Haku | 9 | Lumanti | Lumanti | CORDAID | Training | Vocational training | Electrician (CTEVT) | CTEVT | # of trainees | Yes | Completed | 4 | 4 | 2016-04-15 | 2016-07-15 |  | Uttargaya | 1
15946 | Rasuwa | Haku | 9 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 10 | 10 | 2015-09-02 | 2016-04-30 |  | Uttargaya | 1
15947 | Rasuwa | Jibjibe(Nilkantha) | 2 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 189 | 189 | 2015-03-03 | 2015-09-10 |  | Kalika | 3
15948 | Rasuwa | Jibjibe(Nilkantha) | 3 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 81 | 81 | 2015-12-30 | 2017-12-30 |  | Kalika | 3
15949 | Rasuwa | Jibjibe(Nilkantha) | 3 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 81 | 81 | 2015-12-30 | 2017-12-30 |  | Kalika | 3
15950 | Rasuwa | Jibjibe(Nilkantha) | 3 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Completed | 81 | 81 | 2015-12-30 | 2017-12-30 |  | Kalika | 3
15951 | Rasuwa | Jibjibe(Nilkantha) | 1 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 4 | 4 | 2015-12-30 | 2017-12-30 |  | Kalika | 3
15952 | Rasuwa | Jibjibe(Nilkantha) | 1 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Completed | 21 | 21 | 2015-12-30 | 2017-12-30 |  | Kalika | 3
15953 | Rasuwa | Jibjibe(Nilkantha) | 1 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 21 | 21 | 2015-12-30 | 2017-12-30 |  | Kalika | 3
15954 | Rasuwa | Jibjibe(Nilkantha) | 3 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 96 | 96 | 2015-07-01 | 2015-12-30 |  | Kalika | 3
15955 | Rasuwa | Jibjibe(Nilkantha) | 3 | Lumanti | Lumanti | CORDAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 81 | 81 | 2015-12-30 | 2017-12-30 |  | Kalika | 3
15956 | Rasuwa | Jibjibe(Nilkantha) | 3 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2015-09-02 | 2016-04-30 |  | Kalika | 3
15957 | Rasuwa | Jibjibe(Nilkantha) | 4 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 114 | 113 | 2015-12-30 | 2017-12-30 |  | Kalika | 3
15958 | Rasuwa | Jibjibe(Nilkantha) | 4 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Completed | 114 | 114 | 2015-12-30 | 2017-12-30 |  | Kalika | 3
15959 | Rasuwa | Jibjibe(Nilkantha) | 4 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 114 | 114 | 2015-12-30 | 2017-12-30 |  | Kalika | 3
15960 | Rasuwa | Jibjibe(Nilkantha) | 4 | Lumanti | Lumanti | CORDAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 114 | 114 | 2015-12-30 | 2017-12-30 |  | Kalika | 3
15961 | Rasuwa | Jibjibe(Nilkantha) | 5 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 169 | 169 | 2015-07-01 | 2015-12-30 |  | Kalika | 2
15962 | Rasuwa | Jibjibe(Nilkantha) | 5 | Lumanti | Lumanti | CORDAID | Technical Assistance | Demonstration Construction | House | Brick masonary in cement mortar | # of constructions | Yes | Completed | 1 | 1 | 2016-04-02 | 2017-12-02 |  | Kalika | 2
15963 | Rasuwa | Jibjibe(Nilkantha) | 5 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-09-02 | 2016-04-30 |  | Kalika | 2
15964 | Rasuwa | Jibjibe(Nilkantha) | 6 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 95 | 95 | 2015-07-01 | 2015-12-30 |  | Kalika | 2
15965 | Rasuwa | Jibjibe(Nilkantha) | 6 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2015-09-02 | 2016-04-30 |  | Kalika | 2
15966 | Rasuwa | Jibjibe(Nilkantha) | 7 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 183 | 183 | 2015-07-01 | 2015-12-30 |  | Kalika | 2
15967 | Rasuwa | Jibjibe(Nilkantha) | 7 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 13 | 13 | 2015-09-02 | 2016-04-30 |  | Kalika | 2
15968 | Rasuwa | Jibjibe(Nilkantha) | 8 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 129 | 129 | 2015-07-01 | 2015-12-30 |  | Kalika | 5
15969 | Rasuwa | Jibjibe(Nilkantha) | 8 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-09-02 | 2016-04-30 |  | Kalika | 5
15970 | Rasuwa | Jibjibe(Nilkantha) | 9 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-09-02 | 2016-04-30 |  | Kalika | 5
15971 | Rasuwa | Laharepouwa | 1 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 204 | 204 | 2015-07-01 | 2015-12-30 |  | Uttargaya | 5
15972 | Rasuwa | Laharepouwa | 2 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 193 | 193 | 2015-07-01 | 2015-12-30 |  | Uttargaya | 5
15973 | Rasuwa | Laharepouwa | 2 | Lumanti | Lumanti | CORDAID | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar | # of constructions | Yes | Completed | 1 | 1 | 2016-04-01 | 2017-12-01 |  | Uttargaya | 5
15974 | Rasuwa | Laharepouwa | 3 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 164 | 164 | 2015-07-01 | 2015-12-30 |  | Uttargaya | 5
15975 | Rasuwa | Laharepouwa | 4 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-09-15 | 2016-04-30 |  | Uttargaya | 4
15976 | Rasuwa | Laharepouwa | 6 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-09-15 | 2016-04-30 |  | Uttargaya | 4
15977 | Rasuwa | Laharepouwa | 7 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 99 | 99 | 2015-12-30 | 2017-12-30 |  | Uttargaya | 4
15978 | Rasuwa | Laharepouwa | 7 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 99 | 99 | 2015-12-30 | 2017-12-30 |  | Uttargaya | 4
15979 | Rasuwa | Laharepouwa | 7 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Completed | 99 | 99 | 2015-12-30 | 2017-12-30 |  | Uttargaya | 4
15980 | Rasuwa | Laharepouwa | 7 | Lumanti | Lumanti | CORDAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 99 | 99 | 2015-12-30 | 2017-12-30 |  | Uttargaya | 4
15981 | Rasuwa | Laharepouwa | 7 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2015-09-15 | 2016-04-30 |  | Uttargaya | 4
15982 | Rasuwa | Laharepouwa | 8 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 183 | 183 | 2015-07-01 | 2015-12-30 |  | Kalika | 2
15983 | Rasuwa | Laharepouwa | 8 | Lumanti | Lumanti | CORDAID | Training | Vocational training | Electrician (CTEVT) | CTEVT | # of trainees | Yes | Completed | 9 | 9 | 2016-04-15 | 2016-07-15 |  | Kalika | 2
15984 | Rasuwa | Laharepouwa | 8 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2015-09-15 | 2016-04-30 |  | Kalika | 2
15985 | Rasuwa | Laharepouwa | 9 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 55 | 55 | 2015-12-30 | 2017-12-30 |  | Uttargaya | 5
15986 | Rasuwa | Laharepouwa | 9 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 55 | 55 | 2015-12-30 | 2017-12-30 |  | Uttargaya | 5
15987 | Rasuwa | Laharepouwa | 9 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Completed | 55 | 55 | 2015-12-30 | 2017-12-30 |  | Uttargaya | 5
15988 | Rasuwa | Laharepouwa | 9 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution Of CGI SHEET ( 2 Bundel per HH ) | # of households | Yes | Completed | 109 | 109 | 2015-07-01 | 2015-12-30 |  | Uttargaya | 5
15989 | Rasuwa | Laharepouwa | 2 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 1 | 1 | 2015-07-01 | 2015-12-30 |  | Uttargaya | 5
15990 | Rasuwa | Laharepouwa | 2 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Completed | 10 | 10 | 2015-07-01 | 2015-12-30 |  | Uttargaya | 5
15991 | Rasuwa | Laharepouwa | 2 | Lumanti | Lumanti | CORDAID | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 10 | 10 | 2015-07-01 | 2015-12-30 |  | Uttargaya | 5
15992 | Rasuwa | Laharepouwa | 9 | Lumanti | Lumanti | CORDAID | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 65 | 65 | 2015-12-30 | 2017-12-30 |  | Uttargaya | 5
15993 | Rasuwa | Laharepouwa | 9 | Lumanti | Lumanti | CORDAID | Training | Vocational training | Electrician (CTEVT) | CTEVT | # of trainees | Yes | Completed | 2 | 2 | 2016-04-15 | 2016-07-15 |  | Uttargaya | 5
15994 | Rasuwa | Laharepouwa | 9 | Lumanti | Lumanti | CORDAID | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-09-15 | 2016-04-30 |  | Uttargaya | 5
15995 | Rasuwa | Ramche | 1 | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-15 | 2017-03-15 |  | Kalika | 1
15996 | Rasuwa | Ramche | 2 | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-15 | 2017-03-15 |  | Kalika | 1
15997 | Rasuwa | Ramche | 1 | LWF | BATAS | DEC-II | Technical Assistance | Household drinking water schemes | Household drinking water schemes |  | # of households | Yes | Completed | 150 | 150 | 2016-03-15 | 2017-03-15 |  | Kalika | 1
15998 | Rasuwa | Ramche | 4 | LWF | BATAS | DEC-II | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 1 | 1 | 2016-03-15 | 2017-03-15 |  | Kalika | 1
15999 | Rasuwa | Ramche | 4 | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-15 | 2017-03-15 |  | Kalika | 1
16000 | Rasuwa | Ramche | 5 | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-15 | 2017-03-15 |  | Kalika | 1
16001 | Rasuwa | Ramche | 6 | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-15 | 2017-03-15 |  | Kalika | 1
16002 | Rasuwa | Ramche | 7 | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-15 | 2017-03-15 |  | Kalika | 1
16003 | Rasuwa | Ramche | 8 | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-03-15 | 2017-03-15 |  | Kalika | 1
16004 | Rasuwa | Ramche | 9 | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-15 | 2017-03-15 |  | Kalika | 1
16005 | Rasuwa | Ramche | 3 | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-15 | 2017-03-15 |  | Kalika | 1
16006 | Rasuwa | Yarsa | 1 | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-15 | 2017-03-15 |  | Naukunda | 2
16007 | Rasuwa | Yarsa | 2 | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-15 | 2017-03-15 |  | Naukunda | 2
16008 | Rasuwa | Yarsa | 4 | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-15 | 2017-03-15 |  | Naukunda | 2
16009 | Rasuwa | Yarsa | 5 | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-15 | 2017-03-15 |  | Naukunda | 1
16010 | Rasuwa | Yarsa | 6 | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-15 | 2017-03-15 |  | Naukunda | 1
16011 | Rasuwa | Yarsa | 7 | LWF | BATAS | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Bricks,Sand,Aggregate,Reinforcement Bar,Cement,Truss,CGI Sheet & Plain Sheet,Shovel, Axe Peak, Layout Thread, Measuring Tape, Tagari | # of households | Yes | Completed | 151 | 151 | 2016-03-15 | 2017-03-15 |  | Naukunda | 1
16012 | Rasuwa | Yarsa | 7 | LWF | BATAS | DEC-II | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | Masonry equipments | # of households | Yes | Completed | 151 | 151 | 2016-03-15 | 2017-03-15 |  | Naukunda | 1
16013 | Rasuwa | Yarsa | 7 | LWF | BATAS | DEC-II | Financial/Material/Labour Assistance | Other financial/material/labour assistance | (Please specify in Activity Detail) | Cash support for labour (One lakh three thousand twenty eight ) | # of constructions | Yes | Completed | 151 | 151 | 2016-03-15 | 2017-03-15 |  | Naukunda | 1
16014 | Rasuwa | Yarsa | 7 | LWF | BATAS | DEC-II | Technical Assistance | Community orientation on toilet construction | 2-3 sessions | Engineer, sub-engineer , SM | # of participants | Yes | Completed | 151 | 151 | 2016-03-15 | 2017-03-15 |  | Naukunda | 1
16015 | Rasuwa | Yarsa | 7 | LWF | BATAS | DEC-II | Technical Assistance | Door-to-door technical assistance | Continuous | Engineer, sub-engineer , Two trained masion , SM | # of households | Yes | Completed | 151 | 151 | 2016-03-15 | 2017-03-15 |  | Naukunda | 1
16016 | Rasuwa | Yarsa | 7 | LWF | BATAS | DEC-II | Technical Assistance | Household reconstruction orientation | 2-3 sessions | Engineer, sub-engineer , SM | # of households | Yes | Completed | 151 | 151 | 2016-03-15 | 2017-03-15 |  | Naukunda | 1
16017 | Rasuwa | Yarsa | 7 | LWF | BATAS | DEC-II | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee |  | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2017-03-15 |  | Naukunda | 1
16018 | Rasuwa | Yarsa | 7 | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-15 | 2017-03-15 |  | Naukunda | 1
16019 | Rasuwa | Yarsa | 8 | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-03-15 | 2017-03-15 |  | Naukunda | 1
16020 | Rasuwa | Yarsa | 9 | LWF | BATAS | DEC-II | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-15 | 2017-03-15 |  | Naukunda | 6
16021 | Rasuwa | Yarsa | 3 | LWF | BATAS | DEC-ii | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-15 | 2017-03-15 |  | Naukunda | 2
16022 | Rasuwa | Gatlang | 7 | LWF | MANEKOR | Islamic Relief | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 61 | 61 | 2016-08-01 | 2017-10-30 |  | Parbati Kunda | 2
16023 | Rasuwa | Gatlang | 7 | LWF | MANEKOR | Islamic Relief | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Completed | 61 | 61 | 2016-08-01 | 2017-10-30 |  | Parbati Kunda | 2
16024 | Rasuwa | Gatlang | 7 | LWF | MANEKOR | Islamic Relief | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 61 | 56 | 2016-08-01 | 2017-10-30 |  | Parbati Kunda | 2
16025 | Rasuwa | Gatlang | 7 | LWF | MANEKOR | Islamic Relief | Technical Assistance | Door-to-door technical assistance | Continuous | 1 sub engineer ,1 SM | # of households | Yes | Completed | 79 | 79 | 2016-08-01 | 2017-10-30 |  | Parbati Kunda | 2
16026 | Rasuwa | Gatlang | 7 | LWF | MANEKOR | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 18 | 2017-01-22 | 2017-01-28 |  | Parbati Kunda | 2
16027 | Rasuwa | Gatlang | 8 | LWF | MANEKOR | Islamic Relief | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche II |  | # of households | Yes | Completed | 40 | 40 | 2016-08-01 | 2017-10-30 |  | Parbati Kunda | 2
16028 | Rasuwa | Gatlang | 8 | LWF | MANEKOR | Islamic Relief | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche I |  | # of households | Yes | Completed | 40 | 40 | 2016-08-01 | 2017-10-30 |  | Parbati Kunda | 2
16029 | Rasuwa | Gatlang | 8 | LWF | MANEKOR | Islamic Relief | Financial/Material/Labour Assistance | GoN Housing Grant | Tranche III |  | # of households | Yes | Completed | 40 | 35 | 2016-08-01 | 2017-10-30 |  | Parbati Kunda | 2
16030 | Rasuwa | Gatlang | 8 | LWF | MANEKOR | Islamic Relief | Technical Assistance | Door-to-door technical assistance | Continuous | 1 sub engineer , 1 SM | # of households | Yes | Completed | 71 | 71 | 2016-08-01 | 2017-10-30 |  | Parbati Kunda | 2
16031 | Rasuwa | Gatlang | 8 | LWF | MANEKOR | ACT Alliance | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 25 | 12 | 2017-01-22 | 2017-01-28 |  | Parbati Kunda | 2
16032 | Rasuwa | Bhorle | 6 | PA | JJMS | DFID | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | Resource centers | # of households supported | Yes | Ongoing | 1 | 1 |  |  |  | Kalika | 4
16033 | Rasuwa | Langtang | 2 | SP | OM-N | SP | Technical Assistance | Demonstration Construction | House | Stone masonary in cement mortar (4 Room ) | # of constructions | Yes | Completed | 1 | 1 | 2016-01-01 | 2017-12-31 |  | Gosaikunda | 4
16034 | Rasuwa | Langtang | 2 | SP | OM-N | SP | Technical Assistance | Demonstration Construction | House | Stone masonary in cement mortar (2 Room ) | # of constructions | Yes | Completed | 1 | 1 | 2016-01-01 | 2017-12-31 |  | Gosaikunda | 4
16035 | Rasuwa | Langtang | 3 | SP | OM-N | SP | Technical Assistance | Demonstration Construction | House | Stone masonary in cement mortar (4 Room ) | # of constructions | Yes | Completed | 1 | 1 | 2016-01-01 | 2017-12-31 |  | Gosaikunda | 4
16036 | Rasuwa | Langtang | 4 | SP | OM-N | SP | Technical Assistance | Demonstration Construction | House | Stone masonary in cement mortar (4 Room ) | # of constructions | Yes | Completed | 1 | 1 | 2016-01-01 | 2017-12-31 |  | Gosaikunda | 4
16037 | Rasuwa | Langtang | 7 | SP | OM-N | SP | Technical Assistance | Demonstration Construction | House | Stone masonary in cement mortar (2 Room ) | # of constructions | Yes | Completed | 1 | 1 | 2016-01-01 | 2017-12-31 |  | Gosaikunda | 4
16038 | Rasuwa | Langtang | 7 | SP | SP | SP | Technical Assistance | Demonstration Construction | House |  | # of constructions | Yes | Completed | 14 | 14 |  |  |  | Gosaikunda | 4
16039 | Rasuwa | Langtang | 7 | SP | OM-N | SP | Technical Assistance | Demonstration Construction | House | Stone masonary in cement mortar (2 Room ) | # of constructions | Yes | Completed | 1 | 1 | 2017-05-01 | 2017-12-31 |  | Gosaikunda | 4
16040 | Rasuwa | Langtang | 7 | SP | OM-N | SP | Technical Assistance | Door-to-door technical assistance | Continuous | 3 engineers, SM | # of households | Yes | Ongoing | 116 | 21 | 2016-01-01 | 2017-12-31 |  | Gosaikunda | 4
16041 | Rasuwa | Langtang | 7 | SP | OM-N | SP | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Engineer, sub-engineer , SM | # of households | Yes | Completed | 116 | 116 | 2016-01-01 | 2016-07-31 |  | Gosaikunda | 4
16042 | Rasuwa | Langtang | 7 | SP | OM-N | SP | Technical Assistance | Hygiene and Sanitation Promotion | Hygiene and Sanitation Promotion | WASH Committees & Training | # of households | Yes | Completed | 40 | 40 | 2016-01-01 | 2016-07-31 |  | Gosaikunda | 4
16043 | Rasuwa | Langtang | 7 | SP | OM-N | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Disaster Risk Reduction Training | # of trainees | Yes | Completed | 116 | 116 | 2016-01-01 | 2016-07-31 |  | Gosaikunda | 4
16044 | Rasuwa | Langtang | 7 | SP | OM-N | SP | Training | Other trainings | Other trainings (specify in Activity Detail) | Community Leadership Skills Training | # of trainees | Yes | Ongoing | 116 | 166 | 2016-01-01 | 2016-07-31 |  | Gosaikunda | 4
16045 | Rasuwa | Bhorle | 6 | ACF | LACCOS | DFID | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Completed | 87 | 87 | 2016-09-01 | 2017-06-30 |  | Kalika | 4
16046 | Rasuwa | Bhorle | 8 | ACF | LACCOS | DFID | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Completed | 5 | 5 | 2016-09-01 | 2017-06-30 |  | Kalika | 4
16047 | Rasuwa | Bridhim | 1 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-06-28 |  | Gosaikunda | 3
16048 | Rasuwa | Chilime | 4 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28 |  | Parbati Kunda | 5
16049 | Rasuwa | Chilime | 8 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-05-22 |  | Parbati Kunda | 5
16050 | Rasuwa | Chilime | 9 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-05-16 | 2016-05-22 |  | Parbati Kunda | 5
16051 | Rasuwa | Chilime | 9 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-06-28 |  | Parbati Kunda | 5
16052 | Rasuwa | Dandagoun | 3 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-10 | 2016-06-16 |  | Uttargaya | 2
16053 | Rasuwa | Dandagoun | 4 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-10 | 2016-06-16 |  | Uttargaya | 2
16054 | Rasuwa | Dandagoun | 8 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-10 | 2016-06-16 |  | Uttargaya | 1
16055 | Rasuwa | Dandagoun | 9 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2016-06-10 | 2016-06-16 |  | Uttargaya | 1
16056 | Rasuwa | Dhunche | 1 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Completed | 13 | 13 | 2016-09-01 | 2017-06-30 |  | Gosaikunda | 6
16057 | Rasuwa | Dhunche | 2 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Completed | 13 | 13 | 2016-09-01 | 2017-06-30 |  | Gosaikunda | 6
16058 | Rasuwa | Dhunche | 4 | ACF | LACCOS | DFID | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Completed | 38 | 38 | 2016-09-01 | 2017-06-30 |  | Gosaikunda | 6
16059 | Rasuwa | Gatlang | 1 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28 |  | Parbati Kunda | 3
16060 | Rasuwa | Gatlang | 2 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-16 | 2016-05-22 |  | Parbati Kunda | 3
16061 | Rasuwa | Gatlang | 5 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-05-22 |  | Parbati Kunda | 3
16062 | Rasuwa | Gatlang | 5 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-06-28 |  | Parbati Kunda | 3
16063 | Rasuwa | Gatlang | 6 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28 |  | Parbati Kunda | 3
16064 | Rasuwa | Gatlang | 7 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-16 | 2016-05-22 |  | Parbati Kunda | 2
16065 | Rasuwa | Gatlang | 8 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-05-22 |  | Parbati Kunda | 2
16066 | Rasuwa | Goljung | 3 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-05-16 | 2016-05-22 |  | Parbati Kunda | 4
16067 | Rasuwa | Goljung | 5 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-05-22 |  | Parbati Kunda | 4
16068 | Rasuwa | Goljung | 5 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28 |  | Parbati Kunda | 4
16069 | Rasuwa | Goljung | 6 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-05-22 |  | Parbati Kunda | 4
16070 | Rasuwa | Goljung | 7 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-05-22 |  | Parbati Kunda | 4
16071 | Rasuwa | Goljung | 8 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-05-16 | 2016-05-22 |  | Parbati Kunda | 4
16072 | Rasuwa | Goljung | 8 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-06-28 |  | Parbati Kunda | 4
16073 | Rasuwa | Goljung | 9 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-05-16 | 2016-05-22 |  | Parbati Kunda | 4
16074 | Rasuwa | Haku | 1 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28 |  | Parbati Kunda | 2
16075 | Rasuwa | Haku | 2 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28 |  | Parbati Kunda | 2
16076 | Rasuwa | Haku | 3 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-06-28 |  | Parbati Kunda | 1
16077 | Rasuwa | Haku | 8 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-06-10 | 2016-06-16 |  | Uttargaya | 1
16078 | Rasuwa | Haku | 8 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28 |  | Uttargaya | 1
16079 | Rasuwa | Haku | 9 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-10 | 2016-06-16 |  | Uttargaya | 1
16080 | Rasuwa | Haku | 9 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28 |  | Uttargaya | 1
16081 | Rasuwa | Jibjibe(Nilkantha) | 2 | ACF | LACCOS | DFID | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Completed | 13 | 13 | 2016-09-01 | 2017-06-30 |  | Kalika | 3
16082 | Rasuwa | Laharepouwa | 1 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-10 | 2016-06-16 |  | Uttargaya | 5
16083 | Rasuwa | Laharepouwa | 3 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-10 | 2016-06-16 |  | Uttargaya | 5
16084 | Rasuwa | Laharepouwa | 3 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28 |  | Uttargaya | 5
16085 | Rasuwa | Laharepouwa | 4 | ACF | LACCOS | DFID | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Completed | 88 | 88 | 2016-09-01 | 2017-06-30 |  | Uttargaya | 4
16086 | Rasuwa | Laharepouwa | 8 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-10 | 2016-06-16 |  | Kalika | 2
16087 | Rasuwa | Laharepouwa | 9 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-10 | 2016-06-16 |  | Uttargaya | 5
16088 | Rasuwa | Ramche | 1 | ACF | LACCOS | ACF | Technical Assistance | Household orientation on toilet construction | 2-3 sessions |  | # of households | Yes | Completed | 28 | 28 | 2016-09-01 | 2017-06-30 |  | Kalika | 1
16089 | Rasuwa | Ramche | 2 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Completed | 10 | 10 | 2016-09-01 | 2017-06-30 |  | Kalika | 1
16090 | Rasuwa | Ramche | 2 | ACF | LACCOS | ACF | Technical Assistance | Household orientation on toilet construction | 2-3 sessions |  | # of households | Yes | Completed | 58 | 58 | 2016-08-01 | 2017-04-30 |  | Kalika | 1
16091 | Rasuwa | Ramche | 3 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Completed | 50 | 50 | 2016-09-01 | 2017-06-30 |  | Kalika | 1
16092 | Rasuwa | Ramche | 3 | ACF | LACCOS | ACF | Technical Assistance | Household orientation on toilet construction | 2-3 sessions |  | # of households | Yes | Completed | 96 | 96 | 2016-08-01 | 2017-04-30 |  | Kalika | 1
16093 | Rasuwa | Ramche | 4 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Completed | 20 | 20 | 2016-09-01 | 2017-06-30 |  | Kalika | 1
16094 | Rasuwa | Ramche | 4 | ACF | LACCOS | ACF | Technical Assistance | Household orientation on toilet construction | 2-3 sessions |  | # of households | Yes | Completed | 88 | 88 | 2016-08-01 | 2017-04-30 |  | Kalika | 1
16095 | Rasuwa | Ramche | 4 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-06-22 | 2016-06-28 |  | Kalika | 1
16096 | Rasuwa | Ramche | 5 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Completed | 70 | 70 | 2016-09-01 | 2017-06-30 |  | Kalika | 1
16097 | Rasuwa | Ramche | 5 | ACF | LACCOS | ACF | Technical Assistance | Household orientation on toilet construction | 2-3 sessions |  | # of households | Yes | Completed | 72 | 72 | 2016-08-01 | 2017-04-30 |  | Kalika | 1
16098 | Rasuwa | Ramche | 6 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Completed | 20 | 20 | 2016-09-01 | 2017-06-30 |  | Kalika | 1
16099 | Rasuwa | Ramche | 6 | ACF | LACCOS | ACF | Technical Assistance | Household orientation on toilet construction | 2-3 sessions |  | # of households | Yes | Completed | 66 | 66 | 2016-08-01 | 2017-04-30 |  | Kalika | 1
16100 | Rasuwa | Ramche | 7 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Completed | 20 | 20 | 2016-09-01 | 2017-06-30 |  | Kalika | 1
16101 | Rasuwa | Ramche | 7 | ACF | LACCOS | ACF | Technical Assistance | Household orientation on toilet construction | 2-3 sessions |  | # of households | Yes | Completed | 52 | 52 | 2016-08-01 | 2017-04-30 |  | Kalika | 1
16102 | Rasuwa | Ramche | 8 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Completed | 20 | 20 | 2016-09-01 | 2017-06-30 |  | Kalika | 1
16103 | Rasuwa | Ramche | 8 | ACF | LACCOS | ACF | Technical Assistance | Household orientation on toilet construction | 2-3 sessions |  | # of households | Yes | Completed | 81 | 81 | 2016-08-01 | 2017-04-30 |  | Kalika | 1
16104 | Rasuwa | Ramche | 9 | ACF | LACCOS | ACF | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Completed | 75 | 75 | 2016-09-01 | 2017-06-30 |  | Kalika | 1
16105 | Rasuwa | Ramche | 9 | ACF | LACCOS | ACF | Technical Assistance | Household orientation on toilet construction | 2-3 sessions |  | # of households | Yes | Completed | 101 | 101 | 2016-08-01 | 2017-04-30 |  | Kalika | 1
16106 | Rasuwa | Saramthali | 4 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-22 | 2016-06-28 |  | Naukunda | 4
16107 | Rasuwa | Syafru | 9 | ACF | LACCOS | ACF | Technical Assistance | Demonstration Construction | House | Stone Masonary in Mud Mortar . | # of constructions | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-08-30 |  | Gosaikunda | 5
16108 | Rasuwa | syafru | 9 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-22 | 2016-06-28 |  | Gosaikunda | 5
16109 | Rasuwa | Thulogoun | 5 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28 |  | Uttargaya | 3
16110 | Rasuwa | Thulogoun | 6 | ACF | LACCOS | DFID | Financial/Material/Labour Assistance | Material support on household WASH | Community water scheme |  | # of households | Yes | Completed | 26 | 26 | 2016-09-01 | 2017-06-30 |  | Uttargaya | 3
16111 | Rasuwa | Yarsa | 4 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28 |  | Naukunda | 2
16112 | Rasuwa | Yarsa | 5 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28 |  | Naukunda | 1
16113 | Rasuwa | Yarsa | 6 | ACF | LACCOS | ACF | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-06-22 | 2016-06-28 |  | Naukunda | 1
16114 | Rasuwa | Dandagoun | 1 | BC | BC | ARC | Others | Others | (Please specify in Activity Detail) | Design of drawing | # of trainees | Yes | Completed | 9 | 9 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16115 | Rasuwa | Dandagoun | 1 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Site survey | # of households | Yes | Completed | 21 | 21 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16116 | Rasuwa | Dandagoun | 1 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Monitoring of On going construction | # of households | Yes | Completed | 13 | 13 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16117 | Rasuwa | Dandagoun | 2 | BC | BC | ARC | Others | Others | (Please specify in Activity Detail) | Design of drawing | # of trainees | Yes | Completed | 5 | 5 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16118 | Rasuwa | Dandagoun | 2 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Site survey | # of households | Yes | Completed | 7 | 7 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16119 | Rasuwa | Dandagoun | 2 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Monitoring of On going construction | # of households | Yes | Completed | 4 | 4 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16120 | Rasuwa | Dandagoun | 3 | BC | BC | ARC | Others | Others | (Please specify in Activity Detail) | Design of drawing | # of trainees | Yes | Completed | 3 | 3 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16121 | Rasuwa | Dandagoun | 3 | BC | BC | ARC | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | TSC will provide service to the beneficiaries for land assessment, design for construction and technical assessment throughout the construction process. Build Change has established TSC in addition to the agreement with NRA | # of households supported | Yes | Completed | 1 | 1 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16122 | Rasuwa | Dandagoun | 3 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Site survey | # of households | Yes | Completed | 4 | 4 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16123 | Rasuwa | Dandagoun | 3 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Monitoring of On going construction | # of households | Yes | Completed | 1 | 1 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16124 | Rasuwa | Dandagoun | 4 | BC | BC | ARC | Others | Others | (Please specify in Activity Detail) | Design of drawing | # of trainees | Yes | Completed | 3 | 3 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16125 | Rasuwa | Dandagoun | 4 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Site survey | # of households | Yes | Completed | 3 | 3 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16126 | Rasuwa | Dandagoun | 4 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Monitoring of On going construction | # of households | Yes | Completed | 3 | 3 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16127 | Rasuwa | Dandagoun | 5 | BC | BC | ARC | Others | Others | (Please specify in Activity Detail) | Design of drawing | # of trainees | Yes | Completed | 2 | 2 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16128 | Rasuwa | Dandagoun | 5 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Site survey | # of households | Yes | Completed | 2 | 2 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16129 | Rasuwa | Dandagoun | 6 | BC | BC | ARC | Others | Others | (Please specify in Activity Detail) | Design of drawing | # of trainees | Yes | Completed | 4 | 4 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16130 | Rasuwa | Dandagoun | 6 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Site survey | # of households | Yes | Completed | 11 | 11 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16131 | Rasuwa | Dandagoun | 6 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Monitoring of On going construction | # of households | Yes | Completed | 5 | 5 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16132 | Rasuwa | Dandagoun | 7 | BC | BC | ARC | Others | Others | (Please specify in Activity Detail) | Design of drawing | # of trainees | Yes | Completed | 12 | 12 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 1
16133 | Rasuwa | Dandagoun | 7 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Site survey | # of households | Yes | Completed | 72 | 72 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 1
16134 | Rasuwa | Dandagoun | 7 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Monitoring of On going construction | # of households | Yes | Completed | 24 | 24 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 1
16135 | Rasuwa | Dandagoun | 8 | BC | BC | ARC | Others | Others | (Please specify in Activity Detail) | Design of drawing | # of trainees | Yes | Completed | 1 | 1 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 1
16136 | Rasuwa | Dandagoun | 8 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Site survey | # of households | Yes | Completed | 3 | 3 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 1
16137 | Rasuwa | Dandagoun | 9 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Design of drawing | # of households | Yes | Completed | 11 | 11 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 1
16138 | Rasuwa | Dandagoun | 9 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Site survey | # of households | Yes | Completed | 55 | 55 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 1
16139 | Rasuwa | Dandagoun | 9 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Monitoring of On going construction | # of households | Yes | Completed | 33 | 33 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 1
16140 | Rasuwa | Thulogoun | 1 | BC | BC | ARC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre | Build Back Safer Theater program | # of participants | Yes | Completed | 205 | 205 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16141 | Rasuwa | Thulogoun | 1 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Site survey | # of households | Yes | Completed | 42 | 42 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16142 | Rasuwa | Thulogoun | 1 | BC | BC | ARC | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Home Owner Training | # of households | Yes | Completed | 45 | 45 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16143 | Rasuwa | Thulogoun | 1 | BC | BC | ARC | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Design of drawing | # of households | Yes | Completed | 15 | 2 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16144 | Rasuwa | Thulogoun | 1 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Monitoring of On going construction | # of households | Yes | Completed | 18 | 2 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16145 | Rasuwa | Thulogoun | 2 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Site survey | # of households | Yes | Completed | 31 | 31 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16146 | Rasuwa | Thulogoun | 2 | BC | BC | ARC | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Home Owner Training | # of households | Yes | Completed | 28 | 28 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16147 | Rasuwa | Thulogoun | 2 | BC | BC | ARC | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Design of drawing | # of households | Yes | Completed | 7 | 7 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16148 | Rasuwa | Thulogoun | 2 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Monitoring of On going construction | # of households | Yes | Completed | 12 | 12 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16149 | Rasuwa | Thulogoun | 3 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Site survey | # of households | Yes | Completed | 27 | 27 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16150 | Rasuwa | Thulogoun | 3 | BC | BC | ARC | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Home Owner Training | # of households | Yes | Completed | 24 | 24 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16151 | Rasuwa | Thulogoun | 3 | BC | BC | ARC | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Design of drawing | # of households | Yes | Completed | 15 | 15 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16152 | Rasuwa | Thulogoun | 3 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Monitoring of On going construction | # of households | Yes | Completed | 16 | 16 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16153 | Rasuwa | Thulogoun | 4 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Site survey | # of households | Yes | Completed | 33 | 33 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16154 | Rasuwa | Thulogoun | 4 | BC | BC | ARC | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Home Owner Training | # of households | Yes | Completed | 32 | 32 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16155 | Rasuwa | Thulogoun | 4 | BC | BC | ARC | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Design of drawing | # of households | Yes | Completed | 9 | 9 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16156 | Rasuwa | Thulogoun | 4 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Monitoring of On going construction | # of households | Yes | Completed | 10 | 10 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16157 | Rasuwa | Thulogoun | 5 | BC | BC | ARC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre | Build Back Safer Theater program | # of participants | Yes | Completed | 153 | 153 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16158 | Rasuwa | Thulogoun | 5 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Site survey | # of households | Yes | Completed | 45 | 45 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16159 | Rasuwa | Thulogoun | 5 | BC | BC | ARC | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Home Owner Training | # of households | Yes | Completed | 43 | 43 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16160 | Rasuwa | Thulogoun | 5 | BC | BC | ARC | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Design of drawing | # of households | Yes | Completed | 9 | 9 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16161 | Rasuwa | Thulogoun | 5 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Monitoring of On going construction | # of households | Yes | Completed | 13 | 13 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16162 | Rasuwa | Thulogoun | 6 | BC | BC | ARC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre | Build Back Safer Theater program | # of participants | Yes | Completed | 144 | 144 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16163 | Rasuwa | Thulogoun | 6 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Site survey | # of households | Yes | Completed | 35 | 35 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16164 | Rasuwa | Thulogoun | 6 | BC | BC | ARC | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Home Owner Training | # of households | Yes | Completed | 43 | 43 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16165 | Rasuwa | Thulogoun | 6 | BC | BC | ARC | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Design of drawing | # of households | Yes | Completed | 8 | 8 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16166 | Rasuwa | Thulogoun | 6 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Monitoring of On going construction | # of households | Yes | Completed | 10 | 10 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16167 | Rasuwa | Thulogoun | 6 | BC | BC | ARC | Technical Assistance | Helpdesk/technical support center | Helpdesk/technical support center | TSC will provide service to the beneficiaries for land assessment, design for construction and technical assessment throughout the construction process. Build Change has established TSC in addition to the agreement with NRA | # of households supported | Yes | Completed | 1 | 1 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16168 | Rasuwa | Thulogoun | 7 | BC | BC | ARC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre | Build Back Safer Theater program | # of participants | Yes | Completed | 21 | 21 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16169 | Rasuwa | Thulogoun | 7 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Site survey | # of households | Yes | Completed | 21 | 21 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16170 | Rasuwa | Thulogoun | 7 | BC | BC | ARC | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Home Owner Training | # of households | Yes | Completed | 16 | 16 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16171 | Rasuwa | Thulogoun | 7 | BC | BC | ARC | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Design of drawing | # of households | Yes | Completed | 11 | 11 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16172 | Rasuwa | Thulogoun | 7 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Monitoring of On going construction | # of households | Yes | Completed | 12 | 12 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16173 | Rasuwa | Thulogoun | 8 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Site survey | # of households | Yes | Completed | 41 | 41 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16174 | Rasuwa | Thulogoun | 8 | BC | BC | ARC | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Home Owner Training | # of households | Yes | Completed | 39 | 39 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16175 | Rasuwa | Thulogoun | 8 | BC | BC | ARC | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Design of drawing | # of households | Yes | Completed | 16 | 16 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16176 | Rasuwa | Thulogoun | 8 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Monitoring of On going construction | # of households | Yes | Completed | 24 | 24 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 2
16177 | Rasuwa | Thulogoun | 9 | BC | BC | ARC | Technical Assistance | Interactive mobile van/theatre | Interactive mobile van/theatre | Build Back Safer Theater program | # of participants | Yes | Completed | 95 | 95 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16178 | Rasuwa | Thulogoun | 9 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Site survey | # of households | Yes | Completed | 69 | 69 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16179 | Rasuwa | Thulogoun | 9 | BC | BC | ARC | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Home Owner Training | # of households | Yes | Completed | 62 | 62 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16180 | Rasuwa | Thulogoun | 9 | BC | BC | ARC | Technical Assistance | Household reconstruction orientation | 4-5 sessions | Design of drawing | # of households | Yes | Completed | 30 | 30 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16181 | Rasuwa | Thulogoun | 9 | BC | BC | ARC | Technical Assistance | Door-to-door technical assistance | Continuous | Monitoring of On going construction | # of households | Yes | Completed | 45 | 45 | 2016-08-01 | 2019-08-30 |  | Uttargaya | 3
16182 | Rasuwa | Dhunche | 1 | CTEVT | CTEVT | CTEVT | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Gosaikunda | 6
16183 | Rasuwa | Jibjibe(Nilkantha) | 1 | CTEVT | CTEVT | CTEVT | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Kalika | 3
16184 | Rasuwa | Jibjibe(Nilkantha) | 4 | CTEVT | CTEVT | CTEVT | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Kalika | 3
16185 | Rasuwa | Jibjibe(Nilkantha) | 5 | CTEVT | CTEVT | CTEVT | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 |  |  |  | Kalika | 2
16186 | Rasuwa | Jibjibe(Nilkantha) | 6 | CTEVT | CTEVT | CTEVT | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 |  |  |  | Kalika | 2
16187 | Rasuwa | Laharepouwa | 3 | CTEVT | CTEVT | CTEVT | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 |  |  |  | Uttargaya | 5
16188 | Rasuwa | Laharepouwa | 6 | CTEVT | CTEVT | CTEVT | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 |  |  |  | Uttargaya | 4
16189 | Rasuwa | Bhorle | 2 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session | Minimum 75 people in group | # of participants | Yes | Completed | 126 | 126 | 2016-12-12 | 2016-12-18 |  | Naukunda | 6
16190 | Rasuwa | Bhorle | 3 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 153 | 153 | 2016-12-26 | 2017-01-24 |  | Naukunda | 6
16191 | Rasuwa | Bhorle | 4 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 52 | 52 | 2016-12-30 | 2016-12-30 |  | Naukunda | 5
16192 | Rasuwa | Bhorle | 5 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 51 | 51 | 2016-12-25 | 2016-12-25 |  | Naukunda | 5
16193 | Rasuwa | Bhorle | 7 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 32 | 32 | 2016-11-25 | 2016-11-25 |  | Naukunda | 5
16194 | Rasuwa | Bhorle | 9 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 68 | 68 | 2016-11-24 | 2016-11-24 |  | Kalika | 4
16195 | Rasuwa | Jibjibe(Nilkantha) | 1 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session | Minimum 75 people in group | # of participants | Yes | Completed | 68 | 68 | 2016-12-19 | 2016-12-24 |  | Kalika | 3
16196 | Rasuwa | Jibjibe(Nilkantha) | 2 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 154 | 154 | 2016-12-20 | 2016-12-24 |  | Kalika | 3
16197 | Rasuwa | Jibjibe(Nilkantha) | 3 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 48 | 48 | 2016-12-22 | 2016-12-31 |  | Kalika | 3
16198 | Rasuwa | Jibjibe(Nilkantha) | 4 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 48 | 48 | 2017-01-06 | 2017-01-06 |  | Kalika | 3
16199 | Rasuwa | Jibjibe(Nilkantha) | 5 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 92 | 92 | 2017-01-04 | 2017-01-22 |  | Kalika | 2
16200 | Rasuwa | Jibjibe(Nilkantha) | 6 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 43 | 43 | 2016-11-25 | 2017-01-04 |  | Kalika | 2
16201 | Rasuwa | Jibjibe(Nilkantha) | 7 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 64 | 64 | 2016-11-16 | 2016-12-20 |  | Kalika | 2
16202 | Rasuwa | Thulogoun | 1 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session | Minimum 75 people in group | # of participants | Yes | Completed | 39 | 39 | 2016-12-07 | 2016-12-07 |  | Uttargaya | 3
16203 | Rasuwa | Thulogoun | 6 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 34 | 34 | 2016-12-08 | 2016-12-08 |  | Uttargaya | 3
16204 | Rasuwa | Thulogoun | 9 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 49 | 49 | 2016-12-08 | 2016-12-08 |  | Uttargaya | 3
16205 | Rasuwa | Yarsa | 7 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session | Minimum 75 people in group | # of participants | Yes | Completed | 125 | 125 | 2017-01-10 | 2017-01-10 |  | Naukunda | 1
16206 | Rasuwa | Yarsa | 8 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 118 | 118 | 2017-01-25 | 2017-01-25 |  | Naukunda | 1
16207 | Rasuwa | Yarsa | 9 | DEPROSC | DEPROSC | GON - PAF | Technical Assistance | Community reconstruction orientation | 1 session |  | # of participants | Yes | Completed | 79 | 79 | 2017-01-24 | 2017-01-24 |  | Naukunda | 6
16208 | Rasuwa | Dandagoun | 1 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-25 | 2016-05-19 | Furniture making Training | Uttargaya | 2
16209 | Rasuwa | Dandagoun | 1 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-11 | 2016-02-04 | s | Uttargaya | 2
16210 | Rasuwa | Dandagoun | 1 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 4 | 4 | 2016-01-17 | 2016-02-10 |  | Uttargaya | 2
16211 | Rasuwa | Dandagoun | 1 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-11-28 | 6-Dce-16 |  | Uttargaya | 2
16212 | Rasuwa | Dandagoun | 2 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 3 | 3 | 2016-04-25 | 2016-05-19 | Furniture making Training | Uttargaya | 2
16213 | Rasuwa | Dandagoun | 2 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-11 | 2016-02-04 |  | Uttargaya | 2
16214 | Rasuwa | Dandagoun | 2 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-17 | 2016-02-10 |  | Uttargaya | 2
16215 | Rasuwa | Dandagoun | 2 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-11-29 | 6-Dce-16 |  | Uttargaya | 2
16216 | Rasuwa | Dandagoun | 3 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-25 | 2016-05-19 | Furniture making Training | Uttargaya | 2
16217 | Rasuwa | Dandagoun | 3 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-11 | 2016-02-04 |  | Uttargaya | 2
16218 | Rasuwa | Dandagoun | 3 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-17 | 2016-02-10 |  | Uttargaya | 2
16219 | Rasuwa | Dandagoun | 3 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-11-30 | 6-Dce-16 |  | Uttargaya | 2
16220 | Rasuwa | Dandagoun | 4 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-25 | 2016-05-19 | Furniture making Training | Uttargaya | 2
16221 | Rasuwa | Dandagoun | 4 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-11 | 2016-02-04 |  | Uttargaya | 2
16222 | Rasuwa | Dandagoun | 4 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-17 | 2016-02-10 |  | Uttargaya | 2
16223 | Rasuwa | Dandagoun | 4 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-01 | 6-Dce-16 |  | Uttargaya | 2
16224 | Rasuwa | Dandagoun | 5 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 4 | 4 | 2016-04-25 | 2016-05-19 | Furniture making Training | Uttargaya | 2
16225 | Rasuwa | Dandagoun | 5 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-11 | 2016-02-04 |  | Uttargaya | 2
16226 | Rasuwa | Dandagoun | 5 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-17 | 2016-02-10 |  | Uttargaya | 2
16227 | Rasuwa | Dandagoun | 5 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2015-12-02 | 6-Dce-16 |  | Uttargaya | 2
16228 | Rasuwa | Dandagoun | 6 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 1 | 1 | 2016-04-25 | 2016-05-19 | Furniture making Training | Uttargaya | 2
16229 | Rasuwa | Dandagoun | 6 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 4 | 4 | 2016-01-11 | 2016-02-04 |  | Uttargaya | 2
16230 | Rasuwa | Dandagoun | 6 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-17 | 2016-02-10 |  | Uttargaya | 2
16231 | Rasuwa | Dandagoun | 6 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2015-12-03 | 6-Dce-16 |  | Uttargaya | 2
16232 | Rasuwa | Dandagoun | 7 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-11 | 2016-02-04 |  | Uttargaya | 1
16233 | Rasuwa | Dandagoun | 7 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-17 | 2016-02-10 |  | Uttargaya | 1
16234 | Rasuwa | Dandagoun | 7 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-12-04 | 6-Dce-16 |  | Uttargaya | 1
16235 | Rasuwa | Dandagoun | 8 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-05 | 6-Dce-16 |  | Uttargaya | 1
16236 | Rasuwa | Dandagoun | 9 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-12-06 | 6-Dce-16 |  | Uttargaya | 1
16237 | Rasuwa | Syafru | 1 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-17 | 2016-02-10 |  | Gosaikunda | 5
16238 | Rasuwa | Syafru | 1 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-11-27 | 6-Dce-15 |  | Gosaikunda | 5
16239 | Rasuwa | Syafru | 2 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-11 | 2016-02-04 |  | Gosaikunda | 5
16240 | Rasuwa | Syafru | 2 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-17 | 2016-02-10 |  | Gosaikunda | 5
16241 | Rasuwa | Syafru | 2 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2015-11-27 | 6-Dce-15 |  | Gosaikunda | 5
16242 | Rasuwa | Syafru | 3 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-11 | 2016-02-04 |  | Gosaikunda | 5
16243 | Rasuwa | Syafru | 3 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-17 | 2016-02-10 |  | Gosaikunda | 5
16244 | Rasuwa | Syafru | 3 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2015-11-27 | 6-Dce-15 |  | Gosaikunda | 5
16245 | Rasuwa | Syafru | 4 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 4 | 4 | 2016-01-11 | 2016-02-04 |  | Gosaikunda | 5
16246 | Rasuwa | Syafru | 4 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 5 | 5 | 2016-01-17 | 2016-02-10 |  | Gosaikunda | 5
16247 | Rasuwa | Syafru | 4 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 6 | 6 | 2015-11-27 | 6-Dce-15 |  | Gosaikunda | 5
16248 | Rasuwa | Syafru | 5 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 8 | 8 | 2016-01-11 | 2016-02-04 |  | Gosaikunda | 5
16249 | Rasuwa | Syafru | 5 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 2 | 2 | 2016-01-17 | 2016-02-10 |  | Gosaikunda | 5
16250 | Rasuwa | Syafru | 5 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 15 | 15 | 2015-11-27 | 6-Dce-15 |  | Gosaikunda | 5
16251 | Rasuwa | Syafru | 6 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 7 | 7 | 2016-01-11 | 2016-02-04 |  | Gosaikunda | 5
16252 | Rasuwa | Syafru | 6 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 11 | 11 | 2016-01-17 | 2016-02-10 |  | Gosaikunda | 5
16253 | Rasuwa | Syafru | 6 | GIZ | GIZ | GIZ | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2015-11-27 | 6-Dce-15 |  | Gosaikunda | 5
16254 | Rasuwa | Syafru | 7 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-11 | 2016-02-04 |  | Gosaikunda | 5
16255 | Rasuwa | Syafru | 7 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 4 | 4 | 2016-01-17 | 2016-02-10 |  | Gosaikunda | 5
16256 | Rasuwa | Syafru | 9 | GIZ | GIZ | GIZ | Training | Short training | Carpenter |  | # of trainees | Yes | Completed | 6 | 6 | 2016-01-11 | 2016-02-04 |  | Gosaikunda | 5
16257 | Rasuwa | Syafru | 9 | GIZ | GIZ | GIZ | Training | Short training | Electrician |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-17 | 2016-02-10 |  | Gosaikunda | 5
16258 | Rasuwa | Syafru | All | GIZ | GIZ | GIZ | Training | Short training | Masons (other curriculums, specify in Activity Detail) | Iron wilding +Furniture making |  | Yes | Completed | 20 | 20 | 2016-04-09 | 2016-05-09 |  | Gosaikunda | 5
16259 | Rasuwa | Dhunche | 1 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 3 | 3 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16260 | Rasuwa | Dhunche | 1 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 49 | 49 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16261 | Rasuwa | Dhunche | 1 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 49 | 49 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16262 | Rasuwa | Dhunche | 1 | GOAL | UON | ECHO | Technical Assistance | Demonstration Construction | House | Demonstration Panal | # of constructions | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30 | Construct only two side wall with door and window | Gosaikunda | 6
16263 | Rasuwa | Dhunche | 1 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 49 | 49 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Gosaikunda | 6
16264 | Rasuwa | Dhunche | 1 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-24 | 2016-02-28 |  | Gosaikunda | 6
16265 | Rasuwa | Dhunche | 2 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 4 | 4 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16266 | Rasuwa | Dhunche | 2 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 34 | 34 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16267 | Rasuwa | Dhunche | 2 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 34 | 34 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16268 | Rasuwa | Dhunche | 2 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 34 | 34 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Gosaikunda | 6
16269 | Rasuwa | Dhunche | 2 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-02-24 | 2016-02-28 |  | Gosaikunda | 6
16270 | Rasuwa | Dhunche | 3 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 12 | 12 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16271 | Rasuwa | Dhunche | 3 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 37 | 37 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16272 | Rasuwa | Dhunche | 3 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 37 | 37 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16273 | Rasuwa | Dhunche | 3 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 37 | 37 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Gosaikunda | 6
16274 | Rasuwa | Dhunche | 3 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 9 | 9 | 2016-02-24 | 2016-02-28 |  | Gosaikunda | 6
16275 | Rasuwa | Dhunche | 3 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-22 | 2016-03-28 |  | Gosaikunda | 6
16276 | Rasuwa | Dhunche | 4 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 10 | 10 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16277 | Rasuwa | Dhunche | 4 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 40 | 40 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16278 | Rasuwa | Dhunche | 4 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 40 | 40 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16279 | Rasuwa | Dhunche | 4 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 40 | 40 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Gosaikunda | 6
16280 | Rasuwa | Dhunche | 4 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-02-24 | 2016-02-28 |  | Gosaikunda | 6
16281 | Rasuwa | Dhunche | 4 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-22 | 2016-03-28 |  | Gosaikunda | 6
16282 | Rasuwa | Dhunche | 5 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 51 | 51 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16283 | Rasuwa | Dhunche | 5 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 51 | 51 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16284 | Rasuwa | Dhunche | 5 | GOAL | UON | ECHO | Technical Assistance | Demonstration Construction | House | Demonstration Panal | # of constructions | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30 | Construct only two side wall with door and window | Gosaikunda | 6
16285 | Rasuwa | Dhunche | 5 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 51 | 51 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Gosaikunda | 6
16286 | Rasuwa | Dhunche | 6 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 2 | 2 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16287 | Rasuwa | Dhunche | 6 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 34 | 34 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16288 | Rasuwa | Dhunche | 6 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 34 | 34 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16289 | Rasuwa | Dhunche | 6 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 34 | 34 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Gosaikunda | 6
16290 | Rasuwa | Dhunche | 6 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-22 | 2016-03-28 |  | Gosaikunda | 6
16291 | Rasuwa | Dhunche | 7 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16292 | Rasuwa | Dhunche | 7 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 39 | 39 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16293 | Rasuwa | Dhunche | 7 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 39 | 39 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16294 | Rasuwa | Dhunche | 7 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 39 | 39 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Gosaikunda | 6
16295 | Rasuwa | Dhunche | 7 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-22 | 2016-03-28 |  | Gosaikunda | 6
16296 | Rasuwa | Dhunche | 8 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 5 | 5 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16297 | Rasuwa | Dhunche | 8 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 62 | 62 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16298 | Rasuwa | Dhunche | 8 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 62 | 62 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16299 | Rasuwa | Dhunche | 8 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 62 | 62 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Gosaikunda | 6
16300 | Rasuwa | Dhunche | 8 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-03-22 | 2016-03-28 |  | Gosaikunda | 6
16301 | Rasuwa | Dhunche | 9 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16302 | Rasuwa | Dhunche | 9 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 50 | 50 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16303 | Rasuwa | Dhunche | 9 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 50 | 50 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 6
16304 | Rasuwa | Dhunche | 9 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 50 | 50 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Gosaikunda | 6
16305 | Rasuwa | Dhunche | 9 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-03-22 | 2016-03-28 |  | Gosaikunda | 6
16306 | Rasuwa | Gatlang | 1 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 3 | 3 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16307 | Rasuwa | Gatlang | 1 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 69 | 69 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16308 | Rasuwa | Gatlang | 1 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 69 | 69 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16309 | Rasuwa | Gatlang | 1 | GOAL | UON | ECHO | Technical Assistance | Demonstration Construction | House | Demonstration Panal | # of constructions | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30 | Construct only two side wall with door and window | Parbati Kunda | 3
16310 | Rasuwa | Gatlang | 1 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 69 | 69 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Parbati Kunda | 3
16311 | Rasuwa | Gatlang | 1 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-15 | 2016-01-19 |  | Parbati Kunda | 3
16312 | Rasuwa | Gatlang | 2 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 3 | 3 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16313 | Rasuwa | Gatlang | 2 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 48 | 48 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16314 | Rasuwa | Gatlang | 2 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 48 | 48 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16315 | Rasuwa | Gatlang | 2 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 48 | 48 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Parbati Kunda | 3
16316 | Rasuwa | Gatlang | 2 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-01-15 | 2016-01-19 |  | Parbati Kunda | 3
16317 | Rasuwa | Gatlang | 3 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 7 | 7 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16318 | Rasuwa | Gatlang | 3 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 33 | 33 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16319 | Rasuwa | Gatlang | 3 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 33 | 33 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16320 | Rasuwa | Gatlang | 3 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 33 | 33 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Parbati Kunda | 3
16321 | Rasuwa | Gatlang | 3 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-01-15 | 2016-01-19 |  | Parbati Kunda | 3
16322 | Rasuwa | Gatlang | 4 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16323 | Rasuwa | Gatlang | 4 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 36 | 36 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16324 | Rasuwa | Gatlang | 4 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 36 | 36 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16325 | Rasuwa | Gatlang | 4 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 36 | 36 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Parbati Kunda | 3
16326 | Rasuwa | Gatlang | 4 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-15 | 2016-01-19 |  | Parbati Kunda | 3
16327 | Rasuwa | Gatlang | 5 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 8 | 8 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16328 | Rasuwa | Gatlang | 5 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 57 | 57 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16329 | Rasuwa | Gatlang | 5 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 57 | 57 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16330 | Rasuwa | Gatlang | 5 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 57 | 57 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Parbati Kunda | 3
16331 | Rasuwa | Gatlang | 5 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 8 | 8 | 2016-01-15 | 2016-01-19 |  | Parbati Kunda | 3
16332 | Rasuwa | Gatlang | 6 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 4 | 4 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16333 | Rasuwa | Gatlang | 6 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 93 | 93 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16334 | Rasuwa | Gatlang | 6 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 93 | 93 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16335 | Rasuwa | Gatlang | 6 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 93 | 93 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Parbati Kunda | 3
16336 | Rasuwa | Gatlang | 6 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-01-15 | 2016-01-19 |  | Parbati Kunda | 3
16337 | Rasuwa | Gatlang | 7 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 3 | 3 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 2
16338 | Rasuwa | Gatlang | 7 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 58 | 58 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 2
16339 | Rasuwa | Gatlang | 7 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 58 | 58 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 2
16340 | Rasuwa | Gatlang | 7 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 58 | 58 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Parbati Kunda | 2
16341 | Rasuwa | Gatlang | 7 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-03-22 | 2016-03-28 |  | Parbati Kunda | 2
16342 | Rasuwa | Gatlang | 8 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 2 | 2 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 2
16343 | Rasuwa | Gatlang | 8 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 61 | 61 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 2
16344 | Rasuwa | Gatlang | 8 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 61 | 61 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 2
16345 | Rasuwa | Gatlang | 8 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 61 | 61 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Parbati Kunda | 2
16346 | Rasuwa | Gatlang | 8 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 2 | 2 | 2016-03-22 | 2016-03-28 |  | Parbati Kunda | 2
16347 | Rasuwa | Gatlang | 9 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16348 | Rasuwa | Gatlang | 9 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 25 | 25 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16349 | Rasuwa | Gatlang | 9 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 25 | 25 | 2015-08-01 | 2016-04-30 |  | Parbati Kunda | 3
16350 | Rasuwa | Gatlang | 9 | GOAL | UON | ECHO | Technical Assistance | Demonstration Construction | House | Demonstration Panal | # of constructions | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30 | Construct only two side wall with door and window | Parbati Kunda | 3
16351 | Rasuwa | Gatlang | 9 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 25 | 25 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Parbati Kunda | 3
16352 | Rasuwa | Gatlang | 9 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 1 | 1 | 2016-01-15 | 2016-01-19 |  | Parbati Kunda | 3
16353 | Rasuwa | Haku | 2 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 5 | 5 | 2016-04-01 | 2016-06-05 |  | Parbati Kunda | 2
16354 | Rasuwa | Haku | 2 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 5 | 5 | 2016-06-02 | 2016-06-08 |  | Parbati Kunda | 2
16355 | Rasuwa | Haku | 4 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 11 | 11 | 2016-04-01 | 2016-06-05 |  | Parbati Kunda | 1
16356 | Rasuwa | Haku | 4 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 11 | 11 | 2016-06-02 | 2016-06-08 |  | Parbati Kunda | 1
16357 | Rasuwa | Haku | 5 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 7 | 7 | 2016-04-01 | 2016-06-05 |  | Parbati Kunda | 1
16358 | Rasuwa | Haku | 5 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 7 | 7 | 2016-06-02 | 2016-06-08 |  | Parbati Kunda | 1
16359 | Rasuwa | Haku | 6 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 3 | 3 | 2016-04-01 | 2016-06-05 |  | Parbati Kunda | 1
16360 | Rasuwa | Haku | 6 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 3 | 3 | 2016-06-02 | 2016-06-08 |  | Parbati Kunda | 1
16361 | Rasuwa | Haku | 7 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Builder toolkits | Each set for each mason | # of kits | Yes | Completed | 4 | 4 | 2016-04-01 | 2016-06-05 |  | Parbati Kunda | 1
16362 | Rasuwa | Haku | 7 | GOAL | UON | ECHO | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 4 | 4 | 2016-06-02 | 2016-06-08 |  | Parbati Kunda | 1
16363 | Rasuwa | Syafru | 1 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 30 | 30 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 5
16364 | Rasuwa | Syafru | 1 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 30 | 30 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 5
16365 | Rasuwa | Syafru | 1 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 30 | 30 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Gosaikunda | 5
16366 | Rasuwa | Syafru | 3 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 56 | 56 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 5
16367 | Rasuwa | Syafru | 3 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 56 | 56 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 5
16368 | Rasuwa | Syafru | 3 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 56 | 56 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Gosaikunda | 5
16369 | Rasuwa | Syafru | 4 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 50 | 50 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 5
16370 | Rasuwa | Syafru | 4 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 50 | 50 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 5
16371 | Rasuwa | Syafru | 4 | GOAL | UON | ECHO | Technical Assistance | Demonstration Construction | House | Demonstration Panal | # of constructions | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30 | Construct only two side wall with door and window | Gosaikunda | 5
16372 | Rasuwa | Syafru | 4 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 50 | 50 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Gosaikunda | 5
16373 | Rasuwa | Syafru | 5 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 35 | 35 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 5
16374 | Rasuwa | Syafru | 5 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 35 | 35 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 5
16375 | Rasuwa | Syafru | 5 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 35 | 35 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Gosaikunda | 5
16376 | Rasuwa | Syafru | 6 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 15 | 15 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 5
16377 | Rasuwa | Syafru | 6 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 15 | 15 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 5
16378 | Rasuwa | Syafru | 6 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 15 | 15 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Gosaikunda | 5
16379 | Rasuwa | Syafru | 7 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 22 | 22 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 5
16380 | Rasuwa | Syafru | 7 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 22 | 22 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 5
16381 | Rasuwa | Syafru | 7 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 22 | 22 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Gosaikunda | 5
16382 | Rasuwa | Syafru | 8 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 8 | 8 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 5
16383 | Rasuwa | Syafru | 8 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 8 | 8 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 5
16384 | Rasuwa | Syafru | 8 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 8 | 8 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Gosaikunda | 5
16385 | Rasuwa | Syafru | 9 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Construction | Distribution of shelter material timber and Bamboo | # of households | Yes | Completed | 108 | 108 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 5
16386 | Rasuwa | Syafru | 9 | GOAL | UON | ECHO | Financial/Material/Labour Assistance | In kind/material support in housing | Household toolkits | one tool kit set for five HH | # of households | Yes | Completed | 108 | 108 | 2015-08-01 | 2016-04-30 |  | Gosaikunda | 5
16387 | Rasuwa | Syafru | 9 | GOAL | UON | ECHO | Technical Assistance | Demonstration Construction | House | Demonstration Panal | # of constructions | Yes | Completed | 1 | 1 | 2015-08-01 | 2016-04-30 | Construct only two side wall with door and window | Gosaikunda | 5
16388 | Rasuwa | Syafru | 9 | GOAL | UON | ECHO | Technical Assistance | Door-to-door technical assistance | Continuous |  | # of households | Yes | Completed | 108 | 108 | 2015-08-01 | 2016-04-30 | Activities was carried out on Transitional period | Gosaikunda | 5
16389 | Rasuwa | Bridhim | 1 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 3
16390 | Rasuwa | Bridhim | 2 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 3
16391 | Rasuwa | Bridhim | 3 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 3
16392 | Rasuwa | Bridhim | 4 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 3
16393 | Rasuwa | Bridhim | 5 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 3
16394 | Rasuwa | Bridhim | 6 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 3
16395 | Rasuwa | Bridhim | 7 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 3
16396 | Rasuwa | Dandagoun | 1 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 2
16397 | Rasuwa | Dandagoun | 2 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 2
16398 | Rasuwa | Dandagoun | 3 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 2
16399 | Rasuwa | Dandagoun | 4 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 2
16400 | Rasuwa | Dandagoun | 5 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 2
16401 | Rasuwa | Dandagoun | 6 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 2
16402 | Rasuwa | Dandagoun | 7 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 1
16403 | Rasuwa | Dandagoun | 8 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 1
16404 | Rasuwa | Dandagoun | 9 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 1
16405 | Rasuwa | Dhunche | 1 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 6
16406 | Rasuwa | Dhunche | 2 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 6
16407 | Rasuwa | Dhunche | 3 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 6
16408 | Rasuwa | Dhunche | 4 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 6
16409 | Rasuwa | Dhunche | 5 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 6
16410 | Rasuwa | Dhunche | 6 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 6
16411 | Rasuwa | Dhunche | 7 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 6
16412 | Rasuwa | Dhunche | 8 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 6
16413 | Rasuwa | Dhunche | 9 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 6
16414 | Rasuwa | Gatlang | 1 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Parbati Kunda | 3
16415 | Rasuwa | Gatlang | 2 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Parbati Kunda | 3
16416 | Rasuwa | Gatlang | 3 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Parbati Kunda | 3
16417 | Rasuwa | Gatlang | 4 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Parbati Kunda | 3
16418 | Rasuwa | Gatlang | 5 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Parbati Kunda | 3
16419 | Rasuwa | Gatlang | 6 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Parbati Kunda | 3
16420 | Rasuwa | Gatlang | 9 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Parbati Kunda | 3
16421 | Rasuwa | Goljung | 5 | GoN | GoN | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 35 | 35 | 2017-07-15 | 2017-07-22 |  | Parbati Kunda | 4
16422 | Rasuwa | Haku | 1 | GoN | GoN | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 22 | 22 | 2017-07-15 | 2017-07-22 |  | Parbati Kunda | 2
16423 | Rasuwa | Haku | 2 | GoN | GoN | GON | Training | Short training | Masons (7 days DUDBC, rural or urban) |  | # of trainees | Yes | Completed | 12 | 12 | 2017-07-15 | 2017-07-22 |  | Parbati Kunda | 2
16424 | Rasuwa | Langtang | 1 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 4
16425 | Rasuwa | Langtang | 2 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 4
16426 | Rasuwa | Langtang | 3 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 4
16427 | Rasuwa | Langtang | 4 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 4
16428 | Rasuwa | Langtang | 5 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 4
16429 | Rasuwa | Langtang | 6 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 4
16430 | Rasuwa | Langtang | 7 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 4
16431 | Rasuwa | Langtang | 8 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 4
16432 | Rasuwa | Langtang | 9 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 4
16433 | Rasuwa | Ramche | 1 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Kalika | 1
16434 | Rasuwa | Ramche | 2 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Kalika | 1
16435 | Rasuwa | Ramche | 3 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Kalika | 1
16436 | Rasuwa | Ramche | 4 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Kalika | 1
16437 | Rasuwa | Ramche | 5 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Kalika | 1
16438 | Rasuwa | Ramche | 6 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Kalika | 1
16439 | Rasuwa | Ramche | 7 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Kalika | 1
16440 | Rasuwa | Ramche | 8 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Kalika | 1
16441 | Rasuwa | Ramche | 9 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Kalika | 1
16442 | Rasuwa | Syafru | 1 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 5
16443 | Rasuwa | Syafru | 2 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 5
16444 | Rasuwa | Syafru | 3 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 5
16445 | Rasuwa | Syafru | 4 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 5
16446 | Rasuwa | Syafru | 5 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 5
16447 | Rasuwa | Syafru | 6 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 5
16448 | Rasuwa | Syafru | 7 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 5
16449 | Rasuwa | Syafru | 8 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 5
16450 | Rasuwa | Syafru | 9 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Gosaikunda | 5
16451 | Rasuwa | Thulogoun | 1 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 3
16452 | Rasuwa | Thulogoun | 2 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 3
16453 | Rasuwa | Thulogoun | 3 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 3
16454 | Rasuwa | Thulogoun | 4 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 3
16455 | Rasuwa | Thulogoun | 5 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 3
16456 | Rasuwa | Thulogoun | 6 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 3
16457 | Rasuwa | Thulogoun | 7 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 3
16458 | Rasuwa | Thulogoun | 8 | GON | GON | GON | Technical Assistance | Reconstruction Coordination Committee | Reconstruction Coordination Committee | Community Level Reconstruction Coordination Committee(CLRCC) | # of committees | Yes | Completed | 1 | 1 | 2016-03-15 | 2016-10-20 |  | Uttargaya | 2