| Meeting Purpose: | General Palika -level Coordination Meeting |  |  |
| --- | --- | --- | --- |
| Meeting Date: | 9 July 2019 |  |  |
| Meeting Time: | 2:00 PM |  |  |
| Meeting Location: | Paiyun Gaunpalika Office, Parbat district |  |  |
| Meeting Facilitator: | Rijan Gajurel, HRRP District Coordinator, Lamjung Cluster |  |  |
| Minutes Taken By: | Ambika Amatya, HRRP District Coordinator, Lalitpur Cluster |  |  |
| Summary of participants: | Total: 9 | Female: 2 | Male: 7 |

Discussion: (Items/Knowledge Shared)

Agendas: - Welcome and sharing of objective - Reconstruction updates and related challenges at the Palika level - Discussion on reconstruction efforts - AOB Agenda 1 - Welcome and sharing of objective The general palika level coordination meeting was conducted at Palika office of Paiyun Gaupalika, Parbat district. The coordination meeting was chaired by Mr. Khagendra Prasad Tiwari, Palika Chief, in presence of Ms. Jasmati Gurung, Deputy Palika Chief, District Support Engineer, DLPIU Building Parbat, reconstruction engineer and HRRP Nepal. The main agenda of the meeting was to discuss on the reconstruction updates, progress, challenges and issues at Palika level. Agenda 2 - Reconstruction updates and related challenges at the Palika level # Total Beneficiaries; # 658. # PA enrolled; # 634. # 1st tranche; # 634. # 2nd tranche; # 290. # 3rd tranche; # 98. Ward level reconstruction update: - Majority of beneficiaries have rebuild the houses in their adjoining land without demolishing their quake damaged houses to access government grants. They are still using quake damaged houses for purpose of storing grains and other household stuffs etc. - The newly rebuilt 2 roomed houses by beneficiaries have not been enough to meet their daily requirements of large family members that lead to reuse of quake damaged houses without demolishing. - Huge gap were seen in access of 2nd and 3rd tranche by beneficiaries as majority of them have taken 1st tranche. - Engineers have received pressures from beneficiaries to approve the 2nd and 3rd tranche application files, especially in case of non-complaint houses. - Majority of beneficiaries have rebuild the shelter soon after earthquake and their houses havenot received 2nd tranche yet with due conditions of failing to meet minimum requirements that makes houses safer and resilient. Corner stitches, sil and lintel bands were found to be commonly missed during inspection of those houses by technical personnel. - Beneficiaries assures to correct their houses after recommendations from engineers but later they fail to apply correction measures as challenges lies in recovering the expenses incurred already in rebuilding the house immediately after earthquake. - There are significant numbers of houses in retrofitting list (114), however beneficiaries have yet not applied standard retrofitting measures. Majority of them have done minor repair and maintenance works on quake damaged parts. This shows confusions on agency certified retrofitting process and repairment works. - There is lack of well trained local masons as local trained masons are found to fled from Gaunpalika area for other opportunities out of Parbat district and to foreign employment too. - Till date, construction completion certificate have not been provided to none of the houses that have received upto 3rd tranche.

Miscellaneous Items / AOB:

- Team member of HRRP Nepal reminded Palika Chief and Deputy Palika Chief about the MOU agreement conducted between Palikas and GON/NRA during district-level reconstruction review meeting. - Team member of HRRP Nepal highlighted that low cost and modest shelter can be reconstructed by keeping wooden bands and using salvaged materials.

Decisions Made: (What, Why, Impacts)

- Palika office will soon prepare list of beneficiaries who have reconstructed house before the endorsement of NRA’s guidelines and before placement of engineers.

| Next Steps/action points: | Person(s) Responsible | Due Date |
| --- | --- | --- |
| To inform and encourage beneficiaries to carry out rebuilding of houses. | Palika Office | On-going |
| To facilitate grant application file process of beneficiaries | Palika Office | On-going |
| To smoothly carry out resurvey and reverification of grievances | Palika Office | On-going |
| To prepare list of beneficiaries who have reconstructed houses soon after earthquake and before endorsement of NRA’s guidelines | Palika Office | As soon as possible |

| S.N. | Attendees | Gender | Organization | Designation | Phone No. | Email |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Khagendra Prasad Tiwari | Male | Paiyun Gaupalika | Palika Chief |  | paiyungapa@gmail.com |
| 2 | Jasmati Gurung | Female | Paiyun Gaupalika | Deputy Palika Chief |  | paiyungapa@gmail.com |
| 3 | Bishnu Prasad Kafle | Male | Ward no.3, Paiyun Gaupalika | Ward Chief |  | paiyungapa@gmail.com |
| 4 | Jit Bahadur Rana | Male | Paiyun Gaupalika | Chief Administrative Officer | 9857620543 | paiyungapa@gmail.com |
| 5 | Bijendra Man Pradhan | Male | DLPIU Building Parbat | District Support Engineer |  |  |
| 6 | Sanjog Khanal | Male | Paiyun Gaupalika | Engineer | 9860246179 | khanalsanjog@gmail.com |
| 7 | Ambika Amatya | Female | HRRP Lalitpur Cluster | Cluster Coordinator | 9841356409 | Ambika.amatya@hrrpnepal.org |
| 8 | Rijan Gajurel | Male | HRRP Lamjung Cluster | Cluster Coordinator | 9843217112 | Rijan.gajurel@hrrpnepal.org |
| 9 | Biren Shah | Male | HRRP Lamjung Cluster | District Technical Coordinator | 9817396852 | Biren.shah@hrrpnepal.org |